## Sheet1
MREQ_Number | FFID | Date_and_Time_of_Request | Section | Order_Type | Item_Category | Item_Description | Quantity_Required | Unit | Unit_Price | Total_Cost | Category | Date_Required | Delivery_Location | Location_WBS | Activity_WBS | Current_Stage | Operational_Approval | Commercial_Approval | Buyer
MREQ-4915-001 | 4915 | 2018-08-10 09:55 | Section 3 | Material | Aggregate | NULL | 20 | Tonnes | 16 | 320 | Aggregate | 2018-08-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1104 - Footways and Paved Areas | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-4996-0010 | 4996 | 2018-08-13 15:33 | Section 3 | Material | Not on List | NULL | 20 | no | NULL | 0 | NULL | 2018-08-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Rigidrain P/E 150Mm Dia Incl Coup/Sealia | 36 | no | 10.5 | 378 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 30 | Each | 17.45 | 523.5 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21737-001025 | 21737 | 2019-08-02 14:58 | Core | Material | Not on List | Not on List | 1 | No. | 20000 | 20000 | Office Supplies | 2019-08-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21712-001025 | 21712 | 2019-08-02 08:01 | Section 4 | Material | Not on List | Not on List | 4 | rolls | 258.05 | 1032.2 | Builders Merchants (General) | 2019-08-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21741-001025 | 21741 | 2019-08-02 15:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-08-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21748-001025 | 21748 | 2019-08-02 15:45 | Core | Material | Not on List | Not on List | 1 | ea | 8750 | 8750 | Training | 2019-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21748-001025 | 21748 | 2019-08-02 15:45 | Core | Material | Not on List | Not on List | 1 | ea | 473.4 | 473 | Training | 2019-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 20 | Each | 10.04 | 200.8 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21755-001025 | 21755 | 2019-08-02 16:39 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 29 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-08-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21719-001025 | 21719 | 2019-08-02 10:01 | Section 5 | Material | Not on List | NULL | 1 | SM | 1779.84 | 1779.84 | Builders Merchants (General) | NULL | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 12 | Each | 24.44 | 293.28 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 10 | Each | 35.52 | 355.2 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21746-001025 | 21746 | 2019-08-02 15:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 2 | Each | 55.41 | 110.82 | Concrete Drainage | 2019-08-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21782-001025 | 21782 | 2019-08-05 08:10 | Core | Material | Not on List | Not on List | 15 | Boxes | 75 | 1125 | Miscellaneous | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21782-001025 | 21782 | 2019-08-05 08:10 | Core | Material | Not on List | Not on List | 4 | Packs | 36 | 144 | Miscellaneous | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21782-001025 | 21782 | 2019-08-05 08:10 | Core | Material | Not on List | Not on List | 35 | Packs | 118.75 | 4156 | Miscellaneous | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21782-001025 | 21782 | 2019-08-05 08:10 | Core | Material | Not on List | Not on List | 2 | Sets | 395 | 790 | Miscellaneous | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21786-001025 | 21786 | 2019-08-05 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 105.91 | 106 | Miscellaneous | 2019-08-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20693-001025 | 20693 | 2019-07-12 14:14 | Core | Material | Not on List | Not on List | 1 | each | 115668.7 | 115668.7 | Miscellaneous | 2019-07-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 40 | Each | 42.1 | 1684 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21817-001025 | 21817 | 2019-08-06 07:00 | Section 4 | Material | Not on List | Not on List | 144 | NULL | 6.29 | 906 | Small Tools (Consumables) | 2019-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-20236-001025 | 20236 | 2019-07-04 11:32 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21825-001025 | 21825 | 2019-08-06 08:42 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-09-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-21827-001025 | 21827 | 2019-08-06 08:24 | Core | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21827-001025 | 21827 | 2019-08-06 08:24 | Core | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21790-001025 | 21790 | 2019-08-05 13:32 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 26 | Each | 29.25 | 760.5 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21798-001025 | 21798 | 2019-08-05 15:02 | Core | Material | NULL | NULL | 1 | Each | 4116 | 4116 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21839-001025 | 21839 | 2019-08-06 11:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | each | NULL | 0 | PPE | 2019-09-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-21842-001025 | 21842 | 2019-08-06 11:46 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5564-00390 | 5564 | 2018-08-23 11:30 | Section 4 | Material | Not on List | Not on List | 75 | bags | 11.43 | 857.25 | Miscellaneous | 2018-10-22 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21846-001025 | 21846 | 2019-08-06 12:09 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21852-001025 | 21852 | 2019-08-06 12:24 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21339-001025 | 21339 | 2019-07-25 12:36 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 10 | Each | 33.5 | 335 | Builders Merchants (General) | 2019-08-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21339-001025 | 21339 | 2019-07-25 12:36 | Section 5 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 2.97 | 118.8 | Builders Merchants (General) | 2019-08-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21774-001025 | 21774 | 2019-08-05 07:41 | Section 2 | Material | Kerbs | Not on List | 140 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-07 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21774-001025 | 21774 | 2019-08-05 07:41 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 5 | Each | 11.94 | 59.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-07 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21774-001025 | 21774 | 2019-08-05 07:41 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 5 | Each | 11.94 | 59.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-07 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 225Mm Ridgidrain Dbl Skt Coupler | 40 | Each | 3.38 | 135.2 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21877-001025 | 21877 | 2019-08-06 15:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-21878-001025 | 21878 | 2019-08-06 16:24 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | NULL | 0 | PPE | 2019-08-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21860-001025 | 21860 | 2019-08-06 13:27 | Section 3 | Material | Aggregate | Type 1 | 7500 | Tonnes | 21.65 | 162375 | Aggregate | 2019-08-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21334-001025 | 21334 | 2019-07-25 11:50 | Section 3 | Material | Not on List | Not on List | 55 | m | 10.9 | 599.5 | Miscellaneous | 2019-07-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21334-001025 | 21334 | 2019-07-25 11:50 | Section 3 | Material | Not on List | Not on List | 95 | No. | 2.16 | 205.2 | Fixings and Fasteners | 2019-07-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 225Mm Ridgidrain Seal | 100 | Each | 1.86 | 186 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21929-001025 | 21929 | 2019-08-07 09:23 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-08-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21823-001025 | 21823 | 2019-08-06 07:34 | Section 5 | Material | Not on List | Not on List | 1 | SM | 2471.04 | 2471.04 | Miscellaneous | 2019-08-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21931-001025 | 21931 | 2019-08-07 10:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21840-001025 | 21840 | 2019-08-06 11:33 | Section 4 | Material | Not on List | Not on List | 144 | Pack Water | 6.29 | 905.76 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21654-001025 | 21654 | 2019-08-01 07:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | NULL | 6.29 | 905.76 | Small Tools (Consumables) | 2019-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21653-001025 | 21653 | 2019-08-01 07:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 905.76 | 905.76 | Small Tools (Consumables) | 2019-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21768-001025 | 21768 | 2019-08-05 07:31 | Section 4 | Material | Not on List | Not on List | 1 | Each | 200.28 | 200.28 | Miscellaneous | 2019-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21670-001025 | 21670 | 2019-08-01 10:21 | Section 4 | Material | Waste Management | Not on List | 1 | NULL | 1199.88 | 1199.88 | Waste (General) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 605 - Disposal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5564-00390 | 5564 | 2018-08-23 11:30 | Section 4 | Material | NULL | NULL | 1 | Each | 1200 | 1200 | Miscellaneous | 2018-10-22 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Not on List | 28 | No | 39.7 | 1111.6 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5570-00392 | 5570 | 2018-08-23 12:15 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.94 | 94 | Concrete Accessories | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21644-001025 | 21644 | 2019-07-31 17:06 | Section 2 | Material | Ducting | Not on List | 6 | length | NULL | 0 | Electrical | 2019-08-06 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21644-001025 | 21644 | 2019-07-31 17:06 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 3 | roll | NULL | 0 | Small Tools (Consumables) | 2019-08-06 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21043-001025 | 21043 | 2019-07-19 11:38 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21939-001025 | 21939 | 2019-08-07 12:17 | Section 1 | Material | Not on List | Not on List | 10 | boxes | NULL | 0 | Miscellaneous | 2019-08-09 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-21947-001025 | 21947 | 2019-08-07 12:46 | Core | Material | Not on List | Not on List | 1000 | NULL | NULL | 0 | Office Supplies | 2019-08-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5570-00392 | 5570 | 2018-08-23 12:15 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.08 | 108 | Concrete Accessories | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21879-001025 | 21879 | 2019-08-06 16:17 | Section 3 | Material | Not on List | Not on List | 15 | each | 718 | 10770 | Miscellaneous | 2019-08-19 | Gate D - 1339643 - BN10 Via Main Compound Entrance | GN3A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21879-001025 | 21879 | 2019-08-06 16:17 | Section 3 | Material | Not on List | Not on List | 6 | Each | 951.7 | 5710.2 | Miscellaneous | 2019-08-19 | Gate D - 1339643 - BN10 Via Main Compound Entrance | GN3B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21949-001025 | 21949 | 2019-08-07 14:15 | Section 5 | Material | Not on List | Not on List | 4 | EA | 39.65 | 158.6 | Plastic Drainage | 2019-08-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21779-001025 | 21779 | 2019-08-05 09:22 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 407.56 | 407.56 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21873-001025 | 21873 | 2019-08-06 15:57 | Section 4 | Material | Not on List | Not on List | 200 | m | 2.43 | 486 | Builders Merchants (General) | 2019-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21341-001025 | 21341 | 2019-07-25 12:48 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21772-001025 | 21772 | 2019-08-05 08:10 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 12102 | 12102 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21953-001025 | 21953 | 2019-08-07 16:07 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-09 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Request - Ops Pass Back | No - Pass Back | NULL | Req - S1 Buyers
MREQ-21844-001025 | 21844 | 2019-08-06 11:56 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 244.86 | 244.86 | Miscellaneous | 2019-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5578-00396 | 5578 | 2018-08-23 15:02 | Section 4 | Material | Not on List | Not on List | 20 | rolls | 110.27 | 2205.4 | Geotextiles | 2018-09-07 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21977-001025 | 21977 | 2019-08-08 08:24 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 3310.75 | 3311 | Miscellaneous | 2019-08-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21983-001025 | 21983 | 2019-08-08 08:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 827.35 | 827 | Small Tools (Consumables) | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-13758-001025 | 13758 | 2019-03-11 10:56 | Core | Material | Not on List | Not on List | 1 | number | 3061.08 | 3061.08 | Professional Services | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18132-001025 | 18132 | 2019-05-28 14:22 | Core | Material | Not on List | Not on List | 110 | people | 58 | 6380 | Miscellaneous | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21935-001025 | 21935 | 2019-08-07 11:15 | Section 5 | Material | Not on List | Not on List | 1 | SM | 4778.45 | 4778.45 | Miscellaneous | 2019-08-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21985-001025 | 21985 | 2019-08-08 09:27 | Core | Material | Not on List | Not on List | 1 | NULL | 10055 | 10055 | Miscellaneous | 2019-08-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 6 | Each | 3.35 | 20.1 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21933-001025 | 21933 | 2019-08-07 10:35 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1965 | 1965 | Waste (General) | 2019-08-09 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21966-001025 | 21966 | 2019-08-07 17:43 | Section 2 | Material | Concrete Drainage | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-08-26 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 20 | Each | 4.5 | 90 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 20 | Each | 5.6 | 112 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 20 | Each | 3.91 | 78.2 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22010-001025 | 22010 | 2019-08-08 14:28 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Concrete Accessories | 2019-08-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21981-001025 | 21981 | 2019-08-08 08:27 | Section 4 | Material | Ducting | Polypipe 94mm x 6m Black Ridgiduct (877654) | 100 | Each | 12.23 | 1223 | Builders Merchants (General) | 2019-08-12 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21981-001025 | 21981 | 2019-08-08 08:27 | Section 4 | Material | Ducting | Polypipe 94mm Ridgiduct Coupler (877674) | 100 | Each | 2.8 | 280 | Builders Merchants (General) | 2019-08-12 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21981-001025 | 21981 | 2019-08-08 08:27 | Section 4 | Material | Ducting | Not on List | 1 | pack | 313.5 | 313.5 | Builders Merchants (General) | 2019-08-12 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 22 | Each | 22.62 | 497.64 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21991-001025 | 21991 | 2019-08-08 11:28 | Core | Material | Not on List | Not on List | 761.85 | Each | 1 | 761.85 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 1 | Each | 325.5 | 325.5 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22064-001025 | 22064 | 2019-08-09 10:25 | Section 3 | Material | Not on List | Not on List | 100 | Anchor | NULL | 0 | Fixings and Fasteners | 2019-08-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22064-001025 | 22064 | 2019-08-09 10:25 | Section 3 | Material | Not on List | Not on List | 100 | Screw | NULL | 0 | Fixings and Fasteners | 2019-08-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22064-001025 | 22064 | 2019-08-09 10:25 | Section 3 | Material | Not on List | Not on List | 2 | Adapter | NULL | 0 | Fixings and Fasteners | 2019-08-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21914-001025 | 21914 | 2019-08-07 07:33 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | ea | 21.3 | 639 | Ductile Drainage | 2019-08-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22052-001025 | 22052 | 2019-08-09 07:43 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 32 | Each | 52.76 | 1688.32 | Plastic Drainage | 2019-08-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22052-001025 | 22052 | 2019-08-09 07:43 | Section 3 | Material | Concrete Drainage | Not on List | 1 | No. | 153.46 | 153.46 | Concrete Drainage | 2019-08-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22052-001025 | 22052 | 2019-08-09 07:43 | Section 3 | Material | Aggregate | Type 1 | 400 | Tonnes | 21.65 | 8660 | Aggregate | 2019-08-12 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 1 | Hun | 34.09 | 34.09 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22089-001025 | 22089 | 2019-08-09 15:37 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 56 | 112 | Miscellaneous | 2019-08-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | NULL | Yes - Approve | Req - S5 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Not on List | 5 | No | 39.7 | 198.5 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5681-00445 | 5681 | 2018-08-28 12:08 | Section 4 | Material | Not on List | Not on List | 18.147 | tonne | 538 | 9763.09 | Rebar and Mesh | 2018-09-04 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21937-001025 | 21937 | 2019-08-07 11:24 | Section 5 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2019-08-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21937-001025 | 21937 | 2019-08-07 11:24 | Section 5 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 5 | Each | 122.72 | 613.6 | Geotextiles | 2019-08-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21937-001025 | 21937 | 2019-08-07 11:24 | Section 5 | Material | Not on List | Not on List | 1 | SUM | 1340.75 | 1340.75 | Not Sure | 2019-08-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 29 | roll | 177 | 5133 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5753 | 5753 | 2018-08-29 13:27 | Section 4 | Material | Not on List | Not on List | 10000 | NULL | NULL | 0 | Concrete Accessories | 2018-09-05 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 37 | roll | 131 | 4847 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 48 | roll | 188 | 9024 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 56 | roll | 215 | 12040 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 42 | box | 37 | 1554 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 39 | roll | 111.59 | 4352.01 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 1 | each | 107.5 | 107.5 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 750 | each | 42.96 | 32220 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 382 | each | 24.56 | 9381.92 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 2250 | each | 1.41 | 3172.5 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 2264 | each | 0.17 | 384.88 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5758-00463 | 5758 | 2018-08-29 13:49 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Accessories | 2018-09-11 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 1146 | each | 0.71 | 813.66 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 1 | SUM | 3150 | 3150 | Miscellaneous | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22135-001025 | 22135 | 2019-08-12 09:31 | Section 1 | Material | Not on List | Not on List | 1 | EACH | 802.64 | 803 | Miscellaneous | 2019-08-12 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-22136-001025 | 22136 | 2019-08-12 09:33 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 3924.44 | 3924 | Miscellaneous | 2019-08-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5033-0018 | 5033 | 2018-08-14 09:31 | Section 4 | Material | Misc | Kassel Bus Stop Kerb 435*314 (Priced Each Not Mtr) | 15 | no | 112.06 | 1645.43 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | PPE | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 5 | Each | 13 | 65 | PPE | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 10 | Each | 13 | 130 | PPE | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 5mtr/1 (765565) | 5 | Each | 2.7 | 14 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 7.5mtr/2 (765566) | 5 | Each | 5.77 | 29 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 10mtr/3 (765567) | 5 | Each | 12.4 | 62 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Brush Wire 4 Row Heavy Duty C/W Scraper Spartan Pro (504004) | 10 | Each | 0.86 | 9 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289) | 10 | Each | 7.32 | 73 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-5814-00499 | 5814 | 2018-08-30 14:06 | Section 3 | Material | Not on List | Not on List | 1 | no. | 593.22 | 593.22 | Surveying Consumables | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5810-00488 | 5810 | 2018-08-30 12:49 | Section 3 | Material | Not on List | Not on List | 10 | No | 75 | 750 | Builders Merchants (General) | 2018-09-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 2 | EA | 6.82 | 14 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5766-00464 | 5766 | 2018-08-29 16:47 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 13 | NULL | 27.5 | 357.5 | PPE | 2018-09-07 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 48 | TOTAL | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5766-00464 | 5766 | 2018-08-29 16:47 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 34 | NULL | 14.5 | 493 | PPE | 2018-09-07 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14542-001025 | 14542 | 2019-03-22 14:46 | Section 4 | Material | Not on List | Not on List | 52747.62 | Tonne | 5 | 263738.1 | Aggregate | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-5111-00502 | 5111 | 2018-08-15 07:51 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 106.02 | 106.02 | Small Tools (Consumables) | 2018-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14389-001025 | 14389 | 2019-03-20 15:23 | Section 2 | Material | Not on List | Not on List | 10 | item | 0 | 0 | Miscellaneous | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 603 - Processing | IMO Queue | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5506-00494 | 5506 | 2018-08-22 13:55 | Section 3 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2018-08-27 | Gate C - 1339699 - BN08 via Logistics Yard Access | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14641-001025 | 14641 | 2019-03-26 09:09 | Section 2 | Material | Not on List | Not on List | 1500 | number | NULL | 0 | Plastic Drainage | 2019-03-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14642-001025 | 14642 | 2019-03-26 09:07 | Section 6 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-04-02 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 1724 | m2 | 66.88 | 115301.12 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 770 | number | 4.27 | 3287.9 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5506-00494 | 5506 | 2018-08-22 13:55 | Section 3 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2018-08-27 | Gate C - 1339699 - BN08 via Logistics Yard Access | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 770 | roll | 6.31 | 4858.7 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 23 | roll | 177 | 4071 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 14 | roll | 131 | 1834 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 58 | roll | 178 | 10324 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 126 | roll | 215 | 27090 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 232 | roll | 235 | 54520 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 13 | box | 33.57 | 436.41 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 80 | box | 63 | 5040 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 45 | number | 12 | 540 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 1 | number | 100 | 100 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5506-00494 | 5506 | 2018-08-22 13:55 | Section 3 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2018-08-27 | Gate C - 1339699 - BN08 via Logistics Yard Access | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14659-001025 | 14659 | 2019-03-26 11:59 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-14660-001025 | 14660 | 2019-03-26 12:10 | Section 2 | Material | Bricks/Blocks | Not on List | 48 | Number | NULL | 0 | Blocks and Bricks | 2019-03-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14661-001025 | 14661 | 2019-03-26 12:13 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14556-001025 | 14556 | 2019-03-22 16:11 | Section 3 | Material | Not on List | Not on List | 1 | ea | 545.14 | 545.14 | Small Tools (Consumables) | 2019-03-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14556-001025 | 14556 | 2019-03-22 16:11 | Section 3 | Material | Not on List | Not on List | 1 | ea | 248.9 | 248.9 | PPE | 2019-03-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14664-001025 | 14664 | 2019-03-26 12:54 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-14588-001025 | 14588 | 2019-03-25 10:17 | Section 4 | Material | Not on List | Not on List | 30 | Each | 78.44 | 2353.2 | Plastic Drainage | 2019-03-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14588-001025 | 14588 | 2019-03-25 10:17 | Section 4 | Material | Not on List | Not on List | 60 | Each | 4.76 | 285.6 | Plastic Drainage | 2019-03-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5033-0018 | 5033 | 2018-08-14 09:31 | Section 4 | Material | Misc | Kassel Bus Stop Kerb 435*314-Hb Transitn (Priced Each Not Mtr) | 2 | Each | 126.82 | 1645.43 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5506-00494 | 5506 | 2018-08-22 13:55 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Not Sure | 2018-08-27 | Gate C - 1339699 - BN08 via Logistics Yard Access | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14670-001025 | 14670 | 2019-03-26 13:30 | Section 2 | Material | Not on List | Not on List | 5 | rolls | NULL | 0 | Concrete Accessories | 2019-03-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14600-001025 | 14600 | 2019-03-25 13:23 | Section 5 | Material | Concrete Drainage | Not on List | 6 | THOUSAND | 66.02 | 396.12 | Concrete Drainage | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14600-001025 | 14600 | 2019-03-25 13:23 | Section 5 | Material | Concrete Drainage | Not on List | 50 | No | 11.15 | 557.5 | Concrete Drainage | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14600-001025 | 14600 | 2019-03-25 13:23 | Section 5 | Material | Concrete Drainage | Not on List | 60 | No | 2.5 | 150 | Concrete Drainage | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13189-001025 | 13189 | 2019-02-27 15:52 | Core | Material | Not on List | Not on List | 1 | Each | 377.5 | 378 | Miscellaneous | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5815-00500 | 5815 | 2018-08-30 14:03 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 500 | No | 0.85 | 425 | Builders Merchants (General) | 2018-09-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14648-001025 | 14648 | 2019-03-26 10:31 | Section 3 | Material | Not on List | Not on List | 8 | metres | 55.21 | 441.68 | Electrical | 2019-03-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14648-001025 | 14648 | 2019-03-26 10:31 | Section 3 | Material | Concrete Drainage | Not on List | 100 | tubes | 4.97 | 497 | Concrete Accessories | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5815-00500 | 5815 | 2018-08-30 14:03 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 500 | No | 2.75 | 1375 | Builders Merchants (General) | 2018-09-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14527-001025 | 14527 | 2019-03-21 16:10 | Section 4 | Material | Not on List | Not on List | 300 | Each | 4.97 | 1491 | Builders Merchants (General) | 2019-03-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14527-001025 | 14527 | 2019-03-21 16:10 | Section 4 | Material | Not on List | Not on List | 1 | pack | 17.57 | 17.57 | Builders Merchants (General) | 2019-03-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4C - Structures (Culverts) 4C | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14527-001025 | 14527 | 2019-03-21 16:10 | Section 4 | Material | Not on List | Not on List | 2 | Each | 97.14 | 194.28 | Builders Merchants (General) | 2019-03-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13827-001025 | 13827 | 2019-03-12 08:54 | Section 3 | Material | Not on List | Not on List | 1 | number | 46589 | 46589 | Miscellaneous | 2019-03-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14181-001025 | 14181 | 2019-03-18 11:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 15000 | 15000 | Miscellaneous | 2019-03-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13762-001025 | 13762 | 2019-03-11 11:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 349.18 | 349.18 | Miscellaneous | 2019-03-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13835-001025 | 13835 | 2019-03-12 09:51 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1209.4 | 1209.4 | Miscellaneous | 2019-03-13 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14194-001025 | 14194 | 2019-03-18 13:51 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 42.5 | 42.5 | Miscellaneous | 2019-03-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11916-001025 | 11916 | 2019-02-05 09:10 | Section 2 | Material | Not on List | Not on List | 1 | each | 3829.38 | 3829.38 | Not Sure | 2019-02-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-14615-001025 | 14615 | 2019-03-25 15:44 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 3266.08 | 3266.08 | Miscellaneous | 2018-08-22 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14751-001025 | 14751 | 2019-03-27 10:13 | Core | Material | Not on List | Not on List | 1 | NULL | 48424.16 | 48424 | Miscellaneous | 2019-03-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-14757-001025 | 14757 | 2019-03-27 11:25 | Core | Material | Not on List | Not on List | 1 | number | 15.84 | 16 | Surveying Consumables | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14443-001025 | 14443 | 2019-03-21 09:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4495 | 4495 | Miscellaneous | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14443-001025 | 14443 | 2019-03-21 09:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4996 | 4996 | Miscellaneous | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14443-001025 | 14443 | 2019-03-21 09:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1375 | 1375 | Miscellaneous | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14759-001025 | 14759 | 2019-03-27 11:31 | Section 2 | Material | Not on List | Not on List | 150 | number | NULL | 0 | Miscellaneous | 2019-03-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14759-001025 | 14759 | 2019-03-27 11:31 | Section 2 | Material | Not on List | Not on List | 250 | number | NULL | 0 | Miscellaneous | 2019-03-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14759-001025 | 14759 | 2019-03-27 11:31 | Section 2 | Material | Not on List | Not on List | 250 | number | NULL | 0 | Miscellaneous | 2019-03-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12283-001025 | 12283 | 2019-02-12 08:21 | Section 2 | Material | Not on List | Not on List | 12 | Number | NULL | 0 | Fixings and Fasteners | 2019-02-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14679-001025 | 14679 | 2019-03-26 15:11 | Section 3 | Material | PPE, Small Tools and Consumables | Netting Debris Green 50 Metre X 2 Metre Spartan Pro (630025) | 2 | Each | 29.98 | 59.96 | Builders Merchants (General) | 2019-03-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN15 - Connington Road Overbridge | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14716-001025 | 14716 | 2019-03-27 06:55 | Section 5 | Material | NULL | All-In Ballast Bulk Bag (996226) | 2 | Each | 33.5 | 67 | Blocks and Bricks | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14716-001025 | 14716 | 2019-03-27 06:55 | Section 5 | Material | NULL | OP Cement; 25kg bag (767201) | 10 | Each | 2.97 | 29.7 | Blocks and Bricks | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14539-001025 | 14539 | 2019-03-22 12:25 | Section 4 | Material | Not on List | Not on List | 1 | Each | 42588 | 42588 | Miscellaneous | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5198-00503 | 5198 | 2018-08-16 08:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 352 | 352 | PPE | 2018-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14786-001025 | 14786 | 2019-03-27 16:06 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196 | Aggregate | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14786-001025 | 14786 | 2019-03-27 16:06 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142 | Aggregate | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14786-001025 | 14786 | 2019-03-27 16:06 | Section 2 | Material | Twinwall | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14786-001025 | 14786 | 2019-03-27 16:06 | Section 2 | Material | Twinwall | Polypipe 150mm x 25m Ridgiflex (877588) | 6 | Each | 145 | 870 | Plastic Drainage | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5198-00503 | 5198 | 2018-08-16 08:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2018-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14798-001025 | 14798 | 2019-03-27 16:27 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Concrete Accessories | 2019-03-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14464-001025 | 14464 | 2019-03-21 14:57 | Section 4 | Material | NULL | NULL | 1 | Each | 449.99 | 449.99 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-14464-001025 | 14464 | 2019-03-21 14:57 | Section 4 | Material | NULL | NULL | 1 | Each | 255.74 | 255.74 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-14464-001025 | 14464 | 2019-03-21 14:57 | Section 4 | Material | NULL | NULL | 1 | Each | 449.99 | 449.99 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-14464-001025 | 14464 | 2019-03-21 14:57 | Section 4 | Material | NULL | NULL | 1 | Each | 115 | 115 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-11681-001025 | 11681 | 2019-01-30 16:29 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 600 | 600 | Miscellaneous | 2019-02-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5198-00503 | 5198 | 2018-08-16 08:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 532.55 | 532.55 | Small Tools (Consumables) | 2018-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14842-001025 | 14842 | 2019-03-28 09:44 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-01 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5775-00466 | 5775 | 2018-08-29 18:50 | Section 3 | Material | Not on List | Not on List | 1 | EA | 524.75 | 524.75 | PPE | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10033-001025 | 10033 | 2018-12-06 10:11 | Section 4 | Material | NULL | Not on List | 2 | bag | 43.57 | 87.14 | Builders Merchants (General) | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10056-001025 | 10056 | 2018-12-06 13:53 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10056-001025 | 10056 | 2018-12-06 13:53 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10057-001025 | 10057 | 2018-12-06 13:46 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 23.49 | 47 | Small Tools (Consumables) | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 11.94 | 11.94 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 11.94 | 11.94 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 7.68 | 7.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 7.68 | 7.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 16 | Each | 5.69 | 91.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 48 | Each | 4.98 | 239.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 40 | Each | 2.18 | 87.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10057-001025 | 10057 | 2018-12-06 13:46 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 23.49 | 46.98 | Small Tools (Consumables) | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | Each | 110.92 | 110.92 | Miscellaneous | 2018-12-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | Each | 176.09 | 176.09 | Miscellaneous | 2018-12-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 2 | Each | 221.85 | 443.7 | Miscellaneous | 2018-12-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | Each | 221.85 | 221.85 | Miscellaneous | 2018-12-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | Each | 221.85 | 221.85 | Miscellaneous | 2018-12-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9994-001025 | 9994 | 2018-12-05 13:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 600 | 600 | Professional Services | 2018-12-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9992-001025 | 9992 | 2018-12-05 12:46 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 4233.75 | 4233.75 | PPE | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10014-001025 | 10014 | 2018-12-05 17:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 25 | Boxes | 27.85 | 696.25 | PPE | 2018-12-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 10 | no. | 285 | 2850 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 100 | no. | 11.35 | 1135 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 1 | box (6 bags) | 83.7 | 83.7 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10032-001025 | 10032 | 2018-12-06 09:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 278.6 | 278.6 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10056-001025 | 10056 | 2018-12-06 13:53 | Section 4 | Material | Not on List | Not on List | 21640.23 | Each | 1 | 21640.23 | Concrete Drainage | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10056-001025 | 10056 | 2018-12-06 13:53 | Section 4 | Material | Not on List | Not on List | 21640.23 | Each | 1 | 21640.23 | Concrete Drainage | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10106-001025 | 10106 | 2018-12-07 13:29 | Section 3 | Material | Not on List | Not on List | 30 | m | NULL | 0 | Concrete Drainage | 2018-12-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10067-001025 | 10067 | 2018-12-06 16:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 187.63 | 187.63 | Miscellaneous | 2018-12-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10108-001025 | 10108 | 2018-12-07 13:50 | Section 4 | Material | Not on List | Not on List | 2 | number | NULL | 0 | Not Sure | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10108-001025 | 10108 | 2018-12-07 13:50 | Section 4 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Not Sure | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10114-001025 | 10114 | 2018-12-07 15:16 | Section 3 | Material | Aggregate | Type 1 | 1300 | Tonnes | 16 | 20800 | Aggregate | 2018-12-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 606 - Import | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10108-001025 | 10108 | 2018-12-07 13:50 | Section 4 | Material | Not on List | Not on List | 2 | number | 9.75 | 19.5 | Plastic Drainage | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10108-001025 | 10108 | 2018-12-07 13:50 | Section 4 | Material | Not on List | Not on List | 1 | number | 336.95 | 336.95 | Plastic Drainage | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10161-001025 | 10161 | 2018-12-10 10:18 | Section 3 | Material | Not on List | Not on List | 1 | EA | 50 | 50 | Miscellaneous | 2018-12-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 50 | meters | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10161-001025 | 10161 | 2018-12-10 10:18 | Section 3 | Material | Not on List | Not on List | 1 | EA | 23.5 | 24 | Miscellaneous | 2018-12-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10097-001025 | 10097 | 2018-12-07 11:27 | Section 4 | Material | Not on List | Not on List | 15 | Each | 290 | 4350 | Plastic Drainage | 2018-12-19 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9807-001025 | 9807 | 2018-11-30 08:29 | Section 4 | Material | Concrete Drainage | Not on List | 150 | Each | 23 | 3450 | Concrete Drainage | 2018-12-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10170-001025 | 10170 | 2018-12-10 11:19 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1 | 1 | Reinforcement | 2019-01-07 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10096-001025 | 10096 | 2018-12-07 11:05 | Section 4 | Material | Not on List | Not on List | 50 | Each | 16.91 | 845.5 | Builders Merchants (General) | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10096-001025 | 10096 | 2018-12-07 11:05 | Section 4 | Material | Not on List | Not on List | 100 | Each | 13.9 | 1390 | Builders Merchants (General) | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10096-001025 | 10096 | 2018-12-07 11:05 | Section 4 | Material | Not on List | Not on List | 20 | Each | 9.44 | 188.8 | Builders Merchants (General) | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10096-001025 | 10096 | 2018-12-07 11:05 | Section 4 | Material | Not on List | Not on List | 50 | Each | 3.46 | 173 | Builders Merchants (General) | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10123-001025 | 10123 | 2018-12-07 16:45 | Section 3 | Material | Not on List | Not on List | 1 | ea | 315.22 | 315.22 | Small Tools (Consumables) | 2018-12-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10170-001025 | 10170 | 2018-12-10 11:19 | Section 4 | Material | Not on List | Not on List | 2.611 | Tonne | 538 | 1404.72 | Rebar and Mesh | 2019-01-07 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | CL4C - Structures (Culverts) 4C | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10205-001025 | 10205 | 2018-12-11 08:02 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | no | NULL | 0 | Office Supplies | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10210-001025 | 10210 | 2018-12-11 08:32 | Section 4 | Material | Aggregate | Not on List | 120 | t | NULL | 0 | Aggregate | 2018-12-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10106-001025 | 10106 | 2018-12-07 13:29 | Section 3 | Material | Not on List | Not on List | 30 | m | 26.58 | 797.4 | Concrete Drainage | 2018-12-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9991-001025 | 9991 | 2018-12-05 12:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1809 | 1809 | Timber Products | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10106-001025 | 10106 | 2018-12-07 13:29 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 26.58 | 265.8 | Concrete Drainage | 2018-12-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10203-001025 | 10203 | 2018-12-11 07:29 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1392.54 | 1392.54 | Miscellaneous | 2018-12-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 772.44 | 772.44 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 951.6 | 951.6 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 457.2 | 457.2 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1524 | 1524 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10224-001025 | 10224 | 2018-12-11 11:19 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2018-12-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10224-001025 | 10224 | 2018-12-11 11:19 | Section 3 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Not Sure | 2018-12-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10205-001025 | 10205 | 2018-12-11 08:02 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | no | NULL | 0 | Office Supplies | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 16 | ea | 1 | 16 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 6 | ea | 1 | 6 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 8 | ea | 1 | 8 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10243-001025 | 10243 | 2018-12-11 15:19 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 167.85 | 168 | Small Tools (Consumables) | 2018-12-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10181-001025 | 10181 | 2018-12-10 15:10 | Section 4 | Material | Not on List | Not on List | 6 | Each | 47.48 | 284.88 | Not Sure | 2018-12-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10181-001025 | 10181 | 2018-12-10 15:10 | Section 4 | Material | Not on List | Not on List | 50 | Each | 21 | 1050 | Not Sure | 2018-12-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10181-001025 | 10181 | 2018-12-10 15:10 | Section 4 | Material | Not on List | Not on List | 50 | Foot & 2 Clips | 6.5 | 325 | Not Sure | 2018-12-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10181-001025 | 10181 | 2018-12-10 15:10 | Section 4 | Material | Not on List | Not on List | 50 | Each | 20.5 | 1025 | Not Sure | 2018-12-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5362-00247 | 5362 | 2018-08-20 14:53 | Section 3 | Material | Not on List | Not on List | 10500 | NULL | NULL | 0 | Miscellaneous | 2018-08-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 16 | ea | 35.46 | 567.36 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 6 | ea | 50.59 | 303.54 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 8 | ea | 77.79 | 622.32 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9540-001025 | 9540 | 2018-11-23 12:20 | Section 4 | Material | Not on List | Not on List | 1 | Each | 179.5 | 179.5 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9933-001025 | 9933 | 2018-12-04 08:30 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 15 | Each | 47.04 | 705.6 | Concrete Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9933-001025 | 9933 | 2018-12-04 08:30 | Section 4 | Material | Concrete Drainage | Not on List | 15 | Each | 67.9 | 1018.5 | Concrete Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9933-001025 | 9933 | 2018-12-04 08:30 | Section 4 | Material | NULL | NULL | 1 | Each | 200 | 200 | Concrete Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9997-001025 | 9997 | 2018-12-05 13:55 | Section 4 | Material | Not on List | Not on List | 1 | Annual Subsistence Charge | 1580 | 1580 | Professional Services | 2018-12-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | Each | 120.62 | 6031 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 55 | Each | 17.45 | 959.75 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 110 | Each | 9.04 | 994.4 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 140 | Each | 34.82 | 4874.8 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 160 | Each | 6.54 | 1046.4 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 320 | Each | 2.75 | 880 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | Each | 23.14 | 1157 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 55 | Each | 3.38 | 185.9 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 110 | Each | 1.86 | 204.6 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 40 | Each | 10.5 | 420 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | Each | 1.84 | 92 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.85 | 85 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 40 | Each | 26.94 | 1077.6 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 144 | Each | 0.85 | 122.4 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 12 | Each | 84.41 | 1012.92 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 44 | Each | 9.04 | 397.76 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 35 | Each | 144.91 | 5071.85 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | NULL | Not on List | 70 | Each | 2.75 | 192.5 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | NULL | Not on List | 115 | Each | 1.86 | 213.9 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | NULL | Not on List | 10 | Each | 174.42 | 1744.2 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | NULL | Not on List | 35 | Each | 27.62 | 966.7 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 5 | Each | 67.9 | 339.5 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 2 | Each | 50.92 | 101.84 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 2 | Each | 43.16 | 86.32 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 3 | Each | 35.52 | 106.56 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | Each | 47.04 | 376.32 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 30 | Each | 22 | 660 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | Each | 74.3 | 594.4 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | Each | 121.25 | 970 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | Each | 90.94 | 727.52 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 5 | Each | 80.51 | 402.55 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | Each | 102.82 | 822.56 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9833-001025 | 9833 | 2018-11-30 14:00 | Section 3 | Material | Signage | Not on List | 80 | number | 7.35 | 588 | Miscellaneous | 2018-12-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9833-001025 | 9833 | 2018-11-30 14:00 | Section 3 | Material | Signage | Not on List | 80 | number | 12.84 | 1027.2 | Miscellaneous | 2018-12-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10265-001025 | 10265 | 2018-12-12 09:02 | Section 3 | Material | Bagged | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10226-001025 | 10226 | 2018-12-11 11:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 56 | Each | 2.9 | 162.4 | Miscellaneous | 2018-12-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10226-001025 | 10226 | 2018-12-11 11:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3000 | Each | 0.37 | 1110 | Miscellaneous | 2018-12-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10274-001025 | 10274 | 2018-12-12 11:26 | Section 3 | Material | Kerbs | Not on List | 270 | No | NULL | 0 | Builders Merchants (General) | 2019-01-04 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10274-001025 | 10274 | 2018-12-12 11:26 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 540 | Each | 1.45 | 783 | Builders Merchants (General) | 2019-01-04 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9633-001025 | 9633 | 2018-11-26 16:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 288 | Each | 6.29 | 1811.52 | Miscellaneous | 2018-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9738-001025 | 9738 | 2018-11-28 16:40 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 38.82 | 38.82 | PPE | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10154-001025 | 10154 | 2018-12-10 08:53 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | 20ltr Drum | 55.4 | 277 | Miscellaneous | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28980 | 28980 | 2020-02-07 12:22 | Test Section | Material Requisition | Aggregate | 6F2 | 345 | Tonnes | 13 | 4485 | Blocks and Bricks | 2020-02-29 | Test Location | Test Section | Test Section | Operational Approval | NULL | NULL | Chris Henry
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 150 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 50 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18603-001025 | 18603 | 2019-06-05 14:14 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18599-001025 | 18599 | 2019-06-05 13:55 | Section 4 | Material | Not on List | Not on List | 1 | Each | 280 | 280 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18753-001025 | 18753 | 2019-06-07 11:22 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18120-001025 | 18120 | 2019-05-28 13:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 445.84 | 445.84 | Miscellaneous | 2019-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17972-001025 | 17972 | 2019-05-23 13:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1000 | 1000 | Miscellaneous | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17959-001025 | 17959 | 2019-05-23 11:22 | Section 4 | Material | Not on List | Not on List | 1 | Each | 171.2 | 171.2 | Fuel | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18713-001025 | 18713 | 2019-06-07 07:49 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18783-001025 | 18783 | 2019-06-07 14:44 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 601 - Topsoil Strip, Store, Dispose | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-18750-001025 | 18750 | 2019-06-07 11:12 | Section 3 | Material | Not on List | Not on List | 500000 | Litres | 0.1 | 50000 | Gas Oil | 2019-06-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 17 | 51 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 12 | 36 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 12 | 36 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 17 | 17 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 215 | 215 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 20 | 20 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18806-001025 | 18806 | 2019-06-10 07:29 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18820-001025 | 18820 | 2019-06-10 08:42 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18820-001025 | 18820 | 2019-06-10 08:42 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18820-001025 | 18820 | 2019-06-10 08:42 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18824-001025 | 18824 | 2019-06-10 08:58 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18780-001025 | 18780 | 2019-06-07 14:37 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18646-001025 | 18646 | 2019-06-06 09:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18046-001025 | 18046 | 2019-05-24 11:26 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18749-001025 | 18749 | 2019-06-07 10:31 | Section 4 | Material | Not on List | Not on List | 512 | Each | 8.25 | 4224 | Concrete Drainage | 2019-06-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18749-001025 | 18749 | 2019-06-07 10:31 | Section 4 | Material | NULL | Not on List | 80 | eACH | 8.25 | 660 | Concrete Drainage | 2019-06-13 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18633-001025 | 18633 | 2019-06-06 07:05 | Section 2 | Material | NULL | Concrete Kerbs Splayed 45deg 125x255 (898227) | 500 | Each | 4.59 | 2295 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-11 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18633-001025 | 18633 | 2019-06-06 07:05 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 3 | Each | 11.94 | 35.82 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-11 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18633-001025 | 18633 | 2019-06-06 07:05 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 3 | Each | 11.94 | 35.82 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-11 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18633-001025 | 18633 | 2019-06-06 07:05 | Section 2 | Material | NULL | Not on List | 20 | no. | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-11 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18633-001025 | 18633 | 2019-06-06 07:05 | Section 2 | Material | NULL | Not on List | 20 | no. | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-11 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18690-001025 | 18690 | 2019-06-06 15:38 | Section 4 | Material | Not on List | Not on List | 8 | Each | 15.52 | 124.16 | Concrete Accessories | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18690-001025 | 18690 | 2019-06-06 15:38 | Section 4 | Material | NULL | Not on List | 1 | Each | 30 | 30 | Concrete Accessories | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18798-001025 | 18798 | 2019-06-07 16:35 | Section 3 | Material | Not on List | Not on List | 20 | No | 21.6 | 432 | Builders Merchants (General) | 2019-06-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18823-001025 | 18823 | 2019-06-10 08:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Small Tools (Consumables) | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18863-001025 | 18863 | 2019-06-10 12:08 | Section 3 | Material | PPE, Small Tools and Consumables | Cones Blue 750mm - No Sleeve Csp (204013) | 120 | Each | 5.3 | 636 | Miscellaneous | 2019-06-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18863-001025 | 18863 | 2019-06-10 12:08 | Section 3 | Material | PPE, Small Tools and Consumables | Sleeve - White C/W Overhead Structures 750mm Csp (204017) | 120 | Each | 2.18 | 262 | Miscellaneous | 2019-06-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18863-001025 | 18863 | 2019-06-10 12:08 | Section 3 | Material | Not on List | Not on List | 10 | Each | 14.4 | 144 | Miscellaneous | 2019-06-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18650-001025 | 18650 | 2019-06-06 09:58 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 40 | Each | 34.82 | 1392.8 | Plastic Drainage | 2019-06-11 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18650-001025 | 18650 | 2019-06-06 09:58 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 12 | Each | 67.9 | 814.8 | Concrete Drainage | 2019-06-11 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18650-001025 | 18650 | 2019-06-06 09:58 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 4 | Each | 43.16 | 172.64 | Concrete Drainage | 2019-06-11 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18650-001025 | 18650 | 2019-06-06 09:58 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 7 | Each | 35.52 | 248.64 | Concrete Drainage | 2019-06-11 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18650-001025 | 18650 | 2019-06-06 09:58 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 47.04 | 470.4 | Concrete Drainage | 2019-06-11 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18846-001025 | 18846 | 2019-06-10 12:07 | Section 2 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-06-13 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18653-001025 | 18653 | 2019-06-06 10:15 | Section 1 | Material | NULL | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-06-12 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-6639-00750 | 6639 | 2018-09-18 09:16 | Section 3 | Material | Plastic Drainage | Not on List | 39 | metres | NULL | 0 | Concrete Accessories | 2018-09-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5218 | 5218 | 2018-08-16 11:54 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-08-29 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18557-001025 | 18557 | 2019-06-04 17:04 | Section 4 | Material | Not on List | Not on List | 4 | Each | 414.32 | 1657.28 | Fixings and Fasteners | 2019-06-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18557-001025 | 18557 | 2019-06-04 17:04 | Section 4 | Material | Not on List | Not on List | 32 | Each | 1.55 | 49.6 | Fixings and Fasteners | 2019-06-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18557-001025 | 18557 | 2019-06-04 17:04 | Section 4 | Material | NULL | Not on List | 1 | Each | 80 | 80 | Fixings and Fasteners | 2019-06-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18412-001025 | 18412 | 2019-06-03 09:18 | Core | Material | Not on List | Not on List | 1 | Ea | 1040.6 | 1040.6 | Miscellaneous | 2019-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5129-00498 | 5129 | 2018-08-15 10:17 | Section 3 | Material | Not on List | Not on List | 4 | 10 Pack | 57.91 | 231.64 | Miscellaneous | 2018-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153c - Temporary Works - Fencing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18420-001025 | 18420 | 2019-06-03 10:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 30.56 | 611.2 | Small Tools (Consumables) | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18300-001025 | 18300 | 2019-05-30 17:05 | Section 3 | Material | Not on List | Not on List | 10 | no | 1004.73 | 10047.3 | Miscellaneous | 2019-06-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18300-001025 | 18300 | 2019-05-30 17:05 | Section 3 | Material | Not on List | Not on List | 1 | no | 367.4 | 367.4 | Miscellaneous | 2019-06-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18531-001025 | 18531 | 2019-06-04 14:24 | Section 2 | Material | Not on List | Not on List | 250000 | litres | 1 | 250000 | Fuel | 2019-06-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18787-001025 | 18787 | 2019-06-07 15:27 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18814-001025 | 18814 | 2019-06-10 08:22 | Section 4 | Material | Not on List | Not on List | 20 | tonne | 33.55 | 671 | Aggregate | 2019-06-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18812-001025 | 18812 | 2019-06-10 08:13 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 49.5 | 297 | Plastic Drainage | 2019-06-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18817-001025 | 18817 | 2019-06-10 08:26 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 3805 | 3805 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18832-001025 | 18832 | 2019-06-10 11:01 | Section 4 | Material | Concrete Drainage | Not on List | 1 | NULL | 1105.39 | 1105.39 | Concrete Drainage | 2019-06-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18771-001025 | 18771 | 2019-06-07 13:57 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Concrete Drainage | 2019-06-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18712-001025 | 18712 | 2019-06-07 07:46 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Concrete Drainage | 2019-06-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18686-001025 | 18686 | 2019-06-06 14:33 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Ductile Drainage | 2019-06-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18645-001025 | 18645 | 2019-06-06 09:21 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Ductile Drainage | 2019-06-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17905-001025 | 17905 | 2019-05-22 14:22 | Section 4 | Material | Waste Management | Not on List | 1 | Each | 825 | 825 | Waste (General) | 2019-05-24 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18901-001025 | 18901 | 2019-06-11 11:58 | Core | Material | Not on List | Not on List | 1 | each | 850 | 850 | Training | 2019-06-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18907-001025 | 18907 | 2019-06-11 13:38 | Section 4 | Material | Not on List | Not on List | 1 | Day | 550 | 550 | Surveying Consumables | 2019-06-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-18911-001025 | 18911 | 2019-06-11 13:27 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Concrete Accessories | 2019-06-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18912-001025 | 18912 | 2019-06-11 14:33 | Section 3 | Material | Not on List | Not on List | 1 | each | 5077.75 | 5078 | Miscellaneous | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18915-001025 | 18915 | 2019-06-11 14:40 | Section 5 | Material | Not on List | Not on List | 1 | each | 525.3 | 525 | Miscellaneous | 2019-06-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18922-001025 | 18922 | 2019-06-11 09:29 | Core | Material | Not on List | Not on List | 1 | NULL | 105.33 | 105 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Finance Approval | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Can Fuel 5ltr Heavy Duty Green Plastic Long Spout Unleaded (706686) | 5 | Each | 5.82 | 29 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Can Fuel 5ltr Heavy Duty Black Plastic Long Spout For Diesel (706684) | 5 | Each | 5.85 | 29 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Tape Gaffa Waterproof Cloth Grey 50mm X 50 Mtr Ref 3160 (964670) | 40 | Each | 1.91 | 76 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Paint Roller And Tray Set 9" Rskit1 (704256) | 20 | Each | 3.42 | 68 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Bucket Galvanised 2 1/2gall/11.42ltr 10"/30cm Dia Spartan (506016) | 20 | Each | 9 | 180 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Hammer Club C/W Fibreglass Handle Spartan Pro 1.1kg(2.5lb) (724107) | 15 | Each | 8.98 | 135 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 7 | Each | NULL | 0 | PPE | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18678-001025 | 18678 | 2019-06-06 13:46 | Section 4 | Material | NULL | NULL | 7 | 1kg Bag | 2.8 | 19.6 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18933-001025 | 18933 | 2019-06-11 16:58 | Core | Material | Combined Drainage | Not on List | 1 | each | 10665 | 10665 | Flow Control | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Buyers
MREQ-18934-001025 | 18934 | 2019-06-11 16:18 | Core | Material | Not on List | Not on List | 1 | NULL | 317.25 | 317 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18935-001025 | 18935 | 2019-06-11 17:25 | Core | Material | Not on List | Not on List | 1 | NULL | 37.85 | 38 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18935-001025 | 18935 | 2019-06-11 17:25 | Core | Material | Not on List | Not on List | 1 | NULL | 31.65 | 32 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18660-001025 | 18660 | 2019-06-06 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Pack 3 | 6.5 | 26 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18660-001025 | 18660 | 2019-06-06 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | 0.54 | 54 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18660-001025 | 18660 | 2019-06-06 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pairs | 0.52 | 5.2 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18660-001025 | 18660 | 2019-06-06 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 6.5 | 13 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18660-001025 | 18660 | 2019-06-06 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 22.25 | 44.5 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18953-001025 | 18953 | 2019-06-12 08:53 | Section 2 | Material | Not on List | Not on List | 1 | each | 10665 | 10665 | Professional Services | 2019-06-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 501 - Drains | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-18236-001025 | 18236 | 2019-05-30 07:25 | Section 3 | Material | Not on List | Not on List | 70 | NULL | NULL | 0 | Miscellaneous | 2019-06-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18831-001025 | 18831 | 2019-06-10 10:45 | Section 4 | Material | Not on List | Not on List | 10 | 1t Bag | 50.05 | 500.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18978-001025 | 18978 | 2019-06-12 12:30 | Section 1 | Material | Not on List | Not on List | 1 | each | 120.56 | 121 | Miscellaneous | 2019-06-12 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18979-001025 | 18979 | 2019-06-12 12:32 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18993-001025 | 18993 | 2019-06-12 14:51 | Core | Material | Not on List | Not on List | 1 | Each | 850 | 850 | Training | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18994-001025 | 18994 | 2019-06-12 14:54 | Core | Material | Not on List | Not on List | 1 | each | 850 | 850 | Training | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18896-001025 | 18896 | 2019-06-11 11:36 | Section 4 | Material | NULL | Not on List | 3 | Rolles | 72.76 | 218.28 | Miscellaneous | 2019-06-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18894-001025 | 18894 | 2019-06-11 11:15 | Section 4 | Material | NULL | Not on List | 20 | Roll | 6.4 | 128 | Miscellaneous | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18999-001025 | 18999 | 2019-06-12 13:50 | Section 6 | Material | Not on List | Not on List | 1 | number | 995 | 995 | Training | 2019-06-19 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-18969-001025 | 18969 | 2019-06-12 11:01 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18969-001025 | 18969 | 2019-06-12 11:01 | Section 4 | Material | NULL | Not on List | 1 | Each | 15 | 15 | Plastic Drainage | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18897-001025 | 18897 | 2019-06-11 11:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 150 | Each | 1.31 | 196.5 | Small Tools (Consumables) | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18952-001025 | 18952 | 2019-06-12 08:52 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 3723.63 | 3723.63 | Small Tools (Consumables) | 2019-06-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18864-001025 | 18864 | 2019-06-10 15:23 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 3.78 | 7.56 | Rebar and Mesh | 2019-06-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 355 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 220 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 9 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 2 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 4 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 65 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 2 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6824-00751 | 6824 | 2018-09-21 07:52 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 5 | no. | NULL | 0 | Concrete Drainage | 2018-09-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN10 - A1198 Ermine Street Overbridge | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 16 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 1 | no | 95 | 95 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 65 | tonnes | 538 | 34970 | NULL | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 150 | tonnes | 538 | 80700 | NULL | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 35 | tonnes | 538 | 18830 | NULL | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 50 | tonnes | 538 | 26900 | NULL | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | NULL | Not on List | 750 | Each | 2 | 1500 | NULL | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12300-001025 | 12300 | 2019-02-12 11:12 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 88.88 | 88.88 | Small Tools (Consumables) | 2019-02-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12294-001025 | 12294 | 2019-02-12 09:49 | Section 3 | Material | Not on List | Not on List | 80 | 25M Length | 15.5 | 1240 | Miscellaneous | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11649-001025 | 11649 | 2019-01-30 06:51 | Section 4 | Material | Not on List | Not on List | 1 | each | 581.82 | 581.82 | Miscellaneous | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12224-001025 | 12224 | 2019-02-11 10:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 35.6 | 35.6 | Small Tools (Consumables) | 2019-02-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12287-001025 | 12287 | 2019-02-12 08:43 | Section 2 | Material | Not on List | Not on List | 8 | no | 21 | 168 | Concrete Accessories | 2019-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12287-001025 | 12287 | 2019-02-12 08:43 | Section 2 | Material | Not on List | Not on List | 4 | no | 13.75 | 55 | Concrete Accessories | 2019-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12320-001025 | 12320 | 2019-02-12 15:18 | Section 2 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Geotextiles | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5576-00394 | 5576 | 2018-08-23 12:11 | Section 3 | Material | Not on List | Not on List | 50 | Ea | 5.98 | 299 | Miscellaneous | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12330-001025 | 12330 | 2019-02-12 16:13 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 12 | each | 72.5 | 870 | Miscellaneous | 2019-02-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12375-001025 | 12375 | 2019-02-13 11:11 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12379-001025 | 12379 | 2019-02-13 11:33 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12389-001025 | 12389 | 2019-02-13 13:16 | Section 6 | Material | Not on List | Not on List | 1 | number | 1152.96 | 1153 | Miscellaneous | 2019-02-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1201 - Traffic Signs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-12391-001025 | 12391 | 2019-02-13 13:31 | Core | Material | Not on List | Not on List | 1 | unit | 1593.6 | 1594 | Miscellaneous | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-5576-00394 | 5576 | 2018-08-23 12:11 | Section 3 | Material | Not on List | Not on List | 65 | ea | 5.98 | 389 | Miscellaneous | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 200 | EA | 6.9 | 1380 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 150 | EA | 2.18 | 327 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 100 | EA | 2.78 | 278 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 20 | EA | 285 | 5700 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12393-001025 | 12393 | 2019-02-13 14:03 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-02-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-12394-001025 | 12394 | 2019-02-13 13:57 | Section 2 | Material | Not on List | Not on List | 0.782 | t | NULL | 0 | Reinforcement | 2019-02-21 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12396-001025 | 12396 | 2019-02-13 14:46 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12094-001025 | 12094 | 2019-02-07 17:02 | Section 4 | Material | Not on List | Not on List | 10 | Roll | 3674 | 36740 | Concrete Drainage | 2019-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12094-001025 | 12094 | 2019-02-07 17:02 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1000 | 1000 | Concrete Drainage | 2019-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12094-001025 | 12094 | 2019-02-07 17:02 | Section 4 | Material | Not on List | Not on List | 1200 | Each | 2.55 | 3060 | Concrete Drainage | 2019-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12094-001025 | 12094 | 2019-02-07 17:02 | Section 4 | Material | Not on List | Not on List | 1 | Each | 610 | 610 | Concrete Drainage | 2019-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12094-001025 | 12094 | 2019-02-07 17:02 | Section 4 | Material | Not on List | Not on List | 6 | Each | 40.81 | 244.86 | Concrete Drainage | 2019-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12397-001025 | 12397 | 2019-02-13 15:13 | Section 2 | Material | Not on List | Not on List | 15 | NULL | NULL | 0 | Builders Merchants (General) | 2019-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN28 - Ellington Brook Bridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12402-001025 | 12402 | 2019-02-13 15:43 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Ductile Drainage | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12402-001025 | 12402 | 2019-02-13 15:43 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Ductile Drainage | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12404-001025 | 12404 | 2019-02-13 15:54 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12394-001025 | 12394 | 2019-02-13 13:57 | Section 2 | Material | Not on List | Not on List | 0.782 | t | 538 | 420.72 | NULL | 2019-02-21 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12440-001025 | 12440 | 2019-02-14 07:41 | Section 2 | Material | Bagged | Not on List | 4 | NULL | NULL | 0 | Concrete Accessories | 2019-02-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12440-001025 | 12440 | 2019-02-14 07:41 | Section 2 | Material | Bagged | Not on List | 2 | NULL | NULL | 0 | Concrete Accessories | 2019-02-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12453-001025 | 12453 | 2019-02-14 09:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1122 | 1122 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12453-001025 | 12453 | 2019-02-14 09:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 43 | 43 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12454-001025 | 12454 | 2019-02-14 09:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 456 | 456 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12455-001025 | 12455 | 2019-02-14 09:49 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 172.8 | 173 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12457-001025 | 12457 | 2019-02-14 10:02 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 20.4 | 20 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12457-001025 | 12457 | 2019-02-14 10:02 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 312 | 312 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12460-001025 | 12460 | 2019-02-14 10:48 | Core | Material | Not on List | Not on List | 8 | NULL | 37 | 296 | Office Supplies | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12461-001025 | 12461 | 2019-02-14 09:01 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-11712-001025 | 11712 | 2019-01-31 11:53 | Section 4 | Material | Not on List | Not on List | 1 | Each | 350 | 350 | Miscellaneous | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11968-001025 | 11968 | 2019-02-05 17:47 | Section 4 | Material | Not on List | Not on List | 500 | LM | 4.38 | 2190 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12463-001025 | 12463 | 2019-02-14 09:31 | Section 3 | Material | Not on List | Not on List | 10 | no. | NULL | 0 | Concrete Drainage | 2019-02-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12467-001025 | 12467 | 2019-02-14 12:03 | Section 2 | Material | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2019-02-18 | Gate 4 - 1339619 - BN01 via Gate 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12470-001025 | 12470 | 2019-02-14 12:14 | Section 2 | Material | Not on List | Not on List | 2 | each | 12 | 24 | Laboratory Equipment / Certification | 2019-02-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12473-001025 | 12473 | 2019-02-14 12:37 | Section 3 | Material | Not on List | Not on List | 100 | No | NULL | 0 | Builders Merchants (General) | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12476-001025 | 12476 | 2019-02-14 12:34 | Section 4 | Material | Not on List | Not on List | 16 | ea | 1 | 16 | Concrete Drainage | 2019-02-19 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1103 - Linear Drainage Channel Systems | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-12482-001025 | 12482 | 2019-02-14 13:11 | Section 4 | Material | Not on List | Not on List | 4 | EA | 300 | 1200 | Concrete Accessories | 2019-02-19 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 200 | EA | 6.9 | 1380 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 150 | EA | 2.18 | 327 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 100 | EA | 2.78 | 278 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 20 | EA | 285 | 5700 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12365-001025 | 12365 | 2019-02-13 09:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1843.2 | 1843.2 | PPE | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-4957-003 | 4957 | 2018-08-10 17:48 | Section 4 | Material | Not on List | NULL | NULL | NULL | 372.83 | 0 | Rebar and Mesh | 2018-08-14 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | CL4B - Structures (Culverts) 4B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12463-001025 | 12463 | 2019-02-14 09:31 | Section 3 | Material | Not on List | Not on List | 10 | no. | 62 | 620 | Concrete Drainage | 2019-02-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12318-001025 | 12318 | 2019-02-12 15:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 588.94 | 588.94 | Small Tools (Consumables) | 2019-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12473-001025 | 12473 | 2019-02-14 12:37 | Section 3 | Material | Not on List | Not on List | 100 | No | 7.1 | 710 | Builders Merchants (General) | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12215-001025 | 12215 | 2019-02-11 09:20 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1649.94 | 1649.94 | Small Tools (Consumables) | 2019-02-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12467-001025 | 12467 | 2019-02-14 12:03 | Section 2 | Material | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2019-02-18 | Gate 4 - 1339619 - BN01 via Gate 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-11701-001025 | 11701 | 2019-01-31 09:11 | Section 4 | Material | Not on List | Not on List | 1 | Each | 670 | 670 | Miscellaneous | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12497-001025 | 12497 | 2019-02-14 15:08 | Section 4 | Material | Not on List | Not on List | 32 | number | NULL | 0 | Reinforcement | 2019-03-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12499-001025 | 12499 | 2019-02-14 14:50 | Core | Material | PPE, Small Tools and Consumables | Cream Pristine After Work Restore 1 Litre Cartridge (548142) | 1 | Each | 10.45 | 10 | Miscellaneous | 2019-02-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12499-001025 | 12499 | 2019-02-14 14:50 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 6 | 6 | Miscellaneous | 2019-02-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12232-001025 | 12232 | 2019-02-11 12:40 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.9 | 450 | Timber Products | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12232-001025 | 12232 | 2019-02-11 12:40 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 200 | Each | 0.3 | 60 | Timber Products | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12396-001025 | 12396 | 2019-02-13 14:46 | Section 3 | Material | Not on List | Not on List | 1 | ea | 1420 | 1420 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12464-001025 | 12464 | 2019-02-14 11:40 | Section 4 | Material | NULL | Not on List | 1 | ea | 23.95 | 23.95 | Plastic Drainage | 2019-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-12464-001025 | 12464 | 2019-02-14 11:40 | Section 4 | Material | NULL | Not on List | 1 | ea | 7.61 | 7.61 | Plastic Drainage | 2019-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-12464-001025 | 12464 | 2019-02-14 11:40 | Section 4 | Material | NULL | Not on List | 1 | ea | 25.82 | 25.82 | Plastic Drainage | 2019-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-11921-001025 | 11921 | 2019-02-05 09:38 | Section 4 | Material | Not on List | Not on List | 1 | each | 1767.13 | 1767.13 | Miscellaneous | 2019-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12520-001025 | 12520 | 2019-02-14 18:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11922-001025 | 11922 | 2019-02-05 09:50 | Section 3 | Material | Not on List | Not on List | 1 | each | 3760.63 | 3760.63 | Miscellaneous | 2019-02-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12101-001025 | 12101 | 2019-02-07 17:37 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 643.99 | 643.99 | PPE | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12330-001025 | 12330 | 2019-02-12 16:13 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 12 | each | 72.5 | 870 | Miscellaneous | 2019-02-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12485-001025 | 12485 | 2019-02-14 13:38 | Section 4 | Material | Not on List | Not on List | 5 | packs 50 | 24.63 | 123.15 | Builders Merchants (General) | 2019-02-18 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12485-001025 | 12485 | 2019-02-14 13:38 | Section 4 | Material | Not on List | Not on List | 5 | packs 50 | 21.96 | 109.8 | Builders Merchants (General) | 2019-02-18 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12344-001025 | 12344 | 2019-02-12 17:15 | Section 4 | Material | Not on List | Not on List | 200 | Each | 3.38 | 676 | Miscellaneous | 2019-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12502-001025 | 12502 | 2019-02-14 15:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | EACH | 28.8 | 864 | PPE | 2019-02-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12502-001025 | 12502 | 2019-02-14 15:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 19 | EACH | 28.8 | 547.2 | PPE | 2019-02-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12155-001025 | 12155 | 2019-02-08 12:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 12 | each | 112 | 1344 | Tanks and Interceptors | 2019-02-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12546-001025 | 12546 | 2019-02-15 09:26 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2019-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN32 - Brampton Equestrian Underpass | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12546-001025 | 12546 | 2019-02-15 09:26 | Section 2 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Miscellaneous | 2019-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN32 - Brampton Equestrian Underpass | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12470-001025 | 12470 | 2019-02-14 12:14 | Section 2 | Material | Not on List | Not on List | 2 | each | 12 | 24 | Laboratory Equipment / Certification | 2019-02-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12456-001025 | 12456 | 2019-02-14 09:52 | Section 4 | Material | Not on List | Not on List | 12 | Each | 166.32 | 1995.84 | Plastic Drainage | 2019-02-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12456-001025 | 12456 | 2019-02-14 09:52 | Section 4 | Material | Not on List | Not on List | 12 | Each | 15.19 | 182.28 | Plastic Drainage | 2019-02-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12456-001025 | 12456 | 2019-02-14 09:52 | Section 4 | Material | Not on List | NULL | 6 | Each | 159.28 | 955.68 | Plastic Drainage | 2019-02-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12456-001025 | 12456 | 2019-02-14 09:52 | Section 4 | Material | Not on List | Not on List | 6 | Each | 10.04 | 60.24 | Plastic Drainage | 2019-02-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | Twinwall | Not on List | 30 | number | NULL | 0 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 30 | Each | 1.84 | 55 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 150 | Each | 0.85 | 128 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | Twinwall | Polypipe 150mm x 150mm 45deg Junction (878010) | 10 | Each | 14.4 | 144 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12551-001025 | 12551 | 2019-02-15 10:22 | Section 2 | Material | Aggregate | 6G | 300 | Tonnes | 22 | 6600 | Aggregate | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12289-001025 | 12289 | 2019-02-12 09:03 | Core | Material | Not on List | Not on List | 2 | each | 228 | 456 | Office Supplies | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12397-001025 | 12397 | 2019-02-13 15:13 | Section 2 | Material | Not on List | Not on List | 15 | NULL | NULL | 0 | Builders Merchants (General) | 2019-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN28 - Ellington Brook Bridge | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12557-001025 | 12557 | 2019-02-15 11:42 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Ea | NULL | 0 | PPE | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12156-001025 | 12156 | 2019-02-08 13:01 | Core | Material | Not on List | Not on List | 3 | number packs | 21.45 | 64 | Office Supplies | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | NULL
MREQ-11907-001025 | 11907 | 2019-02-05 07:50 | Section 4 | Material | Not on List | Not on List | 1 | Each | 133.5 | 133.5 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11910-001025 | 11910 | 2019-02-05 07:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 531.69 | 531.69 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12278-001025 | 12278 | 2019-02-12 07:56 | Section 4 | Material | Not on List | Not on List | 13 | Each | 77.85 | 1012.05 | Concrete Drainage | 2019-02-21 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12278-001025 | 12278 | 2019-02-12 07:56 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2019-02-21 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12278-001025 | 12278 | 2019-02-12 07:56 | Section 4 | Material | NULL | Not on List | 1 | Each | 240 | 240 | Concrete Drainage | 2019-02-21 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11908-001025 | 11908 | 2019-02-05 07:55 | Section 4 | Material | Not on List | Not on List | 1 | Each | 97.5 | 97.5 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12571-001025 | 12571 | 2019-02-15 13:57 | Section 3 | Material | Not on List | Not on List | 100 | No | NULL | 0 | Builders Merchants (General) | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12574-001025 | 12574 | 2019-02-15 13:19 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Tanker and disposal | 2617.55 | 2618 | Miscellaneous | 2019-02-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12573-001025 | 12573 | 2019-02-15 13:53 | Core | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Training | 2019-02-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12482-001025 | 12482 | 2019-02-14 13:11 | Section 4 | Material | Not on List | Not on List | 4 | EA | 300 | 1200 | Concrete Accessories | 2019-02-19 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12497-001025 | 12497 | 2019-02-14 15:08 | Section 4 | Material | Not on List | Not on List | 32 | number | 281.9 | 9020.8 | Rebar and Mesh | 2019-03-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12582-001025 | 12582 | 2019-02-15 15:00 | Section 3 | Material | Not on List | Not on List | 25 | no | 8.8 | 220 | Fixings and Fasteners | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 838.26 | 838.26 | PPE | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 519.12 | 519.12 | Small Tools (Consumables) | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 88.92 | 88.92 | Janitorial | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12520-001025 | 12520 | 2019-02-14 18:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 176.25 | 176.25 | Small Tools (Consumables) | 2019-02-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12615-001025 | 12615 | 2019-02-18 08:58 | Core | Material | Not on List | Not on List | 6 | ea | 214.58 | 1287 | Office Supplies | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12615-001025 | 12615 | 2019-02-18 08:58 | Core | Material | Not on List | Not on List | 6 | ea | 89.17 | 535 | Office Supplies | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25536-001025 | 25536 | 2019-10-22 09:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 8 | 40 | Small Tools (Consumables) | 2019-10-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25536-001025 | 25536 | 2019-10-22 09:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 12.1 | 61 | Small Tools (Consumables) | 2019-10-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 15.67 | 31.34 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25246-001025 | 25246 | 2019-10-16 13:55 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Miscellaneous | 2019-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 5.65 | 33.9 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 5.65 | 33.9 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24668-001025 | 24668 | 2019-10-04 15:33 | Core | Material | Not on List | Not on List | 1 | EA | 592.4 | 592.4 | Miscellaneous | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 4.14 | 8.28 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25590-001025 | 25590 | 2019-10-23 07:06 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-25597-001025 | 25597 | 2019-10-23 08:01 | Section 2 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Miscellaneous | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1901 - Protection of Steelwork Against Corrosion | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25598-001025 | 25598 | 2019-10-23 08:01 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 4.14 | 8.28 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25603-001025 | 25603 | 2019-10-23 08:10 | Core | Material | Not on List | Not on List | 1 | Each | 170.5 | 171 | Miscellaneous | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25573-001025 | 25573 | 2019-10-22 16:07 | Section 5 | Material | Combined Drainage | NULL | 1 | SM | 92362.43 | 92362.43 | Miscellaneous | 2019-10-23 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25499-001025 | 25499 | 2019-10-21 16:13 | Section 5 | Material | Combined Drainage | NULL | 1 | SM | 1071.94 | 1071.94 | Builders Merchants (General) | NULL | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | CPM 1200mm Concrete Pipe 2.5m (249379) | 34 | Each | 483.27 | 16431.18 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | CPM 1200mm Concrete Rocker (249380) | 4 | Each | 579.92 | 2319.68 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7043-001008 | 7043 | 2018-09-26 16:50 | Section 4 | Material | Not on List | Not on List | 6 | Each | 49.24 | 295.44 | Aggregate | 2018-10-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | CPM 1200mm Concrete Socket (249381) | 2 | Each | 579.92 | 1159.84 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 2 | Each | 579.92 | 1159.84 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Saint Gobain Castings | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 3 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25618-001025 | 25618 | 2019-10-23 10:08 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 990.59 | 991 | PPE | 2019-10-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7043-001008 | 7043 | 2018-09-26 16:50 | Section 4 | Material | Not on List | Not on List | 6 | Each | 69 | 414 | Aggregate | 2018-10-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25618-001025 | 25618 | 2019-10-23 10:08 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 25.5 | 26 | Janitorial | 2019-10-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25618-001025 | 25618 | 2019-10-23 10:08 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 791.22 | 791 | Small Tools (Consumables) | 2019-10-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25567-001025 | 25567 | 2019-10-22 14:49 | Section 5 | Material | Not on List | NULL | 1 | EA | 176.4 | 176.4 | Miscellaneous | 2019-10-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25442-001025 | 25442 | 2019-10-20 18:33 | Section 5 | Material | Not on List | NULL | 1 | SM | 2815.24 | 2815.24 | Plastic Drainage | 2019-10-25 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1501 - Interface with Existing Communications Network | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25583-001025 | 25583 | 2019-10-22 17:34 | Section 5 | Material | Not on List | NULL | 10 | EA | 156.6 | 1566 | Plastic Drainage | NULL | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25543-001025 | 25543 | 2019-10-22 09:29 | Section 4 | Material | NULL | NULL | 200 | Each | 5.99 | 1198 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25543-001025 | 25543 | 2019-10-22 09:29 | Section 4 | Material | NULL | NULL | 10 | Each | 33.55 | 335.5 | Builders Merchants (General) | 2019-10-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25543-001025 | 25543 | 2019-10-22 09:29 | Section 4 | Material | NULL | NULL | 40 | Each | 2.97 | 118.8 | Builders Merchants (General) | 2019-10-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25543-001025 | 25543 | 2019-10-22 09:29 | Section 4 | Material | NULL | NULL | 14 | Each | 15.75 | 220.5 | Builders Merchants (General) | 2019-10-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25441-001025 | 25441 | 2019-10-20 17:30 | Section 5 | Material | Not on List | NULL | 1 | SM | 5716 | 5716 | Concrete Drainage | 2019-10-25 | 4358007 - EB5/2, Works Access, A14 Eastbound, Just on Jcn 32 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25275-001025 | 25275 | 2019-10-16 17:03 | Section 4 | Material | Not on List | Not on List | 1 | Each | 30000 | 30000 | Miscellaneous | 2019-10-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25276-001025 | 25276 | 2019-10-16 17:09 | Section 4 | Material | Not on List | Not on List | 1 | Each | 15000 | 15000 | Miscellaneous | 2019-10-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25150-001025 | 25150 | 2019-10-16 07:53 | Core | Material | Not on List | Not on List | 1 | Each | NULL | 0 | PPE | 2019-10-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 14 | Each | 23.14 | 323.96 | Plastic Drainage | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 14 | Each | 3.65 | 51.1 | Plastic Drainage | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 42 | Each | 2 | 84 | Plastic Drainage | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Bend 22.5deg (878030) | 3 | Each | 27.62 | 82.86 | Plastic Drainage | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Bend 11.25deg (878029) | 3 | Each | 27.62 | 82.86 | Plastic Drainage | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 1 | Ton | 3.56 | 3.56 | Builders Merchants (General) | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 6 | pairs | NULL | 0 | Builders Merchants (General) | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 4 | pairs | NULL | 0 | Builders Merchants (General) | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 3 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 4 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 2 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 4 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25673-001025 | 25673 | 2019-10-24 11:02 | Section 2 | Material | Not on List | Not on List | 20 | Rolls | NULL | 0 | Builders Merchants (General) | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25114-001025 | 25114 | 2019-10-15 13:24 | Core | Material | Not on List | Not on List | 20 | Box 10 | 29.73 | 594.6 | PPE | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25476-001025 | 25476 | 2019-10-21 13:52 | Core | Material | PPE, Small Tools and Consumables | Not on List | 32 | Each | 28.8 | 921.6 | PPE | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25676-001025 | 25676 | 2019-10-24 11:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25539-001025 | 25539 | 2019-10-22 10:28 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25510-001025 | 25510 | 2019-10-21 17:14 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25504-001025 | 25504 | 2019-10-21 16:44 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 694.1 | 694.1 | Small Tools (Consumables) | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25561-001025 | 25561 | 2019-10-22 12:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 5.97 | 119.4 | Janitorial | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25561-001025 | 25561 | 2019-10-22 12:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 23.61 | 236.1 | Janitorial | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25561-001025 | 25561 | 2019-10-22 12:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 24 | NULL | 3.15 | 75.6 | Janitorial | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25608-001025 | 25608 | 2019-10-23 08:53 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1783.06 | 1783.06 | PPE | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25614-001025 | 25614 | 2019-10-23 09:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | NULL | 5.82 | 46.56 | Small Tools (Consumables) | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25614-001025 | 25614 | 2019-10-23 09:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3 | NULL | 13.19 | 39.57 | Small Tools (Consumables) | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25614-001025 | 25614 | 2019-10-23 09:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 3.55 | 71 | Small Tools (Consumables) | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25677-001025 | 25677 | 2019-10-24 11:39 | Section 4 | Material | NULL | NULL | 200 | Each | 16.57 | 3314 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7108-001020 | 7108 | 2018-09-27 17:14 | Section 3 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 1000 | Each | 0.54 | 540 | Miscellaneous | 2018-10-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25591-001025 | 25591 | 2019-10-23 07:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 58.8 | 58.8 | Miscellaneous | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | Not on List | 1 | Each | 0 | 0 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1500x1000 D/S (991900) | 1 | Each | 121.25 | 121.25 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1500X500 D/S (991898) | 1 | Each | 80.51 | 80.51 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7109-001020 | 7109 | 2018-09-27 17:19 | Section 3 | Material | Not on List | Not on List | 10 | Rolls | 32.5 | 325 | Builders Merchants (General) | 2018-10-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 1 | Each | 81.96 | 81.96 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 1 | Each | 53.01 | 53.01 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 1 | Each | 36.62 | 36.62 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25631-001 | 25631 | 2019-10-23 14:05 | Section 3 | Material | Not on List | Not on List | 1 | ea | 166.23 | 166.23 | Concrete Drainage | 2019-10-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25674-001025 | 25674 | 2019-10-24 11:06 | Section 2 | Material | Aggregate | 6G | 100 | Tonnes | 22 | 2200 | Aggregate | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7074-001008 | 7074 | 2018-09-27 08:14 | Section 3 | Material | Concrete Drainage | Not on List | 50 | NULL | 1308 | 65400 | Concrete Drainage | 2018-10-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25738-001025 | 25738 | 2019-10-25 10:37 | Core | Material | Not on List | Not on List | 1 | SM | 960 | 960 | Office Supplies | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25747-001025 | 25747 | 2019-10-25 12:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 90 | 90 | Professional Services | 2019-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1901 - Protection of Steelwork Against Corrosion | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7089-001020 | 7089 | 2018-09-27 12:53 | Section 3 | Material | Not on List | Not on List | 1 | EA | 3993.83 | 3993.83 | Damage Charges | 2018-09-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25672-001025 | 25672 | 2019-10-24 10:49 | Section 4 | Material | NULL | NULL | 4 | Each | 36.36 | 145.44 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25672-001025 | 25672 | 2019-10-24 10:49 | Section 4 | Material | NULL | NULL | 1 | Each | 142.26 | 142.26 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25697-001025 | 25697 | 2019-10-24 14:52 | Section 4 | Material | NULL | NULL | 20 | Each | 31.63 | 632.6 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25697-001025 | 25697 | 2019-10-24 14:52 | Section 4 | Material | NULL | NULL | 65 | Each | 41.2 | 2678 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25697-001025 | 25697 | 2019-10-24 14:52 | Section 4 | Material | NULL | NULL | 20 | Each | 41.2 | 824 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25736-001025 | 25736 | 2019-10-25 10:06 | Section 6 | Material | Bagged | Not on List | 4 | each | NULL | 0 | Builders Merchants (General) | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25736-001025 | 25736 | 2019-10-25 10:06 | Section 6 | Material | Bagged | Building Sand 25kg Bag (996239) | 4 | Each | 1.8 | 7.2 | Builders Merchants (General) | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25736-001025 | 25736 | 2019-10-25 10:06 | Section 6 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 5 | Each | 3.56 | 17.8 | Builders Merchants (General) | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25736-001025 | 25736 | 2019-10-25 10:06 | Section 6 | Material | Twinwall | Polyipipe 150mm Ridgidrain Bend 90deg (878001) | 2 | Each | 8.25 | 16.5 | Plastic Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25736-001025 | 25736 | 2019-10-25 10:06 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain Bend 90deg (878034) | 2 | Each | 27.62 | 55.24 | Plastic Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7089-001020 | 7089 | 2018-09-27 12:53 | Section 3 | Material | Not on List | Not on List | 1 | EA | 218.19 | 218.19 | Damage Charges | 2018-09-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25703-001025 | 25703 | 2019-10-24 15:54 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2019-10-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25710-001025 | 25710 | 2019-10-24 17:11 | Section 3 | Material | Not on List | Not on List | 1 | ea | 67.5 | 67.5 | NULL | 2019-10-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25710-001025 | 25710 | 2019-10-24 17:11 | Section 3 | Material | Not on List | Not on List | 1 | ea | 485 | 485 | Fixings and Fasteners | 2019-10-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25763-001025 | 25763 | 2019-10-25 15:14 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | ea | 22.85 | 69 | Small Tools (Consumables) | 2019-10-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 100 | Each | 11.34 | 1134 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7089-001020 | 7089 | 2018-09-27 12:53 | Section 3 | Material | Not on List | Not on List | 1 | EA | 54.76 | 54.76 | Damage Charges | 2018-09-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 300 | Each | 1.99 | 597 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 150 | Each | 0.92 | 138 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 180 | Each | 24.99 | 4498.2 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 200 | Each | 3.65 | 730 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 400 | Each | 2.01 | 804 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 160 | Each | 37.6 | 6016 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 200 | Each | 7.03 | 1406 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 400 | Each | 2.97 | 1188 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 200 | Each | 130.26 | 26052 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 20 | Each | 147.69 | 2953.8 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7089-001020 | 7089 | 2018-09-27 12:53 | Section 3 | Material | Not on List | Not on List | 1 | CREDIT | 497.76 | 497.76 | Damage Charges | 2018-09-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25731-001025 | 25731 | 2019-10-25 09:42 | Section 6 | Material | Not on List | Not on List | 50 | Tonne | 538 | 26900 | Rebar and Mesh | 2019-11-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25731-001025 | 25731 | 2019-10-25 09:42 | Section 6 | Material | NULL | Not on List | 200 | Each | 2 | 400 | Rebar and Mesh | 2019-11-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25770-001025 | 25770 | 2019-10-25 17:06 | Section 3 | Material | Aggregate | Type 1 | 400 | Tonnes | 21.65 | 8660 | Aggregate | 2019-10-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-25605-001025 | 25605 | 2019-10-23 08:22 | Section 4 | Material | NULL | NULL | 40 | Each | 12.5 | 500 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25786-001025 | 25786 | 2019-10-28 08:59 | Section 5 | Material | Timber | NULL | 100 | EA | 32.95 | 3295 | Not Sure | 2019-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25786-001025 | 25786 | 2019-10-28 08:59 | Section 5 | Material | Timber | NULL | 50 | EA | 15.95 | 797.5 | Not Sure | 2019-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25786-001025 | 25786 | 2019-10-28 08:59 | Section 5 | Material | Timber | NULL | 500 | MTRS | 0.65 | 325 | Not Sure | 2019-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25789-001025 | 25789 | 2019-10-28 09:28 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1453.2 | Each | 1 | 1453.2 | PPE | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 6 | Each | 50.92 | 305.52 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28804-001025 | 28804 | 2020-02-03 15:13 | Section 5 | Material | Not on List | Not on List | 16.592 | m2 | 54 | 895.97 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28804-001025 | 28804 | 2020-02-03 15:13 | Section 5 | Material | Not on List | Not on List | 2 | Roll | 16.18 | 32.36 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28804-001025 | 28804 | 2020-02-03 15:13 | Section 5 | Material | NULL | NULL | 8 | Roll | 9.62 | 76.96 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28804-001025 | 28804 | 2020-02-03 15:13 | Section 5 | Material | NULL | NULL | 1 | Each | 75 | 75 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28804-001025 | 28804 | 2020-02-03 15:13 | Section 5 | Material | NULL | NULL | 1 | Each | 300 | 300 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28784-001025 | 28784 | 2020-02-03 10:51 | Section 4 | Material | Not on List | Not on List | 384 | Each | 3.52 | 1351.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 8 | Each | 43.16 | 345.28 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28784-001025 | 28784 | 2020-02-03 10:51 | Section 4 | Material | Not on List | Not on List | 384 | Each | 4.59 | 1762.56 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28886-001025 | 28886 | 2020-02-05 16:22 | Section 4 | Material | Aggregate | Not on List | 20 | Tonne | 18.5 | 370 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28436-001025 | 28436 | 2020-01-23 12:43 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1396 | 1396 | Professional Services | 2020-01-27 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28918-001025 | 28918 | 2020-02-06 11:56 | Core | Material | Not on List | Not on List | 1 | ea | 933.22 | 933 | Training | 2020-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-28604-001025 | 28604 | 2020-01-28 17:37 | Section 5 | Material | Not on List | Not on List | 1 | Each | 236.42 | 236.42 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28881-001025 | 28881 | 2020-02-05 12:43 | Section 4 | Material | Not on List | Not on List | 300 | Each | 3.97 | 1191 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28928-001025 | 28928 | 2020-02-06 14:43 | Section 5 | Material | Not on List | Not on List | 12 | no. | NULL | 0 | Builders Merchants (General) | 2020-02-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28928-001025 | 28928 | 2020-02-06 14:43 | Section 5 | Material | Not on List | Not on List | 10 | no. | NULL | 0 | Builders Merchants (General) | 2020-02-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 49.62 | 50 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 105.03 | 105 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-5218-00139 | 5218 | 2018-08-16 11:54 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-08-29 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 10 | Each | 35.52 | 355.2 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 40.67 | 41 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 2254.45 | 2254 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 82.78 | 83 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 37.5 | 38 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 0 | NULL | NULL | 0 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28969-001025 | 28969 | 2020-02-07 09:48 | Section 2 | Material | Waste Management | Not on List | 1 | each | 750 | 750 | Waste (General) | 2020-02-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-28971-001025 | 28971 | 2020-02-07 10:08 | Core | Material | Not on List | Not on List | 1 | NULL | 50 | 50 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-28972-001025 | 28972 | 2020-02-07 10:27 | Core | Material | Not on List | Not on List | 1 | NULL | 802.25 | 802 | Miscellaneous | 2019-06-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-28974-001025 | 28974 | 2020-02-07 10:59 | Core | Material | Not on List | Not on List | 1 | NULL | 49.99 | 50 | Miscellaneous | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-28897 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 65 | Each | 19.61 | 1274.65 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | NULL | NULL | NULL
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 14 | Each | 47.04 | 658.56 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28897-001025 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Bend 30deg (877999) | 65 | Each | 17.03 | 1106.95 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28897-001025 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Bend 45deg (878000) | 65 | Each | 17.03 | 1106.95 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28897-001025 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Bend 15deg (877998) | 65 | Each | 17.03 | 1106.95 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28897-001025 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Not on List | Not on List | 65 | Each | 3.15 | 204.75 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28897-001025 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Not on List | Not on List | 130 | Each | 1.55 | 201.5 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 32 | Each | 16.49 | 527.68 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 16 | Each | 74.3 | 1188.8 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 4 | Each | 99 | 396 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5223-00140 | 5223 | 2018-08-16 12:16 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2018-08-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7265-001022 | 7265 | 2018-10-02 09:27 | Section 3 | Material | Not on List | Not on List | 2 | per day | 316.8 | 633.6 | Miscellaneous | 2018-10-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7412-001022 | 7412 | 2018-10-04 17:26 | Section 3 | Material | Not on List | Not on List | 5 | Number | 42.45 | 212.25 | Concrete Accessories | 2018-10-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN07 - B1043 Offord Road Overbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7346-001022 | 7346 | 2018-10-03 11:37 | Section 3 | Material | Not on List | Not on List | 1 | EA | 90 | 90 | Damage Charges | 2018-10-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7402-001022 | 7402 | 2018-10-04 14:58 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 687.5 | Plastic Drainage | 2018-10-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5122-0045 | 5122 | 2018-08-15 09:11 | Section 4 | Material | Not on List | NULL | 4 | Each | 15.47 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7401-001022 | 7401 | 2018-10-04 14:26 | Section 4 | Material | Not on List | Not on List | 6 | Each | 485 | 2910 | Fixings and Fasteners | 2018-10-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7401-001022 | 7401 | 2018-10-04 14:26 | Section 4 | Material | NULL | NULL | 1 | Each | 195 | 195 | Fixings and Fasteners | 2018-10-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5122-0045 | 5122 | 2018-08-15 09:11 | Section 4 | Material | Not on List | NULL | 4 | Each | 15.47 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6802-001022 | 6802 | 2018-09-20 16:00 | Section 3 | Material | Not on List | Not on List | 20 | no | 5.95 | 119 | Surveying Consumables | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN14 - Hilton Road Overbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 24.12 | 24.12 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 24.12 | 24.12 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 24.12 | 24.12 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 24.12 | 24.12 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 20 | ea | 7.5 | 150 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 66.97 | 66.97 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 66.97 | 66.97 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7512-001022 | 7512 | 2018-10-08 11:30 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 67.9 | 1018.5 | Concrete Drainage | 2018-10-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7512-001022 | 7512 | 2018-10-08 11:30 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 25 | Each | 43.16 | 1079 | Concrete Drainage | 2018-10-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7512-001022 | 7512 | 2018-10-08 11:30 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 50 | Each | 35.52 | 1776 | Concrete Drainage | 2018-10-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7512-001022 | 7512 | 2018-10-08 11:30 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 25 | Each | 47.04 | 1176 | Concrete Drainage | 2018-10-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7512-001022 | 7512 | 2018-10-08 11:30 | Section 4 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 50 | Each | 16.49 | 824.5 | Concrete Drainage | 2018-10-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7426-001022 | 7426 | 2018-10-05 08:51 | Section 4 | Material | Not on List | Not on List | 10 | Each | 42.92 | 429.2 | Concrete Drainage | 2018-10-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7426-001022 | 7426 | 2018-10-05 08:51 | Section 4 | Material | Not on List | Not on List | 3 | Each | 53.28 | 159.84 | Concrete Drainage | 2018-10-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7387-001022 | 7387 | 2018-10-04 11:17 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.45 | 45 | Surveying Consumables | 2018-10-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7514-001022 | 7514 | 2018-10-08 13:22 | Section 4 | Material | NULL | Not on List | 16 | Each | 11.94 | 191.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7577-001023 | 7577 | 2018-10-09 15:12 | Section 4 | Material | Not on List | Not on List | 110 | Each | 3.84 | 422.4 | Timber Products | 2018-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7577-001023 | 7577 | 2018-10-09 15:12 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 0.65 | 650 | Timber Products | 2018-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7577-001023 | 7577 | 2018-10-09 15:12 | Section 4 | Material | Not on List | Not on List | 6 | 1kg Bag 50mm Galv Nails | 3.46 | 20.76 | Timber Products | 2018-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5164-0087 | 5164 | 2018-08-15 13:43 | Section 4 | Material | Not on List | Not on List | 45 | Sheet | 13.44 | 0 | Builders Merchants (General) | 2018-08-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5164-0087 | 5164 | 2018-08-15 13:43 | Section 4 | Material | Not on List | Not on List | 10 | Sheet | 8.47 | 0 | Builders Merchants (General) | 2018-08-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7506-001022 | 7506 | 2018-10-08 09:59 | Section 4 | Material | Not on List | Not on List | 1000 | each | 1.07 | 1070 | Timber Products | 2018-10-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7425-001022 | 7425 | 2018-10-05 08:43 | Section 4 | Material | Not on List | Not on List | 100 | Bag | 8.9 | 890 | Concrete Accessories | 2018-10-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7425-001022 | 7425 | 2018-10-05 08:43 | Section 4 | Material | Not on List | Not on List | 10 | Each | 149.64 | 1496.4 | Concrete Accessories | 2018-10-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7435-001023 | 7435 | 2018-10-05 10:30 | Section 4 | Material | Not on List | Not on List | 51.317 | tonnes | 538 | 27608.55 | Rebar and Mesh | 2018-10-17 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7435-001023 | 7435 | 2018-10-05 10:30 | Section 4 | Material | Not on List | Not on List | 28.947 | tonnes | 538 | 15573.49 | Rebar and Mesh | 2018-10-17 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7223-001021 | 7223 | 2018-10-01 13:58 | Section 4 | Material | Not on List | Not on List | 1 | Each | 689.44 | 689.44 | Damage Charges | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.47 | 47 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 10 | Each | 5.74 | 57.4 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 5 | Each | 18.19 | 90.95 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 5 | Each | 57.92 | 289.6 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 10 | Each | 8.47 | 84.7 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 1 | Each | 149.64 | 149.64 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 5 | Each | 42.45 | 212.25 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7508-001022 | 7508 | 2018-10-08 11:03 | Section 4 | Material | Not on List | Not on List | 1600 | Each | 1.45 | 2320 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7508-001022 | 7508 | 2018-10-08 11:03 | Section 4 | Material | NULL | NULL | 1 | Each | 30 | 30 | Miscellaneous | 2018-10-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 20 | Each | 120.62 | 2412.4 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 30 | Each | 17.45 | 523.5 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 60 | Each | 9.04 | 542.4 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 65 | Each | 34.82 | 2263.3 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 75 | Each | 6.54 | 490.5 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 150 | Each | 2.75 | 412.5 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 20 | Each | 10.5 | 210 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 40 | Each | 1.84 | 73.6 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 80 | Each | 0.85 | 68 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5002-0015 | 5002 | 2018-08-13 15:53 | Section 4 | Material | Not on List | NULL | 240 | square meters | NULL | 0 | Blocks and Bricks | 2018-08-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 20 | Each | 14.4 | 288 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 20 | Each | 44.41 | 888.2 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 40 | Each | 7.64 | 305.6 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 40 | Each | 7.64 | 305.6 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 10 | Each | 19.72 | 197.2 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 14 | Each | 67.9 | 950.6 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 3 | Each | 50.92 | 152.76 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 7 | Each | 43.16 | 302.12 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 4 | Each | 35.52 | 142.08 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 12 | Each | 47.04 | 564.48 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 24 | Each | 16.49 | 395.76 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 12 | Each | 74.3 | 891.6 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7666-001023 | 7666 | 2018-10-11 09:48 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2018-10-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7669-001023 | 7669 | 2018-10-11 11:20 | Section 3 | Material | Not on List | Not on List | 1 | SET | NULL | 0 | Not Sure | 2018-10-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7669-001023 | 7669 | 2018-10-11 11:20 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2018-10-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7620-001023 | 7620 | 2018-10-10 14:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 50.4 | 1008 | Small Tools (Consumables) | 2018-10-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7619-001023 | 7619 | 2018-10-10 14:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | EAch | 6.29 | 905.76 | Miscellaneous | 2018-10-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7559-001023 | 7559 | 2018-10-09 11:39 | Section 3 | Material | Not on List | Not on List | 1 | SUM | 601 | 601 | Timber Products | 2018-10-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7540-001023 | 7540 | 2018-10-09 07:48 | Section 3 | Material | Not on List | Not on List | 10 | No | 19.16 | 191.6 | Builders Merchants (General) | 2018-10-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7571-001023 | 7571 | 2018-10-09 13:51 | Section 3 | Material | Not on List | Not on List | 70 | Tonnes | 538 | 37660 | NULL | 2018-10-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7627-001023 | 7627 | 2018-10-10 15:24 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 6 | Each | 42.94 | 257.64 | Builders Merchants (General) | 2018-10-12 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7504-001022 | 7504 | 2018-10-08 08:52 | Section 4 | Material | Concrete Drainage | Not on List | 1 | Each | 3450 | 3450 | Concrete Drainage | 2018-10-29 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5189-00116 | 5189 | 2018-08-16 07:01 | Section 4 | Material | Not on List | Not on List | 400 | 25m Pack | 12.8 | 0 | Miscellaneous | 2018-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5188-00115 | 5188 | 2018-08-15 18:58 | Section 4 | Material | Not on List | Not on List | 1000 | each | 1.07 | 0 | Timber Products | 2018-08-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7787-001023 | 7787 | 2018-10-15 09:37 | Section 3 | Material | Not on List | Not on List | 23 | EA | 212.4 | 4885.2 | Plastic Drainage | 2018-10-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7787-001023 | 7787 | 2018-10-15 09:37 | Section 3 | Material | Not on List | Not on List | 8 | EA | 12.05 | 96.4 | Plastic Drainage | 2018-10-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7787-001023 | 7787 | 2018-10-15 09:37 | Section 3 | Material | Not on List | Not on List | 44 | EA | 31.98 | 1407.12 | Plastic Drainage | 2018-10-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7646-001023 | 7646 | 2018-10-10 18:30 | Section 3 | Material | Not on List | Not on List | 1 | SM | 173.92 | 173.92 | Small Tools (Consumables) | 2018-10-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7519-001023 | 7519 | 2018-10-08 14:47 | Section 4 | Material | Not on List | Not on List | 15 | Each | 55.5 | 832.5 | Not Sure | 2018-10-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 1 | EA | 29.5 | 29.5 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 2 | EA | 47.5 | 95 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 1 | EA | 125 | 125 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 2 | EA | 125 | 250 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 10 | EA | 38.5 | 385 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | NULL | Not on List | 1 | EA | 125 | 125 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20629-001025 | 20629 | 2019-07-11 15:11 | Section 3 | Material | Not on List | Not on List | 500 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20634-001025 | 20634 | 2019-07-11 15:24 | Section 3 | Material | Aggregate | A10 Pipe Bed | 280 | Tonnes | 16.5 | 4620 | Aggregate | 2019-07-17 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20561-001025 | 20561 | 2019-07-10 14:16 | Core | Material | NULL | NULL | 1 | Each | 822.5 | 822.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5142-0070 | 5142 | 2018-08-15 11:34 | Section 3 | Material | Concrete Drainage | Not on List | 14 | Each | 35.52 | 497.28 | Concrete Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | NULL | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20567-001025 | 20567 | 2019-07-10 14:35 | Section 3 | Material | PPE, Small Tools and Consumables | Sleeve - White C/W Overhead Structures 750mm Csp (204017) | 160 | Each | 2.18 | 348.8 | Miscellaneous | 2019-07-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20621-001025 | 20621 | 2019-07-11 13:45 | Section 3 | Material | Not on List | Not on List | 10 | ea | 286.21 | 2862.1 | Miscellaneous | 2019-07-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | NULL | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20655-001025 | 20655 | 2019-07-11 18:38 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-16 | 1358005 - WB5/7 Works Access - 1356563 - A14 Westbound, On Left between Jcn 32 - 31 | SEC5 - Roadworks | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | NULL | Req - S5 Buyers
MREQ-20465-001025 | 20465 | 2019-07-09 08:53 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-20575-001025 | 20575 | 2019-07-10 15:54 | Section 1 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-07-22 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | NULL | Req - S1 Buyers
MREQ-16878-001025 | 16878 | 2019-05-03 13:12 | Section 3 | Material | Not on List | Not on List | 105 | roll | 111.2 | 11676 | Builders Merchants (General) | 2019-05-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16878-001025 | 16878 | 2019-05-03 13:12 | Section 3 | Material | Not on List | Not on List | 850 | No | 1.65 | 1402.5 | Builders Merchants (General) | 2019-05-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16878-001025 | 16878 | 2019-05-03 13:12 | Section 3 | Material | Not on List | Not on List | 17000 | No | 0.3 | 5100 | Builders Merchants (General) | 2019-05-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16878-001025 | 16878 | 2019-05-03 13:12 | Section 3 | Material | Not on List | Not on List | 1500 | m | 0.15 | 225 | Builders Merchants (General) | 2019-05-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20600-001025 | 20600 | 2019-07-11 08:39 | Section 3 | Material | Not on List | Not on List | 1 | Cartridges | 1146.4 | 1146.4 | Builders Merchants (General) | 2019-07-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20600-001025 | 20600 | 2019-07-11 08:39 | Section 3 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Builders Merchants (General) | 2019-07-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | NULL | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20534-001025 | 20534 | 2019-07-10 09:28 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.9 | 450 | Miscellaneous | 2019-07-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20581-001025 | 20581 | 2019-07-10 17:29 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-07-11 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20687-001025 | 20687 | 2019-07-12 10:13 | Core | Material | Not on List | Not on List | 1 | NULL | 1350 | 1350 | Training | 2019-07-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19986-001025 | 19986 | 2019-07-01 09:38 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | NULL | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 198 | ea | 5.6 | 1108.8 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 2.77 | 182.82 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 4.5 | 297 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 3.35 | 221.1 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 5.01 | 330.66 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 3.67 | 242.22 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 3.91 | 258.06 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20674-001025 | 20674 | 2019-07-12 10:46 | Section 5 | Material | NULL | NULL | 2 | ea | 23.22 | 46.44 | NULL | 2019-07-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5380 | 5380 | 2018-08-20 16:43 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Rebar and Mesh | 2018-08-23 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Coverall Flame Retardent Cotton Saturn Fr Reflective Tape (370522) | 2 | Each | 107.6 | 215 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16567-001025 | 16567 | 2019-04-29 12:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 452.88 | 453 | Small Tools (Consumables) | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-16569-001025 | 16569 | 2019-04-29 12:39 | Section 2 | Material | PPE, Small Tools and Consumables | Towel Hand Pristine Z Fold 2ply White Case 3210 Sheet 66955 (539303) | 20 | Each | 26.89 | 538 | Janitorial | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16569-001025 | 16569 | 2019-04-29 12:39 | Section 2 | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 200sheets 517346 (539288) | 20 | Each | 5.97 | 119 | Janitorial | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 120 | Each | 8.55 | 1026 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 120 | Each | 8.55 | 1026 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-5715-00449 | 5715 | 2018-08-29 06:58 | Section 3 | Material | Not on List | Not on List | 1 | No | 2700 | 2700 | Not Sure | 2018-08-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 240 | NULL | NULL | 0 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 240 | NULL | NULL | 0 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | Tissues Uvex Cleaning Box Of 450 Sheets Ref 9991-000 (430589) | 10 | Each | 3.3 | 33 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16090-001025 | 16090 | 2019-04-17 17:12 | Section 4 | Material | NULL | Not on List | 10 | EA | 43.57 | 435.7 | Builders Merchants (General) | 2019-04-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16327-001025 | 16327 | 2019-04-24 15:25 | Section 4 | Material | Not on List | Not on List | 100 | Each | 58 | 5800 | Concrete Drainage | 2019-05-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16327-001025 | 16327 | 2019-04-24 15:25 | Section 4 | Material | Not on List | Not on List | 20 | Each | 62 | 1240 | Concrete Drainage | 2019-05-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16327-001025 | 16327 | 2019-04-24 15:25 | Section 4 | Material | NULL | Not on List | 80 | Each | 60 | 4800 | Concrete Drainage | 2019-05-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16327-001025 | 16327 | 2019-04-24 15:25 | Section 4 | Material | NULL | Not on List | 1 | Each | 500 | 500 | Concrete Drainage | 2019-05-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15778-001025 | 15778 | 2019-04-12 14:02 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 21.41 | 42.82 | Laboratory Equipment / Certification | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6373-00677 | 6373 | 2018-09-12 08:07 | Section 3 | Material | Not on List | Not on List | 20 | 10 ltr drums | NULL | 0 | Miscellaneous | 2018-09-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | CL3B - Structures (Culverts) 3B | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16588-001025 | 16588 | 2019-04-29 15:21 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2901.3 | 2901 | Small Tools (Consumables) | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-16590-001025 | 16590 | 2019-04-29 15:16 | Section 2 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 300mm X 4.8mm Pack Of 100 Spartan (230061) | 50 | Each | 1.94 | 97 | Small Tools (Consumables) | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16590-001025 | 16590 | 2019-04-29 15:16 | Section 2 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 370mm X 7.6mm Pack Of 100 Spartan (230065) | 50 | Each | 3.88 | 194 | Small Tools (Consumables) | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16593-001025 | 16593 | 2019-04-29 15:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 303.87 | 304 | PPE | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-16313-001025 | 16313 | 2019-04-24 13:15 | Section 4 | Material | Not on List | Not on List | 200 | Each | 1.19 | 238 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16313-001025 | 16313 | 2019-04-24 13:15 | Section 4 | Material | Not on List | NULL | 3 | Box 10 | 50.43 | 151.29 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16313-001025 | 16313 | 2019-04-24 13:15 | Section 4 | Material | Not on List | NULL | 3 | Box 10 | 43.69 | 131.07 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16313-001025 | 16313 | 2019-04-24 13:15 | Section 4 | Material | Not on List | Not on List | 3 | Box 10 | 33.64 | 100.92 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16345-001025 | 16345 | 2019-04-24 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 361.76 | 361.76 | Small Tools (Consumables) | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16535-001025 | 16535 | 2019-04-29 07:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 770 | 770 | Miscellaneous | 2019-04-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16347-001025 | 16347 | 2019-04-24 16:54 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2869.68 | 2869.68 | PPE | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16416-001025 | 16416 | 2019-04-25 13:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1519 | 1519 | Laboratory Equipment / Certification | 2019-04-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16638-001025 | 16638 | 2019-04-30 10:20 | Section 2 | Material | Not on List | Not on List | 100 | Lengths | NULL | 0 | Concrete Accessories | 2019-04-30 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15103-001025 | 15103 | 2019-04-02 09:48 | Section 4 | Material | Not on List | Not on List | 77 | Rolls | 49.5 | 3811.5 | Fixings and Fasteners | 2019-05-03 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-14851-001025 | 14851 | 2019-03-28 10:37 | Section 4 | Material | Not on List | Not on List | 40 | Each | 49.91 | 1996.4 | Miscellaneous | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14851-001025 | 14851 | 2019-03-28 10:37 | Section 4 | Material | Not on List | Not on List | 100 | Each | 9.58 | 958 | Miscellaneous | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16656-001025 | 16656 | 2019-04-30 13:59 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16659-001025 | 16659 | 2019-04-30 14:23 | Section 4 | Material | Not on List | Not on List | 3200 | Each | 1 | 3200 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 7 | Each | 67.9 | 475 | Concrete Drainage | 2019-05-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 3 | Each | 35.52 | 107 | Concrete Drainage | 2019-05-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 7 | Each | 47.04 | 329 | Concrete Drainage | 2019-05-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 4 | Each | 43.16 | 173 | Concrete Drainage | 2019-04-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Perf (346338) | 50 | Each | 10.66 | 533 | Plastic Drainage | 2019-04-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 90 | Each | 23.14 | 2083 | Plastic Drainage | 2019-05-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Twinwall | Not on List | 10 | Each | NULL | 0 | Plastic Drainage | 2019-05-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16062-001025 | 16062 | 2019-04-16 15:52 | Section 4 | Material | Not on List | Not on List | 47 | Each | 28 | 1316 | Miscellaneous | 2019-05-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16062-001025 | 16062 | 2019-04-16 15:52 | Section 4 | Material | Not on List | Not on List | 2 | Each | 45 | 90 | Miscellaneous | 2019-05-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16062-001025 | 16062 | 2019-04-16 15:52 | Section 4 | Material | NULL | Not on List | 1 | Each | 97 | 97 | Miscellaneous | 2019-05-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16062-001025 | 16062 | 2019-04-16 15:52 | Section 4 | Material | NULL | Not on List | 6 | Each | 38 | 228 | Miscellaneous | 2019-05-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16062-001025 | 16062 | 2019-04-16 15:52 | Section 4 | Material | NULL | Not on List | 1 | Each | 125 | 125 | Miscellaneous | 2019-05-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | Not on List | Not on List | 230 | Each | 11.51 | 2647.3 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 260 | Each | 1.98 | 514.8 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 520 | Each | 0.91 | 473.2 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | Not on List | Not on List | 24 | Each | 34.6 | 830.4 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 36 | Each | 7.06 | 254.16 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 72 | Each | 2.97 | 213.84 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | Not on List | Not on List | 20 | Each | 164.37 | 3287.4 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | Not on List | Not on List | 20 | Each | 164.37 | 3287.4 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | Not on List | Not on List | 30 | Each | 42.87 | 1286.1 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16482-001025 | 16482 | 2019-04-26 11:47 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 40 | Each | 52.77 | 2110.8 | Plastic Drainage | 2019-04-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16482-001025 | 16482 | 2019-04-26 11:47 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 80 | Each | 2.97 | 237.6 | Plastic Drainage | 2019-04-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6393-00687 | 6393 | 2018-09-12 10:50 | Section 3 | Material | Plastic Drainage | Not on List | 5 | No | 27.92 | 139.6 | Plastic Drainage | 2018-09-14 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16592-001025 | 16592 | 2019-04-29 15:12 | Section 3 | Material | Aggregate | Not on List | 150 | m3 | 47.05 | 7057.5 | Aggregate | 2019-04-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 10 | Each | 166.43 | 1664 | Plastic Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Twinwall | Not on List | 84 | Each | NULL | 0 | Plastic Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Twinwall | Not on List | 30 | Each | NULL | 0 | Plastic Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 6 | Each | 47.04 | 282 | Concrete Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 9 | Each | 67.9 | 611 | Concrete Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 1 | Each | 50.92 | 51 | Concrete Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 2 | Each | 43.16 | 86 | Concrete Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 1 | Each | 35.52 | 36 | Concrete Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16684-001025 | 16684 | 2019-04-30 17:56 | Section 5 | Material | Twinwall | Not on List | 62 | No | NULL | 0 | Plastic Drainage | 2019-05-09 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16684-001025 | 16684 | 2019-04-30 17:56 | Section 5 | Material | Twinwall | Not on List | 10 | No | NULL | 0 | Plastic Drainage | 2019-05-09 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16684-001025 | 16684 | 2019-04-30 17:56 | Section 5 | Material | Twinwall | Not on List | 20 | No | NULL | 0 | Plastic Drainage | 2019-05-09 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16684-001025 | 16684 | 2019-04-30 17:56 | Section 5 | Material | Twinwall | Not on List | 90 | No | NULL | 0 | Plastic Drainage | 2019-05-09 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16674-001025 | 16674 | 2019-04-30 17:02 | Section 3 | Material | Not on List | Not on List | 100 | ea | 2.81 | 281 | Fuel | 2019-05-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16705-001025 | 16705 | 2019-05-01 09:07 | Section 4 | Material | Not on List | Not on List | 24 | Each | 1 | 24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16714-001025 | 16714 | 2019-05-01 10:35 | Core | Material | Not on List | Not on List | 1 | £ | 900 | 900 | Miscellaneous | 2019-05-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 16 | NULL | 85.23 | 1363.68 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 7 | NULL | NULL | 0 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 9 | NULL | NULL | 0 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 49 | NULL | NULL | 0 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 49 | NULL | NULL | 0 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 1 | NULL | 113.55 | 113.55 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 1 | NULL | 79.78 | 79.78 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 3 | NULL | 126.1 | 378.3 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 1 | NULL | 94.57 | 94.57 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16718-001025 | 16718 | 2019-05-01 11:27 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16725-001025 | 16725 | 2019-05-01 13:12 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 780 | Each | 4.59 | 3580.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-02 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 32 | Each | 3.03 | 96.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-02 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 920 | Each | 1.5 | 1380 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 400 | NULL | 24.09 | 9636 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 408 | Each | 17.3 | 7058.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 4 | Each | 355.81 | 1423.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 4 | Each | 50.98 | 203.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 4 | Each | 279.41 | 1117.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 3 | Each | 126.04 | 378.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 59.45 | 59.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 13.08 | 13.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16736-001025 | 16736 | 2019-05-01 14:21 | Section 4 | Material | Not on List | Not on List | 30 | EA | 5.33 | 159.9 | NULL | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4B - Structures (Culverts) 4B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16736-001025 | 16736 | 2019-05-01 14:21 | Section 4 | Material | Not on List | Not on List | 30 | EA | 0.15 | 4.5 | NULL | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4B - Structures (Culverts) 4B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16325-001025 | 16325 | 2019-04-24 14:39 | Section 4 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 520 | Each | 3.52 | 1830.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16325-001025 | 16325 | 2019-04-24 14:39 | Section 4 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 600 | Each | 1.5 | 900 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16325-001025 | 16325 | 2019-04-24 14:39 | Section 4 | Material | NULL | Concrete Kerbs 125x150x914 BN Straight (753034) | 100 | Each | 3.03 | 303 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16325-001025 | 16325 | 2019-04-24 14:39 | Section 4 | Material | NULL | NULL | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16325-001025 | 16325 | 2019-04-24 14:39 | Section 4 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16516-001025 | 16516 | 2019-04-26 15:51 | Section 3 | Material | Not on List | Not on List | 16 | No. | 34.93 | 558.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16516-001025 | 16516 | 2019-04-26 15:51 | Section 3 | Material | Not on List | Not on List | 26 | No. | 182.61 | 4747.86 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16516-001025 | 16516 | 2019-04-26 15:51 | Section 3 | Material | Not on List | Not on List | 12 | No. | 38.85 | 466.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16769-001025 | 16769 | 2019-05-02 07:40 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Fixings and Fasteners | 2019-05-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16681-001025 | 16681 | 2019-04-30 17:44 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (General) | 2019-05-01 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16712-001025 | 16712 | 2019-05-01 09:54 | Section 4 | Material | Not on List | Not on List | 1500 | EA | 1.34 | 2010 | Miscellaneous | 2019-05-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16739-001025 | 16739 | 2019-05-01 14:31 | Section 4 | Material | Not on List | Not on List | 6 | EA | 650 | 3900 | Miscellaneous | 2019-05-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16748-001025 | 16748 | 2019-05-01 15:44 | Section 3 | Material | PPE, Small Tools and Consumables | Safety Goal Post System Sgps01 (203013) | 15 | Each | 285 | 4275 | Miscellaneous | 2019-05-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16800-001025 | 16800 | 2019-05-02 10:31 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 750 | 750 | Surveying Consumables | 2019-05-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16814-001025 | 16814 | 2019-05-02 11:48 | Section 2 | Material | Not on List | Not on List | 1 | each | 1861 | 1861 | Tanks and Interceptors | 2019-05-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16805-001025 | 16805 | 2019-05-02 10:41 | Section 3 | Material | Not on List | Not on List | 32 | Units | 38.76 | 1240.32 | Miscellaneous | 2019-05-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16805-001025 | 16805 | 2019-05-02 10:41 | Section 3 | Material | Not on List | Not on List | 4 | Units | 44.38 | 177.52 | Miscellaneous | 2019-05-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16805-001025 | 16805 | 2019-05-02 10:41 | Section 3 | Material | Not on List | Not on List | 8 | Units | 95 | 760 | Miscellaneous | 2019-05-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16831-001025 | 16831 | 2019-05-02 15:52 | Section 4 | Material | Bagged | Not on List | 1 | Pallet | NULL | 0 | Builders Merchants (General) | 2019-05-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1103 - Linear Drainage Channel Systems | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 100 | Each | 35.59 | 3559 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 2 | Each | 38.85 | 77.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 5 | Each | 250.64 | 1253.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5432-00279 | 5432 | 2018-08-21 12:34 | Section 4 | Material | Not on List | Not on List | 230.88 | m2 | 66.73 | 15406.62 | Not Sure | 2018-10-08 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20735-001025 | 20735 | 2019-07-15 06:58 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5432-00279 | 5432 | 2018-08-21 12:34 | Section 4 | Material | Not on List | Not on List | 189.365 | m2 | 66.57 | 12606.03 | Not Sure | 2018-10-08 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20746-001025 | 20746 | 2019-07-15 09:27 | Core | Material | Not on List | Not on List | 1 | NULL | 1350 | 1350 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20658-001025 | 20658 | 2019-07-12 07:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2019-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19393-001025 | 19393 | 2019-06-19 15:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 74 | 74 | Miscellaneous | 2019-06-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20640-001025 | 20640 | 2019-07-11 16:37 | Core | Material | NULL | NULL | 1 | Each | 92.4 | 92.4 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 4 | ea | 178.81 | 715 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 10 | ea | 43.05 | 431 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 1 | ea | 288 | 288 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5437-00281 | 5437 | 2018-08-21 13:45 | Section 4 | Material | Plastic Drainage | P/Pipe 100Mm X 100Mtr Linflex 100 | 30 | Each | 175 | 5250 | Plastic Drainage | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 6 | ea | 16.16 | 97 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 6 | ea | 6.83 | 41 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 6 | ea | 2.49 | 15 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 5 | ea | 76 | 380 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20764-001025 | 20764 | 2019-07-15 13:01 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20778-001025 | 20778 | 2019-07-15 14:50 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20783-001025 | 20783 | 2019-07-15 15:21 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5439-00282 | 5439 | 2018-08-21 13:48 | Section 4 | Material | Not on List | Not on List | 645 | Each | 4.43 | 2857.35 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19997-001025 | 19997 | 2019-07-01 11:28 | Core | Material | NULL | NULL | 25 | Each | 36.94 | 923.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20789-001025 | 20789 | 2019-07-15 15:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20791-001025 | 20791 | 2019-07-15 16:30 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20798-001025 | 20798 | 2019-07-15 17:28 | Section 3 | Material | Not on List | Not on List | 500 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-23 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 55 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 65 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 10 | Each | 10.5 | 105 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-5439-00282 | 5439 | 2018-08-21 13:48 | Section 4 | Material | Not on List | Not on List | 1344 | Each | 3.4 | 4569.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Twinwall | Polyipipe 150mm Ridgidrain Bend 90deg (878001) | 10 | Each | 8.25 | 83 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Bend 45deg (878000) | 10 | Each | 8.25 | 83 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 38 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 38 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 20 | Each | 0.91 | 18 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 10 | Each | 1.98 | 20 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-5142-0070 | 5142 | 2018-08-15 11:34 | Section 3 | Material | Concrete Drainage | Not on List | 35 | Each | 16.49 | 577.15 | Concrete Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5439-00282 | 5439 | 2018-08-21 13:48 | Section 4 | Material | NULL | NULL | 5 | Each | 30 | 150 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20787-001025 | 20787 | 2019-07-15 15:11 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20817-001025 | 20817 | 2019-07-16 09:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | NULL | NULL | 0 | PPE | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-20823-001025 | 20823 | 2019-07-16 10:25 | Section 2 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 3000 | Each | 0.37 | 1110 | Builders Merchants (General) | 2019-07-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20823-001025 | 20823 | 2019-07-16 10:25 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196 | Builders Merchants (General) | 2019-07-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20823-001025 | 20823 | 2019-07-16 10:25 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 80 | Each | 3.56 | 285 | Builders Merchants (General) | 2019-07-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20823-001025 | 20823 | 2019-07-16 10:25 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-07-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20828-001025 | 20828 | 2019-07-16 11:14 | Core | Material | PPE, Small Tools and Consumables | Not on List | 215.18 | each | 1 | 215 | Miscellaneous | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20834-001025 | 20834 | 2019-07-16 12:14 | Section 5 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-18 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5459-00296 | 5459 | 2018-08-21 12:27 | Section 4 | Material | Plastic Drainage | Not on List | 16 | Each | 45.37 | 725.92 | Plastic Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20405-001025 | 20405 | 2019-07-08 13:51 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 0.9 | 900 | Timber Products | 2019-07-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 5 | EA | 173.24 | 866.2 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | Concrete Drainage | Not on List | 1 | Each | 122.16 | 122.16 | Concrete Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 1 | EA | 39.41 | 39.41 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 1 | EA | 39.41 | 39.41 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 9 | EA | 24.3 | 218.7 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 14 | EA | 18.4 | 257.6 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 3 | EA | 3.13 | 9.39 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 14 | EA | 6.05 | 84.7 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 1 | EA | 22.8 | 22.8 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20857-001025 | 20857 | 2019-07-16 16:25 | Section 3 | Material | Not on List | Not on List | 2000 | No | NULL | 0 | Builders Merchants (General) | 2019-07-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | Concrete Drainage | Not on List | 1 | Each | 91.61 | 91.61 | Concrete Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20869-001025 | 20869 | 2019-07-16 17:35 | Section 5 | Material | Not on List | Not on List | 50 | number | NULL | 0 | Builders Merchants (General) | 2019-07-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20836-001025 | 20836 | 2019-07-16 12:22 | Section 3 | Material | Not on List | Not on List | 1 | ea | 6076.8 | 6076.8 | Miscellaneous | 2019-07-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20838-001025 | 20838 | 2019-07-16 12:53 | Section 6 | Material | Aggregate | Class 1A | 5000 | Tonnes | 12.5 | 62500 | Aggregate | 2019-07-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20891-001025 | 20891 | 2019-07-17 09:27 | Section 4 | Material | Not on List | Not on List | 1 | Number | 8950 | 8950 | Surveying Consumables | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-20897-001025 | 20897 | 2019-07-17 10:09 | Core | Material | Not on List | Not on List | 1 | number | 42 | 42 | Surveying Consumables | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20897-001025 | 20897 | 2019-07-17 10:09 | Core | Material | Not on List | Not on List | 10 | packs | 15 | 150 | Surveying Consumables | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20897-001025 | 20897 | 2019-07-17 10:09 | Core | Material | Not on List | Not on List | 10 | packs | 15 | 150 | Surveying Consumables | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | Concrete Drainage | Not on List | 3 | Each | 79.28 | 237.84 | Concrete Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20897-001025 | 20897 | 2019-07-17 10:09 | Core | Material | Not on List | Not on List | 10 | packs | 15 | 150 | Surveying Consumables | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20899-001025 | 20899 | 2019-07-17 10:29 | Section 4 | Material | Not on List | Not on List | 600 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22138-001025 | 22138 | 2019-08-12 09:35 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 3194.21 | 3194 | Miscellaneous | 2019-08-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22140-001025 | 22140 | 2019-08-12 10:12 | Core | Material | Not on List | Not on List | 1 | NULL | 6620.59 | 6621 | Professional Services | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-5824-00514 | 5824 | 2018-08-30 16:28 | Section 4 | Material | Not on List | Not on List | 60 | Each | 4.55 | 273 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22143-001025 | 22143 | 2019-08-12 10:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | 10 | 40 | Surveying Consumables | 2019-08-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22143-001025 | 22143 | 2019-08-12 10:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 0.1 | 1 | Surveying Consumables | 2019-08-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Timber | Not on List | 100 | EA | 32.95 | 3295 | Timber Products | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Timber | Not on List | 150 | EA | 7.23 | 1084.5 | Timber Products | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Timber | Not on List | 86.4 | MT | 1.85 | 159.84 | Timber Products | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Bagged | Not on List | 1 | BG | 6 | 6 | Builders Merchants (General) | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Bagged | Not on List | 1 | BG | 6.5 | 6.5 | Builders Merchants (General) | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Not on List | Not on List | 1 | SM | 459.96 | 459.96 | Concrete Accessories | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5829-00519 | 5829 | 2018-08-30 15:45 | Section 4 | Material | Not on List | Not on List | 14.311 | Tonnes | 538 | 7699.32 | Rebar and Mesh | 2018-09-13 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21944-001025 | 21944 | 2019-08-07 13:14 | Section 3 | Material | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 32 | Each | 3.03 | 96.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22057-001025 | 22057 | 2019-08-09 10:06 | Core | Material | Not on List | Not on List | 1 | SM | 334.43 | 334.43 | Not Sure | 2019-08-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22058-001025 | 22058 | 2019-08-09 10:09 | Core | Material | Not on List | Not on List | 1 | SM | 500 | 500 | Miscellaneous | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22112-001025 | 22112 | 2019-08-11 14:13 | Section 5 | Material | Twinwall | Not on List | 1 | SM | 734.66 | 734.66 | Plastic Drainage | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5829-00519 | 5829 | 2018-08-30 15:45 | Section 4 | Material | Not on List | Not on List | 14.313 | Tonnes | 538 | 7700.39 | Rebar and Mesh | 2018-09-13 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN20 - Bar Hill Junction West Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22158-001025 | 22158 | 2019-08-12 12:24 | Section 2 | Material | Not on List | Not on List | 1 | no | NULL | 0 | Miscellaneous | 2019-08-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 215 | Each | 3.52 | 756.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Not on List | 6 | Each | 13.78 | 82.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 3 | Each | 10.35 | 31.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 3 | Each | 10.35 | 31.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 3 | Each | 5.44 | 16.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 3 | Each | 5.44 | 16.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 7 | Each | 5.44 | 38.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5829-00519 | 5829 | 2018-08-30 15:45 | Section 4 | Material | Not on List | Not on List | 14.311 | Tonnes | 538 | 7699.32 | Rebar and Mesh | 2018-09-13 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22124-001025 | 22124 | 2019-08-12 08:00 | Section 6 | Material | Timber | Not on List | 21 | NULL | 8.31 | 174.51 | Timber Products | 2019-08-12 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22124-001025 | 22124 | 2019-08-12 08:00 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 15.45 | 15.45 | Timber Products | 2019-08-12 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22124-001025 | 22124 | 2019-08-12 08:00 | Section 6 | Material | Timber | Not on List | 100 | NULL | 0.95 | 95 | Timber Products | 2019-08-12 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22007-001025 | 22007 | 2019-08-08 14:10 | Core | Material | Not on List | Not on List | 1 | SM | 2548.56 | 2548.56 | Training | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22044-001025 | 22044 | 2019-08-09 07:09 | Core | Material | Not on List | Not on List | 1 | each | 7741.44 | 7741.44 | Miscellaneous | 2019-08-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22011-001025 | 22011 | 2019-08-08 14:44 | Section 4 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 1440 | Each | 1.5 | 2160 | Miscellaneous | 2019-08-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22170-001025 | 22170 | 2019-08-12 09:40 | Section 5 | Material | Not on List | Not on List | 1 | EACH | 1360.42 | 1360 | Miscellaneous | 2019-08-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21999-001025 | 21999 | 2019-08-08 11:10 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 16 | ea | 5.43 | 86.88 | Miscellaneous | 2019-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 16 | ea | 5.43 | 86.88 | Miscellaneous | 2019-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5829-00519 | 5829 | 2018-08-30 15:45 | Section 4 | Material | Not on List | Not on List | 14.313 | Tonnes | 538 | 7700.39 | Rebar and Mesh | 2018-09-13 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN21 - Bar Hill Junction East Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | Kerbs | Not on List | 12 | ea | 5.43 | 65.16 | Miscellaneous | 2019-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | Kerbs | Not on List | 16 | ea | 13.39 | 214.24 | Miscellaneous | 2019-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21940-001025 | 21940 | 2019-08-07 12:16 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2232.8 | Each | 1 | 2232.8 | PPE | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21870-001025 | 21870 | 2019-08-06 15:21 | Core | Material | PPE, Small Tools and Consumables | Not on List | 519.28 | Each | 1 | 519.28 | Small Tools (Consumables) | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21838-001025 | 21838 | 2019-08-06 10:44 | Core | Material | NULL | NULL | 4 | Each | 5.5 | 22 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5829-00519 | 5829 | 2018-08-30 15:45 | Section 4 | Material | Not on List | Not on List | 40 | coils | 43.05 | 1722 | Rebar and Mesh | 2018-09-05 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22183-001025 | 22183 | 2019-08-12 17:37 | Section 3 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Stores - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22183-001025 | 22183 | 2019-08-12 17:37 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Stores - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22183-001025 | 22183 | 2019-08-12 17:37 | Section 3 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Concrete Drainage | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Stores - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22194-001025 | 22194 | 2019-08-13 08:02 | Section 2 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 4000 | Each | 0.37 | 1480 | Builders Merchants (General) | 2019-08-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21990-001025 | 21990 | 2019-08-08 10:41 | Section 5 | Material | Saint Gobain Castings | 600x600x150 D400 Inter Ax Manhole Cover (766618) | 30 | Each | 94.87 | 2846.1 | Builders Merchants (General) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21990-001025 | 21990 | 2019-08-08 10:41 | Section 5 | Material | Concrete Drainage | Not on List | 75 | EACH | 23.92 | 1794 | Builders Merchants (General) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21990-001025 | 21990 | 2019-08-08 10:41 | Section 5 | Material | Concrete Drainage | Not on List | 25 | EACH | 9.2 | 230 | Builders Merchants (General) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21990-001025 | 21990 | 2019-08-08 10:41 | Section 5 | Material | Concrete Drainage | Not on List | 6 | EACH | 33.38 | 200.28 | Builders Merchants (General) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5841-00529 | 5841 | 2018-08-31 07:50 | Section 4 | Material | Not on List | Not on List | 14 | Each | 16.55 | 231.7 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21990-001025 | 21990 | 2019-08-08 10:41 | Section 5 | Material | Concrete Drainage | Not on List | 8 | EACH | 24.85 | 198.8 | Builders Merchants (General) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22084-001025 | 22084 | 2019-08-09 14:48 | Section 4 | Material | NULL | NULL | 5 | Each | 33.55 | 167.75 | NULL | NULL | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Rocker (890351) | 3 | Each | 253.14 | 759.42 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Not on List | 32 | No | 2.9 | 92.8 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5841-00529 | 5841 | 2018-08-31 07:50 | Section 4 | Material | Not on List | Not on List | 2 | Each | 33.35 | 66.7 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 4 | Each | 43.16 | 172.64 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 8 | Each | 35.52 | 284.16 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 47.04 | 470.4 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | Not on List | 10 | NULL | NULL | 0 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22211-001025 | 22211 | 2019-08-13 10:56 | Core | Material | Not on List | Not on List | 6 | Items | 264 | 1584 | Miscellaneous | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22204-001025 | 22204 | 2019-08-13 09:25 | Section 1 | Material | Concrete Drainage | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-08-26 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-22204-001025 | 22204 | 2019-08-13 09:25 | Section 1 | Material | Concrete Drainage | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-08-26 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-22161-001025 | 22161 | 2019-08-12 14:16 | Section 5 | Material | Not on List | Not on List | 1 | SUM | 58212.47 | 58212.47 | Professional Services | 2019-08-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5841-00529 | 5841 | 2018-08-31 07:50 | Section 4 | Material | Not on List | Not on List | 4 | Each | 21.6 | 86.4 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22172-001025 | 22172 | 2019-08-12 09:21 | Section 4 | Material | Not on List | Not on List | 40 | Each | 10.85 | 434 | Builders Merchants (General) | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22205-001025 | 22205 | 2019-08-13 09:56 | Core | Material | NULL | NULL | 1 | Each | 410 | 410 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22220-001025 | 22220 | 2019-08-13 12:53 | Section 1 | Material | Not on List | Not on List | 6 | boxes | NULL | 0 | Miscellaneous | 2019-08-15 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-5841-00529 | 5841 | 2018-08-31 07:50 | Section 4 | Material | Not on List | Not on List | 2 | Each | 97.14 | 194.28 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22237-001025 | 22237 | 2019-08-13 16:32 | Section 2 | Material | Not on List | Not on List | 90 | single unit | 0 | 0 | Fixings and Fasteners | 2019-08-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-22222-001025 | 22222 | 2019-08-13 13:33 | Section 2 | Material | Concrete Drainage | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-09-09 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22257-001025 | 22257 | 2019-08-14 08:52 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Rebar and Mesh | 2019-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22257-001025 | 22257 | 2019-08-14 08:52 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Rebar and Mesh | 2019-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22257-001025 | 22257 | 2019-08-14 08:52 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Rebar and Mesh | 2019-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5846-00543 | 5846 | 2018-08-31 09:30 | Section 4 | Material | Concrete Drainage | 1200Mm Concrete Pipe | 1 | Each | 459.88 | 459.88 | Concrete Drainage | 2018-09-05 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22134-001025 | 22134 | 2019-08-12 09:29 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22123-001025 | 22123 | 2019-08-12 08:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 827.35 | Each | 1 | 827.35 | Miscellaneous | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22262-001025 | 22262 | 2019-08-14 09:21 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21864-001025 | 21864 | 2019-08-06 14:25 | Core | Material | NULL | NULL | 3 | Each | 34 | 102 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22267-001025 | 22267 | 2019-08-14 08:32 | Core | Material | Not on List | Not on List | 8 | packs | NULL | 0 | Surveying Consumables | 2019-08-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22066-001025 | 22066 | 2019-08-09 11:32 | Section 4 | Material | Not on List | Not on List | 7 | Each | 35 | 245 | Miscellaneous | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22279-001025 | 22279 | 2019-08-14 12:56 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Plastic Drainage | P/Pipe 150Mmx150Mm 45Deg Ridgidrain Junc | 200 | Each | 14.4 | 2880 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22271-001025 | 22271 | 2019-08-14 10:44 | Section 5 | Material | Aggregate | Type 1 | 1182.06 | Tonnes | 21.65 | 25591.6 | Aggregate | 2019-08-14 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22289-001025 | 22289 | 2019-08-14 16:15 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-08-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Plastic Drainage | P/Pipe 150Mm Ridgidrain Dbl Skt Coupler | 100 | Each | 1.84 | 184 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22278-001025 | 22278 | 2019-08-14 13:04 | Core | Material | NULL | NULL | 1 | Each | 393.42 | 393.42 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22268-001025 | 22268 | 2019-08-14 10:46 | Section 4 | Material | NULL | NULL | 1 | Each | 4041.7 | 4041.7 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22312-001025 | 22312 | 2019-08-15 09:31 | Core | Material | Not on List | Not on List | 1 | ea | 850 | 850 | Training | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22312-001025 | 22312 | 2019-08-15 09:31 | Core | Material | Not on List | Not on List | 1 | ea | 580 | 580 | Training | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22201-001025 | 22201 | 2019-08-13 09:12 | Section 4 | Material | Not on List | Not on List | 100 | Each | 33.73 | 3373 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22201-001025 | 22201 | 2019-08-13 09:12 | Section 4 | Material | Not on List | Not on List | 40 | Each | 2.47 | 98.8 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22201-001025 | 22201 | 2019-08-13 09:12 | Section 4 | Material | NULL | Not on List | 50 | Each | 189 | 9450 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22209-001025 | 22209 | 2019-08-13 10:34 | Section 6 | Material | Timber | Not on List | 1 | NULL | NULL | 0 | Timber Products | 2019-08-13 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | NULL | Buyer - Closed | NULL | Yes - Approve | Req - S6 Buyers
MREQ-22209-001025 | 22209 | 2019-08-13 10:34 | Section 6 | Material | Timber | Not on List | 1 | NULL | NULL | 0 | Timber Products | 2019-08-13 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | NULL | Yes - Approve | Req - S6 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Not on List | Not on List | 100 | Each | 7.64 | 764 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 100 | Each | 1.98 | 198 | Plastic Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 80 | Each | 2.97 | 237.6 | Plastic Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 36 | Each | 10.5 | 378 | Plastic Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Twinwall | Not on List | 3 | NULL | NULL | 0 | Plastic Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 80 | Each | 3.56 | 284.8 | Concrete Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Saint Gobain Castings | Not on List | 40 | NULL | NULL | 0 | Concrete Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 360 | Each | 4.59 | 1652 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 40 | Each | 3.52 | 141 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 60 | Each | 3.03 | 182 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Not on List | Not on List | 100 | Each | 10.5 | 1050 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 4 | Each | 11.94 | 48 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 4 | Each | 11.94 | 48 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 4 | Each | 10.08 | 40 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 4 | Each | 7.68 | 31 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 4 | Each | 7.68 | 31 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 12 | Each | 115.78 | 1389 | Miscellaneous | 2019-08-20 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Not on List | Not on List | 200 | each | NULL | 0 | Fixings and Fasteners | 2019-08-20 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Not on List | Not on List | 1 | Each | 64.7 | 64.7 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Plastic Drainage | P/Pipe 150Mm Ridgidrain Seal | 1000 | Each | 0.85 | 850 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22212-001025 | 22212 | 2019-08-13 11:09 | Section 4 | Material | Not on List | Not on List | 1 | Each | 35717.31 | 35717.31 | Concrete Accessories | 2019-08-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20978-001025 | 20978 | 2019-07-18 09:20 | Section 4 | Material | Waste Management | Not on List | 1 | Each | 1199.88 | 1199.88 | Fuel | 2019-08-16 | RVP 420 - A14 Eastbound - Opposite Crematorium | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Rigidrain P/E 450Mm Dia Incl Coup/Sealia | 6 | no | 126.66 | 759.96 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5925-00577 | 5925 | 2018-09-03 11:31 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 7.1 | 7100 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22392-001025 | 22392 | 2019-08-16 12:16 | Core | Material | Not on List | Not on List | 4 | Days | 649 | 2596 | Miscellaneous | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-9989-001025 | 9989 | 2018-12-05 12:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 150 | EAch | 5 | 750 | PPE | 2018-12-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10243-001025 | 10243 | 2018-12-11 15:19 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 197.25 | 197.25 | Small Tools (Consumables) | 2018-12-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10087-001025 | 10087 | 2018-12-07 09:45 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 650 | 1300 | Concrete Accessories | 2018-12-12 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10087-001025 | 10087 | 2018-12-07 09:45 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 350 | 350 | Concrete Accessories | 2018-12-12 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 15 | Each | 35.52 | 533 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 2 | Each | 36.62 | 73 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10224-001025 | 10224 | 2018-12-11 11:19 | Section 3 | Material | Not on List | Not on List | 1 | ea | 250 | 250 | Not Sure | 2018-12-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10224-001025 | 10224 | 2018-12-11 11:19 | Section 3 | Material | Not on List | Not on List | 3 | ea | 179.2 | 537.6 | Not Sure | 2018-12-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 100 | Each | 29.28 | 2928 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 20 | Each | 15.43 | 308.6 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 7 | Each | 27.56 | 192.92 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 1 | Each | 27.56 | 27.56 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 1 | Each | 27.56 | 27.56 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 7 | Each | 4.67 | 32.69 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 1 | Each | 115 | 115 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9957-001025 | 9957 | 2018-12-04 15:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 68.75 | 68.75 | Damage Charges | 2018-12-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9966-001025 | 9966 | 2018-12-04 16:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 175.93 | 175.93 | Damage Charges | 2018-12-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9604-001025 | 9604 | 2018-11-26 10:03 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 440.02 | 440.02 | Electrical | 2018-11-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5451-00291 | 5451 | 2018-08-21 16:03 | Section 4 | Material | Not on List | Not on List | 3 | Pallet | NULL | 0 | Concrete Accessories | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10161-001025 | 10161 | 2018-12-10 10:18 | Section 3 | Material | Not on List | Not on List | 1 | EA | 50 | 50 | Miscellaneous | 2018-12-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10161-001025 | 10161 | 2018-12-10 10:18 | Section 3 | Material | Not on List | Not on List | 1 | EA | 23.5 | 23.5 | Miscellaneous | 2018-12-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10318-001025 | 10318 | 2018-12-13 09:00 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10265-001025 | 10265 | 2018-12-12 09:02 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327.4 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10327-001025 | 10327 | 2018-12-13 10:27 | Section 3 | Material | Not on List | Not on List | 3 | No. | 75 | 225 | Miscellaneous | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10099-001025 | 10099 | 2018-12-07 12:05 | Section 4 | Material | Not on List | Not on List | 50 | Each | 27.5 | 1375 | Fixings and Fasteners | 2018-12-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411 | Concrete Drainage | 2019-01-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 15 | Each | 35.52 | 533 | Concrete Drainage | 2019-01-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5451-00291 | 5451 | 2018-08-21 16:03 | Section 4 | Material | Not on List | Not on List | 6 | Bag | NULL | 0 | Concrete Accessories | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 30 | Each | 67.9 | 2037 | Concrete Drainage | 2019-01-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10281-001025 | 10281 | 2018-12-12 14:28 | Section 4 | Material | Not on List | Not on List | 1 | Each | 580.43 | 580.43 | Damage Charges | 2018-12-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10341-001025 | 10341 | 2018-12-13 14:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 200 | number | NULL | 0 | Surveying Consumables | 2018-12-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10327-001025 | 10327 | 2018-12-13 10:27 | Section 3 | Material | Not on List | Not on List | 3 | No. | 75 | 225 | Miscellaneous | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-5451-00291 | 5451 | 2018-08-21 16:03 | Section 4 | Material | Not on List | Not on List | 4 | Coil | NULL | 0 | Rebar and Mesh | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10318-001025 | 10318 | 2018-12-13 09:00 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 26.55 | 265.5 | Miscellaneous | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10330-001025 | 10330 | 2018-12-13 11:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 300 | number | 7.1 | 2130 | Surveying Consumables | 2018-12-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10351-001025 | 10351 | 2018-12-13 15:42 | Section 3 | Material | Not on List | Not on List | 11 | NULL | 7.96 | 88 | Small Tools (Consumables) | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10351-001025 | 10351 | 2018-12-13 15:42 | Section 3 | Material | Not on List | Not on List | 6 | NULL | 6.11 | 37 | Small Tools (Consumables) | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9947-001025 | 9947 | 2018-12-04 10:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 850 | 850 | Surveying Consumables | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9947-001025 | 9947 | 2018-12-04 10:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 395 | 395 | Surveying Consumables | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10353-001025 | 10353 | 2018-12-13 16:23 | Section 4 | Material | Not on List | Not on List | 36.42 | tonnes | NULL | 0 | Reinforcement | 2019-01-08 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5451-00291 | 5451 | 2018-08-21 16:03 | Section 4 | Material | Not on List | Not on List | 8 | Coil | NULL | 0 | Rebar and Mesh | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10331-001025 | 10331 | 2018-12-13 11:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 108.55 | 108.55 | Miscellaneous | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10351-001025 | 10351 | 2018-12-13 15:42 | Section 3 | Material | Not on List | Not on List | 11 | ea | 7.96 | 87.56 | Small Tools (Consumables) | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10351-001025 | 10351 | 2018-12-13 15:42 | Section 3 | Material | Not on List | Not on List | 6 | ea | 6.11 | 36.66 | Small Tools (Consumables) | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 15 | Each | 35.52 | 532.8 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 2 | Each | 36.62 | 73.24 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5347-00243 | 5347 | 2018-08-20 11:52 | Section 4 | Material | Not on List | Not on List | 100 | Each | 20.5 | 0 | Not Sure | 2018-08-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10365-001025 | 10365 | 2018-12-14 10:19 | Section 3 | Material | Not on List | Not on List | 13 | no. of schedule components | NULL | 0 | Fixings and Fasteners | 2019-01-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10087-001025 | 10087 | 2018-12-07 09:45 | Section 4 | Material | Not on List | Not on List | 2 | Each | 650 | 1300 | Concrete Accessories | 2018-12-12 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10087-001025 | 10087 | 2018-12-07 09:45 | Section 4 | Material | Not on List | Not on List | 1 | Each | 350 | 350 | Concrete Accessories | 2018-12-12 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ9885 | 9885 | 2018-12-03 14:19 | Section 4 | Material | Not on List | Not on List | 50.105 | tonne | 538 | 26956.49 | Rebar and Mesh | 2019-01-08 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ9885 | 9885 | 2018-12-03 14:19 | Section 4 | Material | NULL | Not on List | 36.424 | tonne | 538 | 19596.11 | Rebar and Mesh | 2019-01-08 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411.2 | Concrete Drainage | 2019-01-08 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 15 | Each | 35.52 | 532.8 | Concrete Drainage | 2019-01-08 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 30 | Each | 67.9 | 2037 | Concrete Drainage | 2019-01-08 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10389-001025 | 10389 | 2018-12-14 14:37 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Fixings and Fasteners | 2018-12-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1801 - Structural Steelwork | Requestor - Buyers Pass Back | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10389-001025 | 10389 | 2018-12-14 14:37 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Fixings and Fasteners | 2018-12-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1801 - Structural Steelwork | Requestor - Buyers Pass Back | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10389-001025 | 10389 | 2018-12-14 14:37 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Fixings and Fasteners | 2018-12-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1801 - Structural Steelwork | Requestor - Buyers Pass Back | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10404-001025 | 10404 | 2018-12-17 08:34 | Section 4 | Material | Not on List | Not on List | 20 | Weeks | 550 | 11000 | Miscellaneous | 2018-12-18 | RVP 417 - 1339631 - Girton Compound Huntingdon Rd A1307 | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10345-001025 | 10345 | 2018-12-13 14:35 | Section 4 | Material | Not on List | Not on List | 10 | number cans (750mL) | NULL | 0 | Concrete Accessories | 2019-01-02 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10345-001025 | 10345 | 2018-12-13 14:35 | Section 4 | Material | Not on List | Not on List | 2 | packs (400ml tins) | 132 | 264 | Concrete Accessories | 2019-01-02 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10314-001025 | 10314 | 2018-12-13 08:42 | Section 4 | Material | Not on List | Not on List | 3 | Each | 32 | 96 | Surveying Consumables | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10314-001025 | 10314 | 2018-12-13 08:42 | Section 4 | Material | Not on List | Not on List | 3 | Each | 35 | 105 | Surveying Consumables | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10333-001025 | 10333 | 2018-12-13 10:08 | Section 4 | Material | Not on List | Not on List | 2 | Number | 49.24 | 98.48 | Miscellaneous | 2018-12-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10341-001025 | 10341 | 2018-12-13 14:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 200 | number | NULL | 0 | Surveying Consumables | 2018-12-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 50 | Each | 0.44 | 22 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 50 | Each | 0.5 | 25 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 50 | Eack | 0.43 | 21.5 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 1 | Each | 43 | 43 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.12 | 24 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 10 | 15kg Coil | 46.5 | 465 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10339-001025 | 10339 | 2018-12-13 12:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4717.86 | 4717.86 | Miscellaneous | 2018-12-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10429-001025 | 10429 | 2018-12-17 16:01 | Section 4 | Material | Not on List | Not on List | 20 | Box | NULL | 0 | Miscellaneous | 2018-12-20 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10430-001025 | 10430 | 2018-12-17 16:11 | Section 4 | Material | Not on List | Not on List | 20 | Box | 7.94 | 158.8 | Miscellaneous | 2018-12-20 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10433-001025 | 10433 | 2018-12-17 16:21 | Section 4 | Material | Not on List | Not on List | 20 | EA | 110.51 | 2210.2 | Miscellaneous | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10334-001025 | 10334 | 2018-12-13 12:23 | Section 4 | Material | Not on List | Not on List | 1 | Each | 911.26 | 911.26 | Miscellaneous | 2018-12-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10464-001025 | 10464 | 2018-12-18 16:41 | Section 3 | Material | Not on List | Not on List | 1 | Each | 56 | 56 | Damage Charges | 2018-12-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10375-001025 | 10375 | 2018-12-14 12:18 | Section 4 | Material | Not on List | Not on List | 20 | Each | 17.56 | 351.2 | Not Sure | 2019-01-03 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10455-001025 | 10455 | 2018-12-18 11:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 5.97 | 119.4 | Janitorial | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10455-001025 | 10455 | 2018-12-18 11:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 40.92 | 818.4 | Janitorial | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10455-001025 | 10455 | 2018-12-18 11:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 125 | Each | 0.77 | 96.25 | Miscellaneous | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10464-001025 | 10464 | 2018-12-18 16:41 | Section 3 | Material | Not on List | Not on List | 1 | Each | 56 | 56 | Damage Charges | 2018-12-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10477-001025 | 10477 | 2018-12-19 08:56 | Section 3 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 2000 | Each | 0.37 | 740 | Miscellaneous | 2019-01-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10418-001025 | 10418 | 2018-12-17 11:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 140.74 | 140.74 | Damage Charges | 2018-12-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1601 - Piling and attendances | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10421-001025 | 10421 | 2018-12-17 12:23 | Section 4 | Material | Not on List | Not on List | 1 | Each | 362.26 | 362.26 | Miscellaneous | 2018-12-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10490-001025 | 10490 | 2018-12-19 16:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 200 | NULL | 2.18 | 436 | Miscellaneous | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10481-001025 | 10481 | 2018-12-19 09:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2306.68 | Each | 1 | 2306.68 | PPE | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10065-001025 | 10065 | 2018-12-06 15:28 | Section 4 | Material | NULL | Not on List | 12 | no | 4.13 | 49.56 | Builders Merchants (General) | 2018-12-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10065-001025 | 10065 | 2018-12-06 15:28 | Section 4 | Material | NULL | Not on List | 30 | no | 0.6 | 18 | Builders Merchants (General) | 2018-12-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10065-001025 | 10065 | 2018-12-06 15:28 | Section 4 | Material | Not on List | Not on List | 75 | m2 | NULL | 0 | Builders Merchants (General) | 2018-12-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 40 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 20 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 240 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 47 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 47 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 1430 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 26 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 80 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10508-001025 | 10508 | 2018-12-20 13:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 700 | Each | 6.35 | 4445 | PPE | 2019-01-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 35 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 45 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5192-00118 | 5192 | 2018-08-16 08:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1071 | 0 | Damage Charges | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 90 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 112 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 75 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 91 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5775-00466 | 5775 | 2018-08-29 18:50 | Section 3 | Material | Not on List | Not on List | 1 | ea | 727.08 | 727.08 | Miscellaneous | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14853-001025 | 14853 | 2019-03-28 10:40 | Section 2 | Material | Kerbs | Not on List | 500 | metres | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5775-00466 | 5775 | 2018-08-29 18:50 | Section 3 | Material | Not on List | Not on List | 1 | ea | 80.8 | 80.8 | Miscellaneous | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14609-001025 | 14609 | 2019-03-25 15:10 | Section 3 | Material | NULL | Not on List | 6 | No | 179.55 | 1077.3 | Builders Merchants (General) | 2019-03-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14874-001025 | 14874 | 2019-03-28 14:36 | Section 2 | Material | Not on List | Not on List | 5 | Number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN32 - Brampton Equestrian Underpass | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14630-001025 | 14630 | 2019-03-26 07:24 | Section 4 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5780-00469 | 5780 | 2018-08-29 23:10 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 174.27 | 174.27 | Janitorial | 2018-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14856-001025 | 14856 | 2019-03-28 11:04 | Section 2 | Material | Not on List | Not on List | 0.465 | Tonnes | 538 | 250.17 | NULL | 2019-04-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14857-001025 | 14857 | 2019-03-28 11:29 | Section 2 | Material | Not on List | Not on List | 12500 | NULL | NULL | 0 | Miscellaneous | 2019-03-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5780-00469 | 5780 | 2018-08-29 23:10 | Section 3 | Material | Not on List | Not on List | 5 | ea | 10.45 | 52.25 | Miscellaneous | 2018-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14764-001025 | 14764 | 2019-03-27 13:16 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 1178.1 | 23562 | Concrete Accessories | 2019-04-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14734-001025 | 14734 | 2019-03-27 08:40 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 235 | 470 | Concrete Drainage | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14734-001025 | 14734 | 2019-03-27 08:40 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 39.5 | 237 | Concrete Drainage | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14838-001025 | 14838 | 2019-03-28 09:28 | Section 4 | Material | NULL | Building Sand Bulk Bag (938155) | 5 | Each | 32.74 | 163.7 | Builders Merchants (General) | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14865-001025 | 14865 | 2019-03-28 12:49 | Section 4 | Material | NULL | NULL | 100 | NULL | 4.97 | 497 | NULL | NULL | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | Janitorial | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5849-00544 | 5849 | 2018-08-31 10:07 | Section 3 | Material | Not on List | Not on List | 100 | ea | 0.48 | 48 | Fixings and Fasteners | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | Janitorial | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Broom 11" Stiff Bass Bracketed 48" X 15/16" Handle (502216) | 12 | Each | 7.14 | 86 | Miscellaneous | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EACH | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EACH | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EACH | NULL | 0 | Miscellaneous | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 24 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | PACKS | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | Aggregate | Not on List | 2 | EACH | NULL | 0 | Aggregate | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | NULL | 0 | Aggregate | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-04 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14678-001025 | 14678 | 2019-03-26 14:41 | Section 5 | Material | Not on List | Not on List | 15 | number | 3.62 | 54.3 | Builders Merchants (General) | 2019-03-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14678-001025 | 14678 | 2019-03-26 14:41 | Section 5 | Material | Not on List | Not on List | 4 | NUMBER | 2.5 | 10 | Builders Merchants (General) | 2019-03-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14678-001025 | 14678 | 2019-03-26 14:41 | Section 5 | Material | Not on List | Not on List | 20 | number | 10.56 | 211.2 | Builders Merchants (General) | 2019-03-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14678-001025 | 14678 | 2019-03-26 14:41 | Section 5 | Material | Not on List | Not on List | 20 | number | 42.2 | 844 | Builders Merchants (General) | 2019-03-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14827-001025 | 14827 | 2019-03-28 07:40 | Section 2 | Material | NULL | Not on List | 270 | metres | NULL | 0 | Ductile Drainage | 2019-04-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14827-001025 | 14827 | 2019-03-28 07:40 | Section 2 | Material | NULL | Not on List | 16 | Number | NULL | 0 | Ductile Drainage | 2019-04-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14827-001025 | 14827 | 2019-03-28 07:40 | Section 2 | Material | NULL | Not on List | 2 | Number | NULL | 0 | Ductile Drainage | 2019-04-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14763-001025 | 14763 | 2019-03-27 13:04 | Section 4 | Material | Not on List | Not on List | 200 | NULL | 9.32 | 1864 | Builders Merchants (General) | 2019-03-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14859-001025 | 14859 | 2019-03-28 12:14 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 25.13 | 150.78 | Plastic Drainage | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5822-00513 | 5822 | 2018-08-30 15:50 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 400 | meters | 1160 | 464000 | Miscellaneous | 2018-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14867-001025 | 14867 | 2019-03-28 13:14 | Section 4 | Material | Not on List | Not on List | 100 | NULL | 16.72 | 1672 | Concrete Accessories | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14867-001025 | 14867 | 2019-03-28 13:14 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 139 | 139 | Concrete Accessories | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 128 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 1 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 4 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 8 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 2 | Each | 11.94 | 23.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 2 | Each | 11.94 | 23.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5113-0043 | 5113 | 2018-08-15 07:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 748.47 | 0 | Small Tools (Consumables) | 2018-08-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Transition Kerbs 125x255 (947297) | 3 | Each | 10.08 | 30.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Transition Kerbs 125x255 (947297) | 4 | Each | 10.08 | 40.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 12 | Metres | 6 | 72 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 32 | Metres | 6 | 192 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14784-001025 | 14784 | 2019-03-27 15:58 | Section 2 | Material | NULL | Not on List | 34 | rolls | 177 | 6018 | Geotextiles | 2019-04-02 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 607 - Compaction | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14784-001025 | 14784 | 2019-03-27 15:58 | Section 2 | Material | NULL | Not on List | 40 | rolls | 181 | 7240 | Geotextiles | 2019-04-02 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 607 - Compaction | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14784-001025 | 14784 | 2019-03-27 15:58 | Section 2 | Material | NULL | Not on List | 45 | rolls | 188 | 8460 | Geotextiles | 2019-04-02 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 607 - Compaction | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14784-001025 | 14784 | 2019-03-27 15:58 | Section 2 | Material | NULL | Not on List | 4 | rolls | 215 | 860 | Geotextiles | 2019-04-02 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 607 - Compaction | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14784-001025 | 14784 | 2019-03-27 15:58 | Section 2 | Material | NULL | Not on List | 10 | rolls | 417 | 4170 | Geotextiles | 2019-04-02 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 607 - Compaction | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5840-00527 | 5840 | 2018-08-31 07:11 | Section 3 | Material | Not on List | Not on List | 20 | NULL | 9 | 180 | Fixings and Fasteners | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14939-001025 | 14939 | 2019-03-29 12:17 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | 2 | 425 | 850 | Small Tools (Consumables) | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14790-001025 | 14790 | 2019-03-27 16:38 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 4603 | 4603 | Concrete Accessories | 2019-04-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14677-001025 | 14677 | 2019-03-26 14:14 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 6956 | 20868 | Surveying Consumables | 2019-03-29 | NULL | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14693-001025 | 14693 | 2019-03-26 15:52 | Section 4 | Material | Not on List | Not on List | 200 | NULL | 0.15 | 30 | Surveying Consumables | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5840-00527 | 5840 | 2018-08-31 07:11 | Section 3 | Material | Not on List | Not on List | 4 | NULL | 18.84 | 75.36 | Miscellaneous | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | CL3B - Structures (Culverts) 3B | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14693-001025 | 14693 | 2019-03-26 15:52 | Section 4 | Material | Not on List | Not on List | 5 | NULL | 36 | 180 | Surveying Consumables | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14693-001025 | 14693 | 2019-03-26 15:52 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 18.5 | 55.5 | Surveying Consumables | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14997-001025 | 14997 | 2019-04-01 08:12 | Section 2 | Material | Not on List | Not on List | 2 | number | 65 | 130 | Small Tools (Consumables) | 2019-04-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14997-001025 | 14997 | 2019-04-01 08:12 | Section 2 | Material | Not on List | Not on List | 2 | number | 61.5 | 123 | Small Tools (Consumables) | 2019-04-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14892-001025 | 14892 | 2019-03-28 15:28 | Section 4 | Material | Not on List | Not on List | 2 | coil | 261.07 | 522.14 | Miscellaneous | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14892-001025 | 14892 | 2019-03-28 15:28 | Section 4 | Material | Not on List | Not on List | 25 | NULL | 8.08 | 202 | Miscellaneous | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14892-001025 | 14892 | 2019-03-28 15:28 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 11.83 | 236.6 | Miscellaneous | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14892-001025 | 14892 | 2019-03-28 15:28 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 22.85 | 22.85 | Miscellaneous | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15019-001025 | 15019 | 2019-04-01 10:01 | Section 2 | Material | Kerbs | Not on List | 4 | No. | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-02 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15019-001025 | 15019 | 2019-04-01 10:01 | Section 2 | Material | Kerbs | Not on List | 4 | No. | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-02 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14863-001025 | 14863 | 2019-03-28 12:41 | Section 3 | Material | Aggregate | Not on List | 880 | m3 | 47.05 | 41404 | Aggregate | 2019-04-02 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14886-001025 | 14886 | 2019-03-28 16:02 | Section 3 | Material | Not on List | Not on List | 1 | number | 44100 | 44100 | Miscellaneous | 2019-03-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-14926-001025 | 14926 | 2019-03-29 09:48 | Section 3 | Material | Not on List | Not on List | 390 | unit | 50 | 19500 | Ductile Drainage | 2019-04-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14926-001025 | 14926 | 2019-03-29 09:48 | Section 3 | Material | Not on List | Not on List | 1 | unit | 60 | 60 | Ductile Drainage | 2019-04-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14926-001025 | 14926 | 2019-03-29 09:48 | Section 3 | Material | Not on List | Not on List | 1 | unit | 60 | 60 | Ductile Drainage | 2019-04-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14926-001025 | 14926 | 2019-03-29 09:48 | Section 3 | Material | Not on List | Not on List | 4 | unit | 650 | 2600 | Ductile Drainage | 2019-04-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14787-001025 | 14787 | 2019-03-27 15:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 82.5 | 82.5 | Miscellaneous | 2019-04-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14968-001025 | 14968 | 2019-03-29 16:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 966.06 | 966.06 | Small Tools (Consumables) | 2019-04-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14968-001025 | 14968 | 2019-03-29 16:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 146.58 | 146.58 | Janitorial | 2019-04-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14968-001025 | 14968 | 2019-03-29 16:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 270.9 | 270.9 | PPE | 2019-04-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14955-001025 | 14955 | 2019-03-29 14:41 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain Bend 45deg (878085) | 10 | Each | 48.86 | 488.6 | Plastic Drainage | 2019-04-01 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14955-001025 | 14955 | 2019-03-29 14:41 | Section 2 | Material | NULL | Polypipe 225mm Ridgidrain Bend 45deg (878031) | 10 | Each | 27.62 | 276.2 | Plastic Drainage | 2019-04-01 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14940-001025 | 14940 | 2019-03-29 11:27 | Section 3 | Material | Not on List | Not on List | 196 | tube | 4.55 | 891.8 | Ductile Drainage | 2019-04-11 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14887-001025 | 14887 | 2019-03-28 16:07 | Section 2 | Material | Not on List | Not on List | 1 | number | 65520 | 65520 | Miscellaneous | 2019-03-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15024-001025 | 15024 | 2019-04-01 10:47 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 40 cubic yard | 1 | Each | 370 | 370 | Waste (General) | 2019-04-02 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14785-001025 | 14785 | 2019-03-27 16:14 | Section 4 | Material | Not on List | Not on List | 9 | NULL | 1659.85 | 14938.65 | Concrete Accessories | 2019-04-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14785-001025 | 14785 | 2019-03-27 16:14 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Accessories | 2019-04-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14821-001025 | 14821 | 2019-03-27 19:08 | Section 3 | Material | NULL | Not on List | 6 | Rolls | 670 | 4020 | Geotextiles | 2019-04-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15025-001025 | 15025 | 2019-04-01 09:22 | Section 3 | Material | Not on List | Not on List | 25 | Drum | 20.25 | 506.25 | Miscellaneous | 2019-04-02 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15025-001025 | 15025 | 2019-04-01 09:22 | Section 3 | Material | Not on List | Not on List | 10 | Drum | 57.92 | 579.2 | Miscellaneous | 2019-04-02 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14888-001025 | 14888 | 2019-03-28 16:01 | Section 3 | Material | Not on List | Not on List | 1 | See Attached Component List | 4877.9 | 4877.9 | Fixings and Fasteners | 2019-04-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14593-001025 | 14593 | 2019-03-25 11:36 | Section 4 | Material | Not on List | Not on List | 10 | Each | 89.39 | 893.9 | Concrete Drainage | 2019-03-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15071-001025 | 15071 | 2019-04-02 07:31 | Section 1 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 10 | Each | 24.32 | 243 | Timber Products | 2019-04-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | BN33 - Ellington Brook Accommodation Bridge | 1703 - Formwork | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S1 Buyers
MREQ-15077-001025 | 15077 | 2019-04-02 08:09 | Section 2 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Surveying Consumables | 2019-04-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14893-001025 | 14893 | 2019-03-28 17:16 | Section 2 | Material | NULL | Not on List | 100 | metres | NULL | 0 | Geotextiles | 2019-04-01 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 602 - Excavation (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14893-001025 | 14893 | 2019-03-28 17:16 | Section 2 | Material | NULL | Not on List | 100 | metres | NULL | 0 | Geotextiles | 2019-04-01 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15085-001025 | 15085 | 2019-04-02 08:24 | Section 2 | Material | Twinwall | Polypipe Road Gully 450mm x 750mm (573006) | 40 | Each | 15.71 | 628 | Plastic Drainage | 2019-04-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15085-001025 | 15085 | 2019-04-02 08:24 | Section 2 | Material | Twinwall | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2019-04-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15085-001025 | 15085 | 2019-04-02 08:24 | Section 2 | Material | Twinwall | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2019-04-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14585-001025 | 14585 | 2019-03-25 09:34 | Section 3 | Material | Not on List | Not on List | 1 | ea | 1519 | 1519 | Professional Services | 2019-04-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25808-001025 | 25808 | 2019-10-28 13:13 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 56 | Each | 6.5 | 364 | Miscellaneous | 2019-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25815-001025 | 25815 | 2019-10-28 15:42 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25791-001025 | 25791 | 2019-10-28 09:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25817-001025 | 25817 | 2019-10-28 15:47 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25734-001025 | 25734 | 2019-10-25 09:45 | Section 2 | Material | Not on List | Not on List | 4 | each | 950 | 3800 | Miscellaneous | 2019-10-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25798-001025 | 25798 | 2019-10-28 12:08 | Section 5 | Material | Concrete Drainage | NULL | 1 | SM | 661.5 | 661.5 | Concrete Drainage | 2019-10-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25843-001025 | 25843 | 2019-10-29 10:12 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25845-001025 | 25845 | 2019-10-29 10:22 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25753-001025 | 25753 | 2019-10-25 13:18 | Section 4 | Material | Kerbs | Not on List | 8 | Each | 7.52 | 60.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25753-001025 | 25753 | 2019-10-25 13:18 | Section 4 | Material | Kerbs | Not on List | 8 | Each | 7.52 | 60.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25753-001025 | 25753 | 2019-10-25 13:18 | Section 4 | Material | Kerbs | Not on List | 18 | Each | 11.68 | 210.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25316-001025 | 25316 | 2019-10-17 10:16 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7079-001013 | 7079 | 2018-09-27 09:10 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1929 | 1929 | Timber Products | 2018-10-01 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25863-001025 | 25863 | 2019-10-29 14:44 | Section 5 | Material | Hazardous Waste | Not on List | 1 | NULL | 352 | 352 | Waste (General) | 2019-11-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 300 | Each | 7.1 | 2130 | Surveying Consumables | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 400 | Each | 8.28 | 3312 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 560 | Each | 21.01 | 11765.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 3 | Each | 151.94 | 455.82 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 2 | Each | 36.67 | 73.34 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5753 | 5753 | 2018-08-29 13:27 | Section 4 | Material | Not on List | Not on List | 10000 | NULL | NULL | 0 | Concrete Accessories | 2018-09-05 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 1 | Each | 36.67 | 36.67 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 593 | Each | 22.84 | 13544.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 30 | Each | 35.47 | 1064.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 1607 | Each | 24.09 | 38712.63 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 6 | Each | 359.42 | 2156.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 1 | Each | 282.24 | 282.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 6 | Each | 282.24 | 1693.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 8 | Each | 30 | 240 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25833-001025 | 25833 | 2019-10-29 09:07 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18724-001025 | 18724 | 2019-06-07 09:11 | Core | Material | Not on List | Not on List | 1 | NULL | 100 | 100 | Miscellaneous | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25502-001025 | 25502 | 2019-10-21 16:41 | Section 3 | Material | Aggregate | Type 1 | 400 | Tonnes | 21.65 | 8660 | Aggregate | 2019-10-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25914-001025 | 25914 | 2019-10-30 14:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-25922-001025 | 25922 | 2019-10-30 14:33 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25821-001025 | 25821 | 2019-10-28 16:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 1.92 | 19.2 | Small Tools (Consumables) | 2019-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25859-001025 | 25859 | 2019-10-29 14:11 | Section 4 | Material | Not on List | Not on List | 2 | Each | 19.71 | 39.42 | Builders Merchants (General) | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25859-001025 | 25859 | 2019-10-29 14:11 | Section 4 | Material | Not on List | Not on List | 2 | Each | 2.86 | 5.72 | Builders Merchants (General) | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25846-001025 | 25846 | 2019-10-29 10:29 | Core | Material | PPE, Small Tools and Consumables | Not on List | 375.78 | each | 1 | 375.78 | Small Tools (Consumables) | 2019-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25655-001025 | 25655 | 2019-10-23 20:26 | Section 4 | Material | Not on List | Not on List | 2 | Each | 1965 | 3930 | Miscellaneous | 2019-10-25 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25167-001025 | 25167 | 2019-10-16 09:24 | Core | Material | NULL | NULL | 20 | Each | 17.78 | 355.6 | NULL | 2019-10-21 | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25927-001025 | 25927 | 2019-10-30 15:54 | Core | Material | Not on List | Not on List | 10 | Packs of 100 | NULL | 0 | Surveying Consumables | 2019-11-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25927-001025 | 25927 | 2019-10-30 15:54 | Core | Material | Not on List | Not on List | 10 | Packs of 100 | NULL | 0 | Surveying Consumables | 2019-11-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7150-001020 | 7150 | 2018-09-28 12:06 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Perf (346346) | 67 | Each | 34.08 | 2283.36 | Plastic Drainage | 2018-10-02 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25935-001025 | 25935 | 2019-10-30 16:32 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-25568-001025 | 25568 | 2019-10-22 14:53 | Section 2 | Material | Not on List | Not on List | 65 | ea | 28 | 1820 | Concrete Accessories | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25568-001025 | 25568 | 2019-10-22 14:53 | Section 2 | Material | Not on List | Not on List | 54 | ea | 28 | 1512 | Concrete Accessories | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7150-001020 | 7150 | 2018-09-28 12:06 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Perf (346341) | 42 | Each | 24.82 | 1042.44 | Plastic Drainage | 2018-10-02 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25568-001025 | 25568 | 2019-10-22 14:53 | Section 2 | Material | Not on List | Not on List | 12 | ea | 28 | 336 | Concrete Accessories | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25568-001025 | 25568 | 2019-10-22 14:53 | Section 2 | Material | Not on List | Not on List | 43 | ea | 28 | 1204 | Concrete Accessories | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25568-001025 | 25568 | 2019-10-22 14:53 | Section 2 | Material | Not on List | Not on List | 30 | ea | 4.79 | 143.7 | Concrete Accessories | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25754-001025 | 25754 | 2019-10-25 13:39 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25796-001025 | 25796 | 2019-10-28 12:05 | Core | Material | NULL | NULL | 10000 | Each | 1 | 10000 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25953-001025 | 25953 | 2019-10-31 08:40 | Section 1 | Material | Not on List | Not on List | 1 | No. | 3430.14 | 3430 | Miscellaneous | 2019-11-11 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1807 - Modification of existing gantries | Stores - Closed | Yes - Approve | NULL | Req - S1 Buyers
MREQ-25953-001025 | 25953 | 2019-10-31 08:40 | Section 1 | Material | Not on List | Not on List | 1 | No. | 2927.95 | 2928 | Miscellaneous | 2019-11-11 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1807 - Modification of existing gantries | Stores - Closed | Yes - Approve | NULL | Req - S1 Buyers
MREQ-25681-001025 | 25681 | 2019-10-24 12:38 | Core | Material | Not on List | NULL | 1 | SM | 2085 | 2085 | Not Sure | 2019-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25901-001025 | 25901 | 2019-10-30 08:21 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 180 | Each | 4.59 | 826.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-01 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25901-001025 | 25901 | 2019-10-30 08:21 | Section 2 | Material | Kerbs | Not on List | 54 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-01 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25860-001025 | 25860 | 2019-10-29 14:18 | Section 4 | Material | Not on List | Not on List | 30 | Each | 25 | 750 | Fixings and Fasteners | 2019-11-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25664-001025 | 25664 | 2019-10-24 08:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 3.96 | 79.2 | Small Tools (Consumables) | 2019-11-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25962-001025 | 25962 | 2019-10-31 11:33 | Core | Material | Not on List | Not on List | 1 | Number | 595 | 595 | Surveying Consumables | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25962-001025 | 25962 | 2019-10-31 11:33 | Core | Material | Not on List | Not on List | 1 | Number | 390 | 390 | Surveying Consumables | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25962-001025 | 25962 | 2019-10-31 11:33 | Core | Material | Not on List | Not on List | 1 | Number | 390 | 390 | Surveying Consumables | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25962-001025 | 25962 | 2019-10-31 11:33 | Core | Material | Not on List | Not on List | 1 | Number | 595 | 595 | Surveying Consumables | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25962-001025 | 25962 | 2019-10-31 11:33 | Core | Material | Not on List | Not on List | 1 | Number | 425 | 425 | Surveying Consumables | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25964-001025 | 25964 | 2019-10-31 12:10 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25669-001025 | 25669 | 2019-10-24 10:00 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | 20kg Bag | 7.9 | 237 | Miscellaneous | 2019-11-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25966-001025 | 25966 | 2019-10-31 12:39 | Section 4 | Material | Combined Drainage | Kerb Drain 480 Access Unit (947299) | 7 | Each | 34.55 | 242 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25966-001025 | 25966 | 2019-10-31 12:39 | Section 4 | Material | Combined Drainage | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25934-001025 | 25934 | 2019-10-30 16:30 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25628-001025 | 25628 | 2019-10-23 12:57 | Core | Material | Not on List | NULL | 1 | SM | 1362 | 1362 | Miscellaneous | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25933-001025 | 25933 | 2019-10-30 16:22 | Section 5 | Material | Not on List | NULL | 1 | SM | 581 | 581 | Builders Merchants (General) | 2019-11-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25970-001025 | 25970 | 2019-10-31 14:02 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 14272.4 | 14272 | Miscellaneous | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2704 - Works on behalf of Designers | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-24758-001025 | 24758 | 2019-10-08 09:11 | Section 4 | Material | Not on List | Not on List | 1 | Each | 5182 | 5182 | Flow Control | 2019-11-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24758-001025 | 24758 | 2019-10-08 09:11 | Section 4 | Material | NULL | Not on List | 1 | Each | 240 | 240 | Flow Control | 2019-11-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25850-001025 | 25850 | 2019-10-29 10:18 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 7 | Each | 67.9 | 475.3 | Concrete Drainage | 2019-10-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25850-001025 | 25850 | 2019-10-29 10:18 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 8 | Each | 35.52 | 284.16 | Concrete Drainage | 2019-10-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25850-001025 | 25850 | 2019-10-29 10:18 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 6 | Each | 47.04 | 282.24 | Concrete Drainage | 2019-10-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7019-00752 | 7019 | 2018-09-26 11:46 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 12 | Each | 115.78 | 1389.36 | Geotextiles | 2018-10-01 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25850-001025 | 25850 | 2019-10-29 10:18 | Section 2 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 6 | Each | 81.73 | 490.38 | Builders Merchants (General) | 2019-10-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25941-001025 | 25941 | 2019-10-30 16:57 | Section 2 | Material | Timber | Not on List | 5 | No | 10.57 | 52.85 | Timber Products | 2019-11-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25941-001025 | 25941 | 2019-10-30 16:57 | Section 2 | Material | Timber | Not on List | 3 | No | 3.6 | 10.8 | Timber Products | 2019-11-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25941-001025 | 25941 | 2019-10-30 16:57 | Section 2 | Material | Timber | Not on List | 2 | No | 12 | 24 | Timber Products | 2019-11-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25941-001025 | 25941 | 2019-10-30 16:57 | Section 2 | Material | Not on List | Not on List | 1 | ea | 27.6 | 27.6 | Miscellaneous | 2019-11-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25950-001025 | 25950 | 2019-10-31 08:08 | Section 5 | Material | Not on List | NULL | 1 | SM | 631.82 | 631.82 | Miscellaneous | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25960-001025 | 25960 | 2019-10-31 11:06 | Section 5 | Material | Not on List | Not on List | 250 | m cube | 73.31 | 18327.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25865-001025 | 25865 | 2019-10-29 14:52 | Section 4 | Material | Not on List | Not on List | 14 | Each | 439.64 | 6154.96 | Rebar and Mesh | 2019-11-01 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25921-001025 | 25921 | 2019-10-30 14:05 | Section 5 | Material | NULL | NULL | 137.12 | Each | 1 | 137.12 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25921-001025 | 25921 | 2019-10-30 14:05 | Section 5 | Material | NULL | NULL | 372.8 | Each | 1 | 372.8 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7211-001020 | 7211 | 2018-10-01 11:36 | Section 3 | Material | NULL | Not on List | 300 | EA | 2.75 | 825 | Timber Products | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25884-001025 | 25884 | 2019-10-29 17:40 | Section 4 | Material | Not on List | Not on List | 22 | Each | 126.49 | 2782.78 | Plastic Drainage | 2019-11-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26005-001025 | 26005 | 2019-11-01 08:41 | Core | Material | NULL | NULL | 748.31 | Each | 1 | 748.31 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26005-001025 | 26005 | 2019-11-01 08:41 | Core | Material | NULL | NULL | 532.32 | Each | 1 | 532.32 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26005-001025 | 26005 | 2019-11-01 08:41 | Core | Material | NULL | NULL | 337.2 | Each | 1 | 337.2 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26032-001025 | 26032 | 2019-11-01 14:10 | Section 4 | Material | Not on List | Not on List | 1 | No. | 8183.1 | 8183 | Miscellaneous | 2019-11-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-26042-001025 | 26042 | 2019-11-01 14:36 | Section 2 | Material | Bagged | Not on List | 3 | NULL | NULL | 0 | Ready Mixed Concrete | 2019-11-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26042-001025 | 26042 | 2019-11-01 14:36 | Section 2 | Material | Bagged | Not on List | 3 | NULL | NULL | 0 | Ready Mixed Concrete | 2019-11-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26042-001025 | 26042 | 2019-11-01 14:36 | Section 2 | Material | Bagged | Not on List | 3 | NULL | NULL | 0 | Ready Mixed Concrete | 2019-11-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26042-001025 | 26042 | 2019-11-01 14:36 | Section 2 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Accessories | 2019-11-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26042-001025 | 26042 | 2019-11-01 14:36 | Section 2 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Accessories | 2019-11-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26048-001025 | 26048 | 2019-11-01 15:42 | Section 3 | Material | Bagged | Not on List | 100 | NULL | NULL | 0 | Aggregate | 2019-11-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 2701 - Accommodation works | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26048-001025 | 26048 | 2019-11-01 15:42 | Section 3 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Aggregate | 2019-11-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 2701 - Accommodation works | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26004-001025 | 26004 | 2019-11-01 08:45 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 2 | Each | 48.86 | 97.72 | Plastic Drainage | 2019-11-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26082-001025 | 26082 | 2019-11-04 08:15 | Section 2 | Material | Not on List | Not on List | 41 | Each | 13 | 533 | Miscellaneous | 2019-11-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1504 - Technology Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25620-001025 | 25620 | 2019-10-23 10:20 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25918-001025 | 25918 | 2019-10-30 14:29 | Core | Material | Not on List | NULL | 6 | EA | 44 | 264 | Not Sure | 2019-11-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26087-001025 | 26087 | 2019-11-04 09:08 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Fixings and Fasteners | 2019-11-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26087-001025 | 26087 | 2019-11-04 09:08 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Fixings and Fasteners | 2019-11-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25956-001025 | 25956 | 2019-10-31 08:57 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26104-001025 | 26104 | 2019-11-04 11:23 | Section 6 | Material | Not on List | Not on List | 5 | Boxes | NULL | 0 | Miscellaneous | 2019-11-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25955-001025 | 25955 | 2019-10-31 08:58 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 41.93 | 167.72 | Small Tools (Consumables) | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25955-001025 | 25955 | 2019-10-31 08:58 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | 58.3 | 174.9 | Small Tools (Consumables) | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25974-001025 | 25974 | 2019-10-31 15:35 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 40 cubic yard | 1 | Each | 250 | 250 | Waste (General) | 2019-11-04 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25932-001025 | 25932 | 2019-10-30 16:17 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2541.6 | each | 1 | 2541.6 | PPE | 2019-11-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26112-001025 | 26112 | 2019-11-04 15:01 | Section 4 | Material | Not on List | Not on List | 20 | Each | 50.5 | 1010 | Builders Merchants (General) | 2019-11-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26135-001025 | 26135 | 2019-11-04 18:30 | Section 2 | Material | Not on List | Not on List | 5 | NULL | 66 | 330 | Concrete Accessories | 2019-11-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26110-001025 | 26110 | 2019-11-04 14:51 | Section 6 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 5 | Each | 115.78 | 578.9 | Geotextiles | 2019-11-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25882-001025 | 25882 | 2019-10-29 17:33 | Section 4 | Material | Not on List | Not on List | 5 | 20ltr | 56.2 | 281 | Miscellaneous | 2019-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26107-001025 | 26107 | 2019-11-04 14:09 | Section 4 | Material | Not on List | Not on List | 120 | Each | 31.37 | 3764.4 | Ductile Drainage | 2019-11-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26089-001025 | 26089 | 2019-11-04 09:30 | Section 4 | Material | Not on List | Not on List | 10 | Each | 81.12 | 811.2 | Plastic Drainage | 2019-11-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25979-001025 | 25979 | 2019-10-31 16:20 | Core | Material | Not on List | NULL | 1 | SM | 19825.83 | 19825.83 | Miscellaneous | 2019-11-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26008-001025 | 26008 | 2019-11-01 09:42 | Section 4 | Material | Not on List | Not on List | 20 | Each | 4.97 | 99.4 | Builders Merchants (General) | 2019-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26008-001025 | 26008 | 2019-11-01 09:42 | Section 4 | Material | Not on List | Not on List | 200 | Each | 4.97 | 994 | Builders Merchants (General) | 2019-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26008-001025 | 26008 | 2019-11-01 09:42 | Section 4 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 400 | Each | 0.35 | 140 | Blocks and Bricks | 2019-11-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-7519-001023 | 7519 | 2018-10-08 14:47 | Section 4 | Material | Not on List | Not on List | 39 | m2 | 11.95 | 466.05 | Not Sure | 2018-10-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7519-001023 | 7519 | 2018-10-08 14:47 | Section 4 | Material | Not on List | Not on List | 15 | Each | 30.68 | 460.2 | Not Sure | 2018-10-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7519-001023 | 7519 | 2018-10-08 14:47 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1659.86 | 1659.86 | Not Sure | 2018-10-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7674-001023 | 7674 | 2018-10-11 13:02 | Section 3 | Material | Not on List | Not on List | 4 | NULL | 51.93 | 207.72 | Small Tools (Consumables) | 2018-10-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-4999-0013 | 4999 | 2018-08-13 16:19 | Section 4 | Material | Not on List | NULL | 1000 | NULL | 2 | 0 | Rebar and Mesh | 2018-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7680-001023 | 7680 | 2018-10-11 14:29 | Section 3 | Material | NULL | Not on List | 300 | EA | 2.75 | 825 | Timber Products | 2018-10-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7765-001023 | 7765 | 2018-10-12 15:55 | Section 3 | Material | NULL | Concrete Kerbs 125x150x914 HB Straight (898181) | 135 | Each | 4.26 | 575.1 | Builders Merchants (General) | 2018-10-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7765-001023 | 7765 | 2018-10-12 15:55 | Section 3 | Material | NULL | Not on List | 3 | each | 20.11 | 60.33 | Builders Merchants (General) | 2018-10-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7765-001023 | 7765 | 2018-10-12 15:55 | Section 3 | Material | NULL | Not on List | 45 | each | 5.69 | 256.05 | Builders Merchants (General) | 2018-10-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | Not on List | Not on List | 40 | No | 15.71 | 628.4 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | Not on List | Not on List | 2 | No | 66.17 | 132.34 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | Not on List | Not on List | 40 | No | 3.9 | 156 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | Not on List | Not on List | 76 | NO | 13.19 | 1002.44 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | Not on List | Not on List | 10 | No | 175 | 1750 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | NULL | Not on List | 42 | No | 72.46 | 3043.32 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | NULL | Not on List | 4 | No | 72.46 | 289.84 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7799-001023 | 7799 | 2018-10-15 14:46 | Section 3 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2018-10-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 604 - Deposition | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7799-001023 | 7799 | 2018-10-15 14:46 | Section 3 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Geotextiles | 2018-10-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 604 - Deposition | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 8 | NULL | 120.62 | 964.96 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 8 | NULL | 17.45 | 139.6 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 16 | NULL | 9.04 | 144.64 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 70 | NULL | 10.66 | 746.2 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 70 | NULL | 1.84 | 128.8 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 30 | NULL | 14.4 | 432 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 30 | NULL | 7.64 | 229.2 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 39.7 | 794 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 44.11 | 882.2 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | NULL | 270 | NULL | 0.85 | 229.5 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | NULL | 40 | NULL | 1.86 | 74.4 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | NULL | 40 | NULL | 2.75 | 110 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7574-001023 | 7574 | 2018-10-09 14:59 | Section 4 | Material | NULL | Not on List | 12 | Each | 70 | 840 | Ductile Drainage | 2018-10-23 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7814-001023 | 7814 | 2018-10-15 16:58 | Section 4 | Material | Not on List | Not on List | 40 | Panels | NULL | 0 | Not Sure | 2018-11-12 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-7818-001023 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 30 | No | NULL | 0 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7818-001023 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 20 | No | NULL | 0 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7823-001023 | 7823 | 2018-10-16 07:35 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-7767-001023 | 7767 | 2018-10-12 16:06 | Section 4 | Material | NULL | Concrete Kerbs Splayed 45deg 125x255 (898227) | 462 | Each | 4.43 | 2046.66 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7767-001023 | 7767 | 2018-10-12 16:06 | Section 4 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 462 | Each | 3.4 | 1570.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7767-001023 | 7767 | 2018-10-12 16:06 | Section 4 | Material | Not on List | Not on List | 58 | NULL | 12 | 696 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7767-001023 | 7767 | 2018-10-12 16:06 | Section 4 | Material | Not on List | NULL | 1 | NULL | 55 | 55 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7767-001023 | 7767 | 2018-10-12 16:06 | Section 4 | Material | Not on List | NULL | 3 | NULL | 30 | 90 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7757-001023 | 7757 | 2018-10-12 14:39 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 200 | No | 7.1 | 1420 | Surveying Consumables | 2018-10-17 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7800-001023 | 7800 | 2018-10-15 14:52 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 250 | no | 7.1 | 1775 | Small Tools (Consumables) | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7806-001023 | 7806 | 2018-10-15 15:12 | Section 4 | Material | Not on List | Not on List | 15 | NULL | 175 | 2625 | Plastic Drainage | 2018-10-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7806-001023 | 7806 | 2018-10-15 15:12 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 1.21 | 24.2 | Plastic Drainage | 2018-10-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7806-001023 | 7806 | 2018-10-15 15:12 | Section 4 | Material | Not on List | Not on List | 40 | NULL | 14.93 | 597.2 | Plastic Drainage | 2018-10-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7806-001023 | 7806 | 2018-10-15 15:12 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 7.64 | 152.8 | Plastic Drainage | 2018-10-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7806-001023 | 7806 | 2018-10-15 15:12 | Section 4 | Material | Not on List | NULL | 200 | NULL | 0.33 | 66 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7771-001023 | 7771 | 2018-10-12 16:51 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1157.8 | Builders Merchants (General) | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7662-001023 | 7662 | 2018-10-11 08:53 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Bundle | 10 | 200 | Surveying Consumables | 2018-10-12 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7662-001023 | 7662 | 2018-10-11 08:53 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No. | 37 | 37 | Surveying Consumables | 2018-10-12 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5002-0015 | 5002 | 2018-08-13 15:53 | Section 4 | Material | Not on List | NULL | 241 | square meters | 11.21 | 0 | Blocks and Bricks | 2018-08-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7843-001023 | 7843 | 2018-10-16 13:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1166.02 | 1166 | Small Tools (Consumables) | 2018-10-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7716-001023 | 7716 | 2018-10-12 10:44 | Section 4 | Material | NULL | Concrete Kerbs Splayed 45deg 125x255 (898227) | 1000 | Each | 4.43 | 4430 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7770-001023 | 7770 | 2018-10-12 16:37 | Section 4 | Material | Not on List | Not on List | 825 | sqm | 4.34 | 3580.5 | Builders Merchants (General) | 2018-11-05 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7770-001023 | 7770 | 2018-10-12 16:37 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 79 | 316 | Builders Merchants (General) | 2018-11-05 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7770-001023 | 7770 | 2018-10-12 16:37 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 8.5 | 170 | Builders Merchants (General) | 2018-11-05 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7770-001023 | 7770 | 2018-10-12 16:37 | Section 4 | Material | NULL | NULL | 6 | NULL | 5 | 30 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7770-001023 | 7770 | 2018-10-12 16:37 | Section 4 | Material | NULL | NULL | 1 | NULL | 240 | 240 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7858-001023 | 7858 | 2018-10-16 17:00 | Section 4 | Material | NULL | Tensar TX160 4m x 75m (150563) | 15 | Each | 535 | 8025 | Geotextiles | 2018-10-17 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7886-001023 | 7886 | 2018-10-17 09:48 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-10-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-7740-001023 | 7740 | 2018-10-12 12:20 | Section 4 | Material | Not on List | Not on List | 10 | ea | 498 | 4980 | Not Sure | 2018-10-17 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7871-001023 | 7871 | 2018-10-17 07:09 | Section 4 | Material | NULL | Building Sand Bulk Bag (938155) | 5 | Each | 32.74 | 163.7 | Miscellaneous | 2018-10-22 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7796-001023 | 7796 | 2018-10-15 13:53 | Section 3 | Material | Not on List | Not on List | 160 | no. | 10.1 | 1616 | Fixings and Fasteners | 2018-10-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5012-0017 | 5012 | 2018-08-13 17:58 | Section 3 | Material | Aggregate | 6N ( 6P ) | 2000 | Tonnes | 15 | 30000 | NULL | 2018-08-15 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 606 - Import | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 2030 | Each | 1.45 | 2943.5 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs 125x150x914 BN Straight (753034) | 0 | Each | 2.93 | 0 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5223-00140 | 5223 | 2018-08-16 12:16 | Section 4 | Material | Not on List | Not on List | 50 | Each | 22 | 0 | Timber Products | 2018-08-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs 125x150x914 HB Straight (898181) | 100 | Each | 2.93 | 293 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 45 | Each | 3.4 | 153 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs Splayed 45deg 125x255 (898227) | 700 | Each | 4.43 | 3101 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 12 | Each | 11.94 | 143.28 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 12 | Each | 11.94 | 143.28 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Not on List | 3 | Each | 9.72 | 29.16 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Not on List | 3 | Each | 9.72 | 29.16 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Not on List | 0 | Each | NULL | 0 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Not on List | 40 | Each | 5.25 | 210 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Not on List | 30 | Each | 5.79 | 173.7 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7818 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 30 | No | 34 | 1020 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7818 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 20 | No | 31.37 | 627.4 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7818 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 30 | No | 34 | 1020 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7818 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 20 | No | 31.37 | 627.4 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7962-001023 | 7962 | 2018-10-18 13:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1680 | 1680 | Not Sure | 2018-11-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5242-00154 | 5242 | 2018-08-16 15:20 | Section 4 | Material | Not on List | Not on List | 40 | NULL | 64 | 2560 | Not Sure | 2018-08-17 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | Not on List | Not on List | 3.352 | tonnes | 538 | 1803.38 | Rebar and Mesh | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | Not on List | Not on List | 3.349 | tonnes | 538 | 1801.76 | Rebar and Mesh | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | Not on List | Not on List | 3.352 | tonnes | 538 | 1803.38 | Rebar and Mesh | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | Not on List | Not on List | 5.686 | tonnes | 538 | 3059.07 | Rebar and Mesh | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | Not on List | Not on List | 3.352 | tonnes | 538 | 1803.38 | Rebar and Mesh | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | NULL | Not on List | 1 | NULL | 125 | 125 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7892-001023 | 7892 | 2018-10-17 11:03 | Section 4 | Material | Misc | NULL | 112 | Bag | 2.9 | 324.8 | Not Sure | 2018-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7924-001023 | 7924 | 2018-10-17 16:25 | Section 4 | Material | Not on List | Not on List | 10 | packs | 168.35 | 1683.5 | Not Sure | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7924-001023 | 7924 | 2018-10-17 16:25 | Section 4 | Material | Not on List | Not on List | 5 | packs | 3.85 | 19.25 | Not Sure | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7924-001023 | 7924 | 2018-10-17 16:25 | Section 4 | Material | Not on List | Not on List | 7 | packs | 11 | 77 | Not Sure | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7960-001023 | 7960 | 2018-10-18 12:32 | Section 4 | Material | Not on List | Not on List | 10 | 25ltr Drum | 57.92 | 579.2 | Concrete Accessories | 2018-10-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7915-001023 | 7915 | 2018-10-17 14:58 | Section 4 | Material | Not on List | Not on List | 10 | rolls | 3.6 | 36 | Not Sure | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7915-001023 | 7915 | 2018-10-17 14:58 | Section 4 | Material | Not on List | Not on List | 300 | no | 1.32 | 396 | NULL | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7915-001023 | 7915 | 2018-10-17 14:58 | Section 4 | Material | NULL | Polypipe 110mm x 50m Ridgiduct Coil Purple (877806) | 6 | Each | 105.04 | 630.24 | Not Sure | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7915-001023 | 7915 | 2018-10-17 14:58 | Section 4 | Material | NULL | Polypipe 110mm x 50m Ridgiduct Coil Orange S/L (877804) | 3 | Each | 105.04 | 315.12 | Not Sure | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7915-001023 | 7915 | 2018-10-17 14:58 | Section 4 | Material | NULL | Polypipe 110mm Ridgiduct Coupler (877674) | 100 | Each | 2.6 | 260 | Not Sure | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7926-001023 | 7926 | 2018-10-17 16:45 | Section 4 | Material | Not on List | Not on List | 13 | 10ltr | 18.84 | 244.92 | Not Sure | 2018-10-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7926-001023 | 7926 | 2018-10-17 16:45 | Section 4 | Material | Not on List | Not on List | 6 | 25ltr | 57.92 | 347.52 | Not Sure | 2018-10-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7925-001023 | 7925 | 2018-10-17 16:18 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 101091.26 | 101091.26 | Not Sure | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7872-001023 | 7872 | 2018-10-17 07:14 | Section 4 | Material | Not on List | Not on List | 100 | Each | 3.46 | 346 | Builders Merchants (General) | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7872-001023 | 7872 | 2018-10-17 07:14 | Section 4 | Material | Not on List | Not on List | 5 | Each | 11.9 | 59.5 | Builders Merchants (General) | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7872-001023 | 7872 | 2018-10-17 07:14 | Section 4 | Material | Not on List | Not on List | 50 | Each | 0.33 | 16.5 | Builders Merchants (General) | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7872-001023 | 7872 | 2018-10-17 07:14 | Section 4 | Material | Not on List | Not on List | 20 | Each | 8.2 | 164 | Builders Merchants (General) | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7948-001023 | 7948 | 2018-10-18 09:25 | Section 3 | Material | Not on List | Not on List | 1 | Visit | 136.69 | 136.69 | Professional Services | 2018-10-19 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7668-001023 | 7668 | 2018-10-11 10:25 | Section 4 | Material | Not on List | Not on List | 8 | U | 31.35 | 250.8 | Concrete Accessories | 2018-10-22 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7668-001023 | 7668 | 2018-10-11 10:25 | Section 4 | Material | NULL | NULL | 1 | NULL | 25 | 25 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7830-001023 | 7830 | 2018-10-16 09:59 | Section 4 | Material | Not on List | Not on List | 600 | m | 29.28 | 17568 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7830-001023 | 7830 | 2018-10-16 09:59 | Section 4 | Material | Not on List | Not on List | 6 | ea | 3.59 | 21.54 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7830-001023 | 7830 | 2018-10-16 09:59 | Section 4 | Material | Not on List | Not on List | 5 | ea | 27.56 | 137.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8019-001023 | 8019 | 2018-10-19 10:24 | Section 3 | Material | NULL | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2018-10-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8019-001023 | 8019 | 2018-10-19 10:24 | Section 3 | Material | Not on List | Not on List | 20 | Rolls | 11.15 | 223 | Concrete Drainage | 2018-10-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7841-001023 | 7841 | 2018-10-16 12:58 | Section 4 | Material | Not on List | Not on List | 10 | 1t Bag | 32.5 | 325 | Builders Merchants (General) | 2018-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7841-001023 | 7841 | 2018-10-16 12:58 | Section 4 | Material | Not on List | Not on List | 112 | Bag | 2.26 | 253.12 | Builders Merchants (General) | 2018-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8015-001023 | 8015 | 2018-10-19 10:13 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 892.78 | 892.78 | Small Tools (Consumables) | 2018-10-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8039-001023 | 8039 | 2018-10-19 14:21 | Section 4 | Material | Not on List | Not on List | 200 | no | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-24 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-7985-001023 | 7985 | 2018-10-19 07:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 5054.62 | 5054.62 | PPE | 2018-10-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7953-001023 | 7953 | 2018-10-18 11:00 | Section 3 | Material | Not on List | Not on List | 40 | Ton | 69 | 2760 | Not Sure | 2018-10-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7807-001023 | 7807 | 2018-10-15 15:57 | Section 3 | Material | Not on List | Not on List | 24 | No | 32.08 | 769.92 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | BN07 - B1043 Offord Road Overbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12156-001025 | 12156 | 2019-02-08 13:01 | Core | Material | Not on List | Not on List | 3 | number packs | 21.45 | 64 | Office Supplies | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | NULL
MREQ-12629-001025 | 12629 | 2019-02-18 12:56 | Core | Material | Not on List | Not on List | 100 | number | 0.4 | 40 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12629-001025 | 12629 | 2019-02-18 12:56 | Core | Material | Not on List | Not on List | 200 | number | 0.22 | 44 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12571-001025 | 12571 | 2019-02-15 13:57 | Section 3 | Material | Not on List | Not on List | 100 | No | 7.1 | 710 | Builders Merchants (General) | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 16 | EA | 14.4 | 230 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 3 | EA | 10.12 | 30 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 2 | EA | 10.12 | 20 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 30 | EA | 5.92 | 178 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12639-001025 | 12639 | 2019-02-18 14:45 | Section 2 | Material | Not on List | Not on List | 52 | Tub | 63.22 | 3287 | Miscellaneous | 2019-02-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | NULL | Not on List | 30 | number | NULL | 0 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 30 | Each | 1.84 | 55.2 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 150 | Each | 0.85 | 127.5 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | NULL | Polypipe 150mm x 150mm 45deg Junction (878010) | 10 | Each | 14.4 | 144 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12629-001025 | 12629 | 2019-02-18 12:56 | Core | Material | Not on List | Not on List | 100 | number | 0.4 | 40 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12629-001025 | 12629 | 2019-02-18 12:56 | Core | Material | Not on List | Not on List | 200 | number | 0.22 | 44 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12642-001025 | 12642 | 2019-02-18 15:53 | Core | Material | Not on List | Not on List | 1 | number | 6995 | 6995 | Professional Services | 2019-02-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 15 | Each | 175 | 2625 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 15 | Each | 10.5 | 158 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 100 | Each | 23.14 | 2314 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 100 | Each | 3.38 | 338 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 20 | Each | 34.82 | 696 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 3 | Each | 47.04 | 141 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 2 | Each | 67.9 | 136 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 3 | Each | 43.16 | 129 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 3 | Each | 35.52 | 107 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12652-001025 | 12652 | 2019-02-18 16:28 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Miscellaneous | 2019-03-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12582-001025 | 12582 | 2019-02-15 15:00 | Section 3 | Material | Not on List | Not on List | 25 | no | 8.8 | 220 | Fixings and Fasteners | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 16 | EA | 14.4 | 230.4 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 3 | EA | 10.12 | 30.36 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 2 | EA | 10.12 | 20.24 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 30 | EA | 5.92 | 177.6 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5355-00246 | 5355 | 2018-08-20 14:08 | Section 3 | Material | Not on List | Not on List | 37 | NULL | NULL | 0 | Office Supplies | 2018-08-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12664-001025 | 12664 | 2019-02-19 08:38 | Core | Material | Not on List | Not on List | 1 | ea | 42200 | 42200 | Office Supplies | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12669-001025 | 12669 | 2019-02-19 09:41 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12242-001025 | 12242 | 2019-02-11 14:13 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1320 | 1320 | Laboratory Equipment / Certification | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12032-001025 | 12032 | 2019-02-07 07:04 | Section 4 | Material | Not on List | Not on List | 1 | Each | 396 | 396 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12687-001025 | 12687 | 2019-02-19 12:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12692-001025 | 12692 | 2019-02-19 12:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 180 | metres | 3.52 | 634 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 6 | Each | 7.68 | 46 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 5 | Each | 7.68 | 38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 903 | metres | 1.5 | 1355 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5539-00352 | 5539 | 2018-08-22 16:19 | Section 3 | Material | Not on List | Not on List | 600 | ea | 0.08 | 48 | Blocks and Bricks | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 30 | metres | 3.03 | 91 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Not on List | 540 | metres | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Not on List | 18 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Not on List | 18 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Not on List | 90 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12693-001025 | 12693 | 2019-02-19 13:48 | Section 2 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 40 | Each | 24.32 | 973 | Timber Products | 2019-02-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12700-001025 | 12700 | 2019-02-19 14:07 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 3 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12700-001025 | 12700 | 2019-02-19 14:07 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | PPE | 2019-02-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12700-001025 | 12700 | 2019-02-19 14:07 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | PPE | 2019-02-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5539-00352 | 5539 | 2018-08-22 16:19 | Section 3 | Material | Not on List | Not on List | 500 | ea | 0.63 | 315 | Blocks and Bricks | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 30 | Each | 3.52 | 106 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 15 | Each | 5.43 | 81 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 10 | Each | 7.68 | 77 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 10 | Each | 7.68 | 77 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12388-001025 | 12388 | 2019-02-13 13:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2623.5 | 2623.5 | Miscellaneous | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12371-001025 | 12371 | 2019-02-13 10:19 | Section 4 | Material | Not on List | Not on List | 1 | Each | 57.02 | 57.02 | Miscellaneous | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1800 x 1000 D/S (528457) | 1 | Each | 155.88 | 156 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5539-00352 | 5539 | 2018-08-22 16:19 | Section 3 | Material | Not on List | Not on List | 10 | ea | 43.05 | 430.5 | Fixings and Fasteners | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1800 x 750 D/S (528456) | 1 | Each | 116.91 | 117 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM 1800 Cover Slab 600x600 Opening (985438) | 1 | Each | 144.04 | 144 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | Not on List | 20 | NULL | NULL | 0 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 7 | Each | 67.9 | 475 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 432 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11944-001025 | 11944 | 2019-02-05 15:29 | Core | Material | Not on List | Not on List | 1 | each | 516 | 516 | Office Supplies | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12718-001025 | 12718 | 2019-02-19 15:35 | Section 2 | Material | Not on List | Not on List | 100 | m | NULL | 0 | Concrete Accessories | 2019-02-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Skip 12 cubic yard | 3 | Each | 195 | 585 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5539-00352 | 5539 | 2018-08-22 16:19 | Section 3 | Material | Not on List | Not on List | 10 | ea | 95.62 | 956.2 | Electrical | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 9 | Each | 370 | 3330 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 2 | Each | 150 | 300 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 2.54 | Each | 115 | 292 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11947-001025 | 11947 | 2019-02-05 15:41 | Core | Material | Not on List | Not on List | 1 | number | 1892.5 | 1892.5 | Office Supplies | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12044-001025 | 12044 | 2019-02-07 10:11 | Core | Material | Not on List | Not on List | 1 | NULL | 226.4 | 226.4 | Laboratory Equipment / Certification | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12499-001025 | 12499 | 2019-02-14 14:50 | Core | Material | PPE, Small Tools and Consumables | Cream Pristine After Work Restore 1 Litre Cartridge (548142) | 1 | Each | 10.45 | 10.45 | Miscellaneous | 2019-02-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12499-001025 | 12499 | 2019-02-14 14:50 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 6 | 6 | Miscellaneous | 2019-02-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12721-001025 | 12721 | 2019-02-19 15:44 | Section 3 | Material | Concrete Drainage | Not on List | 700 | No. | NULL | 0 | Concrete Drainage | 2019-02-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5539-00352 | 5539 | 2018-08-22 16:19 | Section 3 | Material | Not on List | Not on List | 3 | ea | 57.54 | 172.62 | Electrical | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12721-001025 | 12721 | 2019-02-19 15:44 | Section 3 | Material | Concrete Drainage | Not on List | 76 | No. | NULL | 0 | Ductile Drainage | 2019-02-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | Combined Drainage | Not on List | 9 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | Combined Drainage | Not on List | 13 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | Combined Drainage | Not on List | 20 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | Combined Drainage | Not on List | 40 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12734-001025 | 12734 | 2019-02-19 16:49 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 643.99 | 3863.94 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 20.24 | 121.44 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 10.13 | 10.13 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 82.08 | 82.08 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 14.99 | 14.99 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 11.7 | 70.2 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12759-001025 | 12759 | 2019-02-20 08:46 | Section 2 | Material | Bagged | Not on List | 20 | Units | NULL | 0 | Builders Merchants (General) | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12759-001025 | 12759 | 2019-02-20 08:46 | Section 2 | Material | Bagged | Not on List | 20 | Bucket | NULL | 0 | Builders Merchants (General) | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12389-001025 | 12389 | 2019-02-13 13:16 | Section 6 | Material | Not on List | Not on List | 1 | sum | 960.8 | 960.8 | Miscellaneous | 2019-02-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-12764-001025 | 12764 | 2019-02-20 09:46 | Section 2 | Material | Not on List | Not on List | 50 | number | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12764-001025 | 12764 | 2019-02-20 09:46 | Section 2 | Material | Not on List | Not on List | 5 | number | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12764-001025 | 12764 | 2019-02-20 09:46 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12764-001025 | 12764 | 2019-02-20 09:46 | Section 2 | Material | Not on List | Not on List | 5 | number | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12764-001025 | 12764 | 2019-02-20 09:46 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 150 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12659-001025 | 12659 | 2019-02-19 07:50 | Section 4 | Material | Not on List | Not on List | 1 | Each | 318.78 | 318.78 | Gas Oil | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 15 | Each | 175 | 2625 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 15 | Each | 10.5 | 157.5 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 100 | Each | 23.14 | 2314 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 100 | Each | 3.38 | 338 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 20 | Each | 34.82 | 696.4 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 3 | Each | 47.04 | 141.12 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 2 | Each | 67.9 | 135.8 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 3 | Each | 43.16 | 129.48 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 3 | Each | 35.52 | 106.56 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12771-001025 | 12771 | 2019-02-20 11:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No | NULL | 0 | Builders Merchants (General) | 2019-02-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12551-001025 | 12551 | 2019-02-15 10:22 | Section 2 | Material | Aggregate | 6G | 300 | Tonnes | 22 | 6600 | Aggregate | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12722-001025 | 12722 | 2019-02-19 15:43 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 4602.1 | Each | 1 | 4602.1 | Waste (General) | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12722-001025 | 12722 | 2019-02-19 15:43 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 1405 | Each | 1 | 1405 | Waste (General) | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12776-001025 | 12776 | 2019-02-20 13:16 | Section 2 | Material | Not on List | Not on List | 30 | Rolls | NULL | 0 | Concrete Accessories | 2019-02-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12407-001025 | 12407 | 2019-02-13 16:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1062.5 | 1062.5 | Miscellaneous | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18605-001025 | 18605 | 2019-06-05 14:55 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 2041.62 | 2041.62 | Miscellaneous | 2019-06-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 250 | no. | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 5 | no. | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 4 | no. | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 9 | no. | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 40 | roll | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19031-001025 | 19031 | 2019-06-13 08:29 | Section 2 | Material | Not on List | Not on List | 1.132 | tonnes | NULL | 0 | NULL | 2019-06-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18904-001025 | 18904 | 2019-06-11 12:30 | Core | Material | Not on List | Not on List | 1 | NULL | 1230 | 1230 | Miscellaneous | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18593-001025 | 18593 | 2019-06-05 12:31 | Section 4 | Material | Not on List | Not on List | 1 | Each | 457.78 | 457.78 | Concrete Drainage | 2019-06-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18593-001025 | 18593 | 2019-06-05 12:31 | Section 4 | Material | NULL | Not on List | 1 | Each | 50 | 50 | Concrete Drainage | 2019-06-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19041-001025 | 19041 | 2019-06-13 12:22 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Surveying Consumables | 2019-06-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18444-001025 | 18444 | 2019-06-03 14:15 | Section 4 | Material | Not on List | Not on List | 100 | 5m | 6.3 | 630 | Concrete Accessories | 2019-06-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19033-001025 | 19033 | 2019-06-13 09:01 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 15 | Each | 48.86 | 732.9 | Plastic Drainage | 2019-06-17 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19049-001025 | 19049 | 2019-06-13 14:40 | Core | Material | Not on List | Not on List | 1 | each | 350 | 350 | Training | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19049-001025 | 19049 | 2019-06-13 14:40 | Core | Material | Not on List | Not on List | 1 | each | 200 | 200 | Training | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18893-001025 | 18893 | 2019-06-11 11:07 | Section 4 | Material | Not on List | Not on List | 12 | EA | 47.89 | 574.68 | Electrical | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18893-001025 | 18893 | 2019-06-11 11:07 | Section 4 | Material | Not on List | Not on List | 6 | EA | 62.45 | 374.7 | Electrical | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19030-001025 | 19030 | 2019-06-13 08:29 | Section 4 | Material | Not on List | Not on List | 175 | Each | 16.06 | 2810.5 | Concrete Accessories | 2019-06-25 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18996-001025 | 18996 | 2019-06-12 15:20 | Section 2 | Material | Not on List | Not on List | 24 | Pallets | NULL | 0 | Blocks and Bricks | 2019-06-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19061-001025 | 19061 | 2019-06-13 16:13 | Section 4 | Material | Not on List | Not on List | 10000 | m3 | NULL | 0 | Miscellaneous | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19064-001025 | 19064 | 2019-06-13 16:17 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-06-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19064-001025 | 19064 | 2019-06-13 16:17 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-06-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19064-001025 | 19064 | 2019-06-13 16:17 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-06-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18908-001025 | 18908 | 2019-06-11 13:45 | Section 4 | Material | Not on List | Not on List | 100 | number | 0.56 | 56 | Concrete Accessories | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19000-001025 | 19000 | 2019-06-12 14:53 | Section 4 | Material | Not on List | Not on List | 25 | Each | 10.5 | 262.5 | Builders Merchants (General) | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 36 | Each | 24.99 | 899.64 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 108 | Each | 2.65 | 286.2 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 216 | Each | 2 | 432 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 60 | Each | 37.6 | 2256 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 180 | Each | 7.06 | 1270.8 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 360 | Each | 2.97 | 1069.2 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 110 | Each | 130.26 | 14328.6 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 330 | Each | 18.84 | 6217.2 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 660 | Each | 9.76 | 6441.6 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 60 | Each | 125.94 | 7556.4 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 180 | Each | 18.87 | 3396.6 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 360 | Each | 10.84 | 3902.4 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 60 | Each | 179.74 | 10784.4 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 180 | Each | 38.36 | 6904.8 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 360 | Each | 22.36 | 8049.6 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Bend 45deg (878000) | 100 | Each | 8.25 | 825 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Bend 30deg (877999) | 100 | Each | 8.25 | 825 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 400 | Each | 0.91 | 364 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Bend 11.25deg (878082) | 1 | Each | 52.76 | 52.76 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Bend 22.5deg (878083) | 3 | Each | 52.76 | 158.28 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 20 | Each | 52.76 | 1055.2 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 2 | Each | 112.41 | 224.82 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 94 | lengths (3m) | 24.1 | 2265.4 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 96 | lengths (3m) | 5.6 | 537.6 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 8 | lengths (3m) | 3.35 | 26.8 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 8 | lengths (3m) | 2.77 | 22.16 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 72 | lengths (3m) | 4.5 | 324 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 16 | lengths (3m) | 5.01 | 80.16 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 16 | lengths (3m) | 3.67 | 58.72 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 72 | lengths (3m) | 3.91 | 281.52 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 2 | Hun | 32.76 | 65.52 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 2 | Hun | 3.6 | 7.2 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 2 | Hun | 0.81 | 1.62 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18843-001025 | 18843 | 2019-06-10 11:51 | Section 3 | Material | Not on List | Not on List | 1 | No | 953.87 | 953.87 | Rebar and Mesh | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19027-001025 | 19027 | 2019-06-13 08:14 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18869-001025 | 18869 | 2019-06-10 16:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 7107.32 | 7107.32 | PPE | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19058-001025 | 19058 | 2019-06-13 16:05 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 8.66 | 34.64 | Small Tools (Consumables) | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | Not on List | 2 | NULL | 38.08 | 76.16 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | Not on List | 1 | NULL | 63.93 | 63.93 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | Not on List | 6 | NULL | 85.23 | 511.38 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | Not on List | 6 | NULL | 48.02 | 288.12 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 60 | Each | 165.1 | 9906 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | NULL | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 5 | Each | 235 | 1175 | Plastic Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | Not on List | 10 | NULL | 6.76 | 67.6 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17359-001025 | 17359 | 2019-05-14 09:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 150 | Each | 1.31 | 196.5 | Small Tools (Consumables) | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-19034-001025 | 19034 | 2019-06-13 09:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 11.03 | 110.3 | Small Tools (Consumables) | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17507-001025 | 17507 | 2019-05-16 09:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 305.98 | 305.98 | Small Tools (Consumables) | 2019-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18895-001025 | 18895 | 2019-06-11 11:33 | Section 4 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 3 | Each | 165.1 | 495.3 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18895-001025 | 18895 | 2019-06-11 11:33 | Section 4 | Material | Concrete Drainage | CPM 750mm Concrete Rocker (249360) | 4 | Each | 198.12 | 792.48 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18895-001025 | 18895 | 2019-06-11 11:33 | Section 4 | Material | Concrete Drainage | CPM 750mm Concrete Socket (890395) | 2 | Each | 198.12 | 396.24 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18895-001025 | 18895 | 2019-06-11 11:33 | Section 4 | Material | Not on List | Not on List | 2 | Each | 198.12 | 396.24 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19012-001025 | 19012 | 2019-06-12 17:31 | Section 4 | Material | Not on List | Not on List | 2 | Each | 1086.46 | 2172.92 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6797-00751 | 6797 | 2018-09-20 15:46 | Section 3 | Material | Not on List | Not on List | 2000 | NULL | 2 | 4000 | NULL | 2018-09-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19050-001025 | 19050 | 2019-06-13 15:14 | Section 4 | Material | Concrete Drainage | CPM 1800mm Concrete Socket (890407) | 1 | Each | 1086.46 | 1086.46 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19050-001025 | 19050 | 2019-06-13 15:14 | Section 4 | Material | Concrete Drainage | CPM 1800mm Concrete Spigot (890384) | 1 | Each | 1086.46 | 1086.46 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18763-001025 | 18763 | 2019-06-07 12:46 | Section 4 | Material | Not on List | Not on List | 110 | Each | 130.26 | 14328.6 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18763-001025 | 18763 | 2019-06-07 12:46 | Section 4 | Material | Not on List | Not on List | 220 | Each | 18.84 | 4144.8 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18763-001025 | 18763 | 2019-06-07 12:46 | Section 4 | Material | Not on List | Not on List | 550 | Each | 9.76 | 5368 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6776-00751 | 6776 | 2018-09-20 13:14 | Section 3 | Material | Not on List | Not on List | 50 | NULL | 1.8 | 90 | PPE | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-19125-001025 | 19125 | 2019-06-14 12:13 | Section 3 | Material | Not on List | Not on List | 100 | No | NULL | 0 | Builders Merchants (General) | 2019-06-19 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19141-001025 | 19141 | 2019-06-14 12:54 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Reinforcement | 2019-06-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6776-00751 | 6776 | 2018-09-20 13:14 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1124.61 | 1124.61 | Small Tools (Consumables) | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-19112-001025 | 19112 | 2019-06-14 10:56 | Section 5 | Material | Not on List | Not on List | 10 | rolls | 0 | 0 | Builders Merchants (General) | 2019-06-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19074-001025 | 19074 | 2019-06-13 18:48 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 60 | EA | 46.55 | 2793 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 2 | EA | 50.96 | 101.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 1 | EA | 66.64 | 66.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 2 | EA | 66.64 | 133.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 1 | EA | 128 | 128 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6690-00750 | 6690 | 2018-09-18 16:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1263.47 | 1263.47 | PPE | 2018-09-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 8 | EA | 14.95 | 119.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 1 | EA | 38 | 38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 5 | EA | 38 | 190 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 1 | EA | 125 | 125 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18687-001025 | 18687 | 2019-06-06 14:38 | Section 4 | Material | Not on List | Not on List | 15 | Each | 15.96 | 239.4 | Small Tools (Consumables) | 2019-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18687-001025 | 18687 | 2019-06-06 14:38 | Section 4 | Material | Not on List | Not on List | 15 | Each | 15.96 | 239.4 | Small Tools (Consumables) | 2019-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6690-00750 | 6690 | 2018-09-18 16:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 473.47 | 473.47 | Janitorial | 2018-09-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19212-001025 | 19212 | 2019-06-17 10:45 | Section 3 | Material | Not on List | Not on List | 6 | No | NULL | 0 | Builders Merchants (General) | 2019-06-19 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19213-001025 | 19213 | 2019-06-17 11:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 160 | NULL | 16.57 | 2651 | Small Tools (Consumables) | 2019-06-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-19215-001025 | 19215 | 2019-06-17 11:21 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19192-001025 | 19192 | 2019-06-17 07:37 | Section 5 | Material | Plastic Drainage | Not on List | NULL | 1 | 645.65 | 0 | NULL | NULL | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19222-001025 | 19222 | 2019-06-17 13:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19225-001025 | 19225 | 2019-06-17 14:08 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19234-001025 | 19234 | 2019-06-17 15:17 | Section 2 | Material | Waste Management | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19040-001025 | 19040 | 2019-06-13 12:02 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 32 | No. | NULL | 0 | Miscellaneous | 2019-06-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19066-001025 | 19066 | 2019-06-13 16:24 | Section 2 | Material | Not on List | Not on List | 11 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19066-001025 | 19066 | 2019-06-13 16:24 | Section 2 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19042-001025 | 19042 | 2019-06-13 08:43 | Section 6 | Material | Concrete Drainage | Not on List | 26 | NULL | 58 | 1508 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19042-001025 | 19042 | 2019-06-13 08:43 | Section 6 | Material | Concrete Drainage | Not on List | 5 | NULL | 6.76 | 33.8 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19247-001025 | 19247 | 2019-06-17 15:57 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-06-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19268-001025 | 19268 | 2019-06-18 09:07 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-06-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19230-001025 | 19230 | 2019-06-17 14:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | 3.88 | 194 | Small Tools (Consumables) | 2019-06-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19221-001025 | 19221 | 2019-06-17 13:45 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 229.62 | 229.62 | Small Tools (Consumables) | 2019-06-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19124-001025 | 19124 | 2019-06-14 12:01 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Ductile Drainage | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19124-001025 | 19124 | 2019-06-14 12:01 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Ductile Drainage | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19124-001025 | 19124 | 2019-06-14 12:01 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Ductile Drainage | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19124-001025 | 19124 | 2019-06-14 12:01 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Ductile Drainage | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 1 | Each | 39.22 | 39.22 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 1 | Each | 39.22 | 39.22 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 5 | Each | 34.93 | 174.65 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 3 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16320-001025 | 16320 | 2019-04-24 14:16 | Section 4 | Material | NULL | NULL | 3 | Each | 35.91 | 107.73 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16320-001025 | 16320 | 2019-04-24 14:16 | Section 4 | Material | Not on List | NULL | 5 | Each | 250.64 | 1253.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16320-001025 | 16320 | 2019-04-24 14:16 | Section 4 | Material | NULL | NULL | 1 | Each | 170 | 170 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16830-001025 | 16830 | 2019-05-02 15:51 | Section 3 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 400 | Each | 2.31 | 924 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16835-001025 | 16835 | 2019-05-02 16:40 | Section 3 | Material | Not on List | Not on List | 1000 | No | NULL | 0 | Builders Merchants (General) | 2019-05-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16835-001025 | 16835 | 2019-05-02 16:40 | Section 3 | Material | Not on List | Not on List | 1000 | No | NULL | 0 | Builders Merchants (General) | 2019-05-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16322-001025 | 16322 | 2019-04-24 14:27 | Section 4 | Material | NULL | NULL | 110 | Each | 30.73 | 3380.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16322-001025 | 16322 | 2019-04-24 14:27 | Section 4 | Material | NULL | NULL | 2 | EA | 36.31 | 72.62 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16322-001025 | 16322 | 2019-04-24 14:27 | Section 4 | Material | NULL | NULL | 2 | EA | 250.64 | 501.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 100 | Each | 24.32 | 2432 | Timber Products | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 50 | Each | 6.82 | 341 | Timber Products | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | Timber | Not on List | 50 | Each | NULL | 0 | Timber Products | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | Not on List | Not on List | 5 | Packs | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6330-00670 | 6330 | 2018-09-11 13:21 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 198 | Each | 7.9 | 1564.2 | Miscellaneous | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16633-001025 | 16633 | 2019-04-30 10:29 | Section 4 | Material | NULL | NULL | 3400 | Each | 19.96 | 67864 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16633-001025 | 16633 | 2019-04-30 10:29 | Section 4 | Material | NULL | NULL | 27 | Each | 250.64 | 6767.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16633-001025 | 16633 | 2019-04-30 10:29 | Section 4 | Material | NULL | NULL | 16 | Each | 40.16 | 642.56 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16633-001025 | 16633 | 2019-04-30 10:29 | Section 4 | Material | NULL | NULL | 4 | Each | 4.9 | 19.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16633-001025 | 16633 | 2019-04-30 10:29 | Section 4 | Material | NULL | NULL | 200 | Each | 12.5 | 2500 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16851-001025 | 16851 | 2019-05-03 08:06 | Section 5 | Material | Twinwall | Not on List | 42 | No | NULL | 0 | Plastic Drainage | 2019-05-07 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6329-00688 | 6329 | 2018-09-11 13:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 156 | Each | 15.37 | 2397.72 | Miscellaneous | 2018-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16851-001025 | 16851 | 2019-05-03 08:06 | Section 5 | Material | Twinwall | Not on List | 7 | No | NULL | 0 | Plastic Drainage | 2019-05-07 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16851-001025 | 16851 | 2019-05-03 08:06 | Section 5 | Material | Twinwall | Not on List | 55 | No | NULL | 0 | Plastic Drainage | 2019-05-07 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16851-001025 | 16851 | 2019-05-03 08:06 | Section 5 | Material | Twinwall | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-05-07 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16780-001025 | 16780 | 2019-05-02 08:10 | Section 4 | Material | Not on List | Not on List | 50 | Each | 4.95 | 247.5 | Concrete Accessories | 2019-05-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16780-001025 | 16780 | 2019-05-02 08:10 | Section 4 | Material | Not on List | Not on List | 8 | Each | 166.22 | 1329.76 | Concrete Accessories | 2019-05-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-6329-00688 | 6329 | 2018-09-11 13:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 156 | Each | 15.37 | 2397.72 | Miscellaneous | 2018-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | NULL | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Bucket Flexi Tub 26 Litre Black (506342) | 20 | Each | 7.42 | 148 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Bucket Flexi Tub 26 Litre Black (506342) | 20 | Each | 7.42 | 148 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289) | 5 | Each | 7.32 | 37 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Box | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | Timber | 2440x1220x12mm Shuttering Ply (638572) | 1 | Load | 16.5 | 17 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-15626-001025 | 15626 | 2019-04-10 15:46 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 72 | Each | 11.34 | 816.48 | Plastic Drainage | 2019-04-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15626-001025 | 15626 | 2019-04-10 15:46 | Section 3 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 10 | Each | 42.87 | 428.7 | Plastic Drainage | 2019-04-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15626-001025 | 15626 | 2019-04-10 15:46 | Section 3 | Material | Not on List | Not on List | 5 | rolls | 37.6 | 188 | Plastic Drainage | 2019-04-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16793-001025 | 16793 | 2019-05-02 09:25 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 0 | Each | 47.04 | 0 | Concrete Drainage | 2019-05-07 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16793-001025 | 16793 | 2019-05-02 09:25 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 30 | Each | 36.94 | 1108.2 | Concrete Drainage | 2019-05-07 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16882-001025 | 16882 | 2019-05-03 13:49 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-05-07 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16858-001025 | 16858 | 2019-05-03 08:55 | Section 3 | Material | Not on List | Not on List | 10 | ea | 36 | 360 | Small Tools (Consumables) | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16860-001025 | 16860 | 2019-05-03 09:34 | Core | Material | Not on List | Not on List | 96 | ea | 2.5 | 240 | Miscellaneous | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16865-001025 | 16865 | 2019-05-03 10:55 | Section 3 | Material | Not on List | Not on List | 30 | NULL | 0.68 | 20.4 | Miscellaneous | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 9 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 10 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 28 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 12 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 10 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5931-00580 | 5931 | 2018-09-03 11:55 | Section 4 | Material | Not on List | Not on List | 90 | Each | 4 | 360 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 24 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5931-00580 | 5931 | 2018-09-03 11:55 | Section 4 | Material | Not on List | Not on List | 208 | Each | 3.4 | 707.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22432-001025 | 22432 | 2019-08-19 07:12 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22440-001025 | 22440 | 2019-08-19 07:57 | Core | Material | PPE, Small Tools and Consumables | Stake Marking Out Wooden 1200mm Nominal C.r.code Swcoc004463 (740904) | 50 | Each | 1.07 | 54 | Surveying Consumables | 2019-08-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5931-00580 | 5931 | 2018-09-03 11:55 | Section 4 | Material | Not on List | Not on List | 290 | Each | 36.9 | 10701 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22443-001025 | 22443 | 2019-08-19 08:04 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21542-001025 | 21542 | 2019-07-30 10:44 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21547-001025 | 21547 | 2019-07-30 11:10 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22259-001025 | 22259 | 2019-08-14 09:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Small Tools (Consumables) | 2019-08-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5931-00580 | 5931 | 2018-09-03 11:55 | Section 4 | Material | Not on List | Not on List | 2 | Each | 30 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22332-001025 | 22332 | 2019-08-15 14:36 | Section 1 | Material | Concrete Drainage | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-09-09 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-22176-001025 | 22176 | 2019-08-12 17:09 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 30.24 | 302.4 | Small Tools (Consumables) | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22324-001025 | 22324 | 2019-08-15 13:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1400 | Each | 0.37 | 518 | Miscellaneous | 2019-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6072-00608 | 6072 | 2018-09-05 12:09 | Section 4 | Material | Not on List | Not on List | 50 | Each | 3.12 | 156 | Builders Merchants (General) | 2018-09-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22234-001025 | 22234 | 2019-08-13 16:20 | Section 4 | Material | Not on List | Not on List | 3 | Number | 275 | 825 | Surveying Consumables | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22462-001025 | 22462 | 2019-08-19 11:46 | Core | Material | Not on List | Not on List | 1 | Sum | 6758.41 | 6758 | Miscellaneous | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6195-00639 | 6195 | 2018-09-07 11:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 35.5 | 71 | Small Tools (Consumables) | 2018-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22255-001025 | 22255 | 2019-08-14 08:53 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2401 | 2401 | Miscellaneous | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22252-001025 | 22252 | 2019-08-14 08:38 | Section 4 | Material | Not on List | Not on List | 1 | Each | 142.5 | 142.5 | Miscellaneous | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22139-001025 | 22139 | 2019-08-12 09:37 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 2889.15 | 2889.15 | Miscellaneous | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22422-001025 | 22422 | 2019-08-18 14:09 | Section 5 | Material | Twinwall | Not on List | 8 | No | 193.09 | 1544.72 | Plastic Drainage | 2019-09-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22422-001025 | 22422 | 2019-08-18 14:09 | Section 5 | Material | Twinwall | Not on List | 14 | No | 130.26 | 1823.64 | Plastic Drainage | 2019-09-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22422-001025 | 22422 | 2019-08-18 14:09 | Section 5 | Material | Twinwall | Not on List | 22 | No | 125.94 | 2770.68 | Plastic Drainage | 2019-09-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6209-00640 | 6209 | 2018-09-07 13:26 | Section 4 | Material | Not on List | Not on List | 2 | Each | 9.54 | 19.08 | Miscellaneous | 2018-09-14 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22422-001025 | 22422 | 2019-08-18 14:09 | Section 5 | Material | Twinwall | Not on List | 20 | No | 10.84 | 216.8 | Plastic Drainage | 2019-09-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22422-001025 | 22422 | 2019-08-18 14:09 | Section 5 | Material | Twinwall | Not on List | 30 | No | 9.76 | 292.8 | Plastic Drainage | 2019-09-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21491-001025 | 21491 | 2019-07-29 11:10 | Section 4 | Material | Waste Management | Not on List | 1 | Each | 468.65 | 468.65 | Waste (General) | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22385-001025 | 22385 | 2019-08-16 09:50 | Core | Material | NULL | NULL | 1 | Each | 406 | 406 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21932-001025 | 21932 | 2019-08-07 10:12 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2292.65 | 2292.65 | Miscellaneous | 2019-08-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22195-001025 | 22195 | 2019-08-13 08:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1500.74 | 1500.74 | Miscellaneous | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22197-001025 | 22197 | 2019-08-13 08:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1583.44 | 1583.44 | Miscellaneous | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22495-001025 | 22495 | 2019-08-19 16:44 | Core | Material | Not on List | Not on List | 6 | EA | 55 | 330 | Miscellaneous | 2019-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22141-001025 | 22141 | 2019-08-12 09:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 20 | 80 | Surveying Consumables | 2019-08-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6209-00640 | 6209 | 2018-09-07 13:26 | Section 4 | Material | Not on List | Not on List | 2 | Each | 138.54 | 277.08 | Miscellaneous | 2018-09-14 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22141-001025 | 22141 | 2019-08-12 09:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 200 | Each | 0.8 | 160 | Surveying Consumables | 2019-08-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22465-001025 | 22465 | 2019-08-19 12:59 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1019.85 | Each | 1 | 1019.85 | PPE | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22515-001025 | 22515 | 2019-08-20 07:39 | Section 5 | Material | Timber | Not on List | 50 | Each | NULL | 0 | PPE | 2019-08-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-22515-001025 | 22515 | 2019-08-20 07:39 | Section 5 | Material | Timber | Not on List | 40 | Each | NULL | 0 | PPE | 2019-08-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-22389-001025 | 22389 | 2019-08-16 11:34 | Core | Material | NULL | NULL | 10 | Pack 2 | 1.1 | 11 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6209-00640 | 6209 | 2018-09-07 13:26 | Section 4 | Material | Not on List | Not on List | 2 | Each | 88.92 | 177.84 | Miscellaneous | 2018-09-14 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22466-001025 | 22466 | 2019-08-19 13:17 | Section 3 | Material | Kerbs | Not on List | 4 | No | 7.96 | 31.84 | Builders Merchants (General) | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22466-001025 | 22466 | 2019-08-19 13:17 | Section 3 | Material | Kerbs | Not on List | 4 | No | 7.96 | 31.84 | Builders Merchants (General) | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22221-001025 | 22221 | 2019-08-13 12:38 | Section 3 | Material | Not on List | Not on List | 4 | 3m lengths | 1.77 | 7.08 | Miscellaneous | 2019-08-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1506 - Detector Installations | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22221-001025 | 22221 | 2019-08-13 12:38 | Section 3 | Material | Not on List | Not on List | 4 | 3m lengths | 9.36 | 37.44 | Miscellaneous | 2019-08-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1506 - Detector Installations | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22337-001025 | 22337 | 2019-08-15 13:33 | Section 4 | Material | NULL | NULL | 500 | Each | 7.1 | 3550 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22337-001025 | 22337 | 2019-08-15 13:33 | Section 4 | Material | NULL | NULL | 4 | Each | 9 | 36 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22337-001025 | 22337 | 2019-08-15 13:33 | Section 4 | Material | NULL | NULL | 120 | Each | 17.9 | 2148 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22355-001025 | 22355 | 2019-08-15 08:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 7.24 | 7.24 | Miscellaneous | 2019-08-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Not on List | 8 | no | 145 | 1160 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6267 | 6267 | 2018-09-10 13:49 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.8 | 160 | Surveying Consumables | 2018-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22355-001025 | 22355 | 2019-08-15 08:06 | Section 4 | Material | Not on List | Not on List | 2 | Each | 13.95 | 27.9 | Miscellaneous | 2019-08-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22388-001025 | 22388 | 2019-08-16 10:47 | Section 3 | Material | Not on List | Not on List | 1 | No. | 1660 | 1660 | Flow Control | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22388-001025 | 22388 | 2019-08-16 10:47 | Section 3 | Material | Not on List | Not on List | 2 | No. | 3320 | 6640 | Flow Control | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22388-001025 | 22388 | 2019-08-16 10:47 | Section 3 | Material | Not on List | Not on List | 1 | No. | 1765 | 1765 | Flow Control | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22530-001025 | 22530 | 2019-08-20 14:33 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Buyers
MREQ-22532-001025 | 22532 | 2019-08-20 14:52 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-08-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6268-00654 | 6268 | 2018-09-10 14:32 | Section 4 | Material | Not on List | Not on List | 5 | Roll | 241.07 | 1205.35 | Electrical | 2018-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22554-001025 | 22554 | 2019-08-20 17:41 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22573-001025 | 22573 | 2019-08-21 06:37 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-22574-001025 | 22574 | 2019-08-21 06:44 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-22575-001025 | 22575 | 2019-08-21 06:52 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-6268-00654 | 6268 | 2018-09-10 14:32 | Section 4 | Material | Not on List | Not on List | 53 | Each | 8.8 | 466.4 | Electrical | 2018-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22593-001025 | 22593 | 2019-08-21 09:44 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-22529-001025 | 22529 | 2019-08-20 14:25 | Section 4 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 200 | Each | 24.99 | 4998 | Plastic Drainage | 2019-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22529-001025 | 22529 | 2019-08-20 14:25 | Section 4 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 400 | Each | 3.65 | 1460 | Plastic Drainage | 2019-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22529-001025 | 22529 | 2019-08-20 14:25 | Section 4 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 800 | Each | 2 | 1600 | Plastic Drainage | 2019-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22529-001025 | 22529 | 2019-08-20 14:25 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 40 | Each | 48.92 | 1956.8 | Concrete Drainage | 2019-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22518-001025 | 22518 | 2019-08-20 11:33 | Section 5 | Material | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 142 | Each | 4.42 | 627.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6271-00656 | 6271 | 2018-09-10 13:35 | Section 4 | Material | Not on List | Not on List | 3.74 | Tonnes | 538 | 2012.12 | Rebar and Mesh | 2018-09-21 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22518-001025 | 22518 | 2019-08-20 11:33 | Section 5 | Material | Kerbs | Not on List | 2 | NULL | 22.4 | 44.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22518-001025 | 22518 | 2019-08-20 11:33 | Section 5 | Material | Kerbs | Not on List | 2 | NULL | 18.45 | 36.9 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22518-001025 | 22518 | 2019-08-20 11:33 | Section 5 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 4 | Each | 9.75 | 39 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22600-001025 | 22600 | 2019-08-21 11:16 | Section 6 | Material | Aggregate | Class 1A | 5000 | Tonnes | 12.5 | 62500 | Aggregate | 2019-08-27 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 604 - Deposition (excl topsoil) | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-22602-001025 | 22602 | 2019-08-21 11:21 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 15120 | 15120 | Professional Services | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-22613-001025 | 22613 | 2019-08-21 09:54 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 1 | full pallet | 24.32 | 24 | Timber Products | 2019-08-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22613-001025 | 22613 | 2019-08-21 09:54 | Section 5 | Material | Timber | Not on List | 30 | Each | NULL | 0 | Timber Products | 2019-08-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22456-001025 | 22456 | 2019-08-19 07:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 196 | 196 | Surveying Consumables | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22456-001025 | 22456 | 2019-08-19 07:39 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.32 | 132 | Builders Merchants (General) | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22456-001025 | 22456 | 2019-08-19 07:39 | Section 4 | Material | Not on List | Not on List | 250 | Each | 0.67 | 167.5 | Builders Merchants (General) | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6315-00658 | 6315 | 2018-09-11 10:18 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Visit | 2749.65 | 2749.65 | Miscellaneous | 2018-09-12 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22456-001025 | 22456 | 2019-08-19 07:39 | Section 4 | Material | Ducting | Polypipe 110mm x 50m Ridgiduct Coil Orange S/L (877804) | 2 | Each | 113.44 | 226.88 | Builders Merchants (General) | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22456-001025 | 22456 | 2019-08-19 07:39 | Section 4 | Material | Ducting | Polypipe 110mm x 50m Ridgiduct Coil Purple (877806) | 2 | Each | 113.44 | 226.88 | Builders Merchants (General) | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22615-001025 | 22615 | 2019-08-21 14:03 | Section 5 | Material | PPE, Small Tools and Consumables | Pad Maintenance Black And White Economy Ecospill 40cm X 50cm (534067) | 200 | Each | 0.54 | 108 | Miscellaneous | 2019-08-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22616-001025 | 22616 | 2019-08-21 14:08 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-22616-001025 | 22616 | 2019-08-21 14:08 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-22616-001025 | 22616 | 2019-08-21 14:08 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-22525-001025 | 22525 | 2019-08-20 13:39 | Core | Material | NULL | NULL | 3 | Each | 95 | 285 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22467-001025 | 22467 | 2019-08-19 13:21 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 214.23 | Each | 1 | 214.23 | Small Tools (Consumables) | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22619-001025 | 22619 | 2019-08-21 14:24 | Core | Material | Not on List | Not on List | 45 | NULL | 63 | 2835 | Professional Services | 2019-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | NULL | Yes - Approve | REQ - Buyers
MREQ-22558-001025 | 22558 | 2019-08-20 18:17 | Section 4 | Material | Not on List | Not on List | 150 | Each | 1.32 | 198 | Builders Merchants (General) | 2019-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6317-00659 | 6317 | 2018-09-11 11:05 | Section 4 | Material | Misc | Comms Duct 100Mm | 6 | Each | 105.04 | 630.24 | Electrical | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22588-001025 | 22588 | 2019-08-21 09:00 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 304.6 | Each | 1 | 304.6 | Small Tools (Consumables) | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22449-001025 | 22449 | 2019-08-19 09:22 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.9 | 450 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22448-001025 | 22448 | 2019-08-19 09:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2750 | 2750 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22448-001025 | 22448 | 2019-08-19 09:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 40 | 40 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22448-001025 | 22448 | 2019-08-19 09:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 220 | 220 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22523-001025 | 22523 | 2019-08-20 13:22 | Section 4 | Material | Not on List | Not on List | 1 | Number | 145 | 145 | Surveying Consumables | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22630-001025 | 22630 | 2019-08-21 16:06 | Section 4 | Material | Signage | NULL | 1 | SM | 1288.29 | 1288.29 | Not Sure | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6317-00659 | 6317 | 2018-09-11 11:05 | Section 4 | Material | Misc | Comms Duct 100Mm | 1 | Each | 105.04 | 105.04 | Electrical | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22384-001025 | 22384 | 2019-08-16 09:04 | Section 2 | Material | Not on List | Not on List | 8 | each | 7613.6 | 60908.8 | Miscellaneous | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22384-001025 | 22384 | 2019-08-16 09:04 | Section 2 | Material | Not on List | Not on List | 5 | each | 3590 | 17950 | Miscellaneous | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22534-001025 | 22534 | 2019-08-20 15:32 | Section 4 | Material | Waste Management | Not on List | 1 | NULL | 234.32 | 234.32 | Waste (General) | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22151-001025 | 22151 | 2019-08-12 11:58 | Core | Material | NULL | NULL | 50 | Each | 28.8 | 1440 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22151-001025 | 22151 | 2019-08-12 11:58 | Core | Material | NULL | NULL | 10 | Each | 28.8 | 288 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22157-001025 | 22157 | 2019-08-12 13:49 | Core | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | 28.8 | 1152 | PPE | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 28 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 16 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 16 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 12 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 14 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 32 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 8 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 16 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 2 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16929-001025 | 16929 | 2019-05-07 08:58 | Section 4 | Material | Not on List | Not on List | 100 | ea | 10 | 1000 | Miscellaneous | 2019-05-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16806-001025 | 16806 | 2019-05-02 11:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 11.57 | 23.14 | Laboratory Equipment / Certification | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16806-001025 | 16806 | 2019-05-02 11:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 6.96 | 139.2 | Laboratory Equipment / Certification | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16806-001025 | 16806 | 2019-05-02 11:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 0.86 | 17.2 | Laboratory Equipment / Certification | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16806-001025 | 16806 | 2019-05-02 11:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 55.92 | 279.6 | Laboratory Equipment / Certification | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16591-001025 | 16591 | 2019-04-29 15:26 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 370 | 370 | Laboratory Equipment / Certification | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16812-001025 | 16812 | 2019-05-02 11:28 | Core | Material | Not on List | Not on List | 1 | NULL | 329.46 | 329.46 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16938-001025 | 16938 | 2019-05-07 10:27 | Core | Material | Not on List | Not on List | 1 | number | 2500 | 2500 | Office Supplies | 2019-05-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-16849-001025 | 16849 | 2019-05-03 07:36 | Core | Material | Not on List | Not on List | 1 | No | 51.4 | 51.4 | Janitorial | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16849-001025 | 16849 | 2019-05-03 07:36 | Core | Material | Not on List | Not on List | 1 | No | 367.4 | 367.4 | Small Tools (Consumables) | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16849-001025 | 16849 | 2019-05-03 07:36 | Core | Material | Not on List | Not on List | 1 | No | 278.79 | 278.79 | PPE | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16948-001025 | 16948 | 2019-05-07 14:14 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 5 | Each | 11.94 | 60 | Builders Merchants (General) | 2019-05-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16952-001025 | 16952 | 2019-05-07 14:18 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 25.13 | 251 | Miscellaneous | 2019-05-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16807-001025 | 16807 | 2019-05-02 10:58 | Core | Material | Not on List | Not on List | 1 | NULL | 329.46 | 329 | Miscellaneous | 2019-05-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16828-001025 | 16828 | 2019-05-02 15:38 | Core | Material | Not on List | Not on List | 1 | NULL | 478 | 478 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16956-001025 | 16956 | 2019-05-07 15:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2447.01 | 2447 | PPE | 2019-05-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16957-001025 | 16957 | 2019-05-07 15:29 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-16958-001025 | 16958 | 2019-05-07 15:38 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16886-001025 | 16886 | 2019-05-03 14:35 | Section 4 | Material | Not on List | Not on List | 5 | Box 50 | 28.84 | 144.2 | Small Tools (Consumables) | 2019-05-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16959-001025 | 16959 | 2019-05-07 15:55 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16942-001025 | 16942 | 2019-05-07 10:56 | Section 2 | Material | Not on List | Not on List | 2 | Number | 236 | 472 | Plastic Drainage | 2019-05-10 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-16942-001025 | 16942 | 2019-05-07 10:56 | Section 2 | Material | Not on List | Not on List | 8 | Number | 42.75 | 342 | Plastic Drainage | 2019-05-10 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-16942-001025 | 16942 | 2019-05-07 10:56 | Section 2 | Material | Not on List | Not on List | 4 | Number | 23.4 | 94 | Plastic Drainage | 2019-05-10 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-16942-001025 | 16942 | 2019-05-07 10:56 | Section 2 | Material | Not on List | Not on List | 2 | Number | 21.5 | 43 | Plastic Drainage | 2019-05-17 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-16965-001025 | 16965 | 2019-05-07 16:22 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1364.52 | 1365 | Surveying Consumables | 2019-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16979-001025 | 16979 | 2019-05-07 16:59 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-6384-00680 | 6384 | 2018-09-12 09:14 | Section 3 | Material | Not on List | Not on List | 1 | EA | 1539.4 | 1539.4 | PPE | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16981-001025 | 16981 | 2019-05-07 17:09 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16985-001025 | 16985 | 2019-05-07 17:38 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20899-001025 | 20899 | 2019-07-17 10:29 | Section 4 | Material | Not on List | Not on List | 700 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20899-001025 | 20899 | 2019-07-17 10:29 | Section 4 | Material | Not on List | Not on List | 350 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20772-001025 | 20772 | 2019-07-15 14:05 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | Each | 2.97 | 332.64 | Miscellaneous | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20772-001025 | 20772 | 2019-07-15 14:05 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 11.5 | 115 | Miscellaneous | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20839-001025 | 20839 | 2019-07-16 13:02 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-07-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | Concrete Drainage | Not on List | 2 | Each | 92.06 | 184.12 | Concrete Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20845-001025 | 20845 | 2019-07-16 14:05 | Section 3 | Material | Aggregate | 6G | 120 | Tonnes | 32.9 | 3948 | Aggregate | 2019-07-22 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20830-001025 | 20830 | 2019-07-16 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1557.05 | each | 1 | 1557.05 | PPE | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20901-001025 | 20901 | 2019-07-17 10:52 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | 28.8 | 864 | PPE | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20555-001025 | 20555 | 2019-07-10 14:02 | Section 4 | Material | Not on List | Not on List | 1 | each | 2441.5 | 2441.5 | Miscellaneous | 2019-07-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20854-001025 | 20854 | 2019-07-16 16:18 | Section 1 | Material | Concrete Drainage | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-07-29 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | NULL | NULL | 32 | Each | 3.17 | 101.44 | Plastic Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20934-001025 | 20934 | 2019-07-17 15:52 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3216.2 | each | 1 | 3216 | Miscellaneous | 2019-07-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Buyers
MREQ-20871-001025 | 20871 | 2019-07-16 17:38 | Section 4 | Material | NULL | NULL | 20 | Each | 41.2 | 824 | Concrete Drainage | 2019-07-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20871-001025 | 20871 | 2019-07-16 17:38 | Section 4 | Material | NULL | NULL | 4 | Each | 59.57 | 238.28 | Miscellaneous | 2019-07-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20755-001025 | 20755 | 2019-07-15 11:01 | Core | Material | NULL | NULL | 1 | Eack | 837 | 837 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | NULL | NULL | 16 | Each | 5.74 | 91.84 | Plastic Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5492-00323 | 5492 | 2018-08-22 10:58 | Section 4 | Material | Not on List | Not on List | 8 | Each | 66 | 528 | Concrete Accessories | 2018-09-28 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20960-001025 | 20960 | 2019-07-18 08:06 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Accessories | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20960-001025 | 20960 | 2019-07-18 08:06 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Accessories | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5492-00323 | 5492 | 2018-08-22 10:58 | Section 4 | Material | Not on List | Not on List | 8 | Each | 72 | 576 | Concrete Accessories | 2018-08-28 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20981-001025 | 20981 | 2019-07-18 10:03 | Section 3 | Material | PPE, Small Tools and Consumables | Rope Blue Polypropylene 6mm X 500m (approx)on Drum (746415) | 15 | Each | 25.13 | 377 | Miscellaneous | 2019-07-22 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-20909-001025 | 20909 | 2019-07-17 12:11 | Section 4 | Material | Not on List | Not on List | 600 | Box 100 | 45.04 | 27024 | Fixings and Fasteners | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20909-001025 | 20909 | 2019-07-17 12:11 | Section 4 | Material | Not on List | Not on List | 1000 | Box 100 | 83.15 | 83150 | Fixings and Fasteners | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20918-001025 | 20918 | 2019-07-17 14:20 | Section 4 | Material | Not on List | Not on List | 219 | 3.2m Tube | 24.1 | 5277.9 | Fixings and Fasteners | 2019-07-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5144-0075 | 5144 | 2018-08-15 11:44 | Section 3 | Material | Not on List | NULL | 16 | No | 74.3 | 1188.8 | Builders Merchants (General) | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5492-00323 | 5492 | 2018-08-22 10:58 | Section 4 | Material | Not on List | Not on List | 2 | rolls | 3.6 | 7.2 | Concrete Accessories | 2018-08-28 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20843-001025 | 20843 | 2019-07-16 13:39 | Section 4 | Material | Not on List | Not on List | 4 | Box 100 | 4.9 | 19.6 | Surveying Consumables | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20910-001025 | 20910 | 2019-07-17 12:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | EACH | 7.23 | 361.5 | Builders Merchants (General) | 2019-07-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20910-001025 | 20910 | 2019-07-17 12:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | EACH | 16 | 16 | Builders Merchants (General) | 2019-07-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20910-001025 | 20910 | 2019-07-17 12:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | BOX | 2.4 | 12 | Builders Merchants (General) | 2019-07-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20995-001025 | 20995 | 2019-07-18 12:56 | Core | Material | Not on List | Not on List | 1 | NULL | 259.6 | 260 | PPE | 2019-07-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20995-001025 | 20995 | 2019-07-18 12:56 | Core | Material | Not on List | Not on List | 1 | NULL | 539.28 | 539 | Small Tools (Consumables) | 2019-07-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Saint Gobain Castings | 454x454x100 D400 Watershed GG&F (257790) | 40 | Each | 58.04 | 2321.6 | Concrete Drainage | 2019-07-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 40 | EACH | 4.29 | 171.6 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 40 | EACH | 5.95 | 238 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 10 | EACH | 189 | 1890 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 483 | Rolls | 49.5 | 23908.5 | Blocks and Bricks | 2018-10-15 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 30 | EACH | 125.94 | 3778.2 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 10 | EACH | 18.89 | 188.9 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 50 | EACH | 10.84 | 542 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Not on List | Not on List | 20 | EACH | 79.41 | 1588.2 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Saint Gobain Castings | 380x230x125 D400 Surface Box (376797) | 20 | Each | 34 | 680 | Plastic Drainage | 2019-07-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20911-001025 | 20911 | 2019-07-17 12:57 | Section 4 | Material | Not on List | Not on List | 20 | Each | 12.18 | 243.6 | Concrete Accessories | 2019-07-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 8 | Rolls | 139 | 1112 | Blocks and Bricks | 2018-10-15 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20980-001025 | 20980 | 2019-07-18 09:49 | Section 3 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 17 | Each | 179.74 | 3055.58 | Ductile Drainage | 2019-07-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20980-001025 | 20980 | 2019-07-18 09:49 | Section 3 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 6 | Each | 125.94 | 755.64 | Ductile Drainage | 2019-07-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20980-001025 | 20980 | 2019-07-18 09:49 | Section 3 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 20 | Each | 10.5 | 210 | Ductile Drainage | 2019-07-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20980-001025 | 20980 | 2019-07-18 09:49 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 30 | Each | 34.82 | 1044.6 | Ductile Drainage | 2019-07-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20980-001025 | 20980 | 2019-07-18 09:49 | Section 3 | Material | Twinwall | Not on List | 8 | Each | NULL | 0 | Ductile Drainage | 2019-07-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20849-001025 | 20849 | 2019-07-16 14:28 | Section 3 | Material | Not on List | Not on List | 25 | Rolls | 196 | 4900 | Tanks and Interceptors | 2019-07-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20849-001025 | 20849 | 2019-07-16 14:28 | Section 3 | Material | Not on List | Not on List | 1 | Bx of 900 | 40.8 | 40.8 | Tanks and Interceptors | 2019-07-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20849-001025 | 20849 | 2019-07-16 14:28 | Section 3 | Material | Not on List | Not on List | 300 | ea | 2.55 | 765 | Tanks and Interceptors | 2019-07-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20946-001025 | 20946 | 2019-07-17 17:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Bag 1000 | 55 | 55 | Rebar and Mesh | 2019-07-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.22 | 110 | Blocks and Bricks | 2018-10-15 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20549-001025 | 20549 | 2019-07-10 12:30 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 600 | 600 | Miscellaneous | 2019-07-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20959-001025 | 20959 | 2019-07-18 07:52 | Section 5 | Material | Not on List | Not on List | 1 | SUM | 1078.5 | 1078.5 | Concrete Accessories | 2019-07-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21029-001025 | 21029 | 2019-07-19 09:16 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | 36 | 144 | Small Tools (Consumables) | 2019-07-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21029-001025 | 21029 | 2019-07-19 09:16 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 36 | NULL | 2.5 | 90 | Surveying Consumables | 2019-07-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20945-001025 | 20945 | 2019-07-17 17:09 | Core | Material | PPE, Small Tools and Consumables | Not on List | 32 | EA | 28.8 | 921.6 | PPE | 2019-07-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20943-001025 | 20943 | 2019-07-17 17:04 | Core | Material | PPE, Small Tools and Consumables | Not on List | 326.2 | Each | 1 | 326.2 | Miscellaneous | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21026-001025 | 21026 | 2019-07-19 09:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 35 | 350 | Surveying Consumables | 2019-07-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | GR ENVIROPAD - M10 (MEDIUM) GRR 520210 EPAD (534283) | 5 | Each | 110.18 | 551 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 1 | Pack | 1335 | 1335 | Blocks and Bricks | 2018-10-15 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Shovel No2 Solid Socket Square Mouth Myd Handle Spartan (762570) | 10 | Each | 10.19 | 102 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Sprayer 20oz Bottle C/W Adjust Trigger Spray Spartan (510900) | 3 | Each | 2.6 | 8 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Blade Replacement Utility/Trimming Knife 10 Pk Spartan Pro (740081) | 10 | Each | 1.21 | 12 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Sealant Gp Silicone Hansil Contractor Clear 300ml (546650) | 48 | Each | 1.13 | 54 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Nipper Work Pro End-cutting Pliers Size 175mm // 7" (742894) | 10 | Each | 14.79 | 148 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Jerrican Metal 20 Litre Capacity Spartan Pro (708622) | 5 | Each | 13.19 | 66 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 650 | 650 | Blocks and Bricks | 2018-10-15 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 300 | 300 | Blocks and Bricks | 2018-10-01 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21039-001025 | 21039 | 2019-07-19 11:14 | Core | Material | Not on List | Not on List | 1 | number | 99.99 | 100 | Electrical | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21039-001025 | 21039 | 2019-07-19 11:14 | Core | Material | Not on List | Not on List | 1 | number | 41.49 | 41 | Electrical | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20937-001025 | 20937 | 2019-07-17 16:28 | Section 4 | Material | Not on List | Not on List | 684 | ea | 4.13 | 2824.92 | Miscellaneous | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21044-001025 | 21044 | 2019-07-19 11:47 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 44.45 | 44 | Small Tools (Consumables) | 2019-07-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 105 - Site Security | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 500 | 500 | Blocks and Bricks | 2018-10-01 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 450 | 450 | Blocks and Bricks | 2018-10-01 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21077-001025 | 21077 | 2019-07-19 15:15 | Core | Material | Not on List | Not on List | 4 | Days | 649 | 2596 | Professional Services | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20920-001025 | 20920 | 2019-07-17 14:50 | Section 3 | Material | Not on List | Not on List | 20 | No | 21.29 | 425.8 | Builders Merchants (General) | 2019-07-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20920-001025 | 20920 | 2019-07-17 14:50 | Section 3 | Material | Not on List | Not on List | 10 | No | 33.55 | 335.5 | Builders Merchants (General) | 2019-07-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5500-00331 | 5500 | 2018-08-22 13:36 | Section 4 | Material | Not on List | Not on List | 40 | Each | 112.06 | 4482.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21113-001025 | 21113 | 2019-07-22 10:43 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21119-001025 | 21119 | 2019-07-22 11:14 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21125-001025 | 21125 | 2019-07-22 11:24 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21126-001025 | 21126 | 2019-07-22 11:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20759-001025 | 20759 | 2019-07-15 11:34 | Core | Material | NULL | NULL | 1 | Each | 491 | 491 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20963-001025 | 20963 | 2019-07-18 08:27 | Core | Material | NULL | NULL | 1 | Each | 272 | 272 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5144-0075 | 5144 | 2018-08-15 11:44 | Section 3 | Material | Not on List | NULL | 28 | No | 31.37 | 878.36 | Builders Merchants (General) | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5500-00331 | 5500 | 2018-08-22 13:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 126.82 | 253.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21133-001025 | 21133 | 2019-07-22 12:11 | Section 3 | Material | Not on List | Not on List | 28 | NULL | NULL | 0 | Miscellaneous | 2019-07-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21133-001025 | 21133 | 2019-07-22 12:11 | Section 3 | Material | Not on List | Not on List | 41 | NULL | NULL | 0 | Miscellaneous | 2019-07-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21133-001025 | 21133 | 2019-07-22 12:11 | Section 3 | Material | Not on List | Not on List | 19 | NULL | NULL | 0 | Miscellaneous | 2019-07-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21133-001025 | 21133 | 2019-07-22 12:11 | Section 3 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Miscellaneous | 2019-07-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21111-001025 | 21111 | 2019-07-22 09:34 | Section 4 | Material | Not on List | Not on List | 28 | number | 1.37 | 38.36 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21111-001025 | 21111 | 2019-07-22 09:34 | Section 4 | Material | Not on List | Not on List | 56 | number | 0.26 | 14.56 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21111-001025 | 21111 | 2019-07-22 09:34 | Section 4 | Material | Not on List | Not on List | 56 | number | 0.17 | 9.52 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21111-001025 | 21111 | 2019-07-22 09:34 | Section 4 | Material | Not on List | Not on List | 6 | number | 32.18 | 193.08 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17235-001025 | 17235 | 2019-05-13 08:36 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20856-001025 | 20856 | 2019-07-16 16:25 | Core | Material | NULL | NULL | 1 | Each | 7984.5 | 7984.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5500-00331 | 5500 | 2018-08-22 13:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 126.82 | 253.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18585-001025 | 18585 | 2019-06-05 11:16 | Core | Material | NULL | NULL | 1 | Each | 3115 | 3115 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18586-001025 | 18586 | 2019-06-05 11:21 | Core | Material | NULL | NULL | 1 | Each | 2358 | 2358 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20998-001025 | 20998 | 2019-07-18 14:19 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 100 | Each | 1.98 | 198 | Plastic Drainage | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20998-001025 | 20998 | 2019-07-18 14:19 | Section 2 | Material | Twinwall | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20998-001025 | 20998 | 2019-07-18 14:19 | Section 2 | Material | Not on List | Not on List | 120 | NULL | NULL | 0 | Concrete Drainage | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5501-00334 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 525 | Each | 4.43 | 2325.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20998-001025 | 20998 | 2019-07-18 14:19 | Section 2 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 20 | Each | 81.73 | 1634.6 | Concrete Drainage | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20990-001025 | 20990 | 2019-07-18 11:44 | Core | Material | NULL | NULL | 1 | Each | 116 | 116 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 70 | NULL | NULL | 0 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 86 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 106 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5126-0051 | 5126 | 2018-08-15 09:16 | Section 3 | Material | Not on List | NULL | 8 | no. | NULL | 0 | Geotextiles | 2018-08-20 | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 15 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 110 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 254 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 242 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 477 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 35 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 41 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 34 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 55 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 63 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 22 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 15 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 18 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 82 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 36 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5397-00263 | 5397 | 2018-08-21 08:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1304.51 | 0 | Small Tools (Consumables) | 2018-08-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 98 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 345 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 44 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 22 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 36 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 150 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 36 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5478-00302 | 5478 | 2018-08-22 07:29 | Section 3 | Material | Plastic Drainage | Not on List | 40 | No. | NULL | 0 | Plastic Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 16 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 40 | No | 243.87 | 9754.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 5 | EA | 59.17 | 295.85 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 20 | No | 46.35 | 927 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 240 | No | 34.1 | 8184 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 47 | No | 29.01 | 1363.47 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 47 | No | 29.01 | 1363.47 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 1430 | No | 29.28 | 41870.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 26 | No | 4.67 | 121.42 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10429-001025 | 10429 | 2018-12-17 16:01 | Section 4 | Material | Not on List | Not on List | 20 | Box | NULL | 0 | Miscellaneous | 2018-12-20 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 100 | Each | 6.35 | 635 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 36 | Each | 6.35 | 229 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 24 | Each | 6.35 | 152 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 5 | EA | 232.01 | 1160.05 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10490-001025 | 10490 | 2018-12-19 16:00 | Section 3 | Material | Not on List | Not on List | 1 | ea | 861 | 861 | Miscellaneous | 2018-12-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | Kerbs | Not on List | 9 | Packs | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | Kerbs | Not on List | 3 | Packs | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | Kerbs | Not on List | 3 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | Kerbs | Not on List | 3 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 200 | ea | 2.18 | 436 | Miscellaneous | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | ea | 309.24 | 309.24 | Janitorial | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | ea | 128.89 | 128.89 | Small Tools (Consumables) | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | ea | 65.7 | 65.7 | PPE | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10581-001025 | 10581 | 2019-01-04 09:11 | Section 3 | Material | Not on List | Not on List | 2 | packs | NULL | 0 | Plastic Drainage | 2019-01-11 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 8 | EA | 81.96 | 655.68 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 100 | Each | 6.35 | 635 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 36 | Each | 6.35 | 228.6 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 24 | Each | 6.35 | 152.4 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10587-001025 | 10587 | 2019-01-04 11:13 | Section 4 | Material | Not on List | Not on List | 1 | each | 1276.63 | 1277 | Not Sure | 2019-01-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10588-001025 | 10588 | 2019-01-04 11:19 | Section 3 | Material | Not on List | Not on List | 1 | each | 2288.78 | 2289 | Not Sure | 2019-01-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10616-001025 | 10616 | 2019-01-04 15:44 | Section 3 | Material | Not on List | Not on List | 1 | Each | 5 | 5 | Waste (Recycling) | 2019-01-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10588-001025 | 10588 | 2019-01-04 11:19 | Section 3 | Material | Not on List | Not on List | 1 | each | 2288.78 | 2288.78 | Not Sure | 2019-01-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10581-001025 | 10581 | 2019-01-04 09:11 | Section 3 | Material | Not on List | Not on List | 2 | packs | 1377 | 2754 | Plastic Drainage | 2019-01-11 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 5 | EA | 61.48 | 307.4 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10499-001025 | 10499 | 2018-12-19 18:11 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1709.6 | 1709.6 | Miscellaneous | 2018-12-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10477-001025 | 10477 | 2018-12-19 08:56 | Section 3 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 2000 | Each | 0.49 | 980 | Miscellaneous | 2019-01-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10589-001025 | 10589 | 2019-01-04 11:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 4.2 | 16.8 | Small Tools (Consumables) | 2019-01-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10589-001025 | 10589 | 2019-01-04 11:25 | Section 4 | Material | Not on List | Not on List | 10 | Each | 27.98 | 279.8 | Small Tools (Consumables) | 2019-01-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10489-001025 | 10489 | 2018-12-19 15:17 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10682-001025 | 10682 | 2019-01-08 09:12 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10683-001025 | 10683 | 2019-01-08 09:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 5 | EA | 53.01 | 265.05 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10365-001025 | 10365 | 2018-12-14 10:19 | Section 3 | Material | Not on List | Not on List | 13 | no. of schedule components | 258.04 | 3354.52 | Fixings and Fasteners | 2019-01-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10690-001025 | 10690 | 2019-01-08 10:23 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-01-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10692-001025 | 10692 | 2019-01-08 10:22 | Section 4 | Material | Not on List | Not on List | 13.21 | tonne | NULL | 0 | Reinforcement | 2019-01-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10692-001025 | 10692 | 2019-01-08 10:22 | Section 4 | Material | Not on List | Not on List | 8 | number | NULL | 0 | Reinforcement | 2019-01-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10699-001025 | 10699 | 2019-01-08 11:45 | Section 3 | Material | Concrete Drainage | Not on List | 9 | No. | NULL | 0 | Concrete Drainage | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10659-001025 | 10659 | 2019-01-07 16:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2089.48 | Each | 1 | 2089.48 | PPE | 2019-01-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | Each | 166.43 | 3328.6 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | Each | 20.71 | 414.2 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 40 | Each | 34.82 | 1392.8 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 15 | EA | 47.04 | 705.6 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 80 | Each | 6.54 | 523.2 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | Each | 48.86 | 977.2 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 200 | Each | 2.75 | 550 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 12 | Each | 314.15 | 3769.8 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26172-001025 | 26172 | 2019-11-05 16:54 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26173-001025 | 26173 | 2019-11-05 17:16 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26179-001025 | 26179 | 2019-11-05 17:30 | Core | Material | Not on List | Not on List | 40 | swabs | 118.75 | 4750 | Miscellaneous | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26179-001025 | 26179 | 2019-11-05 17:30 | Core | Material | Not on List | Not on List | 3 | tubes | 36 | 108 | Miscellaneous | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26180-001025 | 26180 | 2019-11-05 18:18 | Section 3 | Material | Bagged | OP Cement; 25kg bag (767201) | 50 | Each | 2.9 | 145 | Aggregate | 2019-11-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26181-001025 | 26181 | 2019-11-05 18:18 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26192-001025 | 26192 | 2019-11-06 08:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26196-001025 | 26196 | 2019-11-06 08:23 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26132-001025 | 26132 | 2019-11-04 17:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 25.15 | 251.5 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25939-001025 | 25939 | 2019-10-30 16:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 50.4 | 504 | Miscellaneous | 2019-11-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26157-001025 | 26157 | 2019-11-05 14:47 | Section 4 | Material | Not on List | Not on List | 1 | Each | 413.21 | 413.21 | Miscellaneous | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26211-001025 | 26211 | 2019-11-06 11:38 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 33.6 | 168 | Small Tools (Consumables) | 2019-11-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26211-001025 | 26211 | 2019-11-06 11:38 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 53.2 | 53 | Small Tools (Consumables) | 2019-11-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26219-001025 | 26219 | 2019-11-06 14:29 | Core | Material | Not on List | Not on List | 1 | ea | 486 | 486 | Training | 2019-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26225-001025 | 26225 | 2019-11-06 14:55 | Core | Material | Hazardous Waste | Not on List | 2 | containers | 40 | 80 | Miscellaneous | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26197-001025 | 26197 | 2019-11-06 08:23 | Section 5 | Material | Not on List | Not on List | 1 | sm | 606 | 606 | Not Sure | 2019-11-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1403 - Feeder Pillars & Earth Electrodes | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26243-001025 | 26243 | 2019-11-06 17:08 | Section 2 | Material | PPE, Small Tools and Consumables | Abso Net Plus 20 Ltr Clay Granules (534317) | 40 | Each | 11.24 | 450 | Miscellaneous | 2019-11-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26244-001025 | 26244 | 2019-11-06 17:13 | Section 6 | Material | PPE, Small Tools and Consumables | Abso Net Plus 20 Ltr Clay Granules (534317) | 40 | Each | 7.9 | 316 | Miscellaneous | 2019-11-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26245-001025 | 26245 | 2019-11-06 17:11 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 450 | 450 | Professional Services | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1601 - Piling and attendances | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-25952-001025 | 25952 | 2019-10-31 08:31 | Section 4 | Material | Not on List | Not on List | 166 | units | 29.05 | 4822.3 | Builders Merchants (General) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25952-001025 | 25952 | 2019-10-31 08:31 | Section 4 | Material | Not on List | Not on List | 4 | units | 46.78 | 187.12 | Builders Merchants (General) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25952-001025 | 25952 | 2019-10-31 08:31 | Section 4 | Material | Not on List | Not on List | 4 | units | 106.25 | 425 | Builders Merchants (General) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7200-001020 | 7200 | 2018-10-01 07:53 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 72 | Each | 6.29 | 452.88 | Miscellaneous | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25952-001025 | 25952 | 2019-10-31 08:31 | Section 4 | Material | Not on List | Not on List | 2 | units | 106.25 | 212.5 | Builders Merchants (General) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25952-001025 | 25952 | 2019-10-31 08:31 | Section 4 | Material | Not on List | Not on List | 20 | units | 37.92 | 758.4 | Builders Merchants (General) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7207-001020 | 7207 | 2018-10-01 10:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 50 | each | 3.42 | 171 | Small Tools (Consumables) | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26262-001025 | 26262 | 2019-11-07 08:57 | Core | Material | Not on List | Not on List | 10 | Packs of 100 | NULL | 0 | Surveying Consumables | 2019-11-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26186-001025 | 26186 | 2019-11-06 07:33 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | 1.31 | 78.6 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26186-001025 | 26186 | 2019-11-06 07:33 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 3.7 | 18.5 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26255-001025 | 26255 | 2019-11-06 21:22 | Section 4 | Material | Not on List | Not on List | 1 | Each | 58.24 | 58.24 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1203 - Traffic Signal Installations | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26255-001025 | 26255 | 2019-11-06 21:22 | Section 4 | Material | Not on List | NULL | 1 | Each | 31.36 | 31.36 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1203 - Traffic Signal Installations | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26264-001025 | 26264 | 2019-11-07 09:07 | Section 4 | Material | Kerbs | Not on List | 10 | Ea | 4.9 | 49 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 1 | Each | 102.82 | 102.82 | Concrete Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 18 | Each | 166.43 | 2995.74 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain Seal (346400) | 38 | Each | 20.71 | 786.98 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Not on List | 2 | each | NULL | 0 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Not on List | 8 | each | NULL | 0 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Not on List | 1 | each | NULL | 0 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 36 | Each | 10.5 | 378 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7220-001021 | 7220 | 2018-10-01 13:53 | Section 3 | Material | Not on List | Not on List | 16 | No. | NULL | 0 | Plastic Drainage | 2018-10-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 72 | Each | 0.91 | 65.52 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 36 | Each | 1.98 | 71.28 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 4000 | Each | 0.37 | 1480 | Builders Merchants (General) | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25874-001025 | 25874 | 2019-10-29 16:24 | Section 5 | Material | Not on List | NULL | 1 | EA | 157 | 157 | Surveying Consumables | 2019-11-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26285-001025 | 26285 | 2019-11-07 13:59 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-26290-001025 | 26290 | 2019-11-07 14:32 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 271.44 | 271 | Janitorial | 2019-11-11 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26290-001025 | 26290 | 2019-11-07 14:32 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 248.03 | 248 | PPE | 2019-11-11 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26290-001025 | 26290 | 2019-11-07 14:32 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 621.33 | 621 | Small Tools (Consumables) | 2019-11-11 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26293-001025 | 26293 | 2019-11-07 14:38 | Section 3 | Material | Kerbs | Not on List | 42 | NULL | NULL | 0 | Concrete Drainage | 2019-11-11 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26293-001025 | 26293 | 2019-11-07 14:38 | Section 3 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-11-11 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26293-001025 | 26293 | 2019-11-07 14:38 | Section 3 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-11-11 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26293-001025 | 26293 | 2019-11-07 14:38 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-11-11 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26293-001025 | 26293 | 2019-11-07 14:38 | Section 3 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-11-11 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26333-001025 | 26333 | 2019-11-08 07:59 | Section 6 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 30 | Each | 24.32 | 730 | Timber Products | 2019-11-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26333-001025 | 26333 | 2019-11-08 07:59 | Section 6 | Material | Not on List | Not on List | 5 | Each | NULL | 0 | Timber Products | 2019-11-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26337-001025 | 26337 | 2019-11-08 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | ea | 13.38 | 54 | Small Tools (Consumables) | 2019-11-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25811-001025 | 25811 | 2019-10-28 14:19 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 401 - Safety Barriers | IMO Queue | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6957-00752 | 6957 | 2018-09-25 11:46 | Section 4 | Material | Not on List | Not on List | 1 | Each | 6.8 | 6.8 | Miscellaneous | 2018-10-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26385-001025 | 26385 | 2019-11-08 15:25 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 49.5 | 50 | Concrete Accessories | 2019-11-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26385-001025 | 26385 | 2019-11-08 15:25 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 26.5 | 27 | Fixings and Fasteners | 2019-11-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26392-001025 | 26392 | 2019-11-11 07:39 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26187-001025 | 26187 | 2019-11-06 07:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 25.13 | 251.3 | Miscellaneous | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26408-001025 | 26408 | 2019-11-11 10:54 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26354-001025 | 26354 | 2019-11-08 12:53 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26267-001025 | 26267 | 2019-11-07 08:42 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26248-001025 | 26248 | 2019-11-06 17:34 | Section 4 | Material | Not on List | Not on List | 1 | Each | 880.88 | 880.88 | Miscellaneous | 2019-11-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26343-001025 | 26343 | 2019-11-08 11:13 | Section 5 | Material | NULL | NULL | 4 | Each | 50.86 | 203.44 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7153-001020 | 7153 | 2018-09-28 12:53 | Section 4 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 112 | Each | 3.56 | 398.72 | Concrete Drainage | 2018-10-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26343-001025 | 26343 | 2019-11-08 11:13 | Section 5 | Material | NULL | NULL | 2 | Each | 11.95 | 23.9 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26343-001025 | 26343 | 2019-11-08 11:13 | Section 5 | Material | NULL | NULL | 5 | Each | 36 | 180 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26343-001025 | 26343 | 2019-11-08 11:13 | Section 5 | Material | NULL | NULL | 50 | Each | 1.75 | 87.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26427-001025 | 26427 | 2019-11-11 14:23 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-26399-001025 | 26399 | 2019-11-11 08:43 | Section 2 | Material | Not on List | Not on List | 2.118 | T | NULL | 0 | Rebar and Mesh | 2019-11-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26423-001025 | 26423 | 2019-11-11 13:32 | Section 4 | Material | NULL | NULL | 96 | Ea | 12 | 1152 | Small Tools (Consumables) | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26423-001025 | 26423 | 2019-11-11 13:32 | Section 4 | Material | NULL | NULL | 1 | ea | 30 | 30 | Small Tools (Consumables) | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25743-001025 | 25743 | 2019-10-25 11:50 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Office Supplies | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26164-001025 | 26164 | 2019-11-05 15:40 | Section 6 | Material | Not on List | Not on List | 55 | each | 18.97 | 1043.35 | Builders Merchants (General) | 2019-11-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7212-001020 | 7212 | 2018-10-01 12:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1108.8 | 1108.8 | Miscellaneous | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26164-001025 | 26164 | 2019-11-05 15:40 | Section 6 | Material | Not on List | Not on List | 1 | Pallet | 0.92 | 0.92 | Builders Merchants (General) | 2019-11-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26215-001025 | 26215 | 2019-11-06 12:40 | Section 4 | Material | Not on List | Not on List | 1 | Each | 323.78 | 323.78 | Miscellaneous | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7156-001020 | 7156 | 2018-09-28 13:21 | Section 4 | Material | Hazardous Waste | Oil/water/diesel - 205L drum | 43 | Each | 195 | 8385 | Waste (General) | 2018-10-02 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26109-001025 | 26109 | 2019-11-04 14:48 | Section 5 | Material | Not on List | Not on List | 1 | SM | 246 | 246 | Fixings and Fasteners | 2019-11-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26470-001025 | 26470 | 2019-11-12 11:32 | Core | Material | Not on List | Not on List | 1 | EACH | 835.86 | 836 | Miscellaneous | 2019-11-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26471-001025 | 26471 | 2019-11-12 11:35 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 1088.14 | 1088 | Miscellaneous | 2019-11-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26472-001025 | 26472 | 2019-11-12 11:28 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2055.14 | each | 1 | 2055 | Janitorial | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7156-001020 | 7156 | 2018-09-28 13:21 | Section 4 | Material | Hazardous Waste | Oil/water/diesel - 205L drum | 8 | Hr | 75 | 600 | Waste (General) | 2018-10-02 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26473-001025 | 26473 | 2019-11-12 11:37 | Section 5 | Material | Not on List | Not on List | 1 | EACH | 1370.43 | 1370 | Miscellaneous | 2019-11-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26474-001025 | 26474 | 2019-11-12 11:40 | Section 6 | Material | Not on List | Not on List | 1 | EACH | 289.29 | 289 | Miscellaneous | 2019-11-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26418-001025 | 26418 | 2019-11-11 12:15 | Section 4 | Material | Kerbs | Not on List | 5 | Each | 151.94 | 759.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26418-001025 | 26418 | 2019-11-11 12:15 | Section 4 | Material | Bagged | Not on List | 20 | Each | 31.85 | 637 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26418-001025 | 26418 | 2019-11-11 12:15 | Section 4 | Material | NULL | Not on List | 1 | Each | 115 | 115 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26437-001025 | 26437 | 2019-11-11 16:52 | Section 5 | Material | Saint Gobain Castings | NULL | 1 | SM | 1091.14 | 1091.14 | Ductile Drainage | 2019-11-29 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26482-001025 | 26482 | 2019-11-12 12:02 | Section 4 | Material | Not on List | Not on List | 32 | Each | 6.9 | 220.8 | Concrete Drainage | 2019-11-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26495-001025 | 26495 | 2019-11-12 15:28 | Core | Material | Not on List | Not on List | 1 | ea | 920 | 920 | Training | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26496-001025 | 26496 | 2019-11-12 15:06 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 308.59 | 309 | Small Tools (Consumables) | 2019-11-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26496-001025 | 26496 | 2019-11-12 15:06 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 1089.7 | 1090 | PPE | 2019-11-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26496-001025 | 26496 | 2019-11-12 15:06 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 56.76 | 57 | Janitorial | 2019-11-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26433-001025 | 26433 | 2019-11-11 16:23 | Section 5 | Material | Combined Drainage | NULL | 1 | SM | 20770 | 20770 | Miscellaneous | 2019-11-12 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26497-001025 | 26497 | 2019-11-12 16:03 | Core | Material | Not on List | Not on List | 1 | NULL | 96.75 | 97 | Miscellaneous | 2019-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26510-001025 | 26510 | 2019-11-12 17:38 | Core | Material | Not on List | Not on List | 1 | ea | 687.61 | 688 | Office Supplies | 2019-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26511-001025 | 26511 | 2019-11-12 17:50 | Core | Material | Not on List | Not on List | 1 | ea | 84.76 | 85 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26512-001025 | 26512 | 2019-11-12 17:52 | Core | Material | Not on List | Not on List | 1 | ea | 1597.5 | 1598 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26513-001025 | 26513 | 2019-11-12 17:54 | Core | Material | Not on List | Not on List | 1 | ea | 270.18 | 270 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26514-001025 | 26514 | 2019-11-12 17:57 | Core | Material | Not on List | Not on List | 1 | ea | 208.04 | 208 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26516-001025 | 26516 | 2019-11-12 17:59 | Core | Material | Not on List | Not on List | 1 | ea | 215.94 | 216 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26517-001025 | 26517 | 2019-11-12 18:01 | Core | Material | Not on List | Not on List | 1 | ea | 135 | 135 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26518-001025 | 26518 | 2019-11-12 18:03 | Core | Material | Not on List | Not on List | 1 | ea | 572.4 | 572 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 2 | Each | 212.27 | 424.54 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 1 | Each | 871.8 | 871.8 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 30 | Each | 70.62 | 2118.6 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 15 | Each | 52.97 | 794.55 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 15 | Each | 44.89 | 673.35 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 30 | Each | 48.92 | 1467.6 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 30 | Each | 189 | 5670 | Plastic Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 200 | Each | 2.47 | 494 | Plastic Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26519-001025 | 26519 | 2019-11-12 18:05 | Core | Material | Not on List | Not on List | 1 | ea | 771.38 | 771 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26531-001025 | 26531 | 2019-11-13 08:35 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-26533-001025 | 26533 | 2019-11-13 09:16 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26131-001025 | 26131 | 2019-11-04 10:03 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Fixings and Fasteners | 2019-11-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | IMO Queue | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26537-001025 | 26537 | 2019-11-13 10:16 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 2675.07 | 2675 | Miscellaneous | 2019-11-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26455-001025 | 26455 | 2019-11-12 08:10 | Section 4 | Material | Not on List | Not on List | 270 | Each | 36.24 | 9784.8 | Miscellaneous | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26455-001025 | 26455 | 2019-11-12 08:10 | Section 4 | Material | NULL | Not on List | 1 | Each | 550 | 550 | Miscellaneous | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26540-001025 | 26540 | 2019-11-13 12:33 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4605.14 | each | 1 | 4605 | PPE | 2019-11-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-26484-001025 | 26484 | 2019-11-12 13:25 | Section 4 | Material | Not on List | Not on List | 5 | Each | 50 | 250 | Electrical | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7807-001023 | 7807 | 2018-10-15 15:57 | Section 3 | Material | Not on List | Not on List | 16 | No | 36.75 | 588 | Builders Merchants (General) | 2018-11-02 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7968-001023 | 7968 | 2018-10-18 16:06 | Section 4 | Material | Not on List | Not on List | 16 | Each | 110.27 | 1764.32 | Geotextiles | 2018-10-22 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 604 - Deposition | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 4 | EA | 376.8 | 1507.2 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8083-001023 | 8083 | 2018-10-22 14:06 | Section 4 | Material | Not on List | Not on List | 76 | number | NULL | 0 | Reinforcement | 2018-10-26 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8083-001023 | 8083 | 2018-10-22 14:06 | Section 4 | Material | Not on List | Not on List | 16 | number | NULL | 0 | Reinforcement | 2018-10-26 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7931-001023 | 7931 | 2018-10-17 18:31 | Section 4 | Material | Not on List | Not on List | 1 | Each | 7711.17 | 7711.17 | Damage Charges | 2018-10-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8086-001023 | 8086 | 2018-10-22 15:28 | Section 4 | Material | Not on List | Not on List | 1 | Weekly | 550 | 550 | Miscellaneous | 2018-06-01 | RVP 417 - 1339631 - Girton Compound Huntingdon Rd A1307 | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8087-001023 | 8087 | 2018-10-22 15:48 | Section 4 | Material | Not on List | Not on List | 1 | Deployment Charge | 1519 | 1519 | Miscellaneous | 2018-10-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8059-001023 | 8059 | 2018-10-22 09:00 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pack | 3.79 | 37.9 | Miscellaneous | 2018-10-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7437-001022 | 7437 | 2018-10-05 10:39 | Section 4 | Material | Not on List | Not on List | 6 | boxes of 5 | 11.23 | 67.38 | Not Sure | 2018-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8095-001023 | 8095 | 2018-10-22 16:02 | Section 3 | Material | Aggregate | Not on List | 3500 | m3 | 43.08 | 150780 | Aggregate | 2018-10-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 2 | EA | 452.16 | 904.32 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8095-001023 | 8095 | 2018-10-22 16:02 | Section 3 | Material | Aggregate | Not on List | 3500 | m3 | 43.08 | 150780 | Aggregate | 2018-10-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7959-001023 | 7959 | 2018-10-18 12:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 294.2 | 294.2 | PPE | 2018-10-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7959-001023 | 7959 | 2018-10-18 12:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 337.97 | 337.97 | Small Tools (Consumables) | 2018-10-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8073-001023 | 8073 | 2018-10-22 11:17 | Section 4 | Material | Not on List | Not on List | 10 | Each | NULL | 0 | Not Sure | 2018-10-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8126-001023 | 8126 | 2018-10-23 11:16 | Section 4 | Material | Not on List | Not on List | 300 | NULL | NULL | 0 | Concrete Drainage | 2018-10-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8106-001023 | 8106 | 2018-10-23 07:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 401.56 | 401.56 | Janitorial | 2018-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 3 | EA | 452.16 | 1356.48 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8086-001023 | 8086 | 2018-10-22 15:28 | Section 4 | Material | Not on List | Not on List | 1 | Weekly | 550 | 550 | Miscellaneous | 2018-06-01 | RVP 417 - 1339631 - Girton Compound Huntingdon Rd A1307 | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8108-001023 | 8108 | 2018-10-23 07:36 | Section 4 | Material | Not on List | Not on List | 4 | number | 6.75 | 27 | Not Sure | 2018-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8126-001023 | 8126 | 2018-10-23 11:16 | Section 4 | Material | Not on List | Not on List | 300 | Each | 31.37 | 9411 | Concrete Drainage | 2018-11-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8083-001023 | 8083 | 2018-10-22 14:06 | Section 4 | Material | Not on List | Not on List | 76 | Each | 93.93 | 7138.68 | Concrete Accessories | 2018-10-26 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8083-001023 | 8083 | 2018-10-22 14:06 | Section 4 | Material | Not on List | Not on List | 16 | Each | 51.87 | 829.92 | Concrete Accessories | 2018-10-26 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | NULL | 0 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | NULL | 0 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8087-001023 | 8087 | 2018-10-22 15:48 | Section 4 | Material | Not on List | Not on List | 1 | Deployment Charge | 1519 | 1519 | Miscellaneous | 2018-10-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8039-001023 | 8039 | 2018-10-19 14:21 | Section 4 | Material | Not on List | Not on List | 200 | Each | 6.98 | 1396 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-25 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 1 | EA | 452.16 | 452.16 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500x1000 D/S (991900) | 2 | Each | 121.25 | 243 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500x750 D/S (991899) | 1 | Each | 90.94 | 91 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500X500 D/S (991898) | 1 | Each | 80.51 | 81 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 1 | Each | 102.82 | 103 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 100 | Each | 16.49 | 1649 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 7 | Each | 53.01 | 371 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 750 D/S (913226) | 7 | Each | 61.48 | 430 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | Not on List | 7 | NULL | NULL | 0 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8186-001023 | 8186 | 2018-10-24 08:34 | Section 4 | Material | Not on List | Not on List | 0.068 | Tonne | NULL | 0 | Reinforcement | 2018-10-26 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN20 - Bar Hill Junction West Bridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8186-001023 | 8186 | 2018-10-24 08:34 | Section 4 | Material | Not on List | Not on List | 0.068 | Tonne | NULL | 0 | Reinforcement | 2018-10-26 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN21 - Bar Hill Junction East Bridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 1 | EA | 577.15 | 577.15 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8192-001023 | 8192 | 2018-10-24 11:16 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-10-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8143-001023 | 8143 | 2018-10-23 15:28 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.45 | 147 | Surveying Consumables | 2018-10-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8123-001023 | 8123 | 2018-10-23 09:14 | Section 4 | Material | Not on List | Not on List | 4 | Each | 39.03 | 156.12 | Builders Merchants (General) | 2018-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | 16.84 | 134.72 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | 39.7 | 317.6 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8125-001023 | 8125 | 2018-10-23 10:26 | Section 4 | Material | Not on List | Not on List | 550 | LM | 0.46 | 253 | Miscellaneous | 2018-10-25 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8003-001023 | 8003 | 2018-10-19 09:12 | Section 4 | Material | Not on List | Not on List | 20 | 25kg Bag | 9.34 | 186.8 | Not Sure | 2018-10-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500x1000 D/S (991900) | 2 | Each | 121.25 | 242.5 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500x750 D/S (991899) | 1 | Each | 90.94 | 90.94 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500X500 D/S (991898) | 1 | Each | 80.51 | 80.51 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 1 | EA | 271.01 | 271.01 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 1 | Each | 102.82 | 102.82 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 100 | Each | 16.49 | 1649 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 7 | Each | 53.01 | 371.07 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 750 D/S (913226) | 7 | Each | 61.48 | 430.36 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | Not on List | 7 | ea | 232.01 | 1624.07 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | 16.84 | 134.72 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | 39.7 | 317.6 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8204-001023 | 8204 | 2018-10-24 16:14 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No. | NULL | 0 | Small Tools (Consumables) | 2018-10-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | Saint Gobain Castings | Not on List | 96 | no | 31.37 | 3012 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 1 | EA | 248.57 | 248.57 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | Saint Gobain Castings | Not on List | 26 | no | 31.37 | 816 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 50 | Each | 81.73 | 4087 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8209-001023 | 8209 | 2018-10-24 17:18 | Section 4 | Material | Not on List | Not on List | 48 | NULL | NULL | 0 | Concrete Accessories | 2018-10-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8009-001023 | 8009 | 2018-10-19 09:27 | Section 4 | Material | Not on List | Not on List | 150 | Each | 15.77 | 2365.5 | Plastic Drainage | 2018-10-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8009-001023 | 8009 | 2018-10-19 09:27 | Section 4 | Material | Not on List | Not on List | 150 | Each | 15.77 | 2365.5 | Plastic Drainage | 2018-10-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8009-001023 | 8009 | 2018-10-19 09:27 | Section 4 | Material | Not on List | Not on List | 200 | Each | 2.92 | 584 | Plastic Drainage | 2018-10-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5190-00117 | 5190 | 2018-08-16 07:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 768.16 | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8009-001023 | 8009 | 2018-10-19 09:27 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 1.44 | 1440 | Plastic Drainage | 2018-10-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8234-001023 | 8234 | 2018-10-25 11:22 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1130.86 | 1130.86 | Small Tools (Consumables) | 2018-10-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8227-001023 | 8227 | 2018-10-25 09:31 | Section 4 | Material | PPE, Small Tools and Consumables | Paint Roller And Tray Set 9" Rskit1 (704256) | 50 | Each | 3.42 | 171 | Small Tools (Consumables) | 2018-10-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | NULL | Not on List | 96 | no | 31.37 | 3011.52 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | NULL | Not on List | 26 | no | 31.37 | 815.62 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | NULL | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 50 | Each | 74.3 | 3715 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8240-001023 | 8240 | 2018-10-25 13:42 | Section 3 | Material | Not on List | Not on List | 1 | EA | 71.99 | 71.99 | Miscellaneous | 2018-10-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8282-001023 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 18 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8301-001023 | 8301 | 2018-10-26 11:16 | Section 3 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 36 | Each | 24.32 | 876 | Builders Merchants (General) | 2018-10-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7962 | 7962 | 2018-10-18 13:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1680 | 1680 | Not Sure | 2018-11-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8301-001023 | 8301 | 2018-10-26 11:16 | Section 3 | Material | NULL | 2440x1220x18mm Shuttering Ply (683573) | 36 | Each | 24.32 | 875.52 | Builders Merchants (General) | 2018-10-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8311-001023 | 8311 | 2018-10-26 13:11 | Section 4 | Material | Not on List | Not on List | 3 | boxes | NULL | 0 | Not Sure | 2018-10-31 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 6 | number | NULL | 0 | Not Sure | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 6 | number | NULL | 0 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Signage | Directional Signage - 390 x 510 | 8 | Each | 7.9441 | 64 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Signage | Directional Signage - 390 x 510 | 6 | Each | 7.9441 | 48 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8236-001023 | 8236 | 2018-10-25 11:30 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2518 | 2518 | PPE | 2018-10-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 32 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8367-001023 | 8367 | 2018-10-29 13:07 | Section 4 | Material | Not on List | Not on List | 3 | polybottles | NULL | 0 | Not Sure | 2018-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8192-001023 | 8192 | 2018-10-24 11:16 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 350.58 | 350.58 | Small Tools (Consumables) | 2018-10-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8434-001023 | 8434 | 2018-10-30 10:30 | Section 3 | Material | Not on List | Not on List | 50 | Rolls | NULL | 0 | Builders Merchants (General) | 2018-11-01 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8439-001023 | 8439 | 2018-10-30 11:24 | Section 4 | Material | Bagged | Building Sand Bulk Bag (938155) | 4 | Each | 32.74 | 131 | Builders Merchants (General) | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8311-001023 | 8311 | 2018-10-26 13:11 | Section 4 | Material | Not on List | Not on List | 3 | Box | 63 | 189 | Fixings and Fasteners | 2018-10-31 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8311-001023 | 8311 | 2018-10-26 13:11 | Section 4 | Material | NULL | Not on List | 1 | Each | 30 | 30 | Fixings and Fasteners | 2018-10-31 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8367-001023 | 8367 | 2018-10-29 13:07 | Section 4 | Material | Not on List | Not on List | 3 | Each | 28 | 84 | Concrete Accessories | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8367-001023 | 8367 | 2018-10-29 13:07 | Section 4 | Material | NULL | Not on List | 1 | Each | 40 | 40 | Concrete Accessories | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 55.35 | 55 | PPE | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 20 | NULL | 6.29 | 126 | Miscellaneous | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 16 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8398-001023 | 8398 | 2018-10-29 16:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3000 | Each | 0.37 | 1110 | Miscellaneous | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8391-001023 | 8391 | 2018-10-29 16:26 | Section 4 | Material | NULL | OP Cement; 25kg bag (767201) | 56 | Each | 2.9 | 162.4 | Miscellaneous | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8373-001023 | 8373 | 2018-10-29 12:08 | Section 4 | Material | Not on List | Not on List | 10 | boxes | NULL | 0 | PPE | 2018-11-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8373-001023 | 8373 | 2018-10-29 12:08 | Section 4 | Material | Not on List | Not on List | 100 | each | NULL | 0 | PPE | 2018-11-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8434-001023 | 8434 | 2018-10-30 10:30 | Section 3 | Material | Not on List | Not on List | 50 | Rolls | 6.1 | 305 | Builders Merchants (General) | 2018-11-01 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7972-001023 | 7972 | 2018-10-18 16:28 | Section 4 | Material | Not on List | Not on List | 1 | Each | 69.21 | 69.21 | Plastic Drainage | 2018-11-01 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8464-001023 | 8464 | 2018-10-30 18:14 | Section 3 | Material | PPE, Small Tools and Consumables | Helmet Attachment-jsp Navy Blue Helmet Warmer (271301) | 31 | Each | 5.43 | 168 | PPE | 2018-11-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8471-001023 | 8471 | 2018-10-30 21:48 | Section 4 | Material | Aggregate | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8471-001023 | 8471 | 2018-10-30 21:48 | Section 4 | Material | Aggregate | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8471-001023 | 8471 | 2018-10-30 21:48 | Section 4 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 1 | Price Per Thousand | 345 | 345 | Builders Merchants (General) | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8471-001023 | 8471 | 2018-10-30 21:48 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Builders Merchants (General) | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8472-001023 | 8472 | 2018-10-30 22:32 | Section 4 | Material | Bagged | OP Cement; 25kg bag (767201) | 24 | Each | 2.9 | 70 | Miscellaneous | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8472-001023 | 8472 | 2018-10-30 22:32 | Section 4 | Material | Bagged | Not on List | 12 | NULL | NULL | 0 | Miscellaneous | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8475-001023 | 8475 | 2018-10-31 07:41 | Section 4 | Material | Not on List | Not on List | 15 | number | NULL | 0 | Not Sure | 2018-11-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-8475-001023 | 8475 | 2018-10-31 07:41 | Section 4 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Not Sure | 2018-11-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-8475-001023 | 8475 | 2018-10-31 07:41 | Section 4 | Material | Not on List | Not on List | 4 | number | NULL | 0 | Not Sure | 2018-11-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 358.12 | 358.12 | Small Tools (Consumables) | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 10 | NULL | 650.69 | 6506.9 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 72 | 72 | PPE | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 20 | NULL | 6.29 | 125.8 | Miscellaneous | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 153.86 | 153.86 | Janitorial | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15098-001025 | 15098 | 2019-04-02 09:12 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-4997-0011 | 4997 | 2018-08-13 15:45 | Section 4 | Material | Not on List | Not on List | 9 | Each | 183.3 | 20 | Not Sure | 2018-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14645-001025 | 14645 | 2019-03-26 10:00 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 510 | 510 | Laboratory Equipment / Certification | 2019-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14844-001025 | 14844 | 2019-03-28 09:39 | Core | Material | Not on List | Not on List | 25 | Bundles | 9 | 225 | Surveying Consumables | 2019-04-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14844-001025 | 14844 | 2019-03-28 09:39 | Core | Material | Not on List | Not on List | 10 | Bundles | 9 | 90 | Surveying Consumables | 2019-04-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14844-001025 | 14844 | 2019-03-28 09:39 | Core | Material | Not on List | Not on List | 10 | Bundles | 9 | 90 | Surveying Consumables | 2019-04-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14844-001025 | 14844 | 2019-03-28 09:39 | Core | Material | Not on List | Not on List | 15 | Bundles | 9 | 135 | Surveying Consumables | 2019-04-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14528-001025 | 14528 | 2019-03-22 12:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | 162.11 | 324.22 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | CPM 1800 Cover Slab 600x600 Opening (985438) | 1 | Each | 149.9 | 149.9 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 1 | Each | 165.1 | 165.1 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | CPM 750mm Concrete Rocker (249360) | 2 | Each | 198.12 | 396.24 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | CPM 750mm Concrete Socket (890395) | 1 | Each | 198.12 | 198.12 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 198.12 | 198.12 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | CPM 675mm Concrete Pipe 2.5m (249358) | 1 | Each | 148.8 | 148.8 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | Not on List | 1 | Each | 3540 | 3540 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | Not on List | 3000 | No | 1.85 | 5550 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | Not on List | 2000 | No | 0.31 | 620 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14671-001025 | 14671 | 2019-03-26 13:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 123.3 | 246.6 | Small Tools (Consumables) | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5895-00560 | 5895 | 2018-08-31 14:00 | Section 3 | Material | Not on List | Not on List | 1 | ea | 567.63 | 567.63 | Damage Charges | 2018-09-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5739-00526 | 5739 | 2018-08-29 09:54 | Section 3 | Material | Not on List | Not on List | 1 | EA | 5440.13 | 5440.13 | Damage Charges | 2018-08-30 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5884-00563 | 5884 | 2018-08-31 14:48 | Section 3 | Material | Not on List | Not on List | 2 | ea | 55.44 | 110.88 | Miscellaneous | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15112-001025 | 15112 | 2019-04-02 11:11 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15112-001025 | 15112 | 2019-04-02 11:11 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5884-00563 | 5884 | 2018-08-31 14:48 | Section 3 | Material | Not on List | Not on List | 2 | ea | 43.12 | 86.24 | Miscellaneous | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14768-001025 | 14768 | 2019-03-27 14:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2104.45 | 2104.45 | Small Tools (Consumables) | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15116-001025 | 15116 | 2019-04-02 11:29 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 12.84 | 13 | Electrical | 2019-04-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | IMO - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14975-001025 | 14975 | 2019-04-01 07:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 18.95 | 189.5 | Small Tools (Consumables) | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14975-001025 | 14975 | 2019-04-01 07:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 63.91 | 639.1 | NULL | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 380 | meters | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 90 | number | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 90 | number | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-5884-00563 | 5884 | 2018-08-31 14:48 | Section 3 | Material | Not on List | Not on List | 1 | ea | 24.64 | 24.64 | Miscellaneous | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 90 | number | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15127-001025 | 15127 | 2019-04-02 13:29 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 6 | Metres | 5.43 | 33 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14978-001025 | 14978 | 2019-04-01 07:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 217.8 | 217.8 | PPE | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15137-001025 | 15137 | 2019-04-02 14:29 | Section 5 | Material | Not on List | Not on List | 1 | EACH | 331.05 | 331 | Miscellaneous | 2019-04-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15139-001025 | 15139 | 2019-04-02 14:32 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 5619.3 | 5619 | Miscellaneous | 2019-04-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14562-001025 | 14562 | 2019-03-23 13:33 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-03-25 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15015-001025 | 15015 | 2019-04-01 09:47 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 268.8 | 268.8 | PPE | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15108-001025 | 15108 | 2019-04-02 11:00 | Section 3 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 500 | Each | 3.04 | 1520 | Miscellaneous | 2019-04-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5828-00517 | 5828 | 2018-08-30 17:05 | Section 4 | Material | Not on List | Not on List | 2 | tonnes | 32.74 | 65.48 | Builders Merchants (General) | 2018-08-07 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15108-001025 | 15108 | 2019-04-02 11:00 | Section 3 | Material | Not on List | Not on List | 1 | Each | 24.45 | 24.45 | Miscellaneous | 2019-04-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15106-001025 | 15106 | 2019-04-02 10:12 | Section 4 | Material | Not on List | Not on List | 1 | pack of 100 | 76.5 | 76.5 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15106-001025 | 15106 | 2019-04-02 10:12 | Section 4 | Material | Not on List | Not on List | 1 | pack of 100 | 38.97 | 38.97 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15106-001025 | 15106 | 2019-04-02 10:12 | Section 4 | Material | Not on List | Not on List | 1 | pack of 100 | 29.32 | 29.32 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5828-00517 | 5828 | 2018-08-30 17:05 | Section 4 | Material | Not on List | Not on List | 1 | 25 litre | 41.81 | 41.81 | Builders Merchants (General) | 2018-08-07 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15100-001025 | 15100 | 2019-04-02 09:31 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 16 | Each | 116.88 | 1870.08 | Geotextiles | 2019-04-09 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15109-001025 | 15109 | 2019-04-02 11:09 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | 3.42 | 205.2 | Small Tools (Consumables) | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15136-001025 | 15136 | 2019-04-02 14:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 809.78 | 809.78 | Small Tools (Consumables) | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15182-001025 | 15182 | 2019-04-03 07:11 | Section 2 | Material | Bagged | Sharp Sand Bulk Bag (938208) | 1 | Each | 32.74 | 33 | Builders Merchants (General) | 2019-04-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 601 - Topsoil Strip, Store, Dispose | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15182-001025 | 15182 | 2019-04-03 07:11 | Section 2 | Material | Bagged | OP Cement; 25kg bag (767201) | 20 | Each | 2.9 | 58 | Builders Merchants (General) | 2019-04-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 601 - Topsoil Strip, Store, Dispose | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15145-001025 | 15145 | 2019-04-02 14:47 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 3623.1 | 3623.1 | Miscellaneous | 2019-04-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14937-001025 | 14937 | 2019-03-29 11:57 | Section 4 | Material | Not on List | Not on List | 40 | Each | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14599-001025 | 14599 | 2019-03-25 13:48 | Core | Material | Not on List | Not on List | 1 | Number | 386 | 386 | Office Supplies | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15059-001025 | 15059 | 2019-04-01 17:00 | Section 3 | Material | Not on List | Not on List | 50 | No. | 52.76 | 2638 | Plastic Drainage | 2019-04-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15059-001025 | 15059 | 2019-04-01 17:00 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 687.5 | Plastic Drainage | 2019-04-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15059-001025 | 15059 | 2019-04-01 17:00 | Section 3 | Material | Not on List | Not on List | 30 | No. | 37.6 | 1128 | Plastic Drainage | 2019-04-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15062-001025 | 15062 | 2019-04-01 15:29 | Section 5 | Material | Not on List | Not on List | 1 | each | 103.11 | 103.11 | Waste (General) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15062-001025 | 15062 | 2019-04-01 15:29 | Section 5 | Material | Not on List | Not on List | 2 | each | 485.3 | 970.6 | Professional Services | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15062-001025 | 15062 | 2019-04-01 15:29 | Section 5 | Material | Not on List | Not on List | 70 | EACH | 17.49 | 1224.3 | Timber Products | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15062-001025 | 15062 | 2019-04-01 15:29 | Section 5 | Material | Not on List | Not on List | 200 | M2 | 3.25 | 650 | Miscellaneous | 2019-04-04 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 9 | No | 70.61 | 635.49 | Concrete Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | 52.95 | 105.9 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 8 | No | 44.88 | 359.04 | Concrete Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 14 | No | 36.94 | 517.16 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 48.92 | 489.2 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 8 | No | 85.23 | 681.84 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | 63.93 | 127.86 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 6 | No | 55.13 | 330.78 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 10 | No | 38.08 | 380.8 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 8 | Each | 61.53 | 492.24 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 119.52 | 119.52 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 89.64 | 89.64 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 126.1 | 126.1 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 4 | NULL | 94.57 | 378.28 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 4 | NULL | 83.73 | 334.92 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 4 | NULL | 106.96 | 427.84 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 5 | Each | 162.11 | 810.55 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 121.58 | 121.58 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 149.8 | 149.8 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | CPM 1800 Cover Slab 600x600 Opening (985438) | 1 | Each | 149.8 | 149.8 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 15 | No Carton's | 40.61 | 609.15 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5864-00556 | 5864 | 2018-08-31 13:42 | Section 3 | Material | Not on List | Not on List | 20 | no | 8.8 | 176 | Electrical | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14793-001025 | 14793 | 2019-03-27 16:49 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1050.43 | 1050.43 | PPE | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15151-001025 | 15151 | 2019-04-02 15:34 | Section 3 | Material | Not on List | Not on List | 1 | No | 100.23 | 100.23 | Damage Charges | 2019-04-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 48 | Each | 24.99 | 1199.52 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 106 | Each | 3.65 | 386.9 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 220 | Each | 2 | 440 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 84 | Each | 37.6 | 3158.4 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 180 | Each | 7.06 | 1270.8 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 375 | Each | 2.97 | 1113.75 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 38 | NULL | 130.26 | 4949.88 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5864-00556 | 5864 | 2018-08-31 13:42 | Section 3 | Material | Not on List | Not on List | 100 | lm | 9.64 | 964 | Electrical | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 85 | NULL | 18.84 | 1601.4 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 180 | NULL | 9.76 | 1756.8 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 225mm x 225mm Ridgdrain 45deg Junction (878042) | 6 | Each | 56.17 | 337.02 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 10 | NULL | 156.5 | 1565 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 6 | NULL | 188.37 | 1130.22 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 9 | NULL | 131.32 | 1181.88 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 300mm x 150mm Ridgidrain 45deg Junction (878090) | 8 | Each | 47.96 | 383.68 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 45deg Junction (878038) | 8 | Each | 42.87 | 342.96 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 199.28 | 398.56 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 52.77 | 105.54 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5952-00585 | 5952 | 2018-09-03 09:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Ltrs | 2.77 | 277 | Miscellaneous | 2018-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 27 | NULL | 179.74 | 4852.98 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 60 | NULL | 38.36 | 2301.6 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 135 | NULL | 22.36 | 3018.6 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 7 | NULL | 164.37 | 1150.59 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 4 | NULL | 145 | 580 | Plastic Drainage | 2019-04-05 | EB5/10 Works Access, A14 Eastbound, Central Reservation between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 8 | NULL | 21.29 | 170.32 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14820-001025 | 14820 | 2019-03-27 18:55 | Section 5 | Material | Not on List | Not on List | 4 | No | 38.09 | 152.36 | Concrete Drainage | 2019-04-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15123-001025 | 15123 | 2019-04-02 13:00 | Section 4 | Material | Not on List | Not on List | 100 | Each | 7.5 | 750 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15118-001025 | 15118 | 2019-04-02 11:41 | Section 4 | Material | NULL | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 1 | Pack 504 | 173.88 | 173.88 | Blocks and Bricks | 2019-04-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15176-001025 | 15176 | 2019-04-02 17:22 | Section 4 | Material | Not on List | Not on List | 112 | Each | 38.09 | 4266.08 | Builders Merchants (General) | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15176-001025 | 15176 | 2019-04-02 17:22 | Section 4 | Material | Not on List | Not on List | 30 | Each | 2.97 | 89.1 | Builders Merchants (General) | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15132-001025 | 15132 | 2019-04-02 14:09 | Core | Material | Not on List | Not on List | 8 | NULL | 37 | 296 | Office Supplies | 2019-04-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14658-001025 | 14658 | 2019-03-26 11:33 | Section 2 | Material | Aggregate | Type 1 | 1000 | Tonnes | 21.65 | 21650 | Aggregate | 2019-03-31 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14039-001025 | 14039 | 2019-03-14 13:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1000 | 1000 | Miscellaneous | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14262-001025 | 14262 | 2019-03-19 11:09 | Section 2 | Material | Waste Management | Not on List | 1 | NULL | NULL | 0 | Tanks and Interceptors | 2019-03-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14463-001025 | 14463 | 2019-03-21 14:40 | Core | Material | Not on List | Not on List | 1 | Each | 495 | 495 | Training | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15165-001025 | 15165 | 2019-04-02 16:56 | Section 2 | Material | NULL | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 18 | Each | 166.43 | 2995.74 | Plastic Drainage | 2019-04-04 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12459-001025 | 12459 | 2019-02-14 10:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2390 | 2390 | Miscellaneous | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12382-001025 | 12382 | 2019-02-13 11:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 336.28 | 336.28 | Miscellaneous | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12785-001025 | 12785 | 2019-02-20 15:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12732-001025 | 12732 | 2019-02-19 16:34 | Section 4 | Material | Waste Management | Dry Mixed Recycling - Wheelie Bin 660 Litre | 6 | Each | 61.8 | 370.8 | Waste (General) | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12156-001025 | 12156 | 2019-02-08 13:01 | Core | Material | Not on List | Not on List | 3 | number packs | 21.45 | 64 | Office Supplies | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | 111 - Stationery /Postage | IMO - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12790-001025 | 12790 | 2019-02-20 16:16 | Section 1 | Material | Aggregate | Type 1 | 15000 | Tonnes | 21.65 | 324750 | Aggregate | 2019-02-25 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-12791-001025 | 12791 | 2019-02-20 15:56 | Section 2 | Material | Twinwall | Not on List | 15 | Units | NULL | 0 | Plastic Drainage | 2019-02-25 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12791-001025 | 12791 | 2019-02-20 15:56 | Section 2 | Material | Twinwall | Not on List | 1 | unit | NULL | 0 | Plastic Drainage | 2019-02-25 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12791-001025 | 12791 | 2019-02-20 15:56 | Section 2 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 13 | Each | 116.62 | 1516 | Plastic Drainage | 2019-02-25 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12791-001025 | 12791 | 2019-02-20 15:56 | Section 2 | Material | Concrete Drainage | Not on List | 100 | Units | NULL | 0 | Plastic Drainage | 2019-02-25 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12792-001025 | 12792 | 2019-02-20 16:24 | Section 2 | Material | Not on List | Not on List | 12.553 | NULL | NULL | 0 | Reinforcement | 2019-03-04 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12652-001025 | 12652 | 2019-02-18 16:28 | Section 4 | Material | Not on List | Not on List | 5 | Each | 83 | 415 | Miscellaneous | 2019-03-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12811-001025 | 12811 | 2019-02-21 07:07 | Section 2 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Miscellaneous | 2019-02-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 30 | Each | 3.52 | 105.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Concrete Kerbs 125x255 HB External Radius (947297) | 15 | Each | 5.43 | 81.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 10 | Each | 7.68 | 76.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 10 | Each | 7.68 | 76.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12687-001025 | 12687 | 2019-02-19 12:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 62.75 | 62.75 | Small Tools (Consumables) | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12692-001025 | 12692 | 2019-02-19 12:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 522.72 | 522.72 | Small Tools (Consumables) | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12708-001025 | 12708 | 2019-02-19 14:09 | Section 4 | Material | Not on List | Not on List | 20 | Each | 41.2 | 824 | Miscellaneous | 2019-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3010 - Ground Preparation, Cultivation and Mulching | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12734-001025 | 12734 | 2019-02-19 16:49 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 261.84 | 261.84 | Janitorial | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12816-001025 | 12816 | 2019-02-21 08:18 | Section 2 | Material | Not on List | Not on List | 300 | meters | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 150 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12045-001025 | 12045 | 2019-02-07 10:45 | Core | Material | Not on List | Not on List | 1 | ea | 1265.37 | 1265.37 | Training | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12296-001025 | 12296 | 2019-02-12 10:04 | Core | Material | Not on List | Not on List | 1 | ea | 41504 | 41504 | Office Supplies | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12573-001025 | 12573 | 2019-02-15 13:53 | Core | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Training | 2019-02-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12830-001025 | 12830 | 2019-02-21 09:40 | Section 2 | Material | Not on List | Not on List | 250000 | £ | 1 | 250000 | Fuel | 2019-02-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12831-001025 | 12831 | 2019-02-21 09:01 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 346.49 | 346 | Damage Charges | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-12721-001025 | 12721 | 2019-02-19 15:44 | Section 3 | Material | Concrete Drainage | Not on List | 700 | No. | 18.43 | 12901 | Concrete Drainage | 2019-02-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1800 x 1000 D/S (528457) | 1 | Each | 155.88 | 155.88 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12721-001025 | 12721 | 2019-02-19 15:44 | Section 3 | Material | Concrete Drainage | Not on List | 76 | No. | 74.3 | 5646.8 | Ductile Drainage | 2019-02-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1800 x 750 D/S (528456) | 1 | Each | 116.91 | 116.91 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM 1800 Cover Slab 600x600 Opening (985438) | 1 | Each | 144.04 | 144.04 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | Not on List | 20 | NULL | 209.43 | 4188.6 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411.2 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 7 | Each | 67.9 | 475.3 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509.2 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5625-00424 | 5625 | 2018-08-24 11:29 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 4652 | 4652 | Professional Services | 2018-08-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11827 | 11827 | 2019-02-01 15:45 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12081-001025 | 12081 | 2019-02-07 16:08 | Core | Material | Not on List | Not on List | 1 | number | 180 | 180 | Office Supplies | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | 110 - Welfare Costs | IMO - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12842-001025 | 12842 | 2019-02-21 11:37 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Plastic Drainage | 2019-02-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12850-001025 | 12850 | 2019-02-21 13:23 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-12792-001025 | 12792 | 2019-02-20 16:24 | Section 2 | Material | Not on List | Not on List | 12.553 | NULL | NULL | 0 | NULL | 2019-03-04 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12389-001025 | 12389 | 2019-02-13 13:16 | Section 6 | Material | Not on List | Not on List | 1 | sum | 960.8 | 960.8 | Miscellaneous | 2019-02-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-12574-001025 | 12574 | 2019-02-15 13:19 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Tanker and disposal | 2617.55 | 2617.55 | Miscellaneous | 2019-02-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12860-001025 | 12860 | 2019-02-21 15:21 | Section 5 | Material | Not on List | Not on List | 1 | NULL | 466.88 | 467 | Damage Charges | 2019-02-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-12785-001025 | 12785 | 2019-02-20 15:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 406.28 | 406.28 | Small Tools (Consumables) | 2019-02-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12865-001025 | 12865 | 2019-02-21 15:44 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 1597.71 | 1598 | Miscellaneous | 2019-02-22 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | FEE6 - Fee Based Costs inc. insurance | 107 - Insurance | Buyer - Closed | NULL | Yes - Approve | Req - S6 Buyers
MREQ-12877-001025 | 12877 | 2019-02-21 16:39 | Core | Material | Not on List | Not on List | 1 | Number | 394.8 | 395 | Office Supplies | 2019-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | NULL | Not on List | 9 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | NULL | Not on List | 13 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | NULL | Not on List | 20 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | NULL | Not on List | 40 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 270 | metres | 3.52 | 950.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 9 | Each | 7.68 | 69.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 8 | Each | 7.68 | 61.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 903 | metres | 1.5 | 1354.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Concrete Kerbs 125x150x914 BN Straight (753034) | 30 | metres | 3.03 | 90.9 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Not on List | 450 | metres | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Not on List | 15 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Not on List | 15 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Not on List | 75 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12760-001025 | 12760 | 2019-02-20 08:49 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | number | 6.74 | 404.4 | Miscellaneous | 2019-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12761-001025 | 12761 | 2019-02-20 09:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 4056.35 | 4056.35 | Small Tools (Consumables) | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12763-001025 | 12763 | 2019-02-20 09:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 173 | 173 | PPE | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12821-001025 | 12821 | 2019-02-21 08:53 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 72 | Each | 6.29 | 452.88 | Miscellaneous | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12664-001025 | 12664 | 2019-02-19 08:38 | Core | Material | Not on List | Not on List | 1 | ea | 42200 | 42200 | Office Supplies | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12933-001025 | 12933 | 2019-02-22 08:35 | Core | Material | Not on List | Not on List | 1 | number | 40 | 40 | Miscellaneous | 2019-02-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12842-001025 | 12842 | 2019-02-21 11:37 | Section 4 | Material | Plastic Drainage | Not on List | 4 | 50M | 79.05 | 316.2 | Plastic Drainage | 2019-02-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12947-001025 | 12947 | 2019-02-22 11:23 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1915.2 | 1915 | Laboratory Equipment / Certification | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6321-00661 | 6321 | 2018-09-11 11:19 | Section 4 | Material | Not on List | Not on List | 5.691 | Tonne | 538 | 3061.76 | Rebar and Mesh | 2018-09-27 | RVP 419 - 1340880 - A14 Westbound (West of Junction 28) | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22223-001025 | 22223 | 2019-08-13 13:36 | Core | Material | NULL | NULL | 1 | Each | 109 | 109 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22670-001025 | 22670 | 2019-08-22 12:16 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-22175-001025 | 22175 | 2019-08-12 17:06 | Core | Material | NULL | NULL | 1 | Each | 1959 | 1959 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | No - Reject | REQ - Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Not on List | 6 | EACH | 18.45 | 110.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 16 | Each | 10.8 | 172.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 12 | Each | 10.8 | 129.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 6 | Each | 11.94 | 71.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 6 | Each | 7.96 | 47.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6321-00661 | 6321 | 2018-09-11 11:19 | Section 4 | Material | Not on List | Not on List | 3.376 | Tonne | 538 | 1816.29 | Rebar and Mesh | 2018-09-27 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 6 | Each | 7.96 | 47.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 30 | Each | 10.8 | 324 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 30 | Each | 10.8 | 324 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22577-001025 | 22577 | 2019-08-20 17:17 | Section 4 | Material | Signage | Not on List | 4 | Each | 13.95 | 55.8 | Builders Merchants (General) | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6322-00663 | 6322 | 2018-09-11 11:38 | Section 4 | Material | Not on List | Not on List | 50 | Each | 1.32 | 66 | Concrete Accessories | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22681-001025 | 22681 | 2019-08-22 16:11 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | 36 | 144 | Small Tools (Consumables) | 2019-08-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22681-001025 | 22681 | 2019-08-22 16:11 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 0.68 | 7 | Miscellaneous | 2019-08-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22662-001025 | 22662 | 2019-08-22 10:50 | Section 5 | Material | Not on List | Not on List | 3 | EA | 435 | 1305 | Miscellaneous | 2019-08-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22690-001025 | 22690 | 2019-08-22 17:33 | Section 5 | Material | Aggregate | Type 1 | 4500 | Tonnes | 21.65 | 97425 | Aggregate | NULL | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 604 - Deposition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5091-0039 | 5091 | 2018-08-14 17:07 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 2410.5 | 2410.5 | Damage Charges | 2018-08-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6322-00663 | 6322 | 2018-09-11 11:38 | Section 4 | Material | Not on List | Not on List | 50 | Each | 0.85 | 42.5 | Concrete Accessories | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22676-001025 | 22676 | 2019-08-22 14:33 | Core | Material | Not on List | Not on List | 1 | EA | 1000 | 1000 | Small Tools (Consumables) | NULL | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22624-001025 | 22624 | 2019-08-21 15:39 | Section 2 | Material | Twinwall | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-08-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22712-001025 | 22712 | 2019-08-23 08:17 | Section 4 | Material | Not on List | Not on List | 1 | EA | 11935.84 | 11935.84 | Concrete Accessories | 2019-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21727-001025 | 21727 | 2019-08-01 14:17 | Section 4 | Material | Kerbs | NULL | 16 | ea | 28.41 | 454.56 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21727-001025 | 21727 | 2019-08-01 14:17 | Section 4 | Material | Kerbs | NULL | 16 | ea | 11.68 | 186.88 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21727-001025 | 21727 | 2019-08-01 14:17 | Section 4 | Material | Kerbs | NULL | 16 | ea | 11.68 | 186.88 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6322-00663 | 6322 | 2018-09-11 11:38 | Section 4 | Material | Not on List | Not on List | 10 | Coil | 43.05 | 430.5 | Concrete Accessories | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21727-001025 | 21727 | 2019-08-01 14:17 | Section 4 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 16 | Each | 7.68 | 122.88 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21727-001025 | 21727 | 2019-08-01 14:17 | Section 4 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 16 | Each | 11.94 | 191.04 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22479-001025 | 22479 | 2019-08-19 15:13 | Section 4 | Material | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 384 | Each | 3.52 | 1351.68 | Miscellaneous | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22479-001025 | 22479 | 2019-08-19 15:13 | Section 4 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 390 | Each | 4.59 | 1790.1 | Miscellaneous | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22454-001025 | 22454 | 2019-08-19 09:33 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 49 | Each | 37.6 | 1842.4 | Ductile Drainage | 2019-08-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22454-001025 | 22454 | 2019-08-19 09:33 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 57 | Each | 7.06 | 402.42 | Ductile Drainage | 2019-08-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22454-001025 | 22454 | 2019-08-19 09:33 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 57 | Each | 2.97 | 169.29 | Ductile Drainage | 2019-08-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22678-001025 | 22678 | 2019-08-22 15:49 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 10 | Each | 37.6 | 376 | Plastic Drainage | 2019-08-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22416-001025 | 22416 | 2019-08-16 15:10 | Section 3 | Material | Not on List | Not on List | 50 | No. | 43.2 | 2160 | Flow Control | 2019-08-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22416-001025 | 22416 | 2019-08-16 15:10 | Section 3 | Material | Not on List | Not on List | 1 | Roll | 75 | 75 | Flow Control | 2019-08-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6337 | 6337 | 2018-09-11 14:42 | Section 4 | Material | Not on List | Not on List | 10 | u | NULL | 0 | Rebar and Mesh | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22512-001025 | 22512 | 2019-08-20 10:00 | Section 3 | Material | Kerbs | Not on List | 8 | No. | 39.22 | 313.76 | Builders Merchants (General) | 2019-08-21 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22584-001025 | 22584 | 2019-08-21 08:23 | Section 3 | Material | Kerbs | Not on List | 1 | No. | 39.22 | 39.22 | Builders Merchants (General) | 2019-08-22 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22705-001025 | 22705 | 2019-08-23 07:25 | Section 2 | Material | Not on List | Not on List | 80 | NULL | NULL | 0 | Miscellaneous | 2019-08-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22304-001025 | 22304 | 2019-08-15 08:02 | Section 3 | Material | Not on List | Not on List | 1 | Each | 3920 | 3920 | Concrete Drainage | 2019-08-22 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22753-001025 | 22753 | 2019-08-25 09:28 | Section 6 | Material | Aggregate | Class 1A | 2000 | Tonnes | 12.5 | 25000 | Aggregate | 2019-08-27 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6353-00673 | 6353 | 2018-09-11 16:46 | Section 4 | Material | Not on List | Not on List | 125 | Each | 0.3 | 37.5 | Builders Merchants (General) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22663-001025 | 22663 | 2019-08-22 10:58 | Core | Material | NULL | NULL | 12 | Each | 11.57 | 138.84 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22672-001025 | 22672 | 2019-08-22 14:00 | Core | Material | NULL | NULL | 20 | Pair | 0.52 | 10.4 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22716-001025 | 22716 | 2019-08-23 08:46 | Section 4 | Material | Not on List | Not on List | 60 | sheet | 18.5 | 1110 | Builders Merchants (General) | 2019-08-28 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22596-001025 | 22596 | 2019-08-21 10:17 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20428-001025 | 20428 | 2019-07-08 16:53 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20505-001025 | 20505 | 2019-07-09 14:14 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20521-001025 | 20521 | 2019-07-09 20:09 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-6353-00673 | 6353 | 2018-09-11 16:46 | Section 4 | Material | Not on List | NULL | 1 | Each | 7.95 | 7.95 | Builders Merchants (General) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21253-001025 | 21253 | 2019-07-24 09:54 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22008-001025 | 22008 | 2019-08-08 14:22 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22019-001025 | 22019 | 2019-08-08 15:17 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22673-001025 | 22673 | 2019-08-22 14:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 825 | 825 | Miscellaneous | 2019-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22686-001025 | 22686 | 2019-08-22 16:42 | Section 4 | Material | Not on List | Not on List | 1 | No. | 65 | 65 | Surveying Consumables | 2019-08-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22686-001025 | 22686 | 2019-08-22 16:42 | Section 4 | Material | Not on List | Not on List | 12 | No. | 25 | 300 | Surveying Consumables | 2019-08-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6391-00686 | 6391 | 2018-09-12 10:32 | Section 4 | Material | Not on List | Not on List | 200 | Each | 4.37 | 874 | Miscellaneous | 2018-09-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22818-001025 | 22818 | 2019-08-27 16:13 | Section 5 | Material | PPE, Small Tools and Consumables | Water Natural Mineral Ideal Still 500ml Bottle Case Of 24 (744570) | 72 | Each | 6.29 | 453 | PPE | 2019-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22842-001025 | 22842 | 2019-08-27 18:51 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 27 | 27 | Surveying Consumables | 2019-08-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1804 - Portal Gantries | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-22854-001025 | 22854 | 2019-08-28 07:44 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Concrete Accessories | 2019-08-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22645-001025 | 22645 | 2019-08-22 07:39 | Section 4 | Material | Signage | Not on List | 100 | Each | 5.8 | 580 | Miscellaneous | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22797-001025 | 22797 | 2019-08-27 10:08 | Section 5 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 9.75 | 546 | Builders Merchants (General) | 2019-08-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6403-00693 | 6403 | 2018-09-12 12:53 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 0.89 | 890 | Timber Products | 2018-09-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6405-00694 | 6405 | 2018-09-12 12:56 | Section 4 | Material | Not on List | Not on List | 4 | Each | 258.05 | 1032.2 | Not Sure | 2018-09-24 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 5mtr/1 (765565) | 5 | Each | 2.7 | 14 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 7.5mtr/2 (765566) | 5 | Each | 5.77 | 29 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 10mtr/3 (765567) | 5 | Each | 12.4 | 62 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22815-001025 | 22815 | 2019-08-27 14:34 | Section 5 | Material | Kerbs | NULL | 1 | SM | 2631 | 2631 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22788-001025 | 22788 | 2019-08-27 09:16 | Section 5 | Material | Not on List | Not on List | 18 | ROLL | 9.6 | 172.8 | Concrete Accessories | 2019-08-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6405-00694 | 6405 | 2018-09-12 12:56 | Section 4 | Material | NULL | NULL | 1 | Each | 85 | 85 | NULL | 2018-09-24 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22789-001025 | 22789 | 2019-08-27 09:29 | Section 5 | Material | Bagged | Not on List | 1 | SM | 1779.28 | 1779.28 | Builders Merchants (General) | 2019-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22282-001025 | 22282 | 2019-08-14 14:08 | Core | Material | Not on List | Not on List | 243.92 | Each | 1 | 243.92 | NULL | NULL | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6405-00694 | 6405 | 2018-09-12 12:56 | Section 4 | Material | NULL | NULL | 4 | Each | 10.5 | 42 | NULL | 2018-09-24 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22282-001025 | 22282 | 2019-08-14 14:08 | Core | Material | Not on List | Not on List | 431.77 | Each | 1 | 431.77 | NULL | NULL | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22799-001025 | 22799 | 2019-08-27 10:45 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | NULL | 6.29 | 905.76 | Small Tools (Consumables) | 2019-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22674-001025 | 22674 | 2019-08-22 13:38 | Section 4 | Material | Not on List | Not on List | 3 | Each | 67.58 | 202.74 | Miscellaneous | 2019-08-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22674-001025 | 22674 | 2019-08-22 13:38 | Section 4 | Material | Not on List | Not on List | 1 | Each | 130.68 | 130.68 | Miscellaneous | 2019-08-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22674-001025 | 22674 | 2019-08-22 13:38 | Section 4 | Material | Not on List | Not on List | 1 | Each | 45 | 45 | Miscellaneous | 2019-08-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5108-0042 | 5108 | 2018-08-15 07:26 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 161.16 | 161.16 | Damage Charges | 2018-08-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6405-00694 | 6405 | 2018-09-12 12:56 | Section 4 | Material | NULL | NULL | 1 | Each | 312 | 312 | NULL | 2018-09-24 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6410-00696 | 6410 | 2018-09-12 13:24 | Section 4 | Material | Not on List | Not on List | 14 | sheets | 8.47 | 118.58 | Not Sure | 2018-09-23 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22893-001025 | 22893 | 2019-08-28 15:29 | Section 2 | Material | Not on List | Not on List | 20 | 600ml sausage | NULL | 0 | Ductile Drainage | 2019-09-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22893-001025 | 22893 | 2019-08-28 15:29 | Section 2 | Material | Not on List | Not on List | 2 | no. | NULL | 0 | Ductile Drainage | 2019-09-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22894-001025 | 22894 | 2019-08-28 15:38 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 461.48 | 461 | Miscellaneous | 2019-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22894-001025 | 22894 | 2019-08-28 15:38 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 395.53 | 396 | PPE | 2019-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22895-001025 | 22895 | 2019-08-28 16:08 | Section 5 | Material | Not on List | Not on List | 10 | boxes | NULL | 0 | Builders Merchants (General) | 2019-08-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-22908-001025 | 22908 | 2019-08-29 07:09 | Section 2 | Material | Not on List | Not on List | 500 | metres | NULL | 0 | Concrete Accessories | 2019-09-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-22908-001025 | 22908 | 2019-08-29 07:09 | Section 2 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 25 | Each | 6.82 | 171 | Concrete Accessories | 2019-09-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-22908-001025 | 22908 | 2019-08-29 07:09 | Section 2 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 25 | Each | 10.08 | 252 | Concrete Accessories | 2019-09-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-6451-00701 | 6451 | 2018-09-12 18:28 | Section 3 | Material | Not on List | Not on List | 1 | SM | 203.79 | 203.79 | Damage Charges | 2018-09-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16813-001025 | 16813 | 2019-05-02 11:43 | Core | Material | Not on List | Not on List | 1 | NULL | 162.8 | 163 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22877-001025 | 22877 | 2019-08-28 13:13 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2260.93 | Each | 1 | 2260.93 | PPE | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22878-001025 | 22878 | 2019-08-28 13:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1031.07 | Each | 1 | 1031.07 | Janitorial | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22924-001025 | 22924 | 2019-08-29 10:07 | Core | Material | Not on List | Not on List | 1 | ea | 1000 | 1000 | Office Supplies | 2019-09-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Buyers
MREQ-21788-001025 | 21788 | 2019-08-05 13:28 | Section 2 | Material | Not on List | Not on List | 1 | NULL | 9.99 | 10 | Small Tools (Consumables) | 2019-08-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12956-001025 | 12956 | 2019-02-22 12:36 | Section 2 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12956-001025 | 12956 | 2019-02-22 12:36 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 15 | Each | 10.5 | 158 | Plastic Drainage | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12830-001025 | 12830 | 2019-02-21 09:40 | Section 2 | Material | Not on List | Not on List | 250000 | £ | 1 | 250000 | Fuel | 2019-02-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12983-001025 | 12983 | 2019-02-22 14:54 | Section 2 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-02-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12994-001025 | 12994 | 2019-02-23 07:52 | Section 3 | Material | Not on List | Not on List | 15 | NULL | NULL | 0 | Miscellaneous | 2019-02-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13003-001025 | 13003 | 2019-02-25 08:50 | Core | Material | Not on List | Not on List | 2 | Number | NULL | 0 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13006-001025 | 13006 | 2019-02-25 09:36 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12994-001025 | 12994 | 2019-02-23 07:52 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 210.6 | 210.6 | Miscellaneous | 2019-02-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13018-001025 | 13018 | 2019-02-25 12:07 | Core | Material | Not on List | Not on List | 1 | n | 478.99 | 479 | Janitorial | 2019-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 119 - Cleaning Sub.Con | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12870-001025 | 12870 | 2019-02-21 16:13 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 80 | Each | 1.31 | 104.8 | Small Tools (Consumables) | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13024-001025 | 13024 | 2019-02-25 11:59 | Section 5 | Material | Not on List | Not on List | 48 | kg | NULL | 0 | Builders Merchants (General) | 2019-02-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13024-001025 | 13024 | 2019-02-25 11:59 | Section 5 | Material | Not on List | Not on List | 1 | bag | NULL | 0 | Builders Merchants (General) | 2019-02-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13027-001025 | 13027 | 2019-02-25 13:05 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 15 | Packs | 11 | 165 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 11 | Packs | 1.88 | 21 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 11 | Packs | 1.55 | 17 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13041-001025 | 13041 | 2019-02-25 15:06 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Electrical | 2019-02-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-02-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN19 - Robins Lane Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-02-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-02-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-04-12 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN20 - Bar Hill Junction West Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 3000 | 3000 | Miscellaneous | 2019-02-25 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5113-0043 | 5113 | 2018-08-15 07:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5619-00423 | 5619 | 2018-08-24 11:01 | Section 3 | Material | Plastic Drainage | Not on List | 40 | No | 15.71 | 628.4 | Builders Merchants (General) | 2018-08-31 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | Kerbs | Not on List | 80 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | Kerbs | Not on List | 1 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | Kerbs | Not on List | 1 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13074-001025 | 13074 | 2019-02-26 07:40 | Core | Material | Not on List | Not on List | 100 | each | 0 | 0 | Office Supplies | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13087-001025 | 13087 | 2019-02-26 09:15 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Pipe 2.5m (249364) | 38 | Each | 210.95 | 8016 | Concrete Drainage | 2019-03-07 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13087-001025 | 13087 | 2019-02-26 09:15 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Spigot (890375) | 1 | Each | 253.14 | 253 | Concrete Drainage | 2019-03-07 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13091-001025 | 13091 | 2019-02-26 09:27 | Section 5 | Material | Aggregate | 6F5 | 20000 | Tonnes | 14.65 | 293000 | Aggregate | 2019-02-26 | Stockyard, Gate 2 - 1346365 - Off A14 Eastbound between Jcn 32 – 33 | SEC5 - Roadworks | 602 - Excavation (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13099-001025 | 13099 | 2019-02-26 10:47 | Section 5 | Material | Not on List | Not on List | 1 | number | 333.35 | 333 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-5600-00397 | 5600 | 2018-08-23 20:33 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 33.35 | 200.1 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13108-001025 | 13108 | 2019-02-26 12:21 | Section 2 | Material | Not on List | Not on List | 0.472 | t | 538 | 254 | Rebar and Mesh | 2019-02-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13108-001025 | 13108 | 2019-02-26 12:21 | Section 2 | Material | Not on List | Not on List | 4 | ea | 2 | 8 | Rebar and Mesh | 2019-02-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13108-001025 | 13108 | 2019-02-26 12:21 | Section 2 | Material | Not on List | Not on List | 1 | ea | 25.96 | 26 | Rebar and Mesh | 2019-02-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13108-001025 | 13108 | 2019-02-26 12:21 | Section 2 | Material | Not on List | Not on List | 1 | ea | 75 | 75 | Rebar and Mesh | 2019-02-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13091-001025 | 13091 | 2019-02-26 09:27 | Section 5 | Material | Aggregate | 6F5 | 20000 | Tonnes | 14.65 | 293000 | Aggregate | 2019-02-26 | Stockyard, Gate 2 - 1346365 - Off A14 Eastbound between Jcn 32 – 33 | SEC5 - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13113-001025 | 13113 | 2019-02-26 13:35 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-13114-001025 | 13114 | 2019-02-26 13:54 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-13115-001025 | 13115 | 2019-02-26 14:08 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-5600-00397 | 5600 | 2018-08-23 20:33 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 21.6 | 129.6 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5600-00397 | 5600 | 2018-08-23 20:33 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 0.33 | 1.98 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13029-001025 | 13029 | 2019-02-25 13:10 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | 28.8 | 1728 | PPE | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13160-001025 | 13160 | 2019-02-27 08:56 | Core | Material | Not on List | Not on List | 1 | job lot | 13265.58 | 13266 | Miscellaneous | 2019-03-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 15 | Packs | 11 | 165 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 11 | Packs | 1.88 | 20.68 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 11 | Packs | 1.55 | 17.05 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19239-001025 | 19239 | 2019-06-17 15:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | 20ltr Bag | 16.57 | 662.8 | Small Tools (Consumables) | 2019-06-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19216-001025 | 19216 | 2019-06-17 11:47 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | 20ltr Drum | 56.2 | 281 | Small Tools (Consumables) | 2019-06-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19283-001025 | 19283 | 2019-06-18 08:53 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-06-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19294-001025 | 19294 | 2019-06-18 11:13 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18962-001025 | 18962 | 2019-06-12 09:21 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 62.76 | 62.76 | Laboratory Equipment / Certification | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19208-001025 | 19208 | 2019-06-17 09:47 | Section 5 | Material | Aggregate | NULL | 180 | TON | 32.9 | 5922 | Aggregate | 2019-06-18 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18667-001025 | 18667 | 2019-06-06 12:36 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 61 | 61 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19317-001025 | 19317 | 2019-06-18 13:54 | Section 3 | Material | Not on List | Not on List | 7 | No | NULL | 0 | Builders Merchants (General) | 2019-06-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19317-001025 | 19317 | 2019-06-18 13:54 | Section 3 | Material | Not on List | Not on List | 50 | No | NULL | 0 | Builders Merchants (General) | 2019-06-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19317-001025 | 19317 | 2019-06-18 13:54 | Section 3 | Material | Not on List | Not on List | 1 | No | NULL | 0 | Builders Merchants (General) | 2019-06-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19317-001025 | 19317 | 2019-06-18 13:54 | Section 3 | Material | Not on List | Not on List | 2 | No | NULL | 0 | Builders Merchants (General) | 2019-06-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19317-001025 | 19317 | 2019-06-18 13:54 | Section 3 | Material | Not on List | Not on List | 1 | No | NULL | 0 | Builders Merchants (General) | 2019-06-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 200 | NULL | 14.36 | 2872 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 4 | NULL | 35.91 | 143.64 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 4 | NULL | 201.59 | 806.36 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 4 | NULL | 33.06 | 132.24 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 4 | NULL | 33.06 | 132.24 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 230 | NULL | 29.28 | 6734.4 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19341-001025 | 19341 | 2019-06-18 17:26 | Section 5 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Miscellaneous | 2019-06-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19083-001025 | 19083 | 2019-06-14 07:43 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19355-001025 | 19355 | 2019-06-19 06:25 | Core | Material | PPE, Small Tools and Consumables | Not on List | 36 | NULL | NULL | 0 | Surveying Consumables | 2019-06-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17070-001025 | 17070 | 2019-05-09 08:38 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 884.03 | 884.03 | Laboratory Equipment / Certification | 2019-05-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19134-001025 | 19134 | 2019-06-14 12:23 | Section 2 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Fixings and Fasteners | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19134-001025 | 19134 | 2019-06-14 12:23 | Section 2 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Fixings and Fasteners | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19134-001025 | 19134 | 2019-06-14 12:23 | Section 2 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Fixings and Fasteners | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19134-001025 | 19134 | 2019-06-14 12:23 | Section 2 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Fixings and Fasteners | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19134-001025 | 19134 | 2019-06-14 12:23 | Section 2 | Material | Not on List | Not on List | 2 | number | NULL | 0 | Plastic Drainage | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19360-001025 | 19360 | 2019-06-19 09:34 | Section 2 | Material | Not on List | Not on List | 1 | £ | 18289.75 | 18290 | Professional Services | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19362-001025 | 19362 | 2019-06-19 10:15 | Core | Material | Not on List | Not on List | 1 | NULL | 3000 | 3000 | Professional Services | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19374-001025 | 19374 | 2019-06-19 11:26 | Core | Material | Not on List | Not on List | 1 | NULL | 25200 | 25200 | Miscellaneous | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Stores - Closed | NULL | Yes - Approve | REQ - Buyers
MREQ-19334-001025 | 19334 | 2019-06-18 16:02 | Section 2 | Material | Not on List | Not on List | 145 | linear meters | NULL | 0 | Blocks and Bricks | 2019-06-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19310-001025 | 19310 | 2019-06-18 12:56 | Section 4 | Material | Not on List | Not on List | 4 | Each | 32.15 | 128.6 | Builders Merchants (General) | 2019-06-20 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | NULL | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19303-001025 | 19303 | 2019-06-18 12:27 | Section 4 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 2 | Roll | 122.72 | 245.44 | Geotextiles | 2019-06-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19228-001025 | 19228 | 2019-06-17 14:32 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1447.4 | 1447.4 | Miscellaneous | 2019-06-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18913-001025 | 18913 | 2019-06-11 14:38 | Section 4 | Material | Not on List | Not on List | 1 | each | 3216.78 | 3216.78 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19266-001025 | 19266 | 2019-06-18 08:26 | Section 4 | Material | NULL | NULL | 60 | Each | 5.17 | 310.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17451-001025 | 17451 | 2019-05-15 12:26 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 2392.25 | 2392.25 | Miscellaneous | 2019-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18084-001025 | 18084 | 2019-05-27 09:19 | Section 5 | Material | Not on List | NULL | 1 | EACH | 11768.8 | 11768.8 | Not Sure | 2019-08-02 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19323-001025 | 19323 | 2019-06-18 15:24 | Section 2 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 20 | Each | 24.32 | 486.4 | Concrete Accessories | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19323-001025 | 19323 | 2019-06-18 15:24 | Section 2 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 10 | Each | 10.08 | 100.8 | Concrete Accessories | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19323-001025 | 19323 | 2019-06-18 15:24 | Section 2 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 15 | Each | 6.82 | 102.3 | Concrete Accessories | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19226-001025 | 19226 | 2019-06-17 14:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4762.15 | 4762.15 | Miscellaneous | 2019-06-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19349-001025 | 19349 | 2019-06-19 06:24 | Section 5 | Material | Signage | NULL | 1 | SM | 580.92 | 580.92 | NULL | 2019-06-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6814-00751 | 6814 | 2018-09-20 16:43 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 12 | Ea | 7.96 | 95.52 | Miscellaneous | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19263-001025 | 19263 | 2019-06-18 08:06 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | No - Reject | Req - S5 Buyers
MREQ-18674-001025 | 18674 | 2019-06-06 12:41 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1122.28 | 1122.28 | Miscellaneous | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19020-001025 | 19020 | 2019-06-13 07:20 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 709.92 | 709.92 | Miscellaneous | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19395-001025 | 19395 | 2019-06-19 16:25 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19396-001025 | 19396 | 2019-06-19 16:23 | Core | Material | Not on List | Not on List | 15 | Bundle | 9 | 135 | Surveying Consumables | 2019-06-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19396-001025 | 19396 | 2019-06-19 16:23 | Core | Material | Not on List | Not on List | 15 | Bundle | 9 | 135 | Surveying Consumables | 2019-06-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19396-001025 | 19396 | 2019-06-19 16:23 | Core | Material | Not on List | Not on List | 10 | Bundle | 9 | 90 | Surveying Consumables | 2019-06-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19396-001025 | 19396 | 2019-06-19 16:23 | Core | Material | Not on List | Not on List | 10 | Bundle | 9 | 90 | Surveying Consumables | 2019-06-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19367-001025 | 19367 | 2019-06-19 11:00 | Section 4 | Material | Not on List | Not on List | 10 | EA | 69.14 | 691.4 | Rebar and Mesh | 2019-06-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6814-00751 | 6814 | 2018-09-20 16:43 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 12 | ea | 6.11 | 73.32 | Miscellaneous | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19399-001025 | 19399 | 2019-06-19 17:13 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19422-001025 | 19422 | 2019-06-20 09:35 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19151-001025 | 19151 | 2019-06-14 13:33 | Section 5 | Material | Not on List | Not on List | 50 | 7.1 | NULL | 0 | Surveying Consumables | 2019-06-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-19151-001025 | 19151 | 2019-06-14 13:33 | Section 5 | Material | Not on List | Not on List | 5 | 45 | NULL | 0 | Surveying Consumables | 2019-06-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-19151-001025 | 19151 | 2019-06-14 13:33 | Section 5 | Material | Not on List | Not on List | 1 | 65 | NULL | 0 | Surveying Consumables | 2019-06-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-19151-001025 | 19151 | 2019-06-14 13:33 | Section 5 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Surveying Consumables | 2019-06-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-19424-001025 | 19424 | 2019-06-20 10:33 | Section 3 | Material | Not on List | Not on List | 4000 | No | NULL | 0 | Builders Merchants (General) | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Rope Blue Polypropylene 6mm X 500m (approx)on Drum (746415) | 9 | Each | 25.13 | 226 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 7.5mtr/2 (765566) | 10 | Each | 5.77 | 58 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 10mtr/3 (765567) | 5 | Each | 12.4 | 62 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Scraper First Task 75mm Stripping Knife Ref 14003020 (746838) | 5 | Each | 5.55 | 28 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Filler Foam Expanding Hansil Contractor 750ml (546678) | 10 | Each | 3.17 | 32 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 200mm X 4.8mm Pack Of 100 (230062) | 15 | Each | 1.65 | 25 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 300mm X 4.8mm Pack Of 100 Spartan (230061) | 20 | Each | 1.94 | 39 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 370mm X 7.6mm Pack Of 100 Spartan (230065) | 15 | Each | 3.88 | 58 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Gun Skeleton Metal Suitable For 310/380/400ml Catridges (546684) | 5 | Each | 5.8 | 29 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19311-001025 | 19311 | 2019-06-18 11:57 | Core | Material | Not on List | Not on List | 2 | EA | 85 | 170 | Miscellaneous | 2019-06-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18834-001025 | 18834 | 2019-06-10 11:06 | Section 3 | Material | Not on List | Not on List | 5 | ea | 324 | 1620 | Plastic Drainage | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18834-001025 | 18834 | 2019-06-10 11:06 | Section 3 | Material | Not on List | Not on List | 4 | ea | 133.87 | 535.48 | Plastic Drainage | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18834-001025 | 18834 | 2019-06-10 11:06 | Section 3 | Material | NULL | Polypipe 400mm Seal (346394) | 10 | Each | 9.04 | 90.4 | Plastic Drainage | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18834-001025 | 18834 | 2019-06-10 11:06 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 8 | Each | 2.97 | 23.76 | Plastic Drainage | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18970-001025 | 18970 | 2019-06-12 11:03 | Section 3 | Material | Not on List | Not on List | 10 | No | 24.47 | 244.7 | Miscellaneous | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18970-001025 | 18970 | 2019-06-12 11:03 | Section 3 | Material | Not on List | Not on List | 30 | No | 37.81 | 1134.3 | Plastic Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19443-001025 | 19443 | 2019-06-20 15:15 | Section 3 | Material | Not on List | Not on List | 4 | No | NULL | 0 | Builders Merchants (General) | 2019-06-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19443-001025 | 19443 | 2019-06-20 15:15 | Section 3 | Material | Not on List | Not on List | 6 | No | NULL | 0 | Builders Merchants (General) | 2019-06-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19443-001025 | 19443 | 2019-06-20 15:15 | Section 3 | Material | Not on List | Not on List | 2 | No | NULL | 0 | Builders Merchants (General) | 2019-06-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19211-001025 | 19211 | 2019-06-17 10:35 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 6 | Each | 33.55 | 201.3 | Blocks and Bricks | 2019-06-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19452-001025 | 19452 | 2019-06-20 16:45 | Core | Material | Not on List | Not on List | 3 | NULL | 90 | 270 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19454-001025 | 19454 | 2019-06-20 16:55 | Core | Material | Not on List | Not on List | 3 | £ | 90 | 270 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 48 | Each | 5.43 | 260.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 48 | Each | 5.43 | 260.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 48 | Each | 3.03 | 145.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 32 | Each | 5.43 | 173.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 32 | Each | 10.35 | 331.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 32 | Each | 10.35 | 331.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 64 | Each | 6 | 384 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 32 | Each | 5.43 | 173.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 16 | Each | 11.95 | 191.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 32 | Each | 5.43 | 173.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 16 | Each | 11.95 | 191.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 10 | Each | 85.23 | 852.3 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 78.9 | 78.9 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 3 | Each | 63.93 | 191.79 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16949-001025 | 16949 | 2019-05-07 14:16 | Core | Material | Not on List | Not on List | 1 | Each | 2850 | 2850 | Laboratory Equipment / Certification | 2019-05-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17007-001025 | 17007 | 2019-05-08 09:42 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 938.75 | 939 | PPE | 2019-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-16913-001025 | 16913 | 2019-05-07 07:36 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain Bend 15deg (877998) | 5 | Each | 8.25 | 41.25 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16913-001025 | 16913 | 2019-05-07 07:36 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain Bend 30deg (877999) | 5 | Each | 8.25 | 41.25 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16913-001025 | 16913 | 2019-05-07 07:36 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain Bend 45deg (878000) | 5 | Each | 8.25 | 41.25 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16811-001025 | 16811 | 2019-05-02 11:23 | Core | Material | Not on List | Not on List | 1 | ea | 3032 | 3032 | Training | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Not on List | 40 | NULL | 11.51 | 460.4 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 52 | Each | 1.98 | 102.96 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6384-00680 | 6384 | 2018-09-12 09:14 | Section 3 | Material | Not on List | Not on List | 1 | EA | 660.24 | 660.24 | Small Tools (Consumables) | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 52 | Each | 0.91 | 47.32 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 15 | Each | 24.99 | 374.85 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 22 | Each | 3.65 | 80.3 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 22 | Each | 2 | 44 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 10 | Each | 37.6 | 376 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 18 | Each | 7.06 | 127.08 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 18 | Each | 2.97 | 53.46 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16927-001025 | 16927 | 2019-05-07 08:14 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 15 | Each | 48.92 | 733.8 | Concrete Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16927-001025 | 16927 | 2019-05-07 08:14 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 70.61 | 1059.15 | Concrete Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16927-001025 | 16927 | 2019-05-07 08:14 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 7 | Each | 52.95 | 370.65 | Concrete Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6384-00680 | 6384 | 2018-09-12 09:14 | Section 3 | Material | Not on List | Not on List | 1 | EA | 706.72 | 706.72 | Janitorial | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16927-001025 | 16927 | 2019-05-07 08:14 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16927-001025 | 16927 | 2019-05-07 08:14 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 5 | Each | 36.94 | 184.7 | Concrete Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16179-001025 | 16179 | 2019-04-18 14:44 | Core | Material | Not on List | Not on List | 1 | No. | 19.99 | 20 | Surveying Consumables | 2019-04-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | 113 - Survey Equipment Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17015-001025 | 17015 | 2019-05-08 11:21 | Core | Material | Not on List | Not on List | 1 | number | 1030 | 1030 | Office Supplies | 2019-05-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-17018-001025 | 17018 | 2019-05-08 11:13 | Core | Material | Not on List | Not on List | 1 | 1 | 799.22 | 799 | Professional Services | 2019-05-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-15663-001025 | 15663 | 2019-04-11 09:44 | Section 4 | Material | Not on List | Not on List | 5000 | Each | 1 | 5000 | Miscellaneous | 2019-04-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15855-001025 | 15855 | 2019-04-15 12:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 700 | Each | 0.47 | 329 | Small Tools (Consumables) | 2019-04-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17023-001025 | 17023 | 2019-05-08 13:06 | Section 6 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Fixings and Fasteners | 2019-05-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 301 - Fencing, Gates & Stiles | Commercial Approval | Yes - Approve | NULL | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 45deg Junction (878038) | 6 | Each | 39.7 | 238.2 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 13 | Each | 39.7 | 516.1 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6431-00700 | 6431 | 2018-09-12 16:22 | Section 3 | Material | Plastic Drainage | Not on List | 15 | No. | 48.86 | 732.9 | Plastic Drainage | 2018-09-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 300mm x 150mm Ridgidrain 90deg Junction (878089) | 3 | Each | 44.41 | 133.23 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 70 | Each | 3.65 | 255.5 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 30 | Each | 1.98 | 59.4 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 10 | Each | 7.06 | 70.6 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 400mm Coupler (346401) | 25 | Each | 17.45 | 436.25 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 60 | Each | 0.91 | 54.6 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 150 | Each | 2 | 300 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 20 | Each | 2.97 | 59.4 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 400mm Seal (346394) | 50 | Each | 9.04 | 452 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | Concrete Drainage | Not on List | 70 | Each | NULL | 0 | Concrete Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6344-00672 | 6344 | 2018-09-11 14:32 | Section 3 | Material | Signage | Not on List | 100 | ea | 5.98 | 598 | Miscellaneous | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe Lubricant 2.5kg (574788) | 6 | Each | 19.72 | 118.32 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | Plastic Drainage | Not on List | 1 | Each | 1050 | 1050 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17025-001025 | 17025 | 2019-05-08 13:49 | Core | Material | Not on List | Not on List | 1 | £ | 384.3 | 384 | Office Supplies | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-17027-001025 | 17027 | 2019-05-08 13:52 | Section 3 | Material | Aggregate | Bedding Sand | 200 | Tonnes | 11.5 | 2300 | Aggregate | 2019-05-09 | Gate F - 1339645 - BN11 Near Mere Way | SC3A - Roadworks | 1103 - Linear Drainage Channel Systems | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-17028-001025 | 17028 | 2019-05-08 14:14 | Section 3 | Material | Not on List | Not on List | 1 | No. | 657.86 | 658 | Surveying Consumables | 2019-05-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 701 - Sub-base | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17029-001025 | 17029 | 2019-05-08 14:11 | Section 5 | Material | Bricks/Blocks | Not on List | 120 | NULL | NULL | 0 | Blocks and Bricks | 2019-05-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE24 - Histon Jct East Bridge | 2401 - Brickwork, Blockwork and Stonework | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-17033-001025 | 17033 | 2019-05-08 14:36 | Section 3 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1103 - Linear Drainage Channel Systems | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 1200 | Each | 1.5 | 1800 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 80 | Each | 3.03 | 242 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 105 | Each | 3.52 | 370 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-6401-00692 | 6401 | 2018-09-12 12:41 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 140 | 140 | Small Tools (Consumables) | 2018-09-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 420 | Each | 4.59 | 1928 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 4 | Each | 10.08 | 40 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 4 | Each | 10.08 | 40 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 3 | Each | 7.68 | 23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 3 | Each | 7.68 | 23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 7 | Each | 11.94 | 84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 5 | Each | 11.94 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17036-001025 | 17036 | 2019-05-08 14:22 | Section 5 | Material | Bricks/Blocks | Not on List | 120 | NULL | NULL | 0 | Blocks and Bricks | 2019-05-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE24 - Histon Jct East Bridge | 2401 - Brickwork, Blockwork and Stonework | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-17036-001025 | 17036 | 2019-05-08 14:22 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 2 | Each | 32.74 | 65 | Builders Merchants (General) | 2019-05-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE24 - Histon Jct East Bridge | 2401 - Brickwork, Blockwork and Stonework | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-17036-001025 | 17036 | 2019-05-08 14:22 | Section 5 | Material | Bagged | Post Mix 25kg (348099) | 40 | Each | 3.45 | 138 | Builders Merchants (General) | 2019-05-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE24 - Histon Jct East Bridge | 2401 - Brickwork, Blockwork and Stonework | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-6316-00665 | 6316 | 2018-09-11 09:52 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 29.2 | 58.4 | Timber Products | 2018-09-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17039 | 17039 | 2019-05-08 15:08 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Surveying Consumables | 2019-05-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-17039 | 17039 | 2019-05-08 15:08 | Core | Material | Not on List | Not on List | 1 | number | 491.27 | 491 | Surveying Consumables | 2019-05-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-16954-001025 | 16954 | 2019-05-07 14:36 | Section 4 | Material | Not on List | Not on List | 3 | Boxes (x 150) | 12 | 36 | Surveying Consumables | 2019-05-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17596-001025 | 17596 | 2019-05-17 10:28 | Section 2 | Material | Concrete Drainage | Not on List | 200 | NULL | NULL | 0 | Concrete Drainage | 2019-05-21 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17596-001025 | 17596 | 2019-05-17 10:28 | Section 2 | Material | NULL | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-05-21 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6316-00665 | 6316 | 2018-09-11 09:52 | Section 3 | Material | Not on List | Not on List | 12 | NULL | 11.29 | 135.48 | Timber Products | 2018-09-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17596-001025 | 17596 | 2019-05-17 10:28 | Section 2 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 5 | Each | 175 | 875 | Plastic Drainage | 2019-05-21 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17611-001025 | 17611 | 2019-05-17 12:16 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Surveying Consumables | 2019-05-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17393-001025 | 17393 | 2019-05-14 15:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 479.95 | 479.95 | Small Tools (Consumables) | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17394-001025 | 17394 | 2019-05-14 16:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Pack of 12 | 6.29 | 905.76 | Small Tools (Consumables) | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17619-001025 | 17619 | 2019-05-17 13:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 22 | 220 | PPE | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17602-001025 | 17602 | 2019-05-17 10:48 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Pack | 18 | 72 | Laboratory Equipment / Certification | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17443-001025 | 17443 | 2019-05-15 11:02 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2000 | Each | 0.51 | 1020 | Laboratory Equipment / Certification | 2019-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17365-001025 | 17365 | 2019-05-14 11:13 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 858 | 858 | Laboratory Equipment / Certification | 2019-05-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6316-00665 | 6316 | 2018-09-11 09:52 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 41.6 | 83.2 | Builders Merchants (General) | 2018-09-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17513-001025 | 17513 | 2019-05-16 09:09 | Section 3 | Material | Not on List | Not on List | 75 | Mtr | 0.89 | 66.75 | Builders Merchants (General) | 2019-05-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17513-001025 | 17513 | 2019-05-16 09:09 | Section 3 | Material | Not on List | Not on List | 5 | No | 12.88 | 64.4 | Builders Merchants (General) | 2019-05-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17513-001025 | 17513 | 2019-05-16 09:09 | Section 3 | Material | Not on List | Not on List | 200 | No | 3.56 | 712 | Builders Merchants (General) | 2019-05-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17452-001025 | 17452 | 2019-05-15 12:28 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Tape Gaffa Waterproof Cloth Grey 50mm X 50 Mtr Ref 3160 (964670) | 3 | Boxes | 1.91 | 6 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 24 | number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Keys Hexagonal/Allen Metric Set Of 10 1.5mm To 10mm (662405) | 3 | sets | 5.45 | 16 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Box | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Helmet Safety Jsp Evolite Skyworker White (272558) | 2 | Boxes | 29.82 | 60 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6485-00724 | 6485 | 2018-09-13 14:47 | Section 3 | Material | Plastic Drainage | Not on List | 10 | No | NULL | 0 | Builders Merchants (General) | 2018-09-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 12 | Number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 12 | Number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 12 | Number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 12 | Number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 12 | Number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17542-001025 | 17542 | 2019-05-16 10:07 | Core | Material | Not on List | Not on List | 16 | ea | 81.04 | 1296.64 | Janitorial | 2019-05-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17542-001025 | 17542 | 2019-05-16 10:07 | Core | Material | Not on List | Not on List | 10 | ea | 33.98 | 339.8 | Janitorial | 2019-05-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17415-001025 | 17415 | 2019-05-14 17:36 | Core | Material | Not on List | Not on List | 1 | ea | 1633.18 | 1633.18 | PPE | 2019-05-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17415-001025 | 17415 | 2019-05-14 17:36 | Core | Material | Not on List | Not on List | 1 | ea | 470.25 | 470.25 | Small Tools (Consumables) | 2019-05-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17415-001025 | 17415 | 2019-05-14 17:36 | Core | Material | Not on List | Not on List | 1 | ea | 183.24 | 183.24 | Small Tools (Consumables) | 2019-05-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17716-001025 | 17716 | 2019-05-20 09:14 | Section 3 | Material | Not on List | Not on List | 15 | Sheets | 10.44 | 156.6 | Builders Merchants (General) | 2019-05-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17591-001025 | 17591 | 2019-05-17 10:01 | Section 3 | Material | NULL | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 42 | Each | 74.3 | 3120.6 | Ductile Drainage | 2019-05-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17764-001025 | 17764 | 2019-05-20 16:02 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17769-001025 | 17769 | 2019-05-20 16:19 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-22 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17770-001025 | 17770 | 2019-05-20 16:18 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17771-001025 | 17771 | 2019-05-20 16:22 | Section 5 | Material | PPE, Small Tools and Consumables | Spill Kit Maintenance In Two Wheel Bin Lubetech 120 Litres (534202) | 6 | Each | 195.66 | 1174 | Miscellaneous | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15487-001025 | 15487 | 2019-04-08 17:34 | Section 4 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17531-001025 | 17531 | 2019-05-16 12:19 | Section 4 | Material | NULL | NULL | 150 | Each | 7.5 | 1125 | Surveying Consumables | 2019-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17652-001025 | 17652 | 2019-05-17 16:08 | Section 3 | Material | Concrete Drainage | Not on List | 1 | ea | 677.13 | 677.13 | Ductile Drainage | 2019-05-22 | Gate C - 1339702 - BN06 (East Coast Railway) Via Logistics Yard Access | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17761-001025 | 17761 | 2019-05-20 15:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 6 | EA | 3.05 | 18.3 | PPE | 2019-05-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17801-001025 | 17801 | 2019-05-21 10:28 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Builders Merchants (General) | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17801-001025 | 17801 | 2019-05-21 10:28 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17801-001025 | 17801 | 2019-05-21 10:28 | Section 2 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17802-001025 | 17802 | 2019-05-21 10:56 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 3645 | 3645 | Surveying Consumables | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-17571-001025 | 17571 | 2019-05-16 17:44 | Section 4 | Material | Not on List | Not on List | 20 | Each | 4.97 | 99.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-17767-001025 | 17767 | 2019-05-20 16:11 | Section 4 | Material | Not on List | Not on List | 1 | Each | 245 | 245 | Miscellaneous | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17516-001025 | 17516 | 2019-05-16 09:28 | Section 4 | Material | Not on List | Not on List | 1 | Permit | 1959 | 1959 | Miscellaneous | 2019-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26484-001025 | 26484 | 2019-11-12 13:25 | Section 4 | Material | NULL | Not on List | 6 | Each | 15 | 90 | Electrical | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26484-001025 | 26484 | 2019-11-12 13:25 | Section 4 | Material | NULL | Not on List | 1 | Each | 16 | 16 | Electrical | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26549-001025 | 26549 | 2019-11-13 11:25 | Section 2 | Material | Not on List | Not on List | 2 | NULL | 1305 | 2610 | Concrete Accessories | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-26549-001025 | 26549 | 2019-11-13 11:25 | Section 2 | Material | Not on List | Not on List | 2 | NULL | 1305 | 2610 | Concrete Accessories | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-26549-001025 | 26549 | 2019-11-13 11:25 | Section 2 | Material | Not on List | Not on List | 2 | NULL | 1612.5 | 3225 | Concrete Accessories | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-26549-001025 | 26549 | 2019-11-13 11:25 | Section 2 | Material | Not on List | Not on List | 2 | NULL | 1612.5 | 3225 | Concrete Accessories | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-26577-001025 | 26577 | 2019-11-14 08:45 | Section 2 | Material | Not on List | Not on List | 1 | each | 6000 | 6000 | Professional Services | 2019-11-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26579-001025 | 26579 | 2019-11-14 09:12 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26188-001025 | 26188 | 2019-11-06 07:41 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1016.66 | Each | 1 | 1016.66 | PPE | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26189-001025 | 26189 | 2019-11-06 07:44 | Core | Material | PPE, Small Tools and Consumables | Not on List | 585.1 | Each | 1 | 585.1 | Janitorial | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26206-001025 | 26206 | 2019-11-06 07:50 | Core | Material | PPE, Small Tools and Consumables | Not on List | 726.88 | Each | 1 | 726.88 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7246-001021 | 7246 | 2018-10-01 17:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3427.35 | Each | 1 | 3427.35 | Small Tools (Consumables) | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26111-001025 | 26111 | 2019-11-04 14:57 | Core | Material | NULL | NULL | 1 | EA | 151.91 | 151.91 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26095-001025 | 26095 | 2019-11-04 10:56 | Core | Material | Not on List | NULL | 1 | EA | 239.52 | 239.52 | Miscellaneous | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26158-001025 | 26158 | 2019-11-05 14:48 | Core | Material | NULL | NULL | 1 | Each | 2713 | 2713 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26498-001025 | 26498 | 2019-11-12 15:47 | Core | Material | Not on List | NULL | 1 | SM | 285 | 285 | Miscellaneous | 2019-11-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 1900 | Each | 21.01 | 39919 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 23 | Each | 151.94 | 3494.62 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 20 | Each | 201.59 | 4031.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 10 | Each | 4.9 | 49 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 1 | Each | 34.84 | 34.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7309-001022 | 7309 | 2018-10-02 17:26 | Section 4 | Material | Waste Management | Construction Waste - Skip 12 cubic yard | 1 | Each | 195 | 195 | Not Sure | 2018-10-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 32 | Each | 6 | 192 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26500-001025 | 26500 | 2019-11-12 16:31 | Core | Material | NULL | NULL | 2 | Each | 55 | 110 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26420-001025 | 26420 | 2019-11-11 12:04 | Section 5 | Material | PPE, Small Tools and Consumables | NULL | 1 | EA | 282.81 | 282.81 | Miscellaneous | 2019-11-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26590-001025 | 26590 | 2019-11-14 11:56 | Section 3 | Material | Aggregate | Type 1 | 114 | Tonnes | 21.65 | 2468 | Aggregate | 2019-11-15 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26578-001025 | 26578 | 2019-11-13 12:33 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4605.14 | each | 1 | 4605.14 | PPE | 2019-11-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26544-001025 | 26544 | 2019-11-13 14:57 | Section 5 | Material | Not on List | NULL | 40 | EA | 24.5 | 980 | Miscellaneous | 2019-11-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26591-001025 | 26591 | 2019-11-14 12:24 | Core | Material | NULL | NULL | 1 | Each | 920 | 920 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26580-001025 | 26580 | 2019-11-14 09:10 | Section 5 | Material | Not on List | NULL | 1 | SM | 124.5 | 124.5 | Surveying Consumables | 2019-11-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26585-001025 | 26585 | 2019-11-14 09:48 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | each | 4605.14 | 4605.14 | PPE | 2019-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26603-001025 | 26603 | 2019-11-14 14:43 | Section 2 | Material | Twinwall | Not on List | 2 | NULL | NULL | 0 | Plastic Drainage | 2019-11-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26616-001025 | 26616 | 2019-11-14 16:29 | Section 6 | Material | Not on List | Not on List | 110 | Meters | NULL | 0 | Builders Merchants (General) | 2019-11-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26545-001025 | 26545 | 2019-11-13 15:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 2165 | 4330 | Concrete Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26545-001025 | 26545 | 2019-11-13 15:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 1840 | 3680 | Concrete Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26545-001025 | 26545 | 2019-11-13 15:05 | Section 4 | Material | Not on List | Not on List | 3 | Each | 2490 | 7470 | Concrete Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26545-001025 | 26545 | 2019-11-13 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2555 | 2555 | Concrete Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26545-001025 | 26545 | 2019-11-13 15:05 | Section 4 | Material | NULL | Not on List | 1 | Each | 655 | 655 | Concrete Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26630-001025 | 26630 | 2019-11-15 08:42 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 12.87 | 64 | Small Tools (Consumables) | 2019-11-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | NULL | Yes - Approve | Req - S5 Buyers
MREQ-26630-001025 | 26630 | 2019-11-15 08:42 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | ea | 2.05 | 41 | Small Tools (Consumables) | 2019-11-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | NULL | Yes - Approve | Req - S5 Buyers
MREQ-26641-001025 | 26641 | 2019-11-15 11:29 | Section 5 | Material | Timber | NULL | 1 | SM | 3673.36 | 3673.36 | Timber Products | 2019-11-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26641-001025 | 26641 | 2019-11-15 11:29 | Section 5 | Material | Not on List | NULL | 300 | EA | 0.23 | 69 | Miscellaneous | 2019-11-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26649-001025 | 26649 | 2019-11-15 14:57 | Section 5 | Material | Not on List | Not on List | 1 | NULL | 1365 | 1365 | Miscellaneous | 2019-11-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7298-001022 | 7298 | 2018-10-02 16:05 | Section 4 | Material | Not on List | Not on List | 3000 | Each | 1 | 3000 | Waste (General) | 2018-10-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26655-001025 | 26655 | 2019-11-15 16:27 | Core | Material | Not on List | Not on List | 1 | NULL | 1650 | 1650 | Miscellaneous | 2019-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26688-001025 | 26688 | 2019-11-18 14:21 | Section 6 | Material | Not on List | Not on List | 1 | No. | 8310 | 8310 | Miscellaneous | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26689-001025 | 26689 | 2019-11-18 14:10 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 7123 | 7123 | Miscellaneous | 2019-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | Not on List | Not on List | 2 | Each | 395.57 | 791.14 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | Not on List | Not on List | 2 | Each | 272.12 | 544.24 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | Not on List | Not on List | 2 | Each | 780.31 | 1560.62 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | Not on List | Not on List | 2 | Each | 162.27 | 324.54 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | NULL | Not on List | 1 | Each | 55 | 55 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26715-001025 | 26715 | 2019-11-19 08:13 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | ea | 89.25 | 179 | Concrete Accessories | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26730-001025 | 26730 | 2019-11-19 10:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 50.5 | 51 | Surveying Consumables | 2019-11-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26297-001025 | 26297 | 2019-11-07 15:54 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26487 | 26487 | 2019-10-08 15:08 | Core | Material | Not on List | Not on List | 1 | ea | 179 | 179 | Training | 2019-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-26276-001025 | 26276 | 2019-11-07 10:34 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26653-001025 | 26653 | 2019-11-15 15:18 | Section 5 | Material | Not on List | Not on List | 6 | ea | 53.79 | 322.74 | Builders Merchants (General) | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26653-001025 | 26653 | 2019-11-15 15:18 | Section 5 | Material | Not on List | Not on List | 14 | ea | 84.98 | 1189.72 | Builders Merchants (General) | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26653-001025 | 26653 | 2019-11-15 15:18 | Section 5 | Material | Not on List | Not on List | 5 | ea | 58.54 | 292.7 | Builders Merchants (General) | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26653-001025 | 26653 | 2019-11-15 15:18 | Section 5 | Material | Not on List | Not on List | 2 | ea | 30.93 | 61.86 | Builders Merchants (General) | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26653-001025 | 26653 | 2019-11-15 15:18 | Section 5 | Material | Not on List | Not on List | 1 | ea | 16.96 | 16.96 | Builders Merchants (General) | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26738-001025 | 26738 | 2019-11-19 12:22 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 250 | No | NULL | 0 | Surveying Consumables | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26351-001025 | 26351 | 2019-11-08 13:17 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7234-001021 | 7234 | 2018-10-01 15:11 | Section 4 | Material | Not on List | Not on List | 40 | number | 23.15 | 926 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26742-001025 | 26742 | 2019-11-19 12:57 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26744-001025 | 26744 | 2019-11-19 13:08 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26749-001025 | 26749 | 2019-11-19 13:44 | Core | Material | Not on List | Not on List | 9 | number | 295 | 2655 | Surveying Consumables | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26749-001025 | 26749 | 2019-11-19 13:44 | Core | Material | Not on List | Not on List | 10 | number | 700 | 7000 | Surveying Consumables | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26721-001025 | 26721 | 2019-11-19 08:00 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.98 | 196 | Surveying Consumables | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26721-001025 | 26721 | 2019-11-19 08:00 | Section 4 | Material | Not on List | Not on List | 300 | Each | 0.5 | 150 | Surveying Consumables | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26753-001025 | 26753 | 2019-11-19 15:52 | Core | Material | Not on List | Not on List | 1 | no | 20000 | 20000 | Office Supplies | 2019-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | Pack | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 35 | linier m | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 35 | linier m | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7234-001021 | 7234 | 2018-10-01 15:11 | Section 4 | Material | Not on List | Not on List | 40 | number | 9.6 | 384 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 40 | no | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | PAck | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | Pack | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | Pack | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | Pack | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | Pack | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25645-001025 | 25645 | 2019-10-23 16:34 | Core | Material | NULL | NULL | 1 | Each | 50 | 50 | Miscellaneous | 2019-11-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25645-001025 | 25645 | 2019-10-23 16:34 | Core | Material | NULL | NULL | 1 | Each | 753.36 | 753.36 | Miscellaneous | 2019-11-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25645-001025 | 25645 | 2019-10-23 16:34 | Core | Material | NULL | NULL | 1 | Each | 720 | 720 | Miscellaneous | 2019-11-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7234-001021 | 7234 | 2018-10-01 15:11 | Section 4 | Material | Not on List | Not on List | 40 | number | 5.9 | 236 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26783-001025 | 26783 | 2019-11-20 07:47 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26791-001025 | 26791 | 2019-11-20 08:50 | Section 5 | Material | Not on List | Not on List | 5 | each | 450 | 2250 | Miscellaneous | 2019-11-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26793-001025 | 26793 | 2019-11-20 09:33 | Core | Material | Not on List | Not on List | 1 | ea | 4668 | 4668 | Office Supplies | 2019-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26794-001025 | 26794 | 2019-11-20 09:26 | Section 6 | Material | Not on List | Not on List | 1 | No | NULL | 0 | Surveying Consumables | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26795-001025 | 26795 | 2019-11-20 09:05 | Core | Material | Not on List | Not on List | 1 | NULL | 874.07 | 874 | Miscellaneous | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26800-001025 | 26800 | 2019-11-20 10:56 | Core | Material | Not on List | Not on List | 1 | NULL | 850 | 850 | Miscellaneous | 2019-11-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26684-001025 | 26684 | 2019-11-18 13:45 | Core | Material | PPE, Small Tools and Consumables | Not on List | 879.72 | each | 1 | 879.72 | Small Tools (Consumables) | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26801-001025 | 26801 | 2019-11-20 10:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 446.26 | 446 | Janitorial | 2019-11-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7234-001021 | 7234 | 2018-10-01 15:11 | Section 4 | Material | Not on List | Not on List | 40 | number | 13.9 | 556 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26801-001025 | 26801 | 2019-11-20 10:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 105.78 | 106 | Small Tools (Consumables) | 2019-11-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26801-001025 | 26801 | 2019-11-20 10:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 253.88 | 254 | PPE | 2019-11-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26576-001025 | 26576 | 2019-11-14 08:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | each | 22.5 | 45 | Small Tools (Consumables) | 2019-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26576-001025 | 26576 | 2019-11-14 08:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | each | 66 | 132 | Small Tools (Consumables) | 2019-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26576-001025 | 26576 | 2019-11-14 08:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | each | 78.4 | 78.4 | Small Tools (Consumables) | 2019-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26565-001025 | 26565 | 2019-11-13 16:23 | Section 4 | Material | Waste Management | Not on List | 2 | Each | 1965 | 3930 | Miscellaneous | 2019-11-15 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26534-001025 | 26534 | 2019-11-13 09:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 136.8 | 136.8 | Miscellaneous | 2019-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26535-001025 | 26535 | 2019-11-13 10:12 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 3677.71 | 3677.71 | Miscellaneous | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26573-001025 | 26573 | 2019-11-13 18:35 | Section 4 | Material | Not on List | Not on List | 24 | Each | 12.8 | 307.2 | Miscellaneous | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2702 - Works by the Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7234-001021 | 7234 | 2018-10-01 15:11 | Section 4 | Material | Not on List | Not on List | 40 | number | 6.05 | 242 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26396-001025 | 26396 | 2019-11-11 07:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 165.35 | 165.35 | Miscellaneous | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26771-001025 | 26771 | 2019-11-19 17:48 | Section 4 | Material | Not on List | Not on List | 1 | Each | 555 | 555 | Miscellaneous | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26572-001025 | 26572 | 2019-11-14 07:47 | Section 4 | Material | Not on List | Not on List | 1 | Each | 336 | 336 | Miscellaneous | 2019-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26491-001025 | 26491 | 2019-11-12 14:34 | Section 4 | Material | Not on List | Not on List | 40 | Bag | 31.63 | 1265.2 | Concrete Accessories | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26491-001025 | 26491 | 2019-11-12 14:34 | Section 4 | Material | Not on List | Not on List | 150 | KG | 3.1 | 465 | Rebar and Mesh | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26718-001025 | 26718 | 2019-11-19 08:18 | Section 4 | Material | Not on List | Not on List | 1 | Each | 682.06 | 682.06 | Miscellaneous | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26638-001025 | 26638 | 2019-11-15 10:19 | Core | Material | Not on List | Not on List | 1 | NULL | 1700 | 1700 | Miscellaneous | 2019-11-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7296-001022 | 7296 | 2018-10-02 15:48 | Section 4 | Material | Not on List | Not on List | 2 | Polybottles (5 litre each) | 33.88 | 67.76 | Miscellaneous | 2018-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1705 - Repairs to Existing Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26827-001025 | 26827 | 2019-11-21 07:04 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26830-001025 | 26830 | 2019-11-21 07:33 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7300-001022 | 7300 | 2018-10-02 16:33 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 808.5 | 808.5 | Small Tools (Consumables) | 2018-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26593-001025 | 26593 | 2019-11-14 12:24 | Section 4 | Material | Not on List | Not on List | 200 | Each | 9.92 | 1984 | Miscellaneous | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26834-001025 | 26834 | 2019-11-21 08:13 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26836-001025 | 26836 | 2019-11-21 08:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26728-001025 | 26728 | 2019-11-19 09:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 3320 | 3320 | Concrete Accessories | 2019-11-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN06 - ECML Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26837-001025 | 26837 | 2019-11-21 09:01 | Section 5 | Material | Not on List | Not on List | 10 | bags | NULL | 0 | Builders Merchants (General) | 2019-11-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26654-001025 | 26654 | 2019-11-15 10:38 | Section 5 | Material | NULL | NULL | NULL | ea | NULL | 0 | NULL | 2019-11-22 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26282-001025 | 26282 | 2019-11-07 13:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | each | 2.97 | 332.64 | Builders Merchants (General) | 2019-11-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 12 | Each | 114 | 1368 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 18000 | M2 | 7.5 | 135000 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | NULL | Not on List | 9 | Packs | 54.4 | 489.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | NULL | Not on List | 3 | Packs | 54.4 | 163.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | NULL | Not on List | 3 | No | 10.35 | 31.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | NULL | Not on List | 3 | No | 10.35 | 31.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 15 | EA | 209.35 | 3140.25 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 5 | Each | 149.45 | 747.25 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 10 | Each | 24.44 | 244.4 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 35 | Each | 116.62 | 4081.7 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 45 | Each | 17.48 | 786.6 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 90 | Each | 34.82 | 3133.8 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 112 | Each | 6.54 | 732.48 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 75 | Each | 23.14 | 1735.5 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 91 | Each | 3.38 | 307.58 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 86 | Each | 10.5 | 903 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 106 | Each | 1.84 | 195.04 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 20 | EA | 67.9 | 1358 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 19.72 | 394.4 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | Each | 15.71 | 942.6 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | Each | 4.9 | 294 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | Each | 10.5 | 630 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 30 | Each | 14.4 | 432 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 30 | Each | 39.7 | 1191 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 15 | Each | 44.41 | 666.15 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 20 | EA | 50.92 | 1018.4 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 10 | Each | 84.41 | 844.1 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 15.19 | 303.8 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 110 | Each | 10.04 | 1104.4 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 254 | Each | 2.75 | 698.5 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 242 | Each | 1.86 | 450.12 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 477 | Each | 0.85 | 405.45 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10682-001025 | 10682 | 2019-01-08 09:12 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | no | 877.51 | 877.51 | Miscellaneous | 2019-01-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10699-001025 | 10699 | 2019-01-08 11:45 | Section 3 | Material | Concrete Drainage | Not on List | 9 | No. | 2339.56 | 21056.04 | Concrete Drainage | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10690-001025 | 10690 | 2019-01-08 10:23 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-01-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 20 | EA | 43.16 | 863.2 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10747-001025 | 10747 | 2019-01-09 10:32 | Section 4 | Material | Twinwall | Not on List | 20 | no | NULL | 0 | Plastic Drainage | 2019-01-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10747-001025 | 10747 | 2019-01-09 10:32 | Section 4 | Material | Twinwall | Not on List | 20 | no | NULL | 0 | Plastic Drainage | 2019-01-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10747-001025 | 10747 | 2019-01-09 10:32 | Section 4 | Material | Twinwall | Not on List | 10 | no | NULL | 0 | Plastic Drainage | 2019-01-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10747-001025 | 10747 | 2019-01-09 10:32 | Section 4 | Material | Saint Gobain Castings | Not on List | 15 | no | NULL | 0 | Ductile Drainage | 2019-01-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1502 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10750-001025 | 10750 | 2019-01-09 10:47 | Section 3 | Material | Not on List | Not on List | 5 | Bags | NULL | 0 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10750-001025 | 10750 | 2019-01-09 10:47 | Section 3 | Material | Not on List | Not on List | 120 | kg | NULL | 0 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 35 | Each | 149.45 | 5230.75 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 41 | Each | 24.44 | 1002.04 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 30 | Each | 23.14 | 694.2 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 34 | Each | 3.38 | 114.92 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 55 | Each | 10.5 | 577.5 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 63 | Each | 1.84 | 115.92 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 5 | Each | 19.72 | 98.6 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | Each | 15.71 | 785.5 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | Each | 4.9 | 245 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | Each | 10.5 | 525 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 22 | Each | 14.4 | 316.8 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 15 | Each | 39.7 | 595.5 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 18 | Each | 258.72 | 4656.96 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 82 | Each | 15.19 | 1245.58 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 36 | Each | 10.04 | 361.44 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 98 | Each | 1.86 | 182.28 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 345 | Each | 0.85 | 293.25 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10759-001025 | 10759 | 2019-01-09 12:47 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 145 | 145 | Surveying Consumables | 2019-01-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Boot Wellington Safety Toe And Midsole Black S5 Tuf (165022) | 3 | Each | 10.95 | 33 | PPE | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Scraper Boot Galvanised C/W Brushes (746900) | 10 | Each | 10.19 | 102 | Miscellaneous | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 0.39 | 4 | Miscellaneous | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10761-001025 | 10761 | 2019-01-09 13:06 | Section 3 | Material | Not on List | Not on List | 12 | No | NULL | 0 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 690 | 690 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 555 | 555 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 420 | 420 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 60 | Number | NULL | 0 | Concrete Accessories | 2019-01-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 2302 - Sealing of gaps | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 200 | Number | NULL | 0 | Concrete Accessories | 2019-01-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10746-001025 | 10746 | 2019-01-09 10:43 | Section 4 | Material | Not on List | Not on List | 13.209 | tonne | 538 | 7106.44 | Rebar and Mesh | 2019-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10687-001025 | 10687 | 2019-01-08 10:08 | Section 4 | Material | Not on List | Not on List | 32 | no | 6.26 | 200.32 | Concrete Accessories | 2019-01-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10771-001025 | 10771 | 2019-01-09 14:56 | Section 4 | Material | Timber | Not on List | 500 | NULL | NULL | 0 | Timber Products | 2019-01-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1703 - Formwork | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 105 | Each | 23.14 | 2430 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 53 | Each | 3.38 | 179 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 106 | Each | 1.86 | 197 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 36 | Each | NULL | 0 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Twinwall | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 8 | Each | 39.7 | 318 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5468-00301 | 5468 | 2018-08-21 17:45 | Section 4 | Material | Not on List | Not on List | 1 | Each | 404.45 | 404.45 | Damage Charges | 2018-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 3 | Each | NULL | 0 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Twinwall | Polypipe 150mm x 25m Ridgiflex (877588) | 4 | Each | 145 | 580 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 21 | Each | 67.9 | 1426 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 6 | Each | 43.16 | 259 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 16 | Each | 35.52 | 568 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 21 | Each | 47.04 | 988 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 50 | Each | 16.49 | 824 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Saint Gobain Castings | Not on List | 10 | Each | NULL | 0 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 21 | Each | 81.73 | 1716 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 10 | Each | NULL | 0 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10677-001025 | 10677 | 2019-01-08 08:06 | Section 4 | Material | Not on List | Not on List | 120 | 2m | 211.66 | 25399.2 | Ductile Drainage | 2019-01-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | Not on List | 30 | NULL | NULL | 0 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 67.9 | 1019 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 15 | Each | 50.92 | 764 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 15 | Each | 43.16 | 647 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 5 | Each | 35.52 | 178 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10741-001025 | 10741 | 2019-01-09 07:44 | Section 4 | Material | Not on List | Not on List | 20 | rolls | 9.29 | 185.8 | Not Sure | 2019-01-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10793-001025 | 10793 | 2019-01-09 16:22 | Section 3 | Material | Ducting | Not on List | 1 | no | 837.68 | 838 | Damage Charges | 2019-01-10 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10694-001025 | 10694 | 2019-01-08 10:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1431.54 | Each | 1 | 1431.54 | Small Tools (Consumables) | 2019-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10799-001025 | 10799 | 2019-01-10 07:35 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10780-001025 | 10780 | 2019-01-09 16:11 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 20 | Each | 110.27 | 2205.4 | Geotextiles | 2019-01-11 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 604 - Deposition | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10805-001025 | 10805 | 2019-01-10 08:36 | Section 3 | Material | Not on List | Not on List | 5 | T | NULL | 0 | Builders Merchants (General) | 2019-01-17 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10828-001025 | 10828 | 2019-01-10 12:44 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10777-001025 | 10777 | 2019-01-09 15:53 | Section 4 | Material | NULL | Not on List | 9 | Each | 87.99 | 791.91 | Plastic Drainage | 2019-01-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | Each | 240 | 240 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | Each | 67.9 | 203.7 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | Each | 50.92 | 152.76 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | Each | 43.16 | 43.16 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 6 | Each | 47.04 | 282.24 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 24 | Each | 22 | 528 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 6 | Each | 74.3 | 445.8 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | Each | 121.25 | 121.25 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | Each | 90.94 | 272.82 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 80.51 | 322.04 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 102.82 | 411.28 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 16 | Each | 22 | 352 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 74.3 | 297.2 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 4 | Each | 240 | 960 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 44 | Each | 67.9 | 2987.6 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 400 | Each | 3.4 | 1360 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 2 | Each | 34.82 | 69.64 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 5 | Each | 1.98 | 9.9 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 5 | Each | 7.06 | 35.3 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 12 | Each | 0.91 | 10.92 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 12 | Each | 2.97 | 35.64 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 250 | NULL | NULL | 0 | Concrete Accessories | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 35 | NULL | NULL | 0 | Rebar and Mesh | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Rebar and Mesh | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21187-001025 | 21187 | 2019-07-23 11:18 | Section 3 | Material | PPE, Small Tools and Consumables | Refill Air Care Pristine Wild Berries Air Fragrance 270ml (539229) | 8 | Each | 3.1 | 25 | Janitorial | 2019-07-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 160 | Each | 3.4 | 544 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21127-001025 | 21127 | 2019-07-22 11:23 | Core | Material | Not on List | Not on List | 72 | case | 6.5 | 468 | Miscellaneous | 2019-07-24 | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21190-001025 | 21190 | 2019-07-23 11:54 | Section 4 | Material | Timber | Not on List | 2 | each | NULL | 0 | Builders Merchants (General) | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20589-001025 | 20589 | 2019-07-10 18:34 | Section 3 | Material | Not on List | Not on List | 112 | Bags | 2.97 | 332.64 | Builders Merchants (General) | 2019-07-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20589-001025 | 20589 | 2019-07-10 18:34 | Section 3 | Material | Not on List | Not on List | 56 | Bags | 2.97 | 166.32 | Builders Merchants (General) | 2019-07-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20589-001025 | 20589 | 2019-07-10 18:34 | Section 3 | Material | Not on List | Not on List | 12 | Plates | 219.65 | 2635.8 | Miscellaneous | 2019-08-05 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20589-001025 | 20589 | 2019-07-10 18:34 | Section 3 | Material | Not on List | Not on List | 4 | Plates | 183.04 | 732.16 | Miscellaneous | 2019-08-05 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20589-001025 | 20589 | 2019-07-10 18:34 | Section 3 | Material | Not on List | Not on List | 4 | Plates | 95.74 | 382.96 | Miscellaneous | 2019-08-05 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20892-001025 | 20892 | 2019-07-17 09:27 | Section 3 | Material | Not on List | Not on List | 4 | ea | 8.17 | 32.68 | Miscellaneous | 2019-07-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21202-001025 | 21202 | 2019-07-23 12:30 | Section 3 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-07-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21202-001025 | 21202 | 2019-07-23 12:30 | Section 3 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2019-07-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 12 | Each | 5.24 | 62.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | Kerbs | Not on List | 70 | No | NULL | 0 | Builders Merchants (General) | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | Kerbs | Not on List | 30 | No | NULL | 0 | Builders Merchants (General) | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 760 | Each | 1.5 | 1140 | Builders Merchants (General) | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 2 | Each | 7.68 | 15.36 | Builders Merchants (General) | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 2 | Each | 7.68 | 15.36 | Builders Merchants (General) | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21210-001025 | 21210 | 2019-07-23 13:57 | Section 2 | Material | Timber | Not on List | 20 | NULL | NULL | 0 | Timber Products | 2019-07-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21114-001025 | 21114 | 2019-07-22 10:32 | Section 3 | Material | Not on List | Not on List | 6520 | No | 2.72 | 17734.4 | Builders Merchants (General) | 2019-07-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21114-001025 | 21114 | 2019-07-22 10:32 | Section 3 | Material | Not on List | Not on List | 200 | No | 3.12 | 624 | Builders Merchants (General) | 2019-07-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 64 | Each | 2.93 | 187.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21213-001025 | 21213 | 2019-07-23 14:21 | Core | Material | Not on List | Not on List | 6 | number | NULL | 0 | Surveying Consumables | 2019-08-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21213-001025 | 21213 | 2019-07-23 14:21 | Core | Material | Not on List | Not on List | 2 | number | NULL | 0 | Surveying Consumables | 2019-08-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21146-001025 | 21146 | 2019-07-22 14:53 | Section 3 | Material | Not on List | Not on List | 6 | Beam | 5308.36 | 31850.16 | Miscellaneous | 2019-04-22 | RVP 419 (S3) - 1340880 - A14 Westbound (West of Junction 28) | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21173-001025 | 21173 | 2019-07-23 08:04 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | NULL | 0.63 | 9.45 | Small Tools (Consumables) | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21104-001025 | 21104 | 2019-07-22 08:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Pack 24 Bottled Water | 6.29 | 905.76 | Small Tools (Consumables) | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21217-001025 | 21217 | 2019-07-23 16:03 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21108-001025 | 21108 | 2019-07-22 09:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 70.5 | 70.5 | Miscellaneous | 2019-07-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21118-001025 | 21118 | 2019-07-22 10:53 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | 0.79 | 31.6 | Small Tools (Consumables) | 2019-07-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21178-001025 | 21178 | 2019-07-23 09:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 226.18 | 226.18 | Small Tools (Consumables) | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21180-001025 | 21180 | 2019-07-23 09:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 466.34 | 466.34 | Small Tools (Consumables) | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 5 | Each | 5.25 | 26.25 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21174-001025 | 21174 | 2019-07-23 08:31 | Core | Material | Not on List | Not on List | 1 | No | 67.2 | 67.2 | Office Supplies | 2019-07-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21223-001025 | 21223 | 2019-07-23 17:20 | Section 5 | Material | PPE, Small Tools and Consumables | Water Natural Mineral Ideal Still 500ml Bottle Case Of 24 (744570) | 50 | Each | 6.29 | 315 | Small Tools (Consumables) | 2019-07-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21231-001025 | 21231 | 2019-07-24 06:58 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-21232-001025 | 21232 | 2019-07-24 07:11 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21207-001025 | 21207 | 2019-07-23 13:40 | Section 4 | Material | Waste Management | Plastic - Roll On Roll Off 20 cubic yard | 1 | Each | 360 | 360 | Waste (Recycling) | 2019-07-24 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21235-001025 | 21235 | 2019-07-24 07:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 3 | Each | 50 | 150 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21240-001025 | 21240 | 2019-07-24 08:26 | Section 3 | Material | Not on List | Not on List | 8 | No. | NULL | 0 | Fixings and Fasteners | 2019-07-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | CL3B - Structures (Culverts) 3B | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21240-001025 | 21240 | 2019-07-24 08:26 | Section 3 | Material | Not on List | Not on List | 15 | No. | NULL | 0 | Fixings and Fasteners | 2019-07-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | CL3B - Structures (Culverts) 3B | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21061-001025 | 21061 | 2019-07-19 13:32 | Section 4 | Material | NULL | NULL | 500 | Each | 7.5 | 3750 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21110-001025 | 21110 | 2019-07-22 09:23 | Section 4 | Material | NULL | NULL | 1 | Each | 35.6 | 35.6 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21249-001025 | 21249 | 2019-07-24 10:04 | Section 3 | Material | Not on List | Not on List | 10 | No. | NULL | 0 | Geotextiles | 2019-07-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 400 | Each | 1.45 | 580 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21249-001025 | 21249 | 2019-07-24 10:04 | Section 3 | Material | Not on List | Not on List | 1 | No. of Rolls | NULL | 0 | Geotextiles | 2019-07-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | CL3B - Structures (Culverts) 3B | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18791-001025 | 18791 | 2019-06-07 15:37 | Core | Material | Not on List | Not on List | 8 | licenses | 284.63 | 2277.04 | Miscellaneous | 2019-06-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20156-001025 | 20156 | 2019-07-03 12:20 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20159-001025 | 20159 | 2019-07-03 12:47 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19858-001025 | 19858 | 2019-06-27 15:52 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20977-001025 | 20977 | 2019-07-18 09:19 | Section 4 | Material | Waste Management | Plastic - Roll On Roll Off 20 cubic yard | 1 | Each | 360 | 360 | Waste (General) | 2019-07-22 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20977-001025 | 20977 | 2019-07-18 09:19 | Section 4 | Material | Bagged | Not on List | 20 | Number | 4.95 | 99 | Builders Merchants (General) | 2019-07-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20977-001025 | 20977 | 2019-07-18 09:19 | Section 4 | Material | Bagged | Not on List | 2 | Number | 166.22 | 332.44 | Builders Merchants (General) | 2019-07-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21260-001025 | 21260 | 2019-07-24 11:38 | Core | Material | Not on List | Not on List | 1 | Pack of 100 | 22 | 22 | Surveying Consumables | 2019-08-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Rigidrain P/E 225Mm Dia Incl Coup/Sealia | 1 | no | 4233.6 | 4233.6 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 5 | Each | 5.25 | 26.25 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21260-001025 | 21260 | 2019-07-24 11:38 | Core | Material | Not on List | Not on List | 2 | number | NULL | 0 | Surveying Consumables | 2019-08-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21260-001025 | 21260 | 2019-07-24 11:38 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Surveying Consumables | 2019-08-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21236-001025 | 21236 | 2019-07-24 07:55 | Section 3 | Material | Not on List | Not on List | 20 | roll | 26.25 | 525 | Geotextiles | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20841-001025 | 20841 | 2019-07-16 13:32 | Section 4 | Material | Not on List | Not on List | 3 | Number | 20 | 60 | Surveying Consumables | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20749-001025 | 20749 | 2019-07-15 09:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 9950 | 9950 | Miscellaneous | 2019-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21278-001025 | 21278 | 2019-07-24 15:18 | Core | Material | Not on List | Not on List | 1 | number | 199.6 | 200 | Office Supplies | 2019-07-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20765-001025 | 20765 | 2019-07-15 13:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 693.74 | 693.74 | Miscellaneous | 2019-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21303-001025 | 21303 | 2019-07-25 06:54 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 300Mm X 6M Ridgidrain Plain Ended | 230 | Each | 34.82 | 8008.6 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21304-001025 | 21304 | 2019-07-25 07:14 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21305-001025 | 21305 | 2019-07-25 07:22 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-21306-001025 | 21306 | 2019-07-25 07:55 | Section 3 | Material | Not on List | Not on List | 5000 | No | NULL | 0 | Builders Merchants (General) | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21238-001025 | 21238 | 2019-07-24 08:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 10.5 | 105 | Surveying Consumables | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21238-001025 | 21238 | 2019-07-24 08:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 10.5 | 105 | Surveying Consumables | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21238-001025 | 21238 | 2019-07-24 08:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 10.5 | 105 | Surveying Consumables | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21326-001025 | 21326 | 2019-07-25 11:24 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 300Mm Ridgidrain Dbl Skt Coupler | 260 | Each | 6.54 | 1700.4 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21330-001025 | 21330 | 2019-07-25 11:37 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21332-001025 | 21332 | 2019-07-25 11:46 | Core | Material | Not on List | Not on List | 1 | 1215.2 | 1215.2 | 1215 | Miscellaneous | 2019-07-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21144-001025 | 21144 | 2019-07-22 14:40 | Section 3 | Material | Not on List | Not on List | 100 | ea | 3.38 | 338 | Rebar and Mesh | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21144-001025 | 21144 | 2019-07-22 14:40 | Section 3 | Material | Not on List | Not on List | 1000 | ea | 1.96 | 1960 | Rebar and Mesh | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21144-001025 | 21144 | 2019-07-22 14:40 | Section 3 | Material | Not on List | Not on List | 35 | ea | 1.78 | 62.3 | Concrete Accessories | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21144-001025 | 21144 | 2019-07-22 14:40 | Section 3 | Material | Not on List | Not on List | 100 | ea | 0.34 | 34 | Concrete Accessories | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 300Mm Ridgidrain Seal | 520 | Each | 2.75 | 1430 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21340-001025 | 21340 | 2019-07-25 12:40 | Core | Material | Not on List | Not on List | 1 | NULL | 1865 | 1865 | Professional Services | 2019-07-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21244-001025 | 21244 | 2019-07-24 09:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Small Tools (Consumables) | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21344-001025 | 21344 | 2019-07-25 13:45 | Section 4 | Material | Not on List | Not on List | 1 | Number | 186.09 | 186 | Surveying Consumables | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21317-001025 | 21317 | 2019-07-25 09:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 119.32 | 119.32 | Small Tools (Consumables) | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21351-001025 | 21351 | 2019-07-25 14:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 165.65 | 166 | PPE | 2019-07-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21351-001025 | 21351 | 2019-07-25 14:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 854.18 | 854 | Small Tools (Consumables) | 2019-07-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21351-001025 | 21351 | 2019-07-25 14:19 | Core | Material | Not on List | Not on List | 1 | NULL | 109 | 109 | Janitorial | 2019-07-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21322-001025 | 21322 | 2019-07-25 11:08 | Section 4 | Material | NULL | NULL | 120 | Each | 16.57 | 1988.4 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 400Mm X 6M R-Drain Unperf + Coup | 120 | Each | 120.62 | 14474.4 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21359-001025 | 21359 | 2019-07-25 14:58 | Section 2 | Material | Hazardous Waste | Not on List | 1 | each | 1280 | 1280 | Waste (General) | 2019-07-31 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Concrete Drainage | Cpm 1050X1000 C/W Steps | 30 | Each | 67.9 | 2037 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21247-001025 | 21247 | 2019-07-24 10:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 33.95 | 271.6 | Small Tools (Consumables) | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21042-001025 | 21042 | 2019-07-19 11:44 | Section 5 | Material | Not on List | Not on List | 1 | SM | 52583 | 52583 | Not Sure | 2019-07-29 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 55 | NULL | 179.74 | 9885.7 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 65 | NULL | 22.36 | 1453.4 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 131.32 | 787.92 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 180 | Each | 9.04 | 1627.2 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 38.36 | 230.16 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 10 | NULL | 125.94 | 1259.4 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 10 | NULL | 125.94 | 1259.4 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 10 | NULL | 10.84 | 108.4 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 5 | NULL | 18.87 | 94.35 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 35 | NULL | 130.26 | 4559.1 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 35 | NULL | 9.76 | 341.6 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 12 | NULL | 18.84 | 226.08 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21008-001025 | 21008 | 2019-07-18 17:51 | Section 5 | Material | Not on List | Not on List | 300 | No | 7.5 | 2250 | Surveying Consumables | 2019-07-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21176-001025 | 21176 | 2019-07-23 08:47 | Core | Material | Not on List | Not on List | 6 | ea | 37 | 222 | Office Supplies | 2019-07-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Not on List | Not on List | 11 | Each | 50.92 | 560.12 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21393-001025 | 21393 | 2019-07-26 08:05 | Core | Material | NULL | NULL | 1 | Eack | 393.42 | 393.42 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21280-001025 | 21280 | 2019-07-24 14:29 | Core | Material | NULL | NULL | 2000 | Each | 0.51 | 1020 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21434-001025 | 21434 | 2019-07-26 13:18 | Section 2 | Material | Not on List | Not on List | 2 | 5ltr Tubs | NULL | 0 | Blocks and Bricks | 2019-07-31 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN02 - Grafham Road Bridge | 2401 - Brickwork, Blockwork and Stonework | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-8483-001023 | 8483 | 2018-10-31 09:14 | Section 4 | Material | Not on List | Not on List | 80 | U | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8483-001023 | 8483 | 2018-10-31 09:14 | Section 4 | Material | Not on List | Not on List | 20 | U | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8487-001023 | 8487 | 2018-10-31 09:22 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8489-001023 | 8489 | 2018-10-31 10:03 | Section 4 | Material | Not on List | Not on List | 5 | NULL | 145 | 725 | Surveying Consumables | 2018-11-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8376-001023 | 8376 | 2018-10-29 14:03 | Section 4 | Material | Not on List | Not on List | 400 | Each | 0.48 | 192 | Concrete Accessories | 2018-10-31 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8440-001023 | 8440 | 2018-10-30 11:31 | Section 4 | Material | Not on List | Not on List | 10 | 1t Bag | 32.74 | 327.4 | Builders Merchants (General) | 2018-11-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8439-001023 | 8439 | 2018-10-30 11:24 | Section 4 | Material | NULL | Building Sand Bulk Bag (938155) | 4 | Each | 32.74 | 130.96 | Builders Merchants (General) | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8446-001023 | 8446 | 2018-10-30 11:21 | Section 4 | Material | NULL | Kiln Dried Sand 25kg (518674) | 80 | Each | 2.26 | 180.8 | Builders Merchants (General) | 2018-11-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8495-001023 | 8495 | 2018-10-31 12:11 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Drainage | 2018-11-05 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8511-001023 | 8511 | 2018-10-31 15:25 | Section 3 | Material | Aggregate | Not on List | 1500 | m3 | 43.08 | 64620 | Aggregate | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8516-001023 | 8516 | 2018-10-31 15:46 | Section 3 | Material | Signage | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8532-001023 | 8532 | 2018-10-31 18:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-11-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 6 | number | 310.05 | 1860.3 | Not Sure | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 10 | number | 32.15 | 321.5 | Concrete Accessories | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 6 | number | 89.6 | 537.6 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Signage | Directional Signage - 390 x 510 | 8 | Each | 7.9441 | 63.55 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Signage | Directional Signage - 390 x 510 | 6 | Each | 7.9441 | 47.66 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8537-001023 | 8537 | 2018-11-01 07:38 | Section 3 | Material | Concrete Drainage | Not on List | 20 | Units | 1346 | 26920 | Concrete Drainage | 2018-11-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8464-001023 | 8464 | 2018-10-30 18:14 | Section 3 | Material | PPE, Small Tools and Consumables | Helmet Attachment-jsp Navy Blue Helmet Warmer (271301) | 31 | Each | 5.43 | 168.33 | PPE | 2018-11-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8516-001023 | 8516 | 2018-10-31 15:46 | Section 3 | Material | Signage | Not on List | 1 | number | 252.85 | 252.85 | Miscellaneous | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN06 - ECML Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8566-001023 | 8566 | 2018-11-01 12:43 | Section 3 | Material | Not on List | Not on List | 1 | Number | 3253.2 | 3253 | Miscellaneous | 2018-11-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8511-001023 | 8511 | 2018-10-31 15:25 | Section 3 | Material | Aggregate | Not on List | 1500 | m3 | 43.08 | 64620 | Aggregate | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8532-001023 | 8532 | 2018-10-31 18:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 902 | 902 | Damage Charges | 2018-11-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8537-001023 | 8537 | 2018-11-01 07:38 | Section 3 | Material | Concrete Drainage | Not on List | 20 | Units | 1346 | 26920 | Concrete Drainage | 2018-11-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8487-001023 | 8487 | 2018-10-31 09:22 | Section 3 | Material | Aggregate | NULL | 10 | roll | 24.3 | 243 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8578-001023 | 8578 | 2018-11-01 15:23 | Section 4 | Material | Not on List | Not on List | 25 | NULL | NULL | 0 | Not Sure | 2018-11-05 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8597-001023 | 8597 | 2018-11-01 16:15 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 5993.59 | 5994 | Miscellaneous | 2018-11-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8597-001023 | 8597 | 2018-11-01 16:15 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 5993.59 | 5993.59 | Miscellaneous | 2018-11-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8578-001023 | 8578 | 2018-11-01 15:23 | Section 4 | Material | Not on List | Not on List | 25 | NULL | NULL | 0 | Not Sure | 2018-11-05 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | PPE, Small Tools and Consumables | Stake Marking Out Wooden 1200mm Nominal C.r.code Swcoc004463 (740904) | 500 | Each | 1.07 | 535 | Surveying Consumables | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | NULL | 0 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 941 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 67.9 | 1019 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 432 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | Not on List | 10 | NULL | NULL | 0 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 10 | Each | 59.17 | 592 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8494-001023 | 8494 | 2018-10-31 10:54 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 200 | Each | 0.5 | 100 | Miscellaneous | 2018-11-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8458-001023 | 8458 | 2018-10-30 16:02 | Section 4 | Material | PPE, Small Tools and Consumables | Granules Ice Melt 10kg Bag Ref: 110160 (500258) | 80 | Each | 18.03 | 1442.4 | Miscellaneous | 2018-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8503-001023 | 8503 | 2018-10-31 13:28 | Section 4 | Material | Not on List | Not on List | 7 | Each | 15125 | 105875 | Electrical | 2018-11-01 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8483-001023 | 8483 | 2018-10-31 09:14 | Section 4 | Material | Not on List | Not on List | 80 | U | 2.18 | 174.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8483-001023 | 8483 | 2018-10-31 09:14 | Section 4 | Material | Not on List | Not on List | 20 | U | 5.84 | 116.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8544-001023 | 8544 | 2018-11-01 08:56 | Section 4 | Material | Hazardous Waste | Not on List | 1 | 8 yard hazardous waste Skip | 655 | 655 | Waste (General) | 2018-11-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 3.352 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 3.352 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 3.394 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 2 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8415-001023 | 8415 | 2018-10-30 06:33 | Section 4 | Material | Not on List | Not on List | 3 | 20ltr Case | 145.9 | 437.7 | Miscellaneous | 2018-11-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8495-001023 | 8495 | 2018-10-31 12:11 | Section 4 | Material | Not on List | Not on List | 10 | NULL | 361.34 | 3613.4 | Concrete Drainage | 2018-11-05 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8457-001023 | 8457 | 2018-10-30 15:47 | Section 4 | Material | NULL | Not on List | 1 | 100 Number | 675 | 675 | Timber Products | 2018-11-02 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8662-001023 | 8662 | 2018-11-05 07:56 | Section 3 | Material | Not on List | Not on List | 1 | ea | 96.8 | 97 | Damage Charges | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8676-001023 | 8676 | 2018-11-05 09:55 | Section 4 | Material | Not on List | Not on List | 30 | no | NULL | 0 | Miscellaneous | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | Not on List | Not on List | 1 | no | NULL | 0 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | Not on List | Not on List | 6 | no | NULL | 0 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | Not on List | Not on List | 1 | no | NULL | 0 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5034-0020 | 5034 | 2018-08-14 09:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 920 | NULL | NULL | 0 | Surveying Consumables | 2018-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6694-001023 | 6694 | 2018-09-18 17:31 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | Concrete Drainage | Not on List | 10 | U | NULL | 0 | Concrete Drainage | 2018-11-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | Concrete Drainage | Not on List | 12 | U | NULL | 0 | Concrete Drainage | 2018-11-08 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8712-001024 | 8712 | 2018-11-05 16:20 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Timber Products | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1703 - Formwork | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8712-001024 | 8712 | 2018-11-05 16:20 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Timber Products | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1703 - Formwork | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8712-001024 | 8712 | 2018-11-05 16:20 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Timber Products | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1703 - Formwork | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-5246-00160 | 5246 | 2018-08-16 16:02 | Section 4 | Material | Not on List | Not on List | 2000 | NULL | 0.03 | 60 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8714-001024 | 8714 | 2018-11-05 16:38 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8295-001023 | 8295 | 2018-10-26 10:26 | Section 3 | Material | Not on List | Not on List | 3 | Visits | 950 | 2850 | Professional Services | 2018-10-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8295-001023 | 8295 | 2018-10-26 10:26 | Section 3 | Material | Not on List | Not on List | 1 | Visit | 136.69 | 136.69 | Professional Services | 2018-10-30 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8690-001024 | 8690 | 2018-11-05 11:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8690-001024 | 8690 | 2018-11-05 11:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1000 | EA | 1.07 | 1070 | Miscellaneous | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8736-001024 | 8736 | 2018-11-06 09:00 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-11-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8737-001024 | 8737 | 2018-11-06 08:59 | Section 4 | Material | Concrete Drainage | Not on List | 2 | U | NULL | 0 | Concrete Drainage | 2018-11-09 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8739-001024 | 8739 | 2018-11-06 09:51 | Section 4 | Material | Not on List | Not on List | 0 | NULL | NULL | 0 | Miscellaneous | 2018-11-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-5246-00160 | 5246 | 2018-08-16 16:02 | Section 4 | Material | Not on List | Not on List | 700 | NULL | 0.05 | 35 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8698-001024 | 8698 | 2018-11-05 13:46 | Section 4 | Material | NULL | Building Sand Bulk Bag (938155) | 5 | Each | 32.74 | 163.7 | Builders Merchants (General) | 2018-11-08 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | Ducting | Not on List | 9 | U | NULL | 0 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | Ducting | Not on List | 10 | U | NULL | 0 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | Ducting | Not on List | 20 | U | NULL | 0 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-8602-001023 | 8602 | 2018-11-02 07:26 | Section 4 | Material | Not on List | Not on List | 15 | Each | 36.96 | 554.4 | Small Tools (Consumables) | 2018-11-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8749-001024 | 8749 | 2018-11-06 11:33 | Section 4 | Material | Not on List | Not on List | 75 | (25kg bags) | NULL | 0 | Not Sure | 2018-12-14 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN23 - Structure BN23 | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 12.851 | tonne | 538 | 6913.84 | Rebar and Mesh | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7666 | 7666 | 2018-10-11 09:48 | Section 4 | Material | Not on List | Not on List | 2198 | Each | 1.85 | 4066.3 | Professional Services | 2018-10-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Concrete Drainage | Not on List | 18 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | PPE, Small Tools and Consumables | Stake Marking Out Wooden 1200mm Nominal C.r.code Swcoc004463 (740904) | 500 | Each | 1.07 | 535 | Surveying Consumables | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 940.8 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 67.9 | 1018.5 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509.2 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | Not on List | 10 | Ea | 232.01 | 2320.1 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 10 | Each | 59.17 | 591.7 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8489-001023 | 8489 | 2018-10-31 10:03 | Section 4 | Material | Not on List | Not on List | 5 | Each | 145 | 725 | Surveying Consumables | 2018-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8760-001024 | 8760 | 2018-11-06 14:20 | Section 3 | Material | PPE, Small Tools and Consumables | Jacket A14 Logod Regatta Seal Grey Octagon Ii Mens Softshell (16318) | 21 | Each | 27.5 | 578 | PPE | 2018-11-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Concrete Drainage | Not on List | 4 | NULL | 1259.25 | 5037 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8761-001024 | 8761 | 2018-11-06 14:34 | Section 4 | Material | Aggregate | A40 Pipe Bed | 100 | Tonnes | 20.95 | 2095 | Aggregate | 2018-11-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8763-001024 | 8763 | 2018-11-06 14:51 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2239.35 | 2239 | Not Sure | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8766-001024 | 8766 | 2018-11-06 15:04 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2584.57 | 2585 | Not Sure | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8749-001024 | 8749 | 2018-11-06 11:33 | Section 4 | Material | Not on List | Not on List | 75 | Each | 14.43 | 1082.25 | Miscellaneous | 2018-12-14 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8712-001024 | 8712 | 2018-11-05 16:20 | Section 4 | Material | Not on List | Not on List | 1 | Lot | 765 | 765 | Timber Products | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8755-001024 | 8755 | 2018-11-06 13:57 | Section 4 | Material | Not on List | Not on List | 40 | Each | 44.92 | 1796.8 | Miscellaneous | 2018-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8806-001024 | 8806 | 2018-11-07 08:05 | Section 3 | Material | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Plastic Drainage | 2018-11-12 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Concrete Drainage | Not on List | 12 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8806-001024 | 8806 | 2018-11-07 08:05 | Section 3 | Material | Aggregate | A10 Pipe Bed | 200 | Tonnes | 16.5 | 3300 | Plastic Drainage | 2018-11-12 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8760-001024 | 8760 | 2018-11-06 14:20 | Section 3 | Material | PPE, Small Tools and Consumables | Jacket A14 Logod Regatta Seal Grey Octagon Ii Mens Softshell (16318) | 21 | Each | 27.5 | 577.5 | PPE | 2018-11-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8763-001024 | 8763 | 2018-11-06 14:51 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2239.35 | 2239.35 | Not Sure | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8829-001024 | 8829 | 2018-11-07 14:10 | Section 4 | Material | Not on List | Not on List | 1 | No. | NULL | 0 | Concrete Drainage | 2018-11-07 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8806-001024 | 8806 | 2018-11-07 08:05 | Section 3 | Material | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Plastic Drainage | 2018-11-12 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8806-001024 | 8806 | 2018-11-07 08:05 | Section 3 | Material | Aggregate | A10 Pipe Bed | 200 | Tonnes | 16.5 | 3300 | Plastic Drainage | 2018-11-12 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8834-001024 | 8834 | 2018-11-07 14:22 | Section 3 | Material | Not on List | Not on List | 8 | ea | 41.74 | 334 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Concrete Drainage | Not on List | 15 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8662-001023 | 8662 | 2018-11-05 07:56 | Section 3 | Material | Not on List | Not on List | 1 | ea | 96.8 | 96.8 | Damage Charges | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8766-001024 | 8766 | 2018-11-06 15:04 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2584.57 | 2584.57 | Not Sure | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8837-001024 | 8837 | 2018-11-07 14:46 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 50 | Each | 48.86 | 2443 | Plastic Drainage | 2018-11-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22937-001025 | 22937 | 2019-08-29 10:37 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Full Pallet | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-22938-001025 | 22938 | 2019-08-29 12:16 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Full Pallet | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 2 | Each | 2.9 | 5.8 | Builders Merchants (General) | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22919-001025 | 22919 | 2019-08-29 09:39 | Section 5 | Material | Not on List | NULL | 4 | EA | 51.77 | 207.08 | Builders Merchants (General) | 2019-08-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22891-001025 | 22891 | 2019-08-28 15:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 374.44 | Each | 1 | 374.44 | Small Tools (Consumables) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22889-001025 | 22889 | 2019-08-28 15:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | Bag | 2.97 | 332.64 | Builders Merchants (General) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22888-001025 | 22888 | 2019-08-28 15:19 | Section 4 | Material | Not on List | Not on List | 1 | Each | 255.25 | 255.25 | Miscellaneous | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22921-001025 | 22921 | 2019-08-29 09:09 | Section 4 | Material | Not on List | NULL | 8 | EA | 1895 | 15160 | Not Sure | 2019-09-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22868-001025 | 22868 | 2019-08-28 11:12 | Section 4 | Material | Not on List | Not on List | 9170 | Each | 1 | 9170 | Gas Oil | 2019-09-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 15 | Each | 81.73 | 1225.95 | Concrete Drainage | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 45 | Each | 13.44 | 604.8 | Builders Merchants (General) | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 4000 | Each | 0.37 | 1480 | Builders Merchants (General) | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Tubs | NULL | 0 | Builders Merchants (General) | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | Concrete Drainage | Not on List | 60 | each | NULL | 0 | Concrete Drainage | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | Not on List | Not on List | 500 | metres | NULL | 0 | Builders Merchants (General) | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | Concrete Drainage | Not on List | 20 | tubs | NULL | 0 | Concrete Drainage | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22830-001025 | 22830 | 2019-08-27 17:09 | Section 4 | Material | NULL | NULL | 20 | EAch | 41.2 | 824 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 10 | Each | 116.62 | 1166.2 | Plastic Drainage | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22907-001025 | 22907 | 2019-08-29 07:26 | Section 4 | Material | Not on List | Not on List | 1 | Each | 620 | 620 | Electrical | 2019-08-30 | RVP 420 - A14 Eastbound - Opposite Crematorium | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22890-001025 | 22890 | 2019-08-28 15:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1225.16 | 1225.16 | Small Tools (Consumables) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22860-001025 | 22860 | 2019-08-28 08:40 | Section 5 | Material | Not on List | Not on List | 30 | number | 125.22 | 3756.6 | Concrete Accessories | 2019-08-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22954-001025 | 22954 | 2019-08-29 14:38 | Section 5 | Material | Combined Drainage | NULL | 1 | SM | 7355.55 | 7355.55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-30 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22960-001025 | 22960 | 2019-08-29 16:02 | Section 5 | Material | Not on List | NULL | 6 | EA | 16.5 | 99 | Not Sure | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 40 | Each | 13.86 | 554.4 | Plastic Drainage | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22798-001025 | 22798 | 2019-08-27 10:19 | Section 5 | Material | Not on List | NULL | 1075.8 | SM | 24.88 | 26765.9 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-03 | 1358005 - WB5/7 Works Access - 1356563 - A14 Westbound, On Left between Jcn 32 - 31 | SEC5 - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22838-001025 | 22838 | 2019-08-27 17:32 | Section 5 | Material | Not on List | Not on List | 260 | m2 | 17.66 | 4591.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-03 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22838-001025 | 22838 | 2019-08-27 17:32 | Section 5 | Material | Not on List | Not on List | 25 | EA | 29.44 | 736 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-03 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22946-001025 | 22946 | 2019-08-29 13:03 | Section 2 | Material | Bricks/Blocks | Not on List | 170 | Kerbs | NULL | 0 | Blocks and Bricks | 2019-09-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 22 | Each | 9.04 | 198.88 | Plastic Drainage | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23035-001025 | 23035 | 2019-09-02 08:54 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Tanks and Interceptors | 2019-09-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 3 Buyers
MREQ-22680-001025 | 22680 | 2019-08-22 15:58 | Core | Material | Not on List | Not on List | 45 | each | 63 | 2835 | Miscellaneous | 2019-08-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22958-001025 | 22958 | 2019-08-29 15:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 78 | Each | 1 | 78 | PPE | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 6 | Each | 120.62 | 723.72 | Plastic Drainage | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22949-001025 | 22949 | 2019-08-29 14:01 | Section 6 | Material | Not on List | Not on List | 1 | No. | 246407.52 | 246407.52 | Miscellaneous | 2019-09-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22807-001025 | 22807 | 2019-08-27 11:58 | Core | Material | Not on List | Not on List | 1 | ea | 1737.5 | 1737.5 | Training | 2019-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22813-001025 | 22813 | 2019-08-27 13:38 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2019-09-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 107 - Fee based costs including insurance | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22333-001025 | 22333 | 2019-08-15 14:29 | Section 5 | Material | Not on List | NULL | 1 | SM | 1183.86 | 1183.86 | Miscellaneous | 2019-08-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22959-001025 | 22959 | 2019-08-29 15:39 | Core | Material | PPE, Small Tools and Consumables | Not on List | 445.12 | Each | 1 | 445.12 | Small Tools (Consumables) | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23001-001025 | 23001 | 2019-08-30 14:34 | Section 2 | Material | Combined Drainage | Not on List | 60 | number | NULL | 0 | Ductile Drainage | 2019-09-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23001-001025 | 23001 | 2019-08-30 14:34 | Section 2 | Material | Combined Drainage | Not on List | 60 | number | NULL | 0 | Ductile Drainage | 2019-09-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6470-00712 | 6470 | 2018-09-13 11:02 | Section 4 | Material | Not on List | Not on List | 3.394 | Tonne | 538 | 1825.97 | Rebar and Mesh | 2018-09-27 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23001-001025 | 23001 | 2019-08-30 14:34 | Section 2 | Material | Combined Drainage | Not on List | 72 | number | NULL | 0 | Ductile Drainage | 2019-09-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23001-001025 | 23001 | 2019-08-30 14:34 | Section 2 | Material | Combined Drainage | Not on List | 1 | number | NULL | 0 | Ductile Drainage | 2019-09-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23003-001025 | 23003 | 2019-08-30 14:59 | Section 3 | Material | Aggregate | 6G | 200 | Tonnes | 32.9 | 6580 | Aggregate | 2019-08-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22982-001025 | 22982 | 2019-08-30 09:36 | Section 6 | Material | Aggregate | Class 1A | 2500 | Tonnes | 4 | 10000 | Aggregate | 2019-09-02 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23055-001025 | 23055 | 2019-09-02 11:15 | Section 5 | Material | Ducting | NULL | 3 | EA | 156.6 | 469.8 | Plastic Drainage | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23043-001025 | 23043 | 2019-09-02 09:57 | Section 5 | Material | Ducting | NULL | 16 | EA | 10.42 | 166.72 | Builders Merchants (General) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23043-001025 | 23043 | 2019-09-02 09:57 | Section 5 | Material | Ducting | NULL | 2 | EA | 23.65 | 47.3 | Builders Merchants (General) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23043-001025 | 23043 | 2019-09-02 09:57 | Section 5 | Material | Ducting | NULL | 1 | EA | 25 | 25 | Builders Merchants (General) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5138-0066 | 5138 | 2018-08-15 11:27 | Section 3 | Material | Not on List | NULL | 10 | No | 67.24 | 672.4 | Builders Merchants (General) | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6470-00712 | 6470 | 2018-09-13 11:02 | Section 4 | Material | Not on List | Not on List | 3.394 | Tonne | 538 | 1825.97 | Rebar and Mesh | 2018-09-27 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 36 | Each | 34.82 | 1253.52 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 152 | Each | 2.97 | 451.44 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 21 | Each | 3.65 | 76.65 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 42 | Each | 2 | 84 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 4 | Each | 116.62 | 466.48 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 450mm Ridgidrain Seal (346396) | 4 | Each | 10.04 | 40.16 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23066-001025 | 23066 | 2019-09-02 13:38 | Section 3 | Material | PPE, Small Tools and Consumables | Pendant Barrier Marker 32 X 26m Long Approx (200040) | 25 | Each | 10.7 | 267.5 | Miscellaneous | 2019-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6470-00712 | 6470 | 2018-09-13 11:02 | Section 4 | Material | Not on List | Not on List | 3.394 | Tonne | 538 | 1825.97 | Rebar and Mesh | 2018-09-27 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23049-001025 | 23049 | 2019-09-02 10:13 | Section 3 | Material | Not on List | Not on List | 1 | No | NULL | 0 | Professional Services | 2019-09-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22665-001025 | 22665 | 2019-08-22 11:01 | Section 4 | Material | Not on List | Not on List | 12 | Rolls | 49.5 | 594 | Miscellaneous | 2019-08-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22665-001025 | 22665 | 2019-08-22 11:01 | Section 4 | Material | NULL | Not on List | 1 | Each | 650 | 650 | Miscellaneous | 2019-08-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23069-001025 | 23069 | 2019-09-02 14:13 | Core | Material | Not on List | Not on List | 20 | Packs of 100 | 10.5 | 210 | Surveying Consumables | 2019-09-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23069-001025 | 23069 | 2019-09-02 14:13 | Core | Material | Not on List | Not on List | 10 | Packs of 100 | 10.5 | 105 | Surveying Consumables | 2019-09-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21988-001025 | 21988 | 2019-08-08 10:56 | Core | Material | Not on List | Not on List | 1 | Each | 515 | 515 | Miscellaneous | 2019-08-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23124-001025 | 23124 | 2019-09-03 10:24 | Section 4 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 1 | full load | 0 | 0 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-6498-00725 | 6498 | 2018-09-13 16:38 | Section 4 | Material | Not on List | Not on List | 60 | Each | 1.91 | 114.6 | Concrete Accessories | 2018-09-18 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23124-001025 | 23124 | 2019-09-03 10:24 | Section 4 | Material | Not on List | Not on List | 1 | no. | NULL | 0 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23129-001025 | 23129 | 2019-09-03 11:51 | Core | Material | Not on List | Not on List | 6 | boxes | 16.89 | 101 | Miscellaneous | 2019-09-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22217-001025 | 22217 | 2019-08-13 12:01 | Section 4 | Material | Not on List | Not on List | 12 | Each | 848.6 | 10183.2 | Concrete Accessories | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22217-001025 | 22217 | 2019-08-13 12:01 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1016.89 | 1016.89 | Concrete Accessories | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22217-001025 | 22217 | 2019-08-13 12:01 | Section 4 | Material | Not on List | Not on List | 1 | Each | 204.64 | 204.64 | Concrete Accessories | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22217-001025 | 22217 | 2019-08-13 12:01 | Section 4 | Material | Not on List | Not on List | 1 | Each | 79.02 | 79.02 | Concrete Accessories | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22217-001025 | 22217 | 2019-08-13 12:01 | Section 4 | Material | NULL | Not on List | 1 | Each | 50 | 50 | Concrete Accessories | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22508-001025 | 22508 | 2019-08-20 07:44 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20982-001025 | 20982 | 2019-07-18 09:59 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6498-00725 | 6498 | 2018-09-13 16:38 | Section 4 | Material | Not on List | Not on List | 60 | Each | 0.61 | 36.6 | Concrete Accessories | 2018-09-18 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22346-001025 | 22346 | 2019-08-15 15:31 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22976-001025 | 22976 | 2019-08-30 07:45 | Section 4 | Material | Not on List | Not on List | 5 | Each | 13.95 | 69.75 | Builders Merchants (General) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22976-001025 | 22976 | 2019-08-30 07:45 | Section 4 | Material | Not on List | Not on List | 4 | Each | 13.95 | 55.8 | Builders Merchants (General) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22976-001025 | 22976 | 2019-08-30 07:45 | Section 4 | Material | Not on List | Not on List | 4 | Each | 13.95 | 55.8 | Builders Merchants (General) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23126-001025 | 23126 | 2019-09-03 10:27 | Section 5 | Material | Not on List | NULL | 12 | PK (25) | 27.5 | 330 | Miscellaneous | 2019-09-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23118-001025 | 23118 | 2019-09-03 09:29 | Section 5 | Material | Saint Gobain Castings | 600x600x150 V Shaped Aquamax (376797) | 12 | Each | 114 | 1368 | Concrete Drainage | 2019-09-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23153-001025 | 23153 | 2019-09-03 16:33 | Section 4 | Material | Not on List | Not on List | 250 | each | NULL | 0 | Miscellaneous | 2019-09-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23153-001025 | 23153 | 2019-09-03 16:33 | Section 4 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-09-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-6498-00725 | 6498 | 2018-09-13 16:38 | Section 4 | Material | Not on List | Not on List | 36 | Each | 9.78 | 352.08 | Concrete Accessories | 2018-09-18 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23103-001025 | 23103 | 2019-09-03 06:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Small Tools (Consumables) | 2019-09-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22646-001025 | 22646 | 2019-08-22 07:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 18087.27 | 18087.27 | Fuel | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21299-001025 | 21299 | 2019-07-24 17:53 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6498-00725 | 6498 | 2018-09-13 16:38 | Section 4 | Material | Not on List | Not on List | 120 | Each | 1.75 | 210 | Timber Products | 2018-09-18 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23191-001025 | 23191 | 2019-09-04 12:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23192-001025 | 23192 | 2019-09-04 12:12 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23198-001025 | 23198 | 2019-09-04 12:41 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Surveying Consumables | 2019-09-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23200-001025 | 23200 | 2019-09-04 12:42 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23023-001025 | 23023 | 2019-09-02 06:51 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 84 | Each | 3.03 | 254.52 | Small Tools (Consumables) | 2019-09-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23023-001025 | 23023 | 2019-09-02 06:51 | Section 4 | Material | PPE, Small Tools and Consumables | NULL | 84 | Each | 3.03 | 254.52 | Small Tools (Consumables) | 2019-09-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23167-001025 | 23167 | 2019-09-04 07:26 | Section 4 | Material | Not on List | Not on List | 30000 | Ltrs | 0.6 | 18000 | Fuel | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6553-00744 | 6553 | 2018-09-14 14:11 | Section 4 | Material | Not on List | Not on List | 75 | Each | 2.18 | 163.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23181-001025 | 23181 | 2019-09-04 09:34 | Section 4 | Material | Not on List | Not on List | 1040 | Hours | 21.61 | 22474.4 | Professional Services | 2019-09-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22533-001025 | 22533 | 2019-08-20 15:00 | Section 4 | Material | Not on List | Not on List | 1 | Each | 372.8 | 372.8 | Fuel | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22951-001025 | 22951 | 2019-08-29 14:18 | Section 4 | Material | Not on List | Not on List | 130 | Each | 8.95 | 1163.5 | Concrete Accessories | 2019-09-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22913-001025 | 22913 | 2019-08-29 07:50 | Section 3 | Material | Not on List | Not on List | 3 | No | 352.89 | 1058.67 | Builders Merchants (General) | 2019-08-29 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6553-00744 | 6553 | 2018-09-14 14:11 | Section 4 | Material | Not on List | Not on List | 6 | Each | 5.84 | 35.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23235-001025 | 23235 | 2019-09-05 06:55 | Core | Material | PPE, Small Tools and Consumables | Not on List | 32 | NULL | 28.8 | 922 | PPE | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Buyers
MREQ-21243-001025 | 21243 | 2019-07-24 09:44 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22585-001025 | 22585 | 2019-08-21 08:43 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23238-001025 | 23238 | 2019-09-05 07:53 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23242-001025 | 23242 | 2019-09-05 08:40 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23183-001025 | 23183 | 2019-09-04 09:58 | Section 6 | Material | Not on List | Not on List | 5 | NULL | 80 | 400 | Waste (Recycling) | 2019-09-04 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6575-00749 | 6575 | 2018-09-17 09:24 | Section 4 | Material | Not on List | Not on List | 240 | KG | 2.87 | 688.8 | Concrete Accessories | 2018-09-19 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23244-001025 | 23244 | 2019-09-05 09:09 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23186-001025 | 23186 | 2019-09-04 11:23 | Core | Material | NULL | NULL | 1 | Each | 1119.2 | 1119.2 | NULL | NULL | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23254-001025 | 23254 | 2019-09-05 08:38 | Section 6 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Miscellaneous | 2019-09-09 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23254-001025 | 23254 | 2019-09-05 08:38 | Section 6 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Miscellaneous | 2019-09-09 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23098-001025 | 23098 | 2019-09-02 17:24 | Section 4 | Material | NULL | NULL | 500 | meters | NULL | 0 | Miscellaneous | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23190-001025 | 23190 | 2019-09-04 11:48 | Core | Material | NULL | NULL | 2 | Each | 69.83 | 139.66 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6594-00749 | 6594 | 2018-09-17 13:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.18 | 143.6 | Builders Merchants (General) | 2018-09-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23241-001025 | 23241 | 2019-09-05 08:26 | Section 5 | Material | Not on List | Not on List | 30 | EA | 10.06 | 301.8 | Builders Merchants (General) | 2019-09-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23149-001025 | 23149 | 2019-09-03 16:20 | Section 4 | Material | NULL | NULL | 5 | Each | 33.55 | 167.75 | Builders Merchants (General) | 2019-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22621-001025 | 22621 | 2019-08-21 15:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 73.07 | 146.14 | Miscellaneous | 2019-08-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23201-001025 | 23201 | 2019-09-04 13:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 500.29 | 500.29 | Miscellaneous | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23236-001025 | 23236 | 2019-09-05 07:42 | Section 4 | Material | Not on List | Not on List | 1 | Each | 570.39 | 570.39 | Miscellaneous | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23057-001025 | 23057 | 2019-09-02 11:57 | Section 3 | Material | Not on List | Not on List | 1 | EA | 1910 | 1910 | Miscellaneous | 2019-09-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5138-0066 | 5138 | 2018-08-15 11:27 | Section 3 | Material | Not on List | NULL | 37 | no | 13.9 | 514.3 | Builders Merchants (General) | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15165-001025 | 15165 | 2019-04-02 16:56 | Section 2 | Material | NULL | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 9 | Each | 166.43 | 1497.87 | Plastic Drainage | 2019-04-04 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15102-001025 | 15102 | 2019-04-02 09:39 | Section 2 | Material | Not on List | Not on List | 1 | 20 x 700 rolls | 756.25 | 756 | Office Supplies | 2019-04-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 603 - Processing | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15252-001025 | 15252 | 2019-04-04 06:45 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-04-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1801 - Structural Steelwork | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-15209-001025 | 15209 | 2019-04-03 12:44 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15267-001025 | 15267 | 2019-04-04 08:52 | Core | Material | Not on List | Not on List | 1 | each | 10665 | 10665 | Professional Services | 2019-04-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 153 - Temporary Works | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-15275-001025 | 15275 | 2019-04-04 10:03 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-05 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S1 Buyers
MREQ-15190-001025 | 15190 | 2019-04-03 08:46 | Section 4 | Material | NULL | NULL | 32 | NULL | 6.9 | 220.8 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14873-001025 | 14873 | 2019-03-28 11:41 | Section 4 | Material | Not on List | Not on List | 250 | NULL | 4.42 | 1105 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15285-001025 | 15285 | 2019-04-04 11:11 | Section 4 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BES4 - Existing Structures | 1601 - Piling and attendances | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15207-001025 | 15207 | 2019-04-03 12:25 | Core | Material | Not on List | Not on List | 126 | Each | 16.68 | 2101.68 | Miscellaneous | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15138-001025 | 15138 | 2019-04-02 14:34 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1727.5 | 1727.5 | PPE | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5871-00558 | 5871 | 2018-08-31 14:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 72 | Each | 6.29 | 452.88 | Miscellaneous | 2018-09-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15289-001025 | 15289 | 2019-04-04 12:05 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15142-001025 | 15142 | 2019-04-02 14:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Small Tools (Consumables) | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15142-001025 | 15142 | 2019-04-02 14:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4000 | Each | 0.37 | 1480 | Miscellaneous | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15146-001025 | 15146 | 2019-04-02 15:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 5.8 | 46.4 | Small Tools (Consumables) | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15146-001025 | 15146 | 2019-04-02 15:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 5.82 | 46.56 | Small Tools (Consumables) | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15146-001025 | 15146 | 2019-04-02 15:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 32 | Each | 1.91 | 61.12 | Small Tools (Consumables) | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15299-001025 | 15299 | 2019-04-04 14:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 301.88 | 302 | PPE | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15148-001025 | 15148 | 2019-04-02 15:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 203.22 | 203.22 | PPE | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5852-00545 | 5852 | 2018-08-31 10:57 | Section 4 | Material | Not on List | Not on List | 4 | 1t Bag | 32.74 | 130.96 | Concrete Drainage | 2018-09-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14765-001025 | 14765 | 2019-03-27 12:56 | Section 5 | Material | Not on List | Not on List | 36 | No | 43.65 | 1571.4 | Concrete Drainage | 2019-04-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14765-001025 | 14765 | 2019-03-27 12:56 | Section 5 | Material | Not on List | Not on List | 8 | No | 53 | 424 | Concrete Drainage | 2019-04-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15269-001025 | 15269 | 2019-04-04 09:20 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15256-001025 | 15256 | 2019-04-04 07:56 | Section 4 | Material | Not on List | Not on List | 250 | Each | 0.98 | 245 | Miscellaneous | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15273-001025 | 15273 | 2019-04-04 09:47 | Section 4 | Material | Not on List | Not on List | 500000 | Each | 1 | 500000 | Gas Oil | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15334-001025 | 15334 | 2019-04-05 06:49 | Section 2 | Material | Not on List | Not on List | 20 | rolls | NULL | 0 | Concrete Accessories | 2019-04-07 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14848-001025 | 14848 | 2019-03-28 10:00 | Section 4 | Material | Signage | Not on List | 200 | Each | 6.9 | 1380 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14848-001025 | 14848 | 2019-03-28 10:00 | Section 4 | Material | Signage | Not on List | 25 | Rolls | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14848-001025 | 14848 | 2019-03-28 10:00 | Section 4 | Material | Signage | Not on List | 25 | Each | 2.15 | 53.75 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14848-001025 | 14848 | 2019-03-28 10:00 | Section 4 | Material | Signage | Not on List | 40 | Pack 100 | 9 | 360 | Surveying Consumables | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15296-001025 | 15296 | 2019-04-04 13:42 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2061.98 | 2061.98 | Miscellaneous | 2019-04-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Insulation White Pvc 33m X 19mm Contractor (230006) | 15 | Each | 0.86 | 13 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Insulation Red Pvc 33m X 19mm Contractor (230007) | 15 | Each | 0.86 | 13 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Insulation Blue Pvc 33m X 19mm Contractor (230008) | 15 | Each | 0.86 | 13 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Insulation Yellow Pvc 33m X 19mm Contractor (230009) | 15 | Each | 0.86 | 13 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Insulation Black Pvc 33m X 19mm Contractor (230015) | 15 | Each | 0.86 | 13 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Rake Asphalt/Tarmac Flat Tooth Metal Handle Spartan Pro (762583) | 10 | Each | 17.28 | 173 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Sign 5mph Rigid Plastic Ref 1 7501 (249727) | 40 | Each | 17 | 680 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Hammer Club C/W Fibreglass Handle Spartan Pro 1.1kg(2.5lb) (724107) | 20 | Each | 8.98 | 180 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | DE-ICER CLEANLINE WINDSCREEN 400ML AEROSOL (710091) | 20 | Each | 2.43 | 49 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 55 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Helmet Attachment-jsp Navy Blue Helmet Warmer (271301) | 15 | Each | 5.43 | 81 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 5mtr/1 (765565) | 10 | Each | 2.7 | 27 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 7.5mtr/2 (765566) | 10 | Each | 5.77 | 58 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 10mtr/3 (765567) | 10 | Each | 12.4 | 124 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Paint Roller And Tray Set 9" Rskit1 (704256) | 10 | Each | 3.42 | 34 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Filler Foam Expanding Hansil Contractor 750ml (546678) | 20 | Each | 3.17 | 63 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15250-001025 | 15250 | 2019-04-04 06:33 | Section 4 | Material | Not on List | Not on List | 1 | Each | 310.06 | 310.06 | Miscellaneous | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15250-001025 | 15250 | 2019-04-04 06:33 | Section 4 | Material | Not on List | Not on List | 1 | Each | 561.72 | 561.72 | Miscellaneous | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15161-001025 | 15161 | 2019-04-02 16:30 | Section 4 | Material | Not on List | Not on List | 2 | Each | 72 | 144 | Surveying Consumables | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15161-001025 | 15161 | 2019-04-02 16:30 | Section 4 | Material | Not on List | Not on List | 2 | Each | 128 | 256 | Surveying Consumables | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15357-001025 | 15357 | 2019-04-05 10:16 | Section 2 | Material | Twinwall | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2019-04-08 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15357-001025 | 15357 | 2019-04-05 10:16 | Section 2 | Material | Concrete Drainage | Not on List | 8 | NULL | NULL | 0 | Plastic Drainage | 2019-04-08 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15094-001025 | 15094 | 2019-04-02 08:54 | Section 4 | Material | Not on List | Not on List | 3 | Each | 221.85 | 665.55 | Blocks and Bricks | 2019-04-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15094-001025 | 15094 | 2019-04-02 08:54 | Section 4 | Material | Not on List | Not on List | 9 | Each | 221.85 | 1996.65 | Blocks and Bricks | 2019-04-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5985-00586 | 5985 | 2018-09-04 07:16 | Section 3 | Material | Not on List | Not on List | 1 | no | 1920 | 1920 | Aggregate | 2018-09-05 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15094-001025 | 15094 | 2019-04-02 08:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 176.09 | 176.09 | Blocks and Bricks | 2019-04-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15094-001025 | 15094 | 2019-04-02 08:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 274.1 | 274.1 | Blocks and Bricks | 2019-04-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15200-001025 | 15200 | 2019-04-03 10:30 | Section 3 | Material | Not on List | Not on List | 1 | ea | 2542.17 | 2542.17 | Miscellaneous | 2019-04-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15378-001025 | 15378 | 2019-04-05 11:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 186 | 186 | PPE | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15378-001025 | 15378 | 2019-04-05 11:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 302 | 302 | PPE | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15120-001025 | 15120 | 2019-04-02 12:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 497.86 | 497.86 | Miscellaneous | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15230-001025 | 15230 | 2019-04-03 14:37 | Core | Material | Not on List | Not on List | 250 | number | 0.95 | 237.5 | Surveying Consumables | 2019-04-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5989-00588 | 5989 | 2018-09-04 08:52 | Section 3 | Material | Misc | Not on List | 4 | rolls | 11.01 | 44.04 | Builders Merchants (General) | 2018-09-07 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15230-001025 | 15230 | 2019-04-03 14:37 | Core | Material | Not on List | Not on List | 250 | number | 0.56 | 140 | Surveying Consumables | 2019-04-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15435-001025 | 15435 | 2019-04-08 08:43 | Section 2 | Material | Not on List | Not on List | 2 | Number | NULL | 0 | Surveying Consumables | 2019-04-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-15395-001025 | 15395 | 2019-04-05 14:34 | Section 3 | Material | Not on List | Not on List | 13 | No. | 5.34 | 69.42 | Plastic Drainage | 2019-04-08 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15338-001025 | 15338 | 2019-04-05 07:46 | Core | Material | Not on List | Not on List | 1 | Pack 1000 & Deliver | 198 | 198 | Office Supplies | 2019-04-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5988-00587 | 5988 | 2018-09-04 09:02 | Section 3 | Material | Not on List | Not on List | 4 | Cases | 68.74 | 274.96 | Miscellaneous | 2018-09-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15309-001025 | 15309 | 2019-04-04 15:52 | Core | Material | Not on List | Not on List | 11 | NULL | 5.25 | 57.75 | Office Supplies | 2019-04-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15309-001025 | 15309 | 2019-04-04 15:52 | Core | Material | Not on List | Not on List | 2 | NULL | 5.95 | 11.9 | Office Supplies | 2019-04-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15309-001025 | 15309 | 2019-04-04 15:52 | Core | Material | Not on List | Not on List | 1 | NULL | 9.95 | 9.95 | Office Supplies | 2019-04-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15315-001025 | 15315 | 2019-04-04 16:47 | Core | Material | Not on List | Not on List | 1 | Each | 850 | 850 | Training | 2019-05-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15452-001025 | 15452 | 2019-04-08 12:56 | Section 4 | Material | Not on List | Not on List | 100 | Each | 7.5 | 750 | Surveying Consumables | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15307-001025 | 15307 | 2019-04-04 15:45 | Section 2 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 960 | Metres | 1.5 | 1440 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15454-001025 | 15454 | 2019-04-08 13:08 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-04-09 | RVP 403 - 1339621 - Borrow Pit 5 A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15455-001025 | 15455 | 2019-04-08 13:14 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-04-09 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15312-001025 | 15312 | 2019-04-04 16:21 | Section 4 | Material | Not on List | Not on List | 5 | Each | 9.84 | 49.2 | Builders Merchants (General) | 2019-04-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15312-001025 | 15312 | 2019-04-04 16:21 | Section 4 | Material | Not on List | Not on List | 20 | sheet | 24.28 | 485.6 | Builders Merchants (General) | 2019-04-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15465-001025 | 15465 | 2019-04-08 14:02 | Core | Material | Not on List | Not on List | 1 | each | 200 | 200 | Training | 2019-05-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15478-001025 | 15478 | 2019-04-08 16:22 | Core | Material | Not on List | Not on List | 1 | NULL | 2322 | 2322 | Laboratory Equipment / Certification | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 50 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 1500 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 1500 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 1500 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15460-001025 | 15460 | 2019-04-08 13:46 | Section 2 | Material | Not on List | Not on List | 11.292 | tonnes | NULL | 0 | NULL | 2019-04-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15514-001025 | 15514 | 2019-04-09 09:56 | Core | Material | Not on List | Not on List | 1 | number | 12.99 | 13 | Miscellaneous | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15514-001025 | 15514 | 2019-04-09 09:56 | Core | Material | Not on List | Not on List | 1 | number | 41.19 | 41 | Miscellaneous | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15523-001025 | 15523 | 2019-04-09 10:48 | Section 2 | Material | Aggregate | Not on List | 1 | each | 56 | 56 | Aggregate | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15453-001025 | 15453 | 2019-04-08 11:00 | Core | Material | Not on List | Not on List | 1 | ea | 5972.37 | 5972.37 | Training | 2019-04-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15461-001025 | 15461 | 2019-04-08 13:27 | Core | Material | Not on List | Not on List | 1 | ea | 3250 | 3250 | Training | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15531-001025 | 15531 | 2019-04-09 12:39 | Section 2 | Material | Not on List | Not on List | 100 | pegs | NULL | 0 | Surveying Consumables | 2019-04-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15531-001025 | 15531 | 2019-04-09 12:39 | Section 2 | Material | Not on List | Not on List | 100 | boards | NULL | 0 | Surveying Consumables | 2019-04-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15506-001025 | 15506 | 2019-04-09 08:33 | Section 2 | Material | NULL | Not on List | 6 | BOXES | NULL | 0 | Blocks and Bricks | 2019-04-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15506-001025 | 15506 | 2019-04-09 08:33 | Section 2 | Material | NULL | Not on List | 4 | BOXES | NULL | 0 | Blocks and Bricks | 2019-04-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15178-001025 | 15178 | 2019-04-02 17:27 | Section 5 | Material | Not on List | Not on List | 100 | EACH | 19.8 | 1980 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15222-001025 | 15222 | 2019-04-03 15:41 | Core | Material | Not on List | Not on List | 1 | NULL | 135.66 | 136 | Office Supplies | 2019-04-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | NULL | 114 - Office Furniture | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6007-00591 | 6007 | 2018-09-04 14:23 | Section 3 | Material | Not on List | Not on List | 4 | no | 439 | 1756 | Not Sure | 2018-09-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15521-001025 | 15521 | 2019-04-09 10:40 | Section 2 | Material | Aggregate | Not on List | 1 | each | 1500 | 1500 | Aggregate | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15457-001025 | 15457 | 2019-04-08 13:19 | Section 4 | Material | Waste Management | Plastic - Roll On Roll Off 40 cubic yard | 1 | Each | 360 | 360 | Waste (Recycling) | 2019-04-09 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15451-001025 | 15451 | 2019-04-08 12:52 | Section 2 | Material | NULL | Not on List | 26 | m | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14545-001025 | 14545 | 2019-03-22 14:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 26.25 | 525 | Builders Merchants (General) | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 201 - Site Clearance | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-15467-001025 | 15467 | 2019-04-08 14:58 | Section 3 | Material | Not on List | Not on List | 45 | rolls | NULL | 0 | Builders Merchants (General) | 2019-04-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6007-00591 | 6007 | 2018-09-04 14:23 | Section 3 | Material | Not on List | Not on List | 2 | no | 95 | 190 | Not Sure | 2018-09-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15430-001025 | 15430 | 2019-04-08 08:11 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 6 | Each | 12.39 | 74.34 | Builders Merchants (General) | 2019-04-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15430-001025 | 15430 | 2019-04-08 08:11 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 7 | Each | 12.39 | 86.73 | Builders Merchants (General) | 2019-04-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15533-001025 | 15533 | 2019-04-09 13:00 | Section 4 | Material | Waste Management | Plastic - Roll On Roll Off 40 cubic yard | 1 | Each | 360 | 360 | Waste (Recycling) | 2019-04-10 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6007-00591 | 6007 | 2018-09-04 14:23 | Section 3 | Material | Not on List | Not on List | 1 | no | 95 | 95 | Not Sure | 2018-09-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15525-001025 | 15525 | 2019-04-09 11:41 | Section 4 | Material | Not on List | Not on List | 30 | Sheets | 13.5 | 405 | Builders Merchants (General) | 2019-04-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15599-001025 | 15599 | 2019-04-10 11:21 | Section 2 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 40 | Each | 81.73 | 3269 | Builders Merchants (General) | 2019-04-15 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15599-001025 | 15599 | 2019-04-10 11:21 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142 | Builders Merchants (General) | 2019-04-15 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15599-001025 | 15599 | 2019-04-10 11:21 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 30 | Each | 35.52 | 1066 | Concrete Drainage | 2019-04-15 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15599-001025 | 15599 | 2019-04-10 11:21 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 5 | Each | 36.62 | 183 | Concrete Drainage | 2019-04-15 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15162-001025 | 15162 | 2019-04-02 16:30 | Section 2 | Material | Saint Gobain Castings | Not on List | 2 | No. | NULL | 0 | Miscellaneous | 2019-04-09 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | NULL | Not on List | 80 | No | 11.05 | 884 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | NULL | Not on List | 1 | No | 25.5 | 25.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5601-00400 | 5601 | 2018-08-23 20:40 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | NULL | Not on List | 1 | No | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13165-001025 | 13165 | 2019-02-27 10:37 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Electrical | 2019-03-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13165-001025 | 13165 | 2019-02-27 10:37 | Section 2 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Electrical | 2019-03-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13167-001025 | 13167 | 2019-02-27 11:09 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-04 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-13167-001025 | 13167 | 2019-02-27 11:09 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-04 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-13186-001025 | 13186 | 2019-02-27 14:57 | Section 2 | Material | Waste Management | Clinical Waste - 4 Litre Sharps Disposal Unit (4 Collections Per Annum) | 11 | Each | 500 | 5500 | Waste (General) | 2019-02-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13096-001025 | 13096 | 2019-02-26 10:06 | Section 4 | Material | Not on List | Not on List | 1 | unit | 2589.47 | 2589.47 | Miscellaneous | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5601-00400 | 5601 | 2018-08-23 20:40 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13196-001025 | 13196 | 2019-02-27 17:21 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 80 | Each | 3.56 | 285 | Builders Merchants (General) | 2019-03-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13196-001025 | 13196 | 2019-02-27 17:21 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 30 | Each | 10.5 | 315 | Plastic Drainage | 2019-03-04 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5601-00400 | 5601 | 2018-08-23 20:40 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13220-001025 | 13220 | 2019-02-28 09:16 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12720-001025 | 12720 | 2019-02-19 15:39 | Section 4 | Material | Not on List | Not on List | 200 | Each | 2.18 | 436 | Miscellaneous | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13082-001025 | 13082 | 2019-02-26 08:19 | Section 4 | Material | Not on List | Not on List | 400 | 25m Pack | 12.8 | 5120 | Miscellaneous | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12495-001025 | 12495 | 2019-02-14 15:23 | Section 4 | Material | Signage | Not on List | 12 | EA | 9.58 | 114.96 | Miscellaneous | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13238-001025 | 13238 | 2019-02-28 11:25 | Core | Material | Not on List | Not on List | 1 | ea | 104 | 104 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5601-00400 | 5601 | 2018-08-23 20:40 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 5 | No. | 120.62 | 603.1 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 45 | No. | 34.82 | 1566.9 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 57 | No. | 6.54 | 372.78 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 4 | No. | 17.45 | 69.8 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 16 | No. | 9.04 | 144.64 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 114 | No. | 2.75 | 313.5 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 2 | NULL | 145 | 290 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13110-001025 | 13110 | 2019-02-26 13:05 | Section 4 | Material | Not on List | Not on List | 10 | Each | 258.35 | 2583.5 | Miscellaneous | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12790-001025 | 12790 | 2019-02-20 16:16 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-13256-001025 | 13256 | 2019-02-28 13:06 | Section 6 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Fixings and Fasteners | 2019-02-04 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 105 - Site Security | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 25 | NULL | 2.92 | 73 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13163-001025 | 13163 | 2019-02-27 09:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 481.18 | each | 1 | 481.18 | Small Tools (Consumables) | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13183-001025 | 13183 | 2019-02-27 14:40 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2000 | Each | 0.37 | 740 | Miscellaneous | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13101-001025 | 13101 | 2019-02-26 11:10 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 0 | 0 | PPE | 2019-03-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13250-001025 | 13250 | 2019-02-28 12:37 | Section 3 | Material | Not on List | Not on List | 60 | Ea | 2.5 | 150 | Surveying Consumables | 2019-03-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5083-0038 | 5083 | 2018-08-14 15:19 | Section 4 | Material | Not on List | NULL | 1 | tonne | 357.77 | 357.77 | Rebar and Mesh | 2018-08-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | CL4B - Structures (Culverts) 4B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 25 | NULL | 1.44 | 36 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13250-001025 | 13250 | 2019-02-28 12:37 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 88.88 | 88.88 | Small Tools (Consumables) | 2019-03-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12615-001025 | 12615 | 2019-02-18 08:58 | Core | Material | Not on List | Not on List | 6 | ea | 214.58 | 3645 | Office Supplies | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12615-001025 | 12615 | 2019-02-18 08:58 | Core | Material | Not on List | Not on List | 6 | ea | 89.17 | 3645 | Office Supplies | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13169-001025 | 13169 | 2019-02-27 11:22 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | each | 33.03 | 495.45 | Plastic Drainage | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 25 | NULL | 27.32 | 683 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13209-001025 | 13209 | 2019-02-28 07:24 | Section 4 | Material | Not on List | Not on List | 200 | Each | 2.18 | 436 | Miscellaneous | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13290-001025 | 13290 | 2019-02-28 16:45 | Core | Material | Not on List | Not on List | 1 | NULL | 345.01 | 345 | Miscellaneous | 2019-03-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-12877-001025 | 12877 | 2019-02-21 16:39 | Core | Material | Not on List | Not on List | 1 | Number | 394.8 | 394.8 | Office Supplies | 2019-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13272-001025 | 13272 | 2019-02-28 14:48 | Section 3 | Material | Aggregate | Not on List | 11500 | Ton | 4 | 46000 | Aggregate | 2019-03-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13260-001025 | 13260 | 2019-02-28 13:25 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 550.78 | 550.78 | PPE | 2019-03-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13260-001025 | 13260 | 2019-02-28 13:25 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 333.24 | 333.24 | Miscellaneous | 2019-03-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 191 | No. | 42.14 | 8048.74 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 17 | No. | 33.41 | 567.97 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 27 | No. | 30.78 | 831.06 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 25 | NULL | 5.95 | 148.75 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 9 | No. | 23.52 | 211.68 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 10 | No. | 56.84 | 568.4 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 18 | No. | 58.8 | 1058.4 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13203-001025 | 13203 | 2019-02-27 18:04 | Section 4 | Material | Aggregate | Not on List | 50 | Load | 380 | 19000 | Aggregate | 2019-03-04 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13203-001025 | 13203 | 2019-02-27 18:04 | Section 4 | Material | Aggregate | Not on List | 25 | Load | 380 | 9500 | Aggregate | 2019-03-05 | RVP 403 - 1339621 - Borrow Pit 5 A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13270-001025 | 13270 | 2019-02-28 14:34 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1863.37 | each | 1 | 1863.37 | PPE | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 50 | NULL | 22.52 | 1126 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13239-001025 | 13239 | 2019-02-28 11:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 224.88 | 224.88 | Concrete Drainage | 2019-03-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13239-001025 | 13239 | 2019-02-28 11:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 176.4 | 176.4 | Concrete Drainage | 2019-03-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13222-001025 | 13222 | 2019-02-28 09:36 | Section 4 | Material | Not on List | Not on List | 1 | ea | 1585.07 | 1585.07 | Miscellaneous | 2019-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3010 - Ground Preparation, Cultivation and Mulching | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12841-001025 | 12841 | 2019-02-21 09:56 | Core | Material | Not on List | Not on List | 2 | number | 38 | 76 | Miscellaneous | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13124-001025 | 13124 | 2019-02-26 15:34 | Section 3 | Material | Not on List | Not on List | 1 | No | NULL | 0 | NULL | 2019-03-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN08 - Corpus Christi Accommodation Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13003-001025 | 13003 | 2019-02-25 08:50 | Core | Material | Not on List | Not on List | 2 | Number | 22 | 44 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 900 | No | 35.59 | 32031 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 10 | No | 38.85 | 388.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5658-00428 | 5658 | 2018-08-24 17:16 | Section 3 | Material | Not on List | Not on List | 1 | EA | 136.86 | 136.86 | Damage Charges | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 40 | No | 39.22 | 1568.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 40 | No | 39.22 | 1568.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 140 | No | 34.93 | 4890.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 40 | No | 34.93 | 1397.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 20 | No | 4.9 | 98 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 64 | No | 5.78 | 369.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 100 | No | 11.05 | 1105 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 5 | No | 22.5 | 112.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13319-001025 | 13319 | 2019-03-01 09:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3000 | each | 0.37 | 1110 | Miscellaneous | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13319-001025 | 13319 | 2019-03-01 09:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1500 | each | 0.9 | 1350 | Surveying Consumables | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13319-001025 | 13319 | 2019-03-01 09:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | each | 2.97 | 332.64 | Miscellaneous | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13384-001025 | 13384 | 2019-03-04 09:32 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13386-001025 | 13386 | 2019-03-04 10:14 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 600 | 600 | Laboratory Equipment / Certification | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-5625 | 5625 | 2018-08-24 11:29 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 4652 | 4652 | Professional Services | 2018-08-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13335-001025 | 13335 | 2019-03-01 11:48 | Section 3 | Material | Not on List | Not on List | 100000 | NULL | 1 | 100000 | Gas Oil | 2019-03-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13335-001025 | 13335 | 2019-03-01 11:48 | Section 3 | Material | Not on List | Not on List | 7500 | NULL | 1 | 7500 | Fuel | 2019-03-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13345-001025 | 13345 | 2019-03-01 13:19 | Section 4 | Material | Not on List | Not on List | 16 | 4.5x100m Roll | 116.88 | 1870.08 | Geotextiles | 2019-03-05 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5522-00347 | 5522 | 2018-08-22 16:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 5775.5 | 5775.5 | Damage Charges | 2018-08-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13419-001025 | 13419 | 2019-03-04 14:57 | Core | Material | Not on List | Not on List | 64 | each | 28.8 | 1843 | PPE | 2019-03-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 103 - Staff | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-13425-001025 | 13425 | 2019-03-04 16:15 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 4180.8 | 4181 | Laboratory Equipment / Certification | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-13429-001025 | 13429 | 2019-03-04 16:30 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 900 | 900 | Laboratory Equipment / Certification | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-13450-001025 | 13450 | 2019-03-04 16:08 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13450-001025 | 13450 | 2019-03-04 16:08 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13460-001025 | 13460 | 2019-03-05 08:17 | Section 3 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 500 | Each | 3.04 | 1520 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13463-001025 | 13463 | 2019-03-05 09:19 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5698-00448 | 5698 | 2018-08-28 15:16 | Section 4 | Material | Aggregate | Not on List | 60 | Tonne | NULL | 0 | Blocks and Bricks | 2018-08-30 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | BN17 - Swavesey Junction | 2401 - Brickwork, Blockwork and Stonework | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13418-001025 | 13418 | 2019-03-04 15:29 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-03-04 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13399-001025 | 13399 | 2019-03-04 12:49 | Section 2 | Material | Not on List | Not on List | 4 | Boxes of 12 | 144 | 576 | Blocks and Bricks | 2019-03-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13399-001025 | 13399 | 2019-03-04 12:49 | Section 2 | Material | Not on List | Not on List | 1 | ea | 30 | 30 | Blocks and Bricks | 2019-03-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5122-0045 | 5122 | 2018-08-15 09:11 | Section 4 | Material | Not on List | NULL | 4 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Concrete Kerbs 125x255 HB External Radius (947297) | 16 | Each | 7.97 | 127.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Concrete Kerbs 125x255 HB External Radius (947297) | 16 | Each | 7.97 | 127.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 1 | Each | 7.97 | 7.97 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 1 | Each | 7.97 | 7.97 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 12.38 | 12.38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 12.38 | 12.38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13505-001025 | 13505 | 2019-03-05 14:00 | Section 5 | Material | Not on List | Not on List | 1 | as per list | NULL | 0 | Builders Merchants (General) | 2019-03-11 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13024-001025 | 13024 | 2019-02-25 11:59 | Section 5 | Material | Not on List | Not on List | 48 | kg | 2.08 | 99.84 | Builders Merchants (General) | 2019-02-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13024-001025 | 13024 | 2019-02-25 11:59 | Section 5 | Material | Not on List | Not on List | 1 | bag | 19.8 | 19.8 | Builders Merchants (General) | 2019-02-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13403-001025 | 13403 | 2019-03-04 13:35 | Section 4 | Material | Not on List | Not on List | 1 | Each | 110 | 110 | Miscellaneous | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13403-001025 | 13403 | 2019-03-04 13:35 | Section 4 | Material | Not on List | Not on List | 1 | Each | 175 | 175 | Miscellaneous | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5645-00426 | 5645 | 2018-08-24 13:34 | Section 3 | Material | Not on List | Not on List | 1 | Each | 727.4 | 727.4 | Miscellaneous | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13538-001025 | 13538 | 2019-03-06 11:09 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 2172.5 | 2173 | Miscellaneous | 2019-03-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13541-001025 | 13541 | 2019-03-06 11:18 | Section 5 | Material | Not on List | Not on List | 1 | EACH | 372 | 372 | Miscellaneous | 2019-03-06 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13390-001025 | 13390 | 2019-03-04 10:37 | Section 4 | Material | Not on List | Not on List | 1 | order | 1495.4 | 1495.4 | Miscellaneous | 2019-03-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5576-00394 | 5576 | 2018-08-23 12:11 | Section 3 | Material | Not on List | Not on List | 50 | Ea | 5.98 | 299 | Miscellaneous | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13246-001025 | 13246 | 2019-02-28 12:08 | Core | Material | Not on List | Not on List | 1 | ea | 13725 | 13725 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13246-001025 | 13246 | 2019-02-28 12:08 | Core | Material | Not on List | Not on List | 1 | ea | 3500 | 3500 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13246-001025 | 13246 | 2019-02-28 12:08 | Core | Material | Not on List | Not on List | 1 | ea | 1000 | 1000 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13246-001025 | 13246 | 2019-02-28 12:08 | Core | Material | Not on List | Not on List | 1 | ea | 8975 | 8975 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13246-001025 | 13246 | 2019-02-28 12:08 | Core | Material | Not on List | Not on List | 1 | ea | 3750 | 3750 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13562-001025 | 13562 | 2019-03-06 13:54 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-08 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S1 Buyers
MREQ-13229-001025 | 13229 | 2019-02-28 08:04 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5576-00394 | 5576 | 2018-08-23 12:11 | Section 3 | Material | Not on List | Not on List | 65 | ea | 5.98 | 388.7 | Miscellaneous | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13563-001025 | 13563 | 2019-03-06 14:05 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-03-08 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S1 Buyers
MREQ-13500-001025 | 13500 | 2019-03-05 13:42 | Section 4 | Material | Not on List | Not on List | 1 | number | 1080 | 1080 | Office Supplies | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26645-001025 | 26645 | 2019-11-15 12:36 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26284-001025 | 26284 | 2019-11-07 13:34 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | each | 26.25 | 525 | Builders Merchants (General) | 2019-11-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4C - Structures (Culverts) 4C | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26845-001025 | 26845 | 2019-11-21 12:38 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 5.3 | 27 | Miscellaneous | 2019-11-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | No - Reject | REQ - Buyers
MREQ-26845-001025 | 26845 | 2019-11-21 12:38 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | ea | 11.15 | 45 | Small Tools (Consumables) | 2019-11-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | No - Reject | REQ - Buyers
MREQ-26468-001025 | 26468 | 2019-11-12 11:09 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | each | 21.3 | 639 | Miscellaneous | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26469-001025 | 26469 | 2019-11-12 11:20 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | each | 34.65 | 34.65 | PPE | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7266-001022 | 7266 | 2018-10-02 10:09 | Section 4 | Material | Not on List | Not on List | 600 | bags | 0.12 | 72 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26817-001025 | 26817 | 2019-11-20 16:15 | Section 4 | Material | Not on List | Not on List | 25 | Each | 42.17 | 1054.25 | Plastic Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26817-001025 | 26817 | 2019-11-20 16:15 | Section 4 | Material | Not on List | Not on List | 36 | Each | 26.41 | 950.76 | Plastic Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26848-001025 | 26848 | 2019-11-21 14:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 11.63 | 116 | Small Tools (Consumables) | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26848-001025 | 26848 | 2019-11-21 14:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 11.63 | 116 | Small Tools (Consumables) | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 55 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 11 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 11 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-7291-001022 | 7291 | 2018-10-02 15:27 | Section 4 | Material | Not on List | Not on List | 550 | Each | 59.46 | 32703 | Concrete Accessories | 2018-10-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 550 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26854-001025 | 26854 | 2019-11-21 17:03 | Section 5 | Material | Not on List | Not on List | 1 | no. | NULL | 0 | Builders Merchants (General) | 2019-11-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26832-001025 | 26832 | 2019-11-21 07:14 | Section 3 | Material | Bricks/Blocks | Not on List | 675 | BNO7 WB | 0 | 0 | Blocks and Bricks | 2019-11-22 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | BN10 - A1198 Ermine Street Overbridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7309-001022 | 7309 | 2018-10-02 17:26 | Section 4 | Material | Waste Management | Construction Waste - Skip 12 cubic yard | 1 | Each | 195 | 195 | Not Sure | 2018-10-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26821-001025 | 26821 | 2019-11-20 18:55 | Section 4 | Material | Not on List | Not on List | 16 | Each | NULL | 0 | Miscellaneous | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1301 - Road Lighting Columns and Brackets | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26821-001025 | 26821 | 2019-11-20 18:55 | Section 4 | Material | Not on List | Not on List | 16 | Each | NULL | 0 | Miscellaneous | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1301 - Road Lighting Columns and Brackets | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26821-001025 | 26821 | 2019-11-20 18:55 | Section 4 | Material | Not on List | Not on List | 16 | Each | NULL | 0 | Miscellaneous | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1301 - Road Lighting Columns and Brackets | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26821-001025 | 26821 | 2019-11-20 18:55 | Section 4 | Material | Not on List | Not on List | 16 | Each | NULL | 0 | Miscellaneous | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1301 - Road Lighting Columns and Brackets | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26926-001025 | 26926 | 2019-11-25 08:01 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26899-001025 | 26899 | 2019-11-22 14:06 | Section 4 | Material | NULL | NULL | 1 | Each | 982.98 | 982.98 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26936-001025 | 26936 | 2019-11-25 09:10 | Section 6 | Material | Bagged | Sharp Sand Bulk Bag (938208) | 1 | Each | 32.74 | 33 | Builders Merchants (General) | 2019-11-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26936-001025 | 26936 | 2019-11-25 09:10 | Section 6 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 10 | Each | 3.56 | 36 | Builders Merchants (General) | 2019-11-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26822-001025 | 26822 | 2019-11-20 20:16 | Section 4 | Material | Not on List | Not on List | 160 | 25 meters | 12.8 | 2048 | Miscellaneous | 2019-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1502 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26822-001025 | 26822 | 2019-11-20 20:16 | Section 4 | Material | Not on List | Not on List | 10 | box 100 | 10.5 | 105 | Surveying Consumables | 2019-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26822-001025 | 26822 | 2019-11-20 20:16 | Section 4 | Material | Not on List | Not on List | 10 | box 100 | 10.5 | 105 | Surveying Consumables | 2019-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26702-001025 | 26702 | 2019-11-18 14:49 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 2100 x 1000 D/S (890448) | 2 | Each | 283.24 | 566.48 | Concrete Drainage | 2019-11-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26702-001025 | 26702 | 2019-11-18 14:49 | Section 6 | Material | Concrete Drainage | Not on List | 2 | Each | NULL | 0 | Concrete Drainage | 2019-11-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26702-001025 | 26702 | 2019-11-18 14:49 | Section 6 | Material | Saint Gobain Castings | Not on List | 2 | Each | NULL | 0 | Concrete Drainage | 2019-11-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26702-001025 | 26702 | 2019-11-18 14:49 | Section 6 | Material | Geotextile | Not on List | 12 | Rolls | NULL | 0 | Geotextiles | 2019-11-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26702-001025 | 26702 | 2019-11-18 14:49 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-11-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7283-001022 | 7283 | 2018-10-02 13:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 3066 | 3066 | Damage Charges | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26842-001025 | 26842 | 2019-11-21 12:02 | Section 4 | Material | Not on List | Not on List | 1000 | each | 0.98 | 980 | Surveying Consumables | 2019-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1502 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26828-001025 | 26828 | 2019-11-21 07:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1048.38 | 1048.38 | Miscellaneous | 2019-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 555 | Each | 4.59 | 2547.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 192 | Each | 3.03 | 581.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 2 | Each | 5.43 | 10.86 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 2 | Each | 5.43 | 10.86 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 2 | Each | 30 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 30 | Each | 39.22 | 1176.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 10 | Each | 36.31 | 363.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 55 | Each | 39.22 | 2157.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 11 | Each | 34.93 | 384.23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 11 | Each | 34.93 | 384.23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 10 | Each | 39.22 | 392.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 2 | Each | 28.92 | 57.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 2 | Each | 28.92 | 57.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26951-001025 | 26951 | 2019-11-25 14:17 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 201 - Site Clearance | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-26952-001025 | 26952 | 2019-11-25 14:43 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26761-001025 | 26761 | 2019-11-19 16:35 | Section 2 | Material | Timber | Not on List | 2 | NULL | NULL | 0 | Timber Products | 2019-11-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26893-001025 | 26893 | 2019-11-22 13:02 | Core | Material | Not on List | Not on List | 1 | Each | 2724 | 2724 | Miscellaneous | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26846-001025 | 26846 | 2019-11-21 13:43 | Section 2 | Material | Not on List | Not on List | 1 | each | 249.07 | 249.07 | Professional Services | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26949-001025 | 26949 | 2019-11-25 13:42 | Section 4 | Material | NULL | NULL | 1 | Each | 2810.75 | 2810.75 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26970-001025 | 26970 | 2019-11-26 08:35 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Gas Oil | 2019-11-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26980-001025 | 26980 | 2019-11-26 11:43 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26803-001025 | 26803 | 2019-11-20 11:40 | Core | Material | NULL | NULL | 100 | Pairs | 0.52 | 52 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26981-001025 | 26981 | 2019-11-26 11:51 | Core | Material | NULL | NULL | NULL | NULL | 12600 | 0 | NULL | NULL | NULL | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27022-001025 | 27022 | 2019-11-27 07:14 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26989-001025 | 26989 | 2019-11-26 13:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 646.86 | each | 1 | 646.86 | Small Tools (Consumables) | 2019-12-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27034-001025 | 27034 | 2019-11-27 10:18 | Section 5 | Material | Aggregate | Not on List | 6000 | tons | NULL | 0 | Aggregate | 2019-11-28 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 602 - Excavation (excl topsoil) | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-26735-001025 | 26735 | 2019-11-19 11:33 | Section 4 | Material | Not on List | Not on List | 3 | Each | 900 | 2700 | Miscellaneous | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27042-001025 | 27042 | 2019-11-27 12:19 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27048-001025 | 27048 | 2019-11-27 14:16 | Section 3 | Material | Not on List | Not on List | 6 | ea | 192 | 1152 | Miscellaneous | 2019-12-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 102 - Compound running costs | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 3 Buyers
MREQ-27051-001025 | 27051 | 2019-11-27 15:36 | Section 5 | Material | Not on List | Not on List | 36 | NULL | NULL | 0 | Plastic Drainage | 2019-12-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-27053-001025 | 27053 | 2019-11-27 15:29 | Section 3 | Material | Not on List | Not on List | 1 | EA | 2200 | 2200 | Miscellaneous | 2019-12-05 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-27053-001025 | 27053 | 2019-11-27 15:29 | Section 3 | Material | Not on List | Not on List | 1 | EA | 2666.6 | 2667 | Miscellaneous | 2019-12-05 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-27053-001025 | 27053 | 2019-11-27 15:29 | Section 3 | Material | Not on List | Not on List | 1 | EA | 2810.75 | 2811 | Miscellaneous | 2019-12-05 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-27053-001025 | 27053 | 2019-11-27 15:29 | Section 3 | Material | Not on List | Not on List | 1 | EA | 729.66 | 730 | Miscellaneous | 2019-12-05 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-27053-001025 | 27053 | 2019-11-27 15:29 | Section 3 | Material | Not on List | Not on List | 1 | EA | 4074.01 | 4074 | Miscellaneous | 2019-12-05 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-27086-001025 | 27086 | 2019-11-28 09:36 | Core | Material | Not on List | Not on List | 1 | ea | 6125 | 6125 | Office Supplies | 2019-12-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27086-001025 | 27086 | 2019-11-28 09:36 | Core | Material | Not on List | Not on List | 1 | ea | 1790 | 1790 | Office Supplies | 2019-12-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27087-001025 | 27087 | 2019-11-28 09:46 | Core | Material | Not on List | Not on List | 1 | ea | 5775 | 5775 | Office Supplies | 2019-12-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26937-001025 | 26937 | 2019-11-25 09:20 | Core | Material | Not on List | Not on List | 1 | Each | 6216 | 6216 | Training | 2019-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26937-001025 | 26937 | 2019-11-25 09:20 | Core | Material | Not on List | Not on List | 1 | Each | 2864.38 | 2864.38 | Training | 2019-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27013-001025 | 27013 | 2019-11-26 17:59 | Section 2 | Material | Not on List | Not on List | 2 | Unit | 3136 | 6272 | Miscellaneous | 2019-12-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27013-001025 | 27013 | 2019-11-26 17:59 | Section 2 | Material | Not on List | Not on List | 2 | Unit | 3136 | 6272 | Miscellaneous | 2019-12-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27096-001025 | 27096 | 2019-11-28 11:18 | Section 2 | Material | Concrete Drainage | Not on List | 10 | each | NULL | 0 | Concrete Drainage | 2019-11-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27096-001025 | 27096 | 2019-11-28 11:18 | Section 2 | Material | Concrete Drainage | Not on List | 4 | each | NULL | 0 | Builders Merchants (General) | 2019-11-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26993-001025 | 26993 | 2019-11-26 14:30 | Section 3 | Material | Timber | Not on List | 85.8 | mtrs | 2.86 | 245.39 | Timber Products | 2019-11-27 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN3B - Gantry structures | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26705-001025 | 26705 | 2019-11-18 16:30 | Section 3 | Material | Twinwall | Not on List | 17 | each | NULL | 0 | Plastic Drainage | 2019-11-21 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26177-001025 | 26177 | 2019-11-05 17:41 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26939-001025 | 26939 | 2019-11-25 09:58 | Section 5 | Material | Not on List | Not on List | 1 | No | 280.25 | 280.25 | Damage Charges | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26939-001025 | 26939 | 2019-11-25 09:58 | Section 5 | Material | Not on List | Not on List | 1 | No | 461.89 | 461.89 | Damage Charges | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26939-001025 | 26939 | 2019-11-25 09:58 | Section 5 | Material | Not on List | Not on List | 1 | No | 559.55 | 559.55 | Damage Charges | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26939-001025 | 26939 | 2019-11-25 09:58 | Section 5 | Material | Not on List | Not on List | 1 | No | 519.71 | 519.71 | Damage Charges | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26939-001025 | 26939 | 2019-11-25 09:58 | Section 5 | Material | Not on List | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24468-001025 | 24468 | 2019-10-01 15:48 | Core | Material | Not on List | Not on List | 50 | posters | 1 | 50 | Miscellaneous | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 115 - Medical / 1st Aid | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27101-001025 | 27101 | 2019-11-28 13:59 | Section 4 | Material | Not on List | Not on List | 2 | Each | 128.26 | 256.52 | Plastic Drainage | 2019-11-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27101-001025 | 27101 | 2019-11-28 13:59 | Section 4 | Material | NULL | Not on List | 1 | Each | 15 | 15 | Plastic Drainage | 2019-11-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26477-001025 | 26477 | 2019-11-12 12:18 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26840-001025 | 26840 | 2019-11-21 11:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 708.33 | 708.33 | Miscellaneous | 2019-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27109-001025 | 27109 | 2019-11-28 15:47 | Core | Material | Not on List | Not on List | 60 | Number | NULL | 0 | Surveying Consumables | 2019-12-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27119-001025 | 27119 | 2019-11-28 17:36 | Section 4 | Material | Not on List | Not on List | 1 | roll | NULL | 0 | Geotextiles | 2019-12-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1503 - Cables, Joints & Terminations | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-27076-001025 | 27076 | 2019-11-28 07:20 | Section 4 | Material | Not on List | Not on List | 1 | Each | 136.8 | 136.8 | Miscellaneous | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27077-001025 | 27077 | 2019-11-28 07:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 555 | 555 | Miscellaneous | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-26729-001025 | 26729 | 2019-11-19 10:02 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-27139-001025 | 27139 | 2019-11-29 12:29 | Core | Material | PPE, Small Tools and Consumables | Not on List | 933.22 | Each | 1 | 933 | Small Tools (Consumables) | 2019-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27100-001025 | 27100 | 2019-11-28 13:06 | Section 4 | Material | Aggregate | Type 1 | 36000 | Tonnes | 22.1 | 795600 | Aggregate | 2019-12-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27153-001025 | 27153 | 2019-11-29 13:49 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1739.82 | each | 1 | 1740 | PPE | 2019-12-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27156-001025 | 27156 | 2019-11-29 14:24 | Section 6 | Material | Not on List | Not on List | 1 | n/a | 38880 | 38880 | Professional Services | 2019-12-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153a - Temporary Works Viaduct - MPD | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27170-001025 | 27170 | 2019-11-29 16:07 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2019-11-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27173-001025 | 27173 | 2019-11-29 17:48 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 103 - Staff | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-27173-001025 | 27173 | 2019-11-29 17:48 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 103 - Staff | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-27180-001025 | 27180 | 2019-12-01 20:26 | Section 5 | Material | Not on List | Not on List | 130 | litres | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S5 Buyers
MREQ-27200-001025 | 27200 | 2019-12-02 12:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 131.71 | 132 | Small Tools (Consumables) | 2019-12-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27200-001025 | 27200 | 2019-12-02 12:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 640.11 | 640 | PPE | 2019-12-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27206-001025 | 27206 | 2019-12-02 14:26 | Section 5 | Material | Not on List | Not on List | 5 | ea | 5.3 | 27 | Miscellaneous | 2019-12-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27206-001025 | 27206 | 2019-12-02 14:26 | Section 5 | Material | Not on List | Not on List | 4 | ea | 11.15 | 45 | Small Tools (Consumables) | 2019-12-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27208-001025 | 27208 | 2019-12-02 14:44 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 84 | ea | 2.5 | 210 | Surveying Consumables | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27208-001025 | 27208 | 2019-12-02 14:44 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | ea | 0.6 | 18 | Small Tools (Consumables) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27208-001025 | 27208 | 2019-12-02 14:44 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 8 | ea | 36 | 288 | Small Tools (Consumables) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27222-001025 | 27222 | 2019-12-02 12:20 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27222-001025 | 27222 | 2019-12-02 12:20 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27222-001025 | 27222 | 2019-12-02 12:20 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27222-001025 | 27222 | 2019-12-02 12:20 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27232-001025 | 27232 | 2019-12-03 07:46 | Section 5 | Material | PPE, Small Tools and Consumables | Plant Nappy 1000mm X 685mm All Blue (600200) | 6 | Each | 101.96 | 612 | Miscellaneous | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 8 | Each | 61.53 | 492.24 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 314.62 | 629.24 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 211.68 | 211.68 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 784.62 | 784.62 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 4 | Each | 126.1 | 504.4 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 4 | Each | 94.57 | 378.28 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 4 | Each | 83.73 | 334.92 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 4 | Each | 106.92 | 427.68 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | NULL | Not on List | 4 | Each | 6.05 | 24.2 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | NULL | Not on List | 1 | Each | 80.7 | 80.7 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6662-00750 | 6662 | 2018-09-18 11:47 | Section 3 | Material | Concrete Drainage | Not on List | 40 | No. | 209.35 | 8374 | Concrete Drainage | 2018-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19489-001025 | 19489 | 2019-06-21 09:58 | Core | Material | Not on List | Not on List | 6 | ea | 2000 | 12000 | Office Supplies | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6165 | 6165 | 2018-09-07 08:25 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 1 | 2 | Rebar and Mesh | 2018-09-21 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-17478-001025 | 17478 | 2019-05-15 16:51 | Core | Material | Not on List | Not on List | 1 | NULL | 9060.2 | 9060.2 | Miscellaneous | 2019-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | NULL | Yes - Approve | REQ - Buyers
MREQ-19485-001025 | 19485 | 2019-06-21 09:27 | Section 5 | Material | PPE, Small Tools and Consumables | NULL | 1 | EA | 185 | 185 | NULL | 2019-06-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | No - Reject | Req - S5 Buyers
MREQ-19490-001025 | 19490 | 2019-06-21 10:01 | Core | Material | Not on List | Not on List | 1 | EA | 185 | 185 | Surveying Consumables | 2019-06-24 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5164-0087 | 5164 | 2018-08-15 13:43 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2018-08-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6860-00751 | 6860 | 2018-09-21 11:43 | Section 3 | Material | Not on List | Not on List | 1 | ea | 173.44 | 173.44 | Damage Charges | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6701-00750 | 6701 | 2018-09-19 08:33 | Section 4 | Material | Not on List | Not on List | 1 | Each | 126.96 | 126.96 | Damage Charges | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-19544-001025 | 19544 | 2019-06-21 13:54 | Core | Material | Not on List | Not on List | 2 | NULL | 410 | 820 | Professional Services | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-19229-001025 | 19229 | 2019-06-17 14:20 | Section 6 | Material | Aggregate | A20 Pipe Bed | 300 | Tonnes | 24.5 | 7350 | Concrete Drainage | 2019-06-17 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19229-001025 | 19229 | 2019-06-17 14:20 | Section 6 | Material | Aggregate | Type 1 | 200 | Tonnes | 21.65 | 4330 | Aggregate | 2019-06-17 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19229-001025 | 19229 | 2019-06-17 14:20 | Section 6 | Material | Aggregate | Type 1 | 100 | Tonnes | 21.65 | 2165 | Aggregate | 2019-06-17 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19235-001025 | 19235 | 2019-06-17 15:29 | Section 6 | Material | Aggregate | A20 Pipe Bed | 500 | Tonnes | 24.5 | 12250 | Aggregate | 2019-06-25 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19431-001025 | 19431 | 2019-06-20 12:13 | Section 6 | Material | Aggregate | Type 1 | 14000 | Tonnes | 21.65 | 303100 | Aggregate | 2019-06-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19431-001025 | 19431 | 2019-06-20 12:13 | Section 6 | Material | Aggregate | A20 Pipe Bed | 400 | Tonnes | 24.5 | 9800 | Aggregate | 2019-06-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19431-001025 | 19431 | 2019-06-20 12:13 | Section 6 | Material | Aggregate | A20 Pipe Bed | 300 | Tonnes | 24.5 | 7350 | Aggregate | 2019-06-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19431-001025 | 19431 | 2019-06-20 12:13 | Section 6 | Material | Aggregate | A20 Pipe Bed | 300 | Tonnes | 24.5 | 7350 | Aggregate | 2019-06-27 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19431-001025 | 19431 | 2019-06-20 12:13 | Section 6 | Material | Aggregate | Type 1 | 13000 | Tonnes | 21.65 | 281450 | Aggregate | 2019-06-27 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 25 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 25 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 10 | Each | 18.37 | 184 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 15 | Each | 18.37 | 276 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 20 | Each | 18.37 | 367 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 20 | Each | 18.37 | 367 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 15 | Each | 18.37 | 276 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 15 | Each | 18.37 | 276 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Short Leg Ct01-o (302033) | 5 | Each | 18.37 | 92 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Short Leg Ct01-o (302033) | 5 | Each | 18.37 | 92 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Short Leg Ct01-o (302033) | 5 | Each | 18.37 | 92 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Short Leg Ct01-o (302033) | 2 | Each | 18.37 | 37 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Short Leg Ct01-o (302033) | 2 | Each | 18.37 | 37 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5634-00425 | 5634 | 2018-08-24 11:45 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1710.3 | 1710.3 | Miscellaneous | 2018-08-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | NULL | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19585-001025 | 19585 | 2019-06-24 08:48 | Core | Material | Not on List | Not on List | 1 | 1 | 79 | 79 | Office Supplies | 2019-06-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 2 | Each | 158.75 | 317.5 | Concrete Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Pipe 2.5m (249364) | 54 | Each | 210.95 | 11391.3 | Concrete Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Rocker (890351) | 3 | Each | 253.14 | 759.42 | Concrete Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Socket (890396) | 6 | Each | 253.14 | 1518.84 | Concrete Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 15 | Each | 166.43 | 2496.45 | Plastic Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6675-00750 | 6675 | 2018-09-18 14:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 173.78 | 173.78 | Janitorial | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 3 | Each | 116.62 | 349.86 | Plastic Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6675-00750 | 6675 | 2018-09-18 14:30 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 51.59 | 51.59 | Miscellaneous | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19599-001025 | 19599 | 2019-06-24 11:05 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19600-001025 | 19600 | 2019-06-24 11:14 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19602-001025 | 19602 | 2019-06-24 11:31 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19603-001025 | 19603 | 2019-06-24 11:43 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19296-001025 | 19296 | 2019-06-18 11:01 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | NULL | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6675-00750 | 6675 | 2018-09-18 14:30 | Section 4 | Material | Not on List | Not on List | 2 | Pack 10 | 11.35 | 22.7 | Miscellaneous | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19491-001025 | 19491 | 2019-06-21 10:11 | Section 4 | Material | NULL | NULL | 60 | Each | 7.95 | 477 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-26 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 8 | Each | 61.53 | 492.24 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Not on List | Not on List | 14 | Each | 85.23 | 1193.22 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Not on List | Not on List | 5 | Each | 63.93 | 319.65 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Not on List | Not on List | 5 | Each | 55.13 | 275.65 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 33 | Each | 48.92 | 1614.36 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Not on List | Not on List | 35 | Each | 70.61 | 2471.35 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Not on List | Not on List | 11 | Each | 52.95 | 582.45 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6763-00751 | 6763 | 2018-09-20 11:03 | Section 4 | Material | Not on List | Not on List | 10 | Each | 30.24 | 302.4 | Small Tools (Consumables) | 2018-09-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1601 - Piling and attendances | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19658-001025 | 19658 | 2019-06-25 08:47 | Core | Material | Not on List | Not on List | 1 | NULL | 5.25 | 5 | Office Supplies | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19658-001025 | 19658 | 2019-06-25 08:47 | Core | Material | Not on List | Not on List | 1 | NULL | 5.25 | 5 | Office Supplies | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19658-001025 | 19658 | 2019-06-25 08:47 | Core | Material | Not on List | Not on List | 1 | NULL | 3.5 | 4 | Miscellaneous | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19231-001025 | 19231 | 2019-06-17 14:49 | Section 3 | Material | Not on List | Not on List | 320 | No | 6.22 | 1990.4 | Rebar and Mesh | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19231-001025 | 19231 | 2019-06-17 14:49 | Section 3 | Material | Not on List | Not on List | 2430 | No | 4.33 | 10521.9 | Rebar and Mesh | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19231-001025 | 19231 | 2019-06-17 14:49 | Section 3 | Material | Not on List | Not on List | 940 | No | 2.67 | 2509.8 | Rebar and Mesh | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19231-001025 | 19231 | 2019-06-17 14:49 | Section 3 | Material | Not on List | Not on List | 320 | No | 0.16 | 51.2 | Rebar and Mesh | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5164-0087 | 5164 | 2018-08-15 13:43 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Builders Merchants (General) | 2018-08-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6693-00750 | 6693 | 2018-09-18 17:39 | Section 3 | Material | Misc | Not on List | 1 | number | 173.05 | 173.05 | Miscellaneous | 2018-09-20 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19669-001025 | 19669 | 2019-06-25 09:42 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Surveying Consumables | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 110 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 110 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 110 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 700 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 700 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 700 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 105 | m | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 720 | m | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 3185 | m2 | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 30 | m2 | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 235 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 235 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19483-001025 | 19483 | 2019-06-21 09:29 | Section 4 | Material | Not on List | Not on List | 120 | 2m Length | 5 | 600 | NULL | 2019-06-25 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19678-001025 | 19678 | 2019-06-25 13:20 | Section 4 | Material | Not on List | Not on List | 1 | no | 0 | 0 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-19678-001025 | 19678 | 2019-06-25 13:20 | Section 4 | Material | Not on List | Not on List | 0 | no | 0 | 0 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-19475-001025 | 19475 | 2019-06-21 08:22 | Section 4 | Material | NULL | NULL | 12 | Each | 39.94 | 479.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19439-001025 | 19439 | 2019-06-20 14:49 | Section 4 | Material | NULL | NULL | 50 | Tubes | 4.97 | 248.5 | Concrete Drainage | 2019-06-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19685-001025 | 19685 | 2019-06-25 13:44 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 10 | Each | 5.9 | 59 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 30 | Each | 5.9 | 177 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 2 | Each | 12.39 | 24.78 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 1 | Each | 12.39 | 12.39 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 2 | Each | 12.39 | 24.78 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 1 | Each | 12.39 | 12.39 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19691-001025 | 19691 | 2019-06-25 14:50 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19692-001025 | 19692 | 2019-06-25 14:46 | Core | Material | Not on List | Not on List | 9 | NULL | 28.86 | 260 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-19693-001025 | 19693 | 2019-06-25 14:47 | Core | Material | Not on List | Not on List | 1 | NULL | 850 | 850 | Miscellaneous | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | NULL | REQ - Buyers
MREQ-19223-001025 | 19223 | 2019-06-17 13:49 | Section 3 | Material | NULL | Not on List | 20 | ea | 37.81 | 756.2 | Plastic Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19699-001025 | 19699 | 2019-06-25 15:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19700-001025 | 19700 | 2019-06-25 16:06 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19706-001025 | 19706 | 2019-06-25 16:17 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19486-001025 | 19486 | 2019-06-21 09:12 | Section 3 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 8 | Rolls | 189 | 1512 | Plastic Drainage | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19486-001025 | 19486 | 2019-06-21 09:12 | Section 3 | Material | Ducting | Not on List | 16 | Each | 40 | 640 | Electrical | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19473-001025 | 19473 | 2019-06-21 07:45 | Section 4 | Material | NULL | NULL | 127 | M2 | 19.5 | 2476.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18424-001025 | 18424 | 2019-06-03 10:44 | Section 3 | Material | Not on List | Not on List | 300 | No | 6.22 | 1866 | Builders Merchants (General) | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18424-001025 | 18424 | 2019-06-03 10:44 | Section 3 | Material | Not on List | Not on List | 200 | No | 4.33 | 866 | Builders Merchants (General) | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18424-001025 | 18424 | 2019-06-03 10:44 | Section 3 | Material | Not on List | Not on List | 100 | No | 8.9 | 890 | Builders Merchants (General) | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19732-001025 | 19732 | 2019-06-26 08:45 | Section 4 | Material | Not on List | Not on List | 803 | Kilos | NULL | 0 | Reinforcement | 2019-06-28 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 10 | Each | 44.65 | 446.5 | Concrete Drainage | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 70.99 | 709.9 | Concrete Drainage | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17348-001025 | 17348 | 2019-05-14 08:35 | Core | Material | Not on List | Not on List | 12 | Boxes | 159 | 1908 | Miscellaneous | 2019-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17351-001025 | 17351 | 2019-05-14 08:33 | Core | Material | Not on List | Not on List | 1 | ea | 12000 | 12000 | Office Supplies | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17289-001025 | 17289 | 2019-05-13 14:32 | Section 4 | Material | NULL | NULL | 1 | Roll | 364 | 364 | Geotextiles | 2019-05-22 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17466-001025 | 17466 | 2019-05-15 15:47 | Core | Material | PPE, Small Tools and Consumables | Towel Hand Pristine Z Fold 2ply White Case 3210 Sheet 66955 (539303) | 20 | Each | 26.89 | 537.8 | Office Supplies | 2019-05-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17466-001025 | 17466 | 2019-05-15 15:47 | Core | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289) | 10 | Each | 7.32 | 73.2 | Office Supplies | 2019-05-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17466-001025 | 17466 | 2019-05-15 15:47 | Core | Material | PPE, Small Tools and Consumables | Brush Paint Spartan Pro Triple Pack 1" + 2" + 3" 123 (704041) | 84 | Each | 8.96 | 752.64 | Office Supplies | 2019-05-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17815-001025 | 17815 | 2019-05-21 13:17 | Section 3 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-05-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-17710-001025 | 17710 | 2019-05-20 08:14 | Section 4 | Material | Not on List | Not on List | 13 | Each | 41.7 | 542.1 | Timber Products | 2019-05-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17710-001025 | 17710 | 2019-05-20 08:14 | Section 4 | Material | Not on List | Not on List | 5 | Each | 10.56 | 52.8 | Timber Products | 2019-05-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17710-001025 | 17710 | 2019-05-20 08:14 | Section 4 | Material | Not on List | Not on List | 10 | Each | 9.36 | 93.6 | Timber Products | 2019-05-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17710-001025 | 17710 | 2019-05-20 08:14 | Section 4 | Material | Not on List | Not on List | 50 | Each | 0.95 | 47.5 | Timber Products | 2019-05-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17599-001025 | 17599 | 2019-05-17 09:44 | Section 4 | Material | Concrete Drainage | Not on List | 3 | Each | 180.12 | 540.36 | Concrete Drainage | 2019-05-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17599-001025 | 17599 | 2019-05-17 09:44 | Section 4 | Material | Concrete Drainage | Not on List | 3 | Each | 153.46 | 460.38 | Concrete Drainage | 2019-05-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17599-001025 | 17599 | 2019-05-17 09:44 | Section 4 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 2 | Each | 195.69 | 391.38 | Concrete Drainage | 2019-05-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17599-001025 | 17599 | 2019-05-17 09:44 | Section 4 | Material | Concrete Drainage | Not on List | 2 | Each | 225.3 | 450.6 | Concrete Drainage | 2019-05-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17599-001025 | 17599 | 2019-05-17 09:44 | Section 4 | Material | Concrete Drainage | Not on List | 5 | Each | 105.52 | 527.6 | Concrete Drainage | 2019-05-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17120-001025 | 17120 | 2019-05-09 10:03 | Section 4 | Material | NULL | NULL | 80 | Each | 7.95 | 636 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17786-001025 | 17786 | 2019-05-20 12:28 | Section 3 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 189 | 1890 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17121-001025 | 17121 | 2019-05-09 11:48 | Section 4 | Material | NULL | NULL | 252 | m2 | 19.5 | 4914 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-23 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17526-001025 | 17526 | 2019-05-16 11:12 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Perf (346338) | 26 | Each | 10.66 | 277.16 | Plastic Drainage | 2019-05-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17526-001025 | 17526 | 2019-05-16 11:12 | Section 3 | Material | NULL | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 8 | Each | 166.43 | 1331.44 | Plastic Drainage | 2019-05-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 140 | Each | 58.5 | 8190 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 140 | Each | 38 | 5320 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 38 | 38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 58.5 | 58.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 65 | 65 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6417-00698 | 6417 | 2018-09-12 14:28 | Section 4 | Material | Not on List | Not on List | 1 | Each | 392.6 | 392.6 | Not Sure | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 45 | 45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 2 | Each | 500 | 1000 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 2 | Each | 650 | 1300 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 58.5 | 58.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 38 | 38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 650 | 650 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-23 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17851-001025 | 17851 | 2019-05-22 06:34 | Section 5 | Material | Not on List | Not on List | 4000 | No | NULL | 0 | Fixings and Fasteners | 2019-05-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17851-001025 | 17851 | 2019-05-22 06:34 | Section 5 | Material | Not on List | Not on List | 4000 | No | NULL | 0 | Fixings and Fasteners | 2019-05-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6417-00698 | 6417 | 2018-09-12 14:28 | Section 4 | Material | Not on List | Not on List | 1 | Each | 35 | 35 | Not Sure | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17251-001025 | 17251 | 2019-05-13 09:46 | Section 5 | Material | Not on List | Not on List | 3 | 2019-09-30 | 45 | 135 | Surveying Consumables | 2019-05-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17862-001025 | 17862 | 2019-05-22 08:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17833-001025 | 17833 | 2019-05-21 16:43 | Section 2 | Material | Not on List | Not on List | 2.3 | Tonne | NULL | 0 | Rebar and Mesh | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17871-001025 | 17871 | 2019-05-22 08:58 | Section 5 | Material | Signage | Not on List | 9 | number | 56.49 | 508 | Miscellaneous | 2019-05-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17872-001025 | 17872 | 2019-05-22 08:54 | Core | Material | Not on List | Not on List | 1 | Sum | 1000 | 1000 | Professional Services | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Buyers
MREQ-6398-00691 | 6398 | 2018-09-12 11:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | number | 13.3 | 532 | PPE | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Coverall Hivis Yellow Protal Inherent Fr Fra63 Regular Leg31 (370489) | 3 | Each | 97.85 | 294 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Coverall Hivis Yellow Protal Inherent Fr Fra63 Regular Leg31 (370489) | 3 | Each | 97.85 | 294 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Coverall Hivis Yellow Protal Inherent Fr Fra63 Regular Leg31 (370489) | 3 | Each | 97.85 | 294 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-6508-00729 | 6508 | 2018-09-13 17:34 | Section 4 | Material | Not on List | Not on List | 1 | Number | 531.2 | 531.2 | Not Sure | 2018-09-18 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 10 | Each | 8.55 | 86 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 10 | Each | 8.55 | 86 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 10 | Each | 8.55 | 86 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 10 | Each | 8.55 | 86 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Spanner/Wrench Adjustable 250mm/10" Spartan Pro (760620) | 15 | Each | 9.09 | 136 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 300 | Each | 3.04 | 912 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 75 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 75 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 39.95 | 39.95 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycottn En471cl1 Saturn Regular Ct01-y (302019) | 10 | Each | 13 | 130 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycottn En471cl1 Saturn Regular Ct01-y (302019) | 10 | Each | 13 | 130 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 19.95 | 19.95 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17726-001025 | 17726 | 2019-05-20 10:36 | Section 4 | Material | NULL | NULL | 112 | Each | 5.17 | 579.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-31 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 9.95 | 9.95 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17850-001025 | 17850 | 2019-05-22 00:52 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Number | 46.5 | 279 | Miscellaneous | 2019-05-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 3 | Each | 9.95 | 29.85 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17882-001025 | 17882 | 2019-05-22 10:52 | Core | Material | Not on List | Not on List | 1 | 250 | 752 | 752 | Miscellaneous | 2019-05-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 121 - Phones / Radios / Comms | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17448-001025 | 17448 | 2019-05-15 12:20 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-17832-001025 | 17832 | 2019-05-21 16:45 | Section 4 | Material | Not on List | Not on List | 20 | Each | 380.66 | 7613.2 | Fixings and Fasteners | 2019-05-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17449-001025 | 17449 | 2019-05-15 12:23 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 4895.2 | 4895.2 | Miscellaneous | 2019-05-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17894-001025 | 17894 | 2019-05-22 12:23 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-23 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17894-001025 | 17894 | 2019-05-22 12:23 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-23 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17894-001025 | 17894 | 2019-05-22 12:23 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-23 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17894-001025 | 17894 | 2019-05-22 12:23 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-23 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17865-001025 | 17865 | 2019-05-22 08:14 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 50 | 50 | Laboratory Equipment / Certification | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 5.79 | 5.79 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17827-001025 | 17827 | 2019-05-21 15:34 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 3115 | 3115 | Laboratory Equipment / Certification | 2019-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17899-001025 | 17899 | 2019-05-22 13:13 | Section 2 | Material | Not on List | Not on List | 25 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-17828-001025 | 17828 | 2019-05-21 16:04 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 9.34 | 140.1 | Small Tools (Consumables) | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17908-001025 | 17908 | 2019-05-22 14:23 | Section 5 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 2 | Price Per Thousand | 345 | 690 | Blocks and Bricks | 2019-05-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17908-001025 | 17908 | 2019-05-22 14:23 | Section 5 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 17.91 | 17.91 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17908-001025 | 17908 | 2019-05-22 14:23 | Section 5 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 2 | Each | 1.5 | 3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17908-001025 | 17908 | 2019-05-22 14:23 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 3 | Each | 32.74 | 98 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17908-001025 | 17908 | 2019-05-22 14:23 | Section 5 | Material | Bagged | OP Cement; 25kg bag (767201) | 1 | Each | 2.9 | 3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17910-001025 | 17910 | 2019-05-22 14:49 | Section 4 | Material | Waste Management | Construction Waste - Skip 6 cubic yard | 1 | Each | 825 | 825 | Waste (General) | 2019-05-24 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 602 - Excavation (excl topsoil) | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-17842-001025 | 17842 | 2019-05-21 17:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | Each | 2.97 | 332.64 | Small Tools (Consumables) | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17842-001025 | 17842 | 2019-05-21 17:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 33.03 | 495.45 | Small Tools (Consumables) | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17911-001025 | 17911 | 2019-05-22 15:01 | Core | Material | Not on List | Not on List | 1 | Sum | 2500 | 2500 | Miscellaneous | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 8 | Each | 50.92 | 407.36 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 22 | Each | 43.16 | 949.52 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 8 | Each | 35.52 | 284.16 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 36 | Each | 47.04 | 1693.44 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 150 | Each | 22 | 3300 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 36 | Each | 74.3 | 2674.8 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 10 | Each | 121.25 | 1212.5 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 2 | Each | 90.94 | 181.88 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 4 | Each | 80.51 | 322.04 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 6 | Each | 102.82 | 616.92 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 24 | Each | 22 | 528 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 6 | Each | 74.3 | 445.8 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10757-001025 | 10757 | 2019-01-09 12:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 4473.35 | 4473.35 | Small Tools (Consumables) | 2019-01-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 81 | Each | 34.82 | 2820.42 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 12 | Each | 10.66 | 127.92 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 9 | Each | 10.5 | 94.5 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 23 | Each | 1.84 | 42.32 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 83 | Each | 6.54 | 542.82 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 48 | Each | 0.85 | 40.8 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 164 | Each | 2.75 | 451 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 3 | Each | 7.64 | 22.92 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 5 | Each | 48.86 | 244.3 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 3 | Each | 7.64 | 22.92 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 2 | Each | 75.44 | 150.88 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 3 | Each | 44.41 | 133.23 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 3 | Each | 68.43 | 205.29 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 5 | Each | 19.72 | 98.6 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10750-001025 | 10750 | 2019-01-09 10:47 | Section 3 | Material | Not on List | Not on List | 5 | Bags | 7.65 | 38.25 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10750-001025 | 10750 | 2019-01-09 10:47 | Section 3 | Material | Not on List | Not on List | 120 | kg | 3.1 | 372 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | Not on List | 30 | ea | 209.35 | 6280.5 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 67.9 | 1018.5 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 15 | Each | 50.92 | 763.8 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 15 | Each | 43.16 | 647.4 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 5 | Each | 35.52 | 177.6 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10761-001025 | 10761 | 2019-01-09 13:06 | Section 3 | Material | Not on List | Not on List | 12 | No | 35 | 420 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10868-001025 | 10868 | 2019-01-11 10:39 | Section 4 | Material | Not on List | Not on List | 16 | Rolls | NULL | 0 | Not Sure | 2019-01-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Boot Wellington Safety Toe And Midsole Black S5 Tuf (165022) | 3 | Each | 10.95 | 32.85 | PPE | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Scraper Boot Galvanised C/W Brushes (746900) | 10 | Each | 10.19 | 101.9 | Miscellaneous | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 0.39 | 3.9 | Miscellaneous | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10890-001025 | 10890 | 2019-01-11 13:49 | Section 4 | Material | Not on List | Not on List | 1 | no | NULL | 0 | Concrete Drainage | 2019-01-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10869-001025 | 10869 | 2019-01-11 08:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 720.52 | Each | 1 | 720.52 | Janitorial | 2019-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10869-001025 | 10869 | 2019-01-11 08:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 934.38 | Each | 1 | 934.38 | Small Tools (Consumables) | 2019-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10869-001025 | 10869 | 2019-01-11 08:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1420.2 | Each | 1 | 1420.2 | PPE | 2019-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 930 | Each | 4.43 | 4120 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 15 | Each | 5.79 | 87 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 45 | Each | 5.79 | 261 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 1320 | Each | 1.45 | 1914 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Kerbs 125x150 BN External Radius (947297) | 15 | Each | 5.25 | 79 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Kerbs 125x150 BN External Radius (947297) | 15 | Each | 5.25 | 79 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Not on List | 14 | Each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Not on List | 14 | Each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10793-001025 | 10793 | 2019-01-09 16:22 | Section 3 | Material | NULL | Not on List | 1 | no | 837.68 | 837.68 | Damage Charges | 2019-01-10 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10972-001025 | 10972 | 2019-01-14 14:19 | Section 4 | Material | Not on List | Not on List | 3 | EA | NULL | 0 | Concrete Accessories | 2019-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 105 | Each | 23.14 | 2429.7 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 53 | Each | 3.38 | 179.14 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 106 | Each | 1.86 | 197.16 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 36 | Each | 38.7 | 1393.2 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 8 | Each | 39.7 | 317.6 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 3 | Each | 19.72 | 59.16 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Polypipe 150mm x 25m Ridgiflex (877588) | 4 | Each | 145 | 580 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 21 | Each | 67.9 | 1425.9 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 6 | Each | 43.16 | 258.96 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 16 | Each | 35.52 | 568.32 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 21 | Each | 47.04 | 987.84 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 50 | Each | 16.49 | 824.5 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Not on List | 10 | Each | 34 | 340 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 21 | Each | 74.3 | 1560.3 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10975-001025 | 10975 | 2019-01-14 15:03 | Section 4 | Material | Not on List | Not on List | 0.827 | tonnes | NULL | 0 | Reinforcement | 2019-02-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10976-001025 | 10976 | 2019-01-14 14:05 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2019-01-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10978-001025 | 10978 | 2019-01-14 15:40 | Section 4 | Material | Not on List | Not on List | 40 | ea | 1 | 40 | Builders Merchants (General) | 2019-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10996-001025 | 10996 | 2019-01-15 07:28 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-11000-001025 | 11000 | 2019-01-15 09:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 762 | Each | 1 | 762 | PPE | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11002-001025 | 11002 | 2019-01-15 09:23 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11008-001025 | 11008 | 2019-01-15 10:41 | Section 4 | Material | Timber | Not on List | 24 | NULL | NULL | 0 | Timber Products | 2019-01-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-10805-001025 | 10805 | 2019-01-10 08:36 | Section 3 | Material | Not on List | Not on List | 5 | T | NULL | 0 | Builders Merchants (General) | 2019-01-17 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11013-001025 | 11013 | 2019-01-15 11:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 4660.5 | 4661 | Laboratory Equipment / Certification | 2019-01-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN13 - West Brook Underbridge | 1901 - Protection of Steelwork Against Corrosion | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10616-001025 | 10616 | 2019-01-04 15:44 | Section 3 | Material | Not on List | Not on List | 1 | Each | 5 | 5 | Waste (Recycling) | 2019-01-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Staples Replacement 12mm For Staple Gun Box Of 1000 (770200) | 1 | NULL | 2.6 | 3 | Small Tools (Consumables) | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Refill Air Care Pristine Wild Berries Air Fragrance 270ml (539229) | 6 | Each | 3.1 | 19 | Janitorial | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11026-001025 | 11026 | 2019-01-15 14:18 | Section 4 | Material | Not on List | Not on List | 38 | packs | NULL | 0 | Reinforcement | 2019-01-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11026-001025 | 11026 | 2019-01-15 14:18 | Section 4 | Material | Not on List | Not on List | 30 | packs | NULL | 0 | Reinforcement | 2019-01-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11026-001025 | 11026 | 2019-01-15 14:18 | Section 4 | Material | Not on List | Not on List | 25 | packs | NULL | 0 | Reinforcement | 2019-01-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10976-001025 | 10976 | 2019-01-14 14:05 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 26.55 | 265.5 | Miscellaneous | 2019-01-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11030-001025 | 11030 | 2019-01-15 15:42 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 14.7 | 59 | Small Tools (Consumables) | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11030-001025 | 11030 | 2019-01-15 15:42 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | 0.24 | 12 | Fixings and Fasteners | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11047-001025 | 11047 | 2019-01-16 07:17 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11048-001025 | 11048 | 2019-01-16 07:44 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Pipe 2.5m (249384) | 14 | Each | 535.92 | 7503 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Rocker (249385) | 2 | Each | 643.11 | 1286 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Socket (890401) | 1 | Each | 643.11 | 643 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Spigot (890382) | 1 | Each | 643.11 | 643 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11013-001025 | 11013 | 2019-01-15 11:48 | Section 3 | Material | Not on List | Not on List | 1 | No | 4660.5 | 4660.5 | Laboratory Equipment / Certification | 2019-01-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11058-001025 | 11058 | 2019-01-16 09:36 | Core | Material | Not on List | Not on List | 1 | Cabinet and Installation | 5450 | 5450 | Professional Services | 2019-01-17 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11059-001025 | 11059 | 2019-01-16 09:54 | Section 4 | Material | Not on List | Not on List | 60 | meter | NULL | 0 | Concrete Accessories | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN24 - Girton Interchange Bridge C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11061-001025 | 11061 | 2019-01-16 10:54 | Section 4 | Material | Not on List | Not on List | 25 | number | NULL | 0 | Rebar and Mesh | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10799-001025 | 10799 | 2019-01-10 07:35 | Section 3 | Material | Not on List | Not on List | 1 | No | 8041 | 8041 | Professional Services | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11066-001025 | 11066 | 2019-01-16 12:34 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11070-001025 | 11070 | 2019-01-16 13:34 | Section 4 | Material | Bagged | Not on List | 15 | EA | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-21 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11073-001025 | 11073 | 2019-01-16 14:29 | Section 4 | Material | Not on List | Not on List | 20 | rolls | NULL | 0 | Not Sure | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10828-001025 | 10828 | 2019-01-10 12:44 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411.2 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11058-001025 | 11058 | 2019-01-16 09:36 | Core | Material | Not on List | Not on List | 1 | Cabinet and Installation | 5450 | 5450 | Professional Services | 2019-01-17 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8282 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Finance Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Pipe 2.5m (249384) | 14 | Each | 643.92 | 9014.88 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Rocker (249385) | 2 | Each | 722.86 | 1445.72 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Socket (890401) | 1 | Each | 722.86 | 722.86 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Spigot (890382) | 1 | Each | 722.86 | 722.86 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11073-001025 | 11073 | 2019-01-16 14:29 | Section 4 | Material | Not on List | Not on List | 20 | rolls | 110.27 | 2205.4 | Not Sure | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 16 | items | NULL | 0 | Fixings and Fasteners | 2019-08-05 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 180 | items | NULL | 0 | Fixings and Fasteners | 2019-08-05 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 50 | items | NULL | 0 | Fixings and Fasteners | 2019-01-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 50 | items | NULL | 0 | Fixings and Fasteners | 2019-01-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5490-00309 | 5490 | 2018-08-22 10:10 | Section 3 | Material | Plastic Drainage | Not on List | 160 | No. | 19.72 | 3155.2 | Plastic Drainage | 2019-03-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 100 | items | NULL | 0 | Fixings and Fasteners | 2019-01-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 180 | items | NULL | 0 | Fixings and Fasteners | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 148 | items | NULL | 0 | Fixings and Fasteners | 2019-02-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11061-001025 | 11061 | 2019-01-16 10:54 | Section 4 | Material | Not on List | Not on List | 25 | number | 31.36 | 784 | Rebar and Mesh | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10759-001025 | 10759 | 2019-01-09 12:47 | Section 4 | Material | Not on List | Not on List | 1 | ea | 145 | 145 | Surveying Consumables | 2019-01-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-17870-001025 | 17870 | 2019-05-22 08:52 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1139.6 | 1139.6 | PPE | 2019-05-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17913-001025 | 17913 | 2019-05-22 15:49 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Office Supplies | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 5.84 | 5.84 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 19.95 | 19.95 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6594-00749 | 6594 | 2018-09-17 13:20 | Section 4 | Material | Not on List | Not on List | 10 | Each | 8.49 | 84.9 | Builders Merchants (General) | 2018-09-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23217-001025 | 23217 | 2019-09-04 16:33 | Section 2 | Material | Saint Gobain Castings | Not on List | 3 | each | NULL | 0 | Concrete Drainage | 2019-09-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23217-001025 | 23217 | 2019-09-04 16:33 | Section 2 | Material | Combined Drainage | Not on List | 6 | each | NULL | 0 | Concrete Drainage | 2019-09-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23268-001025 | 23268 | 2019-09-05 13:49 | Section 4 | Material | NULL | NULL | 1 | Each | 5177.12 | 5177.12 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23312-001025 | 23312 | 2019-09-06 09:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23312-001025 | 23312 | 2019-09-06 09:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EA | NULL | 0 | Small Tools (Consumables) | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6597-00749 | 6597 | 2018-09-17 14:13 | Section 4 | Material | Not on List | Not on List | 30 | Each | 104.64 | 3139.2 | Plastic Drainage | 2018-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23312-001025 | 23312 | 2019-09-06 09:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EA | NULL | 0 | Small Tools (Consumables) | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23312-001025 | 23312 | 2019-09-06 09:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EA | NULL | 0 | Janitorial | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23312-001025 | 23312 | 2019-09-06 09:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | PKS | NULL | 0 | Janitorial | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23203-001025 | 23203 | 2019-09-04 12:38 | Section 3 | Material | Concrete Drainage | Not on List | 8 | No | 59 | 472 | Builders Merchants (General) | 2019-09-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23309-001025 | 23309 | 2019-09-06 08:51 | Section 5 | Material | Concrete Drainage | NULL | 1 | SM | 2907.8 | 2907.8 | Concrete Drainage | 2019-09-09 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23257-001025 | 23257 | 2019-09-05 10:41 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 3.51 | 70.2 | Small Tools (Consumables) | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23257-001025 | 23257 | 2019-09-05 10:41 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 3.86 | 77.2 | Small Tools (Consumables) | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23257-001025 | 23257 | 2019-09-05 10:41 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 4.81 | 96.2 | Small Tools (Consumables) | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23303-001025 | 23303 | 2019-09-06 06:48 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Ductile Drainage | 2019-09-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6629-00750 | 6629 | 2018-09-18 08:18 | Section 4 | Material | Not on List | Not on List | 50 | Each | 19.5 | 975 | Timber Products | 2018-09-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22061-001025 | 22061 | 2019-08-09 10:45 | Section 4 | Material | NULL | NULL | 320 | Each | 3.52 | 1126.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22061-001025 | 22061 | 2019-08-09 10:45 | Section 4 | Material | NULL | NULL | 1640 | Each | 1.5 | 2460 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22061-001025 | 22061 | 2019-08-09 10:45 | Section 4 | Material | NULL | NULL | 252 | Each | 4.13 | 1040.76 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22061-001025 | 22061 | 2019-08-09 10:45 | Section 4 | Material | NULL | NULL | 2 | Each | 30 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22061-001025 | 22061 | 2019-08-09 10:45 | Section 4 | Material | NULL | NULL | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6629-00750 | 6629 | 2018-09-18 08:18 | Section 4 | Material | Not on List | Not on List | 120 | Each | 1.2 | 144 | Timber Products | 2018-09-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23138-001025 | 23138 | 2019-09-03 13:58 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23196-001025 | 23196 | 2019-09-04 12:33 | Core | Material | NULL | NULL | 1 | Each | 738 | 738 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23323-001025 | 23323 | 2019-09-06 12:31 | Section 3 | Material | Not on List | Not on List | 500 | No | NULL | 0 | Builders Merchants (General) | 2019-09-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23187-001025 | 23187 | 2019-09-04 11:35 | Section 4 | Material | Not on List | Not on List | 10 | Each | 37.13 | 371.3 | Plastic Drainage | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23187-001025 | 23187 | 2019-09-04 11:35 | Section 4 | Material | Not on List | Not on List | 10 | Each | 60.38 | 603.8 | Plastic Drainage | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6648-00750 | 6648 | 2018-09-18 10:12 | Section 4 | Material | Not on List | Not on List | 20 | Each | 132.3 | 2646 | Builders Merchants (General) | 2018-09-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23187-001025 | 23187 | 2019-09-04 11:35 | Section 4 | Material | NULL | Not on List | 1 | Each | 15 | 15 | Plastic Drainage | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23282-001025 | 23282 | 2019-09-05 15:37 | Section 4 | Material | Ducting | Not on List | 4 | Each | 1.77 | 7.08 | Electrical | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1506 - Detector Installations | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23282-001025 | 23282 | 2019-09-05 15:37 | Section 4 | Material | NULL | Not on List | 4 | Each | 9.36 | 37.44 | Electrical | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1506 - Detector Installations | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23316-001025 | 23316 | 2019-09-06 11:17 | Section 4 | Material | Not on List | Not on List | 4 | Each | 25 | 100 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6648-00750 | 6648 | 2018-09-18 10:12 | Section 4 | Material | NULL | NULL | 1 | Each | 140 | 140 | NULL | 2018-09-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | EA | 103.08 | 206.16 | PPE | 2019-09-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | EA | 3.17 | 19.02 | Small Tools (Consumables) | 2019-09-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 24 | EA | 3.03 | 72.72 | Small Tools (Consumables) | 2019-09-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 24 | EA | 3.03 | 72.72 | Small Tools (Consumables) | 2019-09-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 50 | Each | 25.78 | 1289 | Timber Products | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | Timber | Not on List | 36 | EACH | 44.5 | 1602 | Timber Products | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 192 | LM | 6.28 | 1205.76 | Timber Products | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | Timber | Not on List | 192 | LM | 1.33 | 255.36 | Timber Products | 2019-09-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6655-00750 | 6655 | 2018-09-18 11:15 | Section 4 | Material | Not on List | Not on List | 2 | Each | 79.35 | 158.7 | Miscellaneous | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23390-001025 | 23390 | 2019-09-09 10:28 | Core | Material | Not on List | Not on List | 1 | Sum | 30000 | 30000 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 153 - Temporary Works | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-23402-001025 | 23402 | 2019-09-09 15:44 | Section 3 | Material | Not on List | Not on List | 4 | No. | 75 | 300 | Small Tools (Consumables) | 2019-09-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23320-001025 | 23320 | 2019-09-06 12:08 | Section 3 | Material | Not on List | Not on List | 4 | No | 85 | 340 | Builders Merchants (General) | 2019-09-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6664-00750 | 6664 | 2018-09-18 11:52 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2290.84 | 2290.84 | Concrete Drainage | 2018-10-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23426-001025 | 23426 | 2019-09-10 08:11 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-11 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 2701 - Accommodation works | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-23427-001025 | 23427 | 2019-09-10 08:36 | Core | Material | Not on List | Not on List | 3 | each | 10.3 | 31 | Miscellaneous | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-23427-001025 | 23427 | 2019-09-10 08:36 | Core | Material | Not on List | Not on List | 1 | each | 10.99 | 11 | Miscellaneous | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-23260-001025 | 23260 | 2019-09-05 11:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 13310 | 13310 | Miscellaneous | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23037-001025 | 23037 | 2019-09-02 09:04 | Section 4 | Material | Not on List | Not on List | 1 | Each | 12212.44 | 12212.44 | Tanks and Interceptors | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6664-00750 | 6664 | 2018-09-18 11:52 | Section 4 | Material | Not on List | Not on List | 1 | Each | 252.38 | 252.38 | Concrete Drainage | 2018-10-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23400-001025 | 23400 | 2019-09-09 15:28 | Section 2 | Material | Ducting | Not on List | 2 | No. | 10.23 | 20.46 | Electrical | 2019-09-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23400-001025 | 23400 | 2019-09-09 15:28 | Section 2 | Material | Ducting | Not on List | 2 | No. | 1.77 | 3.54 | Electrical | 2019-09-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23446-001025 | 23446 | 2019-09-10 13:24 | Section 6 | Material | Not on List | Not on List | 1 | each | 117.67 | 118 | Miscellaneous | 2019-09-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6664-00750 | 6664 | 2018-09-18 11:52 | Section 4 | Material | NULL | NULL | 1 | Each | 210 | 210 | Concrete Drainage | 2018-10-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 6 | Roll | 237 | 1422 | Geotextiles | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Geotextiles | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 2 | Roll | 465 | 930 | Geotextiles | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 2 | Roll | 207 | 414 | Geotextiles | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 1 | Box | 18 | 18 | Geotextiles | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 1 | Delivery | 100 | 100 | Miscellaneous | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23450-001025 | 23450 | 2019-09-10 14:43 | Core | Material | Not on List | Not on List | 1 | EACH | 50 | 50 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-23448-001025 | 23448 | 2019-09-10 13:00 | Section 4 | Material | Aggregate | Not on List | 20000 | Tonne | 5 | 100000 | Aggregate | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-4997-0011 | 4997 | 2018-08-13 15:45 | Section 4 | Material | Not on List | Not on List | 1 | 1 | 1 | 1 | Gas Oil | 2018-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5138-0066 | 5138 | 2018-08-15 11:27 | Section 3 | Material | Not on List | NULL | 5 | 5L Tub | 17.1 | 85.5 | Builders Merchants (General) | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 400 | Each | 16.49 | 6596 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23489-001025 | 23489 | 2019-09-11 08:15 | Section 4 | Material | Not on List | Not on List | 1 | pack | NULL | 0 | Miscellaneous | 2019-09-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | SP x BN RH Drop Kerb Direct | 14 | Each | 5.43 | 76.02 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | SP x BN RH Drop Kerb Direct | 14 | Each | 5.43 | 76.02 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | SP x BN RH Drop Kerb Direct | 5 | Each | 5.43 | 27.15 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | SP X BN LH Drop Kerb Direct | 5 | Each | 5.43 | 27.15 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | Not on List | 40 | ea | 4.59 | 183.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 30 | Each | 20 | 600 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 45 | Each | 4.59 | 206.55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 10 | Each | 10.35 | 103.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | Not on List | 40 | ea | 4.59 | 183.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23445-001025 | 23445 | 2019-09-10 13:14 | Core | Material | NULL | NULL | 1 | each | 824.94 | 824.94 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23497-001025 | 23497 | 2019-09-11 10:49 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23281-001025 | 23281 | 2019-09-05 15:15 | Core | Material | Not on List | Not on List | 1 | box | 72 | 72 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23503-001025 | 23503 | 2019-09-11 11:34 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Iron Wear | Not on List | 5 | Each | 102 | 510 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs 125x150 BN External Radius (947297) | 15 | m | 5.43 | 81.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 15 | Each | 6 | 90 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 4 | Each | 11.95 | 47.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 4 | Each | 11.95 | 47.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Drop Kerb HB x BN LH (897468) | 5 | Each | 11.95 | 59.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Drop Kerb HB x BN RH (897464) | 5 | Each | 11.95 | 59.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs 125x150 BN External Radius (947297) | 20 | Each | 5.43 | 108.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 15 | Each | 3.52 | 52.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23512-001025 | 23512 | 2019-09-11 12:38 | Section 2 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Concrete Accessories | 2019-09-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 100 | Each | 74.3 | 7430 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23394-001025 | 23394 | 2019-09-09 13:42 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 3.72 | 37.2 | Janitorial | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23442-001025 | 23442 | 2019-09-10 13:04 | Core | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | 0.83 | 83 | NULL | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23443-001025 | 23443 | 2019-09-10 13:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 64.38 | 257.52 | Miscellaneous | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 3 | Each | 29 | 87 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23318-001025 | 23318 | 2019-09-06 11:41 | Section 5 | Material | Not on List | Not on List | 20 | ea | 33.55 | 671 | Builders Merchants (General) | 2019-09-11 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23523-001025 | 23523 | 2019-09-11 14:22 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 3945.43 | 3945 | Miscellaneous | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23524-001025 | 23524 | 2019-09-11 14:26 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 3237.6 | 3238 | Miscellaneous | 2019-09-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23470-001025 | 23470 | 2019-09-10 18:06 | Section 5 | Material | Ducting | Not on List | 6 | EA | 11.05 | 66.3 | Not Sure | 2019-09-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23392-001025 | 23392 | 2019-09-09 12:27 | Core | Material | Not on List | Not on List | 1 | EA | 317 | 317 | Office Supplies | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22595-001025 | 22595 | 2019-08-21 10:09 | Core | Material | NULL | NULL | NULL | NULL | 392.75 | 0 | Miscellaneous | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23441-001025 | 23441 | 2019-09-10 12:42 | Section 3 | Material | Not on List | Not on List | 200 | ea | 4.97 | 994 | Miscellaneous | 2019-09-16 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23526-001025 | 23526 | 2019-09-11 15:32 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 50 | Each | 24.32 | 1216 | Timber Products | 2019-09-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 1 | Each | 162.27 | 162.27 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23454-001025 | 23454 | 2019-09-10 14:38 | Section 4 | Material | Aggregate | Type 1 | 10000 | Tonnes | 21.65 | 216500 | Aggregate | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23454-001025 | 23454 | 2019-09-10 14:38 | Section 4 | Material | Aggregate | 6G | 900 | Tonnes | 32.9 | 29610 | Aggregate | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23447-001025 | 23447 | 2019-09-10 13:28 | Section 5 | Material | NULL | NULL | 1 | Each | 1221.03 | 1221.03 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23553-001025 | 23553 | 2019-09-12 08:41 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-09-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-23515-001025 | 23515 | 2019-09-11 13:08 | Section 4 | Material | Not on List | Not on List | 50 | Each | 42.86 | 2143 | Miscellaneous | 2019-09-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23482-001025 | 23482 | 2019-09-11 07:47 | Core | Material | PPE, Small Tools and Consumables | Not on List | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 1 | Each | 323.4 | 323.4 | Concrete Drainage | 2018-10-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 1920 | no | 3.4 | 6528 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23528-001025 | 23528 | 2019-09-11 15:54 | Core | Material | Not on List | Not on List | 1 | SM | 1390.37 | 1390.37 | Not Sure | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23525-001025 | 23525 | 2019-09-11 15:28 | Core | Material | Not on List | Not on List | 1 | SM | 158.33 | 158.33 | Miscellaneous | 2019-09-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 160 | no | 3.4 | 544 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23491-001025 | 23491 | 2019-09-11 09:39 | Core | Material | Not on List | Not on List | 2 | EA | 95 | 190 | Laboratory Equipment / Certification | 2019-09-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23514-001025 | 23514 | 2019-09-11 12:56 | Section 6 | Material | Not on List | Not on List | 50 | load | 80 | 4000 | Waste (Recycling) | 2019-09-11 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 10 | no | 5.25 | 52.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23395-001025 | 23395 | 2019-09-09 14:00 | Section 2 | Material | Not on List | Not on List | 1 | each | 174.58 | 174.58 | Professional Services | 2019-09-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23548-001025 | 23548 | 2019-09-12 08:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 9975 | 9975 | Concrete Drainage | 2019-09-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23548-001025 | 23548 | 2019-09-12 08:07 | Section 4 | Material | NULL | Not on List | 1 | Each | 340 | 340 | Concrete Drainage | 2019-09-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5138-0066 | 5138 | 2018-08-15 11:27 | Section 3 | Material | Not on List | NULL | 30 | tubs | 61.94 | 1858.2 | Builders Merchants (General) | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8817-001024 | 8817 | 2018-11-07 10:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 546.98 | 546.98 | Janitorial | 2018-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8839-001024 | 8839 | 2018-11-07 15:38 | Section 3 | Material | Aggregate | Not on List | 300 | Te | NULL | 0 | Aggregate | 2018-11-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8839-001024 | 8839 | 2018-11-07 15:38 | Section 3 | Material | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Aggregate | 2018-11-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8839-001024 | 8839 | 2018-11-07 15:38 | Section 3 | Material | Aggregate | 6F5 | 1000 | Tonnes | 14.65 | 14650 | Aggregate | 2018-11-15 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 701 - Sub-base | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.15 | m | 1751.24 | 7268 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.15 | m | 2126.99 | 8827 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.67 | m | 1751.24 | 8178 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Concrete Drainage | Not on List | 50 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.67 | m | 2126.99 | 9933 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 8.82 | m | 314 | 2769 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 8.82 | m | 314 | 2769 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1340 | 1340 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1340 | 1340 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1100 | 1100 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1100 | 1100 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8849-001024 | 8849 | 2018-11-07 17:16 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8852-001024 | 8852 | 2018-11-07 11:34 | Section 4 | Material | Ducting | Not on List | 1 | U | NULL | 0 | Plastic Drainage | 2018-11-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8853-001024 | 8853 | 2018-11-07 17:37 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8737-001024 | 8737 | 2018-11-06 08:59 | Section 4 | Material | Concrete Drainage | Not on List | 6 | Each | 150 | 900 | Concrete Drainage | 2018-11-09 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8737-001024 | 8737 | 2018-11-06 08:59 | Section 4 | Material | NULL | Not on List | 1 | Each | 120 | 120 | Concrete Drainage | 2018-11-09 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8852-001024 | 8852 | 2018-11-07 11:34 | Section 4 | Material | NULL | Not on List | 1 | Each | 180 | 180 | Plastic Drainage | 2018-11-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8852-001024 | 8852 | 2018-11-07 11:34 | Section 4 | Material | NULL | Not on List | 1 | Each | 50 | 50 | Plastic Drainage | 2018-11-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8714-001024 | 8714 | 2018-11-05 16:38 | Section 4 | Material | Not on List | Not on List | 40 | Each | 4.3 | 172 | Builders Merchants (General) | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8837-001024 | 8837 | 2018-11-07 14:46 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 50 | Each | 48.86 | 2443 | Plastic Drainage | 2018-11-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8834-001024 | 8834 | 2018-11-07 14:22 | Section 3 | Material | Not on List | Not on List | 8 | ea | 41.74 | 333.92 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8866-001024 | 8866 | 2018-11-08 09:04 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 688 | Plastic Drainage | 2018-11-12 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8601-001023 | 8601 | 2018-11-02 06:10 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2179.8 | 2179.8 | Small Tools (Consumables) | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8829-001024 | 8829 | 2018-11-07 14:10 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1308 | 1308 | Concrete Drainage | 2018-11-07 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8694-001024 | 8694 | 2018-11-05 12:13 | Section 4 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Rebar and Mesh | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8878-001024 | 8878 | 2018-11-08 10:57 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 1395.2 | 4186 | Concrete Drainage | 2018-11-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8879-001024 | 8879 | 2018-11-08 11:07 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 1173.5 | 4694 | Concrete Drainage | 2018-11-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8676-001023 | 8676 | 2018-11-05 09:55 | Section 4 | Material | Not on List | Not on List | 10 | EA | 58 | 580 | Miscellaneous | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8676-001023 | 8676 | 2018-11-05 09:55 | Section 4 | Material | NULL | Not on List | 1 | Ea | 80 | 80 | Miscellaneous | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8882-001024 | 8882 | 2018-11-08 12:23 | Section 4 | Material | Aggregate | Not on List | 300 | ton | NULL | 0 | Aggregate | 2018-11-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | NULL | Not on List | 9 | Each | 26.09 | 234.81 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | NULL | Not on List | 10 | Each | 2.92 | 29.2 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | NULL | Not on List | 20 | Each | 1.44 | 28.8 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 11.6 | 12 | PPE | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 9.51 | 95 | Janitorial | 2018-11-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.45 | 147 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8866-001024 | 8866 | 2018-11-08 09:04 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 687.5 | Plastic Drainage | 2018-11-12 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8903-001024 | 8903 | 2018-11-08 16:35 | Section 3 | Material | Aggregate | 6G | 120 | Tonnes | 22 | 2640 | Aggregate | 2018-11-12 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | CL3B - Structures (Culverts) 3B | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8903-001024 | 8903 | 2018-11-08 16:35 | Section 3 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 15 | Each | 115.78 | 1737 | Geotextiles | 2018-11-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8904-001024 | 8904 | 2018-11-08 16:41 | Section 3 | Material | Aggregate | Not on List | 900 | m3 | 43.08 | 38772 | Aggregate | 2018-11-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8909-001024 | 8909 | 2018-11-09 01:12 | Section 3 | Material | Not on List | Not on List | 1 | Each | 67.58 | 68 | Miscellaneous | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8903-001024 | 8903 | 2018-11-08 16:35 | Section 3 | Material | Aggregate | 6G | 120 | Tonnes | 22 | 2640 | Aggregate | 2018-11-12 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8903-001024 | 8903 | 2018-11-08 16:35 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 15 | Each | 115.78 | 1736.7 | Geotextiles | 2018-11-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8904-001024 | 8904 | 2018-11-08 16:41 | Section 3 | Material | Aggregate | Not on List | 900 | m3 | 43.08 | 38772 | Aggregate | 2018-11-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8937-001024 | 8937 | 2018-11-09 13:31 | Section 4 | Material | Not on List | Not on List | 5 | boxes | NULL | 0 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8938-001024 | 8938 | 2018-11-09 13:36 | Section 4 | Material | Not on List | Not on List | 2 | boxes | NULL | 0 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8909-001024 | 8909 | 2018-11-09 01:12 | Section 3 | Material | Not on List | Not on List | 1 | Each | 67.58 | 67.58 | Miscellaneous | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8882-001024 | 8882 | 2018-11-08 12:23 | Section 4 | Material | Aggregate | Not on List | 15 | Load | 370 | 5550 | Aggregate | 2018-11-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8878-001024 | 8878 | 2018-11-08 10:57 | Section 4 | Material | Not on List | Not on List | 3 | Each | 1395.2 | 4185.6 | Concrete Drainage | 2018-11-09 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8879-001024 | 8879 | 2018-11-08 11:07 | Section 4 | Material | Not on List | Not on List | 4 | Each | 1173.5 | 4694 | Concrete Drainage | 2018-11-09 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 5 | boxes | 63 | 315 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 24 | tubes | 12 | 288 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 1 | delivery | 60 | 60 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8736-001024 | 8736 | 2018-11-06 09:00 | Section 4 | Material | Not on List | Not on List | 100 | Each | 54 | 5400 | Plastic Drainage | 2018-11-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8985-001024 | 8985 | 2018-11-12 08:46 | Section 3 | Material | Bagged | Post Mix 25kg (348099) | 60 | Each | 3.45 | 207 | Builders Merchants (General) | 2018-11-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 200 | EA | 1 | 200 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 10 | ea | 1 | 10 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 5 | ea | 1 | 5 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8985-001024 | 8985 | 2018-11-12 08:46 | Section 3 | Material | NULL | Post Mix 25kg (348099) | 60 | Each | 3.45 | 207 | Builders Merchants (General) | 2018-11-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9023-001024 | 9023 | 2018-11-12 15:05 | Section 3 | Material | Concrete Drainage | Not on List | 80 | No. | NULL | 0 | Concrete Drainage | 2018-11-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | Concrete Drainage | Not on List | 10 | Each | 31.13 | 311.3 | Concrete Drainage | 2018-11-19 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | Concrete Drainage | Not on List | 12 | Each | 31.13 | 373.56 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2018-11-19 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | NULL | Not on List | 1 | Each | 50 | 50 | Concrete Drainage | 2018-11-19 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8883-001024 | 8883 | 2018-11-08 12:42 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 16 | Each | 110.27 | 1764.32 | Geotextiles | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 604 - Deposition | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8895-001024 | 8895 | 2018-11-08 14:45 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Bags 100 | 22.05 | 66.15 | Small Tools (Consumables) | 2018-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8832-001024 | 8832 | 2018-11-07 14:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1405.35 | 1405.35 | Small Tools (Consumables) | 2018-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8830-001024 | 8830 | 2018-11-07 14:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1565.34 | 1565.34 | PPE | 2018-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.15 | m | 1751.24 | 7267.65 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.15 | m | 2126.99 | 8827.01 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.67 | m | 1751.24 | 8178.29 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.67 | m | 2126.99 | 9933.04 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 8.82 | m | 314 | 2769.48 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 8.82 | m | 314 | 2769.48 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1340 | 1340 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1340 | 1340 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1100 | 1100 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1100 | 1100 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 5 | boxes | 63 | 315 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 24 | tubes | 12 | 288 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 1 | delivery | 60 | 60 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 200 | Roll | 3.31 | 662 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 50 | Roll | 11.15 | 557.5 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 480 | Metre | 0.29 | 139.2 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5271-00173 | 5271 | 2018-08-17 07:48 | Section 4 | Material | Not on List | Not on List | 1 | ea | 869.95 | 869.95 | Rebar and Mesh | 2018-08-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8910-001024 | 8910 | 2018-11-09 07:24 | Section 4 | Material | Not on List | Not on List | 5 | Each | 86 | 430 | Miscellaneous | 2018-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9059-001024 | 9059 | 2018-11-13 08:55 | Section 3 | Material | Timber | Not on List | 300 | NULL | NULL | 0 | Miscellaneous | 2018-11-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5132-0055 | 5132 | 2018-08-15 10:09 | Section 4 | Material | Not on List | Not on List | 3 | Each | 650 | 1950 | Professional Services | 2018-10-22 | NULL | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9074-001025 | 9074 | 2018-11-13 12:06 | Section 3 | Material | Not on List | Not on List | 4 | No | NULL | 0 | Builders Merchants (General) | 2018-11-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9078-001025 | 9078 | 2018-11-13 12:54 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2018-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9023-001024 | 9023 | 2018-11-12 15:05 | Section 3 | Material | Concrete Drainage | Not on List | 80 | No. | 24 | 1920 | Concrete Drainage | 2018-11-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9078-001025 | 9078 | 2018-11-13 12:54 | Section 4 | Material | Not on List | Not on List | 2 | Each | 159 | 318 | Miscellaneous | 2018-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9091-001025 | 9091 | 2018-11-13 15:59 | Section 3 | Material | Not on List | Not on List | 28 | NULL | NULL | 0 | Miscellaneous | 2018-11-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5190-00117 | 5190 | 2018-08-16 07:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 576.16 | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9059-001024 | 9059 | 2018-11-13 08:55 | Section 3 | Material | NULL | Not on List | 300 | No | 0.95 | 285 | Miscellaneous | 2018-11-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9074-001025 | 9074 | 2018-11-13 12:06 | Section 3 | Material | Not on List | Not on List | 4 | No | 105.04 | 420.16 | Builders Merchants (General) | 2018-11-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Pipe 2.5m (249379) | 9 | Each | 483.27 | 4349 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Socket (249381) | 2 | Each | 579.92 | 1160 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 2 | Each | 579.92 | 1160 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9133-001025 | 9133 | 2018-11-14 12:05 | Section 3 | Material | Not on List | Not on List | 30 | m | NULL | 0 | Miscellaneous | 2018-11-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN06 - ECML Bridge | 1705 - Repairs to Existing Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5239-00148 | 5239 | 2018-08-16 14:33 | Section 4 | Material | Not on List | Not on List | 225 | NULL | 10.66 | 2398.5 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8849-001024 | 8849 | 2018-11-07 17:16 | Section 3 | Material | Not on List | Not on List | 1 | No | 589.18 | 589.18 | Damage Charges | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1714.02 | 1714.02 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 266 | 266 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 4 | Each | 1714.02 | 6856.08 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 4 | Each | 305 | 1220 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 2013.9 | 2013.9 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 305 | 305 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 2013.9 | 2013.9 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 305 | 305 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 1926.68 | 1926.68 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5239-00148 | 5239 | 2018-08-16 14:33 | Section 4 | Material | Not on List | Not on List | 225 | NULL | 6.65 | 1496.25 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 465 | 465 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20458-001025 | 20458 | 2019-07-09 10:00 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21465-001025 | 21465 | 2019-07-26 17:22 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2019-07-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 450Mm X 6M R-Drain Unperf + Coup | 100 | Each | 116.62 | 11662 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21488-001025 | 21488 | 2019-07-29 10:00 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Surveying Consumables | 2019-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21219-001025 | 21219 | 2019-07-23 16:32 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21481-001025 | 21481 | 2019-07-29 07:33 | Section 6 | Material | Not on List | Not on List | 2 | No. | 14965 | 29930 | Miscellaneous | 2019-09-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21477-001025 | 21477 | 2019-07-28 15:20 | Section 5 | Material | Twinwall | Not on List | 28 | No | 265.2 | 7425.6 | Plastic Drainage | 2019-08-02 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21477-001025 | 21477 | 2019-07-28 15:20 | Section 5 | Material | Twinwall | Not on List | 28 | NO | 22.36 | 626.08 | Plastic Drainage | 2019-08-02 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21500-001025 | 21500 | 2019-07-29 12:33 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Not on List | Not on List | 20 | Each | 43.16 | 863.2 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | NULL | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | NULL | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 30 | Each | 8.55 | 257 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 50 | Each | 8.55 | 428 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 50 | Each | 8.55 | 428 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Not on List | 32 | No | 15.71 | 502.72 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 450Mm Ridgidrain Seal | 100 | Each | 10.04 | 1004 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Respirator Disposable 3m 8833 Ffp3 Valved Box Of 10 (292498) | 3 | Each | 33.81 | 101 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21381-001025 | 21381 | 2019-07-25 17:15 | Section 4 | Material | Not on List | Not on List | 110 | EA | 16.83 | 1851.3 | NULL | 2019-08-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21508-001025 | 21508 | 2019-07-29 14:13 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21490-001025 | 21490 | 2019-07-29 10:58 | Section 5 | Material | Combined Drainage | Not on List | 4 | No | 96.19 | 384.76 | Plastic Drainage | 2019-07-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21511-001025 | 21511 | 2019-07-29 14:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Concrete Drainage | Cpm 1050 Slab 600X600 Access | 27 | Each | 47.04 | 1270.08 | Concrete Accessories | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21524-001025 | 21524 | 2019-07-29 16:50 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 656 | 656 | PPE | 2019-07-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21027-001025 | 21027 | 2019-07-19 08:40 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21541-001025 | 21541 | 2019-07-30 09:55 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21379-001025 | 21379 | 2019-07-25 16:45 | Section 4 | Material | Not on List | Not on List | 35 | EA | 51 | 1785 | Miscellaneous | 2019-08-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21379-001025 | 21379 | 2019-07-25 16:45 | Section 4 | Material | Not on List | Not on List | 2 | EA | 139 | 278 | Miscellaneous | 2019-08-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21379-001025 | 21379 | 2019-07-25 16:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 2202.5 | 2202.5 | Miscellaneous | 2019-08-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21379-001025 | 21379 | 2019-07-25 16:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 650 | 650 | Miscellaneous | 2019-08-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19493-001025 | 19493 | 2019-06-21 10:30 | Core | Material | Not on List | Not on List | 1 | ea | 947.85 | 948 | Office Supplies | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 500Mm X 6M R-Drain Unperf + Coup | 45 | Each | 149.45 | 6725.25 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21479-001025 | 21479 | 2019-07-29 07:30 | Section 4 | Material | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 240 | Each | 4.42 | 1060.8 | NULL | 2019-08-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21558-001025 | 21558 | 2019-07-30 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1021.63 | 1022 | Small Tools (Consumables) | 2019-08-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21499-001025 | 21499 | 2019-07-29 12:31 | Section 5 | Material | Not on List | Not on List | 1 | EA | 95 | 95 | Not Sure | 2019-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-21561-001025 | 21561 | 2019-07-30 13:45 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21568-001025 | 21568 | 2019-07-30 15:34 | Section 5 | Material | PPE, Small Tools and Consumables | Spill Kit Maintenance In Two Wheel Bin Lubetech 120 Litres (534202) | 5 | Each | 195.66 | 978 | Miscellaneous | 2019-08-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21572-001025 | 21572 | 2019-07-30 17:04 | Section 2 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 25 | Each | 10.08 | 252 | Timber Products | 2019-08-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21579-001025 | 21579 | 2019-07-31 06:45 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Accessories | 2019-08-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-21554-001025 | 21554 | 2019-07-30 12:30 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 1 | Each | 55.41 | 55.41 | Concrete Drainage | 2019-08-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Concrete Drainage | Cpm 1200X1000 C/W Steps | 10 | Each | 81.96 | 819.6 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21554-001025 | 21554 | 2019-07-30 12:30 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 1 | Each | 82.45 | 82.45 | Concrete Drainage | 2019-08-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21591-001025 | 21591 | 2019-07-31 08:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 211.44 | 211 | Small Tools (Consumables) | 2019-08-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19842-001025 | 19842 | 2019-06-27 11:33 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21615-001025 | 21615 | 2019-07-31 14:25 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | number | NULL | 0 | Small Tools (Consumables) | 2019-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1705 - Repairs to Existing Concrete | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 500Mm Ridgidrain Seal | 75 | Each | 15.19 | 1139.25 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21615-001025 | 21615 | 2019-07-31 14:25 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | number | NULL | 0 | Small Tools (Consumables) | 2019-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1705 - Repairs to Existing Concrete | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-21613-001025 | 21613 | 2019-07-31 13:59 | Section 5 | Material | PPE, Small Tools and Consumables | NULL | 1 | EA | 25.4 | 25.4 | Miscellaneous | 2019-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21613-001025 | 21613 | 2019-07-31 13:59 | Section 5 | Material | PPE, Small Tools and Consumables | NULL | 2 | EA | 53.16 | 106.32 | PPE | 2019-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21520-001025 | 21520 | 2019-07-29 15:42 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 2 | Each | 241.48 | 482.96 | Concrete Drainage | 2019-08-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21520-001025 | 21520 | 2019-07-29 15:42 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 4 | Each | 48.92 | 195.68 | Concrete Drainage | 2019-08-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21520-001025 | 21520 | 2019-07-29 15:42 | Section 3 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 2 | Each | 313.2 | 626.4 | Plastic Drainage | 2019-08-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21464-001025 | 21464 | 2019-07-26 17:03 | Section 3 | Material | Combined Drainage | Kerb Drain 405 Channel 1000mm (947299) | 182 | 7717344434 | 35.59 | 6477.38 | Concrete Drainage | 2019-07-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21464-001025 | 21464 | 2019-07-26 17:03 | Section 3 | Material | Kerbs | Not on List | 1 | 7717344434 | 39.22 | 39.22 | Concrete Drainage | 2019-07-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21464-001025 | 21464 | 2019-07-26 17:03 | Section 3 | Material | Not on List | Not on List | 5 | 7717344434 | 243.87 | 1219.35 | Concrete Drainage | 2019-07-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Not on List | Not on List | 6 | Each | 59.17 | 355.02 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21648-001025 | 21648 | 2019-08-01 06:20 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 77.5 | 155 | Small Tools (Consumables) | 2019-08-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21648-001025 | 21648 | 2019-08-01 06:20 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 51.93 | 104 | Small Tools (Consumables) | 2019-08-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21648-001025 | 21648 | 2019-08-01 06:20 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 0.68 | 7 | Miscellaneous | 2019-08-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21649-001025 | 21649 | 2019-08-01 06:36 | Core | Material | PPE, Small Tools and Consumables | Not on List | 36 | NULL | 2.5 | 90 | Surveying Consumables | 2019-08-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 600Mm X 6M R-Drain Unperf + Coup | 30 | Each | 166.43 | 4992.9 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21641-001025 | 21641 | 2019-07-31 17:24 | Section 5 | Material | Concrete Drainage | Not on List | 3 | EA | 318.91 | 956.73 | Concrete Drainage | 2019-08-01 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21641-001025 | 21641 | 2019-07-31 17:24 | Section 5 | Material | Concrete Drainage | Not on List | 1 | EA | 24.09 | 24.09 | Concrete Drainage | 2019-08-01 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21673-001025 | 21673 | 2019-08-01 11:40 | Section 1 | Material | Geotextile | Not on List | 12 | packs | 39.5 | 474 | Geotextiles | 2019-08-05 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-21680-001025 | 21680 | 2019-08-01 13:02 | Core | Material | Not on List | Not on List | 1 | NULL | 1072.2 | 1072 | Miscellaneous | 2019-08-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21685-001025 | 21685 | 2019-08-01 15:44 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 210 | 210 | Office Supplies | 2019-08-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21685-001025 | 21685 | 2019-08-01 15:44 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 120 | 120 | Office Supplies | 2019-08-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Not on List | Not on List | 2 | Each | 61.48 | 122.96 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 600Mm Ridgidrain Seal | 50 | Each | 20.71 | 1035.5 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21643-001025 | 21643 | 2019-07-31 16:28 | Section 5 | Material | Not on List | Not on List | 3.864 | TON | 538 | 2078.83 | Rebar and Mesh | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21710-001025 | 21710 | 2019-08-02 07:29 | Section 4 | Material | Not on List | Not on List | 1 | SM | 11149.86 | 11149.86 | Miscellaneous | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21682-001025 | 21682 | 2019-08-01 14:13 | Section 4 | Material | Bagged | Sharp Sand Bulk Bag (938208) | 5 | Each | 33.55 | 167.75 | Aggregate | NULL | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Not on List | Not on List | 4 | Each | 53.01 | 212.04 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18957-001025 | 18957 | 2019-06-12 09:04 | Core | Material | Not on List | Not on List | 1 | NULL | 11040 | 11040 | Miscellaneous | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Finance Approval | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13278-001025 | 13278 | 2019-02-28 15:28 | Core | Material | Not on List | Not on List | 8 | ea | 7.76 | 677 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13278-001025 | 13278 | 2019-02-28 15:28 | Core | Material | Not on List | Not on List | 8 | ea | 18.54 | 677 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13278-001025 | 13278 | 2019-02-28 15:28 | Core | Material | Not on List | Not on List | 8 | ea | 1.89 | 677 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13417-001025 | 13417 | 2019-03-04 15:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | 533.46 | NULL | 0 | Small Tools (Consumables) | 2019-03-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13575-001025 | 13575 | 2019-03-06 15:43 | Section 2 | Material | Not on List | Not on List | 10 | each | NULL | 0 | Concrete Accessories | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-5745-00455 | 5745 | 2018-08-29 11:33 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 395 | 1580 | Miscellaneous | 2018-09-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-13474-001025 | 13474 | 2019-03-05 11:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 134.99 | each | 1 | 134.99 | Small Tools (Consumables) | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11135-001025 | 11135 | 2019-01-17 14:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 779 | 779 | Not Sure | 2019-01-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | pair | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 1 | Pallet | 24.32 | 24 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 150 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5753-00459 | 5753 | 2018-08-29 13:27 | Section 4 | Material | Not on List | Not on List | 10000 | NULL | NULL | 0 | Concrete Accessories | 2018-09-05 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5122-0045 | 5122 | 2018-08-15 09:11 | Section 4 | Material | Not on List | NULL | 4 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5748-00456 | 5748 | 2018-08-29 11:34 | Section 3 | Material | Waste Management | Dry Mixed Recycling - Wheelie Bin 1100 Litre | 200 | Each | 7 | 1400 | Waste (Recycling) | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5748-00456 | 5748 | 2018-08-29 11:34 | Section 3 | Material | Waste Management | Not on List | 200 | NULL | 14.25 | 2850 | Waste (Recycling) | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5748-00456 | 5748 | 2018-08-29 11:34 | Section 3 | Material | Waste Management | Food Waste - Wheelie Bin 240 Litre | 140 | Each | 10 | 1400 | Waste (Recycling) | 2018-08-31 | Gate D - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13552-001025 | 13552 | 2019-03-06 12:21 | Section 2 | Material | Not on List | Not on List | 20 | number | NULL | 0 | Concrete Accessories | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 5 | EA | 250.9 | 1254.5 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 2 | EA | 250.9 | 501.8 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 3 | EA | 250.9 | 752.7 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 250.9 | 250.9 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 10 | EA | 49.5 | 495 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 1 | BAG | 409 | 409 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 625 | 625 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 4 | EA | 650 | 2600 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13640-001025 | 13640 | 2019-03-08 08:40 | Section 2 | Material | Not on List | Not on List | 6.798 | ton | NULL | 0 | NULL | 2019-03-18 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13623-001025 | 13623 | 2019-03-07 16:07 | Section 2 | Material | Not on List | Not on List | 59.726 | tonnes | NULL | 0 | NULL | 2019-03-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13349-001025 | 13349 | 2019-03-01 14:29 | Section 2 | Material | Not on List | Not on List | 4550 | Units | NULL | 0 | Concrete Accessories | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13349-001025 | 13349 | 2019-03-01 14:29 | Section 2 | Material | Not on List | Not on List | 390 | Units | NULL | 0 | Concrete Accessories | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13638-001025 | 13638 | 2019-03-08 08:23 | Section 5 | Material | Not on List | Not on List | 40 | kg | 0 | 0 | Builders Merchants (General) | 2019-03-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13725-001025 | 13725 | 2019-03-11 07:24 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-13495-001025 | 13495 | 2019-03-05 12:11 | Section 5 | Material | Not on List | Not on List | 24 | kg | NULL | 0 | Builders Merchants (General) | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13495-001025 | 13495 | 2019-03-05 12:11 | Section 5 | Material | Not on List | Not on List | 3 | LITRE | NULL | 0 | Builders Merchants (General) | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13495-001025 | 13495 | 2019-03-05 12:11 | Section 5 | Material | Not on List | Not on List | 3200 | kg | NULL | 0 | Builders Merchants (General) | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13633-001025 | 13633 | 2019-03-08 07:35 | Section 4 | Material | Not on List | Not on List | 1000 | NULL | NULL | 0 | Miscellaneous | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12152-001025 | 12152 | 2019-02-08 12:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 750 | 750 | Builders Merchants (General) | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13759-001025 | 13759 | 2019-03-11 10:57 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 75 | 75 | Damage Charges | 2019-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13644-001025 | 13644 | 2019-03-08 09:11 | Section 4 | Material | Not on List | Not on List | 10 | Each | 42.31 | 423.1 | Miscellaneous | 2019-03-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5041-0026 | 5041 | 2018-08-14 10:19 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 2181 | 0 | Office Supplies | 2018-09-06 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13448-001025 | 13448 | 2019-03-05 06:53 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 0.9 | 900 | Miscellaneous | 2019-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13764-001025 | 13764 | 2019-03-11 11:32 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 6.35 | 127 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 6.35 | 127 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 6.35 | 127 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 6.35 | 127 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | EACH | 1.78 | 89 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | EACH | 3.84 | 153.6 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | 1.94 | 29.1 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5562-00389 | 5562 | 2018-08-23 10:51 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 98 | 98 | Damage Charges | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | 1.65 | 24.75 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | 4.42 | 44.2 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | 3.64 | 36.4 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | EACH | 0.89 | 35.6 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 7.67 | 153.4 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | EACH | 1.91 | 76.4 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | 44.95 | 449.5 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | 7.54 | 75.4 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | 10 | 100 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 0 | EACH | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5791-00472 | 5791 | 2018-08-30 08:44 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Geotextiles | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Commercial - Rejected | NULL | No - Reject | REQ - Section 4 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | 0.81 | 12.15 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 1.2 | 24 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | EACH | 9.99 | 49.95 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | 10.83 | 0 | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | NULL | 2440x1220x18mm Shuttering Ply (683573) | 100 | EACH | 25.78 | 2578 | Miscellaneous | 2019-03-11 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | EACH | 0.83 | 83 | Concrete Accessories | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13765-001025 | 13765 | 2019-03-11 11:39 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13664-001025 | 13664 | 2019-03-08 11:45 | Section 3 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 108 | Each | 3.56 | 384.48 | Builders Merchants (General) | 2019-03-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 5 | No. | 20 | 100 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-13673-001025 | 13673 | 2019-03-08 13:17 | Section 3 | Material | NULL | Not on List | 5 | T | 32.74 | 163.7 | Builders Merchants (General) | 2019-03-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13772-001025 | 13772 | 2019-03-11 12:04 | Core | Material | Not on List | Not on List | 1 | NUMBER | 46588.5 | 46589 | Miscellaneous | 2019-03-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-13576-001025 | 13576 | 2019-03-06 15:45 | Section 2 | Material | NULL | Not on List | 8 | 30Kg Packs | NULL | 0 | Miscellaneous | 2019-03-13 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13527-001025 | 13527 | 2019-03-06 09:06 | Section 3 | Material | Not on List | Not on List | 14 | no | 32 | 448 | Small Tools (Consumables) | 2019-03-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 10 | boxes | 9 | 90 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-13670-001025 | 13670 | 2019-03-08 13:10 | Section 4 | Material | Not on List | Not on List | 400 | Each | 5.34 | 2136 | Plastic Drainage | 2019-03-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13466-001025 | 13466 | 2019-03-05 10:36 | Section 4 | Material | Not on List | Not on List | 20 | Each | 85.23 | 1704.6 | Concrete Drainage | 2019-03-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13466-001025 | 13466 | 2019-03-05 10:36 | Section 4 | Material | Not on List | Not on List | 6 | Each | 63.93 | 383.58 | Concrete Drainage | 2019-03-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13466-001025 | 13466 | 2019-03-05 10:36 | Section 4 | Material | Not on List | Not on List | 5 | Each | 55.13 | 275.65 | Concrete Drainage | 2019-03-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13466-001025 | 13466 | 2019-03-05 10:36 | Section 4 | Material | Not on List | Not on List | 10 | Each | 61.53 | 615.3 | Concrete Drainage | 2019-03-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 10 | Packs | 10.5 | 105 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | Not on List | Not on List | 30 | Each | 6.2 | 186 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | Not on List | Not on List | 20 | Each | 17.9 | 358 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | Not on List | Not on List | 10 | Each | 88 | 880 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | Not on List | Not on List | 10 | Each | 6.35 | 63.5 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | Not on List | Not on List | 10 | Each | 6.35 | 63.5 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13568-001025 | 13568 | 2019-03-06 08:39 | Section 3 | Material | NULL | Not on List | 22 | No | 62.58 | 1376.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13605-001025 | 13605 | 2019-03-06 18:32 | Section 4 | Material | Not on List | Not on List | 1 | Each | 6108.88 | 6108.88 | Miscellaneous | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 220 | No | 22.84 | 5024.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 10 | Packs | 10.5 | 105 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 200 | No | 24 | 4800 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 30 | No | 60.46 | 1813.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 4 | No | 35.96 | 143.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 4 | No | 35.96 | 143.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 4 | No | 7.68 | 30.72 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 4 | No | 7.68 | 30.72 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 1 | No | 282.24 | 282.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 1 | No | 359.42 | 359.42 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-15603-001025 | 15603 | 2019-04-10 13:20 | Section 2 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 100 | Each | 16.49 | 1649 | Concrete Drainage | 2019-04-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15610-001025 | 15610 | 2019-04-10 13:43 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-04-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15512-001025 | 15512 | 2019-04-09 09:37 | Section 3 | Material | Not on List | Not on List | 1 | No | 7175 | 7175 | Flow Control | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15512-001025 | 15512 | 2019-04-09 09:37 | Section 3 | Material | Not on List | Not on List | 4 | No | 6960 | 27840 | Flow Control | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15512-001025 | 15512 | 2019-04-09 09:37 | Section 3 | Material | Not on List | Not on List | 2 | No | 4758 | 9516 | Flow Control | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15512-001025 | 15512 | 2019-04-09 09:37 | Section 3 | Material | Not on List | Not on List | 7 | No | 982 | 6874 | Flow Control | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15512-001025 | 15512 | 2019-04-09 09:37 | Section 3 | Material | Not on List | Not on List | 7 | No | 787 | 5509 | Flow Control | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15398-001025 | 15398 | 2019-04-05 15:16 | Section 2 | Material | NULL | Not on List | 26 | number | NULL | 0 | Ductile Drainage | 2019-04-10 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15398-001025 | 15398 | 2019-04-05 15:16 | Section 2 | Material | PPE, Small Tools and Consumables | Polythene Pifa Dpm 250 Micron Black Regr/Vir 4x25m 6/8 (606095) | 2 | Each | 59 | 118 | Miscellaneous | 2019-04-10 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15135-001025 | 15135 | 2019-04-02 14:25 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-6076-00609 | 6076 | 2018-09-05 13:29 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-09-05 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Trowel Plastering Spartan Pro 275mm X 113mm (11" X 4 1/2 (767506) | 10 | Each | 6.88 | 69 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Headtorch 3 Led Bulb C/W 3 X Lr03/Aaa Batts Spartan Pro (740434) | 15 | Each | 9.34 | 140 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15551-001025 | 15551 | 2019-04-09 15:57 | Section 2 | Material | NULL | 454x454x100 D400 Watershed GG&F (257790) | 25 | Each | 63.84 | 1596 | Ductile Drainage | 2019-04-16 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15551-001025 | 15551 | 2019-04-09 15:57 | Section 2 | Material | NULL | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-04-16 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 150 | Each | 3.04 | 456 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Cones Blue 750mm - No Sleeve Csp (204013) | 100 | Each | 6.9 | 690 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Sign Plastic 600x200m-warning High Voltage Cables Overhead (249677) | 10 | Each | 11.88 | 119 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycottn En471cl1 Saturn Regular Ct01-y (302019) | 5 | Each | 13 | 65 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycottn En471cl1 Saturn Regular Ct01-y (302019) | 5 | Each | 13 | 65 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Jacket 321136 Keepsafe Yellow Bomber C/W A14 Logos (13047) | 3 | Each | 13.4 | 40 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Jacket 321136 Keepsafe Yellow Bomber C/W A14 Logos (13047) | 3 | Each | 13.4 | 40 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Jacket 321136 Keepsafe Yellow Bomber C/W A14 Logos (13047) | 3 | Each | 13.4 | 40 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Coverall Flame Retardent Cotton Saturn Fr Reflective Tape (370522) | 3 | Each | 107.6 | 323 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Coverall Flame Retardent Cotton Saturn Fr Reflective Tape (370522) | 3 | Each | 107.6 | 323 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Keep Safe First Aid Kit - Burns Dispenser Kit (254960) | 10 | Each | 11.64 | 116 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15601-001025 | 15601 | 2019-04-10 12:24 | Section 2 | Material | Not on List | Not on List | 12 | NULL | 150 | 1800 | Miscellaneous | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1503 - Cables, Joints & Terminations | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15588-001025 | 15588 | 2019-04-10 09:17 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 350 | 1400 | Laboratory Equipment / Certification | 2019-04-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15646-001025 | 15646 | 2019-04-10 17:52 | Section 5 | Material | Not on List | Not on List | 7 | NULL | 150 | 1050 | Miscellaneous | 2019-05-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1503 - Cables, Joints & Terminations | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15589-001025 | 15589 | 2019-04-10 09:34 | Section 4 | Material | Not on List | Not on List | 80 | NULL | 13.95 | 1116 | Concrete Accessories | 2019-04-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15636-001025 | 15636 | 2019-04-10 16:54 | Section 4 | Material | NULL | Building Sand Bulk Bag (938155) | 5 | Each | 33.55 | 167.75 | Aggregate | 2019-04-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15149-001025 | 15149 | 2019-04-02 15:20 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 2710.29 | 2710.29 | Miscellaneous | 2019-04-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-15446-001025 | 15446 | 2019-04-08 12:25 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-04-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15439-001025 | 15439 | 2019-04-08 09:24 | Section 4 | Material | Not on List | Not on List | 5000 | Each | 1 | 5000 | Miscellaneous | 2019-04-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15444-001025 | 15444 | 2019-04-08 12:20 | Core | Material | Not on List | Not on List | 1 | number | 973 | 973 | Office Supplies | 2019-04-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15541-001025 | 15541 | 2019-04-09 14:48 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | each | 130 | 520 | Surveying Consumables | 2019-04-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 12 | No. | 74.74 | 896.88 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 6 | No. | 19.61 | 117.66 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 36 | No. | 20.68 | 744.48 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6089-00611 | 6089 | 2018-09-05 13:52 | Section 3 | Material | Not on List | Not on List | 20 | EA | 284.69 | 5693.8 | Miscellaneous | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 72 | No. | 3.15 | 226.8 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 6 | No. | 29.09 | 174.54 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 180 | No. | 1.55 | 279 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 6 | No. | 29.09 | 174.54 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 10 | No. | 17.03 | 170.3 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 2 | No. | 17.03 | 34.06 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 10 | No. | 15.15 | 151.5 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15476-001025 | 15476 | 2019-04-08 16:17 | Section 4 | Material | Not on List | Not on List | 18 | Each | 17.9 | 322.2 | Surveying Consumables | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15476-001025 | 15476 | 2019-04-08 16:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 45 | 45 | Surveying Consumables | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6085-00610 | 6085 | 2018-09-05 14:49 | Section 3 | Material | Not on List | Not on List | 1 | no. | 1437.42 | 1437.42 | Miscellaneous | 2018-09-07 | Gate D - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15597-001025 | 15597 | 2019-04-10 10:38 | Section 4 | Material | Waste Management | Plastic - Roll On Roll Off 40 cubic yard | 1 | Each | 360 | 360 | Waste (General) | 2019-04-22 | RVP 426 - Robins Lane A14 Eastbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15251-001025 | 15251 | 2019-04-04 06:28 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 40 cubic yard | 1 | Each | 370 | 370 | Waste (General) | 2019-04-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15471-001025 | 15471 | 2019-04-08 15:32 | Core | Material | Not on List | Not on List | 2 | number | 40 | 80 | Surveying Consumables | 2019-04-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15518-001025 | 15518 | 2019-04-09 09:55 | Section 3 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 2.97 | 166.32 | Builders Merchants (General) | 2019-04-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15518-001025 | 15518 | 2019-04-09 09:55 | Section 3 | Material | Not on List | Not on List | 100 | No | 6.38 | 638 | Plastic Drainage | 2019-04-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15518-001025 | 15518 | 2019-04-09 09:55 | Section 3 | Material | Not on List | Not on List | 50 | No | 0.35 | 17.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15518-001025 | 15518 | 2019-04-09 09:55 | Section 3 | Material | Not on List | Not on List | 60 | No | 1.98 | 118.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15449-001025 | 15449 | 2019-04-08 12:51 | Core | Material | Not on List | Not on List | 1 | NULL | 34.95 | 35 | Miscellaneous | 2019-04-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15517-001025 | 15517 | 2019-04-09 10:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 536.28 | 536.28 | Small Tools (Consumables) | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6057-00604 | 6057 | 2018-09-05 09:33 | Section 3 | Material | Not on List | Not on List | 1 | Activity | 10000 | 10000 | Concrete Drainage | 2018-09-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6111-00612 | 6111 | 2018-09-05 18:45 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 581.84 | 581.84 | PPE | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15202-001025 | 15202 | 2019-04-03 10:56 | Section 4 | Material | Not on List | Not on List | 1 | Each | 86.2 | 86.2 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15634-001025 | 15634 | 2019-04-10 16:41 | Section 4 | Material | Not on List | Not on List | 30 | NULL | 189 | 5670 | Plastic Drainage | 2019-04-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15634-001025 | 15634 | 2019-04-10 16:41 | Section 4 | Material | Not on List | Not on List | 40 | NULL | 2.38 | 95.2 | Plastic Drainage | 2019-04-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15290-001025 | 15290 | 2019-04-04 12:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1049.59 | 1049.59 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6111-00612 | 6111 | 2018-09-05 18:45 | Section 3 | Material | Misc | Not on List | 1 | EA | 52.8 | 52.8 | Miscellaneous | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | Not on List | Not on List | 100 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | Not on List | Not on List | 50 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 48 | Each | 6.82 | 327 | Timber Products | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-6133-00619 | 6133 | 2018-09-06 11:30 | Section 3 | Material | Not on List | Not on List | 200 | ea | 12.81 | 2562 | Miscellaneous | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-15631-001025 | 15631 | 2019-04-10 16:32 | Section 3 | Material | Not on List | Not on List | 50 | No | 1.2 | 60 | Miscellaneous | 2019-04-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15672-001025 | 15672 | 2019-04-11 10:33 | Section 2 | Material | NULL | Polypipe 125mm x 6m Black Ridgiduct (877724) | 2 | Each | 20.32 | 40.64 | Plastic Drainage | 2019-04-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15672-001025 | 15672 | 2019-04-11 10:33 | Section 2 | Material | NULL | Not on List | 12 | Each | 28.46 | 341.52 | Plastic Drainage | 2019-04-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15622-001025 | 15622 | 2019-04-10 15:12 | Section 3 | Material | Not on List | Not on List | 1 | ea | 558.09 | 558.09 | Small Tools (Consumables) | 2019-04-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15622-001025 | 15622 | 2019-04-10 15:12 | Section 3 | Material | Not on List | Not on List | 1 | ea | 1303.6 | 1303.6 | PPE | 2019-04-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15622-001025 | 15622 | 2019-04-10 15:12 | Section 3 | Material | Not on List | Not on List | 1 | ea | 57.68 | 57.68 | Janitorial | 2019-04-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15724-001025 | 15724 | 2019-04-11 17:21 | Section 5 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 2701 - Accommodation works | Stores - Closed | Yes - Approve | NULL | Req - S5 Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 4 | number | 18.91 | 75.64 | Not Sure | 2018-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15731-001025 | 15731 | 2019-04-12 07:09 | Section 4 | Material | NULL | NULL | 1 | NULL | 31197.22 | 31197.22 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 216 | ea | 45 | 9720 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 1 | ea | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 1 | ea | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 2 | number | 28.55 | 57.1 | Not Sure | 2018-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 4 | ea | 55 | 220 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 4 | ea | 55 | 220 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 1 | ea | 45 | 45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 1 | ea | 45 | 45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 40 | ea | 13 | 520 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 24 | ea | 8 | 192 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 1 | ea | 35 | 35 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15755-001025 | 15755 | 2019-04-12 11:36 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Miscellaneous | 2019-04-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15755-001025 | 15755 | 2019-04-12 11:36 | Section 2 | Material | Not on List | Not on List | 70 | number | NULL | 0 | Miscellaneous | 2019-04-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 1 | number | 50 | 50 | Not Sure | 2018-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15755-001025 | 15755 | 2019-04-12 11:36 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Miscellaneous | 2019-04-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 40 | number | 20.82 | 832.8 | Not Sure | 2018-09-10 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15608-001025 | 15608 | 2019-04-10 09:15 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Builders Merchants (General) | 2019-04-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 45 | number | 5.25 | 236.25 | Not Sure | 2018-09-10 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15744-001025 | 15744 | 2019-04-12 09:04 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 78.4 | 156.8 | Miscellaneous | 2019-04-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15753-001025 | 15753 | 2019-04-12 11:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 290.3 | 290.3 | Small Tools (Consumables) | 2019-04-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15592-001025 | 15592 | 2019-04-10 09:36 | Section 4 | Material | Not on List | Not on List | 2 | Number | 22.24 | 44.48 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15592-001025 | 15592 | 2019-04-10 09:36 | Section 4 | Material | Not on List | Not on List | 2 | Number | 59.05 | 118.1 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15592-001025 | 15592 | 2019-04-10 09:36 | Section 4 | Material | Not on List | Not on List | 2 | Number | 64.9 | 129.8 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15836-001025 | 15836 | 2019-04-15 10:08 | Section 3 | Material | Not on List | Not on List | 2 | No sets | NULL | 0 | Builders Merchants (General) | 2019-04-17 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15831-001025 | 15831 | 2019-04-15 09:28 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 6 | Each | 122.72 | 736.32 | Geotextiles | 2019-04-17 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3B - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15097-001025 | 15097 | 2019-04-02 09:01 | Core | Material | Not on List | Not on List | 1 | EACH | 726 | 726 | Miscellaneous | 2019-04-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Finance Approval | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 80 | number | 0.55 | 44 | Not Sure | 2018-09-10 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15683-001025 | 15683 | 2019-04-11 12:41 | Core | Material | Not on List | Not on List | 1 | number | 15856.68 | 15856.68 | Professional Services | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15683-001025 | 15683 | 2019-04-11 12:41 | Core | Material | Not on List | Not on List | 1 | number | 4910.8 | 4910.8 | Professional Services | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 107 - Fee based costs including insurance | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15683-001025 | 15683 | 2019-04-11 12:41 | Core | Material | Not on List | Not on List | 1 | number | 9260.56 | 9260.56 | Professional Services | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 107 - Fee based costs including insurance | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6008-00594 | 6008 | 2018-09-04 08:14 | Section 3 | Material | Not on List | Not on List | 6 | Rolls | 258.05 | 1548.3 | Not Sure | 2018-09-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15847-001025 | 15847 | 2019-04-15 11:53 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 99.6 | 199 | Surveying Consumables | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15850-001025 | 15850 | 2019-04-15 12:03 | Core | Material | Not on List | Not on List | 4 | NULL | 1249.99 | 5000 | Miscellaneous | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Operations Rejected | No - Reject | NULL | REQ - Buyers
MREQ-27233-001025 | 27233 | 2019-12-03 07:45 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-26359-001025 | 26359 | 2019-11-08 13:39 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27244-001025 | 27244 | 2019-12-03 09:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 26.5 | 133 | Miscellaneous | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27252-001025 | 27252 | 2019-12-03 10:48 | Section 3 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Fixings and Fasteners | 2019-12-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 1201 - Traffic Signs | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-27252-001025 | 27252 | 2019-12-03 10:48 | Section 3 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Fixings and Fasteners | 2019-12-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 1201 - Traffic Signs | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-27254-001025 | 27254 | 2019-12-03 11:00 | Core | Material | Not on List | Not on List | 35 | nUMBER | 275 | 9625 | Surveying Consumables | 2020-01-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | NULL | Yes - Approve | REQ - Buyers
MREQ-27256-001025 | 27256 | 2019-12-03 11:17 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27204-001025 | 27204 | 2019-12-02 13:56 | Section 4 | Material | Not on List | Not on List | 15 | Each | 41.85 | 627.75 | Plastic Drainage | 2019-12-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27262-001025 | 27262 | 2019-12-03 11:34 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27263-001025 | 27263 | 2019-12-03 11:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27266-001025 | 27266 | 2019-12-03 12:04 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27270-001025 | 27270 | 2019-12-03 13:41 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-27273-001025 | 27273 | 2019-12-03 14:18 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-27274-001025 | 27274 | 2019-12-03 14:29 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27247-001025 | 27247 | 2019-12-03 09:42 | Section 4 | Material | NULL | NULL | 1 | Each | 1859.61 | 1859.61 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27248-001025 | 27248 | 2019-12-03 09:49 | Section 4 | Material | NULL | NULL | 40 | Pack 100 | 10.5 | 420 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27248-001025 | 27248 | 2019-12-03 09:49 | Section 4 | Material | NULL | NULL | 120 | Each | 17.9 | 2148 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27248-001025 | 27248 | 2019-12-03 09:49 | Section 4 | Material | NULL | NULL | 500 | Each | 7.5 | 3750 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27229-001025 | 27229 | 2019-12-03 06:52 | Section 6 | Material | Timber | Not on List | 10 | Lengths | 10.68 | 106.8 | Timber Products | 2019-12-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27229-001025 | 27229 | 2019-12-03 06:52 | Section 6 | Material | Timber | Not on List | 10 | Lengths | 7.23 | 72.3 | Timber Products | 2019-12-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 74 | Each | 36.9 | 2730.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 4 | Each | 124.86 | 499.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 6 | Each | 42.5 | 255 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 2 | Each | 17.5 | 35 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 6 | Each | 21.23 | 127.38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 40 | Each | 13.08 | 523.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 7 | Each | 126.04 | 882.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 2 | Each | 59.45 | 118.9 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 1 | Each | 80 | 80 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 1 | Each | 272.25 | 272.25 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27272-001025 | 27272 | 2019-12-03 13:46 | Section 4 | Material | Not on List | Not on List | 32 | Each | 14.29 | 457.28 | Builders Merchants (General) | 2019-12-06 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27049-001025 | 27049 | 2019-11-27 15:12 | Section 3 | Material | Not on List | Not on List | 3 | ea | 40.33 | 120.99 | Miscellaneous | 2019-12-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27049-001025 | 27049 | 2019-11-27 15:12 | Section 3 | Material | Not on List | Not on List | 3 | ea | 36.71 | 110.13 | Miscellaneous | 2019-12-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27297-001025 | 27297 | 2019-12-03 17:37 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27304-001025 | 27304 | 2019-12-04 06:50 | Section 6 | Material | Timber | Not on List | 100 | linier m | NULL | 0 | Timber Products | 2019-12-05 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26996-001025 | 26996 | 2019-11-26 14:35 | Section 2 | Material | Not on List | Not on List | 3 | ea | 26.25 | 78.75 | Small Tools (Consumables) | 2019-11-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27134-001025 | 27134 | 2019-11-29 09:40 | Section 2 | Material | Not on List | Not on List | 1 | ea | 628 | 628 | Concrete Accessories | 2019-12-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27122-001 | 27122 | 2019-11-29 07:44 | Section 6 | Material | Not on List | Not on List | 5 | Tubs | 36.9 | 184.5 | Builders Merchants (General) | 2019-12-05 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27321-001025 | 27321 | 2019-12-04 11:42 | Core | Material | Not on List | Not on List | 1 | No. | 3000 | 3000 | Miscellaneous | 2019-12-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7264-001021 | 7264 | 2018-10-02 08:56 | Section 3 | Material | Not on List | Not on List | 1 | EA | 836 | 836 | Miscellaneous | 2018-10-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2702 - Works by the Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27152-001025 | 27152 | 2019-11-29 13:47 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27326-001025 | 27326 | 2019-12-04 14:45 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27329-001025 | 27329 | 2019-12-04 15:17 | Section 4 | Material | Aggregate | Type 1 | 1500 | Tonnes | 21.65 | 32475 | Aggregate | 2019-12-05 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27330-001025 | 27330 | 2019-12-04 15:17 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27332-001025 | 27332 | 2019-12-04 15:34 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-27333-001025 | 27333 | 2019-12-04 15:44 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27336-001025 | 27336 | 2019-12-04 16:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26972-001025 | 26972 | 2019-11-26 09:00 | Section 3 | Material | Kerbs | Not on List | 82 | ea | 4.42 | 362.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-28 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | BN10 - A1198 Ermine Street Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7318-001022 | 7318 | 2018-10-02 18:07 | Section 3 | Material | Not on List | Not on List | 5 | number | 33.15 | 165.75 | Concrete Accessories | 2018-10-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN07 - B1043 Offord Road Overbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27339-001025 | 27339 | 2019-12-04 16:21 | Section 4 | Material | Aggregate | Not on List | 600000 | tons | 5 | 3000000 | Aggregate | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-27129-001025 | 27129 | 2019-11-29 08:59 | Section 2 | Material | Not on List | Not on List | 2 | ea | 182.9 | 365.8 | Miscellaneous | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27129-001025 | 27129 | 2019-11-29 08:59 | Section 2 | Material | Not on List | Not on List | 2 | ea | 182.9 | 365.8 | Miscellaneous | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27328-001025 | 27328 | 2019-12-04 15:13 | Section 2 | Material | Not on List | Not on List | 3 | No. | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1201 - Traffic Signs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7357-001022 | 7357 | 2018-10-03 15:55 | Section 4 | Material | Not on List | Not on List | 1 | Each | 679.03 | 679.03 | Damage Charges | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27340-001025 | 27340 | 2019-12-04 16:36 | Section 2 | Material | Not on List | Not on List | 15 | Tins | 19.51 | 292.65 | Concrete Accessories | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27370-001025 | 27370 | 2019-12-05 09:25 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-27371-001025 | 27371 | 2019-12-05 09:35 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27376-001025 | 27376 | 2019-12-05 11:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 276.09 | 276 | Small Tools (Consumables) | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27386-001025 | 27386 | 2019-12-05 14:17 | Section 2 | Material | Not on List | Not on List | 2 | each | 81.8 | 164 | Laboratory Equipment / Certification | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27389-001025 | 27389 | 2019-12-05 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | EACH | 466.01 | 466 | PPE | 2019-12-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7353-001022 | 7353 | 2018-10-03 12:30 | Section 4 | Material | NULL | Not on List | 1280 | Each | 4.16 | 5324.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-08 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26159-001025 | 26159 | 2019-11-05 14:53 | Core | Material | NULL | NULL | 1 | Each | 606 | 606 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27392-001025 | 27392 | 2019-12-05 15:39 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3778.79 | Each | 1 | 3779 | PPE | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27234-001025 | 27234 | 2019-12-03 07:57 | Section 2 | Material | Not on List | Not on List | 6 | no. | 1050.83 | 6304.98 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27179-001025 | 27179 | 2019-12-01 16:08 | Section 5 | Material | NULL | NULL | 48 | Each | 0.21 | 10.08 | Fixings and Fasteners | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27179-001025 | 27179 | 2019-12-01 16:08 | Section 5 | Material | NULL | NULL | 24 | Each | 0.71 | 17.04 | Fixings and Fasteners | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27179-001025 | 27179 | 2019-12-01 16:08 | Section 5 | Material | NULL | NULL | 48 | Each | 0.76 | 36.48 | Fixings and Fasteners | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27309-001025 | 27309 | 2019-12-04 08:38 | Section 4 | Material | NULL | NULL | 195 | Each | 5.17 | 1008.15 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27309-001025 | 27309 | 2019-12-04 08:38 | Section 4 | Material | NULL | NULL | 32 | Each | 11.68 | 373.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 60 | Each | 241.48 | 14488.8 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 10 | Each | 289.77 | 2897.7 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7353-001022 | 7353 | 2018-10-03 12:30 | Section 4 | Material | NULL | NULL | 4 | Each | 30 | 120 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-08 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 10 | Each | 289.77 | 2897.7 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 6 | Each | 289.77 | 1738.62 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 5 | Each | 294.58 | 1472.9 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 1 | Each | 220.93 | 220.93 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 3 | Each | 317.77 | 953.31 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27360-001025 | 27360 | 2019-12-05 07:57 | Section 4 | Material | Aggregate | Type 1 | 5000 | Tonnes | 20 | 100000 | Aggregate | 2019-12-09 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27417-001025 | 27417 | 2019-12-06 07:58 | Section 5 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142 | Builders Merchants (General) | 2019-12-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27317-001025 | 27317 | 2019-12-04 09:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 421.1 | each | 1 | 421.1 | Miscellaneous | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27342-001025 | 27342 | 2019-12-04 16:35 | Section 2 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 40 | Each | 10.08 | 403.2 | Builders Merchants (General) | 2019-12-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27342-001025 | 27342 | 2019-12-04 16:35 | Section 2 | Material | Timber | Not on List | 100 | Each | 1.1 | 110 | Builders Merchants (General) | 2019-12-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27342-001025 | 27342 | 2019-12-04 16:35 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | boxes | 14.85 | 29.7 | Builders Merchants (General) | 2019-12-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27312-001025 | 27312 | 2019-12-04 08:51 | Section 3 | Material | Not on List | Not on List | 210 | meters | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27312-001025 | 27312 | 2019-12-04 08:51 | Section 3 | Material | Not on List | Not on List | 2 | no. | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27312-001025 | 27312 | 2019-12-04 08:51 | Section 3 | Material | Not on List | Not on List | 2 | no. | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27347-001025 | 27347 | 2019-12-04 17:36 | Section 4 | Material | Aggregate | Not on List | 60000 | ton | 5 | 300000 | Aggregate | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27427-001025 | 27427 | 2019-12-06 10:43 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27318-001025 | 27318 | 2019-12-04 10:04 | Section 4 | Material | Not on List | Not on List | 1 | 74 | 1895.21 | 1895.21 | Miscellaneous | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27426-001025 | 27426 | 2019-12-06 09:56 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 3 | Each | 32.74 | 98.22 | Concrete Accessories | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7289-001022 | 7289 | 2018-10-02 14:44 | Section 3 | Material | Not on List | Not on List | 1 | EA | 709.58 | 709.58 | PPE | 2018-10-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27426-001025 | 27426 | 2019-12-06 09:56 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142.4 | Concrete Accessories | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27230-001025 | 27230 | 2019-12-03 07:16 | Section 4 | Material | Not on List | Not on List | 1 | Each | 764.28 | 764.28 | Miscellaneous | 2019-12-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25410-001025 | 25410 | 2019-10-18 15:22 | Section 4 | Material | NULL | NULL | 1 | Each | 369 | 369 | Miscellaneous | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27264-001025 | 27264 | 2019-12-03 11:46 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 162.49 | 162.49 | Miscellaneous | 2019-12-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27430-001025 | 27430 | 2019-12-06 11:28 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27276-001025 | 27276 | 2019-12-03 14:52 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 2200.56 | 2200.56 | Miscellaneous | 2019-12-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7289-001022 | 7289 | 2018-10-02 14:44 | Section 3 | Material | Not on List | Not on List | 1 | EA | 929.69 | 929.69 | Small Tools (Consumables) | 2018-10-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7322-001022 | 7322 | 2018-10-03 07:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4000 | 4000 | Not Sure | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27441-001025 | 27441 | 2019-12-06 14:06 | Section 2 | Material | Not on List | Not on List | 50 | sets | 3.4 | 170 | Fixings and Fasteners | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7311-001022 | 7311 | 2018-10-02 16:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2018-10-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27435-001025 | 27435 | 2019-12-06 13:06 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Number | 40.19 | 40.19 | Small Tools (Consumables) | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27475-001025 | 27475 | 2019-12-09 11:02 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327 | Builders Merchants (General) | 2019-12-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27486-001025 | 27486 | 2019-12-09 13:30 | Core | Material | Not on List | Not on List | 2 | No. | 100 | 200 | Miscellaneous | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27490-001025 | 27490 | 2019-12-09 15:54 | Section 4 | Material | Aggregate | 6G | 25 | Tonnes | 22 | 550 | Aggregate | 2019-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27362-001025 | 27362 | 2019-12-05 08:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 303.21 | each | 1 | 303.21 | Miscellaneous | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27516-001025 | 27516 | 2019-12-10 08:21 | Core | Material | Not on List | Not on List | 1 | NULL | 3250 | 3250 | Professional Services | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27473-001025 | 27473 | 2019-12-09 10:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | EACH | 3970.79 | 3970.79 | Small Tools (Consumables) | 2019-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27135-001025 | 27135 | 2019-11-29 09:54 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | Bag | 2.97 | 332.64 | Miscellaneous | 2019-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27443-001025 | 27443 | 2019-12-06 14:09 | Section 2 | Material | Not on List | Not on List | 2 | each | 545 | 1090 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27443-001025 | 27443 | 2019-12-06 14:09 | Section 2 | Material | Not on List | Not on List | 2 | each | 545 | 1090 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27443-001025 | 27443 | 2019-12-06 14:09 | Section 2 | Material | Not on List | Not on List | 2 | each | 61.25 | 122.5 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27443-001025 | 27443 | 2019-12-06 14:09 | Section 2 | Material | Not on List | Not on List | 2 | each | 61.25 | 122.5 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27517-001025 | 27517 | 2019-12-10 08:30 | Section 6 | Material | Not on List | Not on List | 1 | Each | 63.02 | 63.02 | Miscellaneous | 2019-12-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27350-001025 | 27350 | 2019-12-04 18:25 | Core | Material | Not on List | Not on List | 1 | 1 | 94.99 | 95 | Office Supplies | 2019-12-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27350-001025 | 27350 | 2019-12-04 18:25 | Core | Material | Not on List | Not on List | 2 | 1 | 24.99 | 50 | Office Supplies | 2019-12-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27345-001025 | 27345 | 2019-12-04 17:11 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 974.05 | 974.05 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27532-001025 | 27532 | 2019-12-10 12:36 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | PPE | 2019-12-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27532-001025 | 27532 | 2019-12-10 12:36 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | PPE | 2019-12-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27532-001025 | 27532 | 2019-12-10 12:36 | Section 6 | Material | Not on List | Not on List | 10 | Each | NULL | 0 | PPE | 2019-12-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27532-001025 | 27532 | 2019-12-10 12:36 | Section 6 | Material | Not on List | Not on List | 10 | Each | NULL | 0 | PPE | 2019-12-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27538-001025 | 27538 | 2019-12-10 14:31 | Section 5 | Material | Not on List | Not on List | 20 | Number | NULL | 0 | Builders Merchants (General) | 2019-12-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27539-001025 | 27539 | 2019-12-10 14:07 | Section 3 | Material | Not on List | Not on List | 1 | No. | NULL | 0 | Miscellaneous | 2019-12-10 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 501 - Drains | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 4 | no | 5.25 | 21 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23579-001025 | 23579 | 2019-09-12 14:06 | Section 3 | Material | Not on List | Not on List | 1 | EA | 415.51 | 415.51 | Miscellaneous | 2019-09-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 16 | no | 5.25 | 84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23571-001025 | 23571 | 2019-09-12 12:34 | Section 4 | Material | Not on List | Not on List | 1 | Each | 500000 | 500000 | Gas Oil | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23500-001025 | 23500 | 2019-09-11 11:22 | Section 4 | Material | Not on List | Not on List | 1 | Each | 621.27 | 621.27 | Miscellaneous | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23492-001025 | 23492 | 2019-09-11 09:53 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 45 | 45 | Surveying Consumables | 2019-09-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23581-001025 | 23581 | 2019-09-12 14:25 | Core | Material | Not on List | Not on List | 2 | EA | 850 | 1700 | Not Sure | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23586-001025 | 23586 | 2019-09-12 15:40 | Section 5 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 4 | Each | 158.65 | 634.6 | Ductile Drainage | 2019-09-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23621-001025 | 23621 | 2019-09-13 06:44 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 1 | Each | 370 | 370 | Waste (General) | 2019-09-16 | RVP 403 - 1339621 - Borrow Pit 5 A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 24 | no | 5.25 | 126 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23568-001025 | 23568 | 2019-09-12 12:09 | Section 4 | Material | Not on List | Not on List | 1 | lot | 232.14 | 232.14 | Miscellaneous | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23568-001025 | 23568 | 2019-09-12 12:09 | Section 4 | Material | Not on List | Not on List | 1 | lot | 1308.96 | 1308.96 | Miscellaneous | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23630-001025 | 23630 | 2019-09-13 08:24 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-23565-001025 | 23565 | 2019-09-12 11:17 | Section 2 | Material | Not on List | Not on List | 1 | 1 | 1 | 1 | Rebar and Mesh | 2019-09-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23641-001025 | 23641 | 2019-09-13 10:01 | Section 5 | Material | Not on List | Not on List | 1 | SM | 307.96 | 307.96 | Concrete Accessories | 2019-09-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 4 | no | 14.1 | 56.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23687-001025 | 23687 | 2019-09-14 08:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23687-001025 | 23687 | 2019-09-14 08:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23687-001025 | 23687 | 2019-09-14 08:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 10 | no | 5.25 | 52.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23701-001025 | 23701 | 2019-09-16 07:51 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 16 | no | 2.93 | 46.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23583-001025 | 23583 | 2019-09-12 13:23 | Section 4 | Material | Not on List | Not on List | 14 | NULL | NULL | 0 | NULL | 2019-09-20 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23717-001025 | 23717 | 2019-09-16 10:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Twinwall | Polypipe 225mm Ridgidrain Bend 22.5deg (878030) | 4 | Each | 29.82 | 119.28 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Not on List | Not on List | 70 | Easch | 26.8 | 1876 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 70 | Each | 3.65 | 255.5 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Not on List | Not on List | 134 | Each | 42.87 | 5744.58 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6692-00750 | 6692 | 2018-09-18 17:08 | Section 4 | Material | Not on List | Not on List | 4 | Each | 185 | 740 | Not Sure | 2018-09-26 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 134 | Each | 7.06 | 946.04 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Not on List | Not on List | 60 | Each | 172.02 | 10321.2 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23718-001025 | 23718 | 2019-09-16 10:28 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No. | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23718-001025 | 23718 | 2019-09-16 10:28 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No. | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23535-001025 | 23535 | 2019-09-11 16:56 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 66 | Each | 37.6 | 2481.6 | Plastic Drainage | 2019-09-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23535-001025 | 23535 | 2019-09-11 16:56 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 66 | Each | 7.06 | 465.96 | Plastic Drainage | 2019-09-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23535-001025 | 23535 | 2019-09-11 16:56 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 20 | Each | 2.97 | 59.4 | Plastic Drainage | 2019-09-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23564-001025 | 23564 | 2019-09-12 11:25 | Section 4 | Material | Not on List | Not on List | 0.892 | Tonne | 538 | 479.9 | Rebar and Mesh | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 832 | no | 4.43 | 3685.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23513 | 23513 | 2019-09-11 12:41 | Core | Material | Not on List | Not on List | 1 | SM | 6000 | 6000 | Miscellaneous | 2019-09-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-23589-001025 | 23589 | 2019-09-12 16:04 | Section 3 | Material | Not on List | Not on List | 2 | 7717344434 | 122.5 | 245 | Ductile Drainage | 2019-09-16 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6692-00750 | 6692 | 2018-09-18 17:08 | Section 4 | Material | NULL | NULL | 1 | Each | 65 | 65 | Not Sure | 2018-09-26 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23697-001025 | 23697 | 2019-09-16 06:26 | Core | Material | PPE, Small Tools and Consumables | Not on List | 929.4 | Each | 1 | 929.4 | Janitorial | 2019-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23713-001025 | 23713 | 2019-09-16 09:17 | Section 3 | Material | Not on List | Not on List | 2 | EA | 10.23 | 20.46 | Miscellaneous | 2019-09-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23713-001025 | 23713 | 2019-09-16 09:17 | Section 3 | Material | Not on List | Not on List | 4 | EA | 1.77 | 7.08 | Miscellaneous | 2019-09-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | NULL | NULL | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23440-001025 | 23440 | 2019-09-10 12:33 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | NULL | NULL | 8 | Each | 30 | 240 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23769-001025 | 23769 | 2019-09-17 08:05 | Section 2 | Material | Saint Gobain Castings | Not on List | 3 | units | NULL | 0 | Concrete Drainage | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23769-001025 | 23769 | 2019-09-17 08:05 | Section 2 | Material | Saint Gobain Castings | Not on List | 3 | units | NULL | 0 | Concrete Drainage | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23769-001025 | 23769 | 2019-09-17 08:05 | Section 2 | Material | Not on List | Not on List | 10 | rolls | NULL | 0 | Builders Merchants (General) | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23769-001025 | 23769 | 2019-09-17 08:05 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Tonne | 32.74 | 196.44 | Concrete Drainage | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23769-001025 | 23769 | 2019-09-17 08:05 | Section 2 | Material | Combined Drainage | Not on List | 10 | boxes | NULL | 0 | Concrete Drainage | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23724-001025 | 23724 | 2019-09-16 11:24 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23726-001025 | 23726 | 2019-09-16 12:22 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23585-001025 | 23585 | 2019-09-12 15:05 | Section 4 | Material | Not on List | Not on List | 250 | Load | 95 | 23750 | Aggregate | 2019-09-12 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23585-001025 | 23585 | 2019-09-12 15:05 | Section 4 | Material | Not on List | Not on List | 1370 | Load | 65 | 89050 | Aggregate | 2019-09-12 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23585-001025 | 23585 | 2019-09-12 15:05 | Section 4 | Material | Not on List | Not on List | 400 | Load | 95 | 38000 | Aggregate | 2019-09-12 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | SC4A - Roadworks - Swavesey to Robins Lane | 702 - Pavement | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-6710-00750 | 6710 | 2018-09-19 11:34 | Section 4 | Material | Iron Wear | Not on List | 113 | Each | 44 | 4972 | Ductile Drainage | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23585-001025 | 23585 | 2019-09-12 15:05 | Section 4 | Material | Not on List | Not on List | 850 | Load | 100 | 85000 | Aggregate | 2019-09-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 606 - Import | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23776-001025 | 23776 | 2019-09-17 11:05 | Section 2 | Material | Not on List | Not on List | 1 | NULL | 4545.54 | 4546 | Professional Services | 2019-09-19 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2A - Roadworks - A1 | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-23648-001025 | 23648 | 2019-09-13 11:46 | Section 4 | Material | Concrete Drainage | CPM 1050mm Concrete Rocker (890352) | 1 | Each | 384.68 | 384.68 | Concrete Drainage | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23648-001025 | 23648 | 2019-09-13 11:46 | Section 4 | Material | Concrete Drainage | CPM 1050mm Concrete Spigot (890380) | 1 | Each | 384.68 | 384.68 | Concrete Drainage | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23648-001025 | 23648 | 2019-09-13 11:46 | Section 4 | Material | Concrete Drainage | Not on List | 1 | Each | 289.78 | 289.78 | Concrete Drainage | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23648-001025 | 23648 | 2019-09-13 11:46 | Section 4 | Material | NULL | NULL | 1 | Each | 200 | 200 | Concrete Drainage | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23682-001025 | 23682 | 2019-09-13 16:28 | Section 5 | Material | Not on List | Not on List | 100 | EA | 4.97 | 497 | Builders Merchants (General) | 2019-09-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23682-001025 | 23682 | 2019-09-13 16:28 | Section 5 | Material | Not on List | Not on List | 10 | PK | 11.9 | 119 | Builders Merchants (General) | 2019-09-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23750-001025 | 23750 | 2019-09-16 17:50 | Section 5 | Material | Saint Gobain Castings | Not on List | 16 | EA | 58.04 | 928.64 | Builders Merchants (General) | 2019-09-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6710-00750 | 6710 | 2018-09-19 11:34 | Section 4 | Material | Iron Wear | Not on List | 1 | Each | 44 | 44 | Ductile Drainage | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23708-001025 | 23708 | 2019-09-16 08:54 | Section 3 | Material | Not on List | Not on List | 5 | Sheets | 10.44 | 52.2 | Builders Merchants (General) | 2019-09-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23781-001025 | 23781 | 2019-09-17 13:27 | Core | Material | Not on List | Not on List | 1 | each | 6637.86 | 6638 | Professional Services | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Buyers
MREQ-23747-001025 | 23747 | 2019-09-16 17:35 | Section 5 | Material | Not on List | NULL | 200 | EA | 7.5 | 1500 | Surveying Consumables | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23754-001025 | 23754 | 2019-09-16 18:24 | Section 5 | Material | Not on List | NULL | 8 | EA | 28.28 | 226.24 | Plastic Drainage | 2019-09-19 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23753-001025 | 23753 | 2019-09-16 18:04 | Section 5 | Material | Not on List | NULL | 1 | SM | 2828.92 | 2828.92 | Plastic Drainage | 2019-09-19 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6710-00750 | 6710 | 2018-09-19 11:34 | Section 4 | Material | Iron Wear | Not on List | 2 | Each | 50 | 100 | Ductile Drainage | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6710-00750 | 6710 | 2018-09-19 11:34 | Section 4 | Material | Iron Wear | Not on List | 4 | Each | 250 | 1000 | Ductile Drainage | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23517-001025 | 23517 | 2019-09-11 13:55 | Core | Material | NULL | NULL | 1 | EACH | 5630.75 | 5630.75 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6713-00750 | 6713 | 2018-09-19 11:32 | Section 4 | Material | Not on List | Not on List | 36 | Each | 4.55 | 163.8 | Miscellaneous | 2018-09-20 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6714-00750 | 6714 | 2018-09-19 12:37 | Section 4 | Material | Not on List | Not on List | 1 | Each | 94.19 | 94.19 | Concrete Drainage | 2018-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23832-001025 | 23832 | 2019-09-18 08:28 | Section 4 | Material | Not on List | Not on List | 2 | Each | NULL | 0 | Miscellaneous | 2019-09-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23835-001025 | 23835 | 2019-09-18 09:18 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21183-001025 | 21183 | 2019-07-23 10:02 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23836-001025 | 23836 | 2019-09-18 09:31 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23788-001025 | 23788 | 2019-09-17 14:36 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-09-18 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23839-001025 | 23839 | 2019-09-18 10:36 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Surveying Consumables | 2019-09-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | IMO Queue | Yes - Approve | NULL | REQ - Buyers
MREQ-6714-00750 | 6714 | 2018-09-19 12:37 | Section 4 | Material | NULL | NULL | 2 | Each | 6 | 12 | Concrete Drainage | 2018-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22092-001025 | 22092 | 2019-08-09 15:43 | Core | Material | Not on List | Not on List | 6 | NULL | 3.95 | 24 | Miscellaneous | 2019-08-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | NULL | 115 - Medical / 1st Aid | IMO Queue | Yes - Approve | NULL | REQ - Buyers
MREQ-23784-001025 | 23784 | 2019-09-17 13:50 | Section 4 | Material | Not on List | Not on List | 2 | Number | 8.67 | 17.34 | Surveying Consumables | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23784-001025 | 23784 | 2019-09-17 13:50 | Section 4 | Material | Not on List | Not on List | 2 | Number | 22 | 44 | Surveying Consumables | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23735-001025 | 23735 | 2019-09-16 14:37 | Core | Material | NULL | NULL | 5000 | EA | 0.51 | 2550 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23722-001025 | 23722 | 2019-09-16 11:17 | Core | Material | NULL | NULL | 1 | Each | 1378.5 | 1378.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23768-001025 | 23768 | 2019-09-17 08:09 | Section 3 | Material | Not on List | Not on List | 30 | No | 53.75 | 1612.5 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6714-00750 | 6714 | 2018-09-19 12:37 | Section 4 | Material | NULL | NULL | 2 | Each | 6 | 12 | Concrete Drainage | 2018-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23768-001025 | 23768 | 2019-09-17 08:09 | Section 3 | Material | Not on List | Not on List | 1 | roll 700mtrs | 73.5 | 73.5 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23821-001025 | 23821 | 2019-09-18 07:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 49.16 | 49.16 | Fuel | 2019-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23829-001025 | 23829 | 2019-09-18 08:23 | Section 4 | Material | Not on List | Not on List | 200 | Each | 6.75 | 1350 | Concrete Drainage | 2019-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23569-001025 | 23569 | 2019-09-12 12:16 | Section 4 | Material | NULL | NULL | 45 | Eachch | 6 | 270 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23569-001025 | 23569 | 2019-09-12 12:16 | Section 4 | Material | NULL | NULL | 15 | Each | 6 | 90 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23569-001025 | 23569 | 2019-09-12 12:16 | Section 4 | Material | NULL | NULL | 80 | Each | 3.03 | 242.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23569-001025 | 23569 | 2019-09-12 12:16 | Section 4 | Material | NULL | NULL | 2 | Each | 31.85 | 63.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23569-001025 | 23569 | 2019-09-12 12:16 | Section 4 | Material | NULL | NULL | 80 | Each | 3.03 | 242.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6714-00750 | 6714 | 2018-09-19 12:37 | Section 4 | Material | NULL | NULL | 1 | Each | 80 | 80 | Concrete Drainage | 2018-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23837-001025 | 23837 | 2019-09-18 09:48 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.69 | 345 | Builders Merchants (General) | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23837-001025 | 23837 | 2019-09-18 09:48 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.31 | 131 | Builders Merchants (General) | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23871-001025 | 23871 | 2019-09-18 16:32 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5057-0022 | 5057 | 2018-08-14 12:26 | Section 4 | Material | Not on List | Not on List | 48 | Each | 6.45 | 0 | Miscellaneous | 2018-08-19 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6715-00750 | 6715 | 2018-09-19 12:34 | Section 4 | Material | Concrete Drainage | Not on List | 100 | Roll | 13.9 | 1390 | Builders Merchants (General) | 2018-09-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23871-001025 | 23871 | 2019-09-18 16:32 | Section 4 | Material | Not on List | Not on List | 28 | NULL | NULL | 0 | Plastic Drainage | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 13.44 | 201.6 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 35.35 | 353.5 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-11126-001025 | 11126 | 2019-01-17 12:25 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.79 | 167 | Miscellaneous | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11131-001025 | 11131 | 2019-01-17 13:34 | Section 3 | Material | Not on List | Not on List | 12 | NULL | 7.96 | 96 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11131-001025 | 11131 | 2019-01-17 13:34 | Section 3 | Material | Not on List | Not on List | 7 | NULL | 6.11 | 43 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8282 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Finance Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11070-001025 | 11070 | 2019-01-16 13:34 | Section 4 | Material | NULL | Not on List | 15 | EA | 23.9 | 358.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-21 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5508-00343 | 5508 | 2018-08-22 14:52 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Office Supplies | 2018-10-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11133-001025 | 11133 | 2019-01-17 14:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1061.42 | Each | 1 | 1061 | PPE | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 79.8 | 79.8 | Janitorial | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1424.48 | 1424.48 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 273.89 | 273.89 | PPE | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Staples Replacement 12mm For Staple Gun Box Of 1000 (770200) | 1 | NULL | 2.6 | 2.6 | Small Tools (Consumables) | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 19.8 | 19.8 | Small Tools (Consumables) | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Refill Air Care Pristine Wild Berries Air Fragrance 270ml (539229) | 6 | Each | 3.1 | 18.6 | Janitorial | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11126-001025 | 11126 | 2019-01-17 12:25 | Section 3 | Material | Not on List | Not on List | 60 | tins | 2.79 | 167.4 | Miscellaneous | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11135-001025 | 11135 | 2019-01-17 14:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 779 | 779 | Not Sure | 2019-01-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN10 - A1198 Ermine Street Overbridge | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11140-001025 | 11140 | 2019-01-17 16:08 | Section 3 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 20 | Each | 535 | 10700 | Geotextiles | 2019-01-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5491-00320 | 5491 | 2018-08-22 10:49 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 154.76 | 154.76 | Small Tools (Consumables) | 2018-08-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11154-001025 | 11154 | 2019-01-17 15:32 | Section 3 | Material | Not on List | Not on List | 1 | Each | 114.5 | 115 | Miscellaneous | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11162-001025 | 11162 | 2019-01-17 20:58 | Section 3 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 5 | Each | 535 | 2675 | Geotextiles | 2019-01-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10890-001025 | 10890 | 2019-01-11 13:49 | Section 4 | Material | Not on List | Not on List | 1 | no | 2267.6 | 2267.6 | Concrete Drainage | 2019-01-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11171-001025 | 11171 | 2019-01-18 09:16 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 650 | 2600 | Miscellaneous | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11131-001025 | 11131 | 2019-01-17 13:34 | Section 3 | Material | Not on List | Not on List | 12 | NULL | 7.96 | 95.52 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11131-001025 | 11131 | 2019-01-17 13:34 | Section 3 | Material | Not on List | Not on List | 7 | NULL | 6.11 | 42.77 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11059-001025 | 11059 | 2019-01-16 09:54 | Section 4 | Material | Not on List | Not on List | 6 | 10m Roll | 76.1 | 456.6 | Concrete Accessories | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN24 - Girton Interchange Bridge C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11140-001025 | 11140 | 2019-01-17 16:08 | Section 3 | Material | NULL | Tensar TX160 4m x 75m (150563) | 20 | Each | 535 | 10700 | Geotextiles | 2019-01-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11162-001025 | 11162 | 2019-01-17 20:58 | Section 3 | Material | NULL | Tensar TX160 4m x 75m (150563) | 5 | Each | 535 | 2675 | Geotextiles | 2019-01-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-11140-001025 | 11140 | 2019-01-17 16:08 | Section 3 | Material | NULL | Tensar TX160 4m x 75m (150563) | 20 | Each | 535 | 10700 | Geotextiles | 2019-01-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5491-00320 | 5491 | 2018-08-22 10:49 | Section 3 | Material | Not on List | Not on List | 25 | EA | 0.91 | 22.75 | Small Tools (Consumables) | 2018-08-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11182-001025 | 11182 | 2019-01-18 12:31 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Rocker (249380) | 4 | Each | 579.92 | 2320 | Concrete Drainage | 2019-01-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Socket (249381) | 2 | Each | 579.92 | 1160 | Concrete Drainage | 2019-01-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 3 | Each | 579.92 | 1740 | Concrete Drainage | 2019-01-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10868-001025 | 10868 | 2019-01-11 10:39 | Section 4 | Material | Not on List | Not on List | 16 | Rolls | 215 | 3440 | Not Sure | 2019-01-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11201-001025 | 11201 | 2019-01-18 14:37 | Section 4 | Material | Not on List | Not on List | 8 | boxes | NULL | 0 | Not Sure | 2019-01-22 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11242-001025 | 11242 | 2019-01-21 11:04 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1701 - Insitu Concrete | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11244-001025 | 11244 | 2019-01-21 11:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 889.5 | Each | 1 | 890 | PPE | 2019-01-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 20 | no. | NULL | 0 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 5 | no. | NULL | 0 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5491-00320 | 5491 | 2018-08-22 10:49 | Section 3 | Material | Not on List | Not on List | 2 | ea | 87 | 174 | Small Tools (Consumables) | 2018-08-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 2 | bags | NULL | 0 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 450 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 8 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 15 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 15 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 80 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 10 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | Not on List | Not on List | 2 | Rolls | NULL | 0 | Concrete Accessories | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | Not on List | Not on List | 1 | palett | NULL | 0 | Concrete Accessories | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Builders Merchants (General) | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 2 | Each | 59.17 | 118 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11295-001025 | 11295 | 2019-01-22 09:47 | Section 3 | Material | Not on List | Not on List | 70 | tonne | NULL | 0 | Reinforcement | 2019-02-24 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | BN16 - New Barns Lane Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11298-001025 | 11298 | 2019-01-22 10:28 | Section 3 | Material | Not on List | Not on List | 12 | No | NULL | 0 | Builders Merchants (General) | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5441-00286 | 5441 | 2018-08-21 14:38 | Section 4 | Material | Not on List | Not on List | 1050 | MT | 0.11 | 115.5 | Concrete Accessories | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11305-001025 | 11305 | 2019-01-22 11:08 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2019-01-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11182-001025 | 11182 | 2019-01-18 12:31 | Section 4 | Material | Not on List | Not on List | 1 | Each | 553.53 | 553.53 | Concrete Drainage | 2019-01-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11182-001025 | 11182 | 2019-01-18 12:31 | Section 4 | Material | NULL | Not on List | 1 | Each | 15 | 15 | Concrete Drainage | 2019-01-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 42 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11322-001025 | 11322 | 2019-01-22 16:03 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11334-001025 | 11334 | 2019-01-22 17:20 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Surveying Consumables | 2019-01-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11201-001025 | 11201 | 2019-01-18 14:37 | Section 4 | Material | Not on List | Not on List | 8 | Box | 63 | 504 | Not Sure | 2019-01-24 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Rocker (249380) | 4 | Each | 579.92 | 2319.68 | Concrete Drainage | 2019-01-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5441-00286 | 5441 | 2018-08-21 14:38 | Section 4 | Material | Not on List | Not on List | 96 | 2.5ltr | 17.64 | 1693.44 | Concrete Accessories | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Socket (249381) | 2 | Each | 579.92 | 1159.84 | Concrete Drainage | 2019-01-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 3 | Each | 579.92 | 1739.76 | Concrete Drainage | 2019-01-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | NULL | NULL | 1 | Each | 200 | 200 | Concrete Drainage | 2019-01-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 450 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 8 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 15 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 15 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 80 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 10 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 450 | No | 35.59 | 16015.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5441-00286 | 5441 | 2018-08-21 14:38 | Section 4 | Material | Not on List | Not on List | 2 | 5ltr | 81 | 162 | Concrete Accessories | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 8 | No | 38.85 | 310.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 15 | No | 39.22 | 588.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 15 | No | 39.22 | 588.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 80 | No | 39.22 | 3137.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 10 | No | 4.9 | 49 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11342-001025 | 11342 | 2019-01-23 08:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Number | NULL | 0 | PPE | 2019-01-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11345-001025 | 11345 | 2019-01-23 08:36 | Section 3 | Material | Not on List | Not on List | 4 | no | NULL | 0 | Electrical | 2019-01-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | GN3B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11353-001025 | 11353 | 2019-01-23 10:26 | Section 3 | Material | Aggregate | Type 1 | 1000 | Tonnes | 16 | 16000 | Aggregate | 2019-01-24 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | BN16 - New Barns Lane Overbridge | 1601 - Piling and attendances | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11305-001025 | 11305 | 2019-01-22 11:08 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 524.25 | 524.25 | Damage Charges | 2019-01-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Miscellaneous | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5440-00285 | 5440 | 2018-08-21 14:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 6.87 | 137.4 | Concrete Accessories | 2018-08-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Miscellaneous | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11366-001025 | 11366 | 2019-01-23 13:39 | Section 3 | Material | Geotextile | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 22 | Each | 110.27 | 2426 | Geotextiles | 2019-01-25 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | BN16 - New Barns Lane Overbridge | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11372-001025 | 11372 | 2019-01-23 15:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3922.74 | Each | 1 | 3923 | PPE | 2019-01-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 5 | Each | 90.48 | 452.4 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 10 | Each | 12.48 | 124.8 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 20 | Each | 5.51 | 110.2 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 7 | Each | 149.45 | 1046.15 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 7 | Each | 15.19 | 106.33 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 2 | Each | 92.06 | 184.12 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 3 | Each | 122.16 | 366.48 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 2 | Each | 79.28 | 158.56 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 42 | Each | 24.82 | 1042.44 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 50 | Each | 3.38 | 169 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.86 | 186 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 42 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | NULL | Not on List | NULL | NULL | NULL | 0 | NULL | NULL | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11345-001025 | 11345 | 2019-01-23 08:36 | Section 3 | Material | Not on List | Not on List | 4 | no | 241.07 | 964.28 | Electrical | 2019-01-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | GN3B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11397-001025 | 11397 | 2019-01-24 08:05 | Section 3 | Material | Not on List | Not on List | 12580 | Ton | 4 | 50320 | Aggregate | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 540 | 540 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8853-001024 | 8853 | 2018-11-07 17:37 | Section 3 | Material | Not on List | Not on List | 1 | No | 879.45 | 879.45 | Damage Charges | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9150-001025 | 9150 | 2018-11-14 15:04 | Section 3 | Material | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 128 | Each | 2.93 | 375 | Builders Merchants (General) | 2018-11-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8855-001024 | 8855 | 2018-11-08 07:22 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.35 | 70 | Miscellaneous | 2018-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9133-001025 | 9133 | 2018-11-14 12:05 | Section 3 | Material | Not on List | Not on List | 30 | m | 0.64 | 19.2 | Miscellaneous | 2018-11-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN06 - ECML Bridge | 1705 - Repairs to Existing Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5057-0022 | 5057 | 2018-08-14 12:26 | Section 4 | Material | Not on List | Not on List | 4 | boxes | NULL | 0 | Miscellaneous | 2018-08-19 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5239-00148 | 5239 | 2018-08-16 14:33 | Section 4 | Material | Not on List | Not on List | 225 | NULL | 56 | 12600 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9128-001025 | 9128 | 2018-11-14 10:42 | Section 4 | Material | Not on List | Not on List | 2 | Pack 100 | 76.5 | 153 | Miscellaneous | 2018-11-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9043-001024 | 9043 | 2018-11-13 07:16 | Section 4 | Material | Not on List | Not on List | 100 | Each | 21 | 2100 | Miscellaneous | 2018-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9043-001024 | 9043 | 2018-11-13 07:16 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.5 | 100 | Miscellaneous | 2018-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9043-001024 | 9043 | 2018-11-13 07:16 | Section 4 | Material | Not on List | Not on List | 75 | Each | 5.5 | 412.5 | Miscellaneous | 2018-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9137-001025 | 9137 | 2018-11-14 13:02 | Section 4 | Material | Not on List | Not on List | 1 | each | 796.45 | 796.45 | Damage Charges | 2018-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | Kerbs | Not on List | 4 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | Kerbs | Not on List | 4 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9091-001025 | 9091 | 2018-11-13 15:59 | Section 3 | Material | Not on List | Not on List | 14 | NULL | 32 | 448 | Miscellaneous | 2018-11-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8800-001024 | 8800 | 2018-11-07 07:41 | Section 4 | Material | Not on List | Not on List | 1 | Each | 114.41 | 114.41 | Damage Charges | 2018-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5239-00148 | 5239 | 2018-08-16 14:33 | Section 4 | Material | Not on List | Not on List | 225 | NULL | 9.33 | 2099.25 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Pipe 2.5m (249379) | 9 | Each | 483.27 | 4349.43 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Socket (249381) | 2 | Each | 579.92 | 1159.84 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 2 | Each | 579.92 | 1159.84 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9150-001025 | 9150 | 2018-11-14 15:04 | Section 3 | Material | NULL | Concrete Kerbs 125x150x914 HB Straight (898181) | 128 | Each | 2.93 | 375.04 | Builders Merchants (General) | 2018-11-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9188-001025 | 9188 | 2018-11-15 08:49 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 343.36 | 343.36 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 166.15 | 166.15 | Small Tools (Consumables) | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 211.34 | 211.34 | Janitorial | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 719.5 | 719.5 | PPE | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 11.6 | 11.6 | PPE | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5239-00148 | 5239 | 2018-08-16 14:33 | Section 4 | Material | Not on List | Not on List | 22 | NULL | NULL | 0 | NULL | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 9.51 | 95.1 | Janitorial | 2018-11-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.45 | 147 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8769-001024 | 8769 | 2018-11-06 15:08 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 2159 | 2159 | Not Sure | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9195-001025 | 9195 | 2018-11-15 10:50 | Section 3 | Material | Not on List | Not on List | 4 | Number | NULL | 0 | Miscellaneous | 2018-11-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9195-001025 | 9195 | 2018-11-15 10:50 | Section 3 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2018-11-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9195-001025 | 9195 | 2018-11-15 10:50 | Section 3 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2018-11-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8765-001024 | 8765 | 2018-11-06 14:57 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 3687.55 | 3687.55 | Not Sure | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 298.96 | 298.96 | Janitorial | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 203.8 | 203.8 | PPE | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5287-00223 | 5287 | 2018-08-17 12:25 | Section 4 | Material | Plastic Drainage | Not on List | 10 | no | NULL | 0 | Plastic Drainage | 2018-08-20 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 491.15 | 491.15 | Small Tools (Consumables) | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8759-001024 | 8759 | 2018-11-06 14:10 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1882.92 | 1882.92 | Damage Charges | 2018-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9200-001025 | 9200 | 2018-11-15 11:23 | Section 3 | Material | Not on List | Not on List | 4 | No | NULL | 0 | Builders Merchants (General) | 2018-11-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9205-001025 | 9205 | 2018-11-15 14:52 | Section 3 | Material | Not on List | Not on List | 1 | No. | 281.1 | 281 | Small Tools (Consumables) | 2018-11-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8734-001024 | 8734 | 2018-11-06 08:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 3615 | 3615 | Damage Charges | 2018-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8726-001024 | 8726 | 2018-11-06 07:50 | Section 4 | Material | Not on List | Not on List | 1 | Each | 864.64 | 864.64 | Damage Charges | 2018-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9210-001025 | 9210 | 2018-11-15 16:17 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Box | NULL | 0 | Miscellaneous | 2018-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9213-001025 | 9213 | 2018-11-15 16:19 | Section 3 | Material | Not on List | Not on List | 120 | kg | NULL | 0 | Miscellaneous | 2018-11-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9213-001025 | 9213 | 2018-11-15 16:19 | Section 3 | Material | Not on List | Not on List | 480 | no. | NULL | 0 | Miscellaneous | 2018-11-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5289-00224 | 5289 | 2018-08-17 13:08 | Section 4 | Material | Misc | Not on List | 1 | no | NULL | 0 | Small Tools (Consumables) | 2018-08-20 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8663-001023 | 8663 | 2018-11-05 07:57 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1324 | 1324 | Damage Charges | 2018-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9218-001025 | 9218 | 2018-11-15 16:36 | Section 4 | Material | Kerbs | Not on List | 30 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9188-001025 | 9188 | 2018-11-15 08:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 86.25 | 86.25 | Concrete Drainage | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9188-001025 | 9188 | 2018-11-15 08:49 | Section 4 | Material | NULL | Not on List | 1 | Each | 55 | 55 | Concrete Drainage | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9200-001025 | 9200 | 2018-11-15 11:23 | Section 3 | Material | Not on List | Not on List | 4 | No | 26.94 | 107.76 | Builders Merchants (General) | 2018-11-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9210-001025 | 9210 | 2018-11-15 16:17 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Box | NULL | 0 | Miscellaneous | 2018-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9213-001025 | 9213 | 2018-11-15 16:19 | Section 3 | Material | Not on List | Not on List | 120 | kg | 3.1 | 372 | Miscellaneous | 2018-11-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9213-001025 | 9213 | 2018-11-15 16:19 | Section 3 | Material | Not on List | Not on List | 480 | no. | 1.04 | 499.2 | Miscellaneous | 2018-11-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6694-001023 | 6694 | 2018-09-18 17:31 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9205-001025 | 9205 | 2018-11-15 14:52 | Section 3 | Material | Not on List | Not on List | 1 | No. | 281.1 | 281.1 | Small Tools (Consumables) | 2018-11-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | Not on List | Not on List | 13.12 | t | NULL | 0 | Reinforcement | 2018-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | Not on List | Not on List | 8 | number | NULL | 0 | Reinforcement | 2018-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9274-001025 | 9274 | 2018-11-16 12:04 | Section 4 | Material | Not on List | Not on List | 45 | number | NULL | 0 | Not Sure | 2018-12-09 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9195-001025 | 9195 | 2018-11-15 10:50 | Section 3 | Material | Not on List | Not on List | 20 | Number | 130 | 2600 | Miscellaneous | 2018-11-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9273-001025 | 9273 | 2018-11-16 11:40 | Section 4 | Material | Not on List | Not on List | 1965 | Each | 1 | 1965 | Waste (General) | 2018-11-19 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9273-001025 | 9273 | 2018-11-16 11:40 | Section 4 | Material | Not on List | Not on List | 3930 | Each | 1 | 3930 | Waste (General) | 2018-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9349-001025 | 9349 | 2018-11-20 08:00 | Section 3 | Material | Not on List | Not on List | 4 | No | NULL | 0 | Builders Merchants (General) | 2018-11-22 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9349-001025 | 9349 | 2018-11-20 08:00 | Section 3 | Material | Not on List | Not on List | 4 | No | 105.04 | 420.16 | Builders Merchants (General) | 2018-11-22 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 200 | Each | 16.95 | 3390 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 1 | Each | 33.28 | 33.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 4 | Each | 33.28 | 133.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 4 | Each | 33.28 | 133.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 25 | Each | 33.28 | 832 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 5 | Each | 192.08 | 960.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9362-001025 | 9362 | 2018-11-20 11:19 | Section 3 | Material | Not on List | Not on List | 500 | no. | NULL | 0 | Miscellaneous | 2018-11-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | NULL | Not on List | 10 | Each | 7.06 | 70.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | NULL | Not on List | 4 | Each | 6.73 | 26.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5323-00228 | 5323 | 2018-08-20 08:32 | Section 4 | Material | Not on List | NULL | 2.28 | Tonnes | 538 | 1226.64 | Rebar and Mesh | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | NULL | Not on List | 4 | Each | 6.73 | 26.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9362-001025 | 9362 | 2018-11-20 11:19 | Section 3 | Material | Not on List | Not on List | 500 | no. | 0.09 | 45 | Miscellaneous | 2018-11-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5324-00229 | 5324 | 2018-08-20 08:36 | Section 4 | Material | Not on List | NULL | 0.411 | Tonnes | 538 | 221.12 | Rebar and Mesh | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9367-001025 | 9367 | 2018-11-20 13:27 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 3133.04 | 3133.04 | Janitorial | 2018-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9218-001025 | 9218 | 2018-11-15 16:36 | Section 4 | Material | NULL | Not on List | 30 | Each | 19.02 | 570.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9218-001025 | 9218 | 2018-11-15 16:36 | Section 4 | Material | NULL | Not on List | 1 | Each | 115 | 115 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9385-001025 | 9385 | 2018-11-20 16:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9385-001025 | 9385 | 2018-11-20 16:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9385-001025 | 9385 | 2018-11-20 16:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 320.65 | 320.65 | Small Tools (Consumables) | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9385-001025 | 9385 | 2018-11-20 16:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 407.8 | 407.8 | PPE | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9408-001025 | 9408 | 2018-11-21 10:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5057-0022 | 5057 | 2018-08-14 12:26 | Section 4 | Material | Not on List | Not on List | 2 | number | NULL | 0 | Miscellaneous | 2018-08-19 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5225-00143 | 5225 | 2018-08-16 10:37 | Section 4 | Material | Not on List | Not on List | 72 | NULL | 3.41 | 245.52 | Not Sure | 2018-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9374-001025 | 9374 | 2018-11-20 15:04 | Section 4 | Material | Not on List | Not on List | 2 | Pack (100) | 38.97 | 77.94 | Miscellaneous | 2018-11-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9411-001025 | 9411 | 2018-11-21 10:15 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1730 | 1730 | Professional Services | 2018-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9327-001025 | 9327 | 2018-11-19 11:25 | Section 4 | Material | Not on List | Not on List | 120 | Each | 3.46 | 415.2 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9327-001025 | 9327 | 2018-11-19 11:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 42.45 | 169.8 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9327-001025 | 9327 | 2018-11-19 11:25 | Section 4 | Material | Not on List | Not on List | 10 | Each | 8.2 | 82 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9327-001025 | 9327 | 2018-11-19 11:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 52 | 208 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9327-001025 | 9327 | 2018-11-19 11:25 | Section 4 | Material | Not on List | Not on List | 3 | Each | 88.88 | 266.64 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9379-001025 | 9379 | 2018-11-20 14:42 | Section 4 | Material | Not on List | Not on List | 2 | coils | 44.8 | 89.6 | Not Sure | 2018-11-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9379-001025 | 9379 | 2018-11-20 14:42 | Section 4 | Material | Not on List | Not on List | 20 | coils | 46.5 | 930 | Not Sure | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9372-001025 | 9372 | 2018-11-20 14:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Box 10 | 32.72 | 981.6 | Miscellaneous | 2018-11-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5225-00143 | 5225 | 2018-08-16 10:37 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 18.08 | 72.32 | Not Sure | 2018-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9372-001025 | 9372 | 2018-11-20 14:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | 0.73 | 73 | Miscellaneous | 2018-11-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9376-001025 | 9376 | 2018-11-20 15:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 398.6 | 398.6 | Janitorial | 2018-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9417-001025 | 9417 | 2018-11-21 12:04 | Section 3 | Material | Not on List | Not on List | 7 | NULL | 38.95 | 273 | Miscellaneous | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9377-001025 | 9377 | 2018-11-20 15:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 523.14 | 523.14 | Small Tools (Consumables) | 2018-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9391-001025 | 9391 | 2018-11-20 17:07 | Section 4 | Material | Not on List | Not on List | 400 | 25m rolls | 12.8 | 5120 | Miscellaneous | 2018-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9423-001025 | 9423 | 2018-11-21 14:12 | Section 3 | Material | Not on List | Not on List | 1 | ea | 447.5 | 448 | Damage Charges | 2018-11-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9380-001025 | 9380 | 2018-11-20 16:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 30.24 | 604.8 | Small Tools (Consumables) | 2018-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5225-00143 | 5225 | 2018-08-16 10:37 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 214.53 | 214.53 | Not Sure | 2018-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9371-001025 | 9371 | 2018-11-20 14:40 | Section 4 | Material | Not on List | Not on List | 6 | Each | 79.99 | 479.94 | Miscellaneous | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | Not on List | Not on List | 24.967 | Tonne | 538 | 13432.25 | Rebar and Mesh | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | Not on List | Not on List | 8 | Each | 5.16 | 41.28 | Rebar and Mesh | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | NULL | Not on List | 16 | Each | 3.25 | 52 | Rebar and Mesh | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | NULL | Not on List | 16 | Each | 2.78 | 44.48 | Rebar and Mesh | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9454-001025 | 9454 | 2018-11-22 07:32 | Section 3 | Material | Bagged | Not on List | 1 | palette | NULL | 0 | Builders Merchants (General) | 2018-11-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5289-00224 | 5289 | 2018-08-17 13:08 | Section 4 | Material | Misc | Not on List | 1 | no | 429 | 0 | Small Tools (Consumables) | 2018-08-20 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9458-001025 | 9458 | 2018-11-22 08:11 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-11-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 941 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11398-001025 | 11398 | 2019-01-24 08:31 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 42 | 25kg Bag | 9.48 | 398 | Miscellaneous | 2019-01-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 24 | NULL | 5.98 | 143.52 | Miscellaneous | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 24 | NULL | 5.98 | 143.52 | Miscellaneous | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 12.32 | 12.32 | Miscellaneous | 2019-01-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11295-001025 | 11295 | 2019-01-22 09:47 | Section 3 | Material | Not on List | Not on List | 70 | tonne | 538 | 37660 | NULL | 2019-02-24 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | BN16 - New Barns Lane Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11366-001025 | 11366 | 2019-01-23 13:39 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 22 | Each | 110.27 | 2425.94 | Geotextiles | 2019-01-25 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | PLM3 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Concrete Drainage | Not on List | 60 | Each | 17.14 | 1028.4 | Concrete Drainage | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | NULL | Each | 81.73 | 0 | Miscellaneous | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Saint Gobain Castings | 430x370x100 D400 Watershed GG&F (376797) | 12 | Each | 34 | 408 | Miscellaneous | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Twinwall | Not on List | 25 | Each | 37.18 | 929.5 | Plastic Drainage | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Not on List | Not on List | 12 | Rolls | 6.4 | 76.8 | Fixings and Fasteners | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Ducting | Polypipe 94mm x 6m Black Ridgiduct (877654) | 45 | Each | 11.33 | 509.85 | Electrical | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Ducting | Not on List | 105 | each | 0.36 | 37.8 | Electrical | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Not on List | Not on List | 30 | Each | 3.36 | 100.8 | Miscellaneous | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19492-001025 | 19492 | 2019-06-21 10:14 | Section 3 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 40 | Each | 81.73 | 3269.2 | Ductile Drainage | 2019-06-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19492-001025 | 19492 | 2019-06-21 10:14 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 40 | Each | 18.43 | 737.2 | Concrete Drainage | 2019-06-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19747-001025 | 19747 | 2019-06-26 10:29 | Section 3 | Material | Waste Management | Dry Mixed Recycling - Wheelie Bin 1100 Litre | 100 | Each | 7 | 700 | Waste (Recycling) | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19747-001025 | 19747 | 2019-06-26 10:29 | Section 3 | Material | Waste Management | Municipal Waste - Wheelie Bin 1100 Litre | 100 | Each | 14.25 | 1425 | Waste (General) | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19747-001025 | 19747 | 2019-06-26 10:29 | Section 3 | Material | Waste Management | Food Waste - Wheelie Bin 240 Litre | 10 | Each | 10 | 100 | Waste (Recycling) | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19748-001025 | 19748 | 2019-06-26 10:02 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19451-001025 | 19451 | 2019-06-20 16:11 | Section 4 | Material | Not on List | Not on List | 2 | Number | 968.26 | 1936.52 | Small Tools (Consumables) | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19664-001025 | 19664 | 2019-06-25 09:57 | Section 4 | Material | Not on List | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19665-001025 | 19665 | 2019-06-25 10:00 | Section 4 | Material | Not on List | Not on List | 32 | Each | 28.8 | 921.6 | PPE | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19667-001025 | 19667 | 2019-06-25 10:04 | Section 4 | Material | Not on List | Not on List | 829.44 | Each | 1 | 829.44 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15789-001025 | 15789 | 2019-04-12 14:55 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 1 | Each | 370 | 370 | Waste (General) | 2019-04-15 | RVP 420 - A14 Eastbound - Opposite Crematorium | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19759-001025 | 19759 | 2019-06-26 12:21 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19761-001025 | 19761 | 2019-06-26 12:30 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19762-001025 | 19762 | 2019-06-26 12:41 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19778-001025 | 19778 | 2019-06-26 14:51 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19778-001025 | 19778 | 2019-06-26 14:51 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 1 | Load | 24.32 | 24 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19730-001025 | 19730 | 2019-06-26 08:33 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-06-27 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5098-0041 | 5098 | 2018-08-14 17:59 | Section 3 | Material | Not on List | Not on List | 1 | each | 321.52 | 321.52 | Damage Charges | 2018-08-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19796-001025 | 19796 | 2019-06-26 14:59 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-6919-00751 | 6919 | 2018-09-24 13:27 | Section 3 | Material | Not on List | Not on List | 6 | Frames | 2166.3 | 12997.8 | Fixings and Fasteners | 2018-10-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19796-001025 | 19796 | 2019-06-26 14:59 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19796-001025 | 19796 | 2019-06-26 14:59 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19796-001025 | 19796 | 2019-06-26 14:59 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19724-001025 | 19724 | 2019-06-26 08:02 | Section 4 | Material | Not on List | Not on List | 12 | EA | 13.5 | 162 | Builders Merchants (General) | 2019-06-28 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Level Spirit Heavy Duty Aluminium Spartan Pro 1200mm/4 (740561) | 5 | Each | 14.99 | 75 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289) | 10 | Each | 7.32 | 73 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Tank Dust Suppression Duro 13 Litre Ref Dp-dst-13l (766568) | 4 | Each | 33.95 | 136 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Rake Asphalt/Tarmac Flat Tooth Metal Handle Spartan Pro (762583) | 15 | Each | 17.28 | 259 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-6919-00751 | 6919 | 2018-09-24 13:27 | Section 3 | Material | Not on List | Not on List | 16 | Frames | 4357 | 69712 | Fixings and Fasteners | 2018-10-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Scraper First Task 75mm Stripping Knife Ref 14003020 (746838) | 10 | Each | 5.55 | 56 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Strap Lashing 8m Ratchet Hvy Duty 2 Tonne Load 5 Tonne Break (746483) | 15 | Each | 21.34 | 320 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-17781-001025 | 17781 | 2019-05-20 17:15 | Section 3 | Material | NULL | Not on List | 84 | No | 39.22 | 3294.48 | Concrete Drainage | 2019-05-22 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17946-001025 | 17946 | 2019-05-23 09:08 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Office Supplies | 2019-05-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17896-001025 | 17896 | 2019-05-22 13:13 | Section 4 | Material | Not on List | Not on List | 800 | EA | 0.04 | 32 | Concrete Accessories | 2019-05-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17896-001025 | 17896 | 2019-05-22 13:13 | Section 4 | Material | Not on List | Not on List | 3 | Pack 100 | 8.35 | 25.05 | Concrete Accessories | 2019-05-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17900-001025 | 17900 | 2019-05-22 13:23 | Section 4 | Material | Not on List | Not on List | 120 | EA | 8.43 | 1011.6 | Concrete Accessories | 2019-05-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17950-001025 | 17950 | 2019-05-23 09:31 | Section 1 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 2000 | Each | 0.37 | 740 | Builders Merchants (General) | 2019-05-27 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 2 | Each | 9.48 | 18.96 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17518-001025 | 17518 | 2019-05-16 09:56 | Core | Material | Not on List | Not on List | 1 | NULL | 831.27 | 831.27 | Training | 2019-05-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17518-001025 | 17518 | 2019-05-16 09:56 | Core | Material | Not on List | Not on List | 1 | NULL | 3207.03 | 3207.03 | Training | 2019-05-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17518-001025 | 17518 | 2019-05-16 09:56 | Core | Material | Not on List | Not on List | 1 | NULL | 8494.53 | 8494.53 | Training | 2019-05-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17518-001025 | 17518 | 2019-05-16 09:56 | Core | Material | Not on List | Not on List | 1 | NULL | 140 | 140 | Training | 2019-05-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17919-001025 | 17919 | 2019-05-22 16:56 | Section 3 | Material | Aggregate | Class 1A | 51 | Loads | 80 | 4080 | Aggregate | 2019-05-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6406-00695 | 6406 | 2018-09-12 12:51 | Section 3 | Material | Not on List | Not on List | 72 | ea | 2.45 | 176.4 | Miscellaneous | 2018-09-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17961-001025 | 17961 | 2019-05-23 10:37 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17961-001025 | 17961 | 2019-05-23 10:37 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17961-001025 | 17961 | 2019-05-23 10:37 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17966-001025 | 17966 | 2019-05-23 12:12 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17973-001025 | 17973 | 2019-05-23 13:09 | Section 2 | Material | Saint Gobain Castings | Not on List | 11 | number | NULL | 0 | Concrete Drainage | 2019-05-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17857-001025 | 17857 | 2019-05-22 07:51 | Section 3 | Material | NULL | Not on List | 60 | number | 2.47 | 148.2 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17784-001025 | 17784 | 2019-05-20 17:08 | Section 2 | Material | Not on List | Not on List | 25 | m | NULL | 0 | Plastic Drainage | 2019-05-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17784-001025 | 17784 | 2019-05-20 17:08 | Section 2 | Material | NULL | Polyipipe 150mm Ridgidrain Bend 90deg (878001) | 2 | Each | 8.25 | 16.5 | Plastic Drainage | 2019-05-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17784-001025 | 17784 | 2019-05-20 17:08 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 2 | Each | 1.98 | 3.96 | Plastic Drainage | 2019-05-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17784-001025 | 17784 | 2019-05-20 17:08 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2019-05-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17808-001025 | 17808 | 2019-05-21 12:40 | Section 4 | Material | Not on List | Not on List | 1 | No. | 240.77 | 240.77 | Surveying Consumables | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17812-001025 | 17812 | 2019-05-21 12:58 | Section 4 | Material | Not on List | Not on List | 1 | Each | 495 | 495 | Miscellaneous | 2019-05-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17854-001025 | 17854 | 2019-05-22 07:42 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1501.34 | 1501.34 | Miscellaneous | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17971-001025 | 17971 | 2019-05-23 12:43 | Section 4 | Material | Not on List | Not on List | 1 | Each | 91.14 | 91.14 | Miscellaneous | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18009-001025 | 18009 | 2019-05-24 07:30 | Core | Material | Not on List | Not on List | 1 | £ | 55 | 55 | Miscellaneous | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6452-00702 | 6452 | 2018-09-12 18:55 | Section 4 | Material | Not on List | Not on List | 1 | Each | 689.44 | 689.44 | Damage Charges | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18025-001025 | 18025 | 2019-05-24 09:36 | Section 5 | Material | Not on List | Not on List | 20 | no | NULL | 0 | Plastic Drainage | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 7 | Each | 32.74 | 229.18 | Blocks and Bricks | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | Not on List | Not on List | 1500 | number | 0.31 | 465 | Concrete Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | Not on List | Not on List | 200 | number | 2.47 | 494 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | Not on List | Not on List | 115 | ea | 11.51 | 1323.65 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 100 | Each | 2 | 200 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 50 | Each | 48.86 | 2443 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 90 | Each | 34.82 | 3133.8 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | Not on List | Not on List | 50 | ea | 13.75 | 687.5 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | Not on List | Not on List | 20 | ea | 36.8 | 736 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6510-00730 | 6510 | 2018-09-13 18:36 | Section 3 | Material | Not on List | Not on List | 300 | EA | 1.75 | 525 | Timber Products | 2018-09-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 401 - Safety Barriers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 60 | Each | 23.14 | 1388.4 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17787-001025 | 17787 | 2019-05-20 17:36 | Section 5 | Material | Concrete Drainage | NULL | 9 | NULL | 289 | 2601 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18038-001025 | 18038 | 2019-05-24 10:43 | Section 5 | Material | Not on List | Not on List | 12 | rolls | NULL | 0 | Builders Merchants (General) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | NULL | Req - S5 Buyers
MREQ-18042-001025 | 18042 | 2019-05-24 10:24 | Section 5 | Material | Not on List | Not on List | 4 | No | NULL | 0 | Plastic Drainage | 2019-05-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18043-001025 | 18043 | 2019-05-24 11:21 | Core | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Electrical | 2019-05-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-6467-00711 | 6467 | 2018-09-13 10:31 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2273.5 | 2273.5 | Damage Charges | 2018-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18051-001025 | 18051 | 2019-05-24 12:27 | Section 2 | Material | Waste Management | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2019-05-31 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 5 | bundles | 9 | 45 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 5 | bundles | 9 | 45 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 5 | Bundles | 9 | 45 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 5 | Bundles | 9 | 45 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 5 | Bundles | 9 | 45 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6518-00730 | 6518 | 2018-09-14 07:20 | Section 3 | Material | Not on List | Not on List | 60 | Kerbs | 5.75 | 345 | Builders Merchants (General) | 2018-09-19 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 10 | Boxes | 10 | 100 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 100 | No. | 7.5 | 750 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 2 | Reels | 10 | 20 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 100 | No. | 1.5 | 150 | Surveying Consumables | 2019-05-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 100 | No. | 1 | 100 | Surveying Consumables | 2019-05-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17998-001025 | 17998 | 2019-05-23 16:51 | Section 4 | Material | Not on List | Not on List | 46 | Pack | 168.35 | 7744.1 | Concrete Accessories | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17998-001025 | 17998 | 2019-05-23 16:51 | Section 4 | Material | Not on List | Not on List | 52 | Pack | 11 | 572 | Concrete Accessories | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17998-001025 | 17998 | 2019-05-23 16:51 | Section 4 | Material | Not on List | Not on List | 40 | Hun | 1.88 | 75.2 | Concrete Accessories | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17998-001025 | 17998 | 2019-05-23 16:51 | Section 4 | Material | Not on List | Not on List | 40 | Hun | 1.88 | 75.2 | Concrete Accessories | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18071-001025 | 18071 | 2019-05-24 14:38 | Core | Material | Not on List | Not on List | 1 | NULL | 198 | 198 | Miscellaneous | 2019-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6388-00683 | 6388 | 2018-09-12 10:04 | Section 3 | Material | Not on List | Not on List | 1 | EA | 803.63 | 803.63 | Damage Charges | 2018-09-13 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17606-001025 | 17606 | 2019-05-17 11:40 | Section 4 | Material | Not on List | Not on List | 230 | Each | 43.39 | 9979.7 | Miscellaneous | 2019-05-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17606-001025 | 17606 | 2019-05-17 11:40 | Section 4 | Material | Not on List | Not on List | 50 | Each | 31.44 | 1572 | Miscellaneous | 2019-05-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17606-001025 | 17606 | 2019-05-17 11:40 | Section 4 | Material | NULL | Not on List | 1 | Each | 600 | 600 | Miscellaneous | 2019-05-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17852-001025 | 17852 | 2019-05-22 07:08 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18100-001025 | 18100 | 2019-05-28 09:25 | Core | Material | Not on List | Not on List | 1 | ea | 1081 | 1081 | Training | 2019-05-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17955-001025 | 17955 | 2019-05-23 10:06 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | 5ltre | 16.57 | 66.28 | Laboratory Equipment / Certification | 2019-05-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18102-001025 | 18102 | 2019-05-28 10:14 | Section 2 | Material | Not on List | Not on List | 0.436 | t | NULL | 0 | Rebar and Mesh | 2019-05-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | 9.58 | 191.6 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | 9.58 | 191.6 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 10 | each | 9.58 | 95.8 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 4 | each | 21.57 | 86.28 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | 7.1 | 142 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | 7.1 | 142 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 10 | each | NULL | 0 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | 3 | 60 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 10 | each | 3 | 30 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 10 | each | 9.58 | 95.8 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | NULL | 0 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Bags | 7.9 | 158 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | 20 Fire Buckets | 342.5 | 342.5 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | PPE, Small Tools and Consumables | Scraper Boot Galvanised C/W Brushes (746900) | 15 | Each | 10.19 | 152.85 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | PPE, Small Tools and Consumables | Plant Nappy 1000mm X 685mm All Blue (600200) | 10 | Each | 101.96 | 1019.6 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 51.48 | 102.96 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Not on List | Not on List | 10 | Number | 3.54 | 35.4 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | NULL | Not on List | 150 | Each | 3.04 | 456 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | NULL | Not on List | 4 | Each | 67.2 | 268.8 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | NULL | Not on List | 6 | Each | 44.92 | 269.52 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18096-001025 | 18096 | 2019-05-28 07:18 | Section 2 | Material | NULL | Not on List | 165 | no. | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-05 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | Concrete Drainage | Not on List | 14 | NULL | 95.74 | 1340.36 | Concrete Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | Concrete Drainage | Not on List | 14 | NULL | 93.5 | 1309 | Concrete Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 45deg Junction (878038) | 10 | Each | 39.7 | 397 | Plastic Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | NULL | Polypipe 150mm x 150mm 90deg Junction (878008) | 3 | Each | 14.4 | 43.2 | Plastic Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 10 | Each | 1.98 | 19.8 | Plastic Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 30 | Each | 3.65 | 109.5 | Plastic Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6577-00749 | 6577 | 2018-09-17 10:27 | Section 3 | Material | Not on List | Not on List | 61 | NULL | 538 | 32818 | NULL | 2018-09-27 | Gate C - 1339702 - BN06 (East Coast Railway) Via Logistics Yard Access | BN06 - ECML Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 6 | Each | 7.06 | 42.36 | Plastic Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17940-001025 | 17940 | 2019-05-23 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 661.1 | 661.1 | Small Tools (Consumables) | 2019-05-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17875-001025 | 17875 | 2019-05-22 09:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 543.64 | 543.64 | Small Tools (Consumables) | 2019-05-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18117-001025 | 18117 | 2019-05-28 12:34 | Section 5 | Material | Waste Management | Construction Waste - Skip 12 cubic yard | 1 | Each | 2400 | 2400 | Waste (General) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17993-001025 | 17993 | 2019-05-23 16:06 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 11 | 55 | Laboratory Equipment / Certification | 2019-05-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6416-00697 | 6416 | 2018-09-12 13:56 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 50 | 50 | Professional Services | 2018-09-12 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN16 - New Barns Lane Overbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18128-001025 | 18128 | 2019-05-28 15:11 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18131-001025 | 18131 | 2019-05-28 15:31 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-05-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18131-001025 | 18131 | 2019-05-28 15:31 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-05-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18131-001025 | 18131 | 2019-05-28 15:31 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17884-001025 | 17884 | 2019-05-22 10:09 | Section 4 | Material | Not on List | Not on List | 5 | boxes 200 | 36 | 180 | Surveying Consumables | 2019-05-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17954-001025 | 17954 | 2019-05-23 09:50 | Section 4 | Material | NULL | Not on List | 8 | EA | 47.89 | 383.12 | Electrical | 2019-05-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 2301 - Bridge Deck Expansion Joints | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17954-001025 | 17954 | 2019-05-23 09:50 | Section 4 | Material | NULL | Not on List | 6 | EA | 47.89 | 287.34 | Electrical | 2019-05-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 2301 - Bridge Deck Expansion Joints | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18119-001025 | 18119 | 2019-05-28 12:57 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18119-001025 | 18119 | 2019-05-28 12:57 | Section 6 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18144-001025 | 18144 | 2019-05-28 17:21 | Core | Material | Not on List | Not on List | 1 | NULL | 852 | 852 | Miscellaneous | 2019-05-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18083-001025 | 18083 | 2019-05-27 06:44 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18116-001025 | 18116 | 2019-05-28 12:04 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-05-29 | RVP 424 - Grange Farm – A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18122-001025 | 18122 | 2019-05-28 13:48 | Section 4 | Material | Aggregate | Not on List | 60 | ton | 21.65 | 1299 | Aggregate | 2019-05-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18133-001025 | 18133 | 2019-05-28 15:58 | Section 4 | Material | Not on List | Not on List | 5 | Ea | 69.14 | 345.7 | Rebar and Mesh | 2019-06-19 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 240 | Tubes | 24.1 | 5784 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 65 | No. | 24.84 | 1614.6 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 40 | No. | 21.78 | 871.2 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 50 | No. | 5.6 | 280 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 45 | No. | 3.91 | 175.95 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19814-001025 | 19814 | 2019-06-27 07:32 | Core | Material | Not on List | Not on List | 1 | NULL | 189.6 | 190 | Miscellaneous | 2019-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-18426-001025 | 18426 | 2019-06-03 10:54 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | No - Reject | REQ - Buyers
MREQ-19726-001025 | 19726 | 2019-06-26 08:06 | Section 5 | Material | Concrete Drainage | Not on List | 10 | ea | 148.8 | 1488 | Concrete Drainage | 2019-07-01 | NULL | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19829-001025 | 19829 | 2019-06-27 08:52 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 134 | Each | 37.6 | 5038.4 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 134 | Each | 7.06 | 946.04 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 268 | Each | 2.97 | 795.96 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 182 | ea | 130.26 | 23707.32 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | NULL | ea | NULL | 0 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 182 | ea | 9.76 | 1776.32 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 140 | ea | 167.88 | 23503.2 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | NULL | NULL | NULL | 0 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6952-00752 | 6952 | 2018-09-25 08:33 | Section 3 | Material | Not on List | Not on List | 2 | Ea | 4.35 | 8.7 | Miscellaneous | 2018-09-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 140 | ea | 16.41 | 2297.4 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 132 | ea | 11.51 | 1519.32 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 132 | ea | 1.98 | 261.36 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 264 | ea | 0.91 | 240.24 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19753-001025 | 19753 | 2019-06-26 11:02 | Section 5 | Material | Kerbs | NULL | 18 | ea | 27.9 | 502.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-01 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19791-001025 | 19791 | 2019-06-26 16:06 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19709-001025 | 19709 | 2019-06-25 17:08 | Section 3 | Material | Not on List | Not on List | 1 | No. | 455.2 | 455.2 | Surveying Consumables | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19821-001025 | 19821 | 2019-06-27 08:11 | Section 5 | Material | Not on List | NULL | 50 | EA | 6.31 | 315.5 | Builders Merchants (General) | 2019-06-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19844-001025 | 19844 | 2019-06-27 11:58 | Section 2 | Material | Not on List | Not on List | 1 | each | 268.5 | 269 | Miscellaneous | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6978-00752 | 6978 | 2018-09-25 15:31 | Section 4 | Material | Aggregate | 6F5 | 1500 | Tonnes | 14.65 | 21975 | Aggregate | 2018-09-27 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 606 - Import | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 15 | Each | 8.55 | 128 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 15 | Each | 8.55 | 128 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 15 | Each | 8.55 | 128 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 15 | Each | 8.55 | 128 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19797-001025 | 19797 | 2019-06-26 16:35 | Section 3 | Material | Not on List | Not on List | 56 | No | 2.31 | 129.36 | Builders Merchants (General) | 2019-06-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6978-00752 | 6978 | 2018-09-25 15:31 | Section 4 | Material | Aggregate | 6F5 | 1500 | Tonnes | 14.65 | 21975 | Aggregate | 2018-09-28 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 606 - Import | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-19696-001025 | 19696 | 2019-06-25 14:54 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 920 | Each | 2.31 | 2125.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19659-001025 | 19659 | 2019-06-25 08:43 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 4 | Each | 70.99 | 283.96 | Concrete Drainage | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-19659-001025 | 19659 | 2019-06-25 08:43 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 10 | Each | 44.64 | 446.4 | Concrete Drainage | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-19659-001025 | 19659 | 2019-06-25 08:43 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 70 | Each | 17.14 | 1199.8 | Concrete Drainage | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-19839-001025 | 19839 | 2019-06-27 10:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 650 | Each | 1 | 650 | PPE | 2019-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19742-001025 | 19742 | 2019-06-26 09:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 509 | 509 | Laboratory Equipment / Certification | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19742-001025 | 19742 | 2019-06-26 09:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 220 | 220 | Laboratory Equipment / Certification | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19742-001025 | 19742 | 2019-06-26 09:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 485 | 485 | Laboratory Equipment / Certification | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19742-001025 | 19742 | 2019-06-26 09:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 315 | 315 | Laboratory Equipment / Certification | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19742-001025 | 19742 | 2019-06-26 09:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 350 | 350 | Laboratory Equipment / Certification | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19734-001025 | 19734 | 2019-06-26 08:58 | Core | Material | NULL | NULL | 1 | EAch | 1806.3 | 1806.3 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19899-001025 | 19899 | 2019-06-28 08:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 199 | 199 | Miscellaneous | 2019-07-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-19749-001025 | 19749 | 2019-06-26 10:47 | Section 4 | Material | Not on List | Not on List | 1 | Each | 67.5 | 67.5 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19764-001025 | 19764 | 2019-06-26 13:13 | Section 4 | Material | Not on List | Not on List | 25 | Number | 158.88 | 3972 | Miscellaneous | 2019-07-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19764-001025 | 19764 | 2019-06-26 13:13 | Section 4 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 16 | Each | 116.88 | 1870.08 | Geotextiles | 2019-07-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19721-001025 | 19721 | 2019-06-26 07:44 | Section 2 | Material | Not on List | Not on List | 25 | pots | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19721-001025 | 19721 | 2019-06-26 07:44 | Section 2 | Material | Not on List | Not on List | 5 | 500ml tin | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19721-001025 | 19721 | 2019-06-26 07:44 | Section 2 | Material | Not on List | Not on List | 3 | 25l drum | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19721-001025 | 19721 | 2019-06-26 07:44 | Section 2 | Material | Not on List | Not on List | 2 | number | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19739-001025 | 19739 | 2019-06-26 09:25 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-19915-001025 | 19915 | 2019-06-28 10:23 | Section 6 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Miscellaneous | 2019-07-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-19837-001025 | 19837 | 2019-06-27 10:17 | Section 4 | Material | Signage | Not on List | 3 | Each | 19.1712 | 57.51 | Miscellaneous | 2019-07-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5096-0040 | 5096 | 2018-08-14 17:48 | Section 3 | Material | Not on List | Not on List | 1 | each | 552.2 | 552.2 | Damage Charges | 2018-08-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6970-00752 | 6970 | 2018-09-25 14:06 | Section 3 | Material | Not on List | Not on List | 8 | ea | 57.5 | 460 | Damage Charges | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19177-001025 | 19177 | 2019-06-14 16:59 | Section 2 | Material | NULL | 2440x1220x18mm Shuttering Ply (683573) | 20 | Each | 24.32 | 486.4 | Concrete Accessories | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19177-001025 | 19177 | 2019-06-14 16:59 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Concrete Accessories | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19840-001025 | 19840 | 2019-06-27 11:23 | Section 2 | Material | Not on List | Not on List | 50 | Sheets | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19784-001025 | 19784 | 2019-06-26 15:40 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-06-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-19788-001025 | 19788 | 2019-06-26 15:57 | Section 4 | Material | Not on List | Not on List | 50 | rolls | 189 | 9450 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19788-001025 | 19788 | 2019-06-26 15:57 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 100 | Each | 10.5 | 1050 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19788-001025 | 19788 | 2019-06-26 15:57 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 200 | Each | 1.98 | 396 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19788-001025 | 19788 | 2019-06-26 15:57 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 400 | Each | 0.91 | 364 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19882-001025 | 19882 | 2019-06-28 07:37 | Section 5 | Material | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 16 | Each | 4.42 | 70.72 | Not Sure | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19936-001025 | 19936 | 2019-06-28 14:53 | Section 2 | Material | Not on List | Not on List | 1 | each | 46 | 46 | Laboratory Equipment / Certification | 2019-07-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19942-001025 | 19942 | 2019-06-28 14:59 | Section 6 | Material | Signage | Not on List | 2 | each | 240.55 | 481 | Professional Services | 2019-07-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19942-001025 | 19942 | 2019-06-28 14:59 | Section 6 | Material | Signage | Not on List | 2 | each | 240.55 | 481 | Professional Services | 2019-07-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19608-001025 | 19608 | 2019-06-24 13:18 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19795-001025 | 19795 | 2019-06-26 16:36 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16961-001025 | 16961 | 2019-05-07 15:53 | Section 4 | Material | Not on List | Not on List | 1 | Each | 21895.35 | 21895.35 | Miscellaneous | 2019-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19930-001025 | 19930 | 2019-06-28 14:16 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 22.5deg (878083) | 2 | Each | 81.47 | 162.94 | Plastic Drainage | 2019-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19930-001025 | 19930 | 2019-06-28 14:16 | Section 4 | Material | Twinwall | Not on List | 1 | Each | 214.39 | 214.39 | Plastic Drainage | 2019-07-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20004-001025 | 20004 | 2019-07-01 12:44 | Section 1 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Geotextiles | 2019-07-02 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 606 - Import | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 1 | No | 13.08 | 13.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 10 | Packs | 10.5 | 105 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-13802-001025 | 13802 | 2019-03-11 16:07 | Section 5 | Material | Signage | Not on List | 1 | each | 2597.16 | 2597.16 | Miscellaneous | 2019-03-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13591-001025 | 13591 | 2019-03-06 16:48 | Section 4 | Material | Not on List | Not on List | 1 | Each | 661.38 | 661.38 | Miscellaneous | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13786-001025 | 13786 | 2019-03-11 14:44 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 1 | Each | 150 | 150 | Waste (General) | 2019-03-18 | RVP 403 - 1339621 - Borrow Pit 5 A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13820-001025 | 13820 | 2019-03-12 07:07 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 50 | NULL | 3.59 | 180 | Miscellaneous | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13581-001025 | 13581 | 2019-03-06 16:08 | Core | Material | Not on List | Not on List | 1 | Each | 7750.5 | 7750.5 | Laboratory Equipment / Certification | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13794-001025 | 13794 | 2019-03-11 15:11 | Section 3 | Material | PPE, Small Tools and Consumables | Helmet Safety Jsp Evolite Skyworker White (272558) | 80 | Each | 28.8 | 2304 | PPE | 2019-03-13 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13770-001025 | 13770 | 2019-03-11 11:46 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 457.69 | 457.69 | PPE | 2019-03-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13770-001025 | 13770 | 2019-03-11 11:46 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 503.53 | 503.53 | Small Tools (Consumables) | 2019-03-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 10 | Packs | 10.5 | 105 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-13567-001025 | 13567 | 2019-03-06 14:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 28.8 | 288 | Small Tools (Consumables) | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13775-001025 | 13775 | 2019-03-11 12:32 | Section 3 | Material | Not on List | Not on List | 1 | EA | 382.07 | 382.07 | Damage Charges | 2019-03-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12933-001025 | 12933 | 2019-02-22 08:35 | Core | Material | Not on List | Not on List | 1 | number | 40 | 40 | Miscellaneous | 2019-02-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 110 - Welfare Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13531-001025 | 13531 | 2019-03-06 09:56 | Section 4 | Material | Not on List | Not on List | 1 | Each | 464.16 | 464.16 | Miscellaneous | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13496-001025 | 13496 | 2019-03-05 12:57 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1972 | 1972 | Miscellaneous | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13837-001025 | 13837 | 2019-03-12 09:55 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13839-001025 | 13839 | 2019-03-12 10:03 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-13 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S1 Buyers
MREQ-13840-001025 | 13840 | 2019-03-12 10:09 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13540-001025 | 13540 | 2019-03-06 11:15 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 3484 | 3484 | Miscellaneous | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13573-001025 | 13573 | 2019-03-06 15:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 626.39 | 626.39 | Miscellaneous | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13774-001025 | 13774 | 2019-03-11 12:24 | Core | Material | Not on List | Not on List | 1 | Each | 795 | 795 | Training | 2019-04-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12848-001025 | 12848 | 2019-02-21 12:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1158.07 | 1158.07 | Miscellaneous | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13851-001025 | 13851 | 2019-03-12 11:39 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13853-001025 | 13853 | 2019-03-12 11:50 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-4994-009 | 4994 | 2018-08-13 15:28 | Section 3 | Material | Not on List | NULL | 4 | No. | 82.5 | 0 | Builders Merchants (General) | 2018-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12845-001025 | 12845 | 2019-02-21 12:09 | Section 4 | Material | Not on List | Not on List | 1 | Each | 423.38 | 423.38 | Miscellaneous | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13784-001025 | 13784 | 2019-03-11 14:09 | Section 3 | Material | Not on List | Not on List | 50 | sht | 22.5 | 1125 | Timber Products | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13784-001025 | 13784 | 2019-03-11 14:09 | Section 3 | Material | Not on List | Not on List | 30 | ea | 4.08 | 122.4 | Timber Products | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13784-001025 | 13784 | 2019-03-11 14:09 | Section 3 | Material | Not on List | Not on List | 30 | ea | 5.95 | 178.5 | Timber Products | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13862-001025 | 13862 | 2019-03-12 13:12 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Miscellaneous | 2019-03-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13862-001025 | 13862 | 2019-03-12 13:12 | Section 4 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Miscellaneous | 2019-03-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13862-001025 | 13862 | 2019-03-12 13:12 | Section 4 | Material | Not on List | Not on List | 20 | m | NULL | 0 | Miscellaneous | 2019-03-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12602-001025 | 12602 | 2019-02-18 07:18 | Section 4 | Material | Not on List | Not on List | 1 | Each | 6231.62 | 6231.62 | Miscellaneous | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Waste (Recycling) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Dustpan And Brush Set Blue Ref P.8003/P (540001) | 15 | Each | 0.75 | 11 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Boxes | NULL | 0 | PPE | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pack | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27526-001025 | 27526 | 2019-12-10 11:22 | Section 4 | Material | Not on List | Not on List | 10 | Number. | 11.5 | 115 | Surveying Consumables | 2019-12-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27526-001025 | 27526 | 2019-12-10 11:22 | Section 4 | Material | Not on List | Not on List | 10 | Number. | 9 | 90 | Surveying Consumables | 2019-12-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27541-001025 | 27541 | 2019-12-10 15:28 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 243 | 972 | Builders Merchants (General) | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27549-001025 | 27549 | 2019-12-10 17:28 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 176.22 | 176 | Small Tools (Consumables) | 2019-12-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27549-001025 | 27549 | 2019-12-10 17:28 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 193.4 | 193 | PPE | 2019-12-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27549-001025 | 27549 | 2019-12-10 17:28 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 180.93 | 181 | Janitorial | 2019-12-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27568-001025 | 27568 | 2019-12-11 10:45 | Section 6 | Material | Not on List | Not on List | 2 | NULL | 153.68 | 307 | Miscellaneous | 2019-12-19 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27572-001025 | 27572 | 2019-12-11 13:02 | Section 2 | Material | Not on List | Not on List | 1 | ea | 2838.55 | 2839 | Professional Services | 2019-11-29 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27573-001025 | 27573 | 2019-12-11 13:15 | Section 5 | Material | Not on List | Not on List | 1 | ea | 805.24 | 805 | Professional Services | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27574-001025 | 27574 | 2019-12-11 13:24 | Core | Material | Not on List | Not on List | 1 | No | 397.58 | 398 | Professional Services | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27576-001025 | 27576 | 2019-12-11 14:13 | Section 4 | Material | Not on List | Not on List | 1 | no | 5521.63 | 5522 | Professional Services | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27555-001025 | 27555 | 2019-12-11 07:40 | Section 4 | Material | Not on List | Not on List | 40 | Each | 19.51 | 780.4 | Builders Merchants (General) | 2019-12-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27555-001025 | 27555 | 2019-12-11 07:40 | Section 4 | Material | Not on List | Not on List | 2 | Each | 33.35 | 66.7 | Builders Merchants (General) | 2019-12-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27585-001025 | 27585 | 2019-12-11 16:15 | Section 6 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27606-001025 | 27606 | 2019-12-12 10:15 | Section 5 | Material | Not on List | Not on List | 1 | No | 183.27 | 183 | Professional Services | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27607-001025 | 27607 | 2019-12-12 10:40 | Section 5 | Material | Not on List | Not on List | 1 | No | 483.47 | 483 | Professional Services | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27617-001025 | 27617 | 2019-12-12 12:00 | Section 4 | Material | Not on List | Not on List | 1 | No | 1297.76 | 1298 | Professional Services | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27619-001025 | 27619 | 2019-12-12 12:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 25 | NULL | 1.2 | 30 | Small Tools (Consumables) | 2019-12-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27619-001025 | 27619 | 2019-12-12 12:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | 11.52 | 58 | Small Tools (Consumables) | 2019-12-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27622-001025 | 27622 | 2019-12-12 13:39 | Section 5 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 80 | Each | 3.56 | 285 | Builders Merchants (General) | 2019-12-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27623-001025 | 27623 | 2019-12-12 13:42 | Section 4 | Material | Not on List | Not on List | 25 | NULL | NULL | 0 | Plastic Drainage | 2020-01-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-27623-001025 | 27623 | 2019-12-12 13:42 | Section 4 | Material | Not on List | Not on List | 25 | NULL | NULL | 0 | Plastic Drainage | 2020-01-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-27623-001025 | 27623 | 2019-12-12 13:42 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2020-01-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-27496-001025 | 27496 | 2019-12-09 15:54 | Section 4 | Material | Not on List | Not on List | 2 | Each | 162.11 | 324.22 | Concrete Drainage | 2019-12-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27496-001025 | 27496 | 2019-12-09 15:54 | Section 4 | Material | NULL | Not on List | 1 | Each | 95 | 95 | Concrete Drainage | 2019-12-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27631-001025 | 27631 | 2019-12-12 16:25 | Core | Material | Not on List | Not on List | 1 | NULL | 67.2 | 67 | Office Supplies | 2019-12-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27600-001025 | 27600 | 2019-12-12 08:29 | Section 6 | Material | Not on List | Not on List | 2 | ea | 90.14 | 180.28 | Concrete Accessories | 2019-12-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 1 | Each | 812.44 | 812.44 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 1 | Each | 230.22 | 230.22 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 1 | Each | 738.67 | 738.67 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 1 | Each | 265.78 | 265.78 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 2 | Each | 80 | 160 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 1 | Each | 75 | 75 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 42 | Each | 10.34 | 434.28 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 30 | Each | 1.98 | 59.4 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 121 | Each | 24.99 | 3023.79 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 200 | Each | 3.65 | 730 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 460 | Each | 2 | 920 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 41 | Each | 37.6 | 1541.6 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 80 | Each | 7.06 | 564.8 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 190 | Each | 2.97 | 564.3 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 25 | Each | 130.26 | 3256.5 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 225mm x 150mm Ridgidrain 45deg Junction (878038) | 20 | Each | 42.87 | 857.4 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 10 | Each | 42.87 | 428.7 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Not on List | 12 | Each | 42.88 | 514.56 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 300mm x 150mm Ridgidrain 45deg Junction (878090) | 23 | Each | 47.96 | 1103.08 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 300mm x 150mm Ridgidrain 90deg Junction (878089) | 5 | Each | 44.41 | 222.05 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Not on List | 2 | Each | 47.96 | 95.92 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Not on List | 5 | Each | 177.52 | 887.6 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | CPM 1500 Cover Slab 750x600 Opening (528492) | 37 | Each | 61.54 | 2276.98 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 25 | Each | 38.08 | 952 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 14 | Each | 55.13 | 771.82 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 750 D/S (913226) | 2 | Each | 63.93 | 127.86 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | Not on List | 45 | Each | 257.78 | 11600.1 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | Not on List | 120 | Each | 17.15 | 2058 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | Not on List | 5 | Each | 33.32 | 166.6 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Saint Gobain Castings | Not on List | 31 | Each | 102 | 3162 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Twinwall | Polypipe Road Gully 450mm x 900mm (573005) | 70 | Each | 15.17 | 1061.9 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Twinwall | Not on List | 90 | Each | 5.95 | 535.5 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Saint Gobain Castings | 430x370x100 D400 Watershed GG&F (923947) | 90 | Each | 31.37 | 2823.3 | Ductile Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27628-001025 | 27628 | 2019-12-12 15:27 | Section 5 | Material | NULL | NULL | 2 | Each | 112 | 224 | Miscellaneous | 2020-01-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27628-001025 | 27628 | 2019-12-12 15:27 | Section 5 | Material | NULL | NULL | 2 | Each | 364 | 728 | Miscellaneous | 2020-01-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27567-001025 | 27567 | 2019-12-11 09:43 | Section 5 | Material | NULL | NULL | 1 | Each | 4140 | 4140 | Miscellaneous | 2019-12-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27491-001025 | 27491 | 2019-12-09 15:50 | Section 5 | Material | Aggregate | Not on List | 8425.2 | Tonne | 5.5 | 46338.6 | Aggregate | 2019-12-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27065-001025 | 27065 | 2019-11-27 16:57 | Section 3 | Material | Kerbs | Not on List | 1 | No | 1200 | 1200 | Professional Services | 2019-11-28 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | BN13 - West Brook Underbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27243-001025 | 27243 | 2019-12-03 09:10 | Core | Material | NULL | NULL | 1 | Each | 675 | 675 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27249-001025 | 27249 | 2019-12-03 09:50 | Core | Material | NULL | NULL | 1 | Each | 160 | 160 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27687-001025 | 27687 | 2019-12-16 10:37 | Core | Material | Not on List | Not on List | 1 | NULL | 487.5 | 488 | Miscellaneous | 2019-12-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27300-001025 | 27300 | 2019-12-03 17:41 | Core | Material | NULL | NULL | 1 | Each | 1137.5 | 1138 | Surveying Consumables | 2019-12-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 113 - Survey Equipment Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26943-001025 | 26943 | 2019-11-25 12:22 | Core | Material | Not on List | Not on List | 1 | application | 515 | 515 | Miscellaneous | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27334-001025 | 27334 | 2019-12-04 14:50 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27715-001025 | 27715 | 2019-12-17 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 4 | Each | 58.27 | 233.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-16 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 4 | Each | 13.08 | 52.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-16 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 1 | Each | 80 | 80 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-16 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 2 | Each | 164.35 | 328.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-16 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 2 | Each | 30.44 | 60.88 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 4 | Each | 17.32 | 69.28 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 46 | Each | 12 | 552 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 2 | Each | 21.5 | 43 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 1 | Each | 35 | 35 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27732-001025 | 27732 | 2019-12-17 14:15 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 289.03 | 289 | PPE | 2019-12-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27732-001025 | 27732 | 2019-12-17 14:15 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 185.08 | 185 | Small Tools (Consumables) | 2019-12-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27732-001025 | 27732 | 2019-12-17 14:15 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 109.98 | 110 | Janitorial | 2019-12-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27692-001025 | 27692 | 2019-12-16 07:24 | Section 4 | Material | Not on List | Not on List | 204 | Each | 14.43 | 2943.72 | Builders Merchants (General) | 2020-01-31 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27692-001025 | 27692 | 2019-12-16 07:24 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1200 | 1200 | Builders Merchants (General) | 2019-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 208 | Each | 7.5 | 1560 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 208 | Each | 49.95 | 10389.6 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 26 | Each | 39.6 | 1029.6 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 1 | Each | 600 | 600 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 120 | Each | 95 | 11400 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 50 | Each | 85 | 4250 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 1 | Each | 350 | 350 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7312-001022 | 7312 | 2018-10-02 17:29 | Section 4 | Material | Not on List | Not on List | 30 | Each | 44 | 1320 | Not Sure | 2018-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27759-001025 | 27759 | 2019-12-18 11:23 | Section 4 | Material | Not on List | Not on List | 1 | Number. | 630.54 | 631 | Surveying Consumables | 2019-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27763-001025 | 27763 | 2019-12-18 12:05 | Section 4 | Material | Not on List | Not on List | 1 | ea | 883 | 883 | Professional Services | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27680-001025 | 27680 | 2019-12-16 08:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 187687.9 | 187687.9 | Professional Services | 2019-12-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27758-001025 | 27758 | 2019-12-18 10:58 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 48.92 | 489.2 | Concrete Drainage | 2020-01-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27758-001025 | 27758 | 2019-12-18 10:58 | Section 4 | Material | Not on List | Not on List | 10 | Each | 70.62 | 706.2 | Concrete Drainage | 2020-01-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27758-001025 | 27758 | 2019-12-18 10:58 | Section 4 | Material | Not on List | Not on List | 5 | Each | 162.11 | 810.55 | Concrete Drainage | 2020-01-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27793-001025 | 27793 | 2019-12-19 12:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 200 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27794-001025 | 27794 | 2019-12-19 12:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27808-001025 | 27808 | 2019-12-19 16:21 | Section 6 | Material | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 19 | Each | 241.48 | 4588.12 | Concrete Drainage | 2020-01-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27814-001025 | 27814 | 2019-12-20 13:31 | Section 4 | Material | Not on List | Not on List | 1 | No | 4141.26 | 4141 | Professional Services | 2019-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27858-001025 | 27858 | 2020-01-06 09:59 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 60 | 60 | Surveying Consumables | 2020-01-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27861-001025 | 27861 | 2020-01-06 11:15 | Core | Material | Not on List | Not on List | 1 | NULL | 414 | 414 | Miscellaneous | 2020-01-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27864-001025 | 27864 | 2020-01-06 11:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-01-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27896-001025 | 27896 | 2020-01-07 09:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 228.6 | 229 | PPE | 2020-01-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27896-001025 | 27896 | 2020-01-07 09:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 524.1 | 524 | Janitorial | 2020-01-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27896-001025 | 27896 | 2020-01-07 09:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 405.6 | 406 | Small Tools (Consumables) | 2020-01-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27900-001025 | 27900 | 2020-01-07 11:23 | Core | Material | Not on List | Not on List | 4 | Number | 295 | 1180 | Surveying Consumables | 2020-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27906-001025 | 27906 | 2020-01-07 13:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27916-001025 | 27916 | 2020-01-07 16:35 | Section 4 | Material | Not on List | Not on List | 5 | Number | 8.67 | 43 | Surveying Consumables | 2020-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27916-001025 | 27916 | 2020-01-07 16:35 | Section 4 | Material | Not on List | Not on List | 5 | Number | 22 | 110 | Surveying Consumables | 2020-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27922-001025 | 27922 | 2020-01-07 19:45 | Section 4 | Material | Not on List | Not on List | 160 | each | NULL | 0 | Miscellaneous | 2020-01-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27927-001025 | 27927 | 2020-01-08 07:33 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 1 | pack | 24.32 | 24 | Timber Products | 2020-01-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27931-001025 | 27931 | 2020-01-08 08:50 | Section 2 | Material | Not on List | Not on List | 10 | ea | NULL | 0 | Concrete Accessories | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27932-001025 | 27932 | 2020-01-08 09:08 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-01-13 | 1333676 Swavesey Main Compound, J28 A14, High St Boxworth, CB23 4NG | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27933-001025 | 27933 | 2020-01-08 10:28 | Section 4 | Material | Aggregate | Not on List | 20 | Tonne | NULL | 0 | Aggregate | 2020-01-09 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27777-001025 | 27777 | 2019-12-18 15:00 | Section 5 | Material | Not on List | Not on List | 1 | No | 300.24 | 300.24 | Professional Services | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27815-001025 | 27815 | 2019-12-20 13:37 | Section 5 | Material | Not on List | Not on List | 1 | No | 297.16 | 297.16 | Professional Services | 2019-12-20 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27816-001025 | 27816 | 2019-12-20 13:48 | Core | Material | Not on List | Not on List | 1 | No | 344.58 | 344.58 | Professional Services | 2019-12-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27944-001025 | 27944 | 2020-01-08 16:08 | Section 6 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 6 | Each | 115.78 | 695 | Geotextiles | 2020-01-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27716-001025 | 27716 | 2019-12-17 08:59 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13138-001025 | 13138 | 2019-02-26 17:14 | Section 2 | Material | NULL | Not on List | 160 | units | NULL | 0 | Concrete Drainage | 2019-03-17 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13882-001025 | 13882 | 2019-03-12 15:39 | Section 5 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 3 | Price Per Thousand | 345 | 1035 | Blocks and Bricks | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13882-001025 | 13882 | 2019-03-12 15:39 | Section 5 | Material | Bricks/Blocks | Not on List | 1 | NULL | NULL | 0 | Blocks and Bricks | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13807-001025 | 13807 | 2019-03-11 16:23 | Section 2 | Material | NULL | Not on List | 65.9 | m2 | NULL | 0 | Blocks and Bricks | 2019-03-15 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2A - Roadworks - A1 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13801-001025 | 13801 | 2019-03-11 15:53 | Section 2 | Material | Not on List | Not on List | 12.097 | tonnes | NULL | 0 | NULL | 2019-03-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13401-001025 | 13401 | 2019-03-04 13:09 | Section 4 | Material | Not on List | Not on List | 10.5 | Each | 35 | 367.5 | Miscellaneous | 2019-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13896-001025 | 13896 | 2019-03-12 18:01 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 2 | Each | 32.74 | 65 | Blocks and Bricks | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13897-001025 | 13897 | 2019-03-13 06:42 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13900-001025 | 13900 | 2019-03-13 07:01 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-14 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-13589-001025 | 13589 | 2019-03-06 16:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 11.6 | 69.6 | PPE | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13756-001025 | 13756 | 2019-03-11 10:33 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1465.34 | 1465.34 | Small Tools (Consumables) | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13748-001025 | 13748 | 2019-03-11 09:01 | Section 2 | Material | Not on List | Not on List | 3 | NULL | 150 | 450 | Miscellaneous | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1503 - Cables, Joints & Terminations | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13870-001025 | 13870 | 2019-03-12 14:33 | Section 4 | Material | Not on List | Not on List | 2 | Bag | 8.35 | 16.7 | Builders Merchants (General) | 2019-03-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13870-001025 | 13870 | 2019-03-12 14:33 | Section 4 | Material | Not on List | Not on List | 150 | Each | 0.04 | 6 | Builders Merchants (General) | 2019-03-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13870-001025 | 13870 | 2019-03-12 14:33 | Section 4 | Material | Not on List | Not on List | 150 | Each | 0.06 | 9 | Builders Merchants (General) | 2019-03-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13899-001025 | 13899 | 2019-03-13 06:51 | Section 2 | Material | Concrete Drainage | Not on List | 90 | linier m | NULL | 0 | Concrete Drainage | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13906-001025 | 13906 | 2019-03-13 08:23 | Section 3 | Material | Aggregate | Type 1 | 6000 | Tonnes | 21.65 | 129900 | Aggregate | 2019-03-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13274-001025 | 13274 | 2019-02-28 15:07 | Core | Material | Not on List | Not on List | 1 | ea | 24000 | 24000 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13828-001025 | 13828 | 2019-03-12 08:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 748.68 | 748.68 | Small Tools (Consumables) | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Skip 12 cubic yard | 3 | Each | 195 | 585 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 9 | Each | 370 | 3330 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 2 | Each | 150 | 300 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 2.54 | Each | 115 | 292.1 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13825-001025 | 13825 | 2019-03-12 08:12 | Section 3 | Material | Not on List | Not on List | 16 | Tabs | 59.14 | 946.24 | Builders Merchants (General) | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | 162.11 | 162.11 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | 121.58 | 121.58 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Concrete Drainage | CPM 1800 Cover Slab 600x600 Opening (985438) | 1 | Each | 149.8 | 149.8 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Concrete Drainage | CPM 675mm Concrete Rocker (249355) | 2 | Each | 178.55 | 357.1 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Concrete Drainage | CPM 675mm Concrete Socket (890394) | 1 | Each | 178.55 | 178.55 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Not on List | NULL | 1 | SUM | 200 | 200 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13599-001025 | 13599 | 2019-03-06 17:42 | Section 2 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 20 | Rolls | 175 | 3500 | Plastic Drainage | 2019-03-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13599-001025 | 13599 | 2019-03-06 17:42 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 54 | single pipes | 34.82 | 1880.28 | Plastic Drainage | 2019-03-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13599-001025 | 13599 | 2019-03-06 17:42 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 70 | Each | 6.54 | 457.8 | Plastic Drainage | 2019-03-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13599-001025 | 13599 | 2019-03-06 17:42 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 100 | single pipes | 10.5 | 1050 | Plastic Drainage | 2019-03-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13599-001025 | 13599 | 2019-03-06 17:42 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 100 | Each | 1.84 | 184 | Plastic Drainage | 2019-03-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13958-001025 | 13958 | 2019-03-13 15:05 | Section 2 | Material | Not on List | Not on List | 1 | 1 no. | NULL | 0 | Miscellaneous | 2019-03-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | IMO - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13908-001025 | 13908 | 2019-03-13 08:27 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 551.76 | 551.76 | Small Tools (Consumables) | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5072-0027 | 5072 | 2018-08-14 14:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 72 | Each | 6.29 | 0 | Miscellaneous | 2018-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13974-001025 | 13974 | 2019-03-13 17:18 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 8 | NULL | NULL | 0 | Builders Merchants (General) | 2019-03-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 96 | Each | 5.43 | 521.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 64 | Each | 5.43 | 347.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 14.33 | 57.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 12 | Each | 5.43 | 65.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 208 | Each | 5.43 | 1129.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 28 | Each | 5.43 | 152.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 55 | Each | 5.43 | 298.65 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 32 | Each | 5.43 | 173.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 12 | Each | 5.43 | 65.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 96 | Each | 5.43 | 521.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 20 | Each | 5.43 | 108.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 14.33 | 57.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 5600 | Each | 3.52 | 19712 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 10.08 | 40.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 10.08 | 40.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 20 | Each | 5.43 | 108.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 10 | Each | 11.71 | 117.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 11.71 | 46.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 20 | Each | 5.43 | 108.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 10 | Each | 11.71 | 117.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 11.71 | 46.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 96 | Each | 4.22 | 405.12 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 14 | Each | 14.81 | 207.34 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4600 | Each | 1.5 | 6900 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 8 | Each | 14.81 | 118.48 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 19 | Each | 30 | 570 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13988-001025 | 13988 | 2019-03-14 06:58 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-13994-001025 | 13994 | 2019-03-14 08:19 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Waste (General) | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-13961-001025 | 13961 | 2019-03-13 15:30 | Section 2 | Material | NULL | Not on List | 12 | rolls | 136 | 1632 | Geotextiles | 2019-03-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13961-001025 | 13961 | 2019-03-13 15:30 | Section 2 | Material | NULL | Not on List | 12 | no | 7.17 | 86.04 | NULL | NULL | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13961-001025 | 13961 | 2019-03-13 15:30 | Section 2 | Material | NULL | Not on List | 1 | NO | 120 | 120 | NULL | NULL | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13937-001025 | 13937 | 2019-03-13 12:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 650 | 650 | Concrete Accessories | 2019-03-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13937-001025 | 13937 | 2019-03-13 12:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 570 | 570 | Concrete Accessories | 2019-03-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14007-001025 | 14007 | 2019-03-14 09:05 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-15 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S1 Buyers
MREQ-14011-001025 | 14011 | 2019-03-14 09:10 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1000 | number | NULL | 0 | Concrete Accessories | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14011-001025 | 14011 | 2019-03-14 09:10 | Section 2 | Material | Not on List | Not on List | 4 | number | NULL | 0 | Concrete Accessories | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14011-001025 | 14011 | 2019-03-14 09:10 | Section 2 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Concrete Accessories | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15851-001025 | 15851 | 2019-04-15 12:13 | Core | Material | Not on List | Not on List | 4 | NULL | 60.81 | 243 | Miscellaneous | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Operations Rejected | No - Reject | NULL | REQ - Buyers
MREQ-15858-001025 | 15858 | 2019-04-15 12:53 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Builders Merchants (General) | 2019-04-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-15787-001025 | 15787 | 2019-04-12 14:24 | Section 3 | Material | Not on List | Not on List | 16 | 2.5L can | 64.41 | 1030.56 | Builders Merchants (General) | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 28 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 62 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15868-001025 | 15868 | 2019-04-15 14:35 | Section 4 | Material | NULL | NULL | NULL | NULL | 7858.5 | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6165-00629 | 6165 | 2018-09-07 08:25 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 1 | 2 | Rebar and Mesh | 2018-09-21 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-15880-001025 | 15880 | 2019-04-15 16:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Office Supplies | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15859-001025 | 15859 | 2019-04-15 13:33 | Section 3 | Material | Not on List | Not on List | 5 | tonne | 538 | 2690 | NULL | 2019-04-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN16 - New Barns Lane Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15747-001025 | 15747 | 2019-04-12 09:53 | Section 4 | Material | Not on List | Not on List | 5 | Each | 80 | 400 | Builders Merchants (General) | 2019-04-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15889-001025 | 15889 | 2019-04-15 15:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-04-26 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15889-001025 | 15889 | 2019-04-15 15:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | PPE | 2019-04-26 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15889-001025 | 15889 | 2019-04-15 15:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-04-26 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15889-001025 | 15889 | 2019-04-15 15:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | PPE | 2019-04-26 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15904-001025 | 15904 | 2019-04-16 07:37 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Concrete Accessories | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15905-001025 | 15905 | 2019-04-16 07:35 | Section 1 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Flow Control | 2019-04-17 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Operations Rejected | No - Reject | NULL | Req - S1 Buyers
MREQ-15916-001025 | 15916 | 2019-04-16 08:51 | Section 5 | Material | Not on List | Not on List | 1 | number | 708 | 708 | Miscellaneous | 2019-04-16 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15922-001025 | 15922 | 2019-04-16 09:07 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 100 | Each | 24.32 | 2432 | Timber Products | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15922-001025 | 15922 | 2019-04-16 09:07 | Section 5 | Material | Timber | Not on List | 300 | m | NULL | 0 | Timber Products | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15922-001025 | 15922 | 2019-04-16 09:07 | Section 5 | Material | Not on List | Not on List | 100 | litres | NULL | 0 | Builders Merchants (General) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15922-001025 | 15922 | 2019-04-16 09:07 | Section 5 | Material | Not on List | Not on List | 4 | each | NULL | 0 | Builders Merchants (General) | 2019-04-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15923-001025 | 15923 | 2019-04-16 09:27 | Section 5 | Material | Not on List | Not on List | 60 | No | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15923-001025 | 15923 | 2019-04-16 09:27 | Section 5 | Material | Not on List | Not on List | 60 | No | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15948-001025 | 15948 | 2019-04-16 13:24 | Section 3 | Material | Not on List | Not on List | 6 | NULL | 11.19 | 67 | Miscellaneous | 2019-04-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15948-001025 | 15948 | 2019-04-16 13:24 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-04-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15948-001025 | 15948 | 2019-04-16 13:24 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15948-001025 | 15948 | 2019-04-16 13:24 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-04-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15957-001025 | 15957 | 2019-04-16 15:34 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15958-001025 | 15958 | 2019-04-16 15:31 | Section 6 | Material | Not on List | Not on List | 15 | number | 7.25 | 109 | Surveying Consumables | 2019-04-23 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15958-001025 | 15958 | 2019-04-16 15:31 | Section 6 | Material | Not on List | Not on List | 15 | number | 6.75 | 101 | Surveying Consumables | 2019-04-23 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15583-001025 | 15583 | 2019-04-10 08:50 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 2 | Each | 150 | 300 | Waste (Recycling) | 2019-04-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15657-001025 | 15657 | 2019-04-11 08:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2517.86 | 2517.86 | PPE | 2019-04-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15544-001025 | 15544 | 2019-04-09 15:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Pack of 10 Tear Off Visors | 14.82 | 29.64 | PPE | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15544-001025 | 15544 | 2019-04-09 15:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 14.02 | 280.4 | PPE | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16008-001025 | 16008 | 2019-04-17 07:43 | Section 2 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Concrete Accessories | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16014-001025 | 16014 | 2019-04-17 08:01 | Section 2 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Miscellaneous | 2019-04-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15375-001025 | 15375 | 2019-04-05 11:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EAch | 33.6 | 134.4 | Miscellaneous | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15659-001025 | 15659 | 2019-04-11 08:40 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2061.84 | 2061.84 | Small Tools (Consumables) | 2019-04-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15857-001025 | 15857 | 2019-04-15 12:57 | Section 4 | Material | Not on List | Not on List | 15 | Each | 46.5 | 697.5 | Builders Merchants (General) | 2019-04-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15839-001025 | 15839 | 2019-04-15 10:26 | Section 2 | Material | Not on List | Not on List | 25 | Sheets | NULL | 0 | Rebar and Mesh | 2019-04-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15679 | 15679 | 2019-04-11 11:35 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 8695 | 17390 | Surveying Consumables | 2019-04-14 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15679 | 15679 | 2019-04-11 11:35 | Section 5 | Material | Not on List | Not on List | 1 | NULL | 5250 | 5250 | Surveying Consumables | 2019-04-14 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15781-001025 | 15781 | 2019-04-12 14:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 25 | 25 | Laboratory Equipment / Certification | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16035-001025 | 16035 | 2019-04-17 10:04 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15946-001025 | 15946 | 2019-04-16 13:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 572 | 572 | Miscellaneous | 2019-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15693-001025 | 15693 | 2019-04-11 14:38 | Section 4 | Material | Not on List | Not on List | 12 | each | 97.3 | 1167.6 | Miscellaneous | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Concrete Kerbs 125x150x914 BN Straight (753034) | 15 | Each | 3.03 | 45.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Drop Kerb HB x BN RH (897464) | 5 | Each | 5.44 | 27.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Drop Kerb HB x BN LH (897468) | 5 | Each | 5.44 | 27.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Not on List | 1 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Not on List | 1 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Concrete Kerbs 125x150 BN External Radius (947297) | 1 | Each | 5.43 | 5.43 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6157-00627 | 6157 | 2018-09-07 01:23 | Section 3 | Material | Not on List | Not on List | 150000 | ea | 1 | 150000 | Gas Oil | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Concrete Kerbs 125x150 BN Internal Radius (947297) | 1 | Each | 5.43 | 5.43 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15660-001025 | 15660 | 2019-04-11 08:46 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 50.4 | 756 | Small Tools (Consumables) | 2019-04-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16051-001025 | 16051 | 2019-04-17 13:31 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15936-001025 | 15936 | 2019-04-16 10:31 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Bags | 98.14 | 294.42 | Concrete Accessories | 2019-04-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15936-001025 | 15936 | 2019-04-16 10:31 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Coils | 46.5 | 232.5 | Fixings and Fasteners | 2019-04-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16046-001025 | 16046 | 2019-04-17 12:23 | Section 3 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 8 | Each | 165.1 | 1320.8 | Concrete Drainage | 2019-04-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6157-00627 | 6157 | 2018-09-07 01:23 | Section 3 | Material | Not on List | Not on List | 2899 | ea | 0.69 | 2000.31 | Gas Oil | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16047-001025 | 16047 | 2019-04-17 12:28 | Section 3 | Material | Not on List | Not on List | 1 | No | 1263.25 | 1263.25 | Professional Services | 2019-04-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15745-001025 | 15745 | 2019-04-12 09:07 | Section 2 | Material | NULL | Not on List | 128 | number | NULL | 0 | Blocks and Bricks | 2019-04-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15877-001025 | 15877 | 2019-04-15 15:46 | Section 3 | Material | Not on List | Not on List | 50 | No. | 81.47 | 4073.5 | Plastic Drainage | 2019-04-18 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15877-001025 | 15877 | 2019-04-15 15:46 | Section 3 | Material | Not on List | Not on List | 25 | No. | 74.74 | 1868.5 | Plastic Drainage | 2019-04-18 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15877-001025 | 15877 | 2019-04-15 15:46 | Section 3 | Material | Not on List | Not on List | 50 | No. | 5.14 | 257 | Plastic Drainage | 2019-04-18 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15877-001025 | 15877 | 2019-04-15 15:46 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327.4 | Plastic Drainage | 2019-04-18 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15977-001025 | 15977 | 2019-04-16 16:53 | Section 3 | Material | Not on List | Not on List | 25 | Roll | 11.51 | 287.75 | Miscellaneous | 2019-04-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15977-001025 | 15977 | 2019-04-16 16:53 | Section 3 | Material | Not on List | Not on List | 20 | No. | 37.5 | 750 | Miscellaneous | 2019-04-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16079-001025 | 16079 | 2019-04-17 16:40 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16107-001025 | 16107 | 2019-04-18 07:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 857.61 | 857.61 | Small Tools (Consumables) | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 2000 | m | 1 | 2000 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 2000 | m | 1 | 2000 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 2000 | m | 1 | 2000 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 200 | m | 1 | 200 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 2 | m | 1 | 2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 2 | m | 1 | 2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16106-001025 | 16106 | 2019-04-18 07:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2467.5 | 2467.5 | PPE | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15742-001025 | 15742 | 2019-04-12 09:03 | Section 3 | Material | Not on List | Not on List | 30 | EA | 4.09 | 123 | Miscellaneous | 2019-05-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15073-001025 | 15073 | 2019-04-02 08:02 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-14336-001025 | 14336 | 2019-03-20 07:37 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Wheelbarrow 90ltr Galvanised Puncture Proof (700403) | 2 | Each | 53.17 | 106 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6188-00633 | 6188 | 2018-09-07 10:45 | Section 3 | Material | Concrete Drainage | Not on List | 6 | No. | 209.35 | 1256.1 | Concrete Drainage | 2018-09-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 370mm X 7.6mm Pack Of 100 Spartan (230065) | 15 | Each | 3.88 | 58 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Bucket Galvanised 2 1/2gall/11.42ltr 10"/30cm Dia Spartan (506016) | 5 | Each | 9 | 45 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 150 | Each | 3.04 | 456 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6188-00633 | 6188 | 2018-09-07 10:45 | Section 3 | Material | Concrete Drainage | Not on List | 6 | No. | 232.01 | 1392.06 | Concrete Drainage | 2018-09-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 150 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16130-001025 | 16130 | 2019-04-18 10:20 | Section 5 | Material | Combined Drainage | Not on List | 12 | NULL | NULL | 0 | Concrete Drainage | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16078-001025 | 16078 | 2019-04-17 16:18 | Section 3 | Material | Not on List | Not on List | 27.212 | Tonne | 538 | 14640.06 | NULL | 2019-04-17 | Gate D - 1339643 - BN10 Via Main Compound Entrance | CL3B - Structures (Culverts) 3B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16078-001025 | 16078 | 2019-04-17 16:18 | Section 3 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 3.64 | 203.84 | Builders Merchants (General) | 2019-04-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16137-001025 | 16137 | 2019-04-18 08:14 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6188-00633 | 6188 | 2018-09-07 10:45 | Section 3 | Material | Concrete Drainage | Not on List | 6 | No. | 47.04 | 282.24 | Concrete Drainage | 2018-09-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-16074-001025 | 16074 | 2019-04-17 16:23 | Section 3 | Material | PPE, Small Tools and Consumables | Refill Air Care Pristine Wild Berries Air Fragrance 270ml (539229) | 8 | Each | 3.1 | 24.8 | Janitorial | 2019-04-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 12 | Each | 232.2 | 2786.4 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Spigot (249371) | 2 | Each | 278.64 | 557.28 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Socket (249372) | 2 | Each | 278.64 | 557.28 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6188-00633 | 6188 | 2018-09-07 10:45 | Section 3 | Material | Concrete Drainage | Not on List | 6 | No. | 59.17 | 355.02 | Concrete Drainage | 2018-09-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 25 | Each | 35.52 | 888 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 940.8 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | 1.77 | 88.5 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | 5.43 | 162.9 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 17.75 | 177.5 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 17.75 | 177.5 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 17.75 | 177.5 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | 76.36 | 229.08 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | 76.36 | 229.08 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6715-00750 | 6715 | 2018-09-19 12:34 | Section 4 | Material | Concrete Drainage | Not on List | 4 | Each | 18.35 | 73.4 | Builders Merchants (General) | 2018-09-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 68.46 | 68.46 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 88.37 | 88.37 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23734-001025 | 23734 | 2019-09-16 14:15 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 48.92 | 1467.6 | Concrete Drainage | 2019-09-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23734-001025 | 23734 | 2019-09-16 14:15 | Section 4 | Material | Not on List | Not on List | 10 | Each | 162.27 | 1622.7 | Ductile Drainage | 2019-09-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23734-001025 | 23734 | 2019-09-16 14:15 | Section 4 | Material | Not on List | Not on List | 15 | Each | 225.3 | 3379.5 | Concrete Drainage | 2019-09-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 21 | Each (lengths) | 23.14 | 485.94 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6715-00750 | 6715 | 2018-09-19 12:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.18 | 143.6 | Builders Merchants (General) | 2018-09-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 4 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 26 | Each | 3.65 | 94.9 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 52 | Each | 2 | 104 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 22 | Each | 34.82 | 766.04 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 50 | Each | 120.62 | 6031 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 12 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 10 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 20 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 2 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 4 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6720-00750 | 6720 | 2018-09-19 13:44 | Section 4 | Material | Not on List | Not on List | 15 | Each | 175 | 2625 | Plastic Drainage | 2018-09-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 8 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23845-001025 | 23845 | 2019-09-18 12:21 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pack 100 | 10.5 | 105 | Surveying Consumables | 2019-09-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23845-001025 | 23845 | 2019-09-18 12:21 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pack 100 | 10.5 | 105 | Surveying Consumables | 2019-09-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23792-001025 | 23792 | 2019-09-17 15:33 | Core | Material | NULL | NULL | 1 | Each | 288 | 288 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23905-001025 | 23905 | 2019-09-19 09:48 | Core | Material | Not on List | Not on List | 1 | No. | NULL | 0 | Office Supplies | 2019-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23516-001025 | 23516 | 2019-09-11 13:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 25 | NULL | 30.24 | 756 | Small Tools (Consumables) | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23516-001025 | 23516 | 2019-09-11 13:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 12.78 | 25.56 | Small Tools (Consumables) | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6724-00750 | 6724 | 2018-09-19 09:21 | Section 4 | Material | Not on List | Not on List | 18 | Each | 51.28 | 923.04 | Concrete Accessories | 2018-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN21 - Bar Hill Junction East Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23516-001025 | 23516 | 2019-09-11 13:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 13.31 | 26.62 | Small Tools (Consumables) | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23509-001025 | 23509 | 2019-09-11 12:02 | Section 4 | Material | Not on List | Not on List | 1 | Each | 109.6 | 109.6 | Small Tools (Consumables) | 2019-09-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23495-001025 | 23495 | 2019-09-11 10:40 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | NULL | 6.29 | 905.76 | Small Tools (Consumables) | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23875-001025 | 23875 | 2019-09-18 17:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1310.28 | Each | 1 | 1310.28 | PPE | 2019-09-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23662-001025 | 23662 | 2019-09-13 13:25 | Section 4 | Material | NULL | NULL | 130 | Each | 80 | 10400 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23662-001025 | 23662 | 2019-09-13 13:25 | Section 4 | Material | NULL | NULL | 2 | Each | 1350 | 2700 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23662-001025 | 23662 | 2019-09-13 13:25 | Section 4 | Material | NULL | NULL | 2 | Each | 95 | 190 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23699-001025 | 23699 | 2019-09-16 06:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pack 10 | 1.92 | 19.2 | Small Tools (Consumables) | 2019-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23838-001025 | 23838 | 2019-09-18 10:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1181.99 | 1181.99 | Small Tools (Consumables) | 2019-09-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23912-001025 | 23912 | 2019-09-19 12:42 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23917-001025 | 23917 | 2019-09-19 13:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 150 | NULL | NULL | 0 | Surveying Consumables | 2019-09-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1805 - Cantilever Structures | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23886-001025 | 23886 | 2019-09-19 07:51 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-09-20 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23904-001025 | 23904 | 2019-09-19 09:33 | Section 4 | Material | Not on List | Not on List | 16 | Each | 25 | 400 | Miscellaneous | 2019-09-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23919-001025 | 23919 | 2019-09-19 13:57 | Core | Material | Not on List | Not on List | 1 | NULL | 2988.46 | 2988 | Miscellaneous | 2019-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23922-001025 | 23922 | 2019-09-19 14:21 | Section 5 | Material | Bagged | Not on List | 48 | NULL | NULL | 0 | Builders Merchants (General) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23552-001025 | 23552 | 2019-09-12 08:24 | Section 3 | Material | Not on List | Not on List | 5 | ea | 199.96 | 999.8 | Miscellaneous | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | SC3A - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23955-001025 | 23955 | 2019-09-19 18:22 | Section 5 | Material | Twinwall | Not on List | 8 | NULL | NULL | 0 | Plastic Drainage | 2019-09-23 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23955-001025 | 23955 | 2019-09-19 18:22 | Section 5 | Material | Twinwall | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2019-09-23 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 11 | Each | 81.96 | 901.56 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 4 | Each | 81.96 | 327.84 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 10 | Each | 53.01 | 530.1 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 8 | Each | 36.62 | 292.96 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 16 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 2100 x 1000 D/S (890448) | 3 | Each | 283.24 | 849.72 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 2100 x 1000 D/S (890448) | 3 | Each | 283.24 | 849.72 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 2 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 3 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 52 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Saint Gobain Castings | Not on List | 24 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23846-001025 | 23846 | 2019-09-18 12:43 | Section 6 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Surveying Consumables | 2019-09-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 60 | No | 5.9 | 354 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 64 | No | 4.42 | 282.88 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 64 | No | 7.96 | 509.44 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 2 | No | 25.52 | 51.04 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 2 | No | 25.52 | 51.04 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 4 | No | 12.39 | 49.56 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 4 | No | 12.39 | 49.56 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23840-001025 | 23840 | 2019-09-18 10:51 | Section 5 | Material | NULL | NULL | 1 | EAch | 341.88 | 341.88 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23988-001025 | 23988 | 2019-09-20 09:54 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 145 | 145 | Waste (Recycling) | 2019-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23908-001025 | 23908 | 2019-09-19 10:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 11.63 | 116.3 | Small Tools (Consumables) | 2019-09-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23908-001025 | 23908 | 2019-09-19 10:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | 11.63 | 58.15 | Small Tools (Consumables) | 2019-09-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5057-0022 | 5057 | 2018-08-14 12:26 | Section 4 | Material | Not on List | Not on List | 2 | number | 11.9 | 0 | Miscellaneous | 2018-08-19 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23698-001025 | 23698 | 2019-09-16 06:40 | Section 4 | Material | Not on List | Not on List | 144 | NULL | 6.29 | 905.76 | Small Tools (Consumables) | 2019-09-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23969-001025 | 23969 | 2019-09-20 06:19 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-09-23 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23969-001025 | 23969 | 2019-09-20 06:19 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-09-23 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21324-001025 | 21324 | 2019-07-25 11:03 | Section 5 | Material | NULL | NULL | 1 | Each | 160 | 160 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21506-001025 | 21506 | 2019-07-29 14:00 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | No - Reject | Req - S5 Buyers
MREQ-23945-001025 | 23945 | 2019-09-19 16:55 | Section 4 | Material | Not on List | Not on List | 20 | EA | 21.96 | 439.2 | Concrete Accessories | 2019-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23945-001025 | 23945 | 2019-09-19 16:55 | Section 4 | Material | NULL | Not on List | 1 | EA | 35 | 35 | Concrete Accessories | 2019-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 1134 | Each | 19.95 | 22623.3 | Plastic Drainage | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 1 | Each | 4386.96 | 4386.96 | Geotextiles | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 1 | Each | 1111.54 | 1111.54 | Geotextiles | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6766-00751 | 6766 | 2018-09-20 11:24 | Section 4 | Material | Plastic Drainage | Not on List | 20 | Each | 69.21 | 1384.2 | Plastic Drainage | 2018-09-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1301 - Road Lighting Columns and Brackets | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 17 | Each | 66.48 | 1130.16 | Fixings and Fasteners | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 6 | Each | 106.96 | 641.76 | Plastic Drainage | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 6 | Each | NULL | 0 | Plastic Drainage | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23938-001025 | 23938 | 2019-09-19 12:24 | Section 4 | Material | Not on List | Not on List | 48 | Each | 17 | 816 | Rebar and Mesh | 2019-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23866-001025 | 23866 | 2019-09-18 15:27 | Section 4 | Material | Not on List | Not on List | 22 | Each | 126.49 | 2782.78 | Plastic Drainage | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6780-00751 | 6780 | 2018-09-20 13:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 104587.34 | 104587.34 | Geotextiles | 2018-10-08 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23866-001025 | 23866 | 2019-09-18 15:27 | Section 4 | Material | NULL | Not on List | 22 | Each | 16.59 | 364.98 | Plastic Drainage | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23866-001025 | 23866 | 2019-09-18 15:27 | Section 4 | Material | NULL | Not on List | 44 | Each | 9.2 | 404.8 | Plastic Drainage | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24073-001025 | 24073 | 2019-09-23 09:56 | Core | Material | Not on List | Not on List | 1 | ea | 159456 | 159456 | Office Supplies | 2019-09-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24074-001025 | 24074 | 2019-09-23 10:08 | Core | Material | Not on List | Not on List | 1 | ea | 17100 | 17100 | Office Supplies | 2019-09-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24075-001025 | 24075 | 2019-09-23 10:12 | Core | Material | Not on List | Not on List | 1 | ea | 360 | 360 | Office Supplies | 2019-09-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24078-001025 | 24078 | 2019-09-23 10:40 | Core | Material | Not on List | Not on List | 1 | ea` | 500 | 500 | Office Supplies | 2019-09-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24079-001025 | 24079 | 2019-09-23 10:44 | Core | Material | Not on List | Not on List | 1 | ea | 279.18 | 279 | Office Supplies | 2019-09-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24079-001025 | 24079 | 2019-09-23 10:44 | Core | Material | Not on List | Not on List | 1 | ea | 279.18 | 279 | Office Supplies | 2019-09-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23990-001025 | 23990 | 2019-09-20 09:24 | Section 4 | Material | NULL | NULL | 52 | Each | 16.18 | 841.36 | Miscellaneous | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6783-00751 | 6783 | 2018-09-20 13:37 | Section 4 | Material | Plastic Drainage | NULL | 20 | Each | 47.87 | 957.4 | Plastic Drainage | 2018-09-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24021-001025 | 24021 | 2019-09-20 15:53 | Section 2 | Material | Not on List | Not on List | 50 | NULL | 19.51 | 975.5 | Concrete Accessories | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24021-001025 | 24021 | 2019-09-20 15:53 | Section 2 | Material | Not on List | Not on List | 25 | NULL | 19.51 | 487.75 | Concrete Accessories | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24021-001025 | 24021 | 2019-09-20 15:53 | Section 2 | Material | Not on List | Not on List | 100 | NULL | 19.51 | 1951 | Concrete Accessories | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24089-001025 | 24089 | 2019-09-23 12:10 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-10-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24022-001025 | 24022 | 2019-09-20 16:12 | Section 2 | Material | Not on List | Not on List | 5 | NULL | 64.3 | 321.5 | Concrete Accessories | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6783-00751 | 6783 | 2018-09-20 13:37 | Section 4 | Material | Plastic Drainage | P/Pipe 225Mm Ridgidrain Dbl Skt Coupler | 70 | Each | 5.74 | 401.8 | Plastic Drainage | 2018-09-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24108-001025 | 24108 | 2019-09-23 16:20 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 556.8 | 557 | Miscellaneous | 2019-09-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24023-001025 | 24023 | 2019-09-20 16:15 | Section 2 | Material | Not on List | Not on List | 1 | NULL | 9860 | 9860 | Fixings and Fasteners | 2019-09-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24070-001025 | 24070 | 2019-09-23 09:42 | Section 5 | Material | Not on List | Not on List | 10 | EA | 6.45 | 64.5 | Miscellaneous | NULL | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6783-00751 | 6783 | 2018-09-20 13:37 | Section 4 | Material | Not on List | Not on List | 20 | Each | 31.98 | 639.6 | Plastic Drainage | 2018-09-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24127-001025 | 24127 | 2019-09-24 07:54 | Section 3 | Material | Not on List | Not on List | 40 | No | NULL | 0 | Builders Merchants (General) | 2019-09-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 10 | Each | 81.73 | 817.3 | Miscellaneous | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | 430x370x100 D400 Watershed GG&F (376797) | 2 | Each | 37.4 | 74.8 | Miscellaneous | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | Not on List | 6 | Each | NULL | 0 | Miscellaneous | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 432 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 10 | Each | 35.52 | 355 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9461-001025 | 9461 | 2018-11-22 08:38 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-11-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 941 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 432 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9426-001025 | 9426 | 2018-11-21 14:30 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 196.91 | 196.91 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 940.8 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509.2 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5287-00223 | 5287 | 2018-08-17 12:25 | Section 4 | Material | Plastic Drainage | Not on List | 10 | no | 12.18 | 0 | Plastic Drainage | 2018-08-20 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9408-001025 | 9408 | 2018-11-21 10:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 107.6 | 107.6 | PPE | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9423-001025 | 9423 | 2018-11-21 14:12 | Section 3 | Material | Not on List | Not on List | 1 | ea | 447.5 | 447.5 | Damage Charges | 2018-11-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9454-001025 | 9454 | 2018-11-22 07:32 | Section 3 | Material | NULL | Not on List | 40 | Bags | 15.54 | 621.6 | Builders Merchants (General) | 2018-11-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9458-001025 | 9458 | 2018-11-22 08:11 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1363.79 | 1363.79 | Damage Charges | 2018-11-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9479-001025 | 9479 | 2018-11-22 12:34 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 196.1 | 196 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9425-001025 | 9425 | 2018-11-21 14:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 525 | Each | 1 | 525 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9485-001025 | 9485 | 2018-11-22 14:15 | Section 4 | Material | Not on List | Not on List | 3 | U | 650 | 1950 | Miscellaneous | 2018-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5341-00236 | 5341 | 2018-08-20 10:47 | Section 4 | Material | Misc | Not on List | 4 | Rolls | NULL | 0 | Geotextiles | 2018-08-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9488-001025 | 9488 | 2018-11-22 14:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9366-001025 | 9366 | 2018-11-20 13:06 | Section 4 | Material | Aggregate | Not on List | 5 | no | 32.74 | 163.7 | Builders Merchants (General) | 2018-11-22 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9366-001025 | 9366 | 2018-11-20 13:06 | Section 4 | Material | NULL | Not on List | 4 | no | 11.94 | 47.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-22 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9366-001025 | 9366 | 2018-11-20 13:06 | Section 4 | Material | Not on List | Not on List | 168 | no | 8.4 | 1411.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-22 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9492-001025 | 9492 | 2018-11-22 15:17 | Section 3 | Material | Not on List | Not on List | 40 | Ton | 69.9 | 2796 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 30 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 36 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 30 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 15 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5245-00156 | 5245 | 2018-08-16 15:58 | Section 4 | Material | Not on List | Not on List | 336 | Metres | 5.9 | 1982.4 | Timber Products | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9465-001025 | 9465 | 2018-11-22 09:12 | Section 4 | Material | Not on List | Not on List | 120 | Each | 3.46 | 415.2 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9495-001025 | 9495 | 2018-11-22 16:23 | Section 3 | Material | Not on List | Not on List | 16 | No | NULL | 0 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9495-001025 | 9495 | 2018-11-22 16:23 | Section 3 | Material | Not on List | Not on List | 50 | rolls | NULL | 0 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9464-001025 | 9464 | 2018-11-22 08:49 | Section 4 | Material | Not on List | Not on List | 15 | Weeks | 300 | 4500 | Miscellaneous | 2018-11-22 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 0.533 | tonnes | NULL | 0 | Reinforcement | 2018-11-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 13.261 | tonnes | NULL | 0 | Reinforcement | 2019-01-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 22.285 | tonnes | NULL | 0 | Reinforcement | 2019-01-21 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9516-001025 | 9516 | 2018-11-23 08:35 | Section 3 | Material | Not on List | Not on List | 10 | No | NULL | 0 | Builders Merchants (General) | 2018-11-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 12 | packs | NULL | 0 | Not Sure | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5245-00156 | 5245 | 2018-08-16 15:58 | Section 4 | Material | Not on List | Not on List | 240 | NULL | NULL | 0 | NULL | NULL | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 8 | packs | NULL | 0 | Not Sure | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 10 | packs | NULL | 0 | Not Sure | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 940.8 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509.2 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 10 | Each | 35.52 | 355.2 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5346-00239 | 5346 | 2018-08-20 11:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Roll | NULL | 0 | Miscellaneous | 2018-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9516-001025 | 9516 | 2018-11-23 08:35 | Section 3 | Material | Misc | NULL | 10 | Each | 32.74 | 327.4 | Builders Merchants (General) | 2018-11-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9479-001025 | 9479 | 2018-11-22 12:34 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | 196.1 | 784.4 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9531-001025 | 9531 | 2018-11-23 10:21 | Section 3 | Material | Not on List | Not on List | 2 | each | 1200 | 2400 | Miscellaneous | 2018-11-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9534-001025 | 9534 | 2018-11-23 11:13 | Section 4 | Material | Concrete Drainage | Not on List | 5 | NULL | NULL | 0 | Concrete Drainage | 2018-12-05 | RVP 419 - 1340880 - A14 Westbound (West of Junction 28) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9451-001025 | 9451 | 2018-11-21 19:31 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 39.22 | 235.32 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9451-001025 | 9451 | 2018-11-21 19:31 | Section 4 | Material | Not on List | Not on List | 50 | Set | 27 | 1350 | Fixings and Fasteners | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 50.4 | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9540-001025 | 9540 | 2018-11-23 12:20 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 179.5 | 180 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9540-001025 | 9540 | 2018-11-23 12:20 | Section 4 | Material | Not on List | Not on List | 22 | NULL | NULL | 0 | Plastic Drainage | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9484-001025 | 9484 | 2018-11-22 13:20 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.03 | 15 | Concrete Accessories | 2018-11-26 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9484-001025 | 9484 | 2018-11-22 13:20 | Section 4 | Material | Not on List | Not on List | 1500 | Each | 0.05 | 75 | Concrete Accessories | 2018-11-26 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9549-001025 | 9549 | 2018-11-23 13:39 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Visit | 1179.33 | 1179 | Professional Services | 2018-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9488-001025 | 9488 | 2018-11-22 14:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 266.52 | 266.52 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 30.24 | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9411-001025 | 9411 | 2018-11-21 10:15 | Section 4 | Material | Not on List | Not on List | 1703 | Each | 1 | 1703 | Professional Services | 2018-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9492-001025 | 9492 | 2018-11-22 15:17 | Section 3 | Material | Not on List | Not on List | 40 | Ton | 69.9 | 2796 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9580-001025 | 9580 | 2018-11-23 16:22 | Section 3 | Material | Bagged | Not on List | 1 | palette | NULL | 0 | Builders Merchants (General) | 2018-11-30 | Gate F - 1339645 - BN11 Near Mere Way | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9587-001025 | 9587 | 2018-11-23 17:49 | Section 3 | Material | Not on List | Not on List | 100 | Each | 42.5 | 4250 | Miscellaneous | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9603-001025 | 9603 | 2018-11-26 09:50 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Office Supplies | 2018-12-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9603-001025 | 9603 | 2018-11-26 09:50 | Section 3 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Office Supplies | 2018-12-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9604-001025 | 9604 | 2018-11-26 10:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Electrical | 2018-11-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9495-001025 | 9495 | 2018-11-22 16:23 | Section 3 | Material | Not on List | Not on List | 16 | No | 35 | 560 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9495-001025 | 9495 | 2018-11-22 16:23 | Section 3 | Material | Not on List | Not on List | 50 | rolls | 6.4 | 320 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | 1.31 | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 0.533 | tonnes | 538 | 286.75 | Rebar and Mesh | 2018-11-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 13.261 | tonnes | 538 | 7134.42 | Rebar and Mesh | 2019-01-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 22.285 | tonnes | 538 | 11989.33 | Rebar and Mesh | 2019-01-21 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | NULL | Not on List | 3 | Each | 125 | 375 | Rebar and Mesh | 2018-11-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9328-001025 | 9328 | 2018-11-19 12:35 | Section 3 | Material | Not on List | Not on List | 4 | number | NULL | 0 | Miscellaneous | 2018-11-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN06 - ECML Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 12 | packs | 168.35 | 2020.2 | Fixings and Fasteners | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 8 | packs | 11 | 88 | Fixings and Fasteners | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 10 | Hun | 1.88 | 18.8 | Fixings and Fasteners | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | NULL | Not on List | 10 | Hun | 1.55 | 15.5 | Fixings and Fasteners | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9580-001025 | 9580 | 2018-11-23 16:22 | Section 3 | Material | NULL | Not on List | 60 | palette ( 60 bags ) | 3.45 | 207 | Builders Merchants (General) | 2018-11-30 | Gate F - 1339645 - BN11 Near Mere Way | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5347-00243 | 5347 | 2018-08-20 11:52 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Not Sure | 2018-08-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9417-001025 | 9417 | 2018-11-21 12:04 | Section 3 | Material | Not on List | Not on List | 7 | No | 45 | 315 | Miscellaneous | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9628-001025 | 9628 | 2018-11-26 15:35 | Section 4 | Material | Not on List | Not on List | 0 | NULL | NULL | 0 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9603-001025 | 9603 | 2018-11-26 09:50 | Section 3 | Material | Not on List | Not on List | 1 | ea | 29.17 | 29.17 | Office Supplies | 2018-12-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9603-001025 | 9603 | 2018-11-26 09:50 | Section 3 | Material | Not on List | Not on List | 6 | e | 30.83 | 184.98 | Office Supplies | 2018-12-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9534-001025 | 9534 | 2018-11-23 11:13 | Section 4 | Material | Concrete Drainage | Not on List | 5 | Each | 361.34 | 1806.7 | Concrete Drainage | 2018-12-05 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9534-001025 | 9534 | 2018-11-23 11:13 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2018-12-05 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9274-001025 | 9274 | 2018-11-16 12:04 | Section 4 | Material | Not on List | Not on List | 45.495 | M2 | 71.23 | 3240.61 | Concrete Accessories | 2018-12-10 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9274-001025 | 9274 | 2018-11-16 12:04 | Section 4 | Material | NULL | Not on List | 1 | Each | 650 | 650 | Concrete Accessories | 2018-12-10 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5291-00225 | 5291 | 2018-08-17 13:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2018-08-17 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8073-001023 | 8073 | 2018-10-22 11:17 | Section 4 | Material | Not on List | Not on List | 10 | Each | NULL | 0 | Not Sure | 2018-10-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9677-001025 | 9677 | 2018-11-27 12:35 | Section 4 | Material | Aggregate | Bedding Sand | 20 | Tonnes | 11.5 | 230 | Aggregate | 2018-11-28 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9677-001025 | 9677 | 2018-11-27 12:35 | Section 4 | Material | Aggregate | Not on List | 200 | NULL | NULL | 0 | Aggregate | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5332-00234 | 5332 | 2018-08-20 09:18 | Section 3 | Material | Aggregate | Not on List | 2000 | m3 | 43.08 | 86160 | Aggregate | 2018-08-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9537-001025 | 9537 | 2018-11-23 11:59 | Section 4 | Material | Signage | Hazard Safety Signs - 335 X 500 | 50 | Each | 6.7 | 335 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9537-001025 | 9537 | 2018-11-23 11:59 | Section 4 | Material | Signage | Hazard Safety Signs - 335 X 500 | 50 | Each | 6.7 | 335 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9537-001025 | 9537 | 2018-11-23 11:59 | Section 4 | Material | Signage | Hazard Safety Signs - 335 X 500 | 50 | Each | 6.7 | 335 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9537-001025 | 9537 | 2018-11-23 11:59 | Section 4 | Material | Signage | Hazard Safety Signs - 335 X 500 | 50 | Each | 6.7 | 335 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9537-001025 | 9537 | 2018-11-23 11:59 | Section 4 | Material | Signage | Hazard Safety Signs - 335 X 500 | 50 | Each | 6.7 | 335 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9691-001025 | 9691 | 2018-11-27 15:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2018-12-19 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | Not on List | Not on List | 8 | no | NULL | 0 | Plastic Drainage | 2018-12-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 20 | Each | 10.5 | 210 | Plastic Drainage | 2018-12-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 50 | Each | 0.85 | 43 | Plastic Drainage | 2018-12-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 50 | Each | 1.84 | 92 | Plastic Drainage | 2018-12-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9549-001025 | 9549 | 2018-11-23 13:39 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Visit | 1179.33 | 1179.33 | Professional Services | 2018-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9687-001025 | 9687 | 2018-11-27 14:06 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 16 | Each | 110.27 | 1764.32 | Builders Merchants (General) | 2018-11-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9595-001025 | 9595 | 2018-11-26 07:56 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 16 | Each | 110.27 | 1764.32 | Geotextiles | 2018-11-28 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 30 | Each | 5.79 | 173.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 36 | Each | 5.79 | 208.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 30 | Each | 5.25 | 157.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 15 | Each | 5.25 | 78.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 2 | Each | 5.25 | 10.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 2 | Each | 5.25 | 10.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | Not on List | Not on List | 2 | Rolls | 9.6 | 19.2 | Concrete Accessories | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | Not on List | Not on List | 150 | ea | 0.55 | 82.5 | Concrete Accessories | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 110.27 | 1102.7 | Builders Merchants (General) | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | NULL | NULL | 150 | ea | 0.64 | 96 | Concrete Accessories | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 20 | no. | 47.47 | 949.4 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 5 | no. | 46.5 | 232.5 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 200 | no | 0.07 | 14 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11407-001025 | 11407 | 2019-01-24 11:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1179.2 | Each | 1 | 1179 | Janitorial | 2019-01-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11397-001025 | 11397 | 2019-01-24 08:05 | Section 3 | Material | Not on List | Not on List | 12580 | Ton | 4 | 50320 | Aggregate | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10975-001025 | 10975 | 2019-01-14 15:03 | Section 4 | Material | Not on List | Not on List | 0.827 | tonnes | 538 | 444.93 | NULL | 2019-02-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11298-001025 | 11298 | 2019-01-22 10:28 | Section 3 | Material | Not on List | Not on List | 12 | No | 63.32 | 759.84 | Builders Merchants (General) | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11412-001025 | 11412 | 2019-01-24 13:19 | Section 3 | Material | Not on List | Not on List | 40 | EA | 69 | 2760 | Miscellaneous | 2019-01-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11416-001025 | 11416 | 2019-01-24 14:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | NULL | 0 | PPE | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 289.33 | 289.33 | Small Tools (Consumables) | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 160.1 | 160.1 | Janitorial | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1076.92 | 1076.92 | PPE | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11448-001025 | 11448 | 2019-01-25 07:57 | Section 3 | Material | Not on List | Not on List | 2 | Mo | NULL | 0 | Builders Merchants (General) | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11448-001025 | 11448 | 2019-01-25 07:57 | Section 3 | Material | Twinwall | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 10 | Each | 39.7 | 397 | Builders Merchants (General) | 2019-01-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 690 | 437895 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 555 | 437895 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 420 | 437895 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 60 | Number | 5.45 | 437895 | Concrete Accessories | 2019-01-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 200 | Number | NULL | 437895 | Concrete Accessories | 2019-01-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 4 | rolls | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 2 | packs | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 5 | rolls | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 50 | bags | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5378-00250 | 5378 | 2018-08-20 16:43 | Section 3 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-08-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN31 - Culvert - 199 | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11513-001025 | 11513 | 2019-01-28 08:11 | Section 4 | Material | Not on List | Not on List | 1 | Sample analysis | 286 | 286 | Miscellaneous | 2019-01-30 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11552-001025 | 11552 | 2019-01-28 15:05 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11560-001025 | 11560 | 2019-01-28 15:57 | Section 3 | Material | Not on List | Not on List | 18 | Sheets | NULL | 0 | Not Sure | 2019-01-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11560-001025 | 11560 | 2019-01-28 15:57 | Section 3 | Material | Not on List | Not on List | 6 | Rolls | NULL | 0 | Not Sure | 2019-01-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11593-001025 | 11593 | 2019-01-29 08:14 | Section 4 | Material | Not on List | Not on List | 13 | ea | 1 | 13 | Concrete Drainage | 2019-02-04 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11597-001025 | 11597 | 2019-01-29 08:40 | Section 4 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Not Sure | 2019-01-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11598-001025 | 11598 | 2019-01-29 08:52 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Not Sure | 2019-01-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11171-001025 | 11171 | 2019-01-18 09:16 | Section 4 | Material | Not on List | Not on List | 4 | Each | 650 | 2600 | Miscellaneous | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11607-001025 | 11607 | 2019-01-29 09:58 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 400 | Each | 4.97 | 1988 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5378-00250 | 5378 | 2018-08-20 16:43 | Section 3 | Material | Not on List | Not on List | 6 | boxes | 9 | 0 | Fixings and Fasteners | 2018-08-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 3 | Each | 11.9 | 35.7 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 800 | Metre | 0.26 | 208 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.23 | 46 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 5 | Roll | 82.57 | 412.85 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 50 | Bags | 7.98 | 399 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 100 | Metre | 0.78 | 78 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | NULL | Not on List | 5 | Each | 20.25 | 101.25 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | NULL | Not on List | 3 | Each | 1.6 | 4.8 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11611-001025 | 11611 | 2019-01-29 11:05 | Section 3 | Material | Concrete Drainage | Not on List | 2 | no. | NULL | 0 | Concrete Drainage | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11616-001025 | 11616 | 2019-01-29 11:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | 3.42 | 205 | Small Tools (Consumables) | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5341 | 5341 | 2018-08-20 10:47 | Section 4 | Material | Misc | Not on List | 4 | Rolls | NULL | 0 | Geotextiles | 2018-08-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11616-001025 | 11616 | 2019-01-29 11:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 25 | Each | 30.56 | 764 | Small Tools (Consumables) | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11616-001025 | 11616 | 2019-01-29 11:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Roll | 36.98 | 1109 | Builders Merchants (General) | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11242-001025 | 11242 | 2019-01-21 11:04 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Not Sure | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1701 - Insitu Concrete | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8282 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Finance Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8282 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Finance Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11624-001025 | 11624 | 2019-01-29 13:38 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 500 | 1000 | Surveying Consumables | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-11626-001025 | 11626 | 2019-01-29 13:52 | Section 3 | Material | Not on List | Not on List | 14 | no. | NULL | 0 | Concrete Accessories | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | Twinwall | Not on List | 2 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | Twinwall | Not on List | 1 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | Twinwall | Not on List | 2 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | Twinwall | Not on List | 6 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | Kerbs | Not on List | 1 | No | 600 | 600 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8282 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | Each | 21.43 | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Finance Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8282-001023 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11638-001025 | 11638 | 2019-01-29 16:28 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Reinforcement | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11412-001025 | 11412 | 2019-01-24 13:19 | Section 3 | Material | Not on List | Not on List | 40 | tonne | 69.9 | 2796 | Miscellaneous | 2019-01-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11513-001025 | 11513 | 2019-01-28 08:11 | Section 4 | Material | Not on List | Not on List | 1 | Sample analysis | 286 | 286 | Miscellaneous | 2019-01-30 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11648-001025 | 11648 | 2019-01-30 06:33 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11560-001025 | 11560 | 2019-01-28 15:57 | Section 3 | Material | Not on List | Not on List | 18 | Sheets | 4.8 | 86.4 | Not Sure | 2019-01-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11560-001025 | 11560 | 2019-01-28 15:57 | Section 3 | Material | Not on List | Not on List | 6 | Rolls | 15.19 | 91.14 | Not Sure | 2019-01-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11648-001025 | 11648 | 2019-01-30 06:33 | Section 3 | Material | Not on List | Not on List | 1 | ea | 1396.85 | 1396.85 | Miscellaneous | 2019-01-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11667-001025 | 11667 | 2019-01-30 14:41 | Section 4 | Material | Not on List | Not on List | 400 | EA | NULL | 0 | Concrete Accessories | 2019-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 2 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Timber | Not on List | 1 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 2 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 14 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 3 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 6 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 28 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 4 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 2 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 4 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11681-001025 | 11681 | 2019-01-30 16:29 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 600 | 600 | Miscellaneous | 2019-02-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11696-001025 | 11696 | 2019-01-31 08:09 | Section 3 | Material | Twinwall | Not on List | 48 | No | 0 | 0 | Ductile Drainage | 2019-02-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11696-001025 | 11696 | 2019-01-31 08:09 | Section 3 | Material | Twinwall | Not on List | 36 | No | 0 | 0 | Ductile Drainage | 2019-02-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11702-001025 | 11702 | 2019-01-31 09:42 | Section 3 | Material | Not on List | Not on List | 40 | no | NULL | 0 | Builders Merchants (General) | 2019-02-05 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11702-001025 | 11702 | 2019-01-31 09:42 | Section 3 | Material | Not on List | Not on List | 1 | no | 8987.62 | 8987.62 | Builders Merchants (General) | 2019-02-05 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11710-001025 | 11710 | 2019-01-31 11:43 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-02-05 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11626-001025 | 11626 | 2019-01-29 13:52 | Section 3 | Material | Not on List | Not on List | 14 | no. | 530.95 | 7433.3 | Concrete Accessories | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11624-001025 | 11624 | 2019-01-29 13:38 | Section 4 | Material | Not on List | Not on List | 2 | Each | 500 | 1000 | Surveying Consumables | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-11715-001025 | 11715 | 2019-01-31 12:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1742.38 | Each | 1 | 1742 | PPE | 2019-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11724-001025 | 11724 | 2019-01-31 13:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | Twinwall | Not on List | 3 | 0 | 0 | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | Twinwall | Not on List | 1 | 0 | 0 | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | Twinwall | Not on List | 20 | 0 | 0 | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | Twinwall | Not on List | 10 | 0 | 0 | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | Twinwall | Not on List | 10 | 0 | 0 | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 27 | No. | 39.22 | 1059 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 688 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 50 | No. | 48.86 | 2443 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11735-001025 | 11735 | 2019-01-31 13:58 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 115 | 115 | Surveying Consumables | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | NULL | Not on List | 2 | No | 121.59 | 243.18 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | NULL | Not on List | 1 | No | 113.25 | 113.25 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | NULL | Not on List | 2 | No | 164.37 | 328.74 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | NULL | Not on List | 6 | No | 84.41 | 506.46 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | NULL | Not on List | 1 | No | 600 | 600 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11448-001025 | 11448 | 2019-01-25 07:57 | Section 3 | Material | Not on List | Not on List | 2 | Mo | NULL | 0 | Builders Merchants (General) | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11448-001025 | 11448 | 2019-01-25 07:57 | Section 3 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 10 | Each | 39.7 | 397 | Builders Merchants (General) | 2019-01-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11744-001025 | 11744 | 2019-01-31 15:54 | Section 3 | Material | Twinwall | Not on List | 2 | No | NULL | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11743-001 | 11743 | 2019-01-31 15:53 | Section 3 | Material | Aggregate | A10 Pipe Bed | 300 | Tonnes | 16.5 | 4950 | Aggregate | 2019-02-01 | RVP 419 - 1340880 - A14 Westbound (West of Junction 28) | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11745-001025 | 11745 | 2019-01-31 15:36 | Section 4 | Material | Combined Drainage | Not on List | 8 | EA | 77.85 | 623 | Concrete Drainage | 2019-02-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11696-001025 | 11696 | 2019-01-31 08:09 | Section 3 | Material | NULL | Not on List | 48 | No | 15.71 | 754.08 | Ductile Drainage | 2019-02-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11696-001025 | 11696 | 2019-01-31 08:09 | Section 3 | Material | NULL | Not on List | 36 | No | 10.66 | 383.76 | Ductile Drainage | 2019-02-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | NULL | Not on List | 3 | EA | 84.41 | 253.23 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | NULL | Not on List | 1 | Ea | 44.41 | 44.41 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | NULL | Not on List | 20 | Ea | 7.64 | 152.8 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | NULL | Not on List | 10 | EA | 7.64 | 76.4 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | NULL | Not on List | 10 | EA | 7.64 | 76.4 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11756-001025 | 11756 | 2019-01-31 16:46 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2019-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-11756-001025 | 11756 | 2019-01-31 16:46 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Accessories | 2019-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 30 | No. | 4.5 | 135 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 95 | No. | 5.72 | 543.4 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 145 | No. | 21.33 | 3092.85 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18202-001025 | 18202 | 2019-05-29 14:11 | Section 5 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Builders Merchants (General) | 2019-05-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18202-001025 | 18202 | 2019-05-29 14:11 | Section 5 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 14 | Each | 535 | 7490 | Builders Merchants (General) | 2019-05-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18202-001025 | 18202 | 2019-05-29 14:11 | Section 5 | Material | Not on List | Not on List | 750 | litres | NULL | 0 | Builders Merchants (General) | 2019-05-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18184-001025 | 18184 | 2019-05-29 09:24 | Section 4 | Material | Not on List | Not on List | 25 | EA | 12.81 | 320.25 | Concrete Accessories | 2019-06-12 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18182-001025 | 18182 | 2019-05-29 09:11 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18156-001025 | 18156 | 2019-05-29 07:22 | Section 4 | Material | Not on List | Not on List | 200 | Each | 7.48 | 1496 | Builders Merchants (General) | 2019-05-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18158-001025 | 18158 | 2019-05-29 07:29 | Section 4 | Material | Not on List | Not on List | 100 | Each | 3.04 | 304 | Builders Merchants (General) | 2019-05-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18219-001025 | 18219 | 2019-05-29 17:30 | Section 1 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196 | Aggregate | 2019-06-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18219-001025 | 18219 | 2019-05-29 17:30 | Section 1 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 80 | Each | 3.56 | 285 | Aggregate | 2019-06-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18219-001025 | 18219 | 2019-05-29 17:30 | Section 1 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Aggregate | 2019-06-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18219-001025 | 18219 | 2019-05-29 17:30 | Section 1 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Aggregate | 2019-06-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18219-001025 | 18219 | 2019-05-29 17:30 | Section 1 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Aggregate | 2019-06-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18222-001025 | 18222 | 2019-05-29 17:49 | Section 3 | Material | Twinwall | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-05-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-18237-001025 | 18237 | 2019-05-30 07:36 | Section 5 | Material | Not on List | Not on List | 1 | NULL | 1949 | 1949 | Surveying Consumables | 2019-05-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18248-001025 | 18248 | 2019-05-30 08:01 | Section 2 | Material | Not on List | Not on List | 1 | NULL | 281.7 | 282 | Miscellaneous | 2019-06-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18248-001025 | 18248 | 2019-05-30 08:01 | Section 2 | Material | Not on List | Not on List | 1 | NULL | 385.7 | 386 | Miscellaneous | 2019-06-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18183-001025 | 18183 | 2019-05-29 09:16 | Section 3 | Material | Not on List | Not on List | 1.5 | tonne | 538 | 807 | NULL | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18183-001025 | 18183 | 2019-05-29 09:16 | Section 3 | Material | Not on List | Not on List | 1.5 | tonne | 538 | 807 | NULL | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17958-001025 | 17958 | 2019-05-23 10:26 | Section 3 | Material | Not on List | Not on List | 25 | tins | 20.25 | 506.25 | Miscellaneous | 2019-05-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17958-001025 | 17958 | 2019-05-23 10:26 | Section 3 | Material | Not on List | Not on List | 10 | tins | 57.92 | 579.2 | Miscellaneous | 2019-05-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18229-001025 | 18229 | 2019-05-29 18:26 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18188-001025 | 18188 | 2019-05-29 08:08 | Section 4 | Material | Not on List | Not on List | 25 | coils | 46.5 | 1162.5 | NULL | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18188-001025 | 18188 | 2019-05-29 08:08 | Section 4 | Material | Not on List | Not on List | 9 | Pack | 40.6 | 365.4 | NULL | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18188-001025 | 18188 | 2019-05-29 08:08 | Section 4 | Material | Not on List | Not on List | 2 | Pack | 21 | 42 | NULL | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18188-001025 | 18188 | 2019-05-29 08:08 | Section 4 | Material | Not on List | Not on List | 30 | number | 4.94 | 148.2 | NULL | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18264-001025 | 18264 | 2019-05-30 11:45 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-05-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-6624-00750 | 6624 | 2018-09-18 08:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 128.91 | 128.91 | Builders Merchants (General) | 2018-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2702 - Works by the Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6624-00750 | 6624 | 2018-09-18 08:04 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 53.3 | 533 | Builders Merchants (General) | 2018-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2702 - Works by the Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18241-001025 | 18241 | 2019-05-30 08:08 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Bend 11.25deg (878082) | 2 | Each | 81.47 | 162.94 | Plastic Drainage | 2019-05-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18189-001025 | 18189 | 2019-05-29 10:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1441.64 | 1441.64 | PPE | 2019-06-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18257-001025 | 18257 | 2019-05-30 10:12 | Section 3 | Material | Not on List | Not on List | 4 | No | 104.99 | 419.96 | Plastic Drainage | 2019-06-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18257-001025 | 18257 | 2019-05-30 10:12 | Section 3 | Material | Not on List | Not on List | 4 | No | 125.94 | 503.76 | Plastic Drainage | 2019-06-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18257-001025 | 18257 | 2019-05-30 10:12 | Section 3 | Material | Not on List | Not on List | 4 | No | 18.87 | 75.48 | Plastic Drainage | 2019-06-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18257-001025 | 18257 | 2019-05-30 10:12 | Section 3 | Material | Not on List | Not on List | 16 | No | 10.84 | 173.44 | Plastic Drainage | 2019-06-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18181-001025 | 18181 | 2019-05-29 09:13 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Pack 24 | 6.29 | 905.76 | Small Tools (Consumables) | 2019-06-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-4993-006 | 4993 | 2018-08-13 14:56 | Section 4 | Material | Not on List | NULL | 63 | Each | 3.17 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6624-00750 | 6624 | 2018-09-18 08:04 | Section 3 | Material | Not on List | Not on List | 4 | NULL | 6.33 | 25.32 | Builders Merchants (General) | 2018-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2702 - Works by the Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18291-001025 | 18291 | 2019-05-30 15:34 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Builders Merchants (General) | 2019-05-31 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18080-001025 | 18080 | 2019-05-24 16:22 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18252-001025 | 18252 | 2019-05-30 10:09 | Section 4 | Material | Not on List | Not on List | 10 | bags | 1 | 10 | Builders Merchants (General) | 2019-06-03 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18190-001025 | 18190 | 2019-05-29 10:17 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2249.4 | 2249.4 | Small Tools (Consumables) | 2019-06-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18318-001025 | 18318 | 2019-05-31 07:34 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 5 | Each | 241.48 | 1207.4 | Concrete Drainage | 2019-06-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18318-001025 | 18318 | 2019-05-31 07:34 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Socket (249372) | 1 | Each | 289.78 | 289.78 | Concrete Drainage | 2019-06-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18318-001025 | 18318 | 2019-05-31 07:34 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Spigot (249371) | 1 | Each | 278.64 | 278.64 | Concrete Drainage | 2019-06-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18318-001025 | 18318 | 2019-05-31 07:34 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 4 | Each | 48.92 | 195.68 | Concrete Drainage | 2019-06-04 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18318-001025 | 18318 | 2019-05-31 07:34 | Section 3 | Material | NULL | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 8 | Each | 179.74 | 1437.92 | Plastic Drainage | 2019-06-04 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18247-001025 | 18247 | 2019-05-30 08:52 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 166.85 | 166.85 | Small Tools (Consumables) | 2019-06-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18210-001025 | 18210 | 2019-05-29 16:30 | Section 4 | Material | Concrete Drainage | Not on List | 1 | Each | 225.3 | 225.3 | Concrete Drainage | 2019-06-05 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18330-001025 | 18330 | 2019-05-31 10:28 | Section 5 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-06-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6626-00750 | 6626 | 2018-09-18 08:14 | Section 3 | Material | Not on List | Not on List | 1 | x200 Tubes | 692 | 692 | Concrete Accessories | 2018-09-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN10 - A1198 Ermine Street Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18330-001025 | 18330 | 2019-05-31 10:28 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18330-001025 | 18330 | 2019-05-31 10:28 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18191-001025 | 18191 | 2019-05-29 10:25 | Section 3 | Material | Not on List | Not on List | 175 | roll | 196 | 34300 | Builders Merchants (General) | 2019-06-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18191-001025 | 18191 | 2019-05-29 10:25 | Section 3 | Material | Not on List | Not on List | 450 | No | 2.55 | 1147.5 | Builders Merchants (General) | 2019-06-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18195-001025 | 18195 | 2019-05-29 12:04 | Section 3 | Material | NULL | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 20 | Each | 130.26 | 2605.2 | Plastic Drainage | 2019-06-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18195-001025 | 18195 | 2019-05-29 12:04 | Section 3 | Material | NULL | Polypipe 400mm Seal (346394) | 40 | Each | 9.76 | 390.4 | Plastic Drainage | 2019-06-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18195-001025 | 18195 | 2019-05-29 12:04 | Section 3 | Material | Not on List | Not on List | 5 | ea | 164.37 | 821.85 | Plastic Drainage | 2019-06-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18195-001025 | 18195 | 2019-05-29 12:04 | Section 3 | Material | NULL | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 12 | Each | 125.94 | 1511.28 | Plastic Drainage | 2019-06-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18195-001025 | 18195 | 2019-05-29 12:04 | Section 3 | Material | NULL | Polypipe 450mm Ridgidrain Seal (346396) | 24 | Each | 10.8 | 259.2 | Plastic Drainage | 2019-06-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18378-001025 | 18378 | 2019-05-31 15:50 | Core | Material | Not on List | Not on List | 1 | ea | 1150 | 1150 | Training | 2019-05-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | NULL | Yes - Approve | REQ - Buyers
MREQ-18280-001025 | 18280 | 2019-05-30 14:55 | Section 4 | Material | Not on List | Not on List | 1 | EA | 72 | 72 | Concrete Accessories | 2019-06-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18280-001025 | 18280 | 2019-05-30 14:55 | Section 4 | Material | NULL | Not on List | 1 | Ea | 650 | 650 | Concrete Accessories | 2019-06-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18394-001025 | 18394 | 2019-06-02 15:59 | Section 3 | Material | Not on List | Not on List | 2000 | NULL | NULL | 0 | Miscellaneous | 2019-07-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18346-001025 | 18346 | 2019-05-31 13:32 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-06-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18346-001025 | 18346 | 2019-05-31 13:32 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-06-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18172-001025 | 18172 | 2019-05-29 08:24 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 370 | 370 | Laboratory Equipment / Certification | 2019-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15615-001025 | 15615 | 2019-04-10 14:10 | Core | Material | Not on List | Not on List | 1 | Sum | 1710 | 1710 | Miscellaneous | 2019-04-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15856-001025 | 15856 | 2019-04-15 12:42 | Core | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Office Supplies | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | NULL | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17367-001025 | 17367 | 2019-05-14 11:46 | Core | Material | Not on List | Not on List | 1 | NULL | 29.15 | 29 | Office Supplies | 2019-05-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17333-001025 | 17333 | 2019-05-14 07:34 | Core | Material | Not on List | Not on List | 12 | ea | 6000 | 72000 | Office Supplies | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18313-001025 | 18313 | 2019-05-30 16:44 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-4993-006 | 4993 | 2018-08-13 14:56 | Section 4 | Material | Not on List | NULL | 600 | Each | 0.55 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18285-001025 | 18285 | 2019-05-30 14:54 | Section 3 | Material | Not on List | Not on List | 1 | roll | 78.95 | 78.95 | Fixings and Fasteners | 2019-06-04 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18342-001025 | 18342 | 2019-05-31 13:00 | Section 4 | Material | Not on List | Not on List | 1 | EA | 100 | 100 | Concrete Accessories | 2019-06-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 64 | Each | 24.99 | 1599.36 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 100 | Each | 3.65 | 365 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 200 | Each | 2 | 400 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 55 | Each | 37.6 | 2068 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 70 | Each | 7.06 | 494.2 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 140 | Each | 2.97 | 415.8 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 82 | Each | 130.26 | 10681.32 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 100 | Each | 18.84 | 1884 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 200 | Each | 9.76 | 1952 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 80 | Each | 125.94 | 10075.2 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 100 | Each | 18.87 | 1887 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 200 | Each | 10.84 | 2168 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 16 | Each | 179.74 | 2875.84 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 48 | Each | 38.36 | 1841.28 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 100 | Each | 22.37 | 2237 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17239-001025 | 17239 | 2019-05-13 08:45 | Section 3 | Material | Not on List | Not on List | 1 | ea | 662.73 | 662.73 | Miscellaneous | 2019-05-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17262-001025 | 17262 | 2019-05-13 12:06 | Section 3 | Material | Not on List | Not on List | 1 | EA | 7734.38 | 7734.38 | Miscellaneous | 2019-05-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18390-001025 | 18390 | 2019-06-01 13:36 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18336-001025 | 18336 | 2019-05-31 11:38 | Section 6 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 25 | Each | 0.91 | 22.75 | Plastic Drainage | 2019-06-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18336-001025 | 18336 | 2019-05-31 11:38 | Section 6 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 50 | Each | 2 | 100 | Plastic Drainage | 2019-06-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18336-001025 | 18336 | 2019-05-31 11:38 | Section 6 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 25 | Each | 2.97 | 74.25 | Plastic Drainage | 2019-06-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6668-00750 | 6668 | 2018-09-18 12:53 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18414-001025 | 18414 | 2019-06-03 09:24 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18464-001025 | 18464 | 2019-06-03 16:02 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 48 | Each | 28.8 | 1382.4 | PPE | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18415-001025 | 18415 | 2019-06-03 09:36 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18393-001025 | 18393 | 2019-06-01 16:00 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18507-001025 | 18507 | 2019-06-04 10:41 | Section 3 | Material | Not on List | Not on List | 1 | each | 1580 | 1580 | Miscellaneous | 2019-06-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 3 Buyers
MREQ-16650-001025 | 16650 | 2019-04-30 11:55 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-04-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18456-001025 | 18456 | 2019-06-03 15:24 | Section 4 | Material | Not on List | Not on List | 15 | EA | 32.15 | 482.25 | Builders Merchants (General) | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18513-001025 | 18513 | 2019-06-04 11:25 | Core | Material | PPE, Small Tools and Consumables | Stake Marking Out Wooden 1200mm Nominal C.r.code Swcoc004463 (740904) | 100 | Each | 1.07 | 107 | Surveying Consumables | 2019-06-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18513-001025 | 18513 | 2019-06-04 11:25 | Core | Material | PPE, Small Tools and Consumables | Profile Board Wooden - 900mm Nominal C.r.code Swcoc004463 (740910) | 100 | Each | 0.67 | 67 | Surveying Consumables | 2019-06-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18155-001025 | 18155 | 2019-05-29 06:48 | Core | Material | Not on List | Not on List | 1 | GBP | 2820 | 2820 | Miscellaneous | 2019-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 209 | EA | 52.5 | 10972.5 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6668 | 6668 | 2018-09-18 12:53 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 2 | EA | 60 | 120 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 1 | EA | 75 | 75 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 2 | EA | 1200 | 2400 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 20 | EA | 12 | 240 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 20 | EA | 35 | 700 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 2 | Each | 189.47 | 378.94 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 1 | Each | 49.32 | 49.32 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 2 | Each | 158 | 316 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 1 | Each | 11.68 | 11.68 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18562-001025 | 18562 | 2019-06-04 17:53 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18488-001025 | 18488 | 2019-06-04 07:45 | Section 4 | Material | NULL | NULL | 1 | Ea | NULL | 0 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18488-001025 | 18488 | 2019-06-04 07:45 | Section 4 | Material | NULL | NULL | 0 | Ea | NULL | 0 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18570-001025 | 18570 | 2019-06-05 07:42 | Core | Material | Not on List | Not on List | 150 | no | NULL | 0 | Surveying Consumables | 2019-06-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27945-001025 | 27945 | 2020-01-08 16:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Box | NULL | 0 | Small Tools (Consumables) | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 3020 - Seeding, Turfing and Planting | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27945-001025 | 27945 | 2020-01-08 16:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Box | NULL | 0 | Small Tools (Consumables) | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 3020 - Seeding, Turfing and Planting | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27952-001025 | 27952 | 2020-01-08 16:36 | Section 4 | Material | Kerbs | Not on List | 25 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | NULL | NULL | REQ - Section 4 Buyers
MREQ-27952-001025 | 27952 | 2020-01-08 16:36 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | NULL | NULL | REQ - Section 4 Buyers
MREQ-27963-001025 | 27963 | 2020-01-09 09:14 | Section 5 | Material | Timber | Not on List | 3 | packs | NULL | 0 | Timber Products | 2020-01-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27972-001025 | 27972 | 2020-01-09 11:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 80.82 | 162 | Small Tools (Consumables) | 2020-01-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27972-001025 | 27972 | 2020-01-09 11:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 21.6 | 22 | Small Tools (Consumables) | 2020-01-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27973-001025 | 27973 | 2020-01-09 11:43 | Section 4 | Material | Not on List | Not on List | 150 | NULL | NULL | 0 | Timber Products | 2020-01-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27974-001025 | 27974 | 2020-01-09 11:56 | Core | Material | Not on List | Not on List | 6 | ea | 6000 | 36000 | Office Supplies | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27975-001025 | 27975 | 2020-01-09 12:24 | Core | Material | Not on List | Not on List | 1000 | ea | 2.75 | 2750 | Office Supplies | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27975-001025 | 27975 | 2020-01-09 12:24 | Core | Material | Not on List | Not on List | 4 | ea | 4.75 | 19 | Office Supplies | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27976-001025 | 27976 | 2020-01-09 12:42 | Core | Material | Not on List | Not on List | 6 | ea | 522 | 3132 | Office Supplies | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Buyers
MREQ-7366-001022 | 7366 | 2018-10-03 17:42 | Section 4 | Material | Not on List | Not on List | 10 | Number | 9906.83 | 99068.3 | Not Sure | 2018-10-18 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27977-001025 | 27977 | 2020-01-09 12:52 | Core | Material | Not on List | Not on List | 6 | ea | 2160 | 12960 | Office Supplies | 2020-01-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-7352-001022 | 7352 | 2018-10-03 12:25 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 16 | Each | 110.27 | 1764.32 | Geotextiles | 2018-10-08 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 30 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 50 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 20 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 20 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27997-001025 | 27997 | 2020-01-09 15:48 | Section 4 | Material | Not on List | Not on List | 2 | Number | 65 | 130 | Surveying Consumables | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27992-001025 | 27992 | 2020-01-09 15:37 | Section 4 | Material | Not on List | Not on List | 30 | No | 23.25 | 697.5 | Builders Merchants (General) | 2020-01-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28022-001025 | 28022 | 2020-01-10 09:58 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27784-001025 | 27784 | 2019-12-18 10:04 | Section 3 | Material | Not on List | Not on List | 15 | no. | 44 | 660 | Miscellaneous | 2020-01-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN14 - Hilton Road Overbridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28037-001025 | 28037 | 2020-01-10 12:29 | Section 4 | Material | Not on List | Not on List | 140000 | ea | 1 | 140000 | Gas Oil | 2020-01-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28053-001025 | 28053 | 2020-01-10 15:05 | Section 4 | Material | Not on List | Not on List | 36 | NULL | NULL | 0 | Plastic Drainage | 2020-01-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27754-001025 | 27754 | 2019-12-18 09:51 | Section 3 | Material | Aggregate | 6G | 60 | Tonnes | 32.9 | 1974 | Aggregate | 2020-01-06 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 8 | meters | 4.6 | 36.8 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 4 | Meters | 4.6 | 18.4 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 3 | Meters | 4.6 | 13.8 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 6 | Number | 4.6 | 27.6 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 2 | Number | 4.6 | 9.2 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 2 | Number | 4.6 | 9.2 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 8 | Meters | 14.67 | 117.36 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 3 | Meters | 14.67 | 44.01 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 3 | Meters | 14.67 | 44.01 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 8 | Number | 19.9 | 159.2 | Fixings and Fasteners | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 3 | Number | 19.9 | 59.7 | Fixings and Fasteners | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 3 | Number | 19.9 | 59.7 | Fixings and Fasteners | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27988-001025 | 27988 | 2020-01-09 14:47 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28076-001025 | 28076 | 2020-01-13 08:20 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | PPE | 2020-01-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28076-001025 | 28076 | 2020-01-13 08:20 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | PPE | 2020-01-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28077-001025 | 28077 | 2020-01-13 08:32 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Ductile Drainage | 2020-01-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28083-001025 | 28083 | 2020-01-13 10:11 | Core | Material | Signage | Directional Signage - 460 x 190 | 1 | number | 694.09 | 694 | Miscellaneous | 2020-01-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28009-001025 | 28009 | 2020-01-09 16:20 | Section 5 | Material | Concrete Drainage | CPM 2100 Cover Slab 600x600 Opening (890472) | 1 | Each | 4360.79 | 4360.79 | Concrete Drainage | 2020-01-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 20 | ea | NULL | 0 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28088-001025 | 28088 | 2020-01-13 12:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28093-001025 | 28093 | 2020-01-13 14:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-01-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28094-001025 | 28094 | 2020-01-13 15:24 | Section 2 | Material | Not on List | Not on List | 1 | ea | 89.4 | 89 | Professional Services | 2019-12-29 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28103-001025 | 28103 | 2020-01-13 16:07 | Section 5 | Material | Not on List | Not on List | 1 | ea | 1437.48 | 1437 | Professional Services | 2019-12-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28123-001025 | 28123 | 2020-01-14 08:49 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 100 | Each | 5.9 | 590 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 66.97 | 67 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 30 | Each | 167.88 | 5036.4 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 30 | Each | 16.41 | 492.3 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 30 | Each | 11.34 | 340.2 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 30 | Each | 1.98 | 59.4 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 60 | Each | 0.91 | 54.6 | Ductile Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 30 | Each | 26.4 | 792 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 60 | Each | 16.41 | 984.6 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 45 | Each | 74.3 | 3343.5 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 80 | Each | 189 | 15120 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 50 | Each | 16.96 | 848 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 66.97 | 67 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 10 | Each | 125.94 | 1259.4 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 10 | Each | 18.87 | 188.7 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 36 | Each | 11.51 | 414.36 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 36 | Each | 1.98 | 71.28 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 36 | Each | 0.91 | 32.76 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28138-001025 | 28138 | 2020-01-14 12:35 | Section 4 | Material | Not on List | Not on List | 1 | Number | 336 | 336 | Surveying Consumables | 2020-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 100 | number | 34.33 | 3433 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 60 | number | 43.4 | 2604 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 2 | number | 53.14 | 106.28 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 300 | number | 28.09 | 8427 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 60 | number | 27.9 | 1674 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 8 | number | 61.16 | 489.28 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 60 | number | 63.68 | 3820.8 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 42 | number | 13.08 | 549.36 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28145-001025 | 28145 | 2020-01-14 14:13 | Section 5 | Material | Not on List | Not on List | 4 | bags | NULL | 0 | Concrete Accessories | 2020-01-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28156-001025 | 28156 | 2020-01-14 15:31 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 25 | 50 | Surveying Consumables | 2020-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28091-001025 | 28091 | 2020-01-13 14:17 | Section 4 | Material | NULL | NULL | 384 | Each | 5.9 | 2265.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28170-001025 | 28170 | 2020-01-15 10:53 | Core | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Office Supplies | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28171-001025 | 28171 | 2020-01-15 10:56 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 50 | number | NULL | 0 | Surveying Consumables | 2020-01-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28171-001025 | 28171 | 2020-01-15 10:56 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 50 | number | NULL | 0 | Surveying Consumables | 2020-01-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28099-001025 | 28099 | 2020-01-13 15:46 | Section 2 | Material | Not on List | Not on List | 1 | ea | 1353.57 | 1353.57 | Fixings and Fasteners | 2020-01-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28192-001025 | 28192 | 2020-01-15 16:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 664.46 | 664 | PPE | 2020-01-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28192-001025 | 28192 | 2020-01-15 16:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 286.48 | 286 | Janitorial | 2020-01-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28192-001025 | 28192 | 2020-01-15 16:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 69.48 | 69 | Small Tools (Consumables) | 2020-01-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28199-001025 | 28199 | 2020-01-15 17:28 | Section 6 | Material | Signage | Not on List | 16 | each | 7.65 | 122 | Professional Services | 2020-01-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28199-001025 | 28199 | 2020-01-15 17:28 | Section 6 | Material | Signage | Not on List | 10 | each | 7.65 | 77 | Professional Services | 2020-01-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 65 | Each | 65 | 4225 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 2 | Each | 2 | 4 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 30 | Each | 30 | 900 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 30 | Each | 30 | 900 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 27 | Each | 27 | 729 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 36 | Each | 36 | 1296 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 48 | Each | 48 | 2304 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 70 | Each | 70 | 4900 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28206-001025 | 28206 | 2020-01-16 08:29 | Core | Material | Not on List | Not on List | 1 | No | 373 | 373 | Office Supplies | 2020-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 118 - Catering Costs (buffets etc) | IMO - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-28196-001025 | 28196 | 2020-01-15 16:42 | Section 4 | Material | Not on List | Not on List | 1 | ea | 254.83 | 255 | Professional Services | 2019-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28214-001025 | 28214 | 2020-01-16 09:03 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 96.16 | 96 | Small Tools (Consumables) | 2020-01-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28221-001025 | 28221 | 2020-01-16 13:22 | Section 4 | Material | Not on List | Not on List | 1 | no | 5000 | 5000 | Electrical | 2020-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28228-001025 | 28228 | 2020-01-16 14:37 | Section 6 | Material | Not on List | Not on List | 1 | No | 434.16 | 434 | Professional Services | 2019-11-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28233-001025 | 28233 | 2020-01-16 14:50 | Section 5 | Material | Not on List | Not on List | 1 | No | 125 | 125 | Professional Services | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28233-001025 | 28233 | 2020-01-16 14:50 | Section 5 | Material | Not on List | Not on List | 1 | No | 165 | 165 | Professional Services | 2020-01-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28239-001025 | 28239 | 2020-01-16 15:34 | Core | Material | Not on List | Not on List | 1 | NULL | 7246.01 | 7246 | Miscellaneous | 2020-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28241-001025 | 28241 | 2020-01-16 16:01 | Core | Material | Not on List | Not on List | 1 | NULL | 207 | 207 | Miscellaneous | 2020-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28242-001025 | 28242 | 2020-01-16 15:40 | Section 3 | Material | Not on List | Not on List | 1 | No | 1440 | 1440 | Professional Services | 2019-12-19 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7437-001022 | 7437 | 2018-10-05 10:39 | Section 4 | Material | Not on List | Not on List | 6 | boxes of 5 | 11.23 | 67 | Not Sure | 2018-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28242-001025 | 28242 | 2020-01-16 15:40 | Section 3 | Material | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2019-11-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28244-001025 | 28244 | 2020-01-16 16:52 | Section 4 | Material | Not on List | Not on List | 1 | No | 1478.32 | 1478 | Professional Services | 2020-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28244-001025 | 28244 | 2020-01-16 16:52 | Section 4 | Material | Not on List | Not on List | 1 | No | 270 | 270 | Professional Services | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 62 | Each | 70.62 | 4378.44 | Ductile Drainage | 2020-01-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 34 | Each | 52.97 | 1800.98 | Ductile Drainage | 2020-01-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 30 | Each | 44.89 | 1346.7 | Ductile Drainage | 2020-01-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 60 | Each | 48.92 | 2935.2 | Concrete Drainage | 2020-01-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19441-001025 | 19441 | 2019-06-20 14:59 | Section 4 | Material | Waste Management | Metal - Skip 12 cubic yard | 1 | Each | 75 | 75 | Laboratory Equipment / Certification | 2019-06-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17361-001025 | 17361 | 2019-05-14 09:49 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 80 | Each | 1.31 | 104.8 | Small Tools (Consumables) | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19854-001025 | 19854 | 2019-06-27 14:43 | Section 2 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-07-02 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19854-001025 | 19854 | 2019-06-27 14:43 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 3 | Each | 67.9 | 203.7 | Concrete Drainage | 2019-07-02 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19854-001025 | 19854 | 2019-06-27 14:43 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 3 | Each | 47.04 | 141.12 | Concrete Drainage | 2019-07-02 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19854-001025 | 19854 | 2019-06-27 14:43 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2019-07-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19854-001025 | 19854 | 2019-06-27 14:43 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2019-07-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19991-001025 | 19991 | 2019-07-01 10:56 | Section 2 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1157.8 | Geotextiles | 2019-07-03 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19992-001025 | 19992 | 2019-06-26 15:30 | Section 4 | Material | Not on List | Not on List | 200 | bags | 14.43 | 2886 | Builders Merchants (General) | 2019-07-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19992-001025 | 19992 | 2019-06-26 15:30 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1200 | 1200 | Laboratory Equipment / Certification | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19766-001025 | 19766 | 2019-06-26 12:53 | Section 3 | Material | Not on List | Not on List | 2 | EACH | 16.1 | 32.2 | Miscellaneous | 2019-07-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20010-001025 | 20010 | 2019-07-01 13:56 | Section 5 | Material | Not on List | Not on List | 16 | EA | 134.7 | 2155.2 | Miscellaneous | 2019-07-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19872-001025 | 19872 | 2019-06-27 18:07 | Section 3 | Material | Not on List | Not on List | 200 | Bags | 14.43 | 2886 | Concrete Accessories | 2019-07-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19946-001025 | 19946 | 2019-06-28 15:15 | Section 2 | Material | Geotextile | Not on List | 20 | rolls | 266.67 | 5333.4 | Geotextiles | 2019-07-09 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19946-001025 | 19946 | 2019-06-28 15:15 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1000 | pins | 1.86 | 1860 | Miscellaneous | 2019-07-09 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19588-001025 | 19588 | 2019-06-24 09:07 | Core | Material | NULL | NULL | 1 | Each | 687.44 | 687.44 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19487-001025 | 19487 | 2019-06-21 09:48 | Core | Material | NULL | NULL | 1 | Each | 262 | 262 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19969-001025 | 19969 | 2019-06-30 21:04 | Section 5 | Material | Twinwall | NULL | 1 | SM | 3577.11 | 3577.11 | Plastic Drainage | 2019-07-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20051-001025 | 20051 | 2019-07-02 09:51 | Section 2 | Material | Aggregate | Type 1 | 750 | Tonnes | 21.65 | 16237.5 | Aggregate | 2019-07-02 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19950-001025 | 19950 | 2019-06-28 15:46 | Section 2 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 2 | Each | 535 | 1070 | Geotextiles | 2019-07-03 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19950-001025 | 19950 | 2019-06-28 15:46 | Section 2 | Material | Geotextile | Not on List | 5 | each | NULL | 0 | Geotextiles | 2019-07-03 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19482-001025 | 19482 | 2019-06-21 09:29 | Core | Material | NULL | NULL | 1 | Each | 650 | 650 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19978-001025 | 19978 | 2019-07-01 08:24 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Miscellaneous | 2019-07-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19790-001025 | 19790 | 2019-06-26 15:52 | Section 2 | Material | Not on List | Not on List | 129 | NULL | NULL | 0 | Ductile Drainage | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19790-001025 | 19790 | 2019-06-26 15:52 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Ductile Drainage | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19790-001025 | 19790 | 2019-06-26 15:52 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Ductile Drainage | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19790-001025 | 19790 | 2019-06-26 15:52 | Section 2 | Material | Not on List | Not on List | 65 | NULL | NULL | 0 | Ductile Drainage | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20098-001025 | 20098 | 2019-07-02 14:30 | Core | Material | Not on List | Not on List | 1 | NULL | 312 | 312 | Miscellaneous | 2019-07-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19657-001025 | 19657 | 2019-06-25 08:48 | Core | Material | NULL | NULL | 1 | Each | 280 | 280 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19785-001025 | 19785 | 2019-06-26 15:52 | Section 4 | Material | Not on List | Not on List | 1 | ea | 241.48 | 241.48 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19785-001025 | 19785 | 2019-06-26 15:52 | Section 4 | Material | Not on List | Not on List | 2 | ea | 289.78 | 579.56 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19785-001025 | 19785 | 2019-06-26 15:52 | Section 4 | Material | NULL | Not on List | 1 | ea | 200 | 200 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19785-001025 | 19785 | 2019-06-26 15:52 | Section 4 | Material | NULL | Not on List | 1 | ea | 240 | 240 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20118-001025 | 20118 | 2019-07-02 19:48 | Section 5 | Material | Not on List | Not on List | 6 | number | 75 | 450 | Surveying Consumables | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | NULL | Req - S5 Buyers
MREQ-19661-001025 | 19661 | 2019-06-25 09:06 | Core | Material | NULL | NULL | 5 | Set 2 20ltr Buckets C/W Lids | 18.9 | 94.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18592-001025 | 18592 | 2019-06-05 12:20 | Section 4 | Material | Not on List | Not on List | 1 | £ | 9.99 | 10 | Office Supplies | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5142-0070 | 5142 | 2018-08-15 11:34 | Section 3 | Material | Concrete Drainage | Cpm 1050 Slab 600X600 Access | 16 | Each | 47.04 | 752.64 | Concrete Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20137-001025 | 20137 | 2019-07-03 08:42 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1720 | 1720 | Miscellaneous | 2019-07-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Ear Muff Helmet Mounted Jsp Inter Ex Black/Red Snr28 (254222) | 5 | Each | 13.44 | 67 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Water Natural Mineral Ideal Still 500ml Bottle Case Of 24 (744570) | 1 | Pallet | 6.29 | 6 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6465-00710 | 6465 | 2018-09-13 10:14 | Section 3 | Material | Not on List | Not on List | 1 | SUM | 2838.5 | 2838.5 | Damage Charges | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Tank Dust Suppression Duro 13 Litre Ref Dp-dst-13l (766568) | 4 | Each | 33.95 | 136 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Level Spirit Heavy Duty Aluminium Spartan Pro 1200mm/4 (740561) | 3 | Each | 14.99 | 45 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289) | 20 | Each | 7.32 | 146 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Rake Asphalt/Tarmac Flat Tooth Metal Handle Spartan Pro (762583) | 10 | Each | 17.28 | 173 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Strap Lashing 8m Ratchet Hvy Duty 2 Tonne Load 5 Tonne Break (746483) | 10 | Each | 21.34 | 213 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Scraper First Task 75mm Stripping Knife Ref 14003020 (746838) | 5 | Each | 5.55 | 28 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Scourer Grooved Sponge Yellow 150 X 70mm Pack Of 10 (546416) | 5 | Each | 6.26 | 31 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Bucket Flexi Tub 40 Litre Black (506338) | 10 | Each | 9 | 90 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19947-001025 | 19947 | 2019-06-28 15:45 | Section 3 | Material | Not on List | Not on List | 1 | Roll 700M | 78.95 | 78.95 | Aggregate | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20005-001025 | 20005 | 2019-07-01 12:49 | Section 4 | Material | NULL | NULL | 126 | Each | 29.76 | 3749.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-08 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20005-001025 | 20005 | 2019-07-01 12:49 | Section 4 | Material | NULL | NULL | 1 | Each | 204.75 | 204.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-08 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20005-001025 | 20005 | 2019-07-01 12:49 | Section 4 | Material | NULL | NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-08 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20009-001025 | 20009 | 2019-07-01 15:03 | Section 3 | Material | Not on List | Not on List | 5 | Boxes | 99.4 | 497 | Miscellaneous | 2019-07-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20139-001025 | 20139 | 2019-07-03 08:52 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5558-00360 | 5558 | 2018-08-23 09:26 | Section 4 | Material | Not on List | Not on List | 137055 | Each | 1 | 137055 | Geotextiles | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20170-001025 | 20170 | 2019-07-03 13:52 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20170-001025 | 20170 | 2019-07-03 13:52 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20170-001025 | 20170 | 2019-07-03 13:52 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19838-001025 | 19838 | 2019-06-27 10:35 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1188.8 | Each | 1 | 1188.8 | Small Tools (Consumables) | 2019-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19838-001025 | 19838 | 2019-06-27 10:35 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | 2.5kg Tub | 33.03 | 660.6 | Miscellaneous | 2019-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19698-001025 | 19698 | 2019-06-25 11:38 | Section 4 | Material | NULL | NULL | 1 | Each | 1930.86 | 1930.86 | Miscellaneous | 2019-07-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19900-001025 | 19900 | 2019-06-28 08:51 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1800 x 500 D/S (528455) | 1 | Each | 108.94 | 108.94 | Concrete Drainage | 2019-07-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20109-001025 | 20109 | 2019-07-02 15:57 | Section 6 | Material | Twinwall | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-07-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20109-001025 | 20109 | 2019-07-02 15:57 | Section 6 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Plastic Drainage | 2019-07-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20109-001025 | 20109 | 2019-07-02 15:57 | Section 6 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Electrical | 2019-07-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5001-0014 | 5001 | 2018-08-13 16:25 | Section 4 | Material | Plastic Drainage | Not on List | 4 | each | 57.28 | 0 | Plastic Drainage | 2018-08-14 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20179-001025 | 20179 | 2019-07-03 16:30 | Section 6 | Material | Concrete Drainage | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-07-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20191-001025 | 20191 | 2019-07-04 01:59 | Section 5 | Material | Not on List | Not on List | 185 | no. | NULL | 0 | Reinforcement | 2019-07-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20148-001025 | 20148 | 2019-07-03 11:13 | Section 3 | Material | Not on List | Not on List | 6 | No. Cans | 24.35 | 146.1 | Builders Merchants (General) | 2019-07-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20202-001025 | 20202 | 2019-07-04 10:01 | Core | Material | Not on List | Not on List | 50 | NULL | 42 | 2100 | Training | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5179-00112 | 5179 | 2018-08-15 16:25 | Section 4 | Material | Not on List | NULL | 21 | Sqmtr | 27.88 | 585.48 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20152-001025 | 20152 | 2019-07-03 11:49 | Section 3 | Material | Not on List | Not on List | 6 | Plates | 15 | 90 | Ductile Drainage | 2019-07-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20057-001025 | 20057 | 2019-07-02 10:29 | Core | Material | NULL | NULL | 1 | Each | 1397 | 1397 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20056-001025 | 20056 | 2019-07-02 10:18 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 17 | ea | 90 | 1530 | Miscellaneous | 2019-07-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20047-001025 | 20047 | 2019-07-02 09:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | 38.09 | 1142.7 | Miscellaneous | 2019-07-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19779-001025 | 19779 | 2019-06-26 14:30 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20208-001025 | 20208 | 2019-07-04 11:01 | Section 4 | Material | Twinwall | Polyipipe 150mm Ridgidrain Bend 90deg (878001) | 5 | Each | 17.06 | 85.3 | Plastic Drainage | 2019-07-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5179-00112 | 5179 | 2018-08-15 16:25 | Section 4 | Material | NULL | NULL | 4 | Each | 10 | 40 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20208-001025 | 20208 | 2019-07-04 11:01 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Bend 15deg (877998) | 30 | Each | 17.03 | 510.9 | Plastic Drainage | 2019-07-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20208-001025 | 20208 | 2019-07-04 11:01 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 60 | Each | 1.55 | 93 | Plastic Drainage | 2019-07-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20034-001025 | 20034 | 2019-07-02 07:45 | Section 4 | Material | Not on List | Not on List | 100 | Each | 142.82 | 14282 | Concrete Drainage | 2019-07-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20034-001025 | 20034 | 2019-07-02 07:45 | Section 4 | Material | NULL | Not on List | 1 | Each | 190 | 190 | Concrete Drainage | 2019-07-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20259-001025 | 20259 | 2019-07-05 07:10 | Section 3 | Material | Not on List | Not on List | 10 | No. | NULL | 0 | Builders Merchants (General) | 2019-07-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20052-001025 | 20052 | 2019-07-02 10:07 | Core | Material | NULL | NULL | 1 | Each | 1227.5 | 1227.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5179-00112 | 5179 | 2018-08-15 16:25 | Section 4 | Material | NULL | NULL | 4 | Each | 34.5 | 138 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20281-001025 | 20281 | 2019-07-05 08:59 | Section 5 | Material | Not on List | Not on List | 1 | pack | NULL | 0 | Builders Merchants (General) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20281-001025 | 20281 | 2019-07-05 08:59 | Section 5 | Material | Not on List | Not on List | 1 | list | NULL | 0 | Builders Merchants (General) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20281-001025 | 20281 | 2019-07-05 08:59 | Section 5 | Material | Not on List | Not on List | 20 | m | NULL | 0 | Builders Merchants (General) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5249-00162 | 5249 | 2018-08-16 16:33 | Section 4 | Material | Plastic Drainage | NULL | 200 | Each | 15.77 | 3154 | Plastic Drainage | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20281-001025 | 20281 | 2019-07-05 08:59 | Section 5 | Material | Not on List | Not on List | 25 | m | NULL | 0 | Builders Merchants (General) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20281-001025 | 20281 | 2019-07-05 08:59 | Section 5 | Material | Not on List | Not on List | 35 | number | NULL | 0 | Builders Merchants (General) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20285-001025 | 20285 | 2019-07-05 10:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 199 | 199 | Miscellaneous | 2019-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20232-001025 | 20232 | 2019-07-04 15:02 | Section 4 | Material | NULL | NULL | 2 | Each | 273.24 | 546.48 | Miscellaneous | 2019-07-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20301-001025 | 20301 | 2019-07-05 13:42 | Core | Material | Not on List | Not on List | 1 | NULL | 37.5 | 38 | Training | 2019-07-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20212-001025 | 20212 | 2019-07-04 11:21 | Core | Material | PPE, Small Tools and Consumables | Not on List | 443.76 | each | 1 | 443.76 | Janitorial | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5249-00162 | 5249 | 2018-08-16 16:33 | Section 4 | Material | Plastic Drainage | NULL | 100 | Each | 15.77 | 1577 | Plastic Drainage | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20210-001025 | 20210 | 2019-07-04 11:10 | Core | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20130-001025 | 20130 | 2019-07-03 08:02 | Section 4 | Material | NULL | NULL | 400 | Each | 7.5 | 3000 | Surveying Consumables | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20140-001025 | 20140 | 2019-07-03 10:39 | Core | Material | NULL | NULL | 215.26 | Each | 1 | 215.26 | NULL | 2019-07-10 | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20141-001025 | 20141 | 2019-07-03 10:49 | Core | Material | NULL | NULL | 419 | Each | 1 | 419 | NULL | 2019-07-10 | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20143-001025 | 20143 | 2019-07-03 10:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 127.1 | Each | 1 | 127.1 | Miscellaneous | 2019-07-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20209-001025 | 20209 | 2019-07-04 11:01 | Core | Material | PPE, Small Tools and Consumables | Not on List | 48 | Each | 28.8 | 1382.4 | PPE | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20209-001025 | 20209 | 2019-07-04 11:01 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 13.44 | 134.4 | PPE | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20211-001025 | 20211 | 2019-07-04 11:15 | Core | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | 3.42 | 136.8 | Small Tools (Consumables) | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5142-0070 | 5142 | 2018-08-15 11:34 | Section 3 | Material | Concrete Drainage | Not on List | 16 | Each | 209.35 | 3349.6 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5249-00162 | 5249 | 2018-08-16 16:33 | Section 4 | Material | Plastic Drainage | NULL | 100 | Each | 15.77 | 1577 | Plastic Drainage | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20382-001025 | 20382 | 2019-07-08 10:52 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 1 | Load | 24.32 | 24 | Timber Products | 2019-07-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20386-001025 | 20386 | 2019-07-08 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5249-00162 | 5249 | 2018-08-16 16:33 | Section 4 | Material | Plastic Drainage | NULL | 20 | Each | 26.5 | 530 | Plastic Drainage | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24142-001025 | 24142 | 2019-09-23 14:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | NULL | NULL | 0 | PPE | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S5 Buyers
MREQ-24142-001025 | 24142 | 2019-09-23 14:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | PPE | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S5 Buyers
MREQ-24142-001025 | 24142 | 2019-09-23 14:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S5 Buyers
MREQ-24119-001025 | 24119 | 2019-09-23 17:47 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 50 | Each | 52.76 | 2638 | Plastic Drainage | 2019-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24119-001025 | 24119 | 2019-09-23 17:47 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 45deg (878085) | 20 | Each | 52.76 | 1055.2 | Plastic Drainage | 2019-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24119-001025 | 24119 | 2019-09-23 17:47 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 140 | Each | 2.97 | 415.8 | Plastic Drainage | 2019-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6783-00751 | 6783 | 2018-09-20 13:37 | Section 4 | Material | Not on List | Not on List | 10 | Each | 59.5 | 595 | Plastic Drainage | 2018-09-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24184-001025 | 24184 | 2019-09-25 07:58 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 11.19 | 22 | Miscellaneous | 2019-09-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24184-001025 | 24184 | 2019-09-25 07:58 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 16.23 | 32 | Miscellaneous | 2019-09-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24194-001025 | 24194 | 2019-09-25 08:30 | Section 2 | Material | Waste Management | Not on List | 1 | each | 600 | 600 | Waste (General) | 2019-09-25 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | PLM2 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24203-001025 | 24203 | 2019-09-25 09:56 | Section 3 | Material | Not on List | Not on List | 500 | No | NULL | 0 | Builders Merchants (General) | 2019-09-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24163-001025 | 24163 | 2019-09-24 14:14 | Section 5 | Material | Aggregate | Type 1 | 1000 | Tonnes | 21.65 | 21650 | Aggregate | 2019-09-25 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23775-001025 | 23775 | 2019-09-17 10:32 | Section 4 | Material | Not on List | Not on List | 1 | Number | 2097.66 | 2097.66 | Surveying Consumables | 2019-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23973-001025 | 23973 | 2019-09-20 07:31 | Section 2 | Material | Not on List | Not on List | 3500 | m2 | NULL | 0 | Concrete Accessories | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23885-001025 | 23885 | 2019-09-19 07:46 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Concrete Accessories | 2019-09-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6833-00751 | 6833 | 2018-09-21 08:48 | Section 4 | Material | Not on List | Not on List | 10 | Each | 4.18 | 41.8 | Concrete Accessories | 2018-09-25 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23885-001025 | 23885 | 2019-09-19 07:46 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Accessories | 2019-09-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23850-001025 | 23850 | 2019-09-18 12:22 | Section 3 | Material | Combined Drainage | Kerb Drain 405 Drop Kerb 480 (947299) | 2 | Each | 34.93 | 69.86 | Concrete Drainage | 2019-09-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23850-001025 | 23850 | 2019-09-18 12:22 | Section 3 | Material | Combined Drainage | Kerb Drain Splayed Gully Access (947299) | 1 | Each | 40.5 | 40.5 | Blocks and Bricks | 2019-09-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24130-001025 | 24130 | 2019-09-24 08:17 | Section 2 | Material | Not on List | Not on List | 1 | each | 3331.91 | 3331.91 | Professional Services | 2019-09-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6847-00751 | 6847 | 2018-09-21 09:48 | Section 4 | Material | Iron Wear | Not on List | 25 | Each | 58.04 | 1451 | Ductile Drainage | 2018-10-05 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24204-001025 | 24204 | 2019-09-25 10:38 | Section 3 | Material | Kerbs | Not on List | 6 | No | 7.96 | 47.76 | Builders Merchants (General) | 2019-09-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24214-001025 | 24214 | 2019-09-25 12:20 | Section 2 | Material | Geotextile | Not on List | 10 | rolls | 2047.57 | 20475.7 | Geotextiles | 2019-09-30 | Gate S/B5 - 1340891 - Access to BN03 East, A1 Southbound | SC2B - Roadworks - A14 | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24214-001025 | 24214 | 2019-09-25 12:20 | Section 2 | Material | Geotextile | Not on List | 5500 | pins | 1.3 | 7150 | Geotextiles | 2019-09-30 | Gate S/B5 - 1340891 - Access to BN03 East, A1 Southbound | SC2B - Roadworks - A14 | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24206-001025 | 24206 | 2019-09-25 11:22 | Section 4 | Material | Not on List | Not on List | 1 | Each | 485 | 485 | Fixings and Fasteners | 2019-09-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-24206-001025 | 24206 | 2019-09-25 11:22 | Section 4 | Material | NULL | Not on List | 1 | Each | 175 | 175 | Fixings and Fasteners | 2019-09-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-24176-001025 | 24176 | 2019-09-24 17:45 | Section 2 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2019-09-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24207-001025 | 24207 | 2019-09-25 11:08 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 4 | each | 70.99 | 283.96 | Concrete Drainage | 2019-09-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24207-001025 | 24207 | 2019-09-25 11:08 | Section 3 | Material | Not on List | Not on List | 4 | each | 74.3 | 297.2 | Miscellaneous | 2019-09-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6847-00751 | 6847 | 2018-09-21 09:48 | Section 4 | Material | Iron Wear | Not on List | 175 | Each | 58.04 | 10157 | Ductile Drainage | 2018-10-05 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24240-001025 | 24240 | 2019-09-26 08:16 | Section 3 | Material | Not on List | Not on List | 6 | EA | NULL | 0 | Fixings and Fasteners | 2019-09-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1201 - Traffic Signs | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-24240-001025 | 24240 | 2019-09-26 08:16 | Section 3 | Material | Not on List | Not on List | 6 | EA | NULL | 0 | Fixings and Fasteners | 2019-09-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1201 - Traffic Signs | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-5188-00115 | 5188 | 2018-08-15 18:58 | Section 4 | Material | Not on List | Not on List | 1000 | each | NULL | 0 | Timber Products | 2018-08-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6847-00751 | 6847 | 2018-09-21 09:48 | Section 4 | Material | Iron Wear | Not on List | 175 | Each | 86.24 | 15092 | Ductile Drainage | 2018-10-05 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24244-001025 | 24244 | 2019-09-26 09:18 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-09-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-23902-001025 | 23902 | 2019-09-19 09:29 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24266-001025 | 24266 | 2019-09-26 14:05 | Section 5 | Material | Not on List | Not on List | 2 | EA | 88.22 | 176.44 | Not Sure | 2019-09-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24274-001025 | 24274 | 2019-09-26 15:05 | Section 6 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2019-10-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6848-00751 | 6848 | 2018-09-21 09:56 | Section 4 | Material | Not on List | Not on List | 3 | Each | 336.95 | 1010.85 | Plastic Drainage | 2018-10-01 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24274-001025 | 24274 | 2019-09-26 15:05 | Section 6 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2019-10-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24293-001025 | 24293 | 2019-09-27 07:45 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24303-001025 | 24303 | 2019-09-27 10:05 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Surveying Consumables | 2019-10-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24304-001025 | 24304 | 2019-09-27 10:52 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-09-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 2 | Each | 1460 | 2920 | Flow Control | 2019-10-04 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 1 | Each | 265 | 265 | Flow Control | 2019-10-04 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 1 | Each | 265 | 265 | Flow Control | 2019-10-04 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6848-00751 | 6848 | 2018-09-21 09:56 | Section 4 | Material | Not on List | Not on List | 18 | Each | 2.92 | 52.56 | Plastic Drainage | 2018-10-01 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 2 | Each | 95 | 190 | Flow Control | 2019-10-04 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 5 | Boxes | NULL | 0 | Concrete Drainage | 2019-10-04 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 2 | Boxes | NULL | 0 | Concrete Drainage | 2019-10-04 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24310-001025 | 24310 | 2019-09-27 12:17 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24318-001025 | 24318 | 2019-09-27 13:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1201 - Traffic Signs | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-24318-001025 | 24318 | 2019-09-27 13:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1201 - Traffic Signs | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-6848-00751 | 6848 | 2018-09-21 09:56 | Section 4 | Material | Not on List | Not on List | 8 | Each | 26.94 | 215.52 | Plastic Drainage | 2018-10-01 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6853-00751 | 6853 | 2018-09-21 07:56 | Section 4 | Material | Not on List | Not on List | 0.29 | Tonne | 538 | 156.02 | Rebar and Mesh | 2018-10-09 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6853-00751 | 6853 | 2018-09-21 07:56 | Section 4 | Material | Not on List | Not on List | 0.29 | Tonne | 538 | 156.02 | Rebar and Mesh | 2018-10-09 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6853-00751 | 6853 | 2018-09-21 07:56 | Section 4 | Material | Not on List | Not on List | 20 | Each | 93.93 | 1878.6 | Rebar and Mesh | 2018-10-04 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24302-001025 | 24302 | 2019-09-27 09:12 | Core | Material | Not on List | Not on List | 1 | SM | 623.54 | 623.54 | Not Sure | 2019-09-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24258-001025 | 24258 | 2019-09-26 11:54 | Section 5 | Material | Not on List | Not on List | 1 | NULL | 2699.4 | 2699.4 | Damage Charges | 2019-09-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24378-001025 | 24378 | 2019-09-30 11:00 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24369-001025 | 24369 | 2019-09-30 08:19 | Section 4 | Material | NULL | NULL | 1 | Each | 19.2 | 19.2 | Plastic Drainage | 2019-10-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6853-00751 | 6853 | 2018-09-21 07:56 | Section 4 | Material | Not on List | Not on List | 20 | Each | 51.87 | 1037.4 | Rebar and Mesh | 2018-10-04 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24381-001025 | 24381 | 2019-09-30 12:20 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24375-001025 | 24375 | 2019-09-30 09:22 | Section 5 | Material | Twinwall | Not on List | 2 | No | 81.47 | 162.94 | Plastic Drainage | 2019-09-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24330-001025 | 24330 | 2019-09-27 15:11 | Section 4 | Material | Not on List | Not on List | 15 | Each | 51.5 | 772.5 | Rebar and Mesh | 2019-10-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24330-001025 | 24330 | 2019-09-27 15:11 | Section 4 | Material | Not on List | Not on List | 15 | Each | 38.77 | 581.55 | Builders Merchants (General) | 2019-10-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24394-001025 | 24394 | 2019-09-30 15:13 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24416-001025 | 24416 | 2019-10-01 06:23 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-10-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 153 - Temporary Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24434-001025 | 24434 | 2019-10-01 08:38 | Section 3 | Material | Not on List | Not on List | 1000 | 7717344434 | NULL | 0 | Miscellaneous | 2019-10-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24435-001025 | 24435 | 2019-10-01 08:45 | Section 2 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Miscellaneous | 2019-10-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 100 | Each | 25.5 | 2550 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24440-001025 | 24440 | 2019-10-01 09:58 | Section 4 | Material | Not on List | Not on List | 30 | NULL | 26.25 | 788 | Miscellaneous | 2019-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-24449-001025 | 24449 | 2019-10-01 13:17 | Section 5 | Material | Not on List | Not on List | 5 | Number | NULL | 0 | Miscellaneous | 2019-10-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23649-001025 | 23649 | 2019-09-13 11:35 | Section 4 | Material | Not on List | Not on List | 5 | Each | 51.48 | 257.4 | Concrete Accessories | 2019-09-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23649-001025 | 23649 | 2019-09-13 11:35 | Section 4 | Material | Not on List | Not on List | 225 | Kg | 3.1 | 697.5 | Concrete Accessories | 2019-09-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23649-001025 | 23649 | 2019-09-13 11:35 | Section 4 | Material | Not on List | Not on List | 2 | coils | 261.07 | 522.14 | Concrete Accessories | 2019-09-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23649-001025 | 23649 | 2019-09-13 11:35 | Section 4 | Material | NULL | Not on List | 3 | Each | 36.34 | 109.02 | Concrete Accessories | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23649-001025 | 23649 | 2019-09-13 11:35 | Section 4 | Material | NULL | Not on List | 1 | Each | 35 | 35 | Concrete Accessories | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 100 | Each | 2.65 | 265 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24165-001025 | 24165 | 2019-09-24 15:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 282.81 | 282.81 | Small Tools (Consumables) | 2019-09-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24472-001025 | 24472 | 2019-10-01 15:59 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 602 - Excavation (excl topsoil) | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-24472-001025 | 24472 | 2019-10-01 15:59 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-10-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 2703 - Works on behalf of Statutory Undertakers | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-24159-001025 | 24159 | 2019-09-24 13:13 | Section 4 | Material | NULL | NULL | 104 | Each | 16.18 | 1682.72 | Miscellaneous | 2019-10-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24242-001025 | 24242 | 2019-09-26 08:49 | Section 4 | Material | Not on List | Not on List | 8 | Each | 35 | 280 | Electrical | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24242-001025 | 24242 | 2019-09-26 08:49 | Section 4 | Material | Not on List | Not on List | 10 | Each | 10 | 100 | Electrical | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24242-001025 | 24242 | 2019-09-26 08:49 | Section 4 | Material | Not on List | Not on List | 2 | Each | 50 | 100 | Electrical | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24242-001025 | 24242 | 2019-09-26 08:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 50 | 50 | Electrical | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24483-001025 | 24483 | 2019-10-02 07:24 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5189-00116 | 5189 | 2018-08-16 07:01 | Section 4 | Material | Not on List | Not on List | 400 | each | NULL | 0 | Miscellaneous | 2018-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 100 | Each | 9.51 | 951 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24372-001025 | 24372 | 2019-09-30 07:59 | Section 6 | Material | Not on List | Not on List | 23 | Each | 36.14 | 831.22 | Miscellaneous | 2019-10-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24372-001025 | 24372 | 2019-09-30 07:59 | Section 6 | Material | Not on List | Not on List | 1 | Each | 20.92 | 20.92 | Miscellaneous | 2019-10-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24372-001025 | 24372 | 2019-09-30 07:59 | Section 6 | Material | Not on List | Not on List | 7 | Each | 25.34 | 177.38 | Miscellaneous | 2019-10-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24372-001025 | 24372 | 2019-09-30 07:59 | Section 6 | Material | Not on List | Not on List | 2 | Each | 39.34 | 78.68 | Miscellaneous | 2019-10-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24372-001025 | 24372 | 2019-09-30 07:59 | Section 6 | Material | Not on List | Not on List | 75 | Metres | NULL | 0 | Miscellaneous | 2019-10-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 100 | Each | 15.77 | 1577 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 100 | Each | 15.77 | 1577 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24512-001025 | 24512 | 2019-10-02 10:45 | Section 5 | Material | Not on List | Not on List | 1 | each | 750 | 750 | Miscellaneous | 2019-10-01 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24506-001025 | 24506 | 2019-10-02 09:58 | Section 2 | Material | Kerbs | Not on List | 45 | number | 5.75 | 258.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24463-001025 | 24463 | 2019-10-01 14:49 | Core | Material | NULL | NULL | 1 | Each | 1556 | 1556 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 400 | Each | 1.44 | 576 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24484-001025 | 24484 | 2019-10-02 07:17 | Section 4 | Material | Not on List | Not on List | 9 | packs | 168.5 | 1516.5 | Fixings and Fasteners | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24484-001025 | 24484 | 2019-10-02 07:17 | Section 4 | Material | Not on List | Not on List | 9 | packs | 11 | 99 | Fixings and Fasteners | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24484-001025 | 24484 | 2019-10-02 07:17 | Section 4 | Material | Not on List | Not on List | 6 | packs | 2.12 | 12.72 | Fixings and Fasteners | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24484-001025 | 24484 | 2019-10-02 07:17 | Section 4 | Material | Not on List | Not on List | 6 | packs | 1.55 | 9.3 | Fixings and Fasteners | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24484-001025 | 24484 | 2019-10-02 07:17 | Section 4 | Material | NULL | Not on List | 1 | Each | 38.5 | 38.5 | Fixings and Fasteners | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 5 | Each | 28.5 | 142.5 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23267-001025 | 23267 | 2019-09-05 13:11 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24460-001025 | 24460 | 2019-10-01 14:34 | Core | Material | NULL | NULL | 1 | Each | 950 | 950 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24501-001025 | 24501 | 2019-10-02 09:00 | Section 4 | Material | Not on List | Not on List | 20 | Each | 38.77 | 775.4 | Builders Merchants (General) | 2019-10-04 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24522-001025 | 24522 | 2019-10-02 12:34 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24528-001025 | 24528 | 2019-10-02 13:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 313.11 | 313 | Small Tools (Consumables) | 2019-10-07 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 20 | Each | 5.74 | 114.8 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24528-001025 | 24528 | 2019-10-02 13:12 | Core | Material | Not on List | Not on List | 1 | NULL | 474.28 | 474 | Janitorial | 2019-10-07 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24528-001025 | 24528 | 2019-10-02 13:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1553.1 | 1553 | PPE | 2019-10-07 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 40 | Each | 3.17 | 126.8 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24327-001025 | 24327 | 2019-09-27 14:45 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24560-001025 | 24560 | 2019-10-03 08:37 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6863-00751 | 6863 | 2018-09-21 12:23 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Pipe 2.5m (249379) | 21 | Each | 483.27 | 10148.67 | Concrete Drainage | 2018-10-08 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24562-001025 | 24562 | 2019-10-03 09:05 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24565-001025 | 24565 | 2019-10-03 09:10 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23707-001025 | 23707 | 2019-09-16 08:46 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24241-001025 | 24241 | 2019-09-26 08:46 | Core | Material | NULL | NULL | 1 | No. | 160.45 | 160 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24347-001025 | 24347 | 2019-09-28 15:10 | Section 5 | Material | Combined Drainage | NULL | 1 | SM | 17490.28 | 17490.28 | NULL | 2019-10-03 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14015-001025 | 14015 | 2019-03-14 09:26 | Section 2 | Material | Timber | Not on List | 35 | m | NULL | 0 | Timber Products | 2019-03-20 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14015-001025 | 14015 | 2019-03-14 09:26 | Section 2 | Material | Not on List | Not on List | 25 | NULL | NULL | 0 | Miscellaneous | 2019-03-20 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 44 | No. | 34.82 | 1532.08 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 16 | No. | 6.54 | 104.64 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 76 | No. | 2.75 | 209 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 36 | No. | 10.66 | 383.76 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 36 | No. | 1.84 | 66.24 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 72 | No. | 0.85 | 61.2 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14025-001025 | 14025 | 2019-03-14 10:59 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-15 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S1 Buyers
MREQ-13555-001025 | 13555 | 2019-03-06 12:50 | Section 2 | Material | Not on List | Not on List | 44 | No. | 14.46 | 636.24 | Fixings and Fasteners | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14032-001025 | 14032 | 2019-03-14 11:53 | Section 5 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Miscellaneous | 2019-03-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13456-001025 | 13456 | 2019-03-04 09:54 | Core | Material | Not on List | Not on List | 1 | NULL | 513 | 513 | Office Supplies | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14019-001025 | 14019 | 2019-03-14 09:35 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 100 | each | 28.8 | 2880 | PPE | 2019-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14009-001025 | 14009 | 2019-03-14 09:13 | Section 4 | Material | Not on List | Not on List | 2 | Number | 44.25 | 88.5 | Miscellaneous | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13771-001025 | 13771 | 2019-03-11 12:01 | Core | Material | Not on List | Not on List | 1 | Number | 319.37 | 319 | Miscellaneous | 2019-03-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | 110 - Welfare Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 145 | Each | 28 | 4060 | Plastic Drainage | 2019-03-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 28 | 28 | Plastic Drainage | 2019-02-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 28 | 56 | Plastic Drainage | 2019-02-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 45 | 90 | Plastic Drainage | 2019-04-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 3000 | 3000 | Miscellaneous | 2019-02-25 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 20 | Each | 38 | 760 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 121 | Each | 28 | 3388 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 28 | 56 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 45 | 90 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 15 | Each | 38 | 570 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-4948-002 | 4948 | 2018-08-10 14:44 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 3987.4 | 0 | Miscellaneous | NULL | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5059-0024 | 5059 | 2018-08-14 12:47 | Section 4 | Material | Plastic Drainage | P/Pipe 100Mm X 100Mtr Linflex 100 | 20 | Each | 175 | 3500 | Plastic Drainage | 2018-08-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 145 | Each | 28 | 4060 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 28 | 28 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 28 | 56 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 45 | 90 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 20 | Each | 38 | 760 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 117 | Each | 28 | 3276 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 4 | Each | 28 | 112 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 28 | 28 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 45 | 90 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 15 | Each | 38 | 570 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 125 | 125 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13970-001025 | 13970 | 2019-03-13 15:47 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 3 | each | 304 | 912 | Fuel | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13970-001025 | 13970 | 2019-03-13 15:47 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | each | 68 | 408 | Fuel | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13970-001025 | 13970 | 2019-03-13 15:47 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 10 | each | 86 | 860 | Fuel | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13970-001025 | 13970 | 2019-03-13 15:47 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | each | 170 | 1020 | Fuel | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13970-001025 | 13970 | 2019-03-13 15:47 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 100 | each | 11.99 | 1199 | Fuel | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14072-001025 | 14072 | 2019-03-14 17:21 | Section 2 | Material | Hazardous Waste | Not on List | 3 | each | 655 | 1965 | Waste (General) | 2019-03-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14023-001025 | 14023 | 2019-03-14 10:31 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | 18.32 | 54.96 | Small Tools (Consumables) | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14023-001025 | 14023 | 2019-03-14 10:31 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 39.38 | 236.28 | Small Tools (Consumables) | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14024-001025 | 14024 | 2019-03-14 10:31 | Section 2 | Material | Not on List | Not on List | 80 | number | NULL | 0 | Miscellaneous | 2019-03-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14024-001025 | 14024 | 2019-03-14 10:31 | Section 2 | Material | Not on List | Not on List | 50 | number | NULL | 0 | Miscellaneous | 2019-03-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14024-001025 | 14024 | 2019-03-14 10:31 | Section 2 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Miscellaneous | 2019-03-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13915-001025 | 13915 | 2019-03-13 08:47 | Section 3 | Material | Not on List | Not on List | 30 | EA | 48.86 | 1465.8 | Builders Merchants (General) | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13915-001025 | 13915 | 2019-03-13 08:47 | Section 3 | Material | Not on List | Not on List | 30 | ea | 13.75 | 412.5 | Builders Merchants (General) | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13915-001025 | 13915 | 2019-03-13 08:47 | Section 3 | Material | Not on List | Not on List | 15 | EA | 34.82 | 522.3 | Builders Merchants (General) | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13571-001025 | 13571 | 2019-03-06 15:21 | Section 4 | Material | Not on List | Not on List | 30 | Each | NULL | 0 | Concrete Accessories | 2019-03-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13571-001025 | 13571 | 2019-03-06 15:21 | Section 4 | Material | Not on List | Not on List | 30 | Each | 0.13 | 3.9 | Concrete Accessories | 2019-03-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13571-001025 | 13571 | 2019-03-06 15:21 | Section 4 | Material | Not on List | Not on List | 10 | Each | 24.18 | 241.8 | Concrete Accessories | 2019-03-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13571-001025 | 13571 | 2019-03-06 15:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 101 | 101 | Concrete Accessories | 2019-03-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13571-001025 | 13571 | 2019-03-06 15:21 | Section 4 | Material | Not on List | Not on List | 3 | Each | 12.81 | 38.43 | Concrete Accessories | 2019-03-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14093-001025 | 14093 | 2019-03-15 09:58 | Section 2 | Material | Bagged | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14093-001025 | 14093 | 2019-03-15 09:58 | Section 2 | Material | Twinwall | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14093-001025 | 14093 | 2019-03-15 09:58 | Section 2 | Material | Twinwall | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14093-001025 | 14093 | 2019-03-15 09:58 | Section 2 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 30 | Each | 81.73 | 2452 | Plastic Drainage | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14103-001025 | 14103 | 2019-03-15 10:46 | Section 3 | Material | Twinwall | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-14061-001025 | 14061 | 2019-03-14 16:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3012.6 | Each | 1 | 3012.6 | Miscellaneous | 2019-03-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14111-001025 | 14111 | 2019-03-15 12:23 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14089-001025 | 14089 | 2019-03-15 09:09 | Section 4 | Material | Aggregate | Not on List | 10000 | Loads | 75 | 750000 | Aggregate | 2019-03-25 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14003-001025 | 14003 | 2019-03-14 08:57 | Section 4 | Material | Waste Management | Not on List | 38500 | Each | 1 | 38500 | Waste (General) | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14006-001025 | 14006 | 2019-03-14 09:03 | Section 4 | Material | Waste Management | Not on List | 47500 | Each | 1 | 47500 | Waste (General) | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13849-001025 | 13849 | 2019-03-12 11:26 | Section 4 | Material | Not on List | Not on List | 1 | Each | 336.28 | 336.28 | Miscellaneous | 2019-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14121-001025 | 14121 | 2019-03-15 13:44 | Section 2 | Material | Not on List | Not on List | 900 | sq meters | NULL | 0 | Concrete Accessories | 2019-03-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14121-001025 | 14121 | 2019-03-15 13:44 | Section 2 | Material | Not on List | Not on List | 180 | Lengths | NULL | 0 | Concrete Accessories | 2019-03-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14121-001025 | 14121 | 2019-03-15 13:44 | Section 2 | Material | Not on List | Not on List | 180 | Lengths | NULL | 0 | Concrete Accessories | 2019-03-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13539-001025 | 13539 | 2019-03-06 11:13 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2923.25 | 2923.25 | Miscellaneous | 2019-03-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14125-001025 | 14125 | 2019-03-15 10:04 | Section 4 | Material | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2019-03-18 | RVP 420 - A14 Eastbound - Opposite Crematorium | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-14051-001025 | 14051 | 2019-03-14 15:38 | Section 3 | Material | Not on List | Not on List | 2 | ea | 3083.08 | 6166.16 | Damage Charges | 2019-03-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13838-001025 | 13838 | 2019-03-12 09:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 159.25 | 159.25 | Miscellaneous | 2019-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13936-001025 | 13936 | 2019-03-13 12:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 176.16 | 176.16 | Miscellaneous | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5672-00429 | 5672 | 2018-08-28 09:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2843.69 | 2843.69 | Small Tools (Consumables) | 2018-08-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Not on List | 20 | Units | NULL | 0 | Concrete Drainage | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 22 | Each | 67.9 | 1493.8 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 4 | Each | 50.92 | 203.68 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 10 | Each | 35.52 | 355.2 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1500x1000 D/S (991900) | 4 | Each | 121.25 | 485 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1500x750 D/S (991899) | 2 | Each | 90.94 | 181.88 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 6 | Each | 102.82 | 616.92 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5812-00493 | 5812 | 2018-08-30 13:00 | Section 3 | Material | Misc | Not on List | 3 | Hours | 40 | 120 | Professional Services | 2018-08-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 940.8 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 50 | Each | 34.82 | 1741 | Plastic Drainage | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 40 | Each | 120.62 | 4824.8 | Plastic Drainage | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14095-001025 | 14095 | 2019-03-15 10:07 | Core | Material | Not on List | Not on List | 1 | ea | 63002 | 63002 | Office Supplies | 2019-03-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14083-001025 | 14083 | 2019-03-15 08:07 | Core | Material | Not on List | Not on List | 1 | ea | 1440 | 1440 | Training | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14028-001025 | 14028 | 2019-03-14 11:17 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 144 | 144 | Laboratory Equipment / Certification | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13293-001025 | 13293 | 2019-02-28 16:57 | Core | Material | Not on List | Not on List | 1 | NULL | 345.01 | 345.01 | Miscellaneous | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5811-00489 | 5811 | 2018-08-30 12:54 | Section 3 | Material | Not on List | Not on List | 2 | Packs | 138.24 | 276.48 | Builders Merchants (General) | 2018-09-03 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11919-001025 | 11919 | 2019-02-05 09:28 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12009-001025 | 12009 | 2019-02-06 14:48 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-14163-001025 | 14163 | 2019-03-18 09:59 | Section 5 | Material | Signage | Miscellaneous Signs - 75 | 1 | Each | 0.22466 | 0 | Miscellaneous | 2019-03-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14163-001025 | 14163 | 2019-03-18 09:59 | Section 5 | Material | Signage | Miscellaneous Signs - 75 | 1 | Each | 0.22466 | 0 | Miscellaneous | 2019-03-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Padlock Brass Spartan 50mm Open Shackle (744428) | 30 | Each | 3.66 | 110 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Level Spirit Heavy Duty Boat Shaped Spartan Pro 225mm/9 (740523) | 5 | Each | 4.48 | 22 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Mallet Rubber C/W Wooden Handle 0.7kg/2 (790014) | 5 | Each | 4.78 | 24 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Mallet Rubber C/W Wooden Handle 0.7kg/2 (790014) | 5 | Each | 4.78 | 24 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Jerrican Metal 20 Litre Capacity Spartan Pro (708622) | 5 | Each | 13.19 | 66 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5811-00489 | 5811 | 2018-08-30 12:54 | Section 3 | Material | Not on List | Not on List | 2 | Packs | 138.24 | 276.48 | Builders Merchants (General) | 2018-09-03 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Can Fuel 5ltr Heavy Duty Green Plastic Long Spout Unleaded (706686) | 5 | Each | 5.82 | 29 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5811-00489 | 5811 | 2018-08-30 12:54 | Section 3 | Material | Not on List | Not on List | 2 | Packs | 138.24 | 276.48 | Builders Merchants (General) | 2018-09-03 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14171-001025 | 14171 | 2019-03-18 11:25 | Section 2 | Material | Not on List | Not on List | 11 | ea | NULL | 0 | Miscellaneous | 2019-03-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 401 - Safety Barriers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14021-001025 | 14021 | 2019-03-14 09:39 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.8 | 80 | Surveying Consumables | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14021-001025 | 14021 | 2019-03-14 09:39 | Section 4 | Material | NULL | Not on List | 10 | Each | 25 | 250 | Surveying Consumables | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14132-001025 | 14132 | 2019-03-15 14:42 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327.4 | Aggregate | 2019-03-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 180 | Each | 2 | 360 | Plastic Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | Not on List | 30 | Each | NULL | 0 | Plastic Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 9 | Rolls | 175 | 1575 | Plastic Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Not on List | Not on List | 3 | Boxes | NULL | 0 | Miscellaneous | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15635-001025 | 15635 | 2019-04-10 16:43 | Core | Material | Not on List | Not on List | 1 | Number | 295 | 295 | Miscellaneous | 2019-04-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16166-001025 | 16166 | 2019-04-18 12:11 | Core | Material | Not on List | Not on List | 200 | Number | NULL | 0 | Surveying Consumables | 2019-04-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 900 | M | 1 | 900 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 22 | M | 1 | 22 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 18 | M | 1 | 18 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 30 | ea | 1 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 250 | M | 1 | 250 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 2 | M | 1 | 2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 2 | M | 1 | 2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16127-001025 | 16127 | 2019-04-18 09:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 55.46 | 554.6 | Small Tools (Consumables) | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16127-001025 | 16127 | 2019-04-18 09:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 113.57 | 1135.7 | Small Tools (Consumables) | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15876-001025 | 15876 | 2019-04-15 15:46 | Section 2 | Material | Not on List | Not on List | 23.123 | t | NULL | 0 | NULL | 2019-04-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16173-001025 | 16173 | 2019-04-18 14:23 | Core | Material | Not on List | Not on List | 1 | number | 2000 | 2000 | Miscellaneous | 2019-04-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6185-00631 | 6185 | 2018-09-07 10:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Packs | 9 | 90 | Small Tools (Consumables) | 2018-09-10 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6179-00630 | 6179 | 2018-09-07 09:57 | Section 4 | Material | Not on List | Not on List | 15 | number | 7.98 | 119.7 | Small Tools (Consumables) | 2018-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16177-001025 | 16177 | 2019-04-18 14:13 | Core | Material | Not on List | Not on List | 1 | NULL | 5827.5 | 5828 | Miscellaneous | 2019-04-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5489-00305 | 5489 | 2018-08-22 09:10 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 19.59 | 39.18 | Miscellaneous | 2018-08-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16180-001025 | 16180 | 2019-04-18 14:45 | Core | Material | Not on List | Not on List | 1 | number | 5827.5 | 5828 | Miscellaneous | 2019-04-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16192-001025 | 16192 | 2019-04-23 07:09 | Section 2 | Material | Not on List | Not on List | 20 | Rolls | NULL | 0 | Concrete Accessories | 2019-04-26 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16206-001025 | 16206 | 2019-04-23 08:49 | Section 4 | Material | Not on List | Not on List | 1000 | m | 1 | 1000 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16214-001025 | 16214 | 2019-04-23 10:15 | Section 2 | Material | Bagged | Not on List | 285 | No. | NULL | 0 | Miscellaneous | 2019-06-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16214-001025 | 16214 | 2019-04-23 10:15 | Section 2 | Material | Not on List | Not on List | 1 | No. | NULL | 0 | Miscellaneous | 2019-06-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16227-001025 | 16227 | 2019-04-23 11:54 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196 | Aggregate | 2019-04-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16227-001025 | 16227 | 2019-04-23 11:54 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142 | Aggregate | 2019-04-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5489-00305 | 5489 | 2018-08-22 09:10 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 100.11 | 200.22 | Miscellaneous | 2018-08-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16227-001025 | 16227 | 2019-04-23 11:54 | Section 2 | Material | Bagged | Not on List | 10 | NULL | NULL | 0 | Builders Merchants (General) | 2019-04-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16065-001025 | 16065 | 2019-04-17 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 350 | 350 | Surveying Consumables | 2019-04-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16073-001025 | 16073 | 2019-04-17 16:17 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-04-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16073-001025 | 16073 | 2019-04-17 16:17 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-04-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16061-001025 | 16061 | 2019-04-17 12:42 | Section 3 | Material | Not on List | Not on List | 500 | No | 0.26 | 130 | Builders Merchants (General) | 2019-04-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16061-001025 | 16061 | 2019-04-17 12:42 | Section 3 | Material | Not on List | Not on List | 600 | No | 0.37 | 222 | Builders Merchants (General) | 2019-04-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16039-001025 | 16039 | 2019-04-17 10:37 | Section 4 | Material | Not on List | Not on List | 3 | Each | 75 | 225 | Surveying Consumables | 2019-04-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15485-001025 | 15485 | 2019-04-08 17:29 | Section 4 | Material | Not on List | Not on List | 5 | Each | 18 | 90 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15485-001025 | 15485 | 2019-04-08 17:29 | Section 4 | Material | Not on List | Not on List | 2 | Each | 95 | 190 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6267-00653 | 6267 | 2018-09-10 13:49 | Section 4 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Surveying Consumables | 2018-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16184-001025 | 16184 | 2019-04-18 16:40 | Section 3 | Material | Not on List | Not on List | 2 | No. | 80 | 160 | Builders Merchants (General) | 2019-04-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 609 - Ground water lowering | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 100 | Each | 11.34 | 1134 | Plastic Drainage | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 300 | Each | 1.98 | 594 | Plastic Drainage | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 600 | Each | 0.91 | 546 | Plastic Drainage | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 50 | Each | 24.99 | 1249.5 | Plastic Drainage | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 150 | Each | 3.65 | 547.5 | Plastic Drainage | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 300 | Each | 2 | 600 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 100 | Each | 37.6 | 3760 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 150 | Each | 7.06 | 1059 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 300 | Each | 2.97 | 891 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 10 | Each | 130.26 | 1302.6 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 30 | Each | 18.84 | 565.2 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 60 | Each | 9.76 | 585.6 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 20 | Each | 125.94 | 2518.8 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 60 | Each | 18.87 | 1132.2 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 120 | Each | 10.84 | 1300.8 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16266-001025 | 16266 | 2019-04-23 17:27 | Section 5 | Material | Twinwall | Not on List | 2 | No | NULL | 0 | Plastic Drainage | 2019-04-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16266-001025 | 16266 | 2019-04-23 17:27 | Section 5 | Material | Twinwall | Not on List | 2 | No | NULL | 0 | Plastic Drainage | 2019-04-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15643-001025 | 15643 | 2019-04-10 16:23 | Section 4 | Material | Not on List | Not on List | 28 | Each | 150 | 4200 | Miscellaneous | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2702 - Works by the Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14719-001025 | 14719 | 2019-03-27 07:18 | Section 4 | Material | Signage | Directional Signage - 2300 x 750 | 1 | Each | 93.16 | 93.16 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14719-001025 | 14719 | 2019-03-27 07:18 | Section 4 | Material | Signage | Directional Signage - 460 x 190 | 1 | Each | 7.9 | 7.9 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14719-001025 | 14719 | 2019-03-27 07:18 | Section 4 | Material | Signage | Directional Signage - 460 x 190 | 1 | Each | 5.61 | 5.61 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16142-001025 | 16142 | 2019-04-18 11:46 | Section 4 | Material | Not on List | Not on List | 250 | Each | 0.34 | 85 | Concrete Accessories | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16142-001025 | 16142 | 2019-04-18 11:46 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.32 | 132 | Concrete Accessories | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16142-001025 | 16142 | 2019-04-18 11:46 | Section 4 | Material | Not on List | Not on List | 5 | Each | 46.5 | 232.5 | Concrete Accessories | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16142-001025 | 16142 | 2019-04-18 11:46 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.03 | 103 | Concrete Accessories | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16142-001025 | 16142 | 2019-04-18 11:46 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.88 | 88 | Concrete Accessories | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16293-001025 | 16293 | 2019-04-24 10:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 921.6 | 922 | PPE | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-6307-00657 | 6307 | 2018-09-11 09:04 | Section 4 | Material | Not on List | Not on List | 48 | NULL | NULL | 0 | Fixings and Fasteners | 2018-09-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16175-001025 | 16175 | 2019-04-18 14:33 | Core | Material | Not on List | Not on List | 5 | number | 800 | 4000 | Office Supplies | 2019-04-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16235-001025 | 16235 | 2019-04-23 13:05 | Section 2 | Material | NULL | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 40 | Each | 120.62 | 4824.8 | Plastic Drainage | 2019-04-29 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16308-001025 | 16308 | 2019-04-24 12:30 | Section 3 | Material | Not on List | Not on List | 300 | lm | NULL | 0 | Miscellaneous | 2019-04-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16139-001025 | 16139 | 2019-04-18 11:15 | Core | Material | Not on List | Not on List | 1 | Each | 1737.5 | 1737.5 | Training | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16264-001025 | 16264 | 2019-04-23 17:36 | Section 2 | Material | NULL | Not on List | 16 | Number | NULL | 0 | Concrete Drainage | 2019-04-26 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16323-001025 | 16323 | 2019-04-24 14:37 | Core | Material | Not on List | Not on List | 1 | each | 945 | 945 | Laboratory Equipment / Certification | 2019-04-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16037-001025 | 16037 | 2019-04-17 10:26 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2002.65 | 2002.65 | Surveying Consumables | 2019-04-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 150 | Each | 23.14 | 3471 | Plastic Drainage | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 85 | Each | 34.82 | 2960 | Plastic Drainage | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Twinwall | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 50 | Each | 120.62 | 6031 | Plastic Drainage | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 1 | Price Per Thousand | 345 | 345 | Blocks and Bricks | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Bagged | Sharp Sand Bulk Bag (938208) | 1 | Each | 32.74 | 33 | Builders Merchants (General) | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Bagged | OP Cement; 25kg bag (767201) | 50 | Each | 2.9 | 145 | Builders Merchants (General) | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Laboratory Equipment / Certification | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Laboratory Equipment / Certification | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Laboratory Equipment / Certification | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Laboratory Equipment / Certification | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Laboratory Equipment / Certification | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 40 | Each | 10.5 | 420 | Plastic Drainage | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15665-001025 | 15665 | 2019-04-11 09:52 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 17.87 | 107.22 | Miscellaneous | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16334-001025 | 16334 | 2019-04-24 15:42 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16338-001025 | 16338 | 2019-04-24 16:32 | Section 3 | Material | Aggregate | A10 Pipe Bed | 400 | Tonnes | 16.5 | 6600 | Aggregate | 2019-04-30 | Gate F - 1339644 - BN11 Access off A1198 | SC3A - Roadworks | 606 - Import | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16207-001025 | 16207 | 2019-04-23 09:10 | Section 4 | Material | Not on List | Not on List | 150 | ea | 7.5 | 1125 | Miscellaneous | 2019-04-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16354-001025 | 16354 | 2019-04-24 17:32 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-26 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16295-001025 | 16295 | 2019-04-24 10:37 | Section 4 | Material | Waste Management | Dry Mixed Recycling - Skip 8 cubic yard | 2 | Each | 75 | 150 | Waste (General) | 2019-04-25 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 1783 | ea | 17.12 | 30525 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 25 | ea | 150.47 | 3762 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 13 | ea | 29.09 | 378 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 239 | ea | 22.61 | 5404 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 2 | ea | 35.11 | 70 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 1 | ea | 16712 | 16712 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 1319 | ea | 29.46 | 38858 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 10 | ea | 57.68 | 577 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 3 | ea | 32.03 | 96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 3329 | ea | 23.84 | 79363 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 49 | ea | 355.81 | 17435 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 37 | ea | 279.41 | 10338 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 24 | ea | 1260432.03 | 30250369 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 1 | ea | 5945 | 5945 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 37 | ea | 13.08 | 484 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 37 | ea | 13.08 | 484 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16317-001025 | 16317 | 2019-04-24 13:48 | Section 2 | Material | NULL | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2019-04-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16050-001025 | 16050 | 2019-04-17 13:18 | Section 3 | Material | Not on List | Not on List | 1 | person | 650 | 650 | Miscellaneous | 2019-04-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 5 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 2 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 14 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 46 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 58 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 5 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 62 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 124 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 8 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 38 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 44 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-9685-001025 | 9685 | 2018-11-27 13:52 | Section 4 | Material | Not on List | Not on List | 230 | Each | 1.04 | 239.2 | Concrete Accessories | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9685-001025 | 9685 | 2018-11-27 13:52 | Section 4 | Material | Not on List | Not on List | 400 | Each | 0.12 | 48 | Concrete Accessories | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9685-001025 | 9685 | 2018-11-27 13:52 | Section 4 | Material | Not on List | Not on List | 15 | Coil | 46.5 | 697.5 | Concrete Accessories | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9524-001025 | 9524 | 2018-11-23 08:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 13.19 | 105.52 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9524-001025 | 9524 | 2018-11-23 08:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 25.13 | 376.95 | Miscellaneous | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9524-001025 | 9524 | 2018-11-23 08:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 25.58 | 204.64 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9675-001025 | 9675 | 2018-11-27 12:05 | Section 4 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 3.56 | 199.36 | Builders Merchants (General) | 2018-11-29 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9682-001025 | 9682 | 2018-11-27 13:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 229 | 229 | Damage Charges | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1601 - Piling and attendances | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9718-001025 | 9718 | 2018-11-28 12:04 | Section 4 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Not Sure | 2018-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9720-001025 | 9720 | 2018-11-28 12:06 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Blocks and Bricks | 2018-12-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9723-001025 | 9723 | 2018-11-28 13:28 | Section 4 | Material | Not on List | Not on List | 3 | number | NULL | 0 | Not Sure | 2018-12-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9657-001025 | 9657 | 2018-11-27 07:19 | Section 4 | Material | Not on List | Not on List | 1 | Each | 326.03 | 326.03 | Not Sure | 2018-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | Combined Drainage | Not on List | 50 | M | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9485-001025 | 9485 | 2018-11-22 14:15 | Section 4 | Material | Not on List | Not on List | 3 | Each | 650 | 1950 | Miscellaneous | 2018-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9628-001025 | 9628 | 2018-11-26 15:35 | Section 4 | Material | Not on List | Not on List | 1 | Each | 3457.31 | 3457.31 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5034-0020 | 5034 | 2018-08-14 09:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 920 | Each | 1.07 | 0 | Surveying Consumables | 2018-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5378-00250 | 5378 | 2018-08-20 16:43 | Section 3 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-08-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN31 - Culvert - 199 | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9726-001025 | 9726 | 2018-11-28 15:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2353.08 | 2353.08 | Small Tools (Consumables) | 2018-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 1 | U | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 2 | U | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 1 | U | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 9 | M | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 33 | M | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5378-00250 | 5378 | 2018-08-20 16:43 | Section 3 | Material | Not on List | Not on List | 6 | boxes | NULL | 0 | Fixings and Fasteners | 2018-08-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 17 | M | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9428-001025 | 9428 | 2018-11-21 15:03 | Section 4 | Material | Not on List | Not on List | 1 | Each | 415.92 | 415.92 | Damage Charges | 2018-11-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9736-001025 | 9736 | 2018-11-28 16:24 | Section 4 | Material | Not on List | Not on List | 1 | Each | 506 | 506 | Electrical | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 300 | No | 29.28 | 8784 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 10 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 10 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 50 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 2 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 7 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Not on List | Not on List | 70 | No | NULL | 0 | Not Sure | 2018-12-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5380-00252 | 5380 | 2018-08-20 16:43 | Section 4 | Material | Not on List | Not on List | 0.103 | Tonnes | 538 | 55.41 | Rebar and Mesh | 2018-08-23 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 6 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | Combined Drainage | Not on List | 1 | U | 40.95 | 41 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | Combined Drainage | Not on List | 1 | U | 633.75 | 634 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | Combined Drainage | Not on List | 1 | U | 56.55 | 57 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | Combined Drainage | Not on List | 1 | U | 53.62 | 54 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9750-001025 | 9750 | 2018-11-29 07:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 199 | 199 | Damage Charges | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9737-001025 | 9737 | 2018-11-28 16:41 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4500 | 4500 | Damage Charges | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9807-001025 | 9807 | 2018-11-30 08:29 | Section 4 | Material | Concrete Drainage | Not on List | 10 | Packs | NULL | 0 | Concrete Drainage | 2018-12-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9531 | 9531 | 2018-11-23 10:21 | Section 3 | Material | Not on List | Not on List | 2 | each | 1200 | 2400 | Miscellaneous | 2018-11-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9758-001025 | 9758 | 2018-11-29 08:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 10.76 | 64.56 | Small Tools (Consumables) | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 20 | no | 22.62 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9758-001025 | 9758 | 2018-11-29 08:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 37.08 | 222.48 | Small Tools (Consumables) | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9758-001025 | 9758 | 2018-11-29 08:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 10.76 | 64.56 | Small Tools (Consumables) | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 370mm X 7.6mm Pack Of 100 Spartan (230065) | 25 | Each | 3.88 | 97 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Microwave Oven Manual 700watt (230937) | 2 | Each | 38.22 | 76 | Miscellaneous | 2018-12-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Kettle Jug Electric Cordless White C/W Gauge 1.7ltrs 2.2kw (230998) | 4 | Each | 10.48 | 42 | Miscellaneous | 2018-12-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Torch Head Varta Indestructible 1watt Led 3aaa (764082) | 2 | Each | 15 | 30 | Miscellaneous | 2018-11-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9765-001025 | 9765 | 2018-11-29 08:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1342.96 | 1342.96 | Janitorial | 2018-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | 24.84 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9587-001025 | 9587 | 2018-11-23 17:49 | Section 3 | Material | Not on List | Not on List | 60 | Each | 42.5 | 2550 | Miscellaneous | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9718-001025 | 9718 | 2018-11-28 12:04 | Section 4 | Material | Not on List | Not on List | 200 | Each | 10 | 2000 | Fixings and Fasteners | 2018-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9723-001025 | 9723 | 2018-11-28 13:28 | Section 4 | Material | Not on List | Not on List | 3 | Each | 336.95 | 1010.85 | Plastic Drainage | 2018-12-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9833-001025 | 9833 | 2018-11-30 14:00 | Section 3 | Material | Signage | Not on List | 80 | number | NULL | 0 | Miscellaneous | 2018-12-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9833-001025 | 9833 | 2018-11-30 14:00 | Section 3 | Material | Signage | Not on List | 80 | number | NULL | 0 | Miscellaneous | 2018-12-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 370mm X 7.6mm Pack Of 100 Spartan (230065) | 25 | Each | 3.88 | 97 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Microwave Oven Manual 700watt (230937) | 2 | Each | 38.22 | 76.44 | Miscellaneous | 2018-12-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Kettle Jug Electric Cordless White C/W Gauge 1.7ltrs 2.2kw (230998) | 4 | Each | 10.48 | 41.92 | Miscellaneous | 2018-12-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Torch Head Varta Indestructible 1watt Led 3aaa (764082) | 2 | Each | 15 | 30 | Miscellaneous | 2018-11-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | 21.33 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 110 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 300 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | 6.1 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 120 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 45 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 45 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | 6.26 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9756-001025 | 9756 | 2018-11-29 07:24 | Section 4 | Material | Not on List | Not on List | 150 | no | 20.5 | 3075 | Miscellaneous | 2018-12-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9756-001025 | 9756 | 2018-11-29 07:24 | Section 4 | Material | Not on List | Not on List | 110 | no | 9.58 | 1053.8 | Miscellaneous | 2018-12-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9819-001025 | 9819 | 2018-11-30 11:14 | Section 4 | Material | Aggregate | Not on List | 4 | Each | 52.5 | 210 | Builders Merchants (General) | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9819-001025 | 9819 | 2018-11-30 11:14 | Section 4 | Material | Aggregate | Not on List | 6 | Each | 32.74 | 196.44 | Builders Merchants (General) | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9819-001025 | 9819 | 2018-11-30 11:14 | Section 4 | Material | Aggregate | Not on List | 56 | Bag | 2.9 | 162.4 | Builders Merchants (General) | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9720-001025 | 9720 | 2018-11-28 12:06 | Section 4 | Material | Not on List | Not on List | 60 | Ea | 12 | 720 | Blocks and Bricks | 2018-12-04 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | NULL | Not on List | 1 | Each | 40.95 | 40.95 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | NULL | Not on List | 1 | Each | 633.75 | 633.75 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | NULL | Not on List | 1 | Each | 56.55 | 56.55 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | 3.35 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | NULL | Not on List | 1 | Each | 53.62 | 53.62 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | NULL | Not on List | 100 | Each | 35 | 3500 | NULL | NULL | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 100 | Each | 35 | 3500 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 1 | Each | 45 | 45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 1 | Each | 58 | 58 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 1 | Each | 61 | 61 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 8 | Each | 7.5 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 14 | Each | 14.95 | 209.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 1 | Each | 38 | 38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ9885 | 9885 | 2018-12-03 14:19 | Section 4 | Material | Not on List | Not on List | 86 | t | NULL | 0 | Reinforcement | 2019-01-08 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | 2.77 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9691-001025 | 9691 | 2018-11-27 15:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4449.2 | 4449.2 | Plastic Drainage | 2019-01-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9691-001025 | 9691 | 2018-11-27 15:36 | Section 4 | Material | NULL | Not on List | 1 | Each | 140 | 140 | NULL | 2019-01-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9677-001025 | 9677 | 2018-11-27 12:35 | Section 4 | Material | Aggregate | Not on List | 200 | NULL | NULL | 0 | Aggregate | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9672-001025 | 9672 | 2018-11-27 11:27 | Section 4 | Material | Not on List | Not on List | 5 | Each | 11.5 | 57.5 | Surveying Consumables | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9672-001025 | 9672 | 2018-11-27 11:27 | Section 4 | Material | Not on List | Not on List | 3 | Each | 20 | 60 | Surveying Consumables | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9672-001025 | 9672 | 2018-11-27 11:27 | Section 4 | Material | Not on List | Not on List | 2 | Each | 28 | 56 | Surveying Consumables | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9672-001025 | 9672 | 2018-11-27 11:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 49 | 49 | Surveying Consumables | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 300 | No | 29.28 | 8784 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 10 | No | 29.01 | 290.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 10 | No | 29.01 | 290.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | 5.6 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 50 | No | 34.1 | 1705 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 2 | No | 46.35 | 92.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 7 | No | 243.87 | 1707.09 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Not on List | Not on List | 70 | No | 7.5 | 525 | Not Sure | 2018-12-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 6 | No | 4.67 | 28.02 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | NULL | 0 | Not Sure | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11760-001025 | 11760 | 2019-01-31 17:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1399.48 | Each | 1 | 1399 | Small Tools (Consumables) | 2019-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11745-001025 | 11745 | 2019-01-31 15:36 | Section 4 | Material | NULL | Not on List | 8 | EA | 77.85 | 622.8 | Concrete Drainage | 2019-02-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11745-001025 | 11745 | 2019-01-31 15:36 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2019-02-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11745-001025 | 11745 | 2019-01-31 15:36 | Section 4 | Material | NULL | Not on List | 1 | Each | 240 | 240 | Concrete Drainage | 2019-02-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 2 | No | 121.59 | 243.18 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 1 | No | 113.25 | 113.25 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 2 | No | 164.37 | 328.74 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 14 | No | 83.41 | 1167.74 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 3 | No | 44.41 | 133.23 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 6 | No | 62.54 | 375.24 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 28 | No | 94.82 | 2654.96 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 4 | No | 103.11 | 412.44 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 2 | No | 111.58 | 223.16 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 4 | No | 182.18 | 728.72 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11744-001025 | 11744 | 2019-01-31 15:54 | Section 3 | Material | NULL | Not on List | 2 | No | 39.7 | 79.4 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11842-001025 | 11842 | 2019-02-04 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-02-08 | Gate C - 1339702 - BN06 (East Coast Railway) Via Logistics Yard Access | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11743-001 | 11743 | 2019-01-31 15:53 | Section 3 | Material | Aggregate | A10 Pipe Bed | 300 | Tonnes | 21.1 | 6330 | Aggregate | 2019-02-01 | RVP 419 - 1340880 - A14 Westbound (West of Junction 28) | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 27 | No. | 34.82 | 940.14 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 687.5 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 50 | No. | 48.86 | 2443 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11854-001025 | 11854 | 2019-02-04 11:49 | Section 4 | Material | Not on List | Not on List | 180 | ROLLS | NULL | 0 | Concrete Accessories | 2019-02-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11877-001025 | 11877 | 2019-02-04 16:24 | Section 4 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 3 | Price Per Thousand | 345 | 1035 | Blocks and Bricks | 2019-02-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - Buyers Group
MREQ-11877-001025 | 11877 | 2019-02-04 16:24 | Section 4 | Material | Not on List | Not on List | 500 | no | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - Buyers Group
MREQ-11877-001025 | 11877 | 2019-02-04 16:24 | Section 4 | Material | Kerbs | Not on List | 250 | no | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - Buyers Group
MREQ-11882-001025 | 11882 | 2019-02-04 16:38 | Section 2 | Material | Aggregate | 6G | 240 | Tonnes | 22 | 5280 | Aggregate | 2019-02-12 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Perf (346341) | 14 | Each | 24.82 | 347 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Perf (346341) | 14 | Each | 24.82 | 347 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 3 | Each | 34.82 | 104 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 2 | Each | 120.62 | 241 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 14 | Each | 116.62 | 1633 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 100 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Not on List | 9 | NULL | NULL | 0 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Not on List | 2 | NULL | NULL | 0 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 47.04 | 470 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 4 | Each | 59.17 | 237 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 8 | Each | 67.9 | 543 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 2 | Each | 35.52 | 71 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 3 | Each | 81.96 | 246 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 1 | Each | 53.01 | 53 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 7 | Each | 3.38 | 24 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 2 | Each | 6.54 | 13 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Not on List | 5 | NULL | NULL | 0 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11903-001025 | 11903 | 2019-02-05 07:29 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11905-001025 | 11905 | 2019-02-05 07:41 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11907-001025 | 11907 | 2019-02-05 07:50 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11908-001025 | 11908 | 2019-02-05 07:55 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11910-001025 | 11910 | 2019-02-05 07:59 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11916-001025 | 11916 | 2019-02-05 09:10 | Section 2 | Material | Not on List | Not on List | 1 | each | 3829.38 | 3829 | Not Sure | 2019-02-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11919-001025 | 11919 | 2019-02-05 09:28 | Section 5 | Material | Not on List | Not on List | 1 | each | 243.38 | 243 | Not Sure | 2019-02-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11920 | 11920 | 2019-04-11 11:35 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-02-07 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Request - Ops Pass Back | No - Pass Back | NULL | NULL
MREQ-11921-001025 | 11921 | 2019-02-05 09:38 | Section 4 | Material | Not on List | Not on List | 1 | each | 1767.13 | 1767 | Miscellaneous | 2019-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11922-001025 | 11922 | 2019-02-05 09:50 | Section 3 | Material | Not on List | Not on List | 1 | each | 3760.63 | 3761 | Miscellaneous | 2019-02-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11923-001025 | 11923 | 2019-02-05 10:18 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11812 | 11812 | 2019-02-01 13:29 | Section 4 | Material | Not on List | Not on List | 25 | rolls | 9.62 | 240.5 | Geotextiles | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-11812 | 11812 | 2019-02-01 13:29 | Section 4 | Material | Not on List | Not on List | 10 | rolls | 16.18 | 161.8 | Geotextiles | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-11812 | 11812 | 2019-02-01 13:29 | Section 4 | Material | NULL | Not on List | 1 | Each | 260 | 260 | Geotextiles | 2019-02-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | Ducting | Not on List | 2300 | metres | NULL | 0 | Electrical | 2019-02-08 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | Ducting | Polypipe 94mm Ridgiduct Coupler (877674) | 400 | Number | 2.6 | 1040 | Electrical | 2019-02-08 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | Ducting | Not on List | 800 | Number | NULL | 0 | Electrical | 2019-02-08 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | Ducting | Not on List | 400 | Number | NULL | 0 | Electrical | 2019-02-08 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | Ducting | Draw Cord 450m (537046) | 6 | Each | 25 | 150 | Electrical | 2019-02-08 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11926-001025 | 11926 | 2019-02-05 10:39 | Section 2 | Material | Not on List | Not on List | 1 | each | 56 | 56 | Laboratory Equipment / Certification | 2019-02-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11927-001025 | 11927 | 2019-02-05 10:49 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11927-001025 | 11927 | 2019-02-05 10:49 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Accessories | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11929-001025 | 11929 | 2019-02-05 11:01 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2019-02-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11930 | 11930 | NULL | NULL | NULL | Not on List | Not on List | 15 | ea | 330 | 4950 | Not Sure | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Buyer - Closed | NULL | NULL | NULL
MREQ-11930 | 11930 | NULL | NULL | NULL | Not on List | Not on List | 1 | ea | 330 | 330 | Not Sure | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Buyer - Closed | NULL | NULL | NULL
MREQ-11933-001025 | 11933 | 2019-02-05 11:54 | Section 2 | Material | Timber | Not on List | 6 | packs of 25 normally | 0 | 0 | Timber Products | 2019-02-08 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11933-001025 | 11933 | 2019-02-05 11:54 | Section 2 | Material | Timber | Not on List | 4 | packs of 25 normally | 0 | 0 | Timber Products | 2019-02-08 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11944-001025 | 11944 | 2019-02-05 15:29 | Core | Material | Not on List | Not on List | 20000 | each | NULL | 0 | Office Supplies | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11947-001025 | 11947 | 2019-02-05 15:41 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Office Supplies | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11964-001025 | 11964 | 2019-02-05 17:05 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Fixings and Fasteners | 2019-02-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11968-001025 | 11968 | 2019-02-05 17:47 | Section 4 | Material | Not on List | Not on List | 500 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11982-001025 | 11982 | 2019-02-06 08:03 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Operations Rejected | No - Reject | NULL | NULL
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 100 | Meters | 4.59 | 459 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 40 | Meters | 6 | 240 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 1 | Each | 11.94 | 12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 200 | Meter | 3.52 | 704 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 20 | Meter | 5.43 | 109 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 3 | Each | 7.68 | 23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 3 | Each | 7.68 | 23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 600 | Meter | 1.5 | 900 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11995-001025 | 11995 | 2019-02-06 11:20 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 28 | 28 | Miscellaneous | 2019-02-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11996 | 11996 | NULL | NULL | NULL | Not on List | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | NULL | NULL | NULL
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 220 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 200 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 30 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 4 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 4 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 4 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 4 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 1 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 1 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 1 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12002-001025 | 12002 | 2019-02-06 12:37 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-08 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | NULL
MREQ-12004 | 12004 | 2019-01-31 13:58 | Core | Material | Not on List | Not on List | 10 | Each | NULL | 0 | Electrical | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12006-001025 | 12006 | 2019-02-06 14:06 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Drainage | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12006-001025 | 12006 | 2019-02-06 14:06 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Drainage | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12007-001025 | 12007 | 2019-02-06 14:13 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2019-02-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12008-001025 | 12008 | 2019-02-06 14:18 | Section 4 | Material | Not on List | Not on List | 1 | Each | 440.75 | 441 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12009-001025 | 12009 | 2019-02-06 14:48 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-08 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11982-001025 | 11986 | 2019-02-06 09:02 | Section 2 | Material | Not on List | Not on List | 20 | Roll | 46.5 | 930 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196 | Concrete Drainage | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142 | Concrete Drainage | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | Bagged | Not on List | 20 | Unit | NULL | 0 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | Bagged | Not on List | 40 | Tubs | NULL | 0 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12022-001025 | 12022 | 2019-02-06 17:10 | Section 2 | Material | Aggregate | Type 1 | 9400 | Tonnes | 16 | 150400 | Aggregate | 2019-02-06 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | NULL | Req - Buyers Group
MREQ-12031-001025 | 12031 | 2019-02-07 06:55 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12033-001025 | 12033 | 2019-02-07 07:25 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-08 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | NULL | Req - Buyers Group
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 12 | Each | 85.24 | 1022.88 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 8 | Each | 55.13 | 441.04 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 2 | Each | 126.11 | 252.22 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 10 | Each | 149.45 | 1494.5 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 2 | Each | 121.59 | 243.18 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 2 | Each | 109.94 | 219.88 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 12 | Each | 61.54 | 738.48 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 3 | Each | 106.93 | 320.79 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 3 | Each | 149.8 | 449.4 | Concrete Drainage | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 55 | Each | 31.37 | 1725.35 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 55 | Each | 31.37 | 1725.35 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 22 | Each | 86.24 | 1897.28 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28256-001025 | 28256 | 2020-01-17 07:23 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-01-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28259-001025 | 28259 | 2020-01-17 07:44 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-01-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 6 | Each | 24.45 | 146.7 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28038-001025 | 28038 | 2020-01-10 13:06 | Section 6 | Material | Not on List | Not on List | 1 | No | 115 | 115 | Builders Merchants (General) | 2020-01-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28266-001025 | 28266 | 2020-01-17 09:35 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 621.12 | 621 | Damage Charges | 2020-01-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 602 - Excavation (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28090-001025 | 28090 | 2020-01-13 13:37 | Section 6 | Material | Aggregate | A20 Pipe Bed | 300 | Tonnes | 4 | 1200 | Aggregate | 2020-01-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 32 | Each | 15.19 | 486.08 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27155-001025 | 27155 | 2019-11-29 14:22 | Section 3 | Material | Signage | IFE Signs - 540 | 6 | Each | 32 | 192 | Small Tools (Consumables) | 2019-12-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 1201 - Traffic Signs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28319-001025 | 28319 | 2020-01-20 09:45 | Section 4 | Material | Not on List | Not on List | 650 | NULL | NULL | 0 | Fixings and Fasteners | 2020-01-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27912-001025 | 27912 | 2020-01-07 15:33 | Section 3 | Material | Not on List | Not on List | 7 | no. | 418.81 | 2931.67 | Miscellaneous | 2020-01-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26353-001025 | 26353 | 2019-11-08 13:28 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 18 | Each | 120.62 | 2171.16 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28338-001025 | 28338 | 2020-01-20 16:24 | Section 6 | Material | Not on List | Not on List | 130 | Number | NULL | 0 | Fixings and Fasteners | 2020-01-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16715-001025 | 16715 | 2019-05-01 10:35 | Core | Material | Not on List | Not on List | 1 | NULL | 1440 | 1440 | Miscellaneous | 2019-05-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28353-001025 | 28353 | 2020-01-21 07:44 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (General) | 2020-01-21 | RVP 417 - 1339631 - Girton Compound Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28274-001025 | 28274 | 2020-01-17 11:57 | Section 4 | Material | NULL | NULL | 300 | Each | 35.58 | 10674 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28274-001025 | 28274 | 2020-01-17 11:57 | Section 4 | Material | NULL | NULL | 10 | Each | 38.85 | 388.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28274-001025 | 28274 | 2020-01-17 11:57 | Section 4 | Material | NULL | NULL | 20 | Each | 41.1 | 822 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28274-001025 | 28274 | 2020-01-17 11:57 | Section 4 | Material | NULL | NULL | 7 | Each | 144.35 | 1010.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28274-001025 | 28274 | 2020-01-17 11:57 | Section 4 | Material | NULL | NULL | 200 | Each | 7.1 | 1420 | Builders Merchants (General) | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 22 | Each | 17.45 | 383.9 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27930-001025 | 27930 | 2020-01-08 08:46 | Section 4 | Material | Hazardous Waste | Oil/water/diesel - 205L drum | 1 | Each | 4203.9 | 4203.9 | Fuel | 2020-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28332-001025 | 28332 | 2020-01-20 15:26 | Section 4 | Material | Not on List | Not on List | 4 | Each | 365 | 1460 | Ductile Drainage | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 44 | Each | 9.04 | 397.76 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 300 | Each | 4.59 | 1377 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 32 | Each | 5.44 | 174.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 32 | Each | 5.44 | 174.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 16 | Each | 5.44 | 87.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 16 | Each | 5.44 | 87.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 1 | Each | 22.5 | 22.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28381-001025 | 28381 | 2020-01-21 16:29 | Core | Material | Not on List | Not on List | 1 | NULL | 2750 | 2750 | Miscellaneous | 2020-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No | 222.75 | 223 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | No | 13.44 | 27 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 68 | Each | 34.82 | 2367.76 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | No | 15.55 | 31 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No | 145.89 | 146 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | Not on List | Not on List | 3 | No | 22 | 66 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | Not on List | Not on List | 1 | No | 30 | 30 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | Not on List | Not on List | 2 | Hr | 35 | 70 | Professional Services | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | Not on List | Not on List | 1 | No | 53.98 | 54 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28365-001025 | 28365 | 2020-01-21 13:26 | Section 4 | Material | NULL | NULL | 10 | Each | 5.24 | 52.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28365-001025 | 28365 | 2020-01-21 13:26 | Section 4 | Material | NULL | NULL | 6 | Each | 5.24 | 31.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 78 | Each | 6.54 | 510.12 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28404-001025 | 28404 | 2020-01-22 14:10 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-01-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 3020 - Seeding, Turfing and Planting | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28393-001025 | 28393 | 2020-01-22 09:16 | Section 4 | Material | NULL | NULL | 200 | Each | 4.97 | 994 | Builders Merchants (General) | 2020-01-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28409-001025 | 28409 | 2020-01-22 16:31 | Section 4 | Material | Kerbs | Not on List | 8 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28409-001025 | 28409 | 2020-01-22 16:31 | Section 4 | Material | Kerbs | Not on List | 8 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28409-001025 | 28409 | 2020-01-22 16:31 | Section 4 | Material | Kerbs | Not on List | 16 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28423-001025 | 28423 | 2020-01-23 08:15 | Section 4 | Material | Not on List | Not on List | 2 | Pallet | NULL | 0 | Miscellaneous | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28423-001025 | 28423 | 2020-01-23 08:15 | Section 4 | Material | Not on List | Not on List | 2 | Pallet | NULL | 0 | Miscellaneous | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28427-001025 | 28427 | 2020-01-23 08:36 | Section 4 | Material | Not on List | Not on List | 2000 | Number | NULL | 0 | Surveying Consumables | 2020-01-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28427-001025 | 28427 | 2020-01-23 08:36 | Section 4 | Material | Not on List | Not on List | 1000 | Number | NULL | 0 | Surveying Consumables | 2020-01-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 156 | Each | 2.75 | 429 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28427-001025 | 28427 | 2020-01-23 08:36 | Section 4 | Material | Not on List | Not on List | 1000 | Number | NULL | 0 | Surveying Consumables | 2020-01-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28428-001025 | 28428 | 2020-01-23 09:00 | Section 5 | Material | Not on List | Not on List | 1 | No | 3623 | 3623 | Miscellaneous | 2020-01-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-28431-001025 | 28431 | 2020-01-23 09:15 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 12 | Each | 179.84 | 2158.08 | Plastic Drainage | 2020-01-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28431-001025 | 28431 | 2020-01-23 09:15 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain Seal (346400) | 18 | Each | 22.36 | 402.48 | Plastic Drainage | 2020-01-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28431-001025 | 28431 | 2020-01-23 09:15 | Section 2 | Material | Twinwall | Not on List | 6 | ea | 231.57 | 1389.42 | Plastic Drainage | 2020-01-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28377-001025 | 28377 | 2020-01-21 15:07 | Section 4 | Material | NULL | NULL | 10 | Each | 40.16 | 401.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28377-001025 | 28377 | 2020-01-21 15:07 | Section 4 | Material | NULL | NULL | 10 | Each | 6 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 54 | Each | 23.14 | 1249.56 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28395-001025 | 28395 | 2020-01-22 11:41 | Section 5 | Material | NULL | NULL | 3 | Each | 92.7 | 278.1 | Plastic Drainage | 2020-01-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28453-001025 | 28453 | 2020-01-23 15:54 | Section 4 | Material | Not on List | Not on List | 1 | No | 490.47 | 490 | Professional Services | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28479-001025 | 28479 | 2020-01-24 08:30 | Section 4 | Material | Not on List | Not on List | 200 | no | NULL | 0 | Miscellaneous | 2020-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28445-001025 | 28445 | 2020-01-23 14:31 | Section 5 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28445-001025 | 28445 | 2020-01-23 14:31 | Section 5 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28445-001025 | 28445 | 2020-01-23 14:31 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 4 | Each | 32.74 | 131 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 65 | Each | 3.38 | 219.7 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28484-001025 | 28484 | 2020-01-24 10:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | 15.68 | 78 | Small Tools (Consumables) | 2020-01-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28486-001025 | 28486 | 2020-01-24 10:05 | Section 4 | Material | Not on List | Not on List | 1 | No | 555 | 555 | Miscellaneous | 2020-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 270 | No | 30.16 | 8143.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 5 | No | 311.01 | 1555.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 5 | No | 58.27 | 291.35 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 14 | bags | 59.26 | 829.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 1 | NULL | 215.85 | 215.85 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 1 | NULL | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 130 | Each | 1.86 | 241.8 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28405-001025 | 28405 | 2020-01-22 14:44 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 1210 | 1210 | Miscellaneous | 2020-01-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28234-001025 | 28234 | 2020-01-16 14:57 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28500-001025 | 28500 | 2020-01-24 13:46 | Section 4 | Material | Aggregate | 6G | 500 | Tonnes | 32.9 | 16450 | Aggregate | 2020-01-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28569-001025 | 28569 | 2020-01-28 07:59 | Section 6 | Material | Not on List | Not on List | 420 | Number | NULL | 0 | Fixings and Fasteners | 2020-01-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28569-001025 | 28569 | 2020-01-28 07:59 | Section 6 | Material | Not on List | Not on List | 50 | Number | NULL | 0 | Timber Products | 2020-01-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 12 | Each | 10.5 | 126 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28569-001025 | 28569 | 2020-01-28 07:59 | Section 6 | Material | Not on List | Not on List | 60 | m2 | NULL | 0 | Geotextiles | 2020-01-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28569-001025 | 28569 | 2020-01-28 07:59 | Section 6 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Fixings and Fasteners | 2020-01-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28569-001025 | 28569 | 2020-01-28 07:59 | Section 6 | Material | Not on List | Not on List | 3 | Number | NULL | 0 | Miscellaneous | 2020-01-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 20 | Each | 1.84 | 36.8 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28556-001025 | 28556 | 2020-01-27 16:09 | Section 4 | Material | Not on List | Not on List | 74 | Each | 130.26 | 9639.24 | Plastic Drainage | 2020-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28556-001025 | 28556 | 2020-01-27 16:09 | Section 4 | Material | Not on List | Not on List | 65 | Each | 9.46 | 614.9 | Plastic Drainage | 2020-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 1 | No. | 81 | 81 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 5 | No. | 115 | 575 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 20 | packs of 100 Flags | 10.5 | 210 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 15 | packs of 100 Flags | 10.5 | 158 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 20 | packs of 100 Flags | 10.5 | 210 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 40 | Each | 0.85 | 34 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 10 | packs of 100 Flags | 10.5 | 105 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 10 | box | 10 | 100 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28293-001025 | 28293 | 2020-01-17 15:13 | Section 5 | Material | Not on List | Not on List | 23 | ea | 15.47 | 355.81 | Builders Merchants (General) | 2020-01-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28583-001025 | 28583 | 2020-01-28 11:33 | Section 4 | Material | Not on List | Not on List | 3 | Number | 32 | 96 | Surveying Consumables | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28583-001025 | 28583 | 2020-01-28 11:33 | Section 4 | Material | Not on List | Not on List | 1 | Number | 195 | 195 | Surveying Consumables | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28583-001025 | 28583 | 2020-01-28 11:33 | Section 4 | Material | Not on List | Not on List | 200 | Number | 0.2 | 40 | Surveying Consumables | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 124 | ea | 25.77 | 3195.48 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 62 | ea | 42.91 | 2660.42 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 56 | ea | 4.15 | 232.4 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 124 | ea | 15.8 | 1959.2 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 50 | Each | 14.93 | 746.5 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 2 | ea | 200.81 | 401.62 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 1 | ea | 111.15 | 111.15 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 1 | ea | 9.62 | 9.62 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 1 | ea | 9.62 | 9.62 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24354-001025 | 24354 | 2019-09-29 17:24 | Section 5 | Material | Not on List | Not on List | 1 | SM | 17490.28 | 17490.28 | Concrete Drainage | 2019-10-03 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24356-001025 | 24356 | 2019-09-29 18:07 | Section 5 | Material | Not on List | Not on List | 1 | SM | 17490.28 | 17490.28 | Not Sure | 2019-10-03 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24297-001025 | 24297 | 2019-09-27 08:20 | Section 5 | Material | Not on List | Not on List | 1 | SM | 15876.56 | 15876.56 | Miscellaneous | 2019-10-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6863-00751 | 6863 | 2018-09-21 12:23 | Section 4 | Material | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 4 | Each | 232.2 | 928.8 | Concrete Drainage | 2018-10-08 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24593-001025 | 24593 | 2019-10-03 13:33 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 339.6 | 340 | Miscellaneous | 2019-08-27 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24547-001025 | 24547 | 2019-10-02 17:42 | Core | Material | PPE, Small Tools and Consumables | Not on List | 144 | Pack 24 | 6.29 | 905.76 | Miscellaneous | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24389-001025 | 24389 | 2019-09-30 13:13 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | PACK | 55 | 110 | Janitorial | 2019-10-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24542-001025 | 24542 | 2019-10-02 15:51 | Section 2 | Material | Not on List | Not on List | 12 | Each | 36.14 | 433.68 | Builders Merchants (General) | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Pipe 2.5m (249364) | 17 | Each | 210.95 | 3586.15 | Concrete Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 2 | Each | 47.04 | 94.08 | Concrete Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6865-00751 | 6865 | 2018-09-21 12:34 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2166.3 | 2166.3 | Fixings and Fasteners | 2018-10-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 1 | Each | 59.17 | 59.17 | Concrete Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Twinwall | Polypipe Road Gully 450mm x 900mm (573005) | 14 | Each | 15.71 | 219.94 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Twinwall | Not on List | 10 | Each | NULL | 0 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 5 | Each | 116.62 | 583.1 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 18 | Each | 166.43 | 2995.74 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 72 | Each | 10.5 | 756 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Saint Gobain Castings | 454x454x100 D400 Watershed GG&F (257790) | 9 | Each | 63.84 | 574.56 | Builders Merchants (General) | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Saint Gobain Castings | Not on List | 1 | Each | NULL | 0 | Builders Merchants (General) | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5190-00117 | 5190 | 2018-08-16 07:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6865-00751 | 6865 | 2018-09-21 12:34 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1115.5 | 1115.5 | Fixings and Fasteners | 2018-10-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24510-001025 | 24510 | 2019-10-02 10:43 | Section 3 | Material | Not on List | Not on List | 1 | each | 1247.79 | 1247.79 | Miscellaneous | 2019-10-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24590-001025 | 24590 | 2019-10-03 09:58 | Section 4 | Material | Not on List | Not on List | 1 | SM | 1135.44 | 1135.44 | Miscellaneous | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24557-001025 | 24557 | 2019-10-03 07:46 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain Seal (346400) | 30 | Each | 28.18 | 845.4 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24557-001025 | 24557 | 2019-10-03 07:46 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 144 | Each | 1.55 | 223.2 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24606-001025 | 24606 | 2019-10-03 13:43 | Section 4 | Material | Not on List | Not on List | 10 | EA | 122.72 | 1227.2 | Builders Merchants (General) | 2019-10-04 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24509-001025 | 24509 | 2019-10-02 10:40 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 3281.5 | 3281.5 | Miscellaneous | 2019-10-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6914-00751 | 6914 | 2018-09-24 10:28 | Section 4 | Material | Not on List | Not on List | 3.188 | Tonne | 538 | 1715.14 | Rebar and Mesh | 2018-10-01 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24601-001025 | 24601 | 2019-10-03 12:53 | Section 2 | Material | Bagged | Not on List | 3 | NULL | NULL | 0 | Concrete Accessories | 2019-10-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24601-001025 | 24601 | 2019-10-03 12:53 | Section 2 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Accessories | 2019-10-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24651-001025 | 24651 | 2019-10-04 12:13 | Section 2 | Material | Not on List | Not on List | 48 | NULL | NULL | 0 | Miscellaneous | 2019-10-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24594-001025 | 24594 | 2019-10-03 13:47 | Section 4 | Material | Not on List | Not on List | 7 | EA | 365 | 2555 | Plastic Drainage | 2019-10-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24594-001025 | 24594 | 2019-10-03 13:47 | Section 4 | Material | Not on List | Not on List | 20 | no | 4.6 | 92 | Plastic Drainage | 2019-10-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24323-001025 | 24323 | 2019-09-27 13:33 | Section 3 | Material | Not on List | Not on List | 2 | ea | 31.85 | 63.7 | Miscellaneous | 2019-10-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6914-00751 | 6914 | 2018-09-24 10:28 | Section 4 | Material | Not on List | Not on List | 3.788 | Tonne | 538 | 2037.94 | Rebar and Mesh | 2018-10-01 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24659-001025 | 24659 | 2019-10-04 13:45 | Section 4 | Material | Not on List | Not on List | 8 | EA | 46.5 | 372 | Rebar and Mesh | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6915-00751 | 6915 | 2018-09-24 12:21 | Section 4 | Material | Not on List | Not on List | 16 | Each | 18.51 | 296.16 | Miscellaneous | 2018-10-01 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN24 - Girton Interchange Bridge C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23522-001025 | 23522 | 2019-09-11 14:13 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 3387.91 | 3387.91 | Miscellaneous | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24708-001025 | 24708 | 2019-10-07 12:13 | Core | Material | Not on List | Not on List | 12823 | SUM | 1 | 12823 | Professional Services | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24682-001025 | 24682 | 2019-10-07 07:01 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 70 | no | 3.35 | 234.5 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24713-001025 | 24713 | 2019-10-07 13:39 | Section 2 | Material | Not on List | Not on List | 200 | m | NULL | 0 | Builders Merchants (General) | 2019-10-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24705-001025 | 24705 | 2019-10-07 11:41 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | EA | 3.42 | 68.4 | Small Tools (Consumables) | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24730-001025 | 24730 | 2019-10-07 16:13 | Core | Material | Not on List | Not on List | 1 | ea | 26860.8 | 26861 | Training | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24733-001025 | 24733 | 2019-10-07 16:39 | Core | Material | Not on List | Not on List | 2 | number | 165 | 330 | Surveying Consumables | 2019-10-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24732-001025 | 24732 | 2019-10-07 16:33 | Section 2 | Material | Not on List | Not on List | 75 | no. | NULL | 0 | Concrete Accessories | 2019-10-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24744-001025 | 24744 | 2019-10-08 07:24 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23763-001025 | 23763 | 2019-09-17 07:37 | Section 2 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 50 | Each | 24.32 | 1216 | Timber Products | 2019-09-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23763-001025 | 23763 | 2019-09-17 07:37 | Section 2 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 50 | Each | 6.82 | 341 | Timber Products | 2019-09-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23763-001025 | 23763 | 2019-09-17 07:37 | Section 2 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 50 | Each | 10.08 | 504 | Timber Products | 2019-09-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 70 | no | 2.77 | 193.9 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24518-001025 | 24518 | 2019-10-02 11:36 | Section 5 | Material | Kerbs | Not on List | 1 | SM | 358.84 | 358.84 | Not Sure | 2019-10-09 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24520-001025 | 24520 | 2019-10-02 11:17 | Section 6 | Material | Not on List | Not on List | 1 | Each | 1460 | 1460 | Flow Control | 2019-10-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24520-001025 | 24520 | 2019-10-02 11:17 | Section 6 | Material | Not on List | Not on List | 1 | Each | 1650 | 1650 | Flow Control | 2019-10-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24520-001025 | 24520 | 2019-10-02 11:17 | Section 6 | Material | Not on List | Not on List | 1 | Each | 265 | 265 | Flow Control | 2019-10-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24520-001025 | 24520 | 2019-10-02 11:17 | Section 6 | Material | Not on List | Not on List | 1 | Each | 265 | 265 | Flow Control | 2019-10-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24520-001025 | 24520 | 2019-10-02 11:17 | Section 6 | Material | Not on List | Not on List | 2 | Each | 95 | 190 | Flow Control | 2019-10-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24485-001025 | 24485 | 2019-10-02 07:38 | Core | Material | NULL | NULL | 1 | Each | 384.26 | 384.26 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 70 | no | 5.6 | 392 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24626-001025 | 24626 | 2019-10-04 06:57 | Section 4 | Material | Not on List | Not on List | 2000 | Each | 0.9 | 1800 | Timber Products | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24531-001025 | 24531 | 2019-10-02 13:47 | Core | Material | PPE, Small Tools and Consumables | Not on List | 32 | Each | 28.8 | 921.6 | PPE | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24534-001025 | 24534 | 2019-10-02 15:09 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1098.95 | Each | 1 | 1098.95 | Janitorial | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24773-001025 | 24773 | 2019-10-08 11:08 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | EACH | 76.5 | 153 | Small Tools (Consumables) | 2019-10-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24628-001025 | 24628 | 2019-10-04 07:26 | Section 4 | Material | Not on List | Not on List | 4 | Pack 100 | 10.5 | 42 | Surveying Consumables | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24756-001025 | 24756 | 2019-10-08 09:01 | Section 2 | Material | Not on List | Not on List | 100000 | Litres | 1 | 100000 | Fuel | 2019-10-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24689-001025 | 24689 | 2019-10-07 08:21 | Core | Material | NULL | NULL | 1 | Each | 440 | 440 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 70 | no | 3.91 | 273.7 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24625-001025 | 24625 | 2019-10-04 06:36 | Section 4 | Material | Not on List | Not on List | 10 | Each | 285 | 2850 | Miscellaneous | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24639-001025 | 24639 | 2019-10-04 10:55 | Core | Material | NULL | NULL | 1 | Each | 506 | 506 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24609-001025 | 24609 | 2019-10-03 16:37 | Core | Material | NULL | NULL | 1 | Each | 22 | 22 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24685-001025 | 24685 | 2019-10-07 07:22 | Section 3 | Material | Not on List | Not on List | 150 | EA | 0.95 | 142.5 | Surveying Consumables | 2019-10-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24685-001025 | 24685 | 2019-10-07 07:22 | Section 3 | Material | Not on List | Not on List | 4 | EA | 29.11 | 116.44 | Concrete Drainage | 2019-10-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24685-001025 | 24685 | 2019-10-07 07:22 | Section 3 | Material | Not on List | Not on List | 4 | EA | 29.11 | 116.44 | Concrete Drainage | 2019-10-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24575-001025 | 24575 | 2019-10-03 10:46 | Section 4 | Material | Not on List | Not on List | 112 | Each | 2.97 | 332.64 | Small Tools (Consumables) | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24702-001025 | 24702 | 2019-10-07 10:56 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 0.37 | 370 | Miscellaneous | 2019-10-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24710-001025 | 24710 | 2019-10-07 12:29 | Section 4 | Material | Not on List | Not on List | 60 | Each | 10.7 | 642 | Small Tools (Consumables) | 2019-10-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 140 | no | 24.84 | 3477.6 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24516-001025 | 24516 | 2019-10-02 11:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 3.66 | 29.28 | Small Tools (Consumables) | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24787-001025 | 24787 | 2019-10-08 14:21 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | 5.92 | 30 | Concrete Accessories | 2019-10-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24787-001025 | 24787 | 2019-10-08 14:21 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Concrete Accessories | 2019-10-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24787-001025 | 24787 | 2019-10-08 14:21 | Section 2 | Material | PPE, Small Tools and Consumables | Brush Wire 4 Row Heavy Duty C/W Scraper Spartan Pro (504004) | 10 | Each | 0.86 | 9 | Concrete Accessories | 2019-10-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24636-001025 | 24636 | 2019-10-04 09:34 | Section 4 | Material | Not on List | Not on List | 200 | NULL | 0.2 | 40 | Surveying Consumables | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24247-001025 | 24247 | 2019-09-26 09:41 | Section 4 | Material | Not on List | Not on List | 1 | Number | 100 | 100 | Surveying Consumables | 2019-09-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24259-001025 | 24259 | 2019-09-26 12:04 | Section 4 | Material | Not on List | Not on List | 1 | Number | 252.2 | 252.2 | Surveying Consumables | 2019-09-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24280-001025 | 24280 | 2019-09-26 16:09 | Section 4 | Material | Not on List | Not on List | 2 | Number | 18 | 36 | Surveying Consumables | 2019-09-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 140 | no | 21.33 | 2986.2 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24707-001025 | 24707 | 2019-10-07 12:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 30.24 | 302.4 | Small Tools (Consumables) | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24796-001025 | 24796 | 2019-10-08 16:11 | Core | Material | Not on List | Not on List | 1 | No. | 381.65 | 382 | Miscellaneous | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-24706-001025 | 24706 | 2019-10-07 11:47 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | 21.3 | 639 | Miscellaneous | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24766-001025 | 24766 | 2019-10-08 10:16 | Section 4 | Material | NULL | NULL | 450 | Each | 4.59 | 2065.5 | Builders Merchants (General) | 2019-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24766-001025 | 24766 | 2019-10-08 10:16 | Section 4 | Material | NULL | NULL | 12 | Each | 5.44 | 65.28 | Builders Merchants (General) | 2019-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24766-001025 | 24766 | 2019-10-08 10:16 | Section 4 | Material | NULL | NULL | 12 | Each | 5.44 | 65.28 | Builders Merchants (General) | 2019-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5192-00118 | 5192 | 2018-08-16 08:39 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 140 | no | 6.1 | 854 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 140 | no | 6.26 | 876.4 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24380-001025 | 24380 | 2019-09-30 12:13 | Section 4 | Material | Not on List | Not on List | 1 | Each | 264.25 | 264.25 | Miscellaneous | 2019-09-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24647-001025 | 24647 | 2019-10-04 11:40 | Core | Material | NULL | NULL | 1 | Each | 505.71 | 505.71 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24654-001025 | 24654 | 2019-10-04 10:11 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24763-001025 | 24763 | 2019-10-08 09:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 7 | EAch | 53.6 | 375.2 | PPE | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24836-001025 | 24836 | 2019-10-09 11:33 | Section 2 | Material | Not on List | Not on List | 10 | ea | 35.15 | 351.5 | Damage Charges | 2019-10-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 250 | no | 22.62 | 5655 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23771-001025 | 23771 | 2019-09-17 08:59 | Core | Material | NULL | NULL | 1 | Each | 7944.71 | 7944.71 | Professional Services | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23771-001025 | 23771 | 2019-09-17 08:59 | Core | Material | NULL | NULL | 1 | Each | 6637.86 | 6637.86 | Professional Services | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23771-001025 | 23771 | 2019-09-17 08:59 | Core | Material | NULL | NULL | 1 | Each | 4710.44 | 4710.44 | Professional Services | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24864-001025 | 24864 | 2019-10-09 15:28 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24866-001025 | 24866 | 2019-10-09 15:54 | Section 6 | Material | Aggregate | Class 1A | 10000 | Tonnes | 4 | 40000 | Aggregate | 2019-10-11 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 604 - Deposition (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24891-001025 | 24891 | 2019-10-10 07:47 | Section 5 | Material | Not on List | Not on List | 4 | NULL | 950 | 3800 | Miscellaneous | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 500 | no | 0.9 | 450 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24891-001025 | 24891 | 2019-10-10 07:47 | Section 5 | Material | Not on List | Not on List | 5 | NULL | 718 | 3590 | Miscellaneous | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24251-001025 | 24251 | 2019-09-26 09:57 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24802-001025 | 24802 | 2019-10-08 16:25 | Section 6 | Material | Not on List | Not on List | 6 | Each | NULL | 0 | Miscellaneous | 2019-10-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24802-001025 | 24802 | 2019-10-08 16:25 | Section 6 | Material | Not on List | Not on List | 4 | Each | NULL | 0 | Miscellaneous | 2019-10-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24802-001025 | 24802 | 2019-10-08 16:25 | Section 6 | Material | Not on List | Not on List | 4 | Each | NULL | 0 | Miscellaneous | 2019-10-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24802-001025 | 24802 | 2019-10-08 16:25 | Section 6 | Material | Geotextile | Not on List | 1 | Roll (25m) | NULL | 0 | Geotextiles | 2019-10-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24764-001025 | 24764 | 2019-10-08 09:53 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1098.95 | Each | 1 | 1098.95 | Janitorial | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | No - Reject | REQ - Buyers
MREQ-24910-001025 | 24910 | 2019-10-10 10:53 | Core | Material | PPE, Small Tools and Consumables | Jalas E-Sport S3 Mid-Cut Safety Boot (120102) | 5 | Each | 39.99 | 200 | PPE | 2019-10-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24910-001025 | 24910 | 2019-10-10 10:53 | Core | Material | Not on List | Not on List | 1 | Each | 91.36 | 91 | Janitorial | 2019-10-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24910-001025 | 24910 | 2019-10-10 10:53 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1017.13 | 1017 | Small Tools (Consumables) | 2019-10-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24908-001025 | 24908 | 2019-10-10 10:40 | Section 5 | Material | Not on List | Not on List | 40 | EA | 6.5 | 260 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24821-001025 | 24821 | 2019-10-08 17:47 | Section 1 | Material | Not on List | Not on List | 1 | SM | 4349.78 | 4349.78 | Not Sure | 2019-10-14 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-24776-001025 | 24776 | 2019-10-08 12:27 | Core | Material | NULL | NULL | 1 | Each | 75 | 75 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24934-001025 | 24934 | 2019-10-10 16:39 | Section 4 | Material | Not on List | Not on List | 5 | Number | 60 | 300 | Surveying Consumables | 2019-10-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-24946-001025 | 24946 | 2019-10-10 18:08 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2176.86 | 2176.86 | Miscellaneous | 2019-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24980-001025 | 24980 | 2019-10-11 12:54 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 150 | EA | 7.5 | 1125 | Surveying Consumables | 2019-10-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18505-001025 | 18505 | 2019-06-04 10:34 | Section 2 | Material | Not on List | Not on List | 1 | each | 718 | 718 | Miscellaneous | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-18509-001025 | 18509 | 2019-06-04 10:37 | Section 3 | Material | Aggregate | 6C/6A1 | 60 | Tonnes | 22.2 | 1332 | Aggregate | 2019-06-06 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | CL3B - Structures (Culverts) 3B | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18580-001025 | 18580 | 2019-06-05 09:28 | Section 6 | Material | Not on List | Not on List | 1 | Set | NULL | 0 | Miscellaneous | 2019-06-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18580-001025 | 18580 | 2019-06-05 09:28 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-06-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18581-001025 | 18581 | 2019-06-05 10:13 | Core | Material | Not on List | Not on List | 1 | each | 850 | 850 | Training | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Gaffa Waterproof Cloth Grey 50mm X 50 Mtr Ref 3160 (964670) | 40 | Each | 1.91 | 76 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Paint Roller And Tray Set 9" Rskit1 (704256) | 20 | Each | 3.42 | 68 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Bucket Galvanised 2 1/2gall/11.42ltr 10"/30cm Dia Spartan (506016) | 20 | Each | 9 | 180 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Red (742163) | 20 | Each | 6.7 | 134 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Can Fuel 5ltr Heavy Duty Green Plastic Long Spout Unleaded (706686) | 5 | Each | 5.82 | 29 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-4993-006 | 4993 | 2018-08-13 14:56 | Section 4 | Material | Not on List | NULL | 1 | 25kg Box | 61.66 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Can Fuel 5ltr Heavy Duty Black Plastic Long Spout For Diesel (706684) | 5 | Each | 5.85 | 29 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18587-001025 | 18587 | 2019-06-05 10:52 | Section 5 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18529-001025 | 18529 | 2019-06-04 14:05 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 20 | Each | 8.55 | 171 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 20 | Each | 8.55 | 171 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 25 | Each | 8.55 | 214 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 20 | Each | 8.55 | 171 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml White (742159) | 45 | Each | 6.71 | 302 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Red (742163) | 25 | Each | 6.7 | 168 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Blue (742162) | 25 | Each | 6.66 | 167 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Yellow (742161) | 25 | Each | 6.71 | 168 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18575-001025 | 18575 | 2019-06-05 08:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-06-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18617-001025 | 18617 | 2019-06-05 16:33 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 55.99 | 112 | Office Supplies | 2019-06-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18630-001025 | 18630 | 2019-06-06 06:58 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-06-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18631-001025 | 18631 | 2019-06-06 07:16 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18637-001025 | 18637 | 2019-06-06 08:23 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-07 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | NULL | Not on List | 1 | bag | NULL | 0 | Fixings and Fasteners | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | NULL | Not on List | 5 | sheets | NULL | 0 | Timber Products | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | NULL | Not on List | 20 | meters | NULL | 0 | Timber Products | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 8 | units | NULL | 0 | Miscellaneous | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 3 | units | NULL | 0 | Miscellaneous | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 9 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 9 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 9 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 22 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 9 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 8 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 8 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 60 | meters | NULL | 0 | Miscellaneous | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 3 | bags | NULL | 0 | Ready Mixed Concrete | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18639-001025 | 18639 | 2019-06-06 08:34 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18649-001025 | 18649 | 2019-06-06 09:40 | Core | Material | Not on List | Not on List | 60 | NULL | 2.5 | 150 | Surveying Consumables | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18654-001025 | 18654 | 2019-06-06 10:43 | Section 4 | Material | Not on List | Not on List | 1 | Number | 5450 | 5450 | Surveying Consumables | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-18654-001025 | 18654 | 2019-06-06 10:43 | Section 4 | Material | Not on List | Not on List | 1 | Number | 290 | 290 | Surveying Consumables | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-18602-001025 | 18602 | 2019-06-05 14:13 | Section 4 | Material | NULL | NULL | 10 | Each | 37.54 | 375.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-06 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18544-001025 | 18544 | 2019-06-04 15:59 | Section 4 | Material | Not on List | Not on List | 100 | Hun | 838 | 83800 | Concrete Drainage | 2019-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18671-001025 | 18671 | 2019-06-06 11:43 | Section 5 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18512-001025 | 18512 | 2019-06-04 10:55 | Section 3 | Material | Aggregate | 6G | 150 | Tonnes | 32.9 | 4935 | Aggregate | 2019-06-10 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | CL3B - Structures (Culverts) 3B | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18220-001025 | 18220 | 2019-05-29 17:26 | Section 3 | Material | NULL | Not on List | 5 | ea | 164.37 | 821.85 | Plastic Drainage | 2019-05-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18220-001025 | 18220 | 2019-05-29 17:26 | Section 3 | Material | NULL | Polypipe 450mm Ridgidrain Seal (346396) | 6 | Each | 10.04 | 60.24 | Plastic Drainage | 2019-05-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18220-001025 | 18220 | 2019-05-29 17:26 | Section 3 | Material | NULL | Not on List | 6 | ea | 89.45 | 536.7 | Plastic Drainage | 2019-05-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18618-001025 | 18618 | 2019-06-05 16:34 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18688-001025 | 18688 | 2019-06-06 14:27 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18688-001025 | 18688 | 2019-06-06 14:27 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18688-001025 | 18688 | 2019-06-06 14:27 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18692-001025 | 18692 | 2019-06-06 15:26 | Core | Material | Not on List | Not on List | 1 | ea | 360 | 360 | Training | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18684-001025 | 18684 | 2019-06-06 14:14 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18694-001025 | 18694 | 2019-06-06 16:03 | Core | Material | Not on List | Not on List | 1 | NULL | 110 | 110 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18695-001025 | 18695 | 2019-06-06 16:05 | Section 3 | Material | Not on List | Not on List | 400 | NULL | 2.06 | 824 | Office Supplies | 2019-06-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-18274-001025 | 18274 | 2019-05-30 14:03 | Core | Material | Not on List | Not on List | 60 | number | 50 | 3000 | Miscellaneous | 2019-05-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18702-001025 | 18702 | 2019-06-06 12:22 | Core | Material | Not on List | Not on List | 1 | NULL | 698.45 | 698 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18702-001025 | 18702 | 2019-06-06 12:22 | Core | Material | Not on List | Not on List | 1 | NULL | 19.21 | 19 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18707-001025 | 18707 | 2019-06-06 17:39 | Section 4 | Material | Not on List | Not on List | 300 | Each | 7.5 | 2250 | Surveying Consumables | 2019-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18683-001025 | 18683 | 2019-06-06 14:09 | Section 4 | Material | Not on List | Not on List | 1 | Number | 5450 | 5450 | Surveying Consumables | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18683-001025 | 18683 | 2019-06-06 14:09 | Section 4 | Material | Not on List | Not on List | 1 | Number | 290 | 290 | Surveying Consumables | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17373-001025 | 17373 | 2019-05-14 13:03 | Core | Material | Not on List | Not on List | 150 | NULL | 0.14 | 21 | Office Supplies | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18576-001025 | 18576 | 2019-06-05 08:32 | Section 2 | Material | NULL | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 30 | Each | 81.73 | 2451.9 | Ductile Drainage | 2019-06-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18576-001025 | 18576 | 2019-06-05 08:32 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18576-001025 | 18576 | 2019-06-05 08:32 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18576-001025 | 18576 | 2019-06-05 08:32 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18719-001025 | 18719 | 2019-06-07 09:03 | Core | Material | Not on List | Not on List | 1 | number | 6577.75 | 6578 | Professional Services | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18638-001025 | 18638 | 2019-06-06 07:49 | Section 3 | Material | Not on List | Not on List | 2370 | No | 3.12 | 7394.4 | Builders Merchants (General) | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18638-001025 | 18638 | 2019-06-06 07:49 | Section 3 | Material | Not on List | Not on List | 2370 | No | 3.12 | 7394.4 | Builders Merchants (General) | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18657-001025 | 18657 | 2019-06-06 10:54 | Section 4 | Material | Not on List | Not on List | 3 | Number | 1295 | 3885 | Surveying Consumables | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18698-001025 | 18698 | 2019-06-06 16:39 | Section 3 | Material | NULL | Not on List | 26 | No | 7.52 | 195.52 | Builders Merchants (General) | 2019-06-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18523-001025 | 18523 | 2019-06-04 13:17 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 247.97 | 247.97 | Small Tools (Consumables) | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18727-001025 | 18727 | 2019-06-07 09:40 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | Surveying Consumables | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Ops Pass Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-18727-001025 | 18727 | 2019-06-07 09:40 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | Surveying Consumables | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Ops Pass Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-18727-001025 | 18727 | 2019-06-07 09:40 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | Surveying Consumables | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Ops Pass Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-18727-001025 | 18727 | 2019-06-07 09:40 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | Surveying Consumables | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Ops Pass Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-18524-001025 | 18524 | 2019-06-04 13:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 860.93 | 860.93 | Small Tools (Consumables) | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18689-001025 | 18689 | 2019-06-06 15:23 | Section 4 | Material | Not on List | Not on List | 16 | sheets | 54 | 864 | NULL | 2019-06-10 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18703-001025 | 18703 | 2019-06-06 17:09 | Section 4 | Material | Not on List | Not on List | 2 | packs | 217.7 | 435.4 | NULL | 2019-06-10 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18703-001025 | 18703 | 2019-06-06 17:09 | Section 4 | Material | Not on List | Not on List | 1 | packs | 149.8 | 149.8 | NULL | 2019-06-10 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18651-001025 | 18651 | 2019-06-06 10:07 | Section 3 | Material | Not on List | Not on List | 3 | ea | 36 | 108 | Small Tools (Consumables) | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18651-001025 | 18651 | 2019-06-06 10:07 | Section 3 | Material | Not on List | Not on List | 1 | ea | 126 | 126 | Small Tools (Consumables) | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18651-001025 | 18651 | 2019-06-06 10:07 | Section 3 | Material | NULL | Not on List | NULL | NULL | NULL | 0 | NULL | NULL | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18738-001025 | 18738 | 2019-06-07 10:50 | Core | Material | Not on List | Not on List | 1 | number | 223.65 | 224 | Miscellaneous | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18635-001025 | 18635 | 2019-06-06 07:51 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | Each | 2.97 | 332.64 | Builders Merchants (General) | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18697-001025 | 18697 | 2019-06-06 16:28 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18696-001025 | 18696 | 2019-06-06 16:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 218.8 | 218.8 | Small Tools (Consumables) | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18525-001025 | 18525 | 2019-06-04 13:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 668.5 | 668.5 | PPE | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18757-001025 | 18757 | 2019-06-07 11:55 | Core | Material | Not on List | Not on List | 4 | Number | 5.99 | 24 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17594-001025 | 17594 | 2019-05-17 10:21 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18101-001025 | 18101 | 2019-05-28 09:59 | Section 4 | Material | Not on List | Not on List | 1 | Number | 524.7 | 524.7 | Surveying Consumables | 2019-05-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18659-001025 | 18659 | 2019-06-06 11:11 | Section 4 | Material | Not on List | Not on List | 1 | each | 388.7 | 388.7 | Miscellaneous | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14132-001025 | 14132 | 2019-03-15 14:42 | Section 3 | Material | Not on List | Not on List | 10 | Each | 16.5 | 165 | Aggregate | 2019-03-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5811-00489 | 5811 | 2018-08-30 12:54 | Section 3 | Material | Not on List | Not on List | 4 | Packs | 116 | 464 | Builders Merchants (General) | 2018-09-03 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11593-001025 | 11593 | 2019-01-29 08:14 | Section 4 | Material | Not on List | Not on List | 13 | Each | 314.15 | 4083.95 | Concrete Drainage | 2019-03-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13544-001025 | 13544 | 2019-03-06 11:30 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 21.75 | 108.75 | Laboratory Equipment / Certification | 2019-03-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14201-001025 | 14201 | 2019-03-18 14:44 | Section 5 | Material | Not on List | Not on List | 100 | units | NULL | 0 | Builders Merchants (General) | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14201-001025 | 14201 | 2019-03-18 14:44 | Section 5 | Material | Not on List | Not on List | 1 | each | NULL | 0 | Builders Merchants (General) | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5723-00451 | 5723 | 2018-08-29 07:45 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 336.48 | 336.48 | Small Tools (Consumables) | 2018-08-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 4 | Each | 85.23 | 340.92 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 9 | Each | 63.93 | 575.37 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 2 | Each | 120.1 | 240.2 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 1 | Each | 106.93 | 106.93 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 2 | Each | 128.32 | 256.64 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 2 | Each | 294.58 | 589.16 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 1 | Each | 777.06 | 777.06 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13781-001025 | 13781 | 2019-03-11 14:07 | Core | Material | Not on List | Not on List | 4 | Each | 850 | 3400 | Training | 2019-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13783-001025 | 13783 | 2019-03-11 14:12 | Core | Material | Not on List | Not on List | 1 | Each | 1737.5 | 1737.5 | Training | 2019-04-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12865-001025 | 12865 | 2019-02-21 15:44 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 1597.71 | 1597.71 | Miscellaneous | 2019-02-22 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 107 - Insurance | Buyer - Closed | NULL | Yes - Approve | Req - S6 Buyers
MREQ-14082-001025 | 14082 | 2019-03-15 08:01 | Core | Material | Not on List | Not on List | 1 | ea | 1500 | 1500 | Training | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14169-001025 | 14169 | 2019-03-18 10:40 | Section 3 | Material | Not on List | Not on List | 1 | No | 175.45 | 175.45 | Professional Services | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14252-001025 | 14252 | 2019-03-19 09:05 | Section 3 | Material | Not on List | Not on List | 20 | Sheet | 12.81 | 256.2 | Concrete Accessories | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5721-00450 | 5721 | 2018-08-29 07:41 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 698.51 | 698.51 | Small Tools (Consumables) | 2018-08-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14252-001025 | 14252 | 2019-03-19 09:05 | Section 3 | Material | Not on List | Not on List | 20 | Sheet | 10.44 | 208.8 | Concrete Accessories | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14252-001025 | 14252 | 2019-03-19 09:05 | Section 3 | Material | Not on List | Not on List | 1 | Coil | 45.5 | 45.5 | Concrete Accessories | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14193-001025 | 14193 | 2019-03-18 13:47 | Section 3 | Material | Not on List | Not on List | 1 | ea | 400 | 400 | Miscellaneous | 2019-03-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14212-001025 | 14212 | 2019-03-18 16:03 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | 8.18 | 32.72 | Small Tools (Consumables) | 2019-03-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14251-001025 | 14251 | 2019-03-19 09:12 | Section 3 | Material | Not on List | Not on List | 2000 | No | 0.49 | 980 | Builders Merchants (General) | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14251-001025 | 14251 | 2019-03-19 09:12 | Section 3 | Material | Not on List | Not on List | 500 | No | 0.25 | 125 | Builders Merchants (General) | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14205-001025 | 14205 | 2019-03-18 15:20 | Section 5 | Material | Not on List | Not on List | 1000 | EACH | 0.31 | 310 | Builders Merchants (General) | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14268-001025 | 14268 | 2019-03-19 11:22 | Section 3 | Material | Aggregate | Not on List | 250000 | Tonne | 4 | 1000000 | Aggregate | 2019-03-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14250-001025 | 14250 | 2019-03-19 09:05 | Section 3 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 6 | Each | 165.1 | 990.6 | Concrete Drainage | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14250-001025 | 14250 | 2019-03-19 09:05 | Section 3 | Material | Concrete Drainage | CPM 750mm Concrete Socket (890395) | 2 | Each | 198.12 | 396.24 | Concrete Drainage | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5827-00516 | 5827 | 2018-08-30 16:49 | Section 3 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Office Supplies | 2018-08-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14250-001025 | 14250 | 2019-03-19 09:05 | Section 3 | Material | Concrete Drainage | CPM 750mm Concrete Spigot (890374) | 2 | Each | 198.12 | 396.24 | Concrete Drainage | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14235-001025 | 14235 | 2019-03-18 19:19 | Section 3 | Material | Not on List | Not on List | 2.821 | tonne | 538 | 1517.7 | Rebar and Mesh | 2019-04-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14261-001025 | 14261 | 2019-03-19 11:05 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Pack 24 | 6.29 | 905.76 | Small Tools (Consumables) | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14330-001025 | 14330 | 2019-03-20 07:10 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 3 | number | NULL | 0 | PPE | 2019-03-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2302 - Sealing of gaps | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-14330-001025 | 14330 | 2019-03-20 07:10 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 3 | number | NULL | 0 | PPE | 2019-03-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2302 - Sealing of gaps | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-14334-001025 | 14334 | 2019-03-20 07:24 | Section 2 | Material | Bagged | OP Cement; 25kg bag (767201) | 40 | Each | 2.9 | 116 | Builders Merchants (General) | 2019-03-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2401 - Brickwork, Blockwork and Stonework | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14334-001025 | 14334 | 2019-03-20 07:24 | Section 2 | Material | Bagged | Not on List | 10 | each | NULL | 0 | Builders Merchants (General) | 2019-03-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2401 - Brickwork, Blockwork and Stonework | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14334-001025 | 14334 | 2019-03-20 07:24 | Section 2 | Material | Not on List | Not on List | 62 | each | NULL | 0 | Concrete Accessories | 2019-03-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2401 - Brickwork, Blockwork and Stonework | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14084-001025 | 14084 | 2019-03-15 08:28 | Core | Material | Not on List | Not on List | 1 | ea | 1023 | 1023 | Training | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13754-001025 | 13754 | 2019-03-11 10:07 | Core | Material | Not on List | Not on List | 2 | Number | 500 | 1000 | Surveying Consumables | 2019-04-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14360-001025 | 14360 | 2019-03-20 09:57 | Section 2 | Material | Not on List | Not on List | 30 | number | NULL | 0 | Reinforcement | 2019-03-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Municipal Waste - Wheelie Bin 1100 Litre | 150 | Each | 14.25 | 2137.5 | Waste (General) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Wood - Roll On Roll Off 20 cubic yard | 30 | Each | 250 | 7500 | Waste (Recycling) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Plastic - Roll On Roll Off 40 cubic yard | 30 | Each | 360 | 10800 | Waste (General) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 30 | Each | 95 | 2850 | Waste (General) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 30 | Each | 370 | 11100 | Waste (General) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Dry Mixed Recycling - Wheelie Bin 1100 Litre | 125 | Each | 7 | 875 | Waste (General) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14366-001025 | 14366 | 2019-03-20 11:03 | Section 2 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Surveying Consumables | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-14368-001025 | 14368 | 2019-03-20 11:33 | Section 5 | Material | Not on List | Not on List | 30 | LTRS | NULL | 0 | Miscellaneous | 2019-03-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14369-001025 | 14369 | 2019-03-20 11:39 | Section 5 | Material | Not on List | Not on List | 4 | each | NULL | 0 | Builders Merchants (General) | 2019-03-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14372-001025 | 14372 | 2019-03-20 11:57 | Core | Material | Not on List | Not on List | 1 | NULL | 372.38 | 372 | Miscellaneous | 2019-03-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Operations Rejected | No - Reject | NULL | REQ - Buyers
MREQ-14367-001025 | 14367 | 2019-03-20 11:02 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 22550 | 22550 | Miscellaneous | 2019-03-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5128-0052 | 5128 | 2018-08-15 10:09 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Electrical | 2018-08-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-14308-001025 | 14308 | 2019-03-19 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | 1.99 | 79.6 | Small Tools (Consumables) | 2019-03-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14296-001025 | 14296 | 2019-03-19 15:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | 3.88 | 194 | Small Tools (Consumables) | 2019-03-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14296-001025 | 14296 | 2019-03-19 15:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | 3.13 | 313 | PPE | 2019-03-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14057-001025 | 14057 | 2019-03-14 16:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 10.8 | 108 | Office Supplies | 2019-03-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13656-001025 | 13656 | 2019-03-08 11:36 | Core | Material | Not on List | Not on List | 5 | Boxes | 10 | 50 | Surveying Consumables | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13656-001025 | 13656 | 2019-03-08 11:36 | Core | Material | Not on List | Not on List | 1 | number | 81 | 81 | Surveying Consumables | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13996-001025 | 13996 | 2019-03-14 08:14 | Core | Material | Not on List | Not on List | 3 | No. | 500 | 1500 | Surveying Consumables | 2019-03-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13996-001025 | 13996 | 2019-03-14 08:14 | Core | Material | Not on List | Not on List | 1 | No. | 165 | 165 | Surveying Consumables | 2019-03-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13996-001025 | 13996 | 2019-03-14 08:14 | Core | Material | Not on List | Not on List | 3 | boxes | 40 | 120 | Surveying Consumables | 2019-03-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13537-001025 | 13537 | 2019-03-06 11:05 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-14297-001025 | 14297 | 2019-03-19 15:43 | Section 4 | Material | Not on List | Not on List | 2 | Each | 13 | 26 | Concrete Drainage | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14297-001025 | 14297 | 2019-03-19 15:43 | Section 4 | Material | Not on List | Not on List | 2 | Each | 38.47 | 76.94 | Concrete Drainage | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14297-001025 | 14297 | 2019-03-19 15:43 | Section 4 | Material | Not on List | Not on List | 1 | Each | 242.19 | 242.19 | Concrete Drainage | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14297-001025 | 14297 | 2019-03-19 15:43 | Section 4 | Material | Not on List | Not on List | 1 | Each | 247.12 | 247.12 | Concrete Drainage | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14354-001025 | 14354 | 2019-03-20 09:36 | Section 3 | Material | Not on List | Not on List | 20 | tonne | 538 | 10760 | NULL | 2019-04-10 | RVP 419 (S3) - 1340880 - A14 Westbound (West of Junction 28) | BN16 - New Barns Lane Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14364-001025 | 14364 | 2019-03-20 10:40 | Section 4 | Material | Not on List | Not on List | 500 | Each | 2.18 | 1090 | Miscellaneous | 2019-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14364-001025 | 14364 | 2019-03-20 10:40 | Section 4 | Material | Not on List | Not on List | 500 | Each | 3.38 | 1690 | Miscellaneous | 2019-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14348-001025 | 14348 | 2019-03-20 09:12 | Section 3 | Material | Not on List | Not on List | 126 | NULL | 2.5 | 315 | Miscellaneous | 2019-03-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14266-001025 | 14266 | 2019-03-19 11:17 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 320.54 | 320.54 | Small Tools (Consumables) | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14392-001025 | 14392 | 2019-03-20 15:59 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 10 | Each | 33.35 | 333.5 | Builders Merchants (General) | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 10 | Each | 179.94 | 1799.4 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 40 | Each | 38.36 | 1534.4 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 120 | Each | 22.36 | 2683.2 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 25 | Each | 26.8 | 670 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 100 | Each | 3.65 | 365 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 250 | Each | 2 | 500 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 10 | Each | 37.6 | 376 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 50 | Each | 7.06 | 353 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 120 | Each | 2.97 | 356.4 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14329-001025 | 14329 | 2019-03-20 07:15 | Section 4 | Material | Not on List | Not on List | 8 | Each | 15.52 | 124.16 | Rebar and Mesh | 2019-03-22 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14329-001025 | 14329 | 2019-03-20 07:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 30 | 30 | Rebar and Mesh | 2019-03-22 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14329-001025 | 14329 | 2019-03-20 07:15 | Section 4 | Material | NULL | Not on List | 20 | Each | 7.82 | 156.4 | Rebar and Mesh | 2019-03-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14387-001025 | 14387 | 2019-03-20 15:25 | Section 3 | Material | Not on List | Not on List | 1 | Unit | 30000 | 30000 | Concrete Accessories | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14414-001025 | 14414 | 2019-03-21 07:31 | Section 2 | Material | Not on List | Not on List | 40 | m2 | NULL | 0 | Concrete Accessories | 2019-03-24 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5831-00524 | 5831 | 2018-08-30 19:04 | Section 4 | Material | Not on List | Not on List | 14 | 500Litres | 16.55 | 232 | Builders Merchants (General) | 2018-08-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14439-001025 | 14439 | 2019-03-21 09:41 | Section 6 | Material | Timber | Not on List | 200 | number | NULL | 0 | Surveying Consumables | 2019-03-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-14424-001025 | 14424 | 2019-03-21 08:28 | Section 3 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Unproofed 31" X 13" 7.5oz (746642) | 2000 | Each | 0.31 | 620 | Builders Merchants (General) | 2019-03-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5831-00524 | 5831 | 2018-08-30 19:04 | Section 4 | Material | Not on List | Not on List | 4 | Number | NULL | 0 | Builders Merchants (General) | 2018-08-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14109-001025 | 14109 | 2019-03-15 12:00 | Section 4 | Material | Not on List | Not on List | 56 | Each | 10.85 | 607.6 | Builders Merchants (General) | 2019-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14109-001025 | 14109 | 2019-03-15 12:00 | Section 4 | Material | Not on List | Not on List | 112 | Each | 10.85 | 1215.2 | Builders Merchants (General) | 2019-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14109-001025 | 14109 | 2019-03-15 12:00 | Section 4 | Material | Not on List | Not on List | 4 | Each | 0.65 | 2.6 | Builders Merchants (General) | 2019-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14109-001025 | 14109 | 2019-03-15 12:00 | Section 4 | Material | Not on List | Not on List | 3 | Each | 11.9 | 35.7 | Builders Merchants (General) | 2019-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4C - Structures (Culverts) 4C | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14359-001025 | 14359 | 2019-03-20 10:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 100 | NULL | 28.8 | 2880 | PPE | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14359-001025 | 14359 | 2019-03-20 10:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 16 | NULL | 28.8 | 460.8 | PPE | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14380-001025 | 14380 | 2019-03-20 14:35 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 15 | 90 | Miscellaneous | 2019-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13964-001025 | 13964 | 2019-03-13 16:07 | Section 4 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13773-001025 | 13773 | 2019-03-11 12:17 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 6215 | 6215 | Miscellaneous | 2019-03-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13233-001025 | 13233 | 2019-02-28 11:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 27 | 27 | Small Tools (Consumables) | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 105 - Site Security | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13233-001025 | 13233 | 2019-02-28 11:07 | Section 4 | Material | NULL | Not on List | 2 | Each | 28.9 | 57.8 | Small Tools (Consumables) | 2019-03-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 105 - Site Security | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14455-001025 | 14455 | 2019-03-21 13:53 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Surveying Consumables | 2019-03-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13243-001025 | 13243 | 2019-02-28 12:00 | Core | Material | Not on List | Not on List | 1 | NULL | 93.47 | 90 | Miscellaneous | 2019-03-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14440-001025 | 14440 | 2019-03-21 09:14 | Section 3 | Material | Not on List | Not on List | 4 | Packs | 27.73 | 110.92 | Rebar and Mesh | 2019-04-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14440-001025 | 14440 | 2019-03-21 09:14 | Section 3 | Material | Not on List | Not on List | 150 | each | 0.55 | 82.5 | Concrete Accessories | 2019-04-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14440-001025 | 14440 | 2019-03-21 09:14 | Section 3 | Material | NULL | Not on List | 1 | Bag | 7.6 | 7.6 | Concrete Accessories | 2019-03-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14440-001025 | 14440 | 2019-03-21 09:14 | Section 3 | Material | Not on List | Not on List | 1 | (10 Sheets) | 109.4 | 109.4 | Miscellaneous | 2019-04-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14480-001025 | 14480 | 2019-03-21 16:00 | Section 2 | Material | NULL | Not on List | 20 | number | 188 | 3760 | Geotextiles | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14480-001025 | 14480 | 2019-03-21 16:00 | Section 2 | Material | NULL | Not on List | 6 | number | 181 | 1086 | Geotextiles | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14480-001025 | 14480 | 2019-03-21 16:00 | Section 2 | Material | NULL | Not on List | 19 | number | 177 | 3363 | Geotextiles | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14480-001025 | 14480 | 2019-03-21 16:00 | Section 2 | Material | NULL | Not on List | 1 | no | 650 | 650 | NULL | NULL | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14510-001025 | 14510 | 2019-03-22 09:46 | Section 3 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Concrete Accessories | 2019-03-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN16 - New Barns Lane Overbridge | 1701 - Insitu Concrete | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 3 Buyers
MREQ-14500-001025 | 14500 | 2019-03-21 18:24 | Section 3 | Material | Not on List | Not on List | 36 | Tubes | 11.08 | 398.88 | Concrete Accessories | 2019-03-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14500-001025 | 14500 | 2019-03-21 18:24 | Section 3 | Material | Not on List | Not on List | 200 | 600ml Foil packs | 4.97 | 994 | Concrete Accessories | 2019-03-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN16 - New Barns Lane Overbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14209-001025 | 14209 | 2019-03-18 15:51 | Core | Material | Not on List | Not on List | 1 | number | 4212.44 | 4212.44 | Miscellaneous | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14381-001025 | 14381 | 2019-03-20 14:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 638.69 | 638.69 | Laboratory Equipment / Certification | 2019-03-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14204-001025 | 14204 | 2019-03-18 15:14 | Core | Material | Not on List | Not on List | 1 | ea | 250 | 250 | Miscellaneous | 2019-01-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14376-001025 | 14376 | 2019-03-20 13:11 | Core | Material | Not on List | Not on List | 1 | ea | 13289.52 | 13289.52 | Office Supplies | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14362-001025 | 14362 | 2019-03-20 10:44 | Core | Material | Not on List | Not on List | 500 | NULL | 0.67 | 335 | Office Supplies | 2019-03-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14351-001025 | 14351 | 2019-03-20 09:32 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 205.2 | 205.2 | Laboratory Equipment / Certification | 2019-03-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14531-001025 | 14531 | 2019-03-22 13:27 | Section 5 | Material | Not on List | Not on List | 300 | number | NULL | 0 | Builders Merchants (General) | 2019-03-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20395-001025 | 20395 | 2019-07-08 12:07 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20407-001025 | 20407 | 2019-07-08 14:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20407-001025 | 20407 | 2019-07-08 14:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5249-00162 | 5249 | 2018-08-16 16:33 | Section 4 | Material | Plastic Drainage | NULL | 100 | Each | 5.95 | 595 | Plastic Drainage | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20006-001025 | 20006 | 2019-07-01 13:06 | Section 4 | Material | NULL | NULL | 4 | Each | 93.97 | 375.88 | Plastic Drainage | 2019-07-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20006-001025 | 20006 | 2019-07-01 13:06 | Section 4 | Material | NULL | NULL | 1 | Each | 115 | 115 | Plastic Drainage | 2019-07-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20413-001025 | 20413 | 2019-07-08 16:01 | Core | Material | Not on List | Not on List | 7 | NULL | 5.25 | 37 | Office Supplies | 2019-07-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20413-001025 | 20413 | 2019-07-08 16:01 | Core | Material | Not on List | Not on List | 2 | NULL | 5.75 | 12 | Office Supplies | 2019-07-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20413-001025 | 20413 | 2019-07-08 16:01 | Core | Material | Not on List | Not on List | 1 | NULL | 4.95 | 5 | Miscellaneous | 2019-07-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5250-00168 | 5250 | 2018-08-16 17:00 | Section 4 | Material | Concrete Drainage | Cpm 1500X1000 C/W Steps | 5 | Each | 121.25 | 606.25 | Concrete Drainage | 2018-08-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20295-001025 | 20295 | 2019-07-05 13:05 | Section 5 | Material | Timber | NULL | 35 | No | 27.94 | 977.9 | NULL | 2019-07-09 | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5250-00168 | 5250 | 2018-08-16 17:00 | Section 4 | Material | Concrete Drainage | 1500Mm Dia Chamber Ring (R) Opc | 5 | m | 90.94 | 454.7 | Concrete Drainage | 2018-08-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20460-001025 | 20460 | 2019-07-09 10:05 | Core | Material | Not on List | Not on List | 1 | ea | 360 | 360 | Office Supplies | 2019-07-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20462-001025 | 20462 | 2019-07-09 10:10 | Core | Material | Not on List | Not on List | 6 | ea | 180 | 1080 | Office Supplies | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5250-00168 | 5250 | 2018-08-16 17:00 | Section 4 | Material | Concrete Drainage | 1500Mm Dia Chamber Ring (R) Opc | 5 | m | 80.51 | 402.55 | Concrete Drainage | 2018-08-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20390-001025 | 20390 | 2019-07-08 11:26 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 695 | 695 | Miscellaneous | 2019-07-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20084-001025 | 20084 | 2019-07-02 11:13 | Section 3 | Material | Kerbs | NULL | 45 | Each | 3.52 | 158.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20084-001025 | 20084 | 2019-07-02 11:13 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 32 | Each | 6 | 192 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20084-001025 | 20084 | 2019-07-02 11:13 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 48 | Each | 5.43 | 260.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20084-001025 | 20084 | 2019-07-02 11:13 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | NULL | Each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20084-001025 | 20084 | 2019-07-02 11:13 | Section 3 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 10 | Each | 125.94 | 1259.4 | Plastic Drainage | 2019-07-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19758-001025 | 19758 | 2019-06-26 12:08 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 152.9 | 152.9 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5250-00168 | 5250 | 2018-08-16 17:00 | Section 4 | Material | Concrete Drainage | 1500Mm Dia Cover Slab Opc | 5 | Each | 142.82 | 714.1 | Concrete Drainage | 2018-08-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20502-001025 | 20502 | 2019-07-09 16:10 | Core | Material | Not on List | Not on List | 4 | Packs | 18 | 72 | Miscellaneous | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20502-001025 | 20502 | 2019-07-09 16:10 | Core | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20473-001025 | 20473 | 2019-07-09 11:41 | Core | Material | NULL | NULL | 2 | Each | 18 | 36 | NULL | NULL | NULL | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20443-001025 | 20443 | 2019-07-09 08:38 | Section 4 | Material | NULL | NULL | 1 | Each | 301.79 | 301.79 | NULL | NULL | NULL | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5276-00175 | 5276 | 2018-08-17 09:10 | Section 4 | Material | Plastic Drainage | P/Pipe 600Mm Ridgidrain Seal | 12 | Each | 26.1 | 313.2 | Plastic Drainage | 2018-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17457-001025 | 17457 | 2019-05-15 12:57 | Section 3 | Material | Not on List | Not on List | 1 | ea | 105.15 | 105.15 | Miscellaneous | 2019-05-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20476-001025 | 20476 | 2019-07-09 12:27 | Section 4 | Material | NULL | NULL | 1 | Each | 966.87 | 966.87 | NULL | NULL | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20303-001025 | 20303 | 2019-07-05 13:46 | Section 4 | Material | Not on List | Not on List | 16 | EA | 47.89 | 766.24 | Miscellaneous | 2019-07-11 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5276-00175 | 5276 | 2018-08-17 09:10 | Section 4 | Material | Not on List | NULL | 12 | Each | 292.07 | 3504.84 | Plastic Drainage | 2018-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20304-001025 | 20304 | 2019-07-05 13:52 | Section 4 | Material | Not on List | Not on List | 10 | EA | 54 | 540 | Rebar and Mesh | 2019-07-11 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20525-001025 | 20525 | 2019-07-10 08:02 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-07-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5294-00226 | 5294 | 2018-08-17 13:26 | Section 4 | Material | Misc | Not on List | 3 | Tonne | 538 | 1614 | Rebar and Mesh | 2018-08-30 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19641-001025 | 19641 | 2019-06-24 23:35 | Section 4 | Material | Not on List | Not on List | 1 | Number | 3892 | 3892 | Surveying Consumables | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19754-001025 | 19754 | 2019-06-26 11:50 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2314.83 | 2314.83 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19581-001025 | 19581 | 2019-06-24 08:25 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-07-10 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-19740-001025 | 19740 | 2019-06-26 09:39 | Section 1 | Material | Twinwall | Not on List | 3 | NULL | NULL | 0 | Concrete Accessories | 2019-07-01 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-20519-001025 | 20519 | 2019-07-09 19:25 | Section 2 | Material | Not on List | Not on List | 1 | Quotation | 26106.97 | 26106.97 | Miscellaneous | 2019-07-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20520-001025 | 20520 | 2019-07-09 19:32 | Section 2 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 10 | Each | 6.82 | 68.2 | Timber Products | 2019-07-12 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20520-001025 | 20520 | 2019-07-09 19:32 | Section 2 | Material | Not on List | Not on List | 3 | roll | NULL | 0 | Timber Products | 2019-07-12 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20520-001025 | 20520 | 2019-07-09 19:32 | Section 2 | Material | Not on List | Not on List | 2 | roll | NULL | 0 | Timber Products | 2019-07-12 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5142-0070 | 5142 | 2018-08-15 11:34 | Section 3 | Material | Concrete Drainage | Not on List | 3 | Each | 43.16 | 129.48 | Concrete Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5321-00227 | 5321 | 2018-08-20 08:16 | Section 4 | Material | Not on List | NULL | 2 | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20520-001025 | 20520 | 2019-07-09 19:32 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Timber Products | 2019-07-12 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20341-001025 | 20341 | 2019-07-06 15:32 | Section 6 | Material | Ducting | Not on List | 60 | M [= 10x6m lengths] | 0 | 0 | Miscellaneous | 2019-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20533-001025 | 20533 | 2019-07-10 09:12 | Section 3 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 12 | Each | 125.94 | 1511.28 | Plastic Drainage | 2019-07-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20484-001025 | 20484 | 2019-07-09 13:50 | Section 3 | Material | Aggregate | 6G | 160 | Tonnes | 32.9 | 5264 | Aggregate | 2019-07-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20227-001025 | 20227 | 2019-07-04 12:56 | Section 4 | Material | Not on List | Not on List | 50 | Each | 43.39 | 2169.5 | Miscellaneous | 2019-07-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20227-001025 | 20227 | 2019-07-04 12:56 | Section 4 | Material | NULL | Not on List | 1 | Each | 550 | 550 | Miscellaneous | 2019-07-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20475-001025 | 20475 | 2019-07-09 12:04 | Section 3 | Material | Not on List | Not on List | 30 | Roll | 26.25 | 787.5 | Geotextiles | 2019-07-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20441-001025 | 20441 | 2019-07-09 08:07 | Section 4 | Material | NULL | NULL | 400 | Each | 3.52 | 1408 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5323 | 5323 | 2018-08-20 08:32 | Section 4 | Material | Not on List | NULL | 2 | NULL | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20441-001025 | 20441 | 2019-07-09 08:07 | Section 4 | Material | NULL | NULL | 1 | Each | 41.8 | 41.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20441-001025 | 20441 | 2019-07-09 08:07 | Section 4 | Material | NULL | NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20529-001025 | 20529 | 2019-07-10 08:08 | Section 3 | Material | Twinwall | Not on List | 1 | ea | 167.88 | 167.88 | Plastic Drainage | 2019-07-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20529-001025 | 20529 | 2019-07-10 08:08 | Section 3 | Material | Twinwall | Not on List | 1 | ea | 199.68 | 199.68 | Plastic Drainage | 2019-07-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20556-001025 | 20556 | 2019-07-10 14:07 | Section 6 | Material | Not on List | Not on List | 1 | EACH | 166.25 | 166 | Miscellaneous | 2019-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20558-001025 | 20558 | 2019-07-10 14:08 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2401.75 | 2402 | Miscellaneous | 2019-07-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20559-001025 | 20559 | 2019-07-10 14:12 | Section 1 | Material | Not on List | Not on List | 1 | each | 398.75 | 399 | Miscellaneous | 2019-07-10 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-20560-001025 | 20560 | 2019-07-10 14:14 | Section 5 | Material | Not on List | Not on List | 1 | each | 162.5 | 163 | Miscellaneous | 2019-07-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5324 | 5324 | 2018-08-20 08:36 | Section 4 | Material | Not on List | NULL | NULL | NULL | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20562-001025 | 20562 | 2019-07-10 14:18 | Section 2 | Material | Not on List | Not on List | 1 | each | 3310.75 | 3311 | Miscellaneous | 2019-07-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20563-001025 | 20563 | 2019-07-10 14:06 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20563-001025 | 20563 | 2019-07-10 14:06 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20563-001025 | 20563 | 2019-07-10 14:06 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20563-001025 | 20563 | 2019-07-10 14:06 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20453-001025 | 20453 | 2019-07-09 09:12 | Section 4 | Material | Not on List | Not on List | 2 | Number | 350 | 700 | Surveying Consumables | 2019-07-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20545-001025 | 20545 | 2019-07-10 11:24 | Section 6 | Material | Aggregate | Class 1A | 2000 | Tonnes | 12.5 | 25000 | Aggregate | 2019-07-11 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5377-00248 | 5377 | 2018-08-20 16:25 | Section 4 | Material | Not on List | Not on List | 150 | Each | NULL | 0 | Miscellaneous | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20576-001025 | 20576 | 2019-07-10 16:23 | Section 4 | Material | Not on List | Not on List | 1 | Test | NULL | 0 | Miscellaneous | 2019-07-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20457-001025 | 20457 | 2019-07-09 09:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 139.16 | 139.16 | Miscellaneous | 2019-07-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20457-001025 | 20457 | 2019-07-09 09:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 162.63 | 162.63 | Miscellaneous | 2019-07-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20577-001025 | 20577 | 2019-07-10 16:37 | Section 4 | Material | Combined Drainage | 835 Quicklock Grating (163148) | 1 | Each | 6.94 | 7 | Aggregate | 2019-07-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-5377-00248 | 5377 | 2018-08-20 16:25 | Section 4 | Material | Not on List | Not on List | 26 | Each | NULL | 0 | Miscellaneous | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20599-001025 | 20599 | 2019-07-11 08:28 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-07-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20602-001025 | 20602 | 2019-07-11 09:06 | Core | Material | Not on List | Not on List | 1 | number | 120 | 120 | Office Supplies | 2019-07-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19976-001025 | 19976 | 2019-07-01 08:15 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20603-001025 | 20603 | 2019-07-11 08:57 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-07-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 103 - Staff | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 150 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20222-001025 | 20222 | 2019-07-04 12:25 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 257.49 | 257 | Miscellaneous | 2019-07-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 150 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5377-00248 | 5377 | 2018-08-20 16:25 | Section 4 | Material | NULL | NULL | 2 | Each | NULL | 0 | Miscellaneous | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 150 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 8635 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 8635 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 8635 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 45 | m | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 2590 | m | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 6035 | m2 | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 20 | m2 | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 527 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 527 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5377-00248 | 5377 | 2018-08-20 16:25 | Section 4 | Material | NULL | NULL | 2 | Each | NULL | 0 | Miscellaneous | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19597-001025 | 19597 | 2019-06-24 10:22 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20606-001025 | 20606 | 2019-07-11 10:24 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-12 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20572-001025 | 20572 | 2019-07-10 15:31 | Section 4 | Material | Aggregate | Class 6F | 270 | load | 95 | 25650 | Aggregate | 2019-07-15 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Not on List | Not on List | 450 | Load | 75 | 33750 | Miscellaneous | 2019-07-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Not on List | Not on List | 450 | Load | 75 | 33750 | Miscellaneous | 2019-07-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Not on List | Not on List | 450 | Load | 100 | 45000 | Miscellaneous | 2019-07-15 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | SC4C - Roadworks - Dry Drayton to Girton | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Not on List | Not on List | 1000 | Load | 95 | 95000 | Miscellaneous | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 602 - Excavation (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Not on List | Not on List | 500 | Load | 85 | 42500 | Miscellaneous | 2019-07-08 | RVP 403 - 1339621 - Borrow Pit 5 A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | NULL | Not on List | 500 | Load | 85 | 42500 | Miscellaneous | 2019-07-01 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Aggregate | Class 6F | 270 | Tonnes | 95 | 25650 | Miscellaneous | 2019-07-15 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5377-00248 | 5377 | 2018-08-20 16:25 | Section 4 | Material | NULL | NULL | 2 | Each | NULL | 0 | Miscellaneous | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20609-001025 | 20609 | 2019-07-11 11:15 | Section 4 | Material | Not on List | Not on List | 2 | each | NULL | 0 | Small Tools (Consumables) | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1502 - Trenches, Ducts and Chambers | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20283-001025 | 20283 | 2019-07-05 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 542 | 542 | Miscellaneous | 2019-07-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19428-001025 | 19428 | 2019-06-20 10:34 | Section 3 | Material | Not on List | Not on List | 56 | bags | 6.5 | 364 | Builders Merchants (General) | 2019-06-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 688 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 688 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 688 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 1691 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 1691 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 1691 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | 4 | Tonne | 538 | 2152 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20622-001025 | 20622 | 2019-07-11 14:01 | Section 4 | Material | Not on List | Not on List | 1 | EACH | NULL | 0 | Surveying Consumables | 2019-07-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 82 | EA | 29.95 | 2455.9 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | NULL | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 1 | EA | 29.5 | 29.5 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | NULL | 0 | Not Sure | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | NULL | 0 | Not Sure | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | NULL | 0 | Not Sure | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 16 | number | NULL | 0 | Not Sure | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | 3.91 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9933-001025 | 9933 | 2018-12-04 08:30 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 15 | Each | 47.04 | 706 | Concrete Drainage | 2018-12-07 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9933-001025 | 9933 | 2018-12-04 08:30 | Section 4 | Material | Concrete Drainage | Not on List | 15 | NULL | NULL | 0 | Concrete Drainage | 2018-12-07 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9945-001025 | 9945 | 2018-12-04 10:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-12-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9868-001025 | 9868 | 2018-12-03 08:52 | Section 4 | Material | Not on List | Not on List | 10 | 50m Length | 145 | 1450 | Not Sure | 2018-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9868-001025 | 9868 | 2018-12-03 08:52 | Section 4 | Material | Not on List | Not on List | 20 | Each | 1.24 | 24.8 | Not Sure | 2018-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9868-001025 | 9868 | 2018-12-03 08:52 | Section 4 | Material | NULL | Not on List | 20 | Each | 1.09 | 21.8 | Not Sure | 2018-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9957-001025 | 9957 | 2018-12-04 15:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-12-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 2 | Box of 50 | 45.05 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9963-001025 | 9963 | 2018-12-04 16:07 | Section 3 | Material | Not on List | Not on List | 350 | 25kg Bags | NULL | 0 | Builders Merchants (General) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9966-001025 | 9966 | 2018-12-04 16:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-12-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 70 | Each | 26.09 | 1826.3 | Plastic Drainage | 2018-12-06 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 100 | Each | 1.44 | 144 | Plastic Drainage | 2018-12-06 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 100 | Each | 2.92 | 292 | Plastic Drainage | 2018-12-06 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | NULL | NULL | 2 | Each | 376.56 | 753.12 | Plastic Drainage | 2018-12-06 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9951-001025 | 9951 | 2018-12-04 11:34 | Section 4 | Material | Not on List | Not on List | 1 | each | 232.83 | 232.83 | Miscellaneous | 2018-12-06 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5397-00263 | 5397 | 2018-08-21 08:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9945-001025 | 9945 | 2018-12-04 10:22 | Section 3 | Material | Not on List | Not on List | 1 | ea | 1877.34 | 1877.34 | Damage Charges | 2018-12-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 507.3 | 507.3 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1043.68 | 1043.68 | Small Tools (Consumables) | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 156.32 | 156.32 | Janitorial | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9980-001025 | 9980 | 2018-12-05 10:14 | Section 4 | Material | Aggregate | 6F5 | 500 | Tonnes | 14.65 | 7325 | Aggregate | 2018-12-14 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9980-001025 | 9980 | 2018-12-05 10:14 | Section 4 | Material | Aggregate | 6F5 | 500 | Tonnes | 14.65 | 7325 | Aggregate | 2018-12-17 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9990-001025 | 9990 | 2018-12-05 12:27 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-12-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-9991-001025 | 9991 | 2018-12-05 12:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Timber Products | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9994-001025 | 9994 | 2018-12-05 13:06 | Section 4 | Material | Not on List | Not on List | 1 | Comission | 600 | 600 | Not Sure | 2018-12-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 122 | NULL | 60 | 7320 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 65 | 130 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 4 | NULL | 700 | 2800 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 36 | Tubes | NULL | 0 | Ductile Drainage | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Channle 1000mm (758898) | 100 | Each | 29.28 | 2928 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Channel 500mm (758908) | 20 | Each | 15.43 | 309 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Access Unit (947299) | 7 | Each | 30.32 | 212 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Dropper RH (758907) | 1 | Each | 27.56 | 28 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Dropper LH (758901) | 1 | Each | 27.56 | 28 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Inlet (947299) | 7 | Each | 7.59 | 53 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9997-001025 | 9997 | 2018-12-05 13:55 | Section 4 | Material | Not on List | Not on List | 1 | Annual Subsistence Charge | 1580 | 1580 | Not Sure | 2018-12-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | 6.05 | 121 | Not Sure | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | 13.92 | 278.4 | Not Sure | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | 5.9 | 118 | Not Sure | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | 9.6 | 192 | Not Sure | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 16 | number | 23.15 | 370.4 | Not Sure | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10003-001025 | 10003 | 2018-12-05 14:25 | Section 3 | Material | Not on List | Not on List | 8 | EA | 25.48 | 204 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10003-001025 | 10003 | 2018-12-05 14:25 | Section 3 | Material | Not on List | Not on List | 12 | EA | 31.41 | 377 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10007-001025 | 10007 | 2018-12-05 13:50 | Section 3 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 6 | Each | 115.78 | 695 | Geotextiles | 2018-12-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10007-001025 | 10007 | 2018-12-05 13:50 | Section 3 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2018-12-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 144 | NULL | NULL | 0 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 312 | NULL | NULL | 0 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 84 | NULL | NULL | 0 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 144 | NULL | NULL | 0 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10007-001025 | 10007 | 2018-12-05 13:50 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 6 | Each | 115.78 | 694.68 | Geotextiles | 2018-12-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10007-001025 | 10007 | 2018-12-05 13:50 | Section 3 | Material | NULL | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2018-12-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10003-001025 | 10003 | 2018-12-05 14:25 | Section 3 | Material | Not on List | Not on List | 8 | EA | 25.48 | 203.84 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10003-001025 | 10003 | 2018-12-05 14:25 | Section 3 | Material | Not on List | Not on List | 12 | EA | 31.41 | 376.92 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 10 | no. | NULL | 0 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 100 | no. | NULL | 0 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 5 | bags | NULL | 0 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 122 | NULL | 60 | 7320 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 65 | 130 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 4 | NULL | 700 | 2800 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 36 | Tubes | 4.55 | 163.8 | Ductile Drainage | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3B - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10032-001025 | 10032 | 2018-12-06 09:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 55 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 110 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 140 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 160 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 320 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 55 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 110 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 35 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 35 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5072-0027 | 5072 | 2018-08-14 14:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 72 | Each | NULL | 0 | Miscellaneous | 2018-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 60 | Each | 10.5 | 630 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 110 | Each | 1.84 | 202.4 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 300 | Each | 0.85 | 255 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 23.14 | 462.8 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 30 | Each | 3.38 | 101.4 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 60 | Each | 1.86 | 111.6 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 34.82 | 696.4 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 6.54 | 130.8 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | Each | 2.75 | 110 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | Each | 26.94 | 1077.6 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 39.7 | 794 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 44.41 | 888.2 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 120 | Each | 7.64 | 916.8 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 100 | Each | 7.64 | 764 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 100 | Each | 7.64 | 764 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 45 | Each | 15.71 | 706.95 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 45 | Each | 4.9 | 220.5 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 10 | Each | 19.72 | 197.2 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | Each | 10.66 | 426.4 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | NULL | Not on List | 840 | Each | 0.85 | 714 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | NULL | Not on List | 40 | Each | 1.86 | 74.4 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | NULL | Not on List | 40 | Each | 2.75 | 110 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9963-001025 | 9963 | 2018-12-04 16:07 | Section 3 | Material | Not on List | Not on List | 350 | 25kg Bags | 14.43 | 5050.5 | Builders Merchants (General) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10047-001025 | 10047 | 2018-12-06 13:06 | Section 4 | Material | Kerbs | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-10047-001025 | 10047 | 2018-12-06 13:06 | Section 4 | Material | Kerbs | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 126 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 3 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 3 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 28 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 72 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 22 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 50 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 20 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 20 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 50 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15629-001025 | 15629 | 2019-04-10 14:53 | Section 3 | Material | Not on List | Not on List | 10 | ea | 150 | 1500 | Miscellaneous | 2019-04-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 1503 - Cables, Joints & Terminations | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15848-001025 | 15848 | 2019-04-15 11:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | number | 268.91 | 1075.64 | Miscellaneous | 2019-04-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15848-001025 | 15848 | 2019-04-15 11:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | number | 18.94 | 75.76 | Miscellaneous | 2019-04-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15848-001025 | 15848 | 2019-04-15 11:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | number | 19.5 | 78 | Miscellaneous | 2019-04-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16420-001025 | 16420 | 2019-04-25 15:32 | Core | Material | Not on List | Not on List | 1 | £ | 2820 | 2820 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16304-001025 | 16304 | 2019-04-24 11:59 | Section 4 | Material | NULL | Polypipe 110mm x 50m Ridgiduct Coil Orange S/L (877804) | 2 | Each | 113.44 | 226.88 | Builders Merchants (General) | 2019-04-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16304-001025 | 16304 | 2019-04-24 11:59 | Section 4 | Material | Not on List | Not on List | 10 | rolls | 11.51 | 115.1 | Builders Merchants (General) | 2019-04-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16395-001025 | 16395 | 2019-04-25 10:20 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-04-25 | RVP 420 - A14 Eastbound - Opposite Crematorium | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16433-001025 | 16433 | 2019-04-25 14:35 | Section 6 | Material | Signage | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16433-001025 | 16433 | 2019-04-25 14:35 | Section 6 | Material | Signage | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16446-001025 | 16446 | 2019-04-25 15:24 | Section 3 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 400 | Each | 3.04 | 1216 | Miscellaneous | 2019-04-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15938-001025 | 15938 | 2019-04-16 11:49 | Section 4 | Material | Not on List | Not on List | 3 | Each | 191.58 | 574.74 | Miscellaneous | 2019-04-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15938-001025 | 15938 | 2019-04-16 11:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 175.6 | 175.6 | Miscellaneous | 2019-04-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15938-001025 | 15938 | 2019-04-16 11:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 71.98 | 71.98 | Miscellaneous | 2019-04-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15938-001025 | 15938 | 2019-04-16 11:49 | Section 4 | Material | Not on List | Not on List | 2 | Each | 79.86 | 159.72 | Miscellaneous | 2019-04-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6337-00671 | 6337 | 2018-09-11 14:42 | Section 4 | Material | Not on List | Not on List | 10 | u | NULL | 0 | Rebar and Mesh | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16464-001025 | 16464 | 2019-04-26 08:53 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 24.65 | 123.25 | Miscellaneous | 2019-05-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16464-001025 | 16464 | 2019-04-26 08:53 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 24.65 | 123.25 | Miscellaneous | 2019-05-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16419-001025 | 16419 | 2019-04-25 14:45 | Section 3 | Material | Not on List | Not on List | 100 | NULL | 5.3 | 530 | Miscellaneous | 2019-04-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16419-001025 | 16419 | 2019-04-25 14:45 | Section 3 | Material | Not on List | Not on List | 100 | NULL | 2.18 | 218 | Miscellaneous | 2019-04-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16419-001025 | 16419 | 2019-04-25 14:45 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 757.4 | 757.4 | Small Tools (Consumables) | 2019-04-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16476-001025 | 16476 | 2019-04-26 10:51 | Section 3 | Material | Not on List | Not on List | 100000 | Litres | 1 | 100000 | Gas Oil | 2019-04-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16342-001025 | 16342 | 2019-04-24 15:47 | Core | Material | Not on List | Not on List | 1 | NULL | 670 | 670 | Miscellaneous | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 25 | Each | 8.55 | 214 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 25 | Each | 8.55 | 214 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 25 | Each | 8.55 | 214 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Paint Roller And Tray Set 9" Rskit1 (704256) | 20 | Each | 3.42 | 68 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Roller Paint Final Task 9" Power Stripe Kit 16509020 (704250) | 5 | Each | 12.32 | 62 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6255-00648 | 6255 | 2018-09-10 10:06 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2018-09-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Shovel No2 Taper Mouth Insulated Yd Handle - Spartan Xt (762641) | 5 | Each | 36.86 | 184 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Broom 11.5" Natural Fibre Bracketed 48" X 15/16" Handle (502213) | 15 | Each | 2.23 | 33 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Respirator Disposable 3m 8833 Ffp3 Valved Box Of 10 (292498) | 30 | Each | 33.81 | 1014 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Red (742163) | 20 | Each | 6.7 | 134 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Whipcheck End 1/2" To 1 1/4 (850028) | 7 | Each | 5.25 | 37 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Plant Nappy 1000mm X 685mm All Blue (600200) | 3 | Each | 101.96 | 306 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16413-001025 | 16413 | 2019-04-23 16:19 | Section 4 | Material | Not on List | Not on List | 40 | Each | 47.89 | 1915.6 | Builders Merchants (General) | 2019-04-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16413-001025 | 16413 | 2019-04-23 16:19 | Section 4 | Material | Not on List | Not on List | 8 | Each | 47.89 | 383.12 | Builders Merchants (General) | 2019-04-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1502 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6355-00675 | 6355 | 2018-09-11 16:59 | Section 4 | Material | Not on List | Not on List | 3.74 | Tonnes | 287.7 | 1076 | Reinforcement | 2018-09-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15762-001025 | 15762 | 2019-04-12 11:58 | Core | Material | Not on List | Not on List | 30 | Each | 12.76 | 382.8 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16330-001025 | 16330 | 2019-04-24 15:37 | Core | Material | Not on List | Not on List | 1 | Each | 70 | 70 | Miscellaneous | 2019-05-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16330-001025 | 16330 | 2019-04-24 15:37 | Core | Material | Not on List | NULL | 5 | Each | 5 | 25 | Miscellaneous | 2019-04-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16329-001025 | 16329 | 2019-04-24 15:31 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16534-001025 | 16534 | 2019-04-29 07:11 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16536-001025 | 16536 | 2019-04-29 07:19 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6307 | 6307 | 2018-09-11 09:04 | Section 4 | Material | Not on List | Not on List | 48 | NULL | NULL | 0 | Fixings and Fasteners | 2018-09-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16538-001025 | 16538 | 2019-04-29 07:23 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16557-001025 | 16557 | 2019-04-29 09:54 | Core | Material | Not on List | Not on List | 1 | number | 303.8 | 304 | Office Supplies | 2019-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16557-001025 | 16557 | 2019-04-29 09:54 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Office Supplies | 2019-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16558-001025 | 16558 | 2019-04-29 10:03 | Section 5 | Material | Not on List | Not on List | 1 | number | 10556.5 | 10557 | Miscellaneous | 2019-04-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16558-001025 | 16558 | 2019-04-29 10:03 | Section 5 | Material | Not on List | Not on List | 1 | number | 7916.71 | 7917 | Miscellaneous | 2019-04-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 2337.11 | 2337.11 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 7016.34 | 7016.34 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6355 | 6355 | 2018-09-11 16:59 | Section 4 | Material | Not on List | Not on List | 3.74 | Tonnes | 287.7 | 1076 | Reinforcement | 2018-09-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 1379.56 | 1379.56 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 1286.5 | 1286.5 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 7016.34 | 7016.34 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 1026.67 | 1026.67 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 831.27 | 831.27 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 3207.03 | 3207.03 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 8534.53 | 8534.53 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 3376 | ea | 22 | 74272 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 35 | ea | 35 | 1225 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 19 | ea | 17 | 323 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6254-00647 | 6254 | 2018-09-10 09:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | EAch | 1844.62 | 1844.62 | Small Tools (Consumables) | 2018-09-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 531 | ea | 29 | 15399 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 1 | ea | 58 | 58 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 1 | ea | 32 | 32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 3892 | EA | 23 | 89516 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 51 | ea | 355 | 18105 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 37 | ea | 279 | 10323 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 30 | ea | 125 | 3750 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 1 | ea | 100 | 100 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 3 | ea | 100 | 300 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 37 | ea | 100 | 3700 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | NULL | Not on List | 28 | ea | 30 | 840 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 9 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 4 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 9 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 10 | Cartons | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 40 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 25 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 20 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15447-001025 | 15447 | 2019-04-08 12:23 | Section 4 | Material | Not on List | Not on List | 500 | Shims | NULL | 0 | Fixings and Fasteners | 2019-04-11 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15447-001025 | 15447 | 2019-04-08 12:23 | Section 4 | Material | Not on List | Not on List | 500 | Shims | NULL | 0 | Fixings and Fasteners | 2019-04-11 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16474-001025 | 16474 | 2019-04-26 10:32 | Section 3 | Material | Not on List | Not on List | 500 | Number | 80 | 40000 | Aggregate | 2019-04-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15709-001025 | 15709 | 2019-04-11 16:16 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | each | 503 | 503 | Laboratory Equipment / Certification | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16565-001025 | 16565 | 2019-04-29 12:51 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2869.68 | 2870 | PPE | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-12041-001025 | 12041 | 2019-02-07 09:06 | Section 2 | Material | Not on List | Not on List | 6 | Units | NULL | 0 | Plastic Drainage | 2019-02-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12042-001025 | 12042 | 2019-02-07 09:19 | Section 2 | Material | Saint Gobain Castings | 454x454x100 D400 Watershed GG&F (257790) | 25 | Each | 63.84 | 1596 | Builders Merchants (General) | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12044-001025 | 12044 | 2019-02-07 10:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11905-001025 | 11905 | 2019-02-05 07:41 | Section 2 | Material | Misc | NULL | 1 | NULL | 487.54 | 487.54 | Miscellaneous | 2019-02-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12055-001025 | 12055 | 2019-02-07 12:32 | Section 2 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Geotextiles | 2019-02-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11923-001025 | 11923 | 2019-02-05 10:18 | Section 2 | Material | Not on List | Not on List | 1 | EA | 400 | 400 | Miscellaneous | 2019-02-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs Splayed 45deg 125x255 (898227) | 100 | Meters | 4.59 | 459 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 40 | Meters | 6 | 240 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 1 | Each | 11.94 | 11.94 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 200 | Meter | 3.52 | 704 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs 125x255 HB External Radius (947297) | 20 | Meter | 5.43 | 108.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 3 | Each | 7.68 | 23.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 3 | Each | 7.68 | 23.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 600 | Meter | 1.5 | 900 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | NULL | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196.44 | Concrete Drainage | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142.4 | Concrete Drainage | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | NULL | Not on List | 20 | Unit | 13.95 | 279 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | NULL | Not on List | 40 | Tubs | 14.48 | 579.2 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11927-001025 | 11927 | 2019-02-05 10:49 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11927-001025 | 11927 | 2019-02-05 10:49 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Accessories | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11929-001025 | 11929 | 2019-02-05 11:01 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2019-02-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12064-001025 | 12064 | 2019-02-07 14:43 | Section 2 | Material | Not on List | Not on List | 1050 | meters | NULL | 0 | Rebar and Mesh | 2019-02-18 | Gate 2 - 1339617 - BN02 East & BN27, via Gate 2, A1 Layby Southbound Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12064-001025 | 12064 | 2019-02-07 14:43 | Section 2 | Material | Not on List | Not on List | 1050 | meters | NULL | 0 | Rebar and Mesh | 2019-02-18 | Gate 2 - 1339617 - BN02 East & BN27, via Gate 2, A1 Layby Southbound Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12064-001025 | 12064 | 2019-02-07 14:43 | Section 2 | Material | Not on List | Not on List | 420 | meters | NULL | 0 | Rebar and Mesh | 2019-02-18 | Gate 2 - 1339617 - BN02 East & BN27, via Gate 2, A1 Layby Southbound Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12022-001025 | 12022 | 2019-02-06 17:10 | Section 2 | Material | Aggregate | Type 1 | 9400 | Tonnes | 16 | 150400 | Aggregate | 2019-02-06 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | NULL | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 65 | tonnes | NULL | 0 | Reinforcement | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 150 | tonnes | NULL | 0 | Reinforcement | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 35 | tonnes | NULL | 0 | Reinforcement | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 50 | tonnes | NULL | 0 | Reinforcement | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 58.93 | 117.86 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 81.84 | 163.68 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 20.65 | 20.65 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 27.81 | 27.81 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 327.87 | 327.87 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 237.86 | 237.86 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 79.27 | 79.27 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12078-001025 | 12078 | 2019-02-07 15:38 | Section 2 | Material | Bricks/Blocks | Not on List | 395 | m2 | NULL | 0 | Blocks and Bricks | 2019-02-11 | Gate 6 - 1350301 - Processing Plant, Buckden Road, PE19 5UH | SC2A - Roadworks - A1 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11783-001025 | 11783 | 2019-02-01 08:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 27.49 | 27.49 | Electrical | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12008-001025 | 12008 | 2019-02-06 14:18 | Section 4 | Material | Not on List | Not on List | 1 | Each | 440.75 | 440.75 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12081-001025 | 12081 | 2019-02-07 16:08 | Core | Material | Not on List | Not on List | 1 | number | 180 | 180 | Office Supplies | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | IMO - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12006-001025 | 12006 | 2019-02-06 14:06 | Section 4 | Material | Not on List | Not on List | 50 | Each | 38.09 | 1904.5 | Concrete Drainage | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12006-001025 | 12006 | 2019-02-06 14:06 | Section 4 | Material | Not on List | Not on List | 10 | Each | 36 | 360 | Concrete Drainage | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12101-001025 | 12101 | 2019-02-07 17:37 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 643.99 | 644 | PPE | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12109-001025 | 12109 | 2019-02-08 07:20 | Section 2 | Material | Not on List | Not on List | 0.255 | Tonnes | 538 | 137 | Rebar and Mesh | 2019-02-14 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11995-001025 | 11995 | 2019-02-06 11:20 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 28 | 28 | Miscellaneous | 2019-02-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 14 | Each | 24.32 | 340 | Timber Products | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Not on List | Not on List | 1 | Drum | NULL | 0 | Concrete Accessories | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Not on List | Not on List | 1 | Drum | NULL | 0 | Concrete Accessories | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Not on List | Not on List | 20 | m | NULL | 0 | Concrete Accessories | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 6 | Each | 5.82 | 35 | Timber Products | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Not on List | Not on List | 20 | Each | NULL | 0 | Concrete Accessories | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 540.59 | 540.59 | PPE | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 462.25 | 462.25 | Small Tools (Consumables) | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 201.96 | 201.96 | Janitorial | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12120-001025 | 12120 | 2019-02-08 08:13 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-02-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12127-001025 | 12127 | 2019-02-08 08:48 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.5 | 150 | Surveying Consumables | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12042-001025 | 12042 | 2019-02-07 09:19 | Section 2 | Material | NULL | 454x454x100 D400 Watershed GG&F (257790) | 25 | Each | 63.84 | 1596 | Builders Merchants (General) | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12128-001025 | 12128 | 2019-02-08 09:43 | Core | Material | Not on List | Not on List | 1 | ea | 664 | 664 | Training | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12129-001025 | 12129 | 2019-02-08 10:01 | Section 4 | Material | Aggregate | Not on List | 9159.63 | ea | 5 | 45798 | Aggregate | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11933-001025 | 11933 | 2019-02-05 11:54 | Section 2 | Material | NULL | Not on List | 6 | pack | 21.25 | 127.5 | Timber Products | 2019-02-08 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11933-001025 | 11933 | 2019-02-05 11:54 | Section 2 | Material | NULL | Not on List | 4 | pack | 12.5 | 50 | Timber Products | 2019-02-08 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12131-001025 | 12131 | 2019-02-08 10:35 | Core | Material | Not on List | Not on List | 1 | ea | 970 | 970 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12132-001025 | 12132 | 2019-02-08 10:54 | Section 4 | Material | Not on List | Not on List | 1 | number | 4950 | 4950 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11926-001025 | 11926 | 2019-02-05 10:39 | Section 2 | Material | Not on List | Not on List | 1 | each | 56 | 56 | Laboratory Equipment / Certification | 2019-02-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 603 - Processing | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12140-001025 | 12140 | 2019-02-08 10:51 | Section 4 | Material | Not on List | Not on List | 120 | tubes | 12 | 1440 | Blocks and Bricks | 2019-02-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12140-001025 | 12140 | 2019-02-08 10:51 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 60 | 60 | Blocks and Bricks | 2019-02-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11964-001025 | 11964 | 2019-02-05 17:05 | Section 2 | Material | Not on List | Not on List | 2 | No. | NULL | 0 | Fixings and Fasteners | 2019-02-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11842-001025 | 11842 | 2019-02-04 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 324.01 | 324.01 | Concrete Accessories | 2019-02-08 | Gate C - 1339702 - BN06 (East Coast Railway) Via Logistics Yard Access | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12045-001025 | 12045 | 2019-02-07 10:45 | Core | Material | Not on List | Not on List | 1 | ea | 1265.37 | 1265 | Training | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12007-001025 | 12007 | 2019-02-06 14:13 | Section 4 | Material | Not on List | Not on List | 100 | Each | 8.38 | 838 | Plastic Drainage | 2019-02-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12112-001025 | 12112 | 2019-02-08 07:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 653.1 | Each | 1 | 653.1 | Miscellaneous | 2019-02-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12155-001025 | 12155 | 2019-02-08 12:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 12 | each | 102 | 1224 | Tanks and Interceptors | 2019-02-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12156-001025 | 12156 | 2019-02-08 13:01 | Core | Material | Not on List | Not on List | 3 | number packs | 21.45 | 64 | Office Supplies | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | NULL
MREQ-12128-001025 | 12128 | 2019-02-08 09:43 | Core | Material | Not on List | Not on List | 1 | ea | 664 | 664 | Training | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12131-001025 | 12131 | 2019-02-08 10:35 | Core | Material | Not on List | Not on List | 1 | ea | 970 | 970 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-11854-001025 | 11854 | 2019-02-04 11:49 | Section 4 | Material | Not on List | Not on List | 180 | ROLLS | 49.5 | 8910 | Concrete Accessories | 2019-02-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11854-001025 | 11854 | 2019-02-04 11:49 | Section 4 | Material | NULL | Not on List | 1 | Each | 650 | 650 | Concrete Accessories | 2019-02-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12133-001025 | 12133 | 2019-02-08 11:30 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1000 | Each | 1.07 | 1070 | Surveying Consumables | 2019-02-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12129-001025 | 12129 | 2019-02-08 10:01 | Section 4 | Material | Aggregate | Not on List | 9159.63 | ea | 5 | 45798.15 | Aggregate | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12140-001025 | 12140 | 2019-02-08 10:51 | Section 4 | Material | Not on List | Not on List | 120 | tubes | 12 | 1440 | Blocks and Bricks | 2019-02-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12140-001025 | 12140 | 2019-02-08 10:51 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 60 | 60 | Blocks and Bricks | 2019-02-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12127-001025 | 12127 | 2019-02-08 08:48 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.5 | 150 | Surveying Consumables | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12217-001025 | 12217 | 2019-02-11 09:36 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | NULL
MREQ-12217-001025 | 12217 | 2019-02-11 09:36 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | NULL
MREQ-12219-001025 | 12219 | 2019-02-11 10:00 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 7548.8 | 7549 | Laboratory Equipment / Certification | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | NULL
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 5 | no | 439 | 2195 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 2 | no | 95 | 190 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 1 | no | 95 | 95 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12035-001025 | 12035 | 2019-02-07 07:49 | Section 4 | Material | NULL | Not on List | 112 | Each | 4.95 | 554.4 | Builders Merchants (General) | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12078-001025 | 12078 | 2019-02-07 15:38 | Section 2 | Material | NULL | Not on List | 395 | m2 | NULL | 0 | Blocks and Bricks | 2019-02-11 | Gate 6 - 1350301 - Processing Plant, Buckden Road, PE19 5UH | SC2A - Roadworks - A1 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12078-001025 | 12078 | 2019-02-07 15:38 | Section 2 | Material | NULL | Not on List | 60 | number | 10 | 600 | NULL | NULL | Gate 6 - 1350301 - Processing Plant, Buckden Road, PE19 5UH | SC2A - Roadworks - A1 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12247-001025 | 12247 | 2019-02-11 15:21 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2019-02-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12253-001025 | 12253 | 2019-02-11 16:05 | Section 3 | Material | Not on List | Not on List | 1 | EA | 2000 | 2000 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12254-001025 | 12254 | 2019-02-11 16:10 | Section 4 | Material | Not on List | Not on List | 1040 | hour | 21 | 21840 | Professional Services | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12257-001025 | 12257 | 2019-02-11 16:25 | Section 2 | Material | Not on List | Not on List | 15 | Bags | NULL | 0 | Concrete Accessories | 2019-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12268-001025 | 12268 | 2019-02-11 18:34 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 160.57 | 161 | Damage Charges | 2019-02-13 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11751-001025 | 11751 | 2019-01-31 16:38 | Section 4 | Material | Not on List | Not on List | 5 | Each | 20 | 100 | Surveying Consumables | 2019-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11903-001025 | 11903 | 2019-02-05 07:29 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 738.72 | 738.72 | Miscellaneous | 2019-02-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11724-001025 | 11724 | 2019-01-31 13:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 675.34 | 675.34 | Miscellaneous | 2019-02-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12031-001025 | 12031 | 2019-02-07 06:55 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 320 | 320 | Miscellaneous | 2019-02-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12278-001025 | 12278 | 2019-02-12 07:56 | Section 4 | Material | Not on List | Not on List | 13 | ea | NULL | 0 | Concrete Drainage | 2019-02-18 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12283-001025 | 12283 | 2019-02-12 08:21 | Section 2 | Material | Not on List | Not on List | 12 | Number | NULL | 0 | Fixings and Fasteners | 2019-02-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5346-00239 | 5346 | 2018-08-20 11:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Roll | 36.98 | 0 | Miscellaneous | 2018-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12287-001025 | 12287 | 2019-02-12 08:43 | Section 2 | Material | Not on List | Not on List | 8 | no | NULL | 0 | Concrete Accessories | 2019-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12287-001025 | 12287 | 2019-02-12 08:43 | Section 2 | Material | Not on List | Not on List | 4 | no | NULL | 0 | Concrete Accessories | 2019-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12289-001025 | 12289 | 2019-02-12 09:03 | Core | Material | Not on List | Not on List | 2 | each | 228 | 456 | Office Supplies | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12293-001025 | 12293 | 2019-02-12 09:36 | Section 3 | Material | Not on List | Not on List | 250 | NULL | NULL | 0 | Timber Products | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 401 - Safety Barriers | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-12268-001025 | 12268 | 2019-02-11 18:34 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 160.57 | 160.57 | Damage Charges | 2019-02-13 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12294-001025 | 12294 | 2019-02-12 09:49 | Section 3 | Material | Not on List | Not on List | 2000 | NULL | NULL | 0 | Miscellaneous | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12296-001025 | 12296 | 2019-02-12 10:04 | Core | Material | Not on List | Not on List | 1 | ea | 41504 | 41504 | Office Supplies | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-11611-001025 | 11611 | 2019-01-29 11:05 | Section 3 | Material | Concrete Drainage | Not on List | 2 | No. | 5698.22 | 11396.44 | Concrete Drainage | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11713 | 11713 | 2019-01-31 11:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Set | NULL | 0 | Miscellaneous | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12300-001025 | 12300 | 2019-02-12 11:12 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 88.88 | 89 | Small Tools (Consumables) | 2019-02-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12254-001025 | 12254 | 2019-02-11 16:10 | Section 4 | Material | Not on List | Not on List | 1040 | hour | 21 | 21840 | Professional Services | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12253-001025 | 12253 | 2019-02-11 16:05 | Section 3 | Material | Not on List | Not on List | 1 | EA | 2000 | 2000 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12304-001025 | 12304 | 2019-02-12 12:01 | Section 2 | Material | Not on List | Not on List | 1 | Number | 253.66 | 254 | Surveying Consumables | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12304-001025 | 12304 | 2019-02-12 12:01 | Section 2 | Material | Not on List | Not on List | 1 | Number | 15.84 | 16 | Surveying Consumables | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 5 | no | 439 | 2195 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 2 | no | 95 | 190 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28592-001025 | 28592 | 2020-01-28 14:44 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 691.37 | 691 | PPE | 2020-01-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28592-001025 | 28592 | 2020-01-28 14:44 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 272.7 | 273 | Janitorial | 2020-01-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28592-001025 | 28592 | 2020-01-28 14:44 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 203.43 | 203 | Small Tools (Consumables) | 2020-01-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26797-001025 | 26797 | 2019-11-20 09:51 | Core | Material | Not on List | Not on List | 1 | NULL | 140 | 140 | Miscellaneous | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 107 - Fee based costs including insurance | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28597-001025 | 28597 | 2020-01-28 15:19 | Core | Material | Not on List | Not on List | 1 | NULL | 35000 | 35000 | Miscellaneous | 2020-01-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 153 - Temporary Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 2 | Each | 43.49 | 86.98 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28606-001025 | 28606 | 2020-01-28 19:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2020-01-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1502 - Trenches, Ducts and Chambers | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-28558-001025 | 28558 | 2020-01-27 16:43 | Section 2 | Material | Not on List | Not on List | 5 | each | 78.5 | 392.5 | Builders Merchants (General) | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28614-001025 | 28614 | 2020-01-29 09:26 | Core | Material | Not on List | Not on List | 1 | Licence | 1950 | 1950 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7154-001020 | 7154 | 2018-09-28 13:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 494.73 | 494.73 | Professional Services | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28633-001025 | 28633 | 2020-01-29 14:25 | Section 5 | Material | Timber | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28633-001025 | 28633 | 2020-01-29 14:25 | Section 5 | Material | Timber | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7389-001022 | 7389 | 2018-10-04 11:28 | Section 4 | Material | NULL | Not on List | 2156 | M2 | 11.85 | 25548.6 | Blocks and Bricks | 2018-10-15 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28620-001025 | 28620 | 2020-01-29 10:08 | Section 4 | Material | Aggregate | Not on List | 60000 | ton | 5 | 300000 | Aggregate | 2020-01-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Bags | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 10 | Bags | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 10 | Bags | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 1 | Container | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 10 | Bags | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 6 | Packs | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7389-001022 | 7389 | 2018-10-04 11:28 | Section 4 | Material | NULL | NULL | 15 | Each | 30 | 450 | Blocks and Bricks | 2018-10-15 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 4 | Packs | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28603-001025 | 28603 | 2020-01-28 14:29 | Section 4 | Material | NULL | NULL | 1 | Each | 4681.16 | 4681.16 | Miscellaneous | 2020-01-31 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28649-001025 | 28649 | 2020-01-29 16:04 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1101 - Kerbs, Channels and Edgings | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-7415-001022 | 7415 | 2018-10-04 16:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 577.15 | 577.15 | Concrete Drainage | 2018-10-12 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28487-001025 | 28487 | 2020-01-24 10:15 | Section 4 | Material | Not on List | Not on List | 50 | Each | 50.69 | 2534.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28487-001025 | 28487 | 2020-01-24 10:15 | Section 4 | Material | Not on List | Not on List | 15 | Each | 158.78 | 2381.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28487-001025 | 28487 | 2020-01-24 10:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 75.46 | 75.46 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28487-001025 | 28487 | 2020-01-24 10:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 75.46 | 75.46 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28487-001025 | 28487 | 2020-01-24 10:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 115 | 115 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28579-001025 | 28579 | 2020-01-28 09:41 | Section 2 | Material | Concrete Drainage | Not on List | 60 | each | 0 | 0 | Builders Merchants (General) | 2020-01-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28270-001025 | 28270 | 2020-01-17 10:29 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28186-001025 | 28186 | 2020-01-15 15:05 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7415-001022 | 7415 | 2018-10-04 16:27 | Section 4 | Material | Not on List | Not on List | 8 | Each | 361.34 | 2890.72 | Concrete Drainage | 2018-10-12 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28657-001025 | 28657 | 2020-01-30 08:00 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 4 | ea | 30.24 | 120.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28657-001025 | 28657 | 2020-01-30 08:00 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 16 | ea | 1.62 | 25.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28657-001025 | 28657 | 2020-01-30 08:00 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 10.08 | 10.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28651-001025 | 28651 | 2020-01-30 07:31 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 4 | No | 30.24 | 120.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28651-001025 | 28651 | 2020-01-30 07:31 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 16 | No | 1.62 | 25.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28651-001025 | 28651 | 2020-01-30 07:31 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 2 | No | 10.08 | 20.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28650-001025 | 28650 | 2020-01-30 07:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 4 | No | 30.24 | 120.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28650-001025 | 28650 | 2020-01-30 07:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 18 | No | 1.62 | 29.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28650-001025 | 28650 | 2020-01-30 07:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 2 | No | 10.08 | 20.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28754-001025 | 28754 | 2020-02-01 09:52 | Section 5 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7415-001022 | 7415 | 2018-10-04 16:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1238.1 | 1238.1 | Concrete Drainage | 2018-10-12 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28778-001025 | 28778 | 2020-02-03 09:34 | Section 1 | Material | Not on List | Not on List | 20 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-02-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-28778-001025 | 28778 | 2020-02-03 09:34 | Section 1 | Material | Not on List | Not on List | 20 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-02-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-28778-001025 | 28778 | 2020-02-03 09:34 | Section 1 | Material | Not on List | Not on List | 25 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-02-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | GN01 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-7415-001022 | 7415 | 2018-10-04 16:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 534.53 | 534.53 | Concrete Drainage | 2018-10-12 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28786-001025 | 28786 | 2020-02-03 11:01 | Section 5 | Material | Not on List | Not on List | 20 | NULL | 12.43 | 249 | Miscellaneous | 2020-02-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28800-001025 | 28800 | 2020-02-03 14:38 | Section 5 | Material | Combined Drainage | Not on List | 400 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-06 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28801-001025 | 28801 | 2020-02-03 15:03 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28802-001025 | 28802 | 2020-02-03 14:53 | Section 5 | Material | Not on List | Not on List | 10 | bags | NULL | 0 | Builders Merchants (General) | 2020-02-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28802-001025 | 28802 | 2020-02-03 14:53 | Section 5 | Material | Not on List | Not on List | 40 | packs (600ml) | NULL | 0 | Builders Merchants (General) | 2020-02-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7415-001022 | 7415 | 2018-10-04 16:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 527.33 | 527.33 | Concrete Drainage | 2018-10-12 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28034-001025 | 28034 | 2020-01-10 11:45 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Each | 2467.72 | 2467.72 | Waste (General) | 2020-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28034-001025 | 28034 | 2020-01-10 11:45 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Each | 805.14 | 805.14 | Waste (General) | 2020-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28781-001025 | 28781 | 2020-02-03 09:27 | Section 4 | Material | Not on List | Not on List | 55 | Each | 34 | 1870 | Ductile Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28781-001025 | 28781 | 2020-02-03 09:27 | Section 4 | Material | Not on List | Not on List | 10 | Each | 44.73 | 447.3 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28781-001025 | 28781 | 2020-02-03 09:27 | Section 4 | Material | Not on List | Not on List | 10 | Each | 24.33 | 243.3 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28781-001025 | 28781 | 2020-02-03 09:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 79.96 | 79.96 | Small Tools (Consumables) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28781-001025 | 28781 | 2020-02-03 09:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 15 | 15 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28812-001025 | 28812 | 2020-02-03 15:34 | Section 4 | Material | Not on List | Not on List | 20 | Number | NULL | 0 | Builders Merchants (General) | 2020-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 105 - Site Security | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28821-001025 | 28821 | 2020-02-04 08:36 | Core | Material | Not on List | Not on List | 1 | ea | 525 | 525 | Training | 2020-02-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 8 | Each | 81.96 | 655.68 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28836-001025 | 28836 | 2020-02-04 11:40 | Core | Material | Not on List | Not on List | 4 | Number | 42.49 | 170 | Surveying Consumables | 2020-02-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-28847-001025 | 28847 | 2020-02-04 13:35 | Core | Material | Not on List | Not on List | 1 | number | 73.47 | 73 | Office Supplies | 2020-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-28849-001025 | 28849 | 2020-02-04 14:13 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 8 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-02-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28616-001025 | 28616 | 2020-01-29 09:03 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28611-001025 | 28611 | 2020-01-29 08:16 | Section 4 | Material | Not on List | Not on List | 4182 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28635-001025 | 28635 | 2020-01-29 14:32 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28776-001025 | 28776 | 2020-02-03 09:16 | Section 6 | Material | Not on List | Not on List | 336 | m3 | 88.2 | 29635.2 | Ready Mixed Concrete | 2020-02-03 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28776-001025 | 28776 | 2020-02-03 09:16 | Section 6 | Material | Not on List | Not on List | 590 | m3 | 115.12 | 67920.8 | Ready Mixed Concrete | 2020-02-03 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28776-001025 | 28776 | 2020-02-03 09:16 | Section 6 | Material | Not on List | Not on List | 1000 | m3 | 107.76 | 107760 | Ready Mixed Concrete | 2020-02-03 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 4 | Each | 61.48 | 245.92 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28779-001025 | 28779 | 2020-02-03 09:42 | Section 2 | Material | Not on List | Not on List | 20 | m3 | 76.5 | 1530 | Ready Mixed Concrete | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28779-001025 | 28779 | 2020-02-03 09:42 | Section 2 | Material | Not on List | Not on List | 30 | m3 | 87.25 | 2617.5 | Ready Mixed Concrete | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28779-001025 | 28779 | 2020-02-03 09:42 | Section 2 | Material | Not on List | Not on List | 30 | m3 | 107.76 | 3232.8 | Ready Mixed Concrete | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25001-001025 | 25001 | 2019-10-11 17:13 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 721.9 | 722 | Small Tools (Consumables) | 2019-10-16 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24886-001025 | 24886 | 2019-10-10 07:11 | Section 4 | Material | Not on List | Not on List | 15 | Each | 950 | 14250 | Miscellaneous | 2019-12-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24886-001025 | 24886 | 2019-10-10 07:11 | Section 4 | Material | Not on List | Not on List | 12 | Each | 718 | 8616 | Miscellaneous | 2019-12-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24886-001025 | 24886 | 2019-10-10 07:11 | Section 4 | Material | NULL | Not on List | 15 | Each | 120 | 1800 | Miscellaneous | 2019-12-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24886-001025 | 24886 | 2019-10-10 07:11 | Section 4 | Material | NULL | Not on List | 12 | Each | 110 | 1320 | Miscellaneous | 2019-12-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25010-001025 | 25010 | 2019-10-14 08:07 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7038-001008 | 7038 | 2018-09-26 15:49 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.18 | 36 | Fixings and Fasteners | 2018-10-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25019-001025 | 25019 | 2019-10-14 09:02 | Core | Material | Not on List | Not on List | 1 | ea | 850 | 850 | Training | 2019-10-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25033-001025 | 25033 | 2019-10-14 10:04 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 96 | Each | 4.02 | 385.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 160 | Each | 3.03 | 484.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 390 | Each | 4.59 | 1790.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 384 | Each | 3.52 | 1351.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 432 | Each | 3.52 | 1520.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 32 | Each | 5.43 | 173.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 34 | Each | 5.43 | 184.62 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 4 | Each | 30 | 120 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25036-001025 | 25036 | 2019-10-14 11:25 | Section 4 | Material | Not on List | Not on List | 1 | each | 126751.85 | 126751.85 | Gas Oil | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6984-00752 | 6984 | 2018-09-25 16:57 | Section 3 | Material | Not on List | Not on List | 80 | 25m | 13.95 | 1116 | Miscellaneous | 2018-09-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25057-001025 | 25057 | 2019-10-14 14:48 | Section 5 | Material | Not on List | Not on List | 2 | Bundles (100l/m each) | 95 | 190 | Timber Products | 2019-10-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-25042-001025 | 25042 | 2019-10-14 13:15 | Section 4 | Material | NULL | NULL | 16 | Each | 7.96 | 127.36 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25042-001025 | 25042 | 2019-10-14 13:15 | Section 4 | Material | NULL | NULL | 16 | Each | 7.96 | 127.36 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25073-001025 | 25073 | 2019-10-14 16:28 | Core | Material | Not on List | Not on List | 1 | ea | 8750 | 8750 | Training | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25073-001025 | 25073 | 2019-10-14 16:28 | Core | Material | Not on List | Not on List | 1 | ea | 473.4 | 473 | Training | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25080-001025 | 25080 | 2019-10-14 17:12 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327 | Builders Merchants (General) | 2019-10-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-25085-001025 | 25085 | 2019-10-14 17:47 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-10-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25090-001025 | 25090 | 2019-10-15 07:17 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No | NULL | 0 | Small Tools (Consumables) | 2019-10-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25092-001025 | 25092 | 2019-10-15 07:46 | Core | Material | PPE, Small Tools and Consumables | Stake Marking Out Wooden 1200mm Nominal C.r.code Swcoc004463 (740904) | 50 | each | 1.07 | 54 | Surveying Consumables | 2019-10-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7012-00752 | 7012 | 2018-09-26 08:51 | Section 3 | Material | PPE, Small Tools and Consumables | Jalas Jupiter S3 Safety Boots (120104) | 3 | Each | 39.99 | 119.97 | PPE | 2018-10-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25088-001025 | 25088 | 2019-10-15 06:31 | Core | Material | PPE, Small Tools and Consumables | Not on List | 144 | each | 6.29 | 905.76 | Miscellaneous | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25106-001025 | 25106 | 2019-10-15 11:20 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25038-001025 | 25038 | 2019-10-14 11:40 | Section 4 | Material | Bricks/Blocks | Not on List | 2 | box | 468 | 936 | Blocks and Bricks | 2019-10-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25038-001025 | 25038 | 2019-10-14 11:40 | Section 4 | Material | Bricks/Blocks | Not on List | 1 | delivery | 275 | 275 | Blocks and Bricks | 2019-10-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25111-001025 | 25111 | 2019-10-15 12:47 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 283.9 | 284 | PPE | 2019-10-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25111-001025 | 25111 | 2019-10-15 12:47 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 597.9 | 598 | Small Tools (Consumables) | 2019-10-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25027-001025 | 25027 | 2019-10-14 09:33 | Section 3 | Material | Not on List | Not on List | 3 | ea | 88 | 264 | Miscellaneous | 2019-10-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24841-001025 | 24841 | 2019-10-09 12:40 | Core | Material | PPE, Small Tools and Consumables | NULL | 1 | EA | 205 | 205 | Laboratory Equipment / Certification | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7012-00752 | 7012 | 2018-09-26 08:51 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 164.43 | 164.43 | Small Tools (Consumables) | 2018-10-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24847-001025 | 24847 | 2019-10-09 13:09 | Core | Material | Not on List | NULL | 1 | SM | 606 | 606 | Miscellaneous | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24863-001025 | 24863 | 2019-10-09 15:23 | Core | Material | Not on List | NULL | 1 | SM | 200 | 200 | Laboratory Equipment / Certification | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24909-001025 | 24909 | 2019-10-10 10:46 | Core | Material | PPE, Small Tools and Consumables | NULL | 1 | EA | 506 | 506 | Laboratory Equipment / Certification | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24911-001025 | 24911 | 2019-10-10 11:14 | Core | Material | PPE, Small Tools and Consumables | NULL | 1 | SM | 356 | 356 | Laboratory Equipment / Certification | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25104-001025 | 25104 | 2019-10-15 10:38 | Core | Material | Not on List | Not on List | 9016.63 | NULL | 1 | 9016.63 | Professional Services | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 153 - Temporary Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24992-001025 | 24992 | 2019-10-11 14:54 | Section 5 | Material | Aggregate | NULL | 6200 | MT | 21.65 | 134230 | Aggregate | 2019-10-15 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25045-001025 | 25045 | 2019-10-14 13:24 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1480.6 | Each | 1 | 1480.6 | PPE | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7012-00752 | 7012 | 2018-09-26 08:51 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 158.66 | 158.66 | Janitorial | 2018-10-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24827-001025 | 24827 | 2019-10-09 09:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 566.52 | Each | 1 | 566.52 | Small Tools (Consumables) | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7027-00753 | 7027 | 2018-09-26 14:01 | Section 3 | Material | Not on List | Not on List | 30 | Sheets | 9.44 | 283.2 | Concrete Drainage | 2018-10-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24819-001025 | 24819 | 2019-10-09 07:18 | Core | Material | Not on List | Not on List | 1 | Each | 984.64 | 984.64 | Miscellaneous | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25149-001025 | 25149 | 2019-10-16 07:44 | Section 2 | Material | Kerbs | Not on List | 1 | ea | 1200 | 1200 | Ductile Drainage | 2019-10-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25149-001025 | 25149 | 2019-10-16 07:44 | Section 2 | Material | Kerbs | Not on List | 2 | ea | 2150 | 4300 | Ductile Drainage | 2019-10-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25149-001025 | 25149 | 2019-10-16 07:44 | Section 2 | Material | Kerbs | Not on List | 2 | ea | 2250 | 4500 | Ductile Drainage | 2019-10-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25149-001025 | 25149 | 2019-10-16 07:44 | Section 2 | Material | Kerbs | Not on List | 2 | ea | 2350 | 4700 | Ductile Drainage | 2019-10-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25196-001025 | 25196 | 2019-10-16 10:59 | Section 4 | Material | Not on List | Not on List | 1 | each | NULL | 0 | Miscellaneous | 2019-10-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-25220-001025 | 25220 | 2019-10-16 12:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25096-001025 | 25096 | 2019-10-15 08:37 | Section 4 | Material | Not on List | Not on List | 1 | Each | 159 | 159 | Miscellaneous | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25129-001025 | 25129 | 2019-10-15 15:52 | Section 4 | Material | Not on List | Not on List | 12 | bags | 32.1 | 385.2 | Builders Merchants (General) | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25129-001025 | 25129 | 2019-10-15 15:52 | Section 4 | Material | Not on List | Not on List | 1 | ea | 55 | 55 | Builders Merchants (General) | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24890-001025 | 24890 | 2019-10-10 07:51 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4000 | Each | 0.37 | 1480 | Miscellaneous | 2019-10-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25224-001025 | 25224 | 2019-10-16 12:30 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 40 | Each | 47.04 | 1881.6 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24987-001025 | 24987 | 2019-10-11 14:00 | Section 4 | Material | Not on List | Not on List | 100 | Each | 5.8 | 580 | Miscellaneous | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25145-001025 | 25145 | 2019-10-16 07:01 | Section 2 | Material | Not on List | Not on List | 14 | no. | 18.49 | 258.86 | Concrete Accessories | 2019-10-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24973-001025 | 24973 | 2019-10-11 10:02 | Section 4 | Material | Not on List | Not on List | 500 | Each | 2.18 | 1090 | Miscellaneous | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24973-001025 | 24973 | 2019-10-11 10:02 | Section 4 | Material | Not on List | Not on List | 500 | Each | 3.38 | 1690 | Miscellaneous | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24973-001025 | 24973 | 2019-10-11 10:02 | Section 4 | Material | Not on List | Not on List | 160 | Each | 5.3 | 848 | Miscellaneous | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24912-001025 | 24912 | 2019-10-10 11:20 | Section 4 | Material | Not on List | Not on List | 200 | NULL | 0.8 | 160 | Surveying Consumables | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25020-001025 | 25020 | 2019-10-14 09:02 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 34.19 | 683.8 | PPE | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25117-001025 | 25117 | 2019-10-15 14:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 25 | NULL | 2.07 | 51.75 | Small Tools (Consumables) | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 12 | Each | 59.17 | 710.04 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25117-001025 | 25117 | 2019-10-15 14:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | 3.17 | 38.04 | Small Tools (Consumables) | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24508-001025 | 24508 | 2019-10-02 10:37 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 2835.5 | 2835.5 | Miscellaneous | 2019-10-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24862-001025 | 24862 | 2019-10-09 15:03 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 246.88 | 246.88 | Miscellaneous | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24916-001025 | 24916 | 2019-10-10 12:57 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25267-001025 | 25267 | 2019-10-16 15:54 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24790-001025 | 24790 | 2019-10-08 15:09 | Section 4 | Material | Not on List | Not on List | 50 | NULL | 0.98 | 49 | Small Tools (Consumables) | 2019-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25309-001025 | 25309 | 2019-10-17 09:07 | Section 2 | Material | Not on List | Not on List | 1000 | Flags | NULL | 0 | Surveying Consumables | 2019-10-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 750 D/S (913226) | 8 | Each | 61.48 | 491.84 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25128-001025 | 25128 | 2019-10-15 15:19 | Section 5 | Material | Not on List | NULL | 1 | SM | 988.98 | 988.98 | Miscellaneous | 2019-10-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25198-001025 | 25198 | 2019-10-16 10:59 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25110-001025 | 25110 | 2019-10-15 11:04 | Section 4 | Material | Not on List | Not on List | 10 | Number | 81.27 | 812.7 | Surveying Consumables | 2019-10-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25098-001025 | 25098 | 2019-10-15 09:38 | Section 4 | Material | Concrete Drainage | Not on List | 20 | Each | 48.92 | 978.4 | Concrete Drainage | 2019-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25098-001025 | 25098 | 2019-10-15 09:38 | Section 4 | Material | Concrete Drainage | Not on List | 30 | EACH | 70.91 | 2127.3 | Concrete Drainage | 2019-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25098-001025 | 25098 | 2019-10-15 09:38 | Section 4 | Material | Concrete Drainage | Not on List | 20 | EACH | 52.95 | 1059 | Concrete Drainage | 2019-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25098-001025 | 25098 | 2019-10-15 09:38 | Section 4 | Material | Concrete Drainage | Not on List | 20 | EACH | 44.88 | 897.6 | Concrete Drainage | 2019-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25325-001025 | 25325 | 2019-10-17 12:24 | Section 4 | Material | Combined Drainage | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2019-10-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-4997-0011 | 4997 | 2018-08-13 15:45 | Section 4 | Material | Not on List | Not on List | 9 | 1 | 1 | 9 | Not Sure | 2018-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 8 | Each | 53.01 | 424.08 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25241-001025 | 25241 | 2019-10-16 13:48 | Section 4 | Material | Not on List | Not on List | 20 | tonnes | 18.5 | 370 | Aggregate | 2019-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25228-001025 | 25228 | 2019-10-16 12:38 | Section 4 | Material | Bagged | NULL | 10 | EA | 33.55 | 335.5 | Builders Merchants (General) | 2019-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-25341-001025 | 25341 | 2019-10-17 12:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 36 | 216 | Small Tools (Consumables) | 2019-10-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25341-001025 | 25341 | 2019-10-17 12:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 0.6 | 12 | Small Tools (Consumables) | 2019-10-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25341-001025 | 25341 | 2019-10-17 12:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | 1.26 | 38 | Small Tools (Consumables) | 2019-10-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25341-001025 | 25341 | 2019-10-17 12:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | 1.75 | 175 | PPE | 2019-10-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25343-001025 | 25343 | 2019-10-17 14:48 | Section 3 | Material | Aggregate | Type 1 | 30 | Tonnes | 21.65 | 650 | Aggregate | 2019-10-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-25384-001025 | 25384 | 2019-10-18 10:57 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 3 | No | NULL | 0 | PPE | 2019-10-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 12 | Each | 81.96 | 983.52 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25384-001025 | 25384 | 2019-10-18 10:57 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 3 | No | NULL | 0 | PPE | 2019-10-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25384-001025 | 25384 | 2019-10-18 10:57 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 3 | No | NULL | 0 | PPE | 2019-10-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25384-001025 | 25384 | 2019-10-18 10:57 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 3 | No | NULL | 0 | PPE | 2019-10-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25084-001025 | 25084 | 2019-10-14 15:38 | Section 4 | Material | Not on List | Not on List | 26 | ea | 30.81 | 801.06 | Builders Merchants (General) | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25084-001025 | 25084 | 2019-10-14 15:38 | Section 4 | Material | Not on List | Not on List | 14 | ladder | 351.55 | 4921.7 | Fixings and Fasteners | 2019-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25084-001025 | 25084 | 2019-10-14 15:38 | Section 4 | Material | Not on List | Not on List | 125 | number | 4.86 | 607.5 | Fixings and Fasteners | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25356-001025 | 25356 | 2019-10-17 16:41 | Section 2 | Material | Not on List | Not on List | 1 | as per attached quote | NULL | 0 | Concrete Drainage | 2019-11-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 601 - Topsoil Strip, Store, Dispose | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25333-001025 | 25333 | 2019-10-17 13:25 | Section 4 | Material | Concrete Drainage | Not on List | 1 | ea | 668.83 | 668.83 | Concrete Drainage | 2019-10-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | Not on List | 12 | NULL | 232.01 | 2784.12 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25396-001025 | 25396 | 2019-10-18 12:51 | Section 5 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 28 | Each | 48.99 | 1371.72 | Plastic Drainage | 2019-10-21 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25414-001025 | 25414 | 2019-10-18 15:47 | Section 2 | Material | Not on List | Not on List | 5 | Litres | NULL | 0 | Miscellaneous | 2019-10-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7075-001009 | 7075 | 2018-09-27 08:35 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3336.28 | each | 1 | 3336.28 | Miscellaneous | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7078-001009 | 7078 | 2018-09-27 08:41 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1000 | each | 1.07 | 1070 | Surveying Consumables | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25315-001025 | 25315 | 2019-10-17 10:13 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 156.6 | 313.2 | Plastic Drainage | 2019-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25431-001025 | 25431 | 2019-10-18 17:11 | Section 4 | Material | NULL | NULL | 1 | Each | 16229.02 | 16229.02 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23723-001025 | 23723 | 2019-09-16 11:23 | Section 1 | Material | Not on List | Not on List | 6 | EA | 177.12 | 1062.72 | Ductile Drainage | 2019-09-27 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-25480-001025 | 25480 | 2019-10-21 13:56 | Section 6 | Material | Not on List | Not on List | 1 | ea | 69.99 | 70 | Miscellaneous | 2019-10-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25426-001025 | 25426 | 2019-10-18 16:43 | Section 4 | Material | NULL | NULL | 1 | Each | 5786.46 | 5786.46 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25262-001025 | 25262 | 2019-10-16 15:30 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 56.05 | 112.1 | Concrete Drainage | 2019-10-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6989-00752 | 6989 | 2018-09-25 17:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2854.97 | Each | 1 | 2854.97 | Small Tools (Consumables) | 2018-09-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24487-001025 | 24487 | 2019-10-02 07:45 | Section 4 | Material | Not on List | Not on List | 1 | Each | 99.24 | 99.24 | Miscellaneous | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24794-001025 | 24794 | 2019-10-08 15:43 | Section 2 | Material | Geotextile | Not on List | 3 | Rolls | 2047.57 | 6142.71 | Geotextiles | 2019-10-10 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25531-001025 | 25531 | 2019-10-22 08:44 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25532-001025 | 25532 | 2019-10-22 08:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-10-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-25517-001025 | 25517 | 2019-10-21 17:36 | Section 5 | Material | Not on List | Not on List | 30 | EA | 24.18 | 725.4 | Miscellaneous | 2019-10-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 15.67 | 31.34 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28851-001025 | 28851 | 2020-02-04 15:33 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-01-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-28823-001025 | 28823 | 2020-02-04 08:43 | Section 4 | Material | Not on List | Not on List | 10 | rolls | 111.59 | 1115.9 | Miscellaneous | 2020-02-06 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28857-001025 | 28857 | 2020-02-04 17:41 | Section 4 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Fixings and Fasteners | 2020-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28866-001025 | 28866 | 2020-02-05 07:50 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-02-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 4 | Each | 53.01 | 212.04 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28868-001025 | 28868 | 2020-02-05 08:27 | Section 5 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Surveying Consumables | 2020-02-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 110 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 70 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 10 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 8 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 4 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 18 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 6 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 400 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 400 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 4 | Each | 36.62 | 146.48 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 2 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 7 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 12 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 1 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 2 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 2 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 270 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 170 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 1 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 1 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 4 | Each | 59.17 | 236.68 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28875-001025 | 28875 | 2020-02-05 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-28852-001025 | 28852 | 2020-02-04 15:59 | Section 3 | Material | Not on List | Not on List | 120 | m3 | 88.2 | 10584 | Ready Mixed Concrete | 2020-02-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28852-001025 | 28852 | 2020-02-04 15:59 | Section 3 | Material | Not on List | Not on List | 600 | m3 | 106.99 | 64194 | Ready Mixed Concrete | 2020-02-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28852-001025 | 28852 | 2020-02-04 15:59 | Section 3 | Material | Not on List | Not on List | 170 | m3 | 107.76 | 18319.2 | Ready Mixed Concrete | 2020-02-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 25 | Each | 221.73 | 5543.25 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 25 | Each | 275.7 | 6892.5 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 25 | Each | 287.25 | 7181.25 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 25 | Each | 190.83 | 4770.75 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 10 | Each | 44.17 | 441.7 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 4 | Each | 43.12 | 172.48 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 22 | Each | 67.9 | 1493.8 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 4 | Each | 43.12 | 172.48 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 40 | Each | 50.69 | 2027.6 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 11 | Each | 75.46 | 830.06 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | NULL | NULL | 5 | Each | 158.78 | 793.9 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28195-001025 | 28195 | 2020-01-15 16:34 | Section 2 | Material | Not on List | Not on List | 1 | ea | 515.2 | 515 | Professional Services | 2019-11-29 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28291-001025 | 28291 | 2020-01-17 14:50 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28884-001025 | 28884 | 2020-02-05 15:53 | Section 4 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 8300 | Each | 1.5 | 12450 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28896-001025 | 28896 | 2020-02-05 08:51 | Section 4 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2020-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyers - Stores Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28982 | 28982 | 2020-02-07 12:26 | Test Section | Material Requisition | Aggregate | A10 Pipe Bed | 54645 | Tonnes | 16.5 | 901642.5 | Blocks and Bricks | 2020-02-28 | Test Location | Test Section | Test Section | Buyer - Closed | Yes - Approve | Yes - Approve | Chris Henry
MREQ-28991 | 28991 | 2020-02-07 13:12 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 80 | 80 | Miscellaneous | 2020-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-29005 | 29005 | 2020-02-07 15:29 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 8 | No | 41 | 328 | Laboratory Equipment / Certification | 2020-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29027 | 29027 | 2020-02-10 11:09 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 133.35 | 133.35 | Professional Services | 2020-02-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29030 | 29030 | 2020-02-10 12:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 67.23 | 67.23 | Professional Services | 2020-02-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29035 | 29035 | 2020-02-10 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 137.5 | 137.5 | Professional Services | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29035 | 29035 | 2020-02-10 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 61.53 | 61.53 | Small Tools (Consumables) | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29035 | 29035 | 2020-02-10 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 4 | No | 13.8 | 55.2 | Small Tools (Consumables) | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29035 | 29035 | 2020-02-10 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 6 | No | 44.46 | 266.76 | Small Tools (Consumables) | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 15 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 5 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29039 | 29039 | 2020-02-10 16:26 | Section 5 | Material Requisition | Aggregate | A40 Pipe Bed | 100 | Tonnes | 20.95 | 2095 | Aggregate | 2020-02-12 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29041 | 29041 | 2020-02-10 10:14 | Section 2 | Material Requisition | Concrete Drainage | Not on List
1 | each | NULL | 0 | Flow Control | 2020-02-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29041 | REQ - Finance Team | NULL | NULL
MREQ-29043 | 29043 | 2020-02-10 16:45 | Section 2 | Material Requisition | Not on List | Not on List | 5 | Each | 78.5 | 392.5 | Builders Merchants (General) | 2020-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-29064 | 29064 | 2020-02-11 08:36 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 159 | 159 | Surveying Consumables | 2020-02-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-29064 | 29064 | 2020-02-11 08:36 | Core | Material Requisition | Not on List | Not on List | 2 | No. | 150 | 300 | Surveying Consumables | 2020-02-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-29064 | 29064 | 2020-02-11 08:36 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 159 | 159 | Surveying Consumables | 2020-02-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-29065 | 29065 | 2020-02-11 09:00 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 7500 | 7500 | Miscellaneous | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29080 | 29080 | 2020-02-11 14:06 | Section 6 | Material Requisition | Not on List | Not on List
2 | ea | 6.75 | 13.5 | Builders Merchants (General) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 136290 | NULL | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29080 | REQ - Finance Team | NULL | NULL
MREQ-29080 | 29080 | 2020-02-11 14:06 | Section 6 | Material Requisition | Not on List | Not on List | 25 | ea | 2.07 | 51.75 | Builders Merchants (General) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29081 | 29081 | 2020-02-11 14:08 | Section 4 | Material Requisition | Geotextile | Not on List | 80 | Linear M | 26.5 | 2120 | Geotextiles | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29081 | 29081 | 2020-02-11 14:08 | Section 4 | Material Requisition | Geotextile | Not on List | 240 | Each | 0.3 | 72 | Geotextiles | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29081 | 29081 | 2020-02-11 14:08 | Section 4 | Material Requisition | Geotextile | Not on List | 1 | Each | 215 | 215 | Geotextiles | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29084 | 29084 | 2020-02-11 14:32 | Section 6 | Material Requisition | Misc | Not on List | 2 | 0 | 0 | 0 | Small Tools (Consumables) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29084 | 29084 | 2020-02-11 14:32 | Section 6 | Material Requisition | Misc | Not on List | 25 | 0 | 0 | 0 | Small Tools (Consumables) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29086 | 29086 | 2020-02-11 14:45 | Section 6 | Material Requisition | Misc | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | IMO Queue | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29086 | 29086 | 2020-02-11 14:45 | Section 6 | Material Requisition | Misc | Not on List | 25 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | IMO Queue | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29092 | 29092 | 2020-02-11 16:14 | Section 4 | Material Requisition | Geotextile | Not on List | 80 | Linear M | 26.5 | 2120 | Geotextiles | 2020-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29092 | 29092 | 2020-02-11 16:14 | Section 4 | Material Requisition | Geotextile | Not on List | 240 | Each | 0.3 | 72 | Geotextiles | 2020-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29092 | 29092 | 2020-02-11 16:14 | Section 4 | Material Requisition | Geotextile | Not on List | 1 | Each | 215 | 215 | Geotextiles | 2020-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29097 | 29097 | 2020-02-11 16:40 | Section 2 | Material Requisition | Hazardous Waste | Not on List | 1 | Quantity | 1740.84 | 1740.84 | Waste (General) | 2020-02-28 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Passed Back | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-29100 | 29100 | 2020-02-11 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 5 | Each | 75.46 | 377.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29100 | 29100 | 2020-02-11 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 5 | Each | 75.46 | 377.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29100 | 29100 | 2020-02-11 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29100 | 29100 | 2020-02-11 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 3 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29100 | 29100 | 2020-02-11 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 3 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29121 | 29121 | 2020-02-12 09:21 | Section 5 | Material Requisition | Linear Drainage | Not on List | 34 | Each | 9.45 | 321.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-18 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29121 | 29121 | 2020-02-12 09:21 | Section 5 | Material Requisition | Linear Drainage | Not on List | 17 | Each | 23.48 | 399.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-18 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 1222.09 | 1222.09 | Concrete Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 8 | Each | 26.79 | 214.32 | Plastic Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 10 | Each | 37.13 | 371.3 | Plastic Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 10 | Each | 62.47 | 624.7 | Plastic Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 6 | Each | 83.09 | 498.54 | Plastic Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 4 | Each | 89.6 | 358.4 | Plastic Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29138 | 29138 | 2020-02-12 13:39 | Section 4 | Material Requisition | Kerbs | Not on List | 100 | Each | 22.84 | 2284 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29138 | 29138 | 2020-02-12 13:39 | Section 4 | Material Requisition | Kerbs | Not on List | 100 | Each | 24.09 | 2409 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29142 | 29142 | 2020-02-12 14:18 | Section 3 | Material Requisition | Hazardous Waste | Not on List | 1 | batch | 3591 | 3591 | Miscellaneous | 2020-02-28 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-29143 | 29143 | 2020-02-12 14:32 | Section 2 | Material Requisition | Hazardous Waste | Not on List | 1 | Batch | 2850 | 2850 | Waste (General) | 2020-02-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29143 | 29143 | 2020-02-12 14:32 | Section 2 | Material Requisition | Hazardous Waste | Not on List | 1 | Batch | 2550 | 2550 | Waste (General) | 2020-02-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29143 | 29143 | 2020-02-12 14:32 | Section 2 | Material Requisition | Hazardous Waste | Not on List | 1 | Batch | 6650 | 6650 | Waste (General) | 2020-02-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29168 | 29168 | 2020-02-13 09:15 | Section 2 | Material Requisition | Not on List | Not on List | 5 | each | 78.5 | 392.5 | Builders Merchants (General) | 2020-02-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC1 - Roadworks | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29169 | 29169 | 2020-02-13 09:18 | Section 2 | Material Requisition | Concrete Drainage | Not on List
1 | Each | NULL | 0 | Concrete Drainage | 2020-02-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13642 | Keyline Builders Merchants Ltd (1100980) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29169 | REQ - Finance Team | NULL | NULL
MREQ-29171 | 29171 | 2020-02-13 09:01 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | consignment | 904.78 | 904.78 | Waste (General) | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29171 | 29171 | 2020-02-13 09:01 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | consignment | 776.78 | 776.78 | Waste (General) | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29172 | 29172 | 2020-02-13 09:39 | Section 3 | Material Requisition | Hazardous Waste | Not on List | 1 | Consignment | 4909.16 | 4909.16 | Waste (General) | 2020-02-28 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 587.88 | 587.88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 130 | 130 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 289.12 | 289.12 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 50 | 50 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 1927.14 | 1927.14 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 50 | 50 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 50 | 50 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 308.2 | 308.2 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 290 | 290 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29186 | 29186 | 2020-02-13 14:23 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 1000 | 1000 | Professional Services | 2020-02-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29187 | 29187 | 2020-02-13 14:34 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 230 | 230 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-29187 | 29187 | 2020-02-13 14:34 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 135 | 135 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-29188 | 29188 | 2020-02-13 14:46 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 47.16 | 47.16 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29188 | 29188 | 2020-02-13 14:46 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 60 | 60 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29206 | 29206 | 2020-02-13 18:03 | Section 4 | Material Requisition | Not on List | Not on List
2 | Each | 70.18 | 140.36 | Ductile Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | Caulfield | 13652 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29206 | REQ - Finance Team | NULL | NULL
MREQ-29206 | 29206 | 2020-02-13 18:03 | Section 4 | Material Requisition | Not on List | Not on List | 46 | Lengths | 14.98 | 689.08 | Fixings and Fasteners | 2020-02-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29216 | 29216 | 2020-02-14 08:04 | Section 4 | Material Requisition | Not on List | Not on List | 120 | Each | 42.96 | 5155.2 | Miscellaneous | 2020-02-19 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29216 | 29216 | 2020-02-14 08:04 | Section 4 | Material Requisition | Not on List | Not on List | 480 | Each | 1.41 | 676.8 | Miscellaneous | 2020-02-19 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29217 | 29217 | 2020-02-14 08:48 | Section 5 | Material Requisition | Aggregate | Not on List | 20376.77 | Tonne | 5.5 | 112072.24 | Aggregate | 2020-02-14 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29221 | 29221 | 2020-02-14 10:10 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 87.99 | 87.99 | Professional Services | 2020-02-28 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | Req - S1 Buyers
MREQ-29223 | 29223 | 2020-02-14 10:20 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 167.82 | 167.82 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29223 | 29223 | 2020-02-14 10:20 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 660.2 | 660.2 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29223 | 29223 | 2020-02-14 10:20 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 175.33 | 175.33 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29223 | 29223 | 2020-02-14 10:20 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 167.88 | 167.88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29226 | 29226 | 2020-02-14 11:34 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 81.41 | 81.41 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29227 | 29227 | 2020-02-14 11:35 | Core | Material Requisition | Not on List | Not on List | 1 | no. | 159 | 159 | Surveying Consumables | 2020-02-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29227 | 29227 | 2020-02-14 11:35 | Core | Material Requisition | Not on List | Not on List | 1 | no. | 159 | 159 | Surveying Consumables | 2020-02-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29227 | 29227 | 2020-02-14 11:35 | Core | Material Requisition | Not on List | Not on List | 2 | no. | 150 | 300 | Surveying Consumables | 2020-02-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29260 | 29260 | 2020-02-17 09:32 | Section 4 | Material Requisition | Not on List | Not on List | 300 | NULL | NULL | 0 | Miscellaneous | 2020-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29285 | 29285 | 2020-02-17 18:22 | Section 2 | Material Requisition | Hazardous Waste | Packaging waste containing residues** - 820L w/bin | 1 | Each | 2392 | 2392 | Waste (General) | 2020-02-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29286 | 29286 | 2020-02-17 19:41 | Section 4 | Material Requisition | Not on List | Not on List | 12 | Each | 10.85 | 130.2 | Fixings and Fasteners | 2020-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29286 | 29286 | 2020-02-17 19:41 | Section 4 | Material Requisition | Not on List | Not on List | 12 | Each | 3.35 | 40.2 | Fixings and Fasteners | 2020-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29294 | 29294 | 2020-02-18 09:44 | Section 4 | Material Requisition | Kerbs | Not on List | 350 | NULL | 24.09 | 8431.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29295 | 29295 | 2020-02-18 09:41 | Core | Material Requisition | Not on List | Not on List | 1 | Number | 3000 | 3000 | Surveying Consumables | 2020-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29296 | 29296 | 2020-02-18 09:57 | Section 2 | Material Requisition | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2020-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29297 | 29297 | 2020-02-18 09:59 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Number | 40 | 120 | Surveying Consumables | 2020-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29301 | 29301 | 2020-02-18 10:43 | Core | Material Requisition | Not on List | Not on List | 3 | ea | 552.68 | 1658.04 | Office Supplies | 2020-02-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 56 | Each | 130.26 | 7294.56 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 75 | Each | 9.76 | 732 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Each | 18.84 | 376.8 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 47 | Each | 125.94 | 5919.18 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 65 | Each | 10.04 | 652.6 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Each | 18.87 | 377.4 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29314 | 29314 | 2020-02-18 12:46 | Section 6 | Material Requisition | Not on List | Not on List | 1 | NULL | 500 | 500 | Miscellaneous | 2020-03-02 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29322 | 29322 | 2020-02-18 14:28 | Section 4 | Material Requisition | Linear Drainage | Not on List | 2 | Each | 543.04 | 1086.08 | Concrete Drainage | 2020-03-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29326 | 29326 | 2020-02-18 15:27 | Core | Material Requisition | Not on List | Not on List | 1 | number | 1320 | 1320 | Miscellaneous | 2020-02-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29352 | 29352 | 2020-02-19 09:40 | Section 6 | Material Requisition | Concrete Drainage | CPM 600mm Concrete Pipe 2.5m (249353) | 13 | Each | 148.8 | 1934.4 | Concrete Drainage | 2020-02-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29352 | 29352 | 2020-02-19 09:40 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 10 | Boxes | 50.54 | 505.4 | Concrete Drainage | 2020-02-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29353 | 29353 | 2020-02-19 10:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 167.82 | 167.82 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29353 | 29353 | 2020-02-19 10:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 660.2 | 660.2 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29353 | 29353 | 2020-02-19 10:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 175.33 | 175.33 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29353 | 29353 | 2020-02-19 10:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 167.88 | 167.88 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29356 | 29356 | 2020-02-19 12:36 | Section 4 | Material Requisition | Kerbs | Not on List | 550 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29364 | 29364 | 2020-02-19 14:56 | Section 4 | Material Requisition | Not on List | Not on List
160 | tonnes | 19.5 | 3120 | Aggregate | 2020-02-25 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | A14 IDT | 13682 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29364 | REQ - Finance Team | NULL | NULL
MREQ-29368 | 29368 | 2020-02-19 15:58 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-02-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29369 | 29369 | 2020-02-19 16:00 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 143.91 | 143.91 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29371 | 29371 | 2020-02-19 16:34 | Section 4 | Material Requisition | Misc | Not on List | 1 | No | 518.45 | 518.45 | Small Tools (Consumables) | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29371 | 29371 | 2020-02-19 16:34 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 84 | 84 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29376 | 29376 | 2020-02-19 17:42 | Section 4 | Material Requisition | Misc | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29383 | 29383 | 2020-02-20 08:04 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 38 | each | 10.98 | 417.24 | Builders Merchants (General) | 2020-02-21 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29389 | 29389 | 2020-02-20 09:03 | Section 2 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 30 | Each | 4.59 | 137.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29402 | 29402 | 2020-02-20 12:21 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | NULL | 384.4 | 3844 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29403 | 29403 | 2020-02-20 12:45 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 391.5 | 391.5 | Concrete Drainage | 2020-03-06 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29403 | 29403 | 2020-02-20 12:45 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 442.2 | 442.2 | Concrete Drainage | 2020-03-06 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29403 | 29403 | 2020-02-20 12:45 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 442.2 | 442.2 | Concrete Drainage | 2020-03-06 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29403 | 29403 | 2020-02-20 12:45 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 510.3 | 510.3 | Concrete Drainage | 2020-03-06 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29403 | 29403 | 2020-02-20 12:45 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 529.1 | 529.1 | Concrete Drainage | 2020-03-06 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29404 | 29404 | 2020-02-20 12:49 | Section 2 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 442.2 | 442.2 | Concrete Drainage | 2020-03-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29408 | 29408 | 2020-02-20 12:51 | Section 6 | Material Requisition | Not on List | Not on List | 57 | Meters | 362 | 20634 | Concrete Drainage | 2020-03-06 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29408 | 29408 | 2020-02-20 12:51 | Section 6 | Material Requisition | Not on List | Not on List | 4 | no | 40.76 | 163.04 | Concrete Drainage | 2020-03-06 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29408 | 29408 | 2020-02-20 12:51 | Section 6 | Material Requisition | Not on List | Not on List | 4 | no | 407.64 | 1630.56 | Concrete Drainage | 2020-03-06 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29408 | 29408 | 2020-02-20 12:51 | Section 6 | Material Requisition | Not on List | Not on List | 4 | no | 996.45 | 3985.8 | Concrete Drainage | 2020-03-06 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29434 | 29434 | 2020-02-21 07:12 | Section 6 | Material Requisition | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1157.8 | Geotextiles | 2020-02-28 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29441 | 29441 | 2020-02-21 07:34 | Section 5 | Material Requisition | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 4 | Price Per Thousand | 345 | 1380 | Blocks and Bricks | 2020-02-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29441 | 29441 | 2020-02-21 07:34 | Section 5 | Material Requisition | Bagged | Building Sand 25kg Bag (996239) | 8 | Each | 1.8 | 14.4 | Aggregate | 2020-02-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29441 | 29441 | 2020-02-21 07:34 | Section 5 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 1 | Pallet | 3.56 | 3.56 | Aggregate | 2020-02-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29441 | 29441 | 2020-02-21 07:34 | Section 5 | Material Requisition | Bagged | Post Mix 25kg (348099) | 1 | Pallet | 3.45 | 3.45 | Aggregate | 2020-02-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29448 | 29448 | 2020-02-21 09:14 | Section 2 | Material Requisition | PPE, Small Tools and Consumables | Not on List
1 | NULL | NULL | 0 | Miscellaneous | 2020-02-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13676 | Ashtead Plant Hire Company Ltd (1109463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ29448/Request/Quote_3605776.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29448 | REQ - Finance Team | NULL | NULL
MREQ-29450 | 29450 | 2020-02-21 09:38 | Section 3 | Material Requisition | PPE, Small Tools and Consumables | Not on List
1 | NULL | NULL | 0 | Miscellaneous | 2020-02-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13675 | Ashtead Plant Hire Company Ltd (1109463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ29450/Request/Quote_3605776.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29450 | REQ - Finance Team | NULL | NULL
MREQ-29461 | 29461 | 2020-02-21 11:30 | Section 4 | Material Requisition | Not on List | Not on List | 50 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29461 | 29461 | 2020-02-21 11:30 | Section 4 | Material Requisition | Not on List | Not on List | 50 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29461 | 29461 | 2020-02-21 11:30 | Section 4 | Material Requisition | Not on List | Not on List | 50 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29463 | 29463 | 2020-02-21 12:13 | Section 4 | Material Requisition | Not on List | Not on List | 134 | Each | 14.43 | 1933.62 | Builders Merchants (General) | 2020-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29463 | 29463 | 2020-02-21 12:13 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 1200 | 1200 | Builders Merchants (General) | 2020-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29469 | 29469 | 2020-02-21 13:04 | Section 4 | Material Requisition | Kerbs | Not on List | 300 | Each | 5.17 | 1551 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29469 | 29469 | 2020-02-21 13:04 | Section 4 | Material Requisition | Bagged | Not on List | 5 | Each | 33.55 | 167.75 | Builders Merchants (General) | 2020-02-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29491 | 29491 | 2020-02-24 11:07 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No. | 1028 | 1028 | Miscellaneous | 2020-02-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29502 | 29502 | 2020-02-24 16:43 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 151.5 | 151.5 | Miscellaneous | 2020-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29507 | 29507 | 2020-02-24 17:44 | Section 4 | Material Requisition | Aggregate | 6F5 | 50 | Load | 310 | 15500 | Aggregate | 2020-02-26 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 184 | Each | 30.16 | 5549.44 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 93 | Each | 22.84 | 2124.12 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 2 | Each | 16.88 | 33.76 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 8 | Each | 282.24 | 2257.92 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 2 | Each | 311.1 | 622.2 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 1 | Each | 35.47 | 35.47 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | Each | 59.26 | 592.6 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29532 | 29532 | 2020-02-25 14:02 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Number | 40 | 120 | Surveying Consumables | 2020-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29533 | 29533 | 2020-02-25 14:08 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 4580.4 | 4580.4 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29534 | 29534 | 2020-02-25 14:42 | Section 4 | Material Requisition | Not on List | Not on List | 30 | boxes | NULL | 0 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1202 - Road Markings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29536 | 29536 | 2020-02-25 14:39 | Section 4 | Material Requisition | Not on List | Not on List | 5 | Each | 111.59 | 557.95 | Miscellaneous | 2020-02-28 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29563 | 29563 | 2020-02-26 09:17 | Section 4 | Material Requisition | Kerbs | Not on List | 3 | Each | 75.46 | 226.38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29563 | 29563 | 2020-02-26 09:17 | Section 4 | Material Requisition | Kerbs | Not on List | 3 | Each | 75.46 | 226.38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29571 | 29571 | 2020-02-26 12:01 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 224.25 | 224.25 | Professional Services | 2020-02-28 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29571 | 29571 | 2020-02-26 12:01 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 358 | 358 | Professional Services | 2020-02-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29571 | 29571 | 2020-02-26 12:01 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 448.5 | 448.5 | Professional Services | 2020-02-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29571 | 29571 | 2020-02-26 12:01 | Section 2 | Material Requisition | Not on List | Not on List | 1 | N0 | 89.7 | 89.7 | Professional Services | 2020-02-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29572 | 29572 | 2020-02-26 13:15 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 241.5 | 241.5 | Professional Services | 2020-02-28 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29572 | 29572 | 2020-02-26 13:15 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-02-28 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29572 | 29572 | 2020-02-26 13:15 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 106.95 | 106.95 | Professional Services | 2020-02-28 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29574 | 29574 | 2020-02-26 13:48 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-02-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29579 | 29579 | 2020-02-26 15:07 | Section 4 | Material Requisition | Kerbs | Not on List | 30 | Each | 26.38 | 791.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29582 | 29582 | 2020-02-26 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 64 | Each | 4.75 | 304 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29588 | 29588 | 2020-02-26 17:30 | Section 2 | Material Requisition | Plastic Drainage | Not on List
2 | NULL | NULL | 0 | Plastic Drainage | 2020-03-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | Skyland Contractors Ltd | OP 13724 | Keyline Builders Merchants Ltd (1100980) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29588 | REQ - Finance Team | NULL | NULL
MREQ-29588 | 29588 | 2020-02-26 17:30 | Section 2 | Material Requisition | Plastic Drainage | Not on List
2 | NULL | NULL | 0 | Plastic Drainage | 2020-03-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | Skyland Contractors Ltd | OP 13724 | Keyline Builders Merchants Ltd (1100980) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29588 | REQ - Finance Team | NULL | NULL
MREQ-29588 | 29588 | 2020-02-26 17:30 | Section 2 | Material Requisition | Plastic Drainage | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2020-03-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 45 | No | 11.93 | 536.85 | Plastic Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 25 | No | 2.08 | 52 | Plastic Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 45 | No | 0.95 | 42.75 | Plastic Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 22 | No | 176.27 | 3877.94 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 40 | No | 17.23 | 689.2 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 35 | No | 7.43 | 260.05 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 36 | No | 84.83 | 3053.88 | Ductile Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 112.58 | 337.74 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 26 | No | 51.49 | 1338.74 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 60 | No | 18.08 | 1084.8 | Concrete Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 12 | No | 156.53 | 1878.36 | Concrete Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 34 | No | 17.85 | 606.9 | Plastic Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 55 | No | 4.9 | 269.5 | Plastic Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 12 | No | 156.63 | 1879.56 | Concrete Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 187.49 | 187.49 | Concrete Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 187.49 | 187.49 | Concrete Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29598 | 29598 | 2020-02-27 09:11 | Section 5 | Material Requisition | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 20 | Each | 74.3 | 1486 | Ductile Drainage | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29603 | 29603 | 2020-02-27 10:48 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 21.25 | 42.5 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29603 | 29603 | 2020-02-27 10:48 | Section 4 | Material Requisition | Not on List | Not on List | 4 | Each | 9.09 | 36.36 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29604 | 29604 | 2020-02-27 11:00 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 10.06 | 20.12 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29604 | 29604 | 2020-02-27 11:00 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 6.91 | 13.82 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29624 | 29624 | 2020-02-27 13:06 | Section 5 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 21.25 | 4250 | Aggregate | 2020-02-27 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29633 | 29633 | 2020-02-27 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 12 | no | NULL | 0 | Flow Control | 2020-03-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29633 | 29633 | 2020-02-27 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 16 | no | 0.11 | 1.76 | Flow Control | 2020-03-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29633 | 29633 | 2020-02-27 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 1 | no | 1939.13 | 1939.13 | Flow Control | 2020-03-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29644 | 29644 | 2020-02-27 12:10 | Section 4 | Material Requisition | Not on List | Not on List | 18 | Each | NULL | 0 | Plastic Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29644 | 29644 | 2020-02-27 12:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29644 | 29644 | 2020-02-27 12:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29644 | 29644 | 2020-02-27 12:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29644 | 29644 | 2020-02-27 12:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29677 | 29677 | 2020-02-28 09:45 | Section 2 | Material Requisition | Misc | Not on List
1 | NULL | NULL | 0 | Miscellaneous | 2020-03-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13728 | Gap Group Ltd (1108091) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29677 | REQ - Finance Team | NULL | NULL
MREQ-29678 | 29678 | 2020-02-28 09:56 | Section 2 | Material Requisition | Misc | Not on List
1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-03-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13729 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29678 | REQ - Finance Team | NULL | NULL
MREQ-29680 | 29680 | 2020-02-28 10:21 | Section 3 | Material Requisition | PPE, Small Tools and Consumables | Rope Blue Polypropylene 6mm X 500m (approx)on Drum (746415) | 10 | Each | 25.13 | 251.3 | Plastic Drainage | 2020-03-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 1103 - Linear Drainage Channel Systems | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-29686 | 29686 | 2020-02-28 12:30 | Section 5 | Material Requisition | Not on List | Not on List
2 | Each | 875 | 1750 | Ductile Drainage | 2020-03-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 13740 | Fowler & Holden Ltd (1204843) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29686 | REQ - Finance Team | NULL | NULL
MREQ-29702 | 29702 | 2020-02-28 15:54 | Section 5 | Material Requisition | Aggregate | Not on List | 220 | tonnes | NULL | 0 | Aggregate | 2020-03-03 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-29735 | 29735 | 2020-03-02 14:43 | Section 4 | Material Requisition | Not on List | Not on List | 160 | rolls | NULL | 0 | Miscellaneous | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29735 | 29735 | 2020-03-02 14:43 | Section 4 | Material Requisition | Not on List | Not on List
1500 | each | NULL | 0 | Surveying Consumables | 2020-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | op 13741 | SCCS Survey Equipment Ltd t/a (1101886) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29735 | REQ - Finance Team | NULL | NULL
MREQ-29736 | 29736 | 2020-03-02 15:00 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 13125 | 13125 | Training | 2020-03-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29736 | 29736 | 2020-03-02 15:00 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 790 | 790 | Training | 2020-03-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29770 | 29770 | 2020-03-03 15:50 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Each | 28.8 | 576 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29770 | 29770 | 2020-03-03 15:50 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Each | 43.14 | 862.8 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29770 | 29770 | 2020-03-03 15:50 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Each | 64.35 | 1287 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29770 | 29770 | 2020-03-03 15:50 | Section 4 | Material Requisition | Not on List | Not on List | 30 | Each | 82.29 | 2468.7 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29770 | 29770 | 2020-03-03 15:50 | Section 4 | Material Requisition | Not on List | Not on List | 25 | Each | 87.96 | 2199 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Ea | 715 | 715 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Ea | 352 | 352 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Ea | 594 | 594 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Ea | 1386 | 1386 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Ea | 880 | 880 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List
1 | Ea | 189.75 | 189.75 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13751 | Speedy Asset Services Ltd (1241805) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29771 | REQ - Finance Team | NULL | NULL
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List
1 | Ea | 4580.4 | 4580.4 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13751 | Speedy Asset Services Ltd (1241805) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29771 | REQ - Finance Team | NULL | NULL
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 32 | Each | 132.56 | 4241.92 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 11 | Each | 47.7 | 524.7 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 5 | Each | 117.93 | 589.65 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 14 | Each | 39.57 | 553.98 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 9 | Each | 180.45 | 1624.05 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 15 | Each | 8.68 | 130.2 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 18 | Each | 8.68 | 156.24 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 28 | Each | 8.68 | 243.04 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 4 | Each | 189.2 | 756.8 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29791 | 29791 | 2020-03-04 09:23 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 1085 | 1085 | Fixings and Fasteners | 2020-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29792 | 29792 | 2020-03-04 10:39 | Section 4 | Material Requisition | Kerbs | Not on List | 1200 | Each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29795 | 29795 | 2020-03-04 11:38 | Section 4 | Material Requisition | Not on List | Not on List | 60 | Each | 42.96 | 2577.6 | Miscellaneous | 2020-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29795 | 29795 | 2020-03-04 11:38 | Section 4 | Material Requisition | Not on List | Not on List | 50 | Each | 1.41 | 70.5 | Miscellaneous | 2020-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29796 | 29796 | 2020-03-04 12:29 | Section 4 | Material Requisition | Kerbs | Not on List | 400 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyers Passed Back to Requestor | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29796 | 29796 | 2020-03-04 12:29 | Section 4 | Material Requisition | Kerbs | Not on List | 400 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyers Passed Back to Requestor | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29797 | 29797 | 2020-03-04 13:08 | Section 6 | Material Requisition | Timber | Not on List | 240 | meters | 6.3 | 1512 | Timber Products | 2020-03-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29797 | 29797 | 2020-03-04 13:08 | Section 6 | Material Requisition | Not on List | Not on List | 2 | rolls | 103.17 | 206.34 | Miscellaneous | 2020-03-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29798 | 29798 | 2020-03-04 10:26 | Section 4 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2020-03-05 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 701 - Sub-base | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29798 | 29798 | 2020-03-04 10:26 | Section 4 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2020-03-06 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 701 - Sub-base | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29798 | 29798 | 2020-03-04 10:26 | Section 4 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2020-03-09 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 701 - Sub-base | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29798 | 29798 | 2020-03-04 10:26 | Section 4 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2020-03-10 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 701 - Sub-base | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 12 | Each | 147.21 | 1766.52 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 32.7 | 65.4 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 146.95 | 146.95 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 40.4 | 40.4 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 20.2 | 20.2 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 30 | Each | 115 | 3450 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 50 | 50 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 188 | 188 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 257.28 | 257.28 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NO | 88 | 88 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 195 | 195 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29822 | 29822 | 2020-03-04 23:43 | Section 5 | Material Requisition | Kerbs | Not on List | 2 | number | 650 | 1300 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29832 | 29832 | 2020-03-05 08:51 | Section 4 | Material Requisition | Kerbs | Not on List | 200 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyers Passed Back to Requestor | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29855 | 29855 | 2020-03-05 14:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29855 | 29855 | 2020-03-05 14:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 233.5 | 233.5 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29874 | 29874 | 2020-03-06 08:01 | Section 5 | Material Requisition | Bagged | Post Mix 25kg (348099) | 1 | Pallet | 3.45 | 3.45 | Builders Merchants (General) | 2020-03-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29877 | 29877 | 2020-03-06 08:01 | Section 6 | Material Requisition | Twinwall | Not on List | 10 | no | NULL | 0 | Ductile Drainage | 2020-03-16 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29877 | 29877 | 2020-03-06 08:01 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 200 | meters | NULL | 0 | Ductile Drainage | 2020-03-16 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 37.5 | 37.5 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 38.87 | 38.87 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 66.7 | 66.7 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 37.5 | 37.5 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 84.08 | 84.08 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 712.72 | 712.72 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | N0 | 36.21 | 36.21 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 145.26 | 145.26 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 367.49 | 367.49 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 332.27 | 332.27 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 937.5 | 937.5 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 38.87 | 38.87 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 357.81 | 357.81 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29886 | 29886 | 2020-03-06 11:42 | Section 4 | Material Requisition | Not on List | Not on List
8 | Each | 70.18 | 561.44 | Ductile Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | Caulfield | 13753 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29886 | REQ - Finance Team | NULL | NULL
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 66.7 | 66.7 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 43.45 | 43.45 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 112.1 | 112.1 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 242 | 242 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 141.9 | 141.9 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | NO | 172.41 | 172.41 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | NO | 84.06 | 84.06 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29894 | 29894 | 2020-03-06 14:00 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Each | 150.24 | 450.72 | Builders Merchants (General) | 2020-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29894 | 29894 | 2020-03-06 14:00 | Section 4 | Material Requisition | Not on List | Not on List | 4 | Each | 25.97 | 103.88 | Builders Merchants (General) | 2020-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29894 | 29894 | 2020-03-06 14:00 | Section 4 | Material Requisition | Not on List | Not on List | 6 | Each | 14.4 | 86.4 | Builders Merchants (General) | 2020-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29894 | 29894 | 2020-03-06 14:00 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Each | 30.62 | 91.86 | Builders Merchants (General) | 2020-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29923 | 29923 | 2020-03-09 10:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29923 | 29923 | 2020-03-09 10:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29923 | 29923 | 2020-03-09 10:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29923 | 29923 | 2020-03-09 10:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29923 | 29923 | 2020-03-09 10:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29924 | 29924 | 2020-03-09 10:58 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 603.4 | 603.4 | Professional Services | 2020-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29926 | 29926 | 2020-03-09 11:10 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-29929 | 29929 | 2020-03-09 12:15 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 400 | Tonnes | 21.75 | 8700 | Aggregate | 2020-03-11 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29929 | 29929 | 2020-03-09 12:15 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 400 | Tonnes | 21.75 | 8700 | Aggregate | 2020-03-12 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29929 | 29929 | 2020-03-09 12:15 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 400 | Tonnes | 21.75 | 8700 | Aggregate | 2020-03-13 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29931 | 29931 | 2020-03-09 14:00 | Core | Material Requisition | Not on List | Not on List | 6 | NULL | 39 | 234 | Office Supplies | 2020-03-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29931 | 29931 | 2020-03-09 14:00 | Core | Material Requisition | Not on List | Not on List | 13 | NULL | 13.5 | 175.5 | Office Supplies | 2020-03-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29932 | 29932 | 2020-03-09 14:20 | Section 4 | Material Requisition | Not on List | Not on List
37 | NULL | NULL | 0 | Builders Merchants (General) | 2020-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13768 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ29932/Request/abus_41_series.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29932 | REQ - Finance Team | NULL | NULL
MREQ-29932 | 29932 | 2020-03-09 14:20 | Section 4 | Material Requisition | Not on List | Not on List | 30 | bags | NULL | 0 | Builders Merchants (General) | 2020-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29959 | 29959 | 2020-03-10 08:07 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2020-03-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29959 | 29959 | 2020-03-10 08:07 | Section 4 | Material Requisition | Not on List | Not on List | 10 | NULL | NULL | 0 | Builders Merchants (General) | 2020-03-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29970 | 29970 | 2020-03-10 11:58 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 23.16 | 23.16 | Miscellaneous | 2020-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29971 | 29971 | 2020-03-10 12:04 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | No | 44.17 | 441.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30005 | 30005 | 2020-03-11 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Nr | 9000 | 9000 | Miscellaneous | 2020-03-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30005 | 30005 | 2020-03-11 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Nr | 4400 | 4400 | Miscellaneous | 2020-03-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30005 | 30005 | 2020-03-11 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Nr | 8075 | 8075 | Miscellaneous | 2020-03-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30005 | 30005 | 2020-03-11 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Nr | 6800 | 6800 | Miscellaneous | 2020-03-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 704 | Each | 4.59 | 3231.36 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Transition Kerbs 125x255 (947297) | 1 | Each | 10.83 | 10.83 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Transition Kerbs 125x255 (947297) | 2 | Each | 10.08 | 20.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 1 | Each | 11.94 | 11.94 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 637 | Each | 3.52 | 2242.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 10 | Each | 7.68 | 76.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 11 | Each | 7.68 | 84.48 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 202 | Each | 1.61 | 325.22 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 53 | Each | 3.03 | 160.59 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 25 | Each | 5.43 | 135.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 17 | Each | 5.43 | 92.31 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Not on List | 12 | Each | 16.17 | 194.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 16 | m2 | 477.36 | 7637.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 35 | m2 | 1113.84 | 38984.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 75 | m2 | 2817.56 | 211317 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30018 | 30018 | 2020-03-11 13:06 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-03-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30018 | 30018 | 2020-03-11 13:06 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-03-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30018 | 30018 | 2020-03-11 13:06 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List
6 | NULL | NULL | 0 | PPE | 2020-03-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13769 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30018 | REQ - Finance Team | NULL | NULL
MREQ-30019 | 30019 | 2020-03-11 15:24 | Section 5 | Material Requisition | Aggregate | 6G | 178.54 | Tonnes | 32.9 | 5873.97 | Aggregate | 2020-03-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30023 | 30023 | 2020-03-11 15:07 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 2040.09 | 2040.09 | Tanks and Interceptors | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30023 | 30023 | 2020-03-11 15:07 | Section 3 | Material Requisition | Not on List | Not on List
8 | Hrs | 35 | 280 | Tanks and Interceptors | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | A14 IDT | OP 13781 | Selwood Ltd (1105450) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30023/Request/BRW12R2SRV001_BRW_Office_WHL06494_1760_001.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30023 | REQ - Finance Team | NULL | NULL
MREQ-30023 | 30023 | 2020-03-11 15:07 | Section 3 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 200 | 200 | Tanks and Interceptors | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30023 | 30023 | 2020-03-11 15:07 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 41.95 | 41.95 | Tanks and Interceptors | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30023 | 30023 | 2020-03-11 15:07 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 750 | 750 | Tanks and Interceptors | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30044 | 30044 | 2020-03-12 10:53 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 400 | Tonnes | 24.5 | 9800 | Aggregate | 2020-03-16 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30044 | 30044 | 2020-03-12 10:53 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 450 | Tonnes | 24.5 | 11025 | Aggregate | 2020-03-18 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30058 | 30058 | 2020-03-12 12:56 | Section 6 | Material Requisition | Aggregate | A20 Pipe Bed | 100 | Tonnes | 24.5 | 2450 | Aggregate | 2020-03-13 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30113 | 30113 | 2020-03-13 10:20 | Core | Material Requisition | Not on List | Not on List | 300 | NULL | NULL | 0 | Janitorial | 2020-03-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-30125 | 30125 | 2020-03-13 14:44 | Section 3 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 200 | Each | 2.84 | 568 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 2 | Each | 145 | 290 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 145 | 145 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 145 | 145 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 145 | 145 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 2 | Each | 235 | 470 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 235 | 235 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 235 | 235 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 235 | 235 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 235 | 235 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 415 | 415 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 1340 | 1340 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 1340 | 1340 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30174 | 30174 | 2020-03-16 12:16 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 950 | 950 | Miscellaneous | 2020-03-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-30175 | 30175 | 2020-03-16 12:52 | Section 2 | Material Requisition | Not on List | Not on List
1 | NULL | 109.43 | 109.43 | Office Supplies | 2020-03-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30175 | REQ - Finance Team | NULL | NULL
MREQ-30176 | 30176 | 2020-03-16 13:12 | Section 4 | Material Requisition | Not on List | Not on List | 100 | NULL | NULL | 0 | Builders Merchants (General) | 2020-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30179 | 30179 | 2020-03-16 14:36 | Section 5 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 1 | Each | 12.27 | 12.27 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-24 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30179 | 30179 | 2020-03-16 14:36 | Section 5 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 1 | Each | 12.27 | 12.27 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-24 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30179 | 30179 | 2020-03-16 14:36 | Section 5 | Material Requisition | Kerbs | Not on List | 6 | Number | 24.48 | 146.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-24 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30180 | 30180 | 2020-03-16 15:46 | Section 6 | Material Requisition | Misc | Not on List | 1 | each | 245 | 245 | Miscellaneous | 2020-03-18 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1507 - Testing & Commissioning | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-30181 | 30181 | 2020-03-16 15:52 | Section 6 | Material Requisition | Misc | Not on List | 1 | each | 105 | 105 | Miscellaneous | 2020-03-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1507 - Testing & Commissioning | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-30203 | 30203 | 2020-03-17 08:33 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 147.21 | 294.42 | Plastic Drainage | 2020-03-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30203 | 30203 | 2020-03-17 08:33 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 32.71 | 32.71 | Plastic Drainage | 2020-03-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30203 | 30203 | 2020-03-17 08:33 | Section 4 | Material Requisition | Not on List | Not on List | 40 | Each | 20.64 | 825.6 | Plastic Drainage | 2020-03-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30208 | 30208 | 2020-03-17 09:20 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 100 | 200 | Electrical | 2020-03-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30211 | 30211 | 2020-03-17 11:28 | Section 6 | Material Requisition | Not on List | Not on List | 100 | no. | 8 | 800 | Miscellaneous | 2020-03-27 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30225 | 30225 | 2020-03-17 16:51 | Section 6 | Material Requisition | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 6 | Each | 264.13 | 1584.78 | Concrete Drainage | 2020-03-18 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30247 | 30247 | 2020-03-18 09:11 | Section 5 | Material Requisition | Not on List | Not on List | 14 | No | 48.19 | 674.66 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30247 | 30247 | 2020-03-18 09:11 | Section 5 | Material Requisition | Not on List | Not on List | 37 | No | 48.19 | 1783.03 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30248 | 30248 | 2020-03-18 09:44 | Section 5 | Material Requisition | Not on List | Not on List | 5 | No | 32.4 | 162 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30248 | 30248 | 2020-03-18 09:44 | Section 5 | Material Requisition | Not on List | Not on List | 3 | No | 40.5 | 121.5 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 32 | Each | 78.67 | 2517.44 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 3 | Each | 51.56 | 154.68 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 12 | Each | 3.31 | 39.72 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 24 | Each | 1.63 | 39.12 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 30 | Each | 6.51 | 195.3 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 60 | Each | 3.36 | 201.6 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm Ridgidrain Bend 45deg (878031) | 3 | Each | 89.17 | 267.51 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm x 150mm Ridgidrain 45deg Junction (878038) | 3 | Each | 47.92 | 143.76 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm x 225mm Ridgdrain 45deg Junction (878042) | 3 | Each | 109.52 | 328.56 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 300mm Ridgidrain Bend 45deg (878085) | 2 | Each | 85.75 | 171.5 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Not on List | 1 | Each | 224.31 | 224.31 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Not on List | 5 | Each | 52.45 | 262.25 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Not on List | 3 | Each | 80.79 | 242.37 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Not on List | Not on List | 7 | Each | 156.72 | 1097.04 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30256 | 30256 | 2020-03-18 12:06 | Section 4 | Material Requisition | Not on List | Not on List | 28 | NULL | NULL | 0 | Plastic Drainage | 2020-03-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyers Passed Back to Requestor | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30256 | 30256 | 2020-03-18 12:06 | Section 4 | Material Requisition | Not on List | Not on List | 32 | NULL | NULL | 0 | Plastic Drainage | 2020-03-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyers Passed Back to Requestor | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30260 | 30260 | 2020-03-18 12:45 | Section 5 | Material Requisition | Bagged | Building Sand Bulk Bag (938155) | 8 | Each | 32.74 | 261.92 | Builders Merchants (General) | 2020-03-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30260 | 30260 | 2020-03-18 12:45 | Section 5 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 1 | Each | 3.56 | 3.56 | Builders Merchants (General) | 2020-03-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30260 | 30260 | 2020-03-18 12:45 | Section 5 | Material Requisition | Not on List | Building Sand Bulk Bag (938155) | 40 | Pallets | 32.74 | 1309.6 | Builders Merchants (General) | 2020-03-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30262 | 30262 | 2020-03-18 13:58 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 801.72 | 801.72 | Miscellaneous | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13833 | K Guard International Ltd (1340982) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30262 | REQ - Finance Team | NULL | NULL
MREQ-30271 | 30271 | 2020-03-18 15:10 | Section 4 | Material Requisition | Not on List | Not on List | 350 | Ea | 0.68 | 238 | Office Supplies | 2020-03-23 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30299 | 30299 | 2020-03-19 12:00 | Section 4 | Material Requisition | Not on List | Not on List | 26 | Each | 137.11 | 3564.86 | Plastic Drainage | 2020-03-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30299 | 30299 | 2020-03-19 12:00 | Section 4 | Material Requisition | Not on List | Not on List | 42 | Each | 132.56 | 5567.52 | Plastic Drainage | 2020-03-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30299 | 30299 | 2020-03-19 12:00 | Section 4 | Material Requisition | Not on List | Not on List | 10 | Each | 198.95 | 1989.5 | Plastic Drainage | 2020-03-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913)
10 | Each | 87.9 | 879 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | Skyland Contractors Ltd | 13836 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30341 | REQ - Finance Team | NULL | NULL
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 10 | Each | 58.03 | 580.3 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 1 | Each | 40.8 | 40.8 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 10 | Each | 64.76 | 647.6 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 26 | Each | 18.08 | 470.08 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Combined Drainage | Not on List | 10 | Each | 118.92 | 1189.2 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 39 | No | 33.98 | 1325.22 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 12 | No | 53.24 | 638.88 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 10 | No | 15.91 | 159.1 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 7 | Each | 45.12 | 315.84 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 4 | Each | 50.48 | 201.92 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 1 | Each | 44.98 | 44.98 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 1 | Each | 50.31 | 50.31 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 2 | ea | 12.29 | 24.58 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30348 | 30348 | 2020-03-20 16:57 | Core | Material Requisition | Misc | Not on List | 200 | No | 2.75 | 550 | Office Supplies | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-30373 | 30373 | 2020-03-23 14:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-03-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-30387 | 30387 | 2020-03-24 08:21 | Section 6 | Material Requisition | Aggregate | A20 Pipe Bed
200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-03-25 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 13818 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30387 | REQ - Finance Team | NULL | NULL
MREQ-30397 | 30397 | 2020-03-24 12:03 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 2142.8 | 2142.8 | Miscellaneous | 2020-03-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30418 | 30418 | 2020-03-24 17:57 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 57291.51 | 57291.51 | Miscellaneous | 2020-03-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30422 | 30422 | 2020-03-25 08:14 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 540.51 | 540.51 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30424 | 30424 | 2020-03-25 08:22 | Section 4 | Material Requisition | Aggregate | Type 1 | 10000 | Tonnes | 23.5 | 235000 | Aggregate | 2020-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30434 | 30434 | 2020-03-25 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 135 | 135 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30434 | 30434 | 2020-03-25 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30434 | 30434 | 2020-03-25 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 207 | 207 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30450 | 30450 | 2020-03-26 08:18 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 9000 | 9000 | Ductile Drainage | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30450 | 30450 | 2020-03-26 08:18 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 9000 | 9000 | Ductile Drainage | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30457 | 30457 | 2020-03-26 09:36 | Section 2 | Material Requisition | Misc | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-03-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-30461 | 30461 | 2020-03-26 10:56 | Section 4 | Material Requisition | Not on List | Not on List | 38 | Each | 84.83 | 3223.54 | Ductile Drainage | 2020-04-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30461 | 30461 | 2020-03-26 10:56 | Section 4 | Material Requisition | Not on List | Not on List | 80 | Each | 42.5 | 3400 | Concrete Drainage | 2020-04-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30466 | 30466 | 2020-03-26 13:16 | Section 3 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 450 | Each | 2.48 | 1116 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30476 | 30476 | 2020-03-26 14:30 | Section 4 | Material Requisition | Not on List | Not on List | 74 | Each | 13.29 | 983.46 | Builders Merchants (General) | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30487 | 30487 | 2020-03-27 07:20 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 50 | number | NULL | 0 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30487 | 30487 | 2020-03-27 07:20 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 32 | number | NULL | 0 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30487 | 30487 | 2020-03-27 07:20 | Section 4 | Material Requisition | Saint Gobain Castings | Not on List | 38 | number | NULL | 0 | Ductile Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30487 | 30487 | 2020-03-27 07:20 | Section 4 | Material Requisition | Saint Gobain Castings | Not on List | 12 | number | NULL | 0 | Ductile Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30487 | 30487 | 2020-03-27 07:20 | Section 4 | Material Requisition | Aggregate | Not on List | 20 | ton | 25 | 500 | Ductile Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30497 | 30497 | 2020-03-27 10:27 | Section 4 | Material Requisition | Not on List | Not on List | 50 | Each | 35.17 | 1758.5 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30497 | 30497 | 2020-03-27 10:27 | Section 4 | Material Requisition | Not on List | Not on List | 32 | Each | 21.76 | 696.32 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30497 | 30497 | 2020-03-27 10:27 | Section 4 | Material Requisition | Not on List | Not on List | 38 | Each | 34.86 | 1324.68 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30497 | 30497 | 2020-03-27 10:27 | Section 4 | Material Requisition | Not on List | Not on List | 12 | Each | 70.18 | 842.16 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30497 | 30497 | 2020-03-27 10:27 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Tonnes | NULL | 0 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30498 | 30498 | 2020-03-27 10:26 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 733.42 | 733.42 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30498 | 30498 | 2020-03-27 10:26 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30501 | 30501 | 2020-03-27 11:55 | Section 5 | Material Requisition | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 27 | Each | 42.5 | 1147.5 | Concrete Drainage | 2020-04-02 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30501 | 30501 | 2020-03-27 11:55 | Section 5 | Material Requisition | Linear Drainage | Not on List | 1 | Each | 332.63 | 332.63 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-02 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30506 | 30506 | 2020-03-27 14:20 | Section 4 | Material Requisition | Not on List | Not on List | 150 | NULL | NULL | 0 | PPE | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30506 | 30506 | 2020-03-27 14:20 | Section 4 | Material Requisition | Not on List | Not on List | 150 | NULL | NULL | 0 | PPE | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 85 | 85 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 114 | 114 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 72 | 72 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 103.5 | 103.5 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 97.95 | 97.95 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 0 | NULL | NULL | 0 | Professional Services | NaN-NaN-NaN NaN:NaN:NaN | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30511 | 30511 | 2020-03-27 15:35 | Section 5 | Material Requisition | Aggregate | A20 Pipe Bed | 100 | Tonnes | 21.25 | 2125 | Aggregate | 2020-03-31 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30514 | 30514 | 2020-03-27 16:33 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 2142.8 | 2142.8 | Miscellaneous | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30559 | 30559 | 2020-03-30 16:38 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 233.52 | 233.52 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13861 | P Flannery Plant Hire (Oval) L (1107945) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30559/Request/SKM_C284e20032009380 (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30559 | REQ - Finance Team | NULL | NULL
MREQ-30574 | 30574 | 2020-03-31 09:00 | Section 6 | Material Requisition | Not on List | Not on List | 30 | linier m | NULL | 0 | Concrete Accessories | 2020-04-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30574 | 30574 | 2020-03-31 09:00 | Section 6 | Material Requisition | Not on List | Not on List | 100 | ea | NULL | 0 | Concrete Accessories | 2020-04-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30574 | 30574 | 2020-03-31 09:00 | Section 6 | Material Requisition | Not on List | Not on List | 100 | ea | NULL | 0 | Concrete Accessories | 2020-04-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30574 | 30574 | 2020-03-31 09:00 | Section 6 | Material Requisition | Not on List | Not on List | 100 | ea | NULL | 0 | Concrete Accessories | 2020-04-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30574 | 30574 | 2020-03-31 09:00 | Section 6 | Material Requisition | Not on List | Not on List | 15 | ea | NULL | 0 | Concrete Accessories | 2020-04-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30579 | 30579 | 2020-03-31 15:41 | Section 4 | Material Requisition | Misc | Not on List | 1 | Box | NULL | 0 | Miscellaneous | 2020-04-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30581 | 30581 | 2020-03-31 12:11 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 132.25 | 132.25 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13855 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30581/Request/Mobile Job.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30581 | REQ - Finance Team | NULL | NULL
MREQ-30581 | 30581 | 2020-03-31 12:11 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 494.5 | 494.5 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13855 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30581 | REQ - Finance Team | NULL | NULL
MREQ-30581 | 30581 | 2020-03-31 12:11 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 109.25 | 109.25 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13855 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30581 | REQ - Finance Team | NULL | NULL
MREQ-30581 | 30581 | 2020-03-31 12:11 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 57.5 | 57.5 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13855 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30581 | REQ - Finance Team | NULL | NULL
MREQ-30581 | 30581 | 2020-03-31 12:11 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 83.37 | 83.37 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13855 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30581 | REQ - Finance Team | NULL | NULL
MREQ-30581 | 30581 | 2020-03-31 12:11 | Section 4 | Material Requisition | Not on List | Not on List | 81 | Ltrs | 0.8 | 64.8 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30595 | 30595 | 2020-04-01 09:20 | Section 5 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 1 | Pallet | 3.56 | 3.56 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30602 | 30602 | 2020-04-01 09:59 | Section 4 | Material Requisition | Not on List | Not on List
60 | boxes | 32.4 | 1944 | Builders Merchants (General) | 2020-04-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13853 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | Killgerm | /sites/BPM/FlowForma/FormDocuments/MREQ30602/Request/IM June 2018 BF contact.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30602 | REQ - Finance Team | NULL | NULL
MREQ-30602 | 30602 | 2020-04-01 09:59 | Section 4 | Material Requisition | Not on List | Not on List
12 | tube | 4.74 | 56.88 | Builders Merchants (General) | 2020-04-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13853 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | Killgerm | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30602 | REQ - Finance Team | NULL | NULL
MREQ-30603 | 30603 | 2020-04-01 10:19 | Core | Material Requisition | Not on List | Not on List | 1512 | No | 4.8 | 7257.6 | Miscellaneous | 2020-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-30608 | 30608 | 2020-04-01 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Roll | 243.25 | 729.75 | Geotextiles | 2020-04-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30609 | 30609 | 2020-04-01 14:13 | Section 4 | Material Requisition | Not on List | Not on List
5450 | No | 1 | 5450 | Miscellaneous | 2020-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13992 | Savills (UK) Ltd - Cambridge (1128665) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30609/Request/FW A14 - Trespass at Catch Hall Farm Buildings - Claim.msg | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30609 | REQ - Finance Team | NULL | NULL
MREQ-30622 | 30622 | 2020-04-01 16:00 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 97.95 | 97.95 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30622/Request/DOC110320-11032020093949.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
MREQ-30622 | 30622 | 2020-04-01 16:00 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 879.75 | 879.75 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
MREQ-30622 | 30622 | 2020-04-01 16:00 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 288.65 | 288.65 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
MREQ-30622 | 30622 | 2020-04-01 16:00 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 161.7 | 161.7 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
MREQ-30622 | 30622 | 2020-04-01 16:00 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 97.75 | 97.75 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
MREQ-30622 | 30622 | 2020-04-01 16:00 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 109.25 | 109.25 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
MREQ-30622 | 30622 | 2020-04-01 16:00 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 69 | 69 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
MREQ-30622 | 30622 | 2020-04-01 16:00 | Section 4 | Material Requisition | Not on List | Not on List
1 | N0 | 247.25 | 247.25 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
MREQ-30622 | 30622 | 2020-04-01 16:00 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 69 | 69 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
MREQ-30622 | 30622 | 2020-04-01 16:00 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 319 | 319 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
MREQ-30623 | 30623 | 2020-04-01 17:10 | Section 6 | Material Requisition | Aggregate | A20 Pipe Bed
200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-04-03 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | Skyland Contractors Ltd | 13854 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30623 | REQ - Finance Team | NULL | NULL
MREQ-30630 | 30630 | 2020-04-02 07:13 | Section 5 | Material Requisition | PPE, Small Tools and Consumables | Screws Self Tapping 305 Pcs Assorted Box 61275 (662414) | 10 | Boxes | 9.42 | 94.2 | Fixings and Fasteners | 2020-04-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30634 | 30634 | 2020-04-02 08:38 | Section 4 | Material Requisition | Misc | Not on List | 1 | box | NULL | 0 | Miscellaneous | 2020-04-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30634 | 30634 | 2020-04-02 08:38 | Section 4 | Material Requisition | Misc | Not on List | 1 | box | NULL | 0 | Miscellaneous | 2020-04-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30638 | 30638 | 2020-04-02 09:49 | Section 5 | Material Requisition | Not on List | Not on List
4000 | M2 | 4.85 | 19400 | Builders Merchants (General) | 2020-04-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 13871 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30638 | REQ - Finance Team | NULL | NULL
MREQ-30638 | 30638 | 2020-04-02 09:49 | Section 5 | Material Requisition | Not on List | Not on List
5 | 25KG | 7.95 | 39.75 | Builders Merchants (General) | 2020-04-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 13871 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30638 | REQ - Finance Team | NULL | NULL
MREQ-30640 | 30640 | 2020-04-02 11:55 | Section 5 | Material Requisition | Kerbs | Not on List | 80 | Each | 4.93 | 394.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30640 | 30640 | 2020-04-02 11:55 | Section 5 | Material Requisition | Kerbs | Not on List | 3 | Each | 5.84 | 17.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30640 | 30640 | 2020-04-02 11:55 | Section 5 | Material Requisition | Kerbs | Not on List | 3 | Each | 5.84 | 17.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30641 | 30641 | 2020-04-02 15:19 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed
1000 | Tonnes | 21.25 | 21250 | Aggregate | 2020-04-06 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | Caulfield | 13859 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30641 | REQ - Finance Team | NULL | NULL
MREQ-30641 | 30641 | 2020-04-02 15:19 | Section 4 | Material Requisition | Aggregate | Not on List
500 | Tonnes | 21.95 | 10975 | Aggregate | 2020-04-06 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | Caulfield | 13858 | Mick George Ltd (1220483) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30641 | REQ - Finance Team | NULL | NULL
MREQ-30647 | 30647 | 2020-04-02 12:30 | Section 4 | Material Requisition | Not on List | Not on List | 16 | Each | 142.02 | 2272.32 | Plastic Drainage | 2020-04-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30647 | 30647 | 2020-04-02 12:30 | Section 4 | Material Requisition | Not on List | Not on List | 6 | Each | 128.26 | 769.56 | Plastic Drainage | 2020-04-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30647 | 30647 | 2020-04-02 12:30 | Section 4 | Material Requisition | Not on List | Not on List | 6 | Each | 154.93 | 929.58 | Plastic Drainage | 2020-04-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30647 | 30647 | 2020-04-02 12:30 | Section 4 | Material Requisition | Not on List | Not on List | 10 | Each | 107.9 | 1079 | Plastic Drainage | 2020-04-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30647 | 30647 | 2020-04-02 12:30 | Section 4 | Material Requisition | Not on List | Not on List | 42 | Each | 11.93 | 501.06 | Plastic Drainage | 2020-04-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30666 | 30666 | 2020-04-03 10:36 | Section 6 | Material Requisition | Not on List | Not on List
18 | Ea | 5.39 | 97.02 | Miscellaneous | 2020-04-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13866 | Gap Group Ltd (1108091) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30666 | REQ - Finance Team | NULL | NULL
MREQ-30671 | 30671 | 2020-04-03 12:28 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | Each | 8.55 | 85.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30671 | 30671 | 2020-04-03 12:28 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | Each | 8.55 | 85.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30687 | 30687 | 2020-04-03 17:14 | Section 3 | Material Requisition | Misc | Not on List
1 | ea | 468.38 | 468.38 | Damage Charges | 2020-04-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 113868 | Gap Group Ltd (1108091) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30687/Buyers/IMG_20191219_0003 (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30687 | REQ - Finance Team | NULL | NULL
MREQ-30712 | 30712 | 2020-04-06 08:27 | Section 4 | Material Requisition | Not on List | Not on List | 8 | number | 8.99 | 71.92 | Miscellaneous | 2020-04-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30720 | 30720 | 2020-04-06 10:23 | Test Section | Material Requisition | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 2 | Each | 59.17 | 118.34 | Concrete Drainage | 2020-05-07 | Test Location | Test Section | Test Section | IMO Queue | Yes - Approve | Yes - Approve | Chris Henry
MREQ-30729 | 30729 | 2020-04-06 13:32 | Test Section | Material Requisition | Geotextile | Tensar TX160 4m x 75m (150563) | 134 | Each | 535 | 71690 | Aggregate | 2020-05-01 | Test Location | Test Section | Test Section | IMO Queue | Yes - Approve | Yes - Approve | Chris Henry
MREQ-30751 | 30751 | 2020-04-07 09:04 | Section 3 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 360 | Each | 2.48 | 892.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30755 | 30755 | 2020-04-07 09:11 | Section 4 | Material Requisition | Not on List | Not on List | 200 | NULL | NULL | 0 | Builders Merchants (General) | 2020-04-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30758 | 30758 | 2020-04-07 10:34 | Section 6 | Material Requisition | Not on List | Not on List | 36 | No | 5.4 | 194.4 | Miscellaneous | 2020-04-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30763 | 30763 | 2020-04-07 13:44 | Core | Material Requisition | Not on List | Not on List | 1 | number | 823.9 | 823.9 | Miscellaneous | 2020-04-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-30763 | 30763 | 2020-04-07 13:44 | Core | Material Requisition | Not on List | Not on List | 1 | number | 1282 | 1282 | Miscellaneous | 2020-04-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-30764 | 30764 | 2020-04-07 13:49 | Section 4 | Material Requisition | Not on List | Not on List | 1 | roll | NULL | 0 | Miscellaneous | 2020-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1502 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30766 | 30766 | 2020-04-07 15:05 | Section 4 | Material Requisition | Not on List | Not on List
1 | Each | 152.5 | 152.5 | Miscellaneous | 2020-04-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13877 | Morelock Signs Ltd (1255521) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30766/Request/2m Apart.zip | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30766 | REQ - Finance Team | NULL | NULL
MREQ-30767 | 30767 | 2020-04-07 15:56 | Section 5 | Material Requisition | Not on List | Not on List | 225 | m3 | 81.3 | 18292.5 | Ready Mixed Concrete | 2020-04-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30777 | 30777 | 2020-04-08 09:27 | Section 6 | Material Requisition | Not on List | Not on List
24 | each | 18.75 | 450 | Miscellaneous | 2020-04-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13883 | Lattenbury Services Ltd (1289505) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30777 | REQ - Finance Team | NULL | NULL
MREQ-30779 | 30779 | 2020-04-08 10:53 | Section 5 | Material Requisition | Aggregate | Type 1 | 3000 | Tonnes | 23.5 | 70500 | Aggregate | 2020-04-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30780 | 30780 | 2020-04-08 11:04 | Section 2 | Material Requisition | Bricks/Blocks | Not on List | 132.5 | m2. | 34.59 | 4583.18 | Blocks and Bricks | 2020-04-14 | NULL | SEC1 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-30781 | 30781 | 2020-04-08 11:50 | Section 4 | Material Requisition | Kerbs | Not on List | 148 | Each | 31.83 | 4710.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30781 | 30781 | 2020-04-08 11:50 | Section 4 | Material Requisition | Kerbs | Not on List | 2 | Each | 134.8 | 269.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30782 | 30782 | 2020-04-08 12:27 | Section 6 | Material Requisition | Not on List | Not on List | 1 | total | 1513.14 | 1513.14 | Miscellaneous | 2020-04-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30782 | 30782 | 2020-04-08 12:27 | Section 6 | Material Requisition | Not on List | Not on List | 1 | total | 91.73 | 91.73 | Miscellaneous | 2020-04-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30787 | 30787 | 2020-04-08 14:10 | Section 6 | Material Requisition | Not on List | Not on List
1 | No. | 850 | 850 | Small Tools (Consumables) | 2020-04-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13887 | Lattenbury Services Ltd (1289505) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30787 | REQ - Finance Team | NULL | NULL
MREQ-30792 | 30792 | 2020-04-08 15:10 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 85 | 85 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
MREQ-30792 | 30792 | 2020-04-08 15:10 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 114 | 114 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
MREQ-30792 | 30792 | 2020-04-08 15:10 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 72 | 72 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
MREQ-30792 | 30792 | 2020-04-08 15:10 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 103.5 | 103.5 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
MREQ-30792 | 30792 | 2020-04-08 15:10 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 97.95 | 97.95 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
MREQ-30792 | 30792 | 2020-04-08 15:10 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 97.95 | 97.95 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
MREQ-30814 | 30814 | 2020-04-09 07:13 | Section 2 | Material Requisition | Misc | Not on List | 6 | NULL | NULL | 0 | Miscellaneous | 2020-04-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-30826 | 30826 | 2020-04-09 09:48 | Section 4 | Material Requisition | Not on List | Not on List | 30 | Bag | 44.6 | 1338 | Builders Merchants (General) | 2020-04-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30826 | 30826 | 2020-04-09 09:48 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 6.81 | 6.81 | Builders Merchants (General) | 2020-04-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30826 | 30826 | 2020-04-09 09:48 | Section 4 | Material Requisition | Not on List | Not on List | 5 | Each | 3.97 | 19.85 | Builders Merchants (General) | 2020-04-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30830 | 30830 | 2020-04-09 12:24 | Section 6 | Material Requisition | Not on List | Not on List
1 | No | 207 | 207 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | OP 13901 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30830/Request/DOC110320-11032020100911.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30830 | REQ - Finance Team | NULL | NULL
MREQ-30830 | 30830 | 2020-04-09 12:24 | Section 6 | Material Requisition | Not on List | Not on List
1 | No | 5.75 | 5.75 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | OP 13901 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30830 | REQ - Finance Team | NULL | NULL
MREQ-30830 | 30830 | 2020-04-09 12:24 | Section 6 | Material Requisition | Not on List | Not on List
1 | No | 284.12 | 284.12 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | OP 13901 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30830 | REQ - Finance Team | NULL | NULL
MREQ-30830 | 30830 | 2020-04-09 12:24 | Section 6 | Material Requisition | Not on List | Not on List
1 | No | 306.21 | 306.21 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | OP 13901 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30830 | REQ - Finance Team | NULL | NULL
MREQ-30835 | 30835 | 2020-04-09 14:34 | Section 1 | Material Requisition | Not on List | Not on List
1 | No | 84 | 84 | Professional Services | 2020-04-24 | Gate 1 - 1339601 - Main Compound Alconbury | A14 IDT | OP 13893 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30835/Request/DOC100320-10032020115410.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30835 | REQ - Finance Team | NULL | NULL
MREQ-30835 | 30835 | 2020-04-09 14:34 | Section 1 | Material Requisition | Not on List | Not on List
1 | No | 251.25 | 251.25 | Professional Services | 2020-04-24 | Gate 1 - 1339601 - Main Compound Alconbury | A14 IDT | OP 13893 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30835 | REQ - Finance Team | NULL | NULL
MREQ-30835 | 30835 | 2020-04-09 14:34 | Section 1 | Material Requisition | Not on List | Not on List
1 | No | 251.25 | 251.25 | Professional Services | 2020-04-24 | Gate 1 - 1339601 - Main Compound Alconbury | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30835 | REQ - Finance Team | NULL | NULL
MREQ-30952 | 30952 | 2020-04-14 08:23 | Core | Material Requisition | Not on List | Not on List
1 | No | 800 | 800 | Surveying Consumables | 2020-04-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | A14 IDT | OP 13892 | Topcon (Great Britain) Ltd (1114363) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30952 | REQ - Finance Team | NULL | NULL
MREQ-30957 | 30957 | 2020-04-14 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 115.2 | 115.2 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30957 | 30957 | 2020-04-14 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 470.35 | 470.35 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30957 | 30957 | 2020-04-14 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 394.9 | 394.9 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30969 | 30969 | 2020-04-14 10:14 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Rolls | NULL | 0 | Rebar and Mesh | 2020-04-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30975 | 30975 | 2020-04-14 08:44 | Section 4 | Material Requisition | Not on List | Not on List
1 | set of 4 members | NULL | 0 | Miscellaneous | 2020-04-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13904 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30975 | REQ - Finance Team | NULL | NULL
MREQ-30977 | 30977 | 2020-04-14 12:29 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Tubs | NULL | 0 | Miscellaneous | 2020-04-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30981 | 30981 | 2020-04-14 13:38 | Section 2 | Material Requisition | Not on List | Not on List
1 | No | 178.5 | 178.5 | Professional Services | 2020-04-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | A14 IDT | OP 13896 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30981 | REQ - Finance Team | NULL | NULL
MREQ-30981 | 30981 | 2020-04-14 13:38 | Section 2 | Material Requisition | Not on List | Not on List
1 | No | 57.5 | 57.5 | Professional Services | 2020-04-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | A14 IDT | OP 13896 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30981 | REQ - Finance Team | NULL | NULL
MREQ-30988 | 30988 | 2020-04-14 15:39 | Section 3 | Material Requisition | Not on List | Not on List
1 | No | 63.25 | 63.25 | Professional Services | 2020-04-24 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | A14 IDT | OP 13897 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30988/Request/DOC100320-10032020115410 (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30988 | REQ - Finance Team | NULL | NULL
MREQ-30988 | 30988 | 2020-04-14 15:39 | Section 3 | Material Requisition | Not on List | Not on List
1 | No | 69 | 69 | Professional Services | 2020-04-24 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | A14 IDT | OP 13897 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30988 | REQ - Finance Team | NULL | NULL
MREQ-31002 | 31002 | 2020-04-15 08:27 | Section 2 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 50 | Each | 3.56 | 178 | Aggregate | 2020-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31008 | 31008 | 2020-04-15 09:33 | Section 6 | Material Requisition | Concrete Drainage | CPM 900mm Concrete Socket (249372) | 1 | Each | 305.03 | 305.03 | Concrete Drainage | 2020-04-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31008 | 31008 | 2020-04-15 09:33 | Section 6 | Material Requisition | Concrete Drainage | CPM 900mm Concrete Spigot (249371) | 1 | Each | 305.03 | 305.03 | Concrete Drainage | 2020-04-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31008 | 31008 | 2020-04-15 09:33 | Section 6 | Material Requisition | Concrete Drainage | CPM 600mm Concrete Socket (249351) | 1 | Each | 106.73 | 106.73 | Concrete Drainage | 2020-04-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31008 | 31008 | 2020-04-15 09:33 | Section 6 | Material Requisition | Concrete Drainage | CPM 600mm Concrete Spigot (249354) | 1 | Each | 106.73 | 106.73 | Concrete Drainage | 2020-04-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31009 | 31009 | 2020-04-15 10:30 | Section 5 | Material Requisition | Bagged | Building Sand Bulk Bag (938155) | 5 | Each | 32.74 | 163.7 | Builders Merchants (General) | 2020-04-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31011 | 31011 | 2020-04-15 14:16 | Section 4 | Material Requisition | Not on List | Not on List
15 | Each | 20.47 | 307.05 | Builders Merchants (General) | 2020-04-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | JP Flynn Construction Ltd | 13899 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31011 | REQ - Finance Team | NULL | NULL
MREQ-31034 | 31034 | 2020-04-16 10:58 | Section 6 | Material Requisition | Not on List | Not on List | 1 | Ea | 17092.96 | 17092.96 | Miscellaneous | 2020-04-17 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | FEE6 - Fee Based Costs inc. insurance | 107 - Insurance | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31036 | 31036 | 2020-04-16 12:08 | Section 3 | Material Requisition | Not on List | Not on List | 3 | No | 51.5 | 154.5 | Miscellaneous | 2020-04-24 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31036 | 31036 | 2020-04-16 12:08 | Section 3 | Material Requisition | Not on List | Not on List | 3 | No | 45 | 135 | Miscellaneous | 2020-04-24 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31036 | 31036 | 2020-04-16 12:08 | Section 3 | Material Requisition | Not on List | Not on List | 3 | No | 45 | 135 | Miscellaneous | 2020-04-24 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31045 | 31045 | 2020-04-16 14:20 | Section 4 | Material Requisition | Not on List | Not on List | 10 | NULL | NULL | 0 | Ductile Drainage | 2020-04-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31059 | 31059 | 2020-04-17 07:48 | Section 4 | Material Requisition | Not on List | Not on List | 37 | NULL | NULL | 0 | Builders Merchants (General) | 2020-04-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31064 | 31064 | 2020-04-17 09:28 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | contract | 19606.06 | 19606.06 | Professional Services | 2020-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31068 | 31068 | 2020-04-17 10:22 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | Miscellaneous | 2020-04-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31068 | 31068 | 2020-04-17 10:22 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 50 | NULL | NULL | 0 | Miscellaneous | 2020-04-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31072 | 31072 | 2020-04-17 13:12 | Section 4 | Material Requisition | Aggregate | Bedding Sand | 20 | Tonnes | 18.5 | 370 | Aggregate | 2020-04-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31075 | 31075 | 2020-04-17 13:41 | Section 4 | Material Requisition | Not on List | Not on List | 1 | day | 225 | 225 | Electrical | 2020-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31114 | 31114 | 2020-04-20 08:50 | Section 5 | Material Requisition | Not on List | Not on List
500 | pallets | 2.92 | 1460 | Builders Merchants (General) | 2020-04-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 13914 | Keyline Builders Merchants Ltd (1100980) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31114 | REQ - Finance Team | NULL | NULL
MREQ-31115 | 31115 | 2020-04-20 09:07 | Section 4 | Material Requisition | Not on List | Not on List
1040 | Hrs | 21.61 | 22474.4 | Miscellaneous | 2020-04-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13915 | Robert Half Ltd (1263314) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31115 | REQ - Finance Team | NULL | NULL
MREQ-31145 | 31145 | 2020-04-21 08:45 | Section 6 | Material Requisition | Not on List | Not on List
1 | No | 120.5 | 120.5 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | OP 13916 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31145/Request/Advice Note N06-667824.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31145 | REQ - Finance Team | NULL | NULL
MREQ-31145 | 31145 | 2020-04-21 08:45 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31145 | 31145 | 2020-04-21 08:45 | Section 6 | Material Requisition | Misc | Not on List | 52 | Ltrs | 0.8 | 41.6 | Gas Oil | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31147 | 31147 | 2020-04-21 09:40 | Section 6 | Material Requisition | Misc | Not on List
1 | No | 652.31 | 652.31 | Miscellaneous | 2020-04-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13921 | Change Capability Ltd t/a EQ P (1320940) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31147/Request/EQ Partnering Invoice0259.doc | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31147 | REQ - Finance Team | NULL | NULL
MREQ-31149 | 31149 | 2020-04-21 12:39 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 221.63 | 221.63 | Flow Control | 2020-04-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31149 | 31149 | 2020-04-21 12:39 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Each | 529.05 | 1587.15 | Concrete Drainage | 2020-04-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31149 | 31149 | 2020-04-21 12:39 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 384.8 | 769.6 | Concrete Drainage | 2020-04-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31153 | 31153 | 2020-04-21 14:08 | Section 4 | Material Requisition | Not on List | Not on List | 7 | NULL | NULL | 0 | Plastic Drainage | 2020-04-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31154 | 31154 | 2020-04-21 14:30 | Section 4 | Material Requisition | Misc | Not on List | 15 | No | 51.5 | 772.5 | Tanks and Interceptors | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31154 | 31154 | 2020-04-21 14:30 | Section 4 | Material Requisition | Misc | Not on List | 2 | No | 12 | 24 | Tanks and Interceptors | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31154 | 31154 | 2020-04-21 14:30 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 456.83 | 456.83 | Tanks and Interceptors | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31157 | 31157 | 2020-04-21 16:06 | Section 6 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 21.25 | 4250 | Aggregate | 2020-04-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31159 | 31159 | 2020-04-21 16:28 | Core | Material Requisition | Misc | Not on List
1 | No | 613.33 | 613.33 | Miscellaneous | 2020-04-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | 13941 | Change Capability Ltd t/a EQ P (1320940) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31159/Request/EQ Partnering Invoice0259.doc | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31159 | REQ - Finance Team | NULL | NULL
MREQ-31168 | 31168 | 2020-04-22 08:03 | Section 2 | Material Requisition | Aggregate | Type B | 260 | Tonnes | 22.1 | 5746 | Aggregate | 2020-04-26 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31172 | 31172 | 2020-04-22 09:34 | Test Section | Material Requisition | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 4 | Each | 115.78 | 463.12 | Concrete Drainage | 2020-04-28 | Test Location | Test Section | Test Section | Operational Approval | NULL | NULL | Chris Henry
MREQ-31173 | 31173 | 2020-04-22 10:00 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | No | 8132.02 | 8132.02 | Laboratory Equipment / Certification | 2020-04-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31193 | 31193 | 2020-04-23 03:12 | Section 4 | Material Requisition | Not on List | Not on List | 50 | ea | 5.7 | 285 | Fixings and Fasteners | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31193 | 31193 | 2020-04-23 03:12 | Section 4 | Material Requisition | Not on List | Not on List | 50 | ea | 2.84 | 142 | Fixings and Fasteners | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31193 | 31193 | 2020-04-23 03:12 | Section 4 | Material Requisition | Bagged | Building Sand Bulk Bag (938155) | 10 | Each | 34.94 | 349.4 | Builders Merchants (General) | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31193 | 31193 | 2020-04-23 03:12 | Section 4 | Material Requisition | Bagged | OP Cement; 25kg bag (767201) | 112 | Bags | 3.09 | 346.08 | Builders Merchants (General) | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31202 | 31202 | 2020-04-23 11:41 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 3623 | 3623 | Miscellaneous | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31202/Request/Invoice 8308058.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31202 | REQ - Finance Team | NULL | NULL
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 66.7 | 66.7 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 38.87 | 38.87 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 37.5 | 37.5 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 37.5 | 37.5 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 36.21 | 36.21 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 38.87 | 38.87 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 145.26 | 145.26 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31204 | 31204 | 2020-04-23 13:11 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 157.5 | 157.5 | Miscellaneous | 2020-04-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 121 - Phones / Radios / Comms | IMO - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Ducting | Not on List | 720 | M | 3.2 | 2304 | Plastic Drainage | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Ducting | Not on List | 680 | M | 7.42 | 5045.6 | Plastic Drainage | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Misc | Not on List | 720 | M | 0.05 | 36 | Miscellaneous | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Misc | Not on List | 1440 | M | 0.05 | 72 | Miscellaneous | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Misc | Not on List | 400 | M | 0.05 | 20 | Miscellaneous | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Misc | Not on List | 420 | M | 0.05 | 21 | Miscellaneous | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Misc | Not on List | 540 | M | 0.05 | 27 | Miscellaneous | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31212 | 31212 | 2020-04-23 17:47 | Section 4 | Material Requisition | Not on List | Not on List | 18 | Each | 20.64 | 371.52 | Plastic Drainage | 2020-04-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31212 | 31212 | 2020-04-23 17:47 | Section 4 | Material Requisition | Not on List | Not on List | 10 | Each | 84.83 | 848.3 | Ductile Drainage | 2020-04-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31230 | 31230 | 2020-04-24 10:51 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 943.48 | 943.48 | Miscellaneous | NaN-NaN-NaN NaN:NaN:NaN | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31233 | 31233 | 2020-04-24 13:13 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 3260 | 3260 | Miscellaneous | 2020-04-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31250 | 31250 | 2020-04-24 16:09 | Core | Material Requisition | Not on List | Not on List | 1 | no | 370 | 370 | Miscellaneous | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 500 | Each | 1.61 | 805 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 80 | Each | 3.25 | 260 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 2 | Each | 5.84 | 11.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 2 | Each | 5.84 | 11.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 10 | Each | 3.25 | 32.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Drop Kerb HB x BN LH (897468) | 3 | Each | 5.84 | 17.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Drop Kerb HB x BN RH (897464) | 3 | Each | 5.84 | 17.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31271 | 31271 | 2020-04-27 12:01 | Section 6 | Material Requisition | Not on List | Not on List | 1 | number | 880 | 880 | Miscellaneous | 2020-05-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31288 | 31288 | 2020-04-28 12:20 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 1848.3 | 1848.3 | Miscellaneous | 2020-05-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31289 | 31289 | 2020-04-28 14:35 | Section 6 | Material Requisition | Not on List | Not on List
34 | number | 3.21 | 109.14 | Timber Products | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13737 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31289/Request/Fwd Keyline credit.msg | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31289 | REQ - Finance Team | NULL | NULL
MREQ-31291 | 31291 | 2020-04-28 14:47 | Core | Material Requisition | Not on List | Not on List
6 | Number | 45 | 270 | Surveying Consumables | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31291 | REQ - Finance Team | NULL | NULL
MREQ-31295 | 31295 | 2020-04-28 15:57 | Section 6 | Material Requisition | Misc | Not on List | NULL | NULL | NULL | 0 | Miscellaneous | 2020-05-04 | NULL | NULL | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31297 | 31297 | 2020-04-28 16:07 | Section 2 | Material Requisition | Misc | Not on List | 2 | Each | 5.11 | 10.22 | Miscellaneous | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31303 | 31303 | 2020-04-29 08:31 | Section 2 | Material Requisition | Not on List | Not on List | 1 | each | 1861 | 1861 | Professional Services | 2020-04-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31307 | 31307 | 2020-04-29 09:51 | Section 4 | Material Requisition | Not on List | Not on List | 20 | No | NULL | 0 | NULL | 2020-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31315 | 31315 | 2020-04-29 12:29 | Section 2 | Material Requisition | Twinwall | Polypipe 100mm Linflex 100m (877398) | 3 | Each | 198.95 | 596.85 | Plastic Drainage | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31316 | 31316 | 2020-04-29 13:35 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 35 | Each | 3.03 | 106.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31320 | 31320 | 2020-04-29 16:48 | Section 4 | Material Requisition | Bagged | Not on List | 60 | Each | 7.95 | 477 | Builders Merchants (General) | 2020-04-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31325 | 31325 | 2020-04-30 07:23 | Section 5 | Material Requisition | Not on List | Not on List | 30 | Pallet | 2.92 | 87.6 | Builders Merchants (General) | 2020-04-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 24 | No | 6.66 | 159.84 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 20 | Prs | 10.97 | 219.4 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 6 | NULL | 3.96 | 23.76 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 6 | NULL | 9.95 | 59.7 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 12 | NULL | 1.5 | 18 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 16.21 | 32.42 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 14.79 | 29.58 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31346 | 31346 | 2020-05-01 08:08 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31346 | 31346 | 2020-05-01 08:08 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 69 | 69 | Professional Services | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31346 | 31346 | 2020-05-01 08:08 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31347 | 31347 | 2020-05-01 08:29 | Section 1 | Material Requisition | Misc | Not on List
1 | lot | 414.49 | 414.49 | Damage Charges | 2020-05-01 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | A14 IDT | 13966 | Ashtead Plant Hire Company Ltd (1109463) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31347/Buyers/20200512071201917.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31347 | REQ - Finance Team | NULL | NULL
MREQ-31353 | 31353 | 2020-05-01 11:23 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 60 | 60 | Professional Services | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31391 | 31391 | 2020-05-04 12:43 | Section 5 | Material Requisition | Aggregate | 6G | 20 | Tonnes | 22 | 440 | Aggregate | 2020-05-05 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31396 | 31396 | 2020-05-04 16:56 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | NULL | 1580 | 1580 | Waste (General) | 2020-05-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-31406 | 31406 | 2020-05-05 08:29 | Section 4 | Material Requisition | Not on List | Not on List | 45 | No | 25.17 | 1132.65 | Concrete Drainage | 2020-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31406 | 31406 | 2020-05-05 08:29 | Section 4 | Material Requisition | Not on List | Not on List | 8 | No | 241.46 | 1931.68 | Plastic Drainage | 2020-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31409 | 31409 | 2020-05-05 10:17 | Section 6 | Material Requisition | Iron Wear | Not on List | 2 | no | 310.24 | 620.48 | Miscellaneous | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31410 | 31410 | 2020-05-05 10:36 | Section 6 | Material Requisition | Not on List | Not on List | 4 | NULL | 318.9 | 1275.6 | Small Tools (Consumables) | 2020-05-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31410 | 31410 | 2020-05-05 10:36 | Section 6 | Material Requisition | Not on List | Not on List | 5 | No | 4.85 | 24.25 | Small Tools (Consumables) | 2020-05-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31410 | 31410 | 2020-05-05 10:36 | Section 6 | Material Requisition | Not on List | Not on List | 8 | No | 49.16 | 393.28 | Small Tools (Consumables) | 2020-05-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31414 | 31414 | 2020-05-05 12:45 | Core | Material Requisition | Not on List | Not on List
1 | Ea | 1200 | 1200 | Laboratory Equipment / Certification | 2020-05-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | 10325 | Acoustics Noise & Vibration Lt (1109268) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31414/Request/RE ANV POInvoices.msg | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31414 | REQ - Finance Team | NULL | NULL
MREQ-31419 | 31419 | 2020-05-05 14:13 | Section 6 | Material Requisition | Not on List | Not on List | 1 | Pr | 255.5 | 255.5 | Small Tools (Consumables) | 2020-05-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31422 | 31422 | 2020-05-05 16:05 | Section 5 | Material Requisition | Aggregate | Type 1 | 300 | Tonnes | 23.75 | 7125 | Aggregate | 2020-05-07 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31429 | 31429 | 2020-05-06 13:21 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Lot | 1995.84 | 1995.84 | Miscellaneous | 2020-05-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31433 | 31433 | 2020-05-06 13:49 | Section 4 | Material Requisition | Aggregate | Type 1 | 6000 | Tonnes | 23.5 | 141000 | Aggregate | 2020-05-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31446 | 31446 | 2020-05-06 16:04 | Core | Material Requisition | Not on List | Not on List | 1 | no. | 400 | 400 | Surveying Consumables | 2020-05-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-31450 | 31450 | 2020-05-07 08:10 | Section 1 | Material Requisition | Misc | Not on List | 2 | No | 19.5 | 39 | Damage Charges | 2020-05-07 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-31450 | 31450 | 2020-05-07 08:10 | Section 1 | Material Requisition | Misc | Not on List | 1 | No | 12.25 | 12.25 | Damage Charges | 2020-05-07 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-31454 | 31454 | 2020-05-07 07:58 | Section 6 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 40 | Each | 1.61 | 64.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31454 | 31454 | 2020-05-07 07:58 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 650 | Each | 4.93 | 3204.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31454 | 31454 | 2020-05-07 07:58 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 32 | Each | 3.78 | 120.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31454 | 31454 | 2020-05-07 07:58 | Section 6 | Material Requisition | Kerbs | Not on List | 6 | Each | 16.17 | 97.02 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31454 | 31454 | 2020-05-07 07:58 | Section 6 | Material Requisition | Kerbs | Not on List | 6 | Each | 15.65 | 93.9 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31470 | 31470 | 2020-05-07 14:20 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List
150 | Each | 7.1 | 1065 | Miscellaneous | 2020-05-18 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13964 | SCCS Survey Equipment Ltd t/a (1101886) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31470 | REQ - Finance Team | NULL | NULL
MREQ-31471 | 31471 | 2020-05-07 14:50 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 7532.6 | 7532.6 | Miscellaneous | 2020-05-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31509 | 31509 | 2020-05-11 16:09 | Section 4 | Material Requisition | Not on List | Not on List | 61000 | Litres | 0.35 | 21350 | Gas Oil | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31510 | 31510 | 2020-05-11 16:17 | Section 4 | Material Requisition | Not on List | Not on List | 430000 | Litres | 0.35 | 150500 | Gas Oil | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31518 | 31518 | 2020-05-12 11:12 | Section 5 | Material Requisition | Not on List | Not on List | 1 | NUMBER | 139.2 | 139.2 | Miscellaneous | 2020-05-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31522 | 31522 | 2020-05-12 15:16 | Section 4 | Material Requisition | Not on List | Not on List | 16 | Kg | 1.3 | 20.8 | Miscellaneous | 2020-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 90 | 90 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 235 | 235 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31536 | 31536 | 2020-05-13 10:40 | Section 5 | Material Requisition | Not on List | Not on List | 1 | £ | 1890 | 1890 | Professional Services | 2020-05-13 | 1358005 - WB5/7 Works Access - 1356563 - A14 Westbound, On Left between Jcn 32 - 31 | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-31538 | 31538 | 2020-05-13 11:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 102 | 102 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13973 | L Lynch (Plant Hire & Haulage) (1112290) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31538/Request/Advice Note N06-667828.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31538 | REQ - Finance Team | NULL | NULL
MREQ-31538 | 31538 | 2020-05-13 11:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 115 | 115 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31538 | 31538 | 2020-05-13 11:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 69 | 69 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13973 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31538/Request/DOC200420-20042020185334 (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31538 | REQ - Finance Team | NULL | NULL
MREQ-31538 | 31538 | 2020-05-13 11:35 | Section 4 | Material Requisition | Not on List | Not on List | 58 | LT | 0.8 | 46.4 | Gas Oil | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31538 | 31538 | 2020-05-13 11:35 | Section 4 | Material Requisition | Not on List | Not on List
180 | LT | 0.8 | 144 | Gas Oil | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13973 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31538 | REQ - Finance Team | NULL | NULL
MREQ-31538 | 31538 | 2020-05-13 11:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 82.8 | 82.8 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13973 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31538 | REQ - Finance Team | NULL | NULL
MREQ-31538 | 31538 | 2020-05-13 11:35 | Section 4 | Material Requisition | Not on List | Not on List | 55 | LT | 0.8 | 44 | Gas Oil | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31540 | 31540 | 2020-05-13 12:32 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 90 | Each | 5.55 | 499.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31540 | 31540 | 2020-05-13 12:32 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 15 | Each | 4.75 | 71.25 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31540 | 31540 | 2020-05-13 12:32 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 5 | Each | 13.32 | 66.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31540 | 31540 | 2020-05-13 12:32 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 5 | Each | 13.32 | 66.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31545 | 31545 | 2020-05-13 14:23 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 258.75 | 258.75 | Professional Services | 2020-05-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Passed Back | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-31545 | 31545 | 2020-05-13 14:23 | Section 2 | Material Requisition | Not on List | Not on List
1 | No | 86.25 | 86.25 | Professional Services | 2020-05-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Commercial Passed Back | Yes - Approve | No - Pass Back | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31545/Request/Scan_20200424_151518.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31545 | REQ - Finance Team | NULL | NULL
MREQ-31545 | 31545 | 2020-05-13 14:23 | Section 2 | Material Requisition | Not on List | Not on List
115 | LT | 1.8 | 207 | Gas Oil | 2020-05-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Commercial Passed Back | Yes - Approve | No - Pass Back | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31545 | REQ - Finance Team | NULL | NULL
MREQ-31546 | 31546 | 2020-05-13 15:09 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 95 | 95 | Professional Services | 2020-05-29 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31547 | 31547 | 2020-05-13 15:26 | Section 6 | Material Requisition | Not on List | Not on List | 118 | LT | 0.8 | 94.4 | Gas Oil | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Rejected | Yes - Approve | No - Reject | Req - S6 Buyers
MREQ-31556 | 31556 | 2020-05-14 10:13 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Number | 3623 | 3623 | Miscellaneous | 2020-05-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31557 | 31557 | 2020-05-14 10:39 | Section 4 | Material Requisition | Bagged | Kiln Dried Sand 25kg (518674) | 25 | Each | 2.4 | 60 | Builders Merchants (General) | 2020-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 40 | Each | 20.64 | 825.6 | Plastic Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 35 | Each | 3.31 | 115.85 | Plastic Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 70 | Each | 1.63 | 114.1 | Plastic Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm x 150mm 45deg Junction (878010) | 12 | Each | 30.02 | 360.24 | Plastic Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Not on List | Not on List | 15 | No | 70.18 | 1052.7 | Ductile Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Not on List | Not on List | 12 | No | 31.05 | 372.6 | Plastic Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31561 | 31561 | 2020-05-14 16:08 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 700 | Each | 3.25 | 2275 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31561 | 31561 | 2020-05-14 16:08 | Section 4 | Material Requisition | Kerbs | Drop Kerb HB x BN LH (897468) | 10 | Each | 5.84 | 58.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31561 | 31561 | 2020-05-14 16:08 | Section 4 | Material Requisition | Kerbs | Drop Kerb HB x BN RH (897464) | 10 | Each | 5.84 | 58.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31570 | 31570 | 2020-05-14 17:33 | Section 6 | Material Requisition | Not on List | Not on List | 1 | Area | NULL | 0 | Miscellaneous | 2020-05-20 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 106 - Testing equipment and materials testing | Commercial Rejected | Yes - Approve | No - Reject | Req - S6 Buyers
MREQ-31582 | 31582 | 2020-05-15 10:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | £ | 1713.6 | 1713.6 | Professional Services | 2020-05-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 106 - Testing equipment and materials testing | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 885 | Each | 4.93 | 4363.05 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Transition Kerbs 125x255 (947297) | 4 | Each | 5.84 | 23.36 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Transition Kerbs 125x255 (947297) | 3 | Each | 5.84 | 17.52 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 460 | Each | 3.78 | 1738.8 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 4 | Each | 10.83 | 43.32 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 4 | Each | 10.83 | 43.32 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 480 | Each | 1.61 | 772.8 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 32 | Each | 3.25 | 104 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 305 Channel 500mm (758908) | 242 | Each | 17.85 | 4319.7 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 305 Access Unit (947299) | 3 | Each | 30.32 | 90.96 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Not on List | 1 | Each | 221.75 | 221.75 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Not on List | 1 | Each | 221.75 | 221.75 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 305 Dropper LH (758901) | 1 | Each | 31.81 | 31.81 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 305 Dropper RH (758907) | 1 | Each | 31.81 | 31.81 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 305 Center Stone (758899) | 6 | Each | 27.56 | 165.36 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Not on List | 1 | Each | 221.75 | 221.75 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 405 Channel 1000mm (947299) | 15 | Each | 39.14 | 587.1 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 19 | Each | 5.84 | 110.96 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Not on List | 13 | Each | 16.17 | 210.21 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Not on List | 4 | NULL | 15.65 | 62.6 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 288 | No | 4.42 | 1272.96 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 336 | No | 4.42 | 1485.12 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 252 | No | 6.29 | 1585.08 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 35 | No | 6.29 | 220.15 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31621 | 31621 | 2020-05-18 11:05 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 72 | meters | 32.19 | 2317.68 | Plastic Drainage | 2020-05-21 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31623 | 31623 | 2020-05-18 12:59 | Core | Material Requisition | Not on List | Not on List | 1 | No | 9016.63 | 9016.63 | Miscellaneous | 2020-05-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31623 | 31623 | 2020-05-18 12:59 | Core | Material Requisition | Not on List | Not on List | 1 | No | 3364.58 | 3364.58 | Miscellaneous | 2020-05-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31623 | 31623 | 2020-05-18 12:59 | Core | Material Requisition | Not on List | Not on List | 1 | No | 6038.34 | 6038.34 | Miscellaneous | 2020-05-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31631 | 31631 | 2020-05-18 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | 22613.41 | 22613.41 | Damage Charges | 2020-05-21 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BES4 - Existing Structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31632 | 31632 | 2020-05-18 16:36 | Section 4 | Material Requisition | Concrete Drainage | CPM 1200mm Concrete Pipe 2.5m (249379) | 21 | Each | 529.05 | 11110.05 | Concrete Drainage | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31632 | 31632 | 2020-05-18 16:36 | Section 4 | Material Requisition | Concrete Drainage | CPM 1200mm Concrete Rocker (249380) | 2 | Each | 634.85 | 1269.7 | Concrete Drainage | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31632 | 31632 | 2020-05-18 16:36 | Section 4 | Material Requisition | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 2 | Each | 634.85 | 1269.7 | Concrete Drainage | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31634 | 31634 | 2020-05-18 17:06 | Section 4 | Material Requisition | Not on List | Not on List | 1 | £ | 7225 | 7225 | Professional Services | 2020-05-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-31647 | 31647 | 2020-05-19 09:46 | Section 4 | Material Requisition | Not on List | Not on List | 5 | rolls | 3674 | 18370 | Builders Merchants (General) | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31647 | 31647 | 2020-05-19 09:46 | Section 4 | Material Requisition | Not on List | Not on List | 600 | numbers | 2.55 | 1530 | Builders Merchants (General) | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31647 | 31647 | 2020-05-19 09:46 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Box | 40.31 | 120.93 | Builders Merchants (General) | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31652 | 31652 | 2020-05-19 13:54 | Section 6 | Material Requisition | Bagged | Sharp Sand Bulk Bag (938208) | 4 | Each | 34.94 | 139.76 | Builders Merchants (General) | 2020-05-21 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31652 | 31652 | 2020-05-19 13:54 | Section 6 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768)
1 | Pallet | 3.79 | 3.79 | Miscellaneous | 2020-05-21 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 13987 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31652 | REQ - Finance Team | NULL | NULL
MREQ-31652 | 31652 | 2020-05-19 13:54 | Section 6 | Material Requisition | Twinwall | Polypipe 150mm x 25m Ridgiflex (877588) | 6 | meters | 164.84 | 989.04 | Ductile Drainage | 2020-05-21 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31652 | 31652 | 2020-05-19 13:54 | Section 6 | Material Requisition | Twinwall | Not on List | 1 | bag | 248.4 | 248.4 | Ductile Drainage | 2020-05-21 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31652 | 31652 | 2020-05-19 13:54 | Section 6 | Material Requisition | Not on List | Not on List | 1 | pallet | 4.31 | 4.31 | Concrete Drainage | 2020-05-21 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31656 | 31656 | 2020-05-19 15:05 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 28921.05 | 28921.05 | Miscellaneous | 2020-05-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31660 | 31660 | 2020-05-19 17:30 | Section 5 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 23.5 | 11750 | Aggregate | 2020-05-21 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31667 | 31667 | 2020-05-20 11:12 | Section 4 | Material Requisition | Not on List | Not on List | 12 | No | 84.83 | 1017.96 | Ductile Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31678 | 31678 | 2020-05-20 16:33 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 25 | 75 | Professional Services | 2020-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31678 | 31678 | 2020-05-20 16:33 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Np | 50 | 50 | Professional Services | 2020-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31683 | 31683 | 2020-05-20 17:27 | Section 4 | Material Requisition | Not on List | Not on List | 12 | No | 27.96 | 335.52 | Plastic Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31683 | 31683 | 2020-05-20 17:27 | Section 4 | Material Requisition | Not on List | Not on List | 16 | No | 39.87 | 637.92 | Plastic Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31683 | 31683 | 2020-05-20 17:27 | Section 4 | Material Requisition | Not on List | Not on List | 16 | No | 70.58 | 1129.28 | Plastic Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31683 | 31683 | 2020-05-20 17:27 | Section 4 | Material Requisition | Not on List | Not on List | 10 | No | 93.88 | 938.8 | Plastic Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31683 | 31683 | 2020-05-20 17:27 | Section 4 | Material Requisition | Not on List | Not on List | 10 | No | 101.24 | 1012.4 | Plastic Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31686 | 31686 | 2020-05-20 18:15 | Section 4 | Material Requisition | Aggregate | Type 1 | 5000 | Tonnes | 21.65 | 108250 | Aggregate | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31688 | 31688 | 2020-05-20 19:24 | Core | Material Requisition | Not on List | Not on List | 1 | Ea | 10611.02 | 10611.02 | Miscellaneous | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31688 | 31688 | 2020-05-20 19:24 | Core | Material Requisition | Not on List | Not on List | 1 | Ea | 4378 | 4378 | Miscellaneous | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31688 | 31688 | 2020-05-20 19:24 | Core | Material Requisition | Not on List | Not on List | 1 | Ea | 14304 | 14304 | Miscellaneous | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31688 | 31688 | 2020-05-20 19:24 | Core | Material Requisition | Not on List | Not on List | 1 | Ea | 1054.7 | 1054.7 | Miscellaneous | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31688 | 31688 | 2020-05-20 19:24 | Core | Material Requisition | Not on List | Not on List | 1 | Ea | 4187 | 4187 | Miscellaneous | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31695 | 31695 | 2020-05-21 12:40 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 99.96 | 99.96 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31695 | 31695 | 2020-05-21 12:40 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 456 | 456 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31696 | 31696 | 2020-05-21 13:13 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 146.72 | 146.72 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31697 | 31697 | 2020-05-21 13:32 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 113 | 113 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31697 | 31697 | 2020-05-21 13:32 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 676.95 | 676.95 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31698 | 31698 | 2020-05-21 13:38 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 150 | 150 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31698 | 31698 | 2020-05-21 13:38 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 150 | 150 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31699 | 31699 | 2020-05-21 13:43 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 297 | 297 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31699/Request/Invoice ALARM Ltd.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31699 | REQ - Finance Team | NULL | NULL
MREQ-31701 | 31701 | 2020-05-21 13:56 | Section 4 | Material Requisition | Not on List | Not on List | 1 | number | 88.11 | 88.11 | Surveying Consumables | 2020-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31702 | 31702 | 2020-05-21 13:51 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 65 | 65 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31703 | 31703 | 2020-05-21 14:11 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1908 | 1908 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31704 | 31704 | 2020-05-21 14:21 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1440 | 1440 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31707 | 31707 | 2020-05-21 15:02 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 53.72 | 53.72 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31708 | 31708 | 2020-05-21 15:05 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 345 | 345 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31709 | 31709 | 2020-05-21 15:10 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 90 | 90 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31710 | 31710 | 2020-05-21 15:15 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 4000 | 4000 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31711 | 31711 | 2020-05-21 15:24 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 3219.1 | 3219.1 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31712 | 31712 | 2020-05-21 15:27 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 395 | 395 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31735 | 31735 | 2020-05-22 13:51 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Batch | 3789 | 3789 | Flow Control | 2020-05-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31741 | 31741 | 2020-05-22 16:18 | Section 6 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 21.25 | 4250 | Aggregate | 2020-05-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31763 | 31763 | 2020-05-26 10:05 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 25 | Each | 20.64 | 516 | Plastic Drainage | 2020-05-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31765 | 31765 | 2020-05-26 11:09 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Number | 404.13 | 808.26 | Plastic Drainage | 2020-05-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31769 | 31769 | 2020-05-26 09:33 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 446.6 | 446.6 | Miscellaneous | 2020-05-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31780 | 31780 | 2020-05-27 08:13 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2467.43 | 2467.43 | Small Tools (Consumables) | 2020-05-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31785 | 31785 | 2020-05-27 09:52 | Section 4 | Material Requisition | Not on List | Not on List | 30 | No. | 13.62 | 408.6 | Janitorial | 2020-05-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31789 | 31789 | 2020-05-27 14:58 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 40 | Each | 6.6 | 264 | Blocks and Bricks | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31789 | 31789 | 2020-05-27 14:58 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 30 | Each | 5.83 | 174.9 | Blocks and Bricks | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 10 | Each | 25.17 | 251.7 | Concrete Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 6 | Each | 78.67 | 472.02 | Plastic Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 12 | Each | 12.37 | 148.44 | Plastic Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 24 | Each | 5.41 | 129.84 | Plastic Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Saint Gobain Castings | 600x600x150 D400 Inter Ax Manhole Cover (766618) | 5 | Each | 98.48 | 492.4 | Plastic Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Saint Gobain Castings | 454x454x100 D400 Watershed GG&F (257790) | 12 | Each | 62.04 | 744.48 | Plastic Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Misc | Not on List
1 | number | 1650 | 1650 | Flow Control | 2020-06-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | Skyland Contractors Ltd | 14006 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | Althon Ltd 1140767 | /sites/BPM/FlowForma/FormDocuments/MREQ31790/Request/Weir-Orifice Plate and Rolled Steel Angle.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31790 | REQ - Finance Team | NULL | NULL
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Misc | Not on List | 18 | number | NULL | 0 | Flow Control | 2020-06-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Operations Passed Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Misc | Not on List | 1 | number | NULL | 0 | Flow Control | 2020-06-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Operations Passed Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-31804 | 31804 | 2020-05-28 12:36 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 240 | Each | 3.78 | 907.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31804 | 31804 | 2020-05-28 12:36 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 90 | Each | 4.93 | 443.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31819 | 31819 | 2020-05-29 10:27 | Section 4 | Material Requisition | Misc | Not on List | 10 | number | 52.66 | 526.6 | Builders Merchants (General) | 2020-06-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31826 | 31826 | 2020-05-29 15:17 | Section 6 | Material Requisition | Not on List | Not on List | 2 | TINS | 63.89 | 127.78 | Builders Merchants (General) | 2020-06-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | S6SF - Station Forecourt | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31828 | 31828 | 2020-05-29 15:18 | Section 2 | Material Requisition | Not on List | Not on List
11 | number | 47.57 | 523.27 | Builders Merchants (General) | 2020-06-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | Skyland Contractors Ltd | 14025 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31828/Request/H259ps1i1.zip | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31828 | REQ - Finance Team | NULL | NULL
MREQ-31828 | 31828 | 2020-05-29 15:18 | Section 2 | Material Requisition | Aggregate | 6G | 60 | Tonnes | 32.9 | 1974 | Aggregate | 2020-06-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31854 | 31854 | 2020-06-01 09:56 | Core | Material Requisition | Not on List | Not on List | 1 | No | 50484.8 | 50484.8 | Miscellaneous | 2020-06-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 153 - Temporary Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31855 | 31855 | 2020-06-01 12:03 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 103.75 | 103.75 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31855 | 31855 | 2020-06-01 12:03 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 96.8 | 96.8 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31855 | 31855 | 2020-06-01 12:03 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 86.9 | 86.9 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31855 | 31855 | 2020-06-01 12:03 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 52.5 | 52.5 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31868 | 31868 | 2020-06-01 17:43 | Section 6 | Material Requisition | Iron Wear | Not on List
50 | each | 62.04 | 3102 | Ductile Drainage | 2020-06-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 14015 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31868 | REQ - Finance Team | NULL | NULL
MREQ-31868 | 31868 | 2020-06-01 17:43 | Section 6 | Material Requisition | Iron Wear | Not on List
35 | each | 62.04 | 2171.4 | Ductile Drainage | 2020-06-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 14015 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31868 | REQ - Finance Team | NULL | NULL
MREQ-31868 | 31868 | 2020-06-01 17:43 | Section 6 | Material Requisition | Iron Wear | Not on List
4 | each | 62.04 | 248.16 | Ductile Drainage | 2020-06-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 14015 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31868 | REQ - Finance Team | NULL | NULL
MREQ-31868 | 31868 | 2020-06-01 17:43 | Section 6 | Material Requisition | Iron Wear | Not on List
1 | each | 62.04 | 62.04 | Ductile Drainage | 2020-06-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 14015 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31868 | REQ - Finance Team | NULL | NULL
MREQ-31877 | 31877 | 2020-06-03 14:04 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 19853 | 19853 | Miscellaneous | 2020-06-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 119 - Cleaning Sub.Con | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31880 | 31880 | 2020-06-03 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31880 | 31880 | 2020-06-03 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31880 | 31880 | 2020-06-03 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 70 | 70 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31880 | 31880 | 2020-06-03 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 160 | 160 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31880 | 31880 | 2020-06-03 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 200 | 200 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31882 | 31882 | 2020-06-04 16:33 | Section 6 | Material Requisition | Not on List | Not on List | 600 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-06-05 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31882 | 31882 | 2020-06-04 16:33 | Section 6 | Material Requisition | Not on List | Not on List | 120 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-06-05 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31883 | 31883 | 2020-06-04 16:41 | Section 6 | Material Requisition | Aggregate | Not on List | 98.4 | ton | 32.9 | 3237.36 | Aggregate | 2020-06-05 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31907 | 31907 | 2020-06-05 11:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | ea | 6713.96 | 6713.96 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31907 | 31907 | 2020-06-05 11:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | ea | 250 | 250 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31907 | 31907 | 2020-06-05 11:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | ea | 550 | 550 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31952 | 31952 | 2020-06-08 19:39 | Core | Material Requisition | Not on List | Not on List | 1 | No | 1625 | 1625 | Laboratory Equipment / Certification | 2020-06-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31954 | 31954 | 2020-06-09 07:16 | Section 4 | Material Requisition | Not on List | Not on List | 250 | NULL | 7.1 | 1775 | Miscellaneous | 2020-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31962 | 31962 | 2020-06-09 10:50 | Section 4 | Material Requisition | Misc | Not on List | 2 | box | 10.5 | 21 | Miscellaneous | 2020-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 142.5 | 142.5 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 181.96 | 181.96 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 155.76 | 155.76 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 128.48 | 128.48 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 108.39 | 108.39 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 133.38 | 133.38 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 167.32 | 167.32 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 114.85 | 114.85 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 89.32 | 89.32 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 623.96 | 623.96 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 194.4 | 194.4 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 680.09 | 680.09 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31966 | 31966 | 2020-06-09 11:39 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 491.92 | 491.92 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31966 | 31966 | 2020-06-09 11:39 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 379.32 | 379.32 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31966 | 31966 | 2020-06-09 11:39 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 3814.25 | 3814.25 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31967 | 31967 | 2020-06-09 12:11 | Section 2 | Material Requisition | PPE, Small Tools and Consumables | Not on List
1 | No | 103.53 | 103.53 | Concrete Accessories | 2020-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14037 | Ashtead Plant Hire Company Ltd (1109463) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | Sunbelt rentals | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31967 | REQ - Finance Team | NULL | NULL
MREQ-31968 | 31968 | 2020-06-09 12:42 | Section 6 | Material Requisition | Not on List | Not on List | 1 | NULL | 1559.94 | 1559.94 | Office Supplies | 2020-06-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-31968 | 31968 | 2020-06-09 12:42 | Section 6 | Material Requisition | Not on List | Not on List | 6 | ea | 12.74 | 76.44 | Office Supplies | 2020-06-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-31969 | 31969 | 2020-06-09 13:55 | Core | Material Requisition | Not on List | Not on List
1 | Number | NULL | 0 | PPE | 2020-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31969 | REQ - Finance Team | NULL | NULL
MREQ-31969 | 31969 | 2020-06-09 13:55 | Core | Material Requisition | Not on List | Not on List
1 | Number | NULL | 0 | PPE | 2020-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31969 | REQ - Finance Team | NULL | NULL
MREQ-31969 | 31969 | 2020-06-09 13:55 | Core | Material Requisition | Not on List | Not on List
1 | Number | NULL | 0 | PPE | 2020-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31969 | REQ - Finance Team | NULL | NULL
MREQ-31979 | 31979 | 2020-06-09 16:58 | Section 4 | Material Requisition | Saint Gobain Castings | Not on List | 7 | Number | 74.26 | 519.82 | Ductile Drainage | 2020-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31982 | 31982 | 2020-06-10 08:06 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 45 | 45 | Professional Services | 2020-06-26 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-31983 | 31983 | 2020-06-10 08:13 | Section 2 | Material Requisition | Not on List | Not on List | 4 | No | 45 | 180 | Miscellaneous | 2020-06-26 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31987 | 31987 | 2020-06-10 10:58 | Section 4 | Material Requisition | Twinwall | Polypipe Road Gully 450mm x 900mm (573005) | 20 | Each | 31.05 | 621 | Plastic Drainage | 2020-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31987 | 31987 | 2020-06-10 10:58 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 20 | No | 6.95 | 139 | Plastic Drainage | 2020-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31987 | 31987 | 2020-06-10 10:58 | Section 4 | Material Requisition | Saint Gobain Castings | Not on List | 10 | number | 43.58 | 435.8 | Ductile Drainage | 2020-06-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31987 | 31987 | 2020-06-10 10:58 | Section 4 | Material Requisition | Saint Gobain Castings | Not on List | 10 | number | 43.58 | 435.8 | Ductile Drainage | 2020-06-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31991 | 31991 | 2020-06-10 17:08 | Section 4 | Material Requisition | Not on List | Not on List
100 | box of 100 | 45.04 | 4504 | Miscellaneous | 2020-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | op 14046 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31991 | REQ - Finance Team | NULL | NULL
MREQ-31991 | 31991 | 2020-06-10 17:08 | Section 4 | Material Requisition | Not on List | Not on List
100 | box of 100 | 83.15 | 8315 | Miscellaneous | 2020-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | op 14046 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31991 | REQ - Finance Team | NULL | NULL
MREQ-31996 | 31996 | 2020-06-11 08:48 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 3 | NULL | NULL | 0 | PPE | 2020-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32000 | 32000 | 2020-06-11 09:21 | Section 4 | Material Requisition | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 3 | Each | 100.77 | 302.31 | Concrete Drainage | 2020-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32000 | 32000 | 2020-06-11 09:21 | Section 4 | Material Requisition | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 6 | Each | 84.83 | 508.98 | Ductile Drainage | 2020-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32000 | 32000 | 2020-06-11 09:21 | Section 4 | Material Requisition | Concrete Drainage | Not on List | 2 | Each | 1224.54 | 2449.08 | Concrete Drainage | 2020-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32002 | 32002 | 2020-06-11 15:59 | Section 4 | Material Requisition | Not on List | Not on List
3000 | m3 | NULL | 0 | Miscellaneous | 2020-06-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operations Rejected | No - Reject | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32002 | REQ - Finance Team | NULL | NULL
MREQ-32003 | 32003 | 2020-06-11 16:09 | Section 4 | Material Requisition | Not on List | Not on List
0 | 0 | 0 | 0 | Miscellaneous | 2020-06-15 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | A14 IDT | 14049 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32003/Commercial-Approval/Topsoil - G. Webb Quote.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32003 | REQ - Finance Team | NULL | NULL
MREQ-32013 | 32013 | 2020-06-12 13:01 | Section 4 | Material Requisition | Not on List | Not on List | 20 | number | 47.57 | 951.4 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32013 | 32013 | 2020-06-12 13:01 | Section 4 | Material Requisition | Not on List | Not on List | 5 | number | 40 | 200 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32013 | 32013 | 2020-06-12 13:01 | Section 4 | Material Requisition | Aggregate | 6G | 60 | Tonnes | 22 | 1320 | Aggregate | 2020-06-25 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32053 | 32053 | 2020-06-15 08:58 | Section 4 | Material Requisition | Aggregate | Type 1 | 400 | Tonnes | 23.5 | 9400 | Aggregate | 2020-06-16 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32053 | 32053 | 2020-06-15 08:58 | Section 4 | Material Requisition | Aggregate | Type 1 | 300 | Tonnes | 23.5 | 7050 | Aggregate | 2020-06-17 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32053 | 32053 | 2020-06-15 08:58 | Section 4 | Material Requisition | Aggregate | Type 1 | 300 | Tonnes | 23.5 | 7050 | Aggregate | 2020-06-18 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32055 | 32055 | 2020-06-15 10:09 | Section 4 | Material Requisition | Misc | Not on List | 7 | tubs | NULL | 0 | Miscellaneous | 2020-06-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32059 | 32059 | 2020-06-15 11:38 | Section 4 | Material Requisition | Not on List | Not on List | 2 | 12 kg tubs | 49.38 | 98.76 | Builders Merchants (General) | 2020-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32062 | 32062 | 2020-06-15 13:35 | Core | Material Requisition | Not on List | Not on List
1 | Licence | 3500 | 3500 | Surveying Consumables | 2020-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | 14052 | Korec (1114049) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32062 | REQ - Finance Team | NULL | NULL
MREQ-32063 | 32063 | 2020-06-15 14:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-06-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32064 | 32064 | 2020-06-15 15:24 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-06-17 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32064 | 32064 | 2020-06-15 15:24 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-06-18 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32064 | 32064 | 2020-06-15 15:24 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-06-19 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32085 | 32085 | 2020-06-16 17:09 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 15 | Each | 8.08 | 121.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-06-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32086 | 32086 | 2020-06-17 11:02 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 973.42 | 973.42 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32090 | 32090 | 2020-06-17 14:28 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 2231.82 | 2231.82 | Miscellaneous | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32090 | 32090 | 2020-06-17 14:28 | Section 5 | Material Requisition | Not on List | Not on List | 13 | no | 76.48 | 994.24 | Miscellaneous | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Red (742163) | 12 | Each | 6.7 | 80.4 | Surveying Consumables | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Paint Spot Marking Contractor Red 750ml Ref 43083 (742167) | 12 | Each | 3.03 | 36.36 | Surveying Consumables | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Tape Gaffa Waterproof Cloth Black 50mm X 50mtr (764674) | 12 | Each | 4.1 | 49.2 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Cable Tie Plastic Black 300mm X 4.8mm Pack Of 100 Spartan (230061) | 10 | Each | 1.94 | 19.4 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Line Brick Masons 100m Pink Bl100hv Ref 27428 Spartan (767804) | 10 | Each | 7.72 | 77.2 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Broom Head Natural Coco Fibre Size 250mm/10" Flat Stock (502031) | 10 | Each | 1.79 | 17.9 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List
150 | NULL | 6.93 | 1039.5 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14064 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32097 | REQ - Finance Team | NULL | NULL
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List
5 | NULL | 18.43 | 92.15 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14064 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32097 | REQ - Finance Team | NULL | NULL
MREQ-32099 | 32099 | 2020-06-18 08:23 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 3300 | 3300 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32099 | 32099 | 2020-06-18 08:23 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 5930 | 5930 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 45 | 45 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 65 | 65 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 130 | 130 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 45 | 45 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 65 | 65 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 8 | Hrs | 65 | 520 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32108 | 32108 | 2020-06-18 14:01 | Section 2 | Material Requisition | PPE, Small Tools and Consumables | Not on List
3 | NULL | 32.48 | 97.44 | Small Tools (Consumables) | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14069 | Ashtead Plant Hire Company Ltd (1109463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32108 | REQ - Finance Team | NULL | NULL
MREQ-32108 | 32108 | 2020-06-18 14:01 | Section 2 | Material Requisition | PPE, Small Tools and Consumables | Not on List
10 | NULL | 0.72 | 7.2 | Small Tools (Consumables) | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14066 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32108 | REQ - Finance Team | NULL | NULL
MREQ-32108 | 32108 | 2020-06-18 14:01 | Section 2 | Material Requisition | PPE, Small Tools and Consumables | Not on List
10 | NULL | 0.82 | 8.2 | Small Tools (Consumables) | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14066 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32108 | REQ - Finance Team | NULL | NULL
MREQ-32108 | 32108 | 2020-06-18 14:01 | Section 2 | Material Requisition | PPE, Small Tools and Consumables | Not on List
6 | NULL | 0.71 | 4.26 | Small Tools (Consumables) | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14066 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32108 | REQ - Finance Team | NULL | NULL
MREQ-32108 | 32108 | 2020-06-18 14:01 | Section 2 | Material Requisition | PPE, Small Tools and Consumables | Not on List
6 | NULL | 0.47 | 2.82 | Small Tools (Consumables) | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14066 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32108 | REQ - Finance Team | NULL | NULL
MREQ-32123 | 32123 | 2020-06-19 13:05 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 10648.5 | 10648.5 | Miscellaneous | 2020-06-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32165 | 32165 | 2020-06-22 11:27 | Section 2 | Material Requisition | Misc | Not on List | 1 | No | NULL | 0 | Damage Charges | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32192 | 32192 | 2020-06-24 07:55 | Section 4 | Material Requisition | Not on List | Not on List | 36 | number | 7.4 | 266.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32196 | 32196 | 2020-06-24 08:35 | Section 1 | Material Requisition | Not on List | Not on List | 1 | lot | 3324.91 | 3324.91 | Rebar and Mesh | 2020-06-29 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32199 | 32199 | 2020-06-24 11:26 | Section 6 | Material Requisition | Misc | Not on List | 1 | no | 2097 | 2097 | Ductile Drainage | 2020-06-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32202 | 32202 | 2020-06-24 14:19 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 3 | Each | 180 | 540 | Small Tools (Consumables) | 2020-06-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32215 | 32215 | 2020-06-25 10:31 | Section 4 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 23.5 | 11750 | Aggregate | 2020-06-26 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32217 | 32217 | 2020-06-25 11:38 | Section 6 | Material Requisition | Not on List | Not on List | 1 | Number | 390 | 390 | Miscellaneous | 2020-06-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32230 | 32230 | 2020-06-25 15:14 | Section 3 | Material Requisition | Misc | Not on List | 3 | No | 45 | 135 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32230 | 32230 | 2020-06-25 15:14 | Section 3 | Material Requisition | Misc | Not on List | 1 | No | 14 | 14 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32230 | 32230 | 2020-06-25 15:14 | Section 3 | Material Requisition | Misc | Not on List | 1 | No | 18 | 18 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32230 | 32230 | 2020-06-25 15:14 | Section 3 | Material Requisition | Misc | Not on List | 1 | No | 14 | 14 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32230 | 32230 | 2020-06-25 15:14 | Section 3 | Material Requisition | Misc | Not on List | 1 | No | 18 | 18 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32237 | 32237 | 2020-06-26 08:59 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 43262 | 43262 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32237 | 32237 | 2020-06-26 08:59 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 66560 | 66560 | Miscellaneous | 2020-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32237 | 32237 | 2020-06-26 08:59 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 44800 | 44800 | Miscellaneous | 2020-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32237 | 32237 | 2020-06-26 08:59 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 48384 | 48384 | Miscellaneous | 2020-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32238 | 32238 | 2020-06-26 11:14 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32239 | 32239 | 2020-06-26 11:55 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No. | 43262 | 43262 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32240 | 32240 | 2020-06-26 11:58 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 66560 | 66560 | Miscellaneous | 2020-06-26 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32241 | 32241 | 2020-06-26 12:00 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No. | 44800 | 44800 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32242 | 32242 | 2020-06-26 12:04 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No. | 48384 | 48384 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32245 | 32245 | 2020-06-26 15:02 | Section 3 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 200 | Each | 2.48 | 496 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-06-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32245 | 32245 | 2020-06-26 15:02 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 36 | Each | 5.55 | 199.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-06-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32245 | 32245 | 2020-06-26 15:02 | Section 3 | Material Requisition | Not on List | Not on List | 16 | ea | 21.1 | 337.6 | Builders Merchants (General) | 2020-06-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32245 | 32245 | 2020-06-26 15:02 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 18 | Each | 6.34 | 114.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-06-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32272 | 32272 | 2020-06-29 12:33 | Section 6 | Material Requisition | Not on List | Not on List | 5 | NULL | 7.95 | 39.75 | Surveying Consumables | 2020-06-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 300 | Each | 6 | 1800 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 2 | Each | 11.94 | 23.88 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 2 | Each | 11.94 | 23.88 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 300 | Each | 3.52 | 1056 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 2 | Each | 7.68 | 15.36 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 2 | Each | 7.68 | 15.36 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 30 | Each | 3.03 | 90.9 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 30 | Each | 6 | 180 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 75 | Each | 6 | 450 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 80 | Each | 6 | 480 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 70 | Each | 6 | 420 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Bricks/Blocks | Not on List
80.08 | m2 | 69.5 | 5565.56 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | JP Flynn Construction Ltd | 14105 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32274 | REQ - Finance Team | NULL | NULL
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Bricks/Blocks | Not on List
55.44 | m2 | 69.54 | 3855.3 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | JP Flynn Construction Ltd | 14105 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32274 | REQ - Finance Team | NULL | NULL
MREQ-32277 | 32277 | 2020-06-29 16:36 | Section 4 | Material Requisition | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 10 | Each | 84.83 | 848.3 | Ductile Drainage | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32277 | 32277 | 2020-06-29 16:36 | Section 4 | Material Requisition | Not on List | Not on List | 8 | Each | 65.73 | 525.84 | Rebar and Mesh | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32283 | 32283 | 2020-06-30 07:20 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593)
35 | Each | 27.21 | 952.35 | Flow Control | 2020-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14089 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32283 | REQ - Finance Team | NULL | NULL
MREQ-32287 | 32287 | 2020-06-30 10:56 | Section 4 | Material Requisition | Concrete Drainage | CPM Chamber Ring 2400 x 1000 D/S (890451) | 2 | Each | 415.34 | 830.68 | Concrete Accessories | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32287 | 32287 | 2020-06-30 10:56 | Section 4 | Material Requisition | Concrete Drainage | CPM Chamber Ring 2400 x 500 D/S (890449) | 1 | Each | 285.72 | 285.72 | Concrete Accessories | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32287 | 32287 | 2020-06-30 10:56 | Section 4 | Material Requisition | Concrete Drainage | Not on List | 1 | NULL | 1224.54 | 1224.54 | Concrete Accessories | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32289 | 32289 | 2020-06-30 11:21 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 291.03 | 291.03 | Professional Services | 2020-06-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32290 | 32290 | 2020-06-30 11:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 114.87 | 114.87 | Professional Services | 2020-06-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32291 | 32291 | 2020-06-30 11:41 | Section 3 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 3.09 | 173.04 | Builders Merchants (General) | 2020-07-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32296 | 32296 | 2020-06-30 13:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 383.54 | 383.54 | Miscellaneous | 2020-06-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 164.96 | 164.96 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 187.5 | 187.5 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 390.96 | 390.96 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 112.5 | 112.5 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 21.56 | 21.56 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 195.62 | 195.62 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32311 | 32311 | 2020-07-01 11:38 | Section 2 | Material Requisition | Not on List | Not on List | 1 | £ | 1344 | 1344 | Professional Services | 2020-07-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 3010 - Ground Preparation, Cultivation and Mulching | IMO - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32312 | 32312 | 2020-07-01 12:13 | Section 5 | Material Requisition | Not on List | Not on List | 16 | No | 56.7 | 907.2 | Miscellaneous | 2020-07-01 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32314 | 32314 | 2020-07-01 13:54 | Section 2 | Material Requisition | Aggregate | A20 Pipe Bed | 60 | Tonnes | 21.75 | 1305 | Aggregate | 2020-07-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32323 | 32323 | 2020-07-02 07:54 | Section 4 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 400 | Each | 2.48 | 992 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32336 | 32336 | 2020-07-02 13:57 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 342 | 342 | Miscellaneous | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32337 | 32337 | 2020-07-03 13:26 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 342 | 342 | Miscellaneous | 2020-07-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32339 | 32339 | 2020-07-03 13:53 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 1825 | 1825 | Miscellaneous | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32340 | 32340 | 2020-07-03 14:12 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 1825 | 1825 | Miscellaneous | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32341 | 32341 | 2020-07-03 14:23 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2020-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32347 | 32347 | 2020-07-03 15:19 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 89.5 | 89.5 | Small Tools (Consumables) | 2020-07-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32348 | 32348 | 2020-07-03 15:26 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32371 | 32371 | 2020-07-06 11:05 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 18270 | 18270 | Office Supplies | 2020-07-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-32373 | 32373 | 2020-07-06 11:37 | Section 6 | Material Requisition | Not on List | Not on List | 1 | ea | 25832.98 | 25832.98 | Office Supplies | 2020-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32374 | 32374 | 2020-07-06 12:00 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2020-07-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-32375 | 32375 | 2020-07-06 12:02 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 480 | 480 | Miscellaneous | 2020-07-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-32390 | 32390 | 2020-07-07 10:12 | Section 4 | Material Requisition | Not on List | Not on List | 30 | No. | 2.85 | 85.5 | Miscellaneous | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32391 | 32391 | 2020-07-07 11:05 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2020-07-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32392 | 32392 | 2020-07-07 11:43 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 478.2 | 478.2 | Miscellaneous | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32393 | 32393 | 2020-07-07 13:56 | Test Section | Material Requisition | Ducting | Polypipe 110mm x 50m Ridgiduct Coil Blue (877802) | 33 | Each | 105.04 | 3466.32 | Blocks and Bricks | 2020-07-29 | Test Location | Test Section | Test Section | Operational Approval | NULL | NULL | Chris Henry
MREQ-32394 | 32394 | 2020-07-07 14:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | 1 | 365 | 365 | Ductile Drainage | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32395 | 32395 | 2020-07-07 15:45 | Section 6 | Material Requisition | Iron Wear | Not on List | 48 | each | NULL | 0 | Ductile Drainage | 2020-07-17 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32395 | 32395 | 2020-07-07 15:45 | Section 6 | Material Requisition | Iron Wear | Not on List | 17 | each | NULL | 0 | Ductile Drainage | 2020-07-17 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32398 | 32398 | 2020-07-07 16:41 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | £ | 349 | 349 | Small Tools (Consumables) | 2020-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32398 | 32398 | 2020-07-07 16:41 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32405 | 32405 | 2020-07-08 12:02 | Section 4 | Material Requisition | Not on List | Not on List | 3 | 12 kg tubs | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-07-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32405 | 32405 | 2020-07-08 12:02 | Section 4 | Material Requisition | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 30 | Each | 16.49 | 494.7 | Concrete Drainage | 2020-07-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32409 | 32409 | 2020-07-08 12:43 | Section 4 | Material Requisition | Not on List | Not on List | 1 | number | NULL | 0 | Ductile Drainage | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32411 | 32411 | 2020-07-08 13:32 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List
2 | Pounds | 61.57 | 123.14 | Small Tools (Consumables) | 2020-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32411 | REQ - Finance Team | NULL | NULL
MREQ-32411 | 32411 | 2020-07-08 13:32 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List
2 | Pounds | 29.9 | 59.8 | Small Tools (Consumables) | 2020-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32411 | REQ - Finance Team | NULL | NULL
MREQ-32412 | 32412 | 2020-07-08 14:42 | Core | Material Requisition | Misc | Not on List
1 | 908.6 | 908.6 | 908.6 | Office Supplies | 2020-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32412 | REQ - Finance Team | NULL | NULL
MREQ-32412 | 32412 | 2020-07-08 14:42 | Core | Material Requisition | Misc | Not on List
12 | 360 | 4320 | 51840 | Office Supplies | 2020-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32412 | REQ - Finance Team | NULL | NULL
MREQ-32412 | 32412 | 2020-07-08 14:42 | Core | Material Requisition | Misc | Not on List
1 | 1440 | 1440 | 1440 | Office Supplies | 2020-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32412 | REQ - Finance Team | NULL | NULL
MREQ-32413 | 32413 | 2020-07-08 15:23 | Section 2 | Material Requisition | Misc | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2020-07-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-32413 | 32413 | 2020-07-08 15:23 | Section 2 | Material Requisition | Misc | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2020-07-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-32415 | 32415 | 2020-07-08 16:05 | Section 2 | Material Requisition | Ducting | Not on List
2 | NULL | NULL | 0 | Miscellaneous | 2020-07-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32415 | REQ - Finance Team | NULL | NULL
MREQ-32421 | 32421 | 2020-07-09 09:33 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No, | 4024.75 | 4024.75 | Laboratory Equipment / Certification | 2020-07-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32423 | 32423 | 2020-07-09 12:11 | Section 6 | Material Requisition | Not on List | Not on List | 1 | 1 | 150 | 150 | PPE | 2020-07-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32424 | 32424 | 2020-07-09 12:27 | Section 2 | Material Requisition | Not on List | Not on List | 5 | ea | 66 | 330 | Ductile Drainage | 2020-07-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 504 - Drainage and Service Ducts in Structures | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-32429 | 32429 | 2020-07-09 15:57 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Boot Composite Toe/Mid Magnum Roadmaster Black S3 Hro Src (100054) | 1 | Each | 55.3 | 55.3 | PPE | 2020-07-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32433 | 32433 | 2020-07-10 07:29 | Section 4 | Material Requisition | Not on List | Not on List | 65 | Cubic meter | NULL | 0 | Concrete Accessories | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32433 | 32433 | 2020-07-10 07:29 | Section 4 | Material Requisition | Not on List | Not on List | 160 | Cubic meter | NULL | 0 | Concrete Accessories | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32433 | 32433 | 2020-07-10 07:29 | Section 4 | Material Requisition | Not on List | Not on List | 300 | Cubic meter | NULL | 0 | Concrete Accessories | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32433 | 32433 | 2020-07-10 07:29 | Section 4 | Material Requisition | Not on List | Not on List | 60 | Cubic meter | NULL | 0 | Concrete Accessories | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32433 | 32433 | 2020-07-10 07:29 | Section 4 | Material Requisition | Aggregate | Type 1
5000 | Tonnes | 23.5 | 117500 | Aggregate | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32433 | REQ - Finance Team | NULL | NULL
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 180.83 | 180.83 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 90 | 90 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 325 | 325 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | N0 | 59.8 | 59.8 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 375 | Ltrs | 0.8 | 300 | Gas Oil | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 85 | 85 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32454 | 32454 | 2020-07-10 14:44 | Section 6 | Material Requisition | Not on List | Not on List | 1 | 1 | 216.38 | 216.38 | Small Tools (Consumables) | 2020-07-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32454 | 32454 | 2020-07-10 14:44 | Section 6 | Material Requisition | Not on List | Not on List | 1 | 1 | 392.86 | 392.86 | Small Tools (Consumables) | 2020-07-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32465 | 32465 | 2020-07-13 12:04 | Section 6 | Material Requisition | Aggregate | Bedding Sand | 6 | Tonnes | 11.5 | 69 | Aggregate | 2020-07-14 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32480 | 32480 | 2020-07-14 10:33 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-07-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32480 | 32480 | 2020-07-14 10:33 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-07-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32482 | 32482 | 2020-07-14 12:02 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 1718.08 | 1718.08 | Miscellaneous | 2020-07-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32482 | REQ - Finance Team | NULL | NULL
MREQ-32482 | 32482 | 2020-07-14 12:02 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 228.64 | 228.64 | Miscellaneous | 2020-07-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32482/Request/20200713100503935.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32482 | REQ - Finance Team | NULL | NULL
MREQ-32482 | 32482 | 2020-07-14 12:02 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 331.03 | 331.03 | Miscellaneous | 2020-07-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32482/Request/20200713094531833.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32482 | REQ - Finance Team | NULL | NULL
MREQ-32482 | 32482 | 2020-07-14 12:02 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 245.34 | 245.34 | Miscellaneous | 2020-07-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32482 | REQ - Finance Team | NULL | NULL
MREQ-32482 | 32482 | 2020-07-14 12:02 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 556.36 | 556.36 | Miscellaneous | 2020-07-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32482 | REQ - Finance Team | NULL | NULL
MREQ-32484 | 32484 | 2020-07-14 15:57 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-07-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32486 | 32486 | 2020-07-15 08:02 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 60 | 60 | Small Tools (Consumables) | 2020-07-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-32487 | 32487 | 2020-07-15 08:36 | Section 4 | Material Requisition | Not on List | Not on List | 1 | £ | 621 | 621 | Professional Services | 2020-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
| MREQ-17041-001025 | 17041 |  | 2019-05-08 14:26 | Section 1
Material | Not on List | Not on List | Claim from Anglian Water | Claim from Anglain Water to recover the repair cost associated with the damage caused by the IDT to Anglain Water main, off A1 slip road northbound from the A14 | 1 | 1 | Damage Charges
2019-05-10
153f - Tempoary Works - Miscellaneous temporary works | A14 IDT | OP 11456 | Anglian Water Services Ltd (1106439) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32491 | 32491 | 2020-07-06 15:34 | Core | Material Requisition | Not on List | Not on List | 1 | Each | 478.2 | 478.2 | Miscellaneous | 2020-07-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32492 | 32492 | 2020-07-15 15:48 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 897.53 | 897.53 | Miscellaneous | 2020-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32493 | 32493 | 2020-07-15 16:39 | Section 6 | Material Requisition | Not on List | Not on List
150 | Number | NULL | 0 | Fixings and Fasteners | 2020-07-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32493 | REQ - Finance Team | NULL | NULL
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 27 | each | NULL | 0 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 31 | each | NULL | 0 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 1 | Pallet | 3.56 | 3.56 | Miscellaneous | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Twinwall | Not on List | 80 | meters | NULL | 0 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Twinwall | Not on List | 30 | meters | NULL | 0 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Twinwall | Not on List | 1 | bag | NULL | 0 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913)
6 | Each | 81.96 | 491.76 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | Skyland Contractors Ltd | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32494 | REQ - Finance Team | NULL | NULL
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 1 | Each | 36.62 | 36.62 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 2 | Each | 53.01 | 106.02 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 750 D/S (913226) | 1 | Each | 61.48 | 61.48 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 2 | each | NULL | 0 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 16 | each | NULL | 0 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 6 | each | NULL | 0 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 1 | each | NULL | 0 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Not on List | Not on List | 1 | pallet | NULL | 0 | Miscellaneous | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 1 | Each | 81.96 | 81.96 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 100 | Each | 1.98 | 198 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32496 | 32496 | 2020-07-16 06:23 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 1367.93 | 1367.93 | Office Supplies | 2020-07-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-31959 | 31959 | 2020-06-09 10:17 | Section 6 | Material Requisition | Not on List | Not on List
130 | number | NULL | 0 | Fixings and Fasteners | 2020-06-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31959 | REQ - Finance Team | NULL | NULL
MREQ-32498 | 32498 | 2020-07-16 10:13 | Core | Material Requisition | Not on List | Not on List | 1 | Each | 90 | 90 | Professional Services | 2020-07-16 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32498 | 32498 | 2020-07-16 10:13 | Core | Material Requisition | Misc | Not on List | 1 | Each | 1825 | 1825 | Miscellaneous | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32498 | 32498 | 2020-07-16 10:13 | Core | Material Requisition | Misc | Not on List | 1 | Each | 1825 | 1825 | Miscellaneous | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32498 | 32498 | 2020-07-16 10:13 | Core | Material Requisition | Misc | Not on List | 1 | Each | 342 | 342 | Miscellaneous | 2020-07-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32498 | 32498 | 2020-07-16 10:13 | Core | Material Requisition | Misc | Not on List | 1 | Each | 342 | 342 | Miscellaneous | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32500 | 32500 | 2020-07-16 12:10 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | Each | 0 | 0 | Laboratory Equipment / Certification | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32500 | 32500 | 2020-07-16 12:10 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | Each | 0 | 0 | Laboratory Equipment / Certification | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32500 | 32500 | 2020-07-16 12:10 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | Each | 0 | 0 | Laboratory Equipment / Certification | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32501 | 32501 | 2020-07-16 12:17 | Core | Material Requisition | Not on List | Not on List | 1 | Each | 10648.5 | 10648.5 | Miscellaneous | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32502 | 32502 | 2020-07-16 12:21 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2020-07-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32503 | 32503 | 2020-07-16 12:25 | Core | Material Requisition | Not on List | Not on List
1 | Number | NULL | 0 | PPE | 2020-07-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32503 | REQ - Finance Team | NULL | NULL
MREQ-32503 | 32503 | 2020-07-16 12:25 | Core | Material Requisition | Not on List | Not on List
1 | Number | NULL | 0 | PPE | 2020-07-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32503 | REQ - Finance Team | NULL | NULL
MREQ-32503 | 32503 | 2020-07-16 12:25 | Core | Material Requisition | Not on List | Not on List
1 | Number | NULL | 0 | PPE | 2020-07-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32503 | REQ - Finance Team | NULL | NULL
MREQ-17049-001025 | 17049 |  | 2019-05-08 15:56 |  | Section 4 | Material
20 GS6 sets needed for newly installed gantarys ( stats ) | 20 | Each | 285 | 5700 | Builders Merchants (General) | 2019-05-09
GN4A - Gantry structures | 1802 - Miscellaneous Metalwork | A14 IDT
11412/OP/3310504
Greenham Trading Ltd (1100463)
Stores - Closed | NULL | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17049-001025 | 17049 |  | 2019-05-08 15:56 |  | Section 4 | Material | Pendant Barrier Marker | NULL | 60 | Each | 10.7 | 642 | Builders Merchants (General) | 2019-05-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries | 102 - Compound running costs
A14 IDT
11412/OP/3310504
Greenham Trading Ltd (1100463)
Stores - Closed | NULL | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
| MREQ-17057-001025 | 17057 |  | 2019-05-08 17:15 |  | Section 4 | Not on List | Flexitrace 9mmx120m - Land Surveying Equipment
NULL | 1 | Each | 750 | 750 | Surveying Consumables | 2019-05-17
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
102 - Compound running costs
A14 IDT
11408/OP/3310504
Gap Group Ltd (1108091)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17058-001025
17058 | 2019-05-08 17:12
Section 3 | Material | Not on List
Not on List
Fibre Glass Survey Pins
Deliver to Ermine Street Compound
50 | EAch | 7.1 | 355 | Miscellaneous | 2019-05-09
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
SC3A - Roadworks
2701 - Accommodation works
A14 IDT
11426/OP/3310503
SCCS Survey Equipment Ltd t/a (1101886)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32506 | 32506 | 2020-07-16 14:53 | Section 2 | Material Requisition | Not on List | Not on List | 1 | £ | 4778.1 | 4778.1 | Professional Services | 2020-07-16 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-17060-001025
17060 | 2019-05-08 17:57
Section 3
Material | Not on List | Concrete Flat Top Edging 50x150x915 (805282)
NULL | 43 pallets required
1440 | Each | 1.5 | 2160 | Blocks and Bricks
2019-05-13
Gate C - 1339699 - BN08 via Logistics Yard Access
SC3B - Roadworks
1101 - Kerbs, Channels and Edgings
A14 IDT | 11432 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17069-001025
17069 | 2019-05-09 08:35
Core | Material | PPE, Small Tools and Consumables
Not on List | James Fisher Quote 29178.13
NULL | 2 | Each | 90 | 180 | Laboratory Equipment / Certification
2019-05-09
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
Preliminaries | 106 - Testing equipment and materials testing
A14 IDT
11451/OP/3310500
James Fisher Testing Services (1114318)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32507 | 32507 | 2020-07-16 15:20 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 2596.52 | 2596.52 | Miscellaneous | 2020-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-17071-001025
17071 | 2019-05-09 08:00
Section 6
Material | Concrete Drainage
Not on List | 1200mm x 750mm high concrete chamber rings
| 4 | No | 95.27 | 381.08 | Concrete Drainage | 2019-05-15
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11415 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17071-001025
17071 | 2019-05-09 08:00
Section 6
Material | Concrete Drainage
Not on List | 1200mm x 500mm high concrete chamber rings
NULL | 4 | No | 82.45 | 329.8 | Concrete Drainage | 2019-05-15
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11415 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17071-001025
17071 | 2019-05-09 08:00
Section 6
Material | Concrete Drainage
Not on List | 1200mm x 250mm high concrete chamber rings
NULL | 3 | No | 55.41 | 166.23 | Concrete Drainage | 2019-05-15
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11415 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17071-001025
17071 | 2019-05-09 08:00
Section 6
Material | Concrete Drainage
Not on List | Manhole Rings Tokstrip
NULL | 8 | No | 28.56 | 228.48 | Concrete Drainage | 2019-05-15
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11415 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17071-001025
17071 | 2019-05-09 08:00
Section 6
Material | Concrete Drainage
Not on List | Manhole Rings Tokstrip Primer (10 litres)
NULL | 2 | No | 27.6 | 55.2 | Concrete Drainage | 2019-05-15
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11415 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17072-001025
17072 | 2019-05-09 08:48
Core | Material | Not on List
Not on List
Uplift to existing order (previous req MREQ10044)
110 | No | 48 | 5280 | Miscellaneous | 2019-05-15
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
113 - Survey Equipment Costs
A14 IDT
8915 | Radiodetection Ltd. (1113308)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17074-001025
17074 | 2019-05-09 09:27
Core | Material | PPE, Small Tools and Consumables | Not on List | FGG Circular Connector
NULL | 2 | Each | 38.9 | 77.8 | Laboratory Equipment / Certification
2019-05-09
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
120 - Small Tools (hand)
A14 IDT
11459/OP/3310500
E H Smith (Builders Merchants) (1113953)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17080-001025
17080 | 2019-05-09 10:23
Section 2 | Material | Not on List
Not on List
Gabion basket 2m x 1m x 1m
NULL | 36 | Units | 0 | 0 | Concrete Drainage
2019-05-10
Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton
SC2B - Roadworks - A14
503 - Headwalls and Outfall Works
Skyland Contractors Ltd
OP11418 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17080-001025
17080 | 2019-05-09 10:23
Section 2 | Material | Not on List
Not on List
Reno Matress 3m x 2m x 0.17m
NULL | 80 | Units | 0 | 0 | Concrete Drainage
2019-05-10
Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton
SC2B - Roadworks - A14
503 - Headwalls and Outfall Works
Skyland Contractors Ltd
OP11418 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17080-001025
17080 | 2019-05-09 10:23
Section 2 | Material | Not on List
Not on List
Reno Matress 3m x 2m x 023m
NULL | 20 | Units | 0 | 0 | Concrete Drainage
2019-05-10
Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton
SC2B - Roadworks - A14
503 - Headwalls and Outfall Works
Skyland Contractors Ltd
OP11418 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17080-001025
17080 | 2019-05-09 10:23
Section 2 | Material | Not on List
Not on List
Gabion basket 2m x 1m x 0.5m
NULL | 4 | Units | 0 | 0 | Concrete Drainage
2019-05-10
Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton
SC2B - Roadworks - A14
503 - Headwalls and Outfall Works
Skyland Contractors Ltd
OP11418 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17080-001025
17080 | 2019-05-09 10:23
Section 2 | Material | Not on List
Not on List
Lacing Wire
NULL | 1000 | Units | 0 | 0 | Concrete Drainage
2019-05-10
Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton
SC2B - Roadworks - A14
503 - Headwalls and Outfall Works
Skyland Contractors Ltd
OP11418 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17082-001025
17082 | 2019-05-09 08:55
Section 2 | Material | Not on List
Not on List
Stainless Steel Tie Wire Rolls
NULL | 20 | Each | 0 | 0 | Concrete Accessories
2019-05-13
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
BN27 - A14/A1 Link Overbridge
1704 - Reinforcement for Structures
Sian Formwork Ltd
OP11419
Blue Bay Building Products Ltd (1109669)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17082-001025
17082 | 2019-05-09 08:55
Section 2 | Material | Not on List
Not on List
Fosroc Render Roc HB45 25kg Bag
NULL | 10 | Each | 0 | 0 | Concrete Accessories
2019-05-13
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
BN03 - A1 Brampton Interchange Bridge
1701 - Insitu Concrete
Sian Formwork Ltd
OP11419
Blue Bay Building Products Ltd (1109669)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17096-001025
17096 | 2019-05-09 11:37
Section 3 | Material | Not on List
Not on List
Size 8 G40 galvanized tube 40mm x 3.2m
NULL | 180 | No | 24.1 | 4338 | Miscellaneous | 2019-05-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
1701 - Insitu Concrete
A14 IDT
11423
Orbital Fasteners Ltd (1118568)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17096-001025
17096 | 2019-05-09 11:37
Section 3 | Material | Not on List
Not on List
C50 - slope elbow 0-11
To suit G40 tubing
13 | No | 6.61 | 86 | Miscellaneous | 2019-05-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
1701 - Insitu Concrete
A14 IDT
11423
Orbital Fasteners Ltd (1118568)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17096-001025
17096 | 2019-05-09 11:37
Section 3 | Material | Not on List
Not on List
C04 - Long Tee
To suit G40 tubing
13 | No | 4.5 | 59 | Miscellaneous | 2019-05-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
1701 - Insitu Concrete
A14 IDT
11423
Orbital Fasteners Ltd (1118568)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17096-001025
17096 | 2019-05-09 11:37
Section 3 | Material | Not on List
Not on List
C05A - Variable Elbow (11°-30°)
To suit G40 tubing
13 | No | 6.26 | 81 | Miscellaneous | 2019-05-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
1701 - Insitu Concrete
A14 IDT
11423
Orbital Fasteners Ltd (1118568)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17096-001025
17096 | 2019-05-09 11:37
Section 3 | Material | Not on List
Not on List
C12 - Railing Base Flange
To suit G40 tubing
9 | No | 5.6 | 50 | Miscellaneous | 2019-05-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
1701 - Insitu Concrete
A14 IDT
11423
Orbital Fasteners Ltd (1118568)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17096-001025
17096 | 2019-05-09 11:37
Section 3 | Material | Not on List
Not on List
C22 - Two Socket Cross
To suit G40 tubing
17 | No | 17 | 289 | Miscellaneous | 2019-05-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
1701 - Insitu Concrete
A14 IDT
11423
Orbital Fasteners Ltd (1118568)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17096-001025
17096 | 2019-05-09 11:37
Section 3 | Material | Not on List
Not on List
C52 - Long slope tee 0 to 11
To suit G40 tubing
72 | No | 7.4 | 533 | Miscellaneous | 2019-05-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
1701 - Insitu Concrete
A14 IDT
11423
Orbital Fasteners Ltd (1118568)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17096-001025
17096 | 2019-05-09 11:37
Section 3 | Material | Not on List
Not on List
C54 - Slope 2 socket cross 0-11
To suit G40 tubing
127 | No | 7.39 | 939 | Miscellaneous | 2019-05-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
1701 - Insitu Concrete
A14 IDT
11423
Orbital Fasteners Ltd (1118568)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17096-001025
17096 | 2019-05-09 11:37
Section 3 | Material | Not on List
Not on List
C53 - Slope base 0-11
To suit G40 tubing
68 | No | 8.12 | 552 | Miscellaneous | 2019-05-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
1701 - Insitu Concrete
A14 IDT
11423
Orbital Fasteners Ltd (1118568)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17096-001025
17096 | 2019-05-09 11:37
Section 3 | Material | Not on List
Not on List
100mm Thunder Bolts
To suit G40 tubing
200 | No | 0.62 | 124 | Miscellaneous | 2019-05-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
1701 - Insitu Concrete
A14 IDT
11423
Orbital Fasteners Ltd (1118568)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17097-001025
17097 | 2019-05-09 13:21
Core | Material | Signage | Banners - 4500x 1500
CCS Ultrasite Mega Banner
This has been ordered from the CCS.
1 | Each | 282 | 282 | Miscellaneous | 2019-05-12
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
PRLM - Preliminaries
102 - Compound running costs
A14 IDT
OP 11471
Actaccom Ltd (1245624)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17100-001025
17100 | 2019-05-09 13:41
Core | Material | Not on List
Not on List
Holiday Inn - Meeting room invoice
Payment for the use of a meeting room at Holiday Inn Histon. This was for engagment purposes for Milton residents.
1 | No | 360 | 360 | Miscellaneous | 2019-05-08
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
123 - Venue / Meeting Costs (Hotel Conf etc)
A14 IDT
NULL | Unlisted
IMO - Closed
Yes - Approve | Yes - Approve | Yes | Holiday Inn Histon
NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339)
NULL | NULL | 50 | Each | 24.99 | 1249.5 | Plastic Drainage
2019-05-16
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562)
NULL | NULL | 4 | Each | 37.6 | 150.4 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364)
NULL | NULL | 6 | Each | 130.26 | 781.56 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593)
NULL | NULL | 10 | Each | 11.34 | 113.4 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037)
NULL | NULL | 6 | Each | 42.87 | 257.22 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066)
NULL | NULL | 40 | Each | 3.65 | 146 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019)
NULL | NULL | 15 | Each | 1.98 | 29.7 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109)
NULL | NULL | 5 | Each | 7.06 | 35.3 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 400mm Coupler (346401)
NULL | NULL | 7 | Each | 18.84 | 131.88 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385)
NULL | NULL | 30 | Each | 0.91 | 27.3 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386)
NULL | NULL | 80 | Each | 2 | 160 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388)
NULL | NULL | 10 | Each | 2.97 | 29.7 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Polypipe 400mm Seal (346394)
NULL | NULL | 14 | Each | 9.76 | 136.64 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Not on List
1No. Drainage Air Testing Kit
NULL | 1 | Each | 32.5 | 32.5 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11435
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Not on List
1No. Set of 150mm dia pipe stoppers for air test
NULL | 2 | Each | 9.35 | 18.7 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11435
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Not on List
1No. Set of 225mm dia pipe stoppers for air test
NULL | 2 | Each | 21.35 | 42.7 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11435
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Not on List
1No. Set of 300mm dia pipe stoppers for air test
NULL | 2 | Each | 33.45 | 66.9 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11435
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Not on List
1No. Set of 400mm dia pipe stoppers for air test
NULL | 2 | Each | 61.45 | 122.9 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11435
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17101-001025
17101 | 2019-05-09 09:21
Section 6
Material | Twinwall | Not on List
2.5kg x 4 No. Tins of plastic drainage grease
NULL | 4 | Each | 21.29 | 85.16 | Plastic Drainage
2019-05-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
501 - Drains
A14 IDT
11421
Keyline Builders Merchants Ltd (1100980) | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17106-001025
17106 | 2019-05-09 15:30
Section 1
Material | Not on List
Not on List
3m x 2m x 0.15m gabion matress
Deliver to bramtpon compound
4 | Each | 0 | 0 | Concrete Drainage
2019-05-13
Gate 1 - 1339601 - Main Compound Alconbury
SEC1 - Roadworks
503 - Headwalls and Outfall Works
Skyland Contractors Ltd
NULL | NULL | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17122-001025
17122 | 2019-05-09 16:32
Section 3
Material | Not on List
Not on List
Service/repair to Zip boilers - PAY ON P CARD
Service/repairs to Zip wall mounted water heaters undertaken in Dec 2018
1 | No | 989.82 | 989.82 | Miscellaneous
2019-05-09
Gate D - 1339643 - BN10 Via Main Compound Entrance
PLM3 - Site Preliminaries
102 - Compound running costs
A14 IDT
11442/op/3310503
ZIP Heaters (UK) LTD
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17123-001025
17123 | 2019-05-09 16:33
Core
Material | Not on List
Not on List
various items required for the finishing works as asked for by Andrew Curwen (works manager)
Please see attached file
1 | Each | 393.68 | 393.68 | Small Tools (Consumables)
2019-05-14
Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core)
WAOC - Working Areas overhead Costs
120 - Small Tools (hand)
A14 IDT
11443/OP/3310500
Orbital Fasteners Ltd (1118568)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Waistcoat sleeved yellow with red braces - Small
NULL | 2 | Each | 9.08 | 18.16 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Waistcoat sleeved yellow with red braces - Medium
NULL | 3 | Each | 9.08 | 27.24 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Waistcoat sleeved yellow with red braces - Large
NULL | 3 | Each | 9.08 | 27.24 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Waistcoat sleeved yellow with red braces - XLarge
NULL | 3 | Each | 9.08 | 27.24 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Waistcoat sleeved yellow with red braces - XXLarge
NULL | 2 | Each | 9.08 | 27.24 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
KeepSAFE Pro Women's Executive Long Sleeved Waistcoat - Saturn Yellow - XLarge - 015214
NULL | 5 | Each | 6.5 | 32.5 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
KeepSAFE Pro Women's Executive Long Sleeved Waistcoat - Saturn Yellow - XXLarge - 015214
NULL | 5 | Each | 6.5 | 32.5 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023)
Size 30
NULL | 2 | Each | 13 | 26 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023)
Size 32
NULL | 2 | Each | 13 | 26 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023)
Size 34
NULL | 4 | Each | 13 | 52 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023)
Size 36
NULL | 4 | Each | 13 | 52 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023)
Size 38
NULL | 4 | Each | 13 | 52 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023)
Size 40 | NULL | 4 | Each | 13 | 52 | PPE
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
KeepSAFE Nylon Sweatband - 272409
NULL | 100 | Each | 0.85 | 85 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Bucket Flexi Tub 26 Litre Black (506342)
NULL | NULL | 20 | Each | 7.42 | 148.8 | PPE
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Cutting Metal Blades - 300 x 3.5 x 20.00
NULL | 50 | Each | 1.35 | 67.5 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11488 | Ashtead Plant Hire Company Ltd (1109463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Thin Cutting Metal Blades for 4.5 inch grinder - 4" x .045"
NULL | 25 | Each | 0.52 | 13 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11488 | Ashtead Plant Hire Company Ltd (1109463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289)
NULL | NULL | 10 | Each | 5.97 | 59.7 | PPE
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Concrete scraper
NULL | 5 | Each | 14.74 | 73.7 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Hilti Nails
NULL | 2 | Box | 0 | 0 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Measuring Jugs - 500 Ml
NULL | 5 | Each | 4.27 | 21.35 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11488 | Ashtead Plant Hire Company Ltd (1109463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Danger Overhead Cables Cone (sleeves)
NULL | 100 | Each | 4.76 | 476 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Dulux Non Drip Gloss 5L - White
NULL | 3 | Each | 0 | 0 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11493
Keyline Builders Merchants Ltd (1100980)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | Timber
2440x1220x12mm Shuttering Ply (638572)
NULL | NULL | 1 | Load | 16.5 | 16.5 | PPE
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11493
Keyline Builders Merchants Ltd (1100980)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Coverall Hivis Yellow Protal Inherent Fr Fra63 Regular Leg31 (370489)
Medium
NULL | 2 | Each | 97.85 | 195.7 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Coverall Hivis Yellow Protal Inherent Fr Fra63 Regular Leg31 (370489)
Large | NULL | 3 | Each | 97.85 | 293.55 | PPE
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Coverall Hivis Yellow Protal Inherent Fr Fra63 Regular Leg31 (370489)
XLarge
NULL | 2 | Each | 97.85 | 195.7 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Keep Safe First Aid Kit - Burns Dispenser Kit (254960)
NULL | NULL | 10 | Each | 11.64 | 116.4 | PPE
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Ear Muff Helmet Mounted Jsp Inter Ex Black/Red Snr28 (254222)
NULL | NULL | 10 | Each | 13.44 | 134.4 | PPE
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Bulldog Powerbreaker Insulated Treaded Newcastle Drainer Shovel -762662
NULL | 10 | Each | 60.18 | 601.8 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Evolite Skyworker Helmet White A14 & Home Safe Logos -873443
NULL | 32 | Each | 28.8 | 921.6 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17150-001025
17150 | 2019-05-10 09:24
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Evolite Skyworker Helmet Black A14 & Home Safe Logos -873444
NULL | 16 | Each | 28.8 | 460.8 | PPE | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
102 - Compound running costs
A14 IDT
OP 11486
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17154-001025
17154 | 2019-05-10 11:05
Section 5
Material | Not on List
Not on List
Sheet piles and HL profiles for BE25 and BE26
as per attachement
1 | Each | 1026112.98 | 1026112.98 | Miscellaneous
2019-06-03
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
BE25 - Impington Guided Busway Bridge Modifications
1601 - Piling and attendances
JN Piling Ltd
11431
Stabau
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17183-001025
17183 | 2019-05-10 13:14
Section 4
Material | Not on List
Not on List
EPDM Pads
NULL | 1000 | Each | 1.34 | 1340 | Miscellaneous
2019-05-15
RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road)
BN25 - Girton Interchange Bridge A
1702 - Precast Concrete
Keller Ltd
4798 | Reinforced Earth Co Ltd (1113429)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17183-001025
17183 | 2019-05-10 13:14
Section 4
Material | Not on List
Not on List
Delivery Charge
NULL | 1 | Each | 325 | 325 | Miscellaneous
2019-05-15
RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road)
BN25 - Girton Interchange Bridge A
1702 - Precast Concrete
Keller Ltd
4798 | Reinforced Earth Co Ltd (1113429)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17183-001025
17190 | 2019-05-10 14:24
Core
Material | Not on List
Not on List
Payment for 2019 National Ultrs Site Awards Attendance
Approval sought for P-card payment
1 | Tables | 2952 | 2952 | Miscellaneous
2019-05-14
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
122 - Entertainment
A14 IDT
NULL | CCS
IMO - Closed
Yes - Approve | Yes - Approve | Yes
NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2952
NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17210-001025
17210 | 2019-05-10 16:13
Section 5
Material | Not on List
Not on List
Elastomeric Bearing - Type: W1-5 for BE25
Refer to RFI 3336 for Bearing approvals based on SK Bearing Design
5 | No | 214 | 1070 | Miscellaneous
2019-06-17
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
BE25 - Impington Guided Busway Bridge Modifications
2101 - Bearings
A14 IDT
NULL | NULL | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17210-001025
17210 | 2019-05-10 16:13
Section 5
Material | Not on List
Not on List
Elastomeric Bearing - Type: E1-5 for BE25
Refer to RFI 3337 for Bearing approvals based on SK Bearing Design
5 | No | 214 | 1070 | Miscellaneous
2019-06-17
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
BE25 - Impington Guided Busway Bridge Modifications
2101 - Bearings
A14 IDT
NULL | NULL | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17210-001025
17210 | 2019-05-10 16:13
Section 5
Material | Not on List
Not on List
Elastomeric Bearing - Compresion Stiffness Test
1no test required for each bearing type e.g. 1no for E, 1no for W.
2 | No | 175 | 350 | Miscellaneous
2019-06-17
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
BE25 - Impington Guided Busway Bridge Modifications
2101 - Bearings
A14 IDT
NULL | NULL | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17210-001025
17210 | 2019-05-10 16:13
Section 5
Material | Not on List
Not on List
Elastomeric Bearing - Shear Stiffness Test
1no test required for each bearing type e.g. 1no for E, 1no for W.
2 | No | 225 | 450 | Miscellaneous
2019-06-17
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
BE25 - Impington Guided Busway Bridge Modifications
2101 - Bearings
A14 IDT
NULL | NULL | Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17212-001025
17212 | 2019-05-10 16:34
Section 3
Material | Twinwall
Not on List
300mm ID Endcaps for twinwall drainage
NULL | 30 | No | 13.75 | 412.5 | Plastic Drainage
2019-05-17
Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard
SC3A - Roadworks
501 - Drains
A14 IDT
11454 | E H Smith (Builders Merchants) (1113953)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17227-001025
17227 | 2019-05-12 23:01
Section 2
Material | Ducting | Not on List
Purple ridgiducts 110mm x 6m
Please, ensure the duct are not bigger than 110mm external.
20 | No | 0 | 0 | Miscellaneous
2019-05-16
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
GN2B - Gantry structures
1805 - Cantilever Structures
A14 IDT
OP17227
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17228-001025
17228 | 2019-05-13 07:32
Section 4
Material | Not on List
Not on List
A Plant, consumable costs, at end of hire period
total cost £1074.22
1 | Each | 1074.22 | 1074.22 | Miscellaneous | 2019-05-15
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11499/OP/3310504
Ashtead Plant Hire Company Ltd (1109463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17229-001025
17229 | 2019-05-13 07:42
Section 5
Material | Not on List
Not on List
A Plant, consumable costs
1 | Each | 205.81 | 205.81 | Miscellaneous | 2019-05-15
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11452
Ashtead Plant Hire Company Ltd (1109463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17232-001025
17232 | 2019-05-13 08:04
Section 2
Material | Not on List
Not on List
A Plant, consumable costs, total cost £134.23
see attached for details
1 | Each | 67.06 | 67.06 | Miscellaneous | 2019-05-15
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
PLM2 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11460
Ashtead Plant Hire Company Ltd (1109463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17249-001025
17249 | 2019-05-13 09:24
Core
Material | Not on List
Not on List
Return to listing Draka UC-Connect Cat5e UC300 U/UTP Data Cables
NULL | 4 | Each | 66.78 | 267 | Miscellaneous | 2019-05-20
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
117 - Computer & Acc Charges
A14 IDT
NULL | NULL | IMO - Closed
Yes - Approve | Yes - Approve | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 267 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17257-001025
17257 | 2019-05-13 11:27
Section 3
Material | Bagged
OP Cement Multicem Plastic Bag 25kg (210768)
Deliver to logistics yard
NULL | 112 | Bags | 3.56 | 398.72 | Builders Merchants (General)
2019-05-14
Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard
SC3B - Roadworks
502 - Chambers & Gullies
A14 IDT
11445
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17259-001025
17259 | 2019-05-13 11:30
Section 4
Material | Kerbs | Not on List
HB1 Kerbs - 305mm x 150mm x 914mm
For BN25 deck
50 | Each | 9.48 | 474 | Concrete Hard Landscaping (Kerbs, Slabs)
2019-05-20
RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound
SC4C - Roadworks - Dry Drayton to Girton
1101 - Kerbs, Channels and Edgings
JP Flynn Construction Ltd
11468
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17259-001025
17259 | 2019-05-13 11:30
Section 4
Material | Kerbs | Not on List
Quadrants QHB 305mm X 305mm X 255mm
For BN25 deck
2 | Each | 13.39 | 26.78 | Concrete Hard Landscaping (Kerbs, Slabs)
2019-05-20
RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound
SC4C - Roadworks - Dry Drayton to Girton
1101 - Kerbs, Channels and Edgings
JP Flynn Construction Ltd
11468
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17259-001025
17259 | 2019-05-13 11:30
Section 4
Material | Not on List
Not on List
Carriage | NULL | 1 | Each | 102.85 | 102.85 | Concrete Hard Landscaping (Kerbs, Slabs)
2019-05-20
RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound
SC4C - Roadworks - Dry Drayton to Girton
1101 - Kerbs, Channels and Edgings
JP Flynn Construction Ltd
11468
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17259-001025
17259 | 2019-05-13 11:30
Section 4
Material | Not on List
Not on List
Mechanical offload
NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs)
2019-05-20
RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound
SC4C - Roadworks - Dry Drayton to Girton
1101 - Kerbs, Channels and Edgings
JP Flynn Construction Ltd
11468
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32526 | 32526 | 2020-07-19 02:11 | Section 6 | Material Requisition | Iron Wear | Not on List
2 | NULL | NULL | 0 | Miscellaneous | 2020-07-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32526 | REQ - Finance Team | NULL | NULL
MREQ-17297-001025
17297 | 2019-05-13 15:19
Core | Material | PPE, Small Tools and Consumables
Not on List
Impact Quote 38mm Sample Tubes & End Caps QW0219
NULL | 1
Each | 143 | 143 | Laboratory Equipment / Certification
2019-05-13
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
120 - Small Tools (hand)
A14 IDT
11470/OP/3310500
Impact Test Equipment Ltd (1111862)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17327-001025
17327 | 2019-05-14 06:35
Section 5
Material | Not on List | Not on List | Lynch plant, punctures& stolen batterys
total cost £1037.00
1 | Each | 1037 | 1037 | Miscellaneous
2019-05-16
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11457
L Lynch (Plant Hire & Haulage) (1112290)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17328-001025
17328 | 2019-05-14 06:46
Section 4
Material | Not on List | Not on List | Lynch plant, puncture repairs
total cost £855.00
1 | Each | 855 | 855 | Miscellaneous
2019-05-16
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11498/OP/3310504
L Lynch (Plant Hire & Haulage) (1112290)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17337-001025
17337 | 2019-05-14 07:39
Section 2
Material | Not on List | Not on List | Lynch plant, puncture repairs
total cost £899.15
1 | Each | 899.15 | 899.15 | Miscellaneous
2019-05-16
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
PLM2 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11461 | L Lynch (Plant Hire & Haulage) (1112290)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17339-001025
17339 | 2019-05-14 07:53
Section 1 | Material | Not on List | Not on List | Lynch plant, puncture repairs
1 | Each | 395 | 395 | Miscellaneous
2019-05-16
Gate 1 - 1339601 - Main Compound Alconbury
PLM1 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11479
L Lynch (Plant Hire & Haulage) (1112290)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17349-001025
17349 | 2019-05-14 08:37
Section 1 | Material | Not on List | Not on List | A Plant, consumable costs, total cost £93.79
see attached for details
1 | Each | 93.79 | 93.79 | Miscellaneous | 2019-05-16
Gate 1 - 1339601 - Main Compound Alconbury
PLM1 - Site Preliminaries
153f - Tempoary Works - Miscellaneous temporary works
A14 IDT
11464
Ashtead Plant Hire Company Ltd (1109463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17352-001025
17352 | 2019-05-14 08:46
Section 4
Material | Not on List | Not on List | Gap Welfare, consumables, at end of hire.
see attached for details
1 | Each | 204.52 | 204.52 | Miscellaneous | 2019-05-16
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11497/OP/3310504
Gap Group Ltd (1108091)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17357-001025
17357 | 2019-05-14 09:06
Core | Material | PPE, Small Tools and Consumables
Not on List | consumables
NULL | 1 | Each | 931.72 | 931.72 | Janitorial
2019-05-17
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
PRLM - Preliminaries
102 - Compound running costs
A14 IDT
11469/OP/3310500
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17371-001025
17371 | 2019-05-14 12:46
Section 4
Material | Not on List
Not on List
Soltex high density joint filler
2m x 1m sheets
30 | Sheets | 24.28 | 728.4 | Builders Merchants (General)
2019-05-15
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
BN19 - Robins Lane Bridge
1701 - Insitu Concrete
A14 IDT
11463
Blue Bay Building Products Ltd (1109669)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17371-001025
17371 | 2019-05-14 12:46
Section 4
Material | Not on List
Not on List
CHS 140mm x 800mm galvinised sleeves
NULL | 48 | No | 47.89 | 2298.72 | Builders Merchants (General)
2019-05-17
RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound
SC4A - Roadworks - Swavesey to Robins Lane
1502 - Trenches, Ducts and Chambers
A14 IDT
11463
Blue Bay Building Products Ltd (1109669)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17385-001025
17385 | 2019-05-14 14:56
Section 2
Material | PPE, Small Tools and Consumables
Not on List
3m Versafol TR-315UK+ Starter Kit
FAO: Laura Jones
1 | Each | 539.1 | 539.1 | PPE
2019-05-27
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC2B - Roadworks - A14
606 - Import
A14 IDT
OP17385
Greenham Trading Ltd (1100463)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17385-001025
17385 | 2019-05-14 14:56
Section 2
Material | PPE, Small Tools and Consumables
Not on List
3m Versaflo M-306 Helmet
FAO: Laura Jones
1 | Each | 242.1 | 242.1 | PPE
2019-05-27
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC2B - Roadworks - A14
606 - Import
A14 IDT
OP17385
Greenham Trading Ltd (1100463)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17392-001025
17392 | 2019-05-14 15:51
Section 6
Material | Not on List
Not on List
Swift nest boxes to replace breeding sites lost from removal of Huntingdon viaduct.
Will be installed on to local residents houses following visitations.
27 | Each | 40.5 | 1093.5 | Miscellaneous | 2019-07-01
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
3030 - Special Ecological Measures
A14 IDT
11504 | Wildcare
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17406-001025
17406 | 2019-05-14 17:07
Section 3 | Material | PPE, Small Tools and Consumables
Not on List
Square Bar Spacers - 60 mm
2 Pallets of 60 mm Square Bar Spacers
400 | Each | 1.16 | 464 | Concrete Accessories
2019-05-16
Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard
CL3B - Structures (Culverts) 3B
1701 - Insitu Concrete
Kelly Formwork (UK) Ltd
11495
Blue Bay Building Products Ltd (1109669)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17412-001025
17412 | 2019-05-14 17:27
Section 2
Material | Not on List
Not on List
Ekspan 325 channel Drain section (2m Long)
See attached brochure
25 | Each | 0 | 0 | Concrete Accessories
2019-05-21
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC2B - Roadworks - A14
504 - Drainage and Service Ducts in Structures
A14 IDT
OP11475
Ekspan Ltd (1110734)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17412-001025
17412 | 2019-05-14 17:27
Section 2
Material | Not on List
Not on List
Ekspan 325 Channel 90Degree joint (Left)
See attached brochure
3 | Each | 0 | 0 | Concrete Accessories
2019-05-21
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC2B - Roadworks - A14
504 - Drainage and Service Ducts in Structures
A14 IDT
OP11475
Ekspan Ltd (1110734)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17412-001025
17412 | 2019-05-14 17:27
Section 2
Material | Not on List
Not on List
Ekspan 325 Flushing Unit Verge Box
See attached brochure
2 | Each | 0 | 0 | Concrete Accessories
2019-05-21
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC2B - Roadworks - A14
504 - Drainage and Service Ducts in Structures
A14 IDT
OP11475
Ekspan Ltd (1110734)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17412-001025
17412 | 2019-05-14 17:27
Section 2
Material | Not on List
Not on List
Ekspan 325 Transition piece
See attached brochure
2 | Each | 0 | 0 | Concrete Accessories
2019-05-21
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC2B - Roadworks - A14
504 - Drainage and Service Ducts in Structures
A14 IDT
OP11475
Ekspan Ltd (1110734)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17412-001025
17412 | 2019-05-14 17:27
Section 2
Material | Not on List
Not on List
Ekspan 325 Channel end cap
See attached brochure
1 | Each | 0 | 0 | Concrete Accessories
2019-05-21
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC2B - Roadworks - A14
504 - Drainage and Service Ducts in Structures
A14 IDT
OP11475
Ekspan Ltd (1110734)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17412-001025
17412 | 2019-05-14 17:27
Section 2
Material | Not on List
Not on List
Ekspan Custom "Honel" outlet
See attached brochure & Design
3 | Each | 0 | 0 | Concrete Accessories
2019-05-21
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC2B - Roadworks - A14
504 - Drainage and Service Ducts in Structures
A14 IDT
OP11475
Ekspan Ltd (1110734)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17428-001025
17428 | 2019-05-15 08:11
Section 4
Material | Bagged | Building Sand Bulk Bag (938155)
NULL | NULL | 20 | Tonne | 16.95 | 339 | Builders Merchants (General)
2019-05-20
RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound
SC4B - Roadworks - Robins Lane to Dry Drayton
502 - Chambers & Gullies
Caulfield
11489/OP/3310504
Mick George Ltd (1220483)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17431-001025
17431 | 2019-05-15 08:41
Section 4
Material | PPE, Small Tools and Consumables
Not on List
HILTI TE905 POINT
NULL | 10 | Each | 15.96 | 159.6 | Small Tools (Consumables)
2019-05-17
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11483/OP/3310504
Ashtead Plant Hire Company Ltd (1109463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17431-001025
17431 | 2019-05-15 08:41
Section 4
Material | PPE, Small Tools and Consumables
Not on List
HILTI TE905 CHISEL
NULL | 10 | Each | 15.96 | 159.6 | Small Tools (Consumables)
2019-05-17
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11483/OP/3310504
Ashtead Plant Hire Company Ltd (1109463)
Closed - Stores
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17433-001025
17433 | 2019-05-15 08:42
Section 5
Material | Combined Drainage
Not on List
CDKU kerbs
Take off has been completed for all section 5 CDKU and standard kerbs. Attached in files
1 | Each | 185009.99 | 185009.99 | Concrete Hard Landscaping (Kerbs, Slabs)
2019-05-20
WB5/7 Works Access - 1356563 - A14 Westbound, On Left between Jcn 32 - 31
SEC5 - Roadworks
1102 - Combined Drainage and Kerb Units
A14 IDT
11478
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17433-001025
17433 | 2019-05-15 08:42
Section 5
Material | Combined Drainage
Not on List
standard kerbs
Take off has been completed for all section 5 CDKU and standard kerbs. Attached in files
1 | Each | 30364.64 | 30364.64 | Concrete Hard Landscaping (Kerbs, Slabs)
2019-05-20
WB5/7 Works Access - 1356563 - A14 Westbound, On Left between Jcn 32 - 31
SEC5 - Roadworks
1101 - Kerbs, Channels and Edgings
A14 IDT
11477 | Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
| NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 2019-05-20
WB5/7 Works Access - 1356563 - A14 Westbound, On Left between Jcn 32 - 31
SEC5 - Roadworks
1102 - Combined Drainage and Kerb Units
NULL | NULL | NULL | Buyer - Closed | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 110 | 110 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 165 | 165 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 190 | 190 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 585 | 585 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32535 | 32535 | 2020-07-20 14:19 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32535 | 32535 | 2020-07-20 14:19 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32535 | 32535 | 2020-07-20 14:19 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-17437-001025
17437 | 2019-05-15 08:39
Section 4
Material | Not on List
Not on List
TX160
4m x 50m
11 | Rolls | 535 | 5885 | Builders Merchants (General)
2019-05-17
RVP 419 (S4) - 1340880 - A14 Westbound (West of Junction 28)
PLM4 - Site Preliminaries
153a - Temporary Works - Site Infrastructure
A14 IDT
11487/OP/3310504
Keyline Builders Merchants Ltd (1100980)
Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17437-001025
17437 | 2019-05-15 08:39
Section 4
Material | Not on List
Not on List
Terram 1000
4.5m x 100m
16 | Rolls | 116.88 | 1870.08 | Builders Merchants (General)
2019-05-17
RVP 419 (S4) - 1340880 - A14 Westbound (West of Junction 28)
PLM4 - Site Preliminaries
153a - Temporary Works - Site Infrastructure
A14 IDT
11487/OP/3310504
Keyline Builders Merchants Ltd (1100980)
Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17437-001025
17437 | 2019-05-15 08:39
Section 4
Material | Not on List
Not on List
Visqueen | 4m x 25m
3 | Rolls | 0 | 0 | Builders Merchants (General)
2019-05-17
RVP 419 (S4) - 1340880 - A14 Westbound (West of Junction 28)
PLM4 - Site Preliminaries
153a - Temporary Works - Site Infrastructure
A14 IDT
11487/OP/3310504
Keyline Builders Merchants Ltd (1100980)
| Stores - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17437-001025
17437 | 2019-05-15 08:39
Section 4
Material | Not on List
Not on List
A393 mesh
4.8m x 2.4m
15 | Sheets | 69.14 | 1037.1 | Builders Merchants (General)
2019-05-17
RVP 419 (S4) - 1340880 - A14 Westbound (West of Junction 28)
PLM4 - Site Preliminaries
153a - Temporary Works - Site Infrastructure
A14 IDT
11487/OP/3310504
Keyline Builders Merchants Ltd (1100980)
| Stores - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32536 | 32536 | 2020-07-20 13:58 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 185 | 185 | Professional Services | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-32536 | 32536 | 2020-07-20 13:58 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 117.5 | 117.5 | Professional Services | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-32536 | 32536 | 2020-07-20 13:58 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 227.5 | 227.5 | Professional Services | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-32536 | 32536 | 2020-07-20 13:58 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 153.35 | 153.35 | Professional Services | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-17437-001025
17437 | 2019-05-15 08:39
Section 4
Material | Not on List
Not on List
Denso tape
75mm x 10m
20 | Rolls | 6.4 | 128 | Builders Merchants (General)
2019-05-17
RVP 419 (S4) - 1340880 - A14 Westbound (West of Junction 28)
PLM4 - Site Preliminaries
153a - Temporary Works - Site Infrastructure
A14 IDT
11487/OP/3310504
Keyline Builders Merchants Ltd (1100980)
| Stores - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17440-001025
17440 | 2019-05-15 10:07
Section 3
Material | Not on List
Not on List
Denso tape
10m long, 100mm wide rolls
20 | Rolls | 6.4 | 128 | Miscellaneous | 2019-05-16
Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard
BN06 - ECML Bridge
2010 - Waterproofing for concrete structures
A14 IDT
11495
Blue Bay Building Products Ltd (1109669)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17440-001025
17440 | 2019-05-15 10:07
Section 3
Material | Not on List
Not on List
Ultra Crete Bitumen Cold Joint Sealer & Tack Coat
750ml cans - 1No. box (approx. 12 cans)
12 | Cans | 9.7 | 116.4 | Miscellaneous | 2019-05-16
Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard
BN16 - New Barns Lane Overbridge
2010 - Waterproofing for concrete structures
A14 IDT
11495
Blue Bay Building Products Ltd (1109669)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17453-001025
17453 | 2019-05-15 12:30
Section 3
Material | Not on List
Not on List
TYRE REPAIRS APRIL 2019
SEE BACK UP TOTAL $4893.52
1 | Each | 4893.52 | 4893.52 | Miscellaneous
2019-05-15
Gate D - 1339643 - BN10 Via Main Compound Entrance
PLM3 - Site Preliminaries
104 - Site Transport
A14 IDT
11481/OP/3310503
Steve's Tyres (1346872)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17470-001025
17470 | 2019-05-15 16:43
Section 5
Material | Not on List
Not on List
steel fabrication - gantries laddres per approved fabrication drawings and lengths
attached e-mail with quotes
1 | Each | 4214.24 | 4214.24 | Builders Merchants (General)
2019-06-17
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
GN05 - Gantry structures
1801 - Structural Steelwork
A14 IDT
NULL | NULL | Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17479-001025
17479 | 2019-05-15 17:07
Section 5
Material | PPE, Small Tools and Consumables
Not on List
ladder tags - for inspection dates
NULL | 50 | No | NULL | NULL | Builders Merchants (General)
2019-05-20
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
PLM5 - Site Preliminaries
153a - Temporary Works - Site Infrastructure
A14 IDT
NULL | NULL | Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17479-001025
17479 | 2019-05-15 17:07
Section 5
Material | PPE, Small Tools and Consumables
Not on List
plastic cap for M16 bolts - 25mm lenght
NULL | 50 | No | NULL | NULL | Builders Merchants (General)
2019-05-20
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
GN05 - Gantry structures
1702 - Precast Concrete
A14 IDT
NULL | NULL | Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17479-001025
17479 | 2019-05-15 17:07
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Clips RC25
lightning details - rebar clips - attached previous quote from bluebay
3 | No | NULL | NULL | Builders Merchants (General)
2019-05-20
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
GN05 - Gantry structures
1701 - Insitu Concrete
A14 IDT
NULL | NULL | Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17479-001025
17479 | 2019-05-15 17:07
Section 5
Material | PPE, Small Tools and Consumables
Not on List
Clips RC16
lightning details - rebar clips - attached previous quote from bluebay
3 | No | NULL | NULL | Builders Merchants (General)
2019-05-20
Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ
GN05 - Gantry structures
1701 - Insitu Concrete
A14 IDT
NULL | NULL | Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17484-001025
17484 | 2019-05-15 18:07
Section 4
Material | Not on List
Not on List
White Soppec Marker Spray - Land Surveying Equipment
NULL | 36 | Each | 17.9 | 644.4 | Surveying Consumables
2019-05-22
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
102 - Compound running costs
A14 IDT
11491/OP/3310504
E H Smith (Builders Merchants) (1113953)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17523-001025
17523 | 2019-05-16 11:15
Section 3
Material | PPE, Small Tools and Consumables
Not on List
JB Weld adhesive
Please deliver to Simon Lawn in the main compound office.
2 | Packs | 86.18 | 172.36 | Fixings and Fasteners
2019-05-21
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
BN06 - ECML Bridge
2302 - Sealing of gaps
A14 IDT
11502
Orbital Fasteners Ltd (1118568)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17528-001025
17528 | 2019-05-16 11:50
Section 4
Material | Not on List
Not on List
RECo Wall Panel - Po6
NULL | 1 | Each | 246.98 | 246.98 | Miscellaneous
2019-05-27
RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road)
BN25 - Girton Interchange Bridge A
1702 - Precast Concrete
Keller Ltd
4798
Reinforced Earth Co Ltd (1113429)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17528-001025
17528 | 2019-05-16 11:50
Section 4
Material | Not on List
Not on List
RECo Wall Panel - AAo3
NULL | 1 | Each | 175.6 | 175.6 | Miscellaneous
2019-05-27
RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road)
BN25 - Girton Interchange Bridge A
1702 - Precast Concrete
Keller Ltd
4798
Reinforced Earth Co Ltd (1113429)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17528-001025
17528 | 2019-05-16 11:50
Section 4
Material | Not on List
Not on List
RECo Wall Panel - 12A02
NULL | 1 | Each | 79.86 | 79.86 | Miscellaneous
2019-05-27
RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road)
BN25 - Girton Interchange Bridge A
1702 - Precast Concrete
Keller Ltd
4798
Reinforced Earth Co Ltd (1113429)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17572-001025
17572 | 2019-05-16 17:43
Section 3
Material | Bagged
OP Cement; 25kg bag (767201)
NULL | to be used by P&H
80 | Each | 2.97 | 237.6 | Concrete Drainage
2019-05-20
Gate C - 1339699 - BN08 via Logistics Yard Access
SC3A - Roadworks
504 - Drainage and Service Ducts in Structures
P & H Plant Hire Ltd
11503
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17577-001025
17577 | 2019-05-17 07:31
Section 4
Material | Timber
Not on List
meter length peg
1000 pegs needed to set out service corridors (stats)
1000 | Each | 0.9 | 900 | Timber Products
2019-05-20
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
11506/OP/3310504
Firwood Timber & Plywood Co Lt (1101546)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-24511-001025
24511 | 2019-10-02 10:43
Core
Material | Not on List
Not on List
Stamps for Invoices relating to new VAT Requirement
As per attached proof
2 | Each | 36.35 | 73 | Office Supplies
2019-10-02
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
111 - Stationery /Postage
A14 IDT
PCARD | Stamps4u.co.uk
Closed - IMO PCARD
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 72.7
72.7
NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-26739-001025
26739 | 2019-11-19 12:11
Core
Material | PPE, Small Tools and Consumables
Not on List
PPE as per quote 17/289885
NULL | 1 | Each | 281.97 | 281.97 | PPE | 2019-11-25
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
109 - PPE Costs
A14 IDT
13190/OP/3310500
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32540 | 32540 | 2020-07-20 17:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 102 | 102 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32540 | 32540 | 2020-07-20 17:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32540 | 32540 | 2020-07-20 17:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 95 | 95 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32540 | 32540 | 2020-07-20 17:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 95 | 95 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-28848-001025
28848 | 2020-02-04 13:55
Section 2
Material | Not on List
Not on List
Repair to Trimble TSC3 and R10
Please contact Korec Huntingdon - See attached estimate.
1 | No | 1681.75 | 1681.75 | Miscellaneous
2020-02-07
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC2B - Roadworks - A14
1101 - Kerbs, Channels and Edgings
A14 IDT
OP 13627
Korec (1114049)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-28990-001025
28990 | 2020-02-07 12:04
Core
Material | Not on List
Not on List
Celebrating A14 Efficiency Success
PAID BY P CARD - Celebrating A14 Efficiency Success
1 | No | 392.75 | 392.75 | Miscellaneous
2019-06-25
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
122 - Entertainment
A14 IDT
NULL | NULL | IMO - Closed
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 392.75 | 392.75 | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-29275
29275 | 2020-02-17 15:05
Section 6
Material | Not on List
Not on List
Wire fence mesh rolls
2 | Rolls | 89.5 | 179 | Miscellaneous
2020-02-21
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SEC6 - Huntingdon Viaduct works
202 - Demolition
A14 IDT
13663
E H Smith (Builders Merchants) (1113953)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-29302
29302 | 2020-02-18 10:56
Core
Material | Not on List
Not on List
HE mobile phones
We have 3 phones that were provured by Steve Garbut as part of a CE in 2017. I am looking to transfer these over to HE, but for now we are still being charged for them. I supsended the phone service to find out who had the phoones. Monthly charge is around £290 ex VAT
5 | Each | 290 | 1450 | Office Supplies
2020-02-24
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
117 - Computer & Acc Charges
A14 IDT
OP 13758
Matrix Platinum Ltd (1341902)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32546 | 32546 | 2020-07-21 11:27 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List
2000 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | OP 14154 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32546 | REQ - Finance Team | NULL | NULL
MREQ-32547 | 32547 | 2020-07-21 13:31 | Core | Material Requisition | Not on List | Not on List
1 | No. | 573.54 | 573.54 | Surveying Consumables | 2020-07-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | 14161 | Korec (1114049) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32547/Request/est52231.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32547 | REQ - Finance Team | NULL | NULL
MREQ-29346
29346 | 2020-02-19 09:05
Section 4
Material | Misc
Not on List
Additional hours on Gene on solar cube
1 | Each | 2642.98 | 2642.98 | Miscellaneous
2020-02-28
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
OP 13749
Speedy Asset Services Ltd (1241805)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-29731
29731 | 2020-03-02 13:08
Section 2
Material | Misc | Not on List
Fencing
36.00 M8 x 30 Roofing bolts £0.30
1 | Unit | 1586.55 | 1586.55 | Miscellaneous
2020-03-09
Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC2A - Roadworks - A1
2701 - Accommodation works
A14 IDT
13723
E H Smith (Builders Merchants) (1113953)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-30061
30061 | 2020-03-12 14:19
Section 4
Material | Not on List
Not on List
M27 threaded stud as per attached drawing
1 | No | 0 | 0 | Miscellaneous
2020-03-16
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
GN4C - Gantry structures
1804 - Portal Gantries
A14 IDT
FOC | Wec Group Ltd (1322653)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-30283
30283 | 2020-03-19 08:05
Core
Material | Not on List
Not on List
Mobile SIM
Please see attached invoices. Legacy of the tablet deployment. These are now out of contract and the numbers have been reduced to reflect this. Monthly cost moving forward will be £280/month. F7 budget is £10k to cover these invoices and remaining few months of the project | 1 | Each | 10000 | 10000 | Office Supplies
2020-03-30
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
117 - Computer & Acc Charges
A14 IDT
OP 13824
Telephone Technology Ltd (1333647)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-31178
31178
2020-04-22 13:42
Section 6
Material | Not on List
Not on List
Hilti HLS-3 M12/25 131mm anchor length
Hilti HLS-3 M12/25 131mm anchor length
100 | Each | 8.17 | 817.35 | Fixings and Fasteners
2020-04-26
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SEC6 - Huntingdon Viaduct works
202 - Demolition
A14 IDT
OP 13928
Hilti (Gt Britain) Ltd (1111659)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-31959
31959 | 2020-06-09 10:17
Section 6
Material | Not on List
Not on List
Hilti HSL-3 M12 anchor bolts
Hilti HSL-3 M12 anchor bolts
130 | Each | 5.26 | 683.8 | Fixings and Fasteners
2020-06-12
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SEC6 - Huntingdon Viaduct works
202 - Demolition
A14 IDT
14035
Hilti (Gt Britain) Ltd (1111659)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32226
32226
2020-06-25 13:13
Section 6
Material | Not on List
Not on List
S6 DNO Elec.Supplies-New Street Lighting&Furniture Connections
A14CTOH SECTION 6: DNO ELECTRICAL SUPPLIES –NEW STREET LIGHTING & FURNITURE CONNECTIONS
1 | Sum | 455651.21 | 455651.21 | Miscellaneous
2020-06-25
Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton
SC6R - Roadworks Section 6
2702 - Works by the Statutory Undertakers
A14 IDT
14079
UK Power Networks (Operations) (1284772)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7707-001023
7707 | 2018-10-12 09:25
Section 4
Material | Hazardous Waste
Not on List
Emergency Spill Response
A non-A14 lorry spilt 200-300 litres of diesel on the mainline A14.
1 | Visit | 4252.26 | 4252.26 | Miscellaneous
2018-10-12
RVP 413 - 1339629 - The Avenue Site A14 Westbound
PLM4 - Site Preliminaries
154 - Traffic Management & Safety
A14 IDT
91458
Adler & Allan Ltd (1131899)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7739-001023
7739 | 2018-10-12 12:16
Section 4
Material | Not on List
Not on List
Reinforcement Type 2 headwall x2 sets
4.465 | Tonne | 538 | 2402.17 | Miscellaneous
2018-10-22
RVP 428 - (Wash Brook Pit) A14 Eastbound
SC4C - Roadworks - Dry Drayton to Girton
503 - Headwalls and Outfall Works
Kelly Formwork (UK) Ltd
OP/5999
BRC Ltd (1228398)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7764-001023
7764 | 2018-10-12 15:59
Section 3
Material | Not on List
Not on List
Various Janitorial items
Please see attached file. WAOC 110(Welfare) not found on system
1 | No | 200.6 | 200.6 | Janitorial
2018-10-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
PLM3 - Site Preliminaries
151 - Prelims attendant Labour and Equipment
A14 IDT
9204
Greenham Trading Ltd (1100463)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7764-001023
7764 | 2018-10-12 15:59
Section 3
Material | Not on List
Not on List
Various Small Tool Items
Please see attached file
1 | No | 435.37 | 435.37 | Small Tools (Consumables)
2018-10-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
PLM3 - Site Preliminaries
151 - Prelims attendant Labour and Equipment
A14 IDT
9204
Greenham Trading Ltd (1100463)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7764-001023
7764 | 2018-10-12 15:59
Section 3
Material | Not on List
Not on List
Various PPE items
Please see attached file
1 | No | 435.37 | 435.37 | PPE
2018-10-16
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
PLM3 - Site Preliminaries
103 - Staff
A14 IDT
9204
Greenham Trading Ltd (1100463)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7780-001023
7780 | 2018-10-15 08:20
Section 3
Material | PPE, Small Tools and Consumables
Soap Pristine Heavy Duty Citrus 2 Litre Cartridge (548141)
NULL | NULL | 5 | Each | 5.82 | 29.1 | Janitorial
2018-10-19
Gate D - 1339643 - BN10 Via Main Compound Entrance
PLM3 - Site Preliminaries
102 - Compound running costs
A14 IDT
9204
Greenham Trading Ltd (1100463)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7780-001023
7780 | 2018-10-15 08:20
Section 3
Material | PPE, Small Tools and Consumables
Refill Air Care Pristine Cosmopolitan Air Fragrance 270ml (539228)
NULL | NULL | 4 | Each | 3.15 | 13 | Janitorial
2018-10-19
Gate D - 1339643 - BN10 Via Main Compound Entrance
PLM3 - Site Preliminaries
102 - Compound running costs
A14 IDT
9204
Greenham Trading Ltd (1100463)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7788-001023
7788 | 2018-10-15 09:30
Section 4
Material | Not on List
Not on List
Althon Large General Purpose Headwall GPLARGE
Contact site 2hrs prior to arrival in order to arrange unloading.
40 | Each | 135 | 5400 | Not Sure
2018-10-29
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
SC4B - Roadworks - Robins Lane to Dry Drayton
503 - Headwalls and Outfall Works
Caulfield
OP9231
Athlon Ltd
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7788-001023
7788 | 2018-10-15 09:30
Section 4
Material | Not on List
Not on List
Althon Small General Purpose Headwall GPSMALL
Contact site 2hrs prior to arrival in order to arrange unloading.
25 | Each | 95 | 2375 | Not Sure
2018-10-29
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
SC4B - Roadworks - Robins Lane to Dry Drayton
503 - Headwalls and Outfall Works
Caulfield
OP9231
Athlon Ltd
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7789-001023
7789 | 2018-10-15 10:13
Section 3
Material | Not on List
Not on List
Hilti DD150 Drill Attachment
Please see attached file
1 | Each | 48 | 48 | Small Tools (Consumables)
2018-10-17
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
PLM3 - Site Preliminaries
151 - Prelims attendant Labour and Equipment
A14 IDT
9168
Ashtead Plant Hire Company Ltd (1109463)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7792-001023
7792 | 2018-10-15 09:50
Section 4
Material | Bagged
OP Cement; 25kg bag (767201)
NULL | NULL | 56 | Each | 2.9 | 162.4 | Miscellaneous
2018-10-17
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
102 - Compound running costs
A14 IDT
9190/OP/3310504
Keyline Builders Merchants Ltd (1100980)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7795-001023
7795 | 2018-10-15 12:59
Section 4
Material | Not on List
Not on List
675 x 675mm concrete cover frame adjusting unit.'
NULL | 10 | Each | 16.49 | 164.9 | Concrete Drainage
2018-12-10
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
SC4B - Roadworks - Robins Lane to Dry Drayton
502 - Chambers & Gullies
A14 IDT
9576
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7795-001023
7795 | 2018-10-15 12:59
Section 4
Material | Not on List
Not on List
675 x 675 D400 cover and frame.
NULL | 2 | Each | 0 | 0 | Concrete Drainage
2018-12-10
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
SC4B - Roadworks - Robins Lane to Dry Drayton
502 - Chambers & Gullies
A14 IDT
9576
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7795-001023
7795 | 2018-10-15 12:59
Section 4
Material | Not on List
Not on List
DN1050 concrete rocker pipe coated with bitumen waterproofing
NULL | 1 | Each | 452.16 | 452.16 | Concrete Drainage
2018-12-10
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
SC4B - Roadworks - Robins Lane to Dry Drayton
502 - Chambers & Gullies
A14 IDT
9576
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7795-001023
7795 | 2018-10-15 12:59
Section 4
Material | Not on List
Not on List
DN1050 spigot butt coated with bitumen waterproofin
NULL | 1 | Each | 452.16 | 452.16 | Concrete Drainage
2018-12-10
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
SC4B - Roadworks - Robins Lane to Dry Drayton
502 - Chambers & Gullies
A14 IDT
9576
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7795-001023
7795 | 2018-10-15 12:59
Section 4
Material | Not on List
Not on List
DN900 concrete socket butt
NULL | 1 | Each | 278.64 | 278.64 | Concrete Drainage
2018-12-10
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
SC4B - Roadworks - Robins Lane to Dry Drayton
502 - Chambers & Gullies
A14 IDT
9576
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7795-001023
7795 | 2018-10-15 12:59
Section 4
Material | Not on List
Not on List
DN900 rocker pipe
NULL | 1 | Each | 278.64 | 278.64 | Concrete Drainage
2018-12-10
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
SC4B - Roadworks - Robins Lane to Dry Drayton
502 - Chambers & Gullies
A14 IDT
9576
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7795-001023
7795 | 2018-10-15 12:59
Section 4
Material | Not on List
Not on List
DN900 concrete pipe
NULL | 3 | Each | 232.2 | 696.6 | Concrete Drainage
2018-12-10
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
SC4B - Roadworks - Robins Lane to Dry Drayton
502 - Chambers & Gullies
A14 IDT
9576
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7795-001023
7795 | 2018-10-15 12:59
Section 4
Material | Not on List
Not on List
3000mm Chamber Unit
1 | Each | 6038 | 6038 | Concrete Drainage
2018-12-10
RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound
SC4B - Roadworks - Robins Lane to Dry Drayton
502 - Chambers & Gullies
A14 IDT
9576
Keyline Builders Merchants Ltd (1100980)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7809-001023
7809 | 2018-10-15 15:28
Section 4
Material | Not on List
Not on List
6360-2.5-090 HD Short anchors
Supplied by Halfen
20 | No | 10.47 | 209.4 | Not Sure
2018-10-19
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
BN23 - Structure BN23
1702 - Precast Concrete
Kelly Formwork (UK) Ltd
9236/OP/3310504
Halfen Ltd (1111714)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7809-001023
7809 | 2018-10-15 15:28
Section 4
Material | Not on List
Not on List
6358-16 HD Nailing plate
Supplied by Halfen
20 | No | 0.14 | 2.8 | Not Sure
2018-10-19
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
BN23 - Structure BN23
1702 - Precast Concrete
Kelly Formwork (UK) Ltd
9236/OP/3310504
Halfen Ltd (1111714)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7809-001023
7809 | 2018-10-15 15:28
Section 4
Material | Not on List
Not on List
6362-16 HD Lifting links
Supplied by Halfen
8 | No | 81.99 | 655.92 | Not Sure
2018-10-19
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
BN23 - Structure BN23
1702 - Precast Concrete
Kelly Formwork (UK) Ltd
9236/OP/3310504
Halfen Ltd (1111714)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7809-001023
7809 | 2018-10-15 15:28
Section 4
Material | Not on List
Not on List
50mm spacer blocks (200 per bag)
200 blocks per bag (bluebay)
5 | Bags | 23.24 | 166.2 | Miscellaneous
2018-10-19
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
BN23 - Structure BN23
1704 - Reinforcement for Structures
Kelly Formwork (UK) Ltd
9207/OP/3310504
Blue Bay Building Products Ltd (1109669)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7809-001023
7809 | 2018-10-15 15:28
Section 4
Material | Not on List
Not on List
Hilti Type Nail - Length: 32mm
Come in boxes of 200
1 | Box | 35.5 | 35.5 | Surveying Consumables
2018-10-18
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
102 - Compound running costs
A14 IDT
9208/OP/3310504
Hilti (Gt Britain) Ltd (1111659)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7811-001023
7811 | 2018-10-15 16:28
Section 4
Material | PPE, Small Tools and Consumables
Not on List
Tools As Per Attached Quote 17/275231
NULL | 1 | Each | 1166.02 | 1166.02 | Small Tools (Consumables)
2018-10-17
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
102 - Compound running costs
A14 IDT
9196/OP/3310504
Greenham Trading Ltd (1100463)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7826-001023
7826 | 2018-10-16 07:54
Section 4
Material | Not on List
Not on List
duplex webbing sling , 2 tons SWL , 4 metres
purchase price £8.87
4 | Each | 8.87 | 35.48 | Not Sure
2018-10-18
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
151 - Prelims attendant Labour and Equipment
A14 IDT
9209/OP/3310504
Gap Group Ltd (1108091)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7826-001023
7826 | 2018-10-16 07:54
Section 4
Material | Not on List
Not on List
duplex webbing sling , 3 tons SWL , 4 metres
purchase price £12.86
2 | Each | 12.86 | 25.72 | Not Sure
2018-10-18
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound
PLM4 - Site Preliminaries
151 - Prelims attendant Labour and Equipment
A14 IDT
9209/OP/3310504
Gap Group Ltd (1108091)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7829-001023
7829 | 2018-10-16 09:35
Section 3
Material | Not on List
Not on List
18 No. Banners 3000x850mm (Non A14 Branding) 2No signs for each bridge. Please refer to attached quate and design.
Requested by Paul Sprague
18 | Each | 50 | 900 | Miscellaneous
2018-10-17
Gate D - 1339643 - BN10 Via Main Compound Entrance
PLM3 - Site Preliminaries
102 - Compound running costs
A14 IDT
9242/OP/3310503
Morelock Signs Ltd (1255521)
Closed - Stores
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7883-001023
7883 | 2018-10-17 09:43
Section 3
Material | Not on List
Not on List
Gap Welfare charges for August 2 No items
£64.99 total see attachment for details.
1 | No | 64.99 | 64.99 | Damage Charges
2018-10-19
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
PLM3 - Site Preliminaries
152 - Attendant / General Plant
A14 IDT
6587
Gap Group Ltd (1108091)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7885-001023
7885 | 2018-10-17 09:32
Section 3
Material | Not on List
Not on List
Fire extinguisher signs
FAO Christian Leland, Steve says can you piggy back it on to order 9203/OP/3310503 and send over to Beth? Please see attached file. | 5 | No | 2.16 | 10.8 | Not Sure
2018-10-19
Main Compound Gate D - 1339642 - Main Compound Entrance A1198
PLM3 - Site Preliminaries
102 - Compound running costs
A14 IDT
9023
Greenham Trading Ltd (1100463)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-7894-001023
7894 | 2018-10-17 11:07
Section 4
Material | Not on List
Not on List
Reinforcement Call-Off, Central Pier BN19
NULL | 16.308 | Tonnes | 538 | 8773.7 | Not Sure
2018-11-02
RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound
BN19 - Robins Lane Bridge
1704 - Reinforcement for Structures
Kelly Formwork (UK) Ltd
OP5999
BRC Ltd (1228398)
Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-17195-001025
17195 | 2019-05-10 14:40
Core
Material | Not on List
Not on List
National Ultra Site Awards Ceremony Attendance
Approval requested for P-card payment
1 | Each | 2460 | 2460 | Miscellaneous | 2019-05-14
Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core)
WAOC - Working Areas overhead Costs
122 - Entertainment
A14 IDT
NULL | NULL | IMO - Closed
Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | Yes | CCS
NULL | NULL | NULL | NULL | NULL | NULL | NULL
2952
NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32553 | 32553 | 2020-07-21 16:28 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 40 | NULL | NULL | 0 | Fixings and Fasteners | 2020-07-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32556 | 32556 | 2020-07-22 07:49 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32556 | 32556 | 2020-07-22 07:49 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 3 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32556 | 32556 | 2020-07-22 07:49 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 3 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
NULL | 32558 | 2020-07-22 10:39 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 643.68 | 643.68 | Miscellaneous | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32558 | 2020-07-22 10:39 | Section 5 | Material Requisition | Misc | Not on List | 1 | No | 9975 | 9975 | Miscellaneous | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32558 | 2020-07-22 10:39 | Section 5 | Material Requisition | Misc | Not on List | 1 | No | 85 | 85 | Miscellaneous | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32558 | 2020-07-22 10:39 | Section 5 | Material Requisition | Misc | Not on List | 1 | No | 212.45 | 212.45 | Miscellaneous | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32559 | 2020-07-22 12:12 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 165 | 165 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32559 | 2020-07-22 12:12 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 290 | 290 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32559 | 2020-07-22 12:12 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 1182.22 | 1182.22 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32559 | 2020-07-22 12:12 | Section 4 | Material Requisition | Not on List | Not on List | 1 | N0 | 85 | 85 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-17211-001025
17211 | 2019-05-10 16:27
Section 3 | Material | Twinwall
Not on List | 300 ID Endcap for twinwall pipe
NULL | 30 | No | 0 | 0 | Plastic Drainage
2019-05-16
Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard
SC3A - Roadworks
1103 - Linear Drainage Channel Systems
A14 IDT | NULL | NULL | Operations Rejected | No - Reject
NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 32570 | 2020-07-23 10:56 | Section 4 | Material Requisition | Not on List | Not on List | 30 | NULL | NULL | 0 | Miscellaneous | 2020-07-27 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32575 | 2020-07-23 14:11 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-07-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 7 | No | 45 | 315 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 45 | 45 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 5 | No | 45 | 225 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 39 | 39 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 9 | No | 39 | 351 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 7 | No | 51.5 | 360.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 10 | No | 39 | 390 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 4 | No | 45 | 180 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 4 | No | 45 | 180 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 21 | 63 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 21 | 63 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 2 | No | 35.5 | 71 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 11.5 | 11.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 2 | No | 45 | 90 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 21 | 63 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 45 | 135 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 5 | No | 45 | 225 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32577 | 32577 | 2020-07-23 17:40 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 66 | NULL | NULL | 0 | Plastic Drainage | 2020-07-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32578 | 32578 | 2020-07-23 18:03 | Section 5 | Material Requisition | Not on List | Not on List | 40 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-07-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32581 | 32581 | 2020-07-24 07:52 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32581 | 32581 | 2020-07-24 07:52 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 102 | 102 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
NULL | 32582 | 2020-07-24 08:28 | Section 5 | Material Requisition | Not on List | Not on List | 4 | No | 47.37 | 189.48 | Professional Services | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32582 | 2020-07-24 08:28 | Section 5 | Material Requisition | Not on List | Not on List | 0 | NULL | NULL | 0 | Professional Services | NaN-NaN-NaN NaN:NaN:NaN | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 95 | 95 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32583/Request/DOC220620-22062020122019.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32583 | REQ - Finance Team | NULL | NULL
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 43 | 43 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 220 | 220 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 126.5 | 126.5 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 92 | ltrs | 0.8 | 73.6 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 74.22 | 74.22 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 95 | 95 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32584 | 32584 | 2020-07-24 10:16 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 86.25 | 86.25 | Professional Services | 2020-07-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32584 | 32584 | 2020-07-24 10:16 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 95 | 95 | Professional Services | 2020-07-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32584 | 32584 | 2020-07-24 10:16 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 106.88 | 106.88 | Professional Services | 2020-07-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32593 | 32593 | 2020-07-26 08:41 | Section 4 | Material Requisition | Concrete Drainage | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2020-07-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32594 | 32594 | 2020-07-26 08:51 | Section 4 | Material Requisition | Aggregate | A10 Pipe Bed
50 | Tonnes | 16.5 | 825 | Miscellaneous | 2020-07-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | Skyland Contractors Ltd | 14167 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32594 | REQ - Finance Team | NULL | NULL
NULL | 32571 | 2020-07-23 10:25 | Section 4 | Material Requisition | Not on List | Not on List
7 | No | 45 | 315 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32571/Request/3876 Damage letter.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
NULL | 32571 | 2020-07-23 10:25 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
NULL | 32571 | 2020-07-23 10:25 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 45 | 45 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
NULL | 32571 | 2020-07-23 10:25 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 45 | 45 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32571/Request/3619 damage letter.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
NULL | 32571 | 2020-07-23 10:25 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 39 | 39 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32571/Request/3619 damage letter 2.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
NULL | 32571 | 2020-07-23 10:25 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
NULL | 32571 | 2020-07-23 10:25 | Section 4 | Material Requisition | Not on List | Not on List
9 | No | 39 | 351 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
NULL | 32571 | 2020-07-23 10:25 | Section 4 | Material Requisition | Not on List | Not on List
7 | No | 51.5 | 360.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
NULL | 32571 | 2020-07-23 10:25 | Section 4 | Material Requisition | Not on List | Not on List | 0 | NULL | NULL | 0 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 17590 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 19694 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17467 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17547 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 26341 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 19697 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17576 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 18890 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 23507 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 27062 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 29524 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 24592 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 22457 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17439 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17539 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17559 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 27060 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 29768 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 18891 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 26571 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17597 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17580 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 31775 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 10753 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17506 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 30258 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 20552 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 19945 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17197 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17592 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17366 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 29523 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17329 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 18082 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17435 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 26987 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17438 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 27571 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32610 | 32610 | 2020-07-28 08:36 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 2550.9 | 2550.9 | Miscellaneous | 2020-07-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32615 | 32615 | 2020-07-29 10:55 | Core | Material Requisition | Signage | Not on List | 2 | NULL | 69 | 138 | Miscellaneous | 2020-08-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32617 | 32617 | 2020-07-29 13:50 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 1500 | 1500 | Professional Services | 2020-07-30 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32622 | 32622 | 2020-07-30 07:56 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | £ | 92423.92 | 92423.92 | Professional Services | 2020-07-31 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 605 - Disposal | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-32623 | 32623 | 2020-07-30 09:38 | Section 6 | Material Requisition | Bagged | Building Sand Bulk Bag (938155) | 5 | Each | 34.94 | 174.7 | Aggregate | 2020-08-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32623 | 32623 | 2020-07-30 09:38 | Section 6 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.79 | 151.6 | Aggregate | 2020-08-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32624 | 32624 | 2020-07-30 09:30 | Section 1 | Material Requisition | Not on List | Not on List
20 | m3 | 107.76 | 2155.2 | Ready Mixed Concrete | 2020-08-03 | Gate 1 - 1339601 - Main Compound Alconbury | Sian Formwork Ltd | 13593 | Mick George Ltd (1220483) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32624 | REQ - Finance Team | NULL | NULL
MREQ-32626 | 32626 | 2020-07-30 10:13 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Wrap Pallet C/W Extended Core 400mm X 300m X 17mu (766058) | 12 | Each | 11.97 | 143.64 | Miscellaneous | 2020-07-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32626 | 32626 | 2020-07-30 10:13 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Bucket Industrial Black Plastic 3 Gallon (506200) | 6 | Each | 1.43 | 8.58 | Miscellaneous | 2020-07-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32626 | 32626 | 2020-07-30 10:13 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Padlock Cast Iron Spartan 48mm Open Shackle (744411) | 10 | Each | 5.75 | 57.5 | Miscellaneous | 2020-07-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32626 | 32626 | 2020-07-30 10:13 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Bucket Flexi Tub 40 Litre Black (506338) | 3 | Each | 4.95 | 14.85 | Miscellaneous | 2020-07-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32626 | 32626 | 2020-07-30 10:13 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Sack Cleanworks Black Regran 20kg 18x29x38 Cs/200 Gro009 (746625) | 6 | Each | 26.55 | 159.3 | Miscellaneous | 2020-07-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32629 | 32629 | 2020-07-30 12:34 | Section 4 | Material Requisition | Timber | Not on List | 50 | each | 26.97 | 1348.5 | Timber Products | 2020-08-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32629 | 32629 | 2020-07-30 12:34 | Section 4 | Material Requisition | Timber | Not on List | 4 | each | 24 | 96 | Timber Products | 2020-08-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32629 | 32629 | 2020-07-30 12:34 | Section 4 | Material Requisition | Not on List | Not on List | 28 | each | 14.3 | 400.4 | Miscellaneous | 2020-08-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32629 | 32629 | 2020-07-30 12:34 | Section 4 | Material Requisition | Not on List | Not on List | 28 | each | 10 | 280 | Miscellaneous | 2020-08-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32629 | 32629 | 2020-07-30 12:34 | Section 4 | Material Requisition | Bagged | Post Mix 25kg (348099) | 2 | pallets | 5.25 | 10.5 | Builders Merchants (General) | 2020-08-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32645 | 32645 | 2020-07-31 13:12 | Core | Material Requisition | Not on List | Not on List
8 | No. | 74.22 | 593.76 | Electrical | 2020-08-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | Telent Technology Services Ltd | Euros Charge | NULL | IMO - Closed | Yes - Approve | Yes - Approve | Yes | Reichelt Elektronik | /sites/BPM/FlowForma/FormDocuments/MREQ32645/IMO-P-Card-Purchase/MREQ 32645 Receipt_Invoice.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32645 | REQ - Finance Team | NULL | NULL
MREQ-32647 | 32647 | 2020-07-31 14:35 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 205 | 205 | Miscellaneous | 2020-07-31 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32654 | 32654 | 2020-08-03 07:55 | Section 6 | Material Requisition | Not on List | Not on List | 2 | ea | 264.79 | 529.58 | Office Supplies | 2020-08-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Commercial Rejected | Yes - Approve | No - Reject | Req - S6 Buyers
MREQ-32654 | 32654 | 2020-08-03 07:55 | Section 6 | Material Requisition | Not on List | Not on List | 2 | ea | 14.81 | 29.62 | Office Supplies | 2020-08-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Commercial Rejected | Yes - Approve | No - Reject | Req - S6 Buyers
MREQ-32654 | 32654 | 2020-08-03 07:55 | Section 6 | Material Requisition | Not on List | Not on List | 1 | ea | 0 | 0 | Office Supplies | 2020-08-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Commercial Rejected | Yes - Approve | No - Reject | Req - S6 Buyers
MREQ-32658 | 32658 | 2020-08-03 14:39 | Section 6 | Material Requisition | Bagged | Not on List | 6 | Tubs | 10.4 | 62.4 | Builders Merchants (General) | 2020-08-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32668 | 32668 | 2020-08-04 10:25 | Section 6 | Material Requisition | Not on List | Not on List
2 | ea | 264.29 | 528.58 | Office Supplies | 2020-08-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14199 | Comperte Ltd (1323061) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32668 | REQ - Finance Team | NULL | NULL
MREQ-32668 | 32668 | 2020-08-04 10:25 | Section 6 | Material Requisition | Not on List | Not on List
2 | ea | 17.77 | 35.54 | Office Supplies | 2020-08-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14199 | Comperte Ltd (1323061) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32668 | REQ - Finance Team | NULL | NULL
MREQ-32673 | 32673 | 2020-08-04 14:50 | Section 6 | Material Requisition | Not on List | Not on List
2 | ea | 48.96 | 87.98 | Office Supplies | 2020-08-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | Amazon | IMO - Closed | Yes - Approve | Yes - Approve | Yes | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32673/Request/Amazon Cat 5 Cable.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32673 | REQ - Finance Team | NULL | NULL
MREQ-32678 | 32678 | 2020-08-05 08:43 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 65 | 65 | Surveying Consumables | 2020-08-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32679 | 32679 | 2020-08-05 08:25 | Section 2 | Material Requisition | Not on List | Not on List
20 | ton | 0 | 0 | Aggregate | 2020-08-07 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | A14 IDT | 14198 | G Webb Haulage Ltd (1300938) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32679 | REQ - Finance Team | NULL | NULL
MREQ-32682 | 32682 | 2020-08-05 10:25 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 11097.96 | 11097.96 | Office Supplies | 2020-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32682 | 32682 | 2020-08-05 10:25 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 13338.08 | 13338.08 | Office Supplies | 2020-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32683 | 32683 | 2020-08-05 10:35 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 968.06 | 968.06 | Office Supplies | 2020-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 748.11 | 748.11 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 972.97 | 972.97 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 563.98 | 563.98 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 635.57 | 635.57 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 1331.14 | 1331.14 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 444.93 | 444.93 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32686 | 32686 | 2020-08-05 13:12 | Core | Material Requisition | Not on List | Not on List | 1 | no. | 27000 | 27000 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 30 | Number | 8.54 | 256.2 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 8 | Number | 5.76 | 46.08 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 100 | Number | 0.04 | 4 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 30 | Number | 0.11 | 3.3 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 100 | Number | 0.14 | 14 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 11.83 | 11.83 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 45.46 | 45.46 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 6 | NULL | 6.58 | 39.48 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 8.19 | 8.19 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32691 | 32691 | 2020-08-05 16:30 | Core | Material Requisition | Not on List | Not on List | 1 | No | 16214.4 | 16214.4 | Professional Services | 2020-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32693 | 32693 | 2020-08-05 16:59 | Core | Material Requisition | Not on List | Not on List
1 | No | 160316.47 | 160316.47 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | 14206 | JLT Speciality Ltd (1135940) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32693/Request/Additional Premuim for Sections 1,2,3,4 &5.pdf_V1.0.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32693 | REQ - Finance Team | NULL | NULL
MREQ-32694 | 32694 | 2020-08-05 17:23 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 27962.32 | 27962.32 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEE6 - Fee Based Costs inc. insurance | 107 - Insurance | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32709 | 32709 | 2020-08-06 07:30 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 270 | Tonnes | 24.5 | 6615 | Aggregate | 2020-08-10 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32710 | 32710 | 2020-08-06 13:01 | Section 6 | Material Requisition | Not on List | Not on List | 2 | NULL | NULL | 0 | Office Supplies | 2020-08-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 641.46 | 641.46 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 631.13 | 631.13 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 435.33 | 435.33 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 313.65 | 313.65 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 1594.98 | 1594.98 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 306 | 306 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32744 | 32744 | 2020-08-11 14:09 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 3137.73 | 3137.73 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 121 - Phones / Radios / Comms | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32745 | 32745 | 2020-08-11 14:16 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 720 | 720 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Operations Rejected | No - Reject | NULL | REQ - Buyers
MREQ-32748 | 32748 | 2020-08-11 16:31 | Section 6 | Material Requisition | Not on List | Not on List
1 | NULL | 27.14 | 27.14 | PPE | 2020-08-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14214 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32748 | REQ - Finance Team | NULL | NULL
MREQ-32750 | 32750 | 2020-08-12 01:24 | Section 6 | Material Requisition | Bagged | Building Sand Bulk Bag (938155) | 3 | Each | 34.93 | 104.79 | Aggregate | 2020-08-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32757 | 32757 | 2020-08-13 10:08 | Section 2 | Material Requisition | Not on List | Not on List | 1 | £ | 1861 | 1861 | Professional Services | 2020-08-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32758 | 32758 | 2020-08-13 12:43 | Section 6 | Material Requisition | Not on List | Not on List | 1 | ea | 69.44 | 69.44 | PPE | 2020-08-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32758 | 32758 | 2020-08-13 12:43 | Section 6 | Material Requisition | Not on List | Not on List | 3 | ea | 69.44 | 208.32 | PPE | 2020-08-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32758 | 32758 | 2020-08-13 12:43 | Section 6 | Material Requisition | Not on List | Not on List | 4 | ea | 35.64 | 142.56 | PPE | 2020-08-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32763 | 32763 | 2020-08-14 11:15 | Section 2 | Material Requisition | Not on List | Not on List
10 | M3 | 88 | 880 | Ready Mixed Concrete | 2020-08-15 | Gate 1 - 1339601 - Main Compound Alconbury | A14 IDT | 13598 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | Cardinalis Dev ltd 1366537 | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32763 | REQ - Finance Team | NULL | NULL
MREQ-32764 | 32764 | 2020-08-14 11:08 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 621.5 | 621.5 | Small Tools (Consumables) | 2020-08-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | Telent Technology Services Ltd | op 14225 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32764 | REQ - Finance Team | NULL | NULL
MREQ-32765 | 32765 | 2020-08-14 13:18 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 146 | 146 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32765/Request/Imperial Hotel Invoice for Andrew Hobson.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32765 | REQ - Finance Team | NULL | NULL
MREQ-32765 | 32765 | 2020-08-14 13:18 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 146 | 146 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32765/Request/Imperial Hotel Invoice for Nicole Preston.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32765 | REQ - Finance Team | NULL | NULL
MREQ-32765 | 32765 | 2020-08-14 13:18 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 146 | 146 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32765/Request/Imperial Hotel Invoice for Graham Cole.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32765 | REQ - Finance Team | NULL | NULL
MREQ-32765 | 32765 | 2020-08-14 13:18 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 146 | 146 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32765/Request/Imperial Hotel Invoice for Tom Reynolds.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32765 | REQ - Finance Team | NULL | NULL
MREQ-32766 | 32766 | 2020-08-14 13:44 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 15.6 | 15.6 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32766/Request/London Taxi Receipt 15.60.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32766 | REQ - Finance Team | NULL | NULL
MREQ-32767 | 32767 | 2020-08-14 13:47 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 18 | 18 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Grosvenver Receipt 3.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
MREQ-32767 | 32767 | 2020-08-14 13:47 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 20.45 | 20.45 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/London Taxi Receipt 7.11.19. 20.46.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
MREQ-32767 | 32767 | 2020-08-14 13:47 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 5 | 5 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Atrium Bar London Receipt 2.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
MREQ-32767 | 32767 | 2020-08-14 13:47 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 6.2 | 6.2 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Atrium Bar London Receipt 3.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
MREQ-32767 | 32767 | 2020-08-14 13:47 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 5.7 | 5.7 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Atrium Bar London Receipt 4.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
MREQ-32767 | 32767 | 2020-08-14 13:47 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 7.5 | 7.5 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Atrium Bar London Receipt.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
MREQ-32767 | 32767 | 2020-08-14 13:47 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 13.25 | 13.25 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Imperial Receipt 2.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
MREQ-32769 | 32769 | 2020-08-14 14:13 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 319 | 319 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32770 | 32770 | 2020-08-14 15:09 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 29.5 | 29.5 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32775 | 32775 | 2020-08-14 15:15 | Core | Material Requisition | Not on List | Not on List
2 | NULL | 97.5 | 195 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32775 | REQ - Finance Team | NULL | NULL
MREQ-32776 | 32776 | 2020-08-14 15:49 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 10.95 | 10.95 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32777 | 32777 | 2020-08-14 15:53 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 2.85 | 2.85 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32777 | 32777 | 2020-08-14 15:53 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 25.45 | 25.45 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32778 | 32778 | 2020-08-14 15:56 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1020 | 1020 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32778 | 32778 | 2020-08-14 15:56 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 510 | 510 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32779 | 32779 | 2020-08-14 16:02 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 861.86 | 861.86 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32780 | 32780 | 2020-08-14 16:21 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 2874 | 2874 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32781 | 32781 | 2020-08-14 16:24 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 3750 | 3750 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32782 | 32782 | 2020-08-14 16:28 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 720 | 720 | Miscellaneous | 2020-08-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 121 - Phones / Radios / Comms | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32784 | 32784 | 2020-08-14 16:29 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 35.22 | 35.22 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32794 | 32794 | 2020-08-14 23:17 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 39.99 | 39.99 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32795 | 32795 | 2020-08-14 23:35 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 2102.64 | 2102.64 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32796 | 32796 | 2020-08-14 23:49 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 28.99 | 28.99 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32797 | 32797 | 2020-08-14 23:52 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 208.99 | 208.99 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32798 | 32798 | 2020-08-14 23:57 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1248 | 1248 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32798 | 32798 | 2020-08-14 23:57 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1000 | 1000 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32799 | 32799 | 2020-08-15 00:14 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 765.49 | 765.49 | Miscellaneous | 2020-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 101 - Mob/Demob of Compounds | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32803 | 32803 | 2020-08-17 08:33 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 345 | 345 | Miscellaneous | 2020-08-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32804 | 32804 | 2020-08-17 09:10 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 430 | 430 | Office Supplies | 2020-08-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 110 - Welfare Costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32823 | 32823 | 2020-08-18 11:08 | Section 6 | Material Requisition | Not on List | Not on List | 5 | Box's | 132.96 | 664.8 | Builders Merchants (General) | 2020-08-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32829 | 32829 | 2020-08-18 16:46 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 51.84 | 51.84 | Small Tools (Consumables) | 2020-08-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32829 | 32829 | 2020-08-18 16:46 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | 71.11 | 355.55 | Small Tools (Consumables) | 2020-08-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32830 | 32830 | 2020-08-18 17:09 | Section 6 | Material Requisition | Aggregate | Type 1 | 60 | Tonnes | 23.5 | 1410 | Aggregate | 2020-08-20 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | S6SF - Station Forecourt | 2703 - Works on behalf of Statutory Undertakers | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32839 | 32839 | 2020-08-19 12:24 | Section 6 | Material Requisition | Not on List | Not on List
1 | No | 95 | 95 | Professional Services | 2020-08-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | 14232 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32839/Request/DOC140820-14082020094958.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32839 | REQ - Finance Team | NULL | NULL
MREQ-32839 | 32839 | 2020-08-19 12:24 | Section 6 | Material Requisition | Not on List | Not on List
1 | No | 85 | 85 | Professional Services | 2020-08-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | 14232 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32839 | REQ - Finance Team | NULL | NULL
MREQ-32839 | 32839 | 2020-08-19 12:24 | Section 6 | Material Requisition | Not on List | Not on List
1 | No | 95 | 95 | Professional Services | 2020-08-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | 14232 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32839 | REQ - Finance Team | NULL | NULL
MREQ-32839 | 32839 | 2020-08-19 12:24 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.95 | 97.95 | Professional Services | 2020-08-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32839 | 32839 | 2020-08-19 12:24 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.95 | 97.95 | Professional Services | 2020-08-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32840 | 32840 | 2020-08-19 14:55 | Section 2 | Material Requisition | Not on List | Not on List
1 | No | 86.25 | 86.25 | Professional Services | 2020-08-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | A14 IDT | 14233 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32840/Request/DOC140820-14082020094958.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32840 | REQ - Finance Team | NULL | NULL
MREQ-32840 | 32840 | 2020-08-19 14:55 | Section 2 | Material Requisition | Not on List | Not on List
1 | No | 258.75 | 258.75 | Professional Services | 2020-08-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | A14 IDT | 14233 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32840 | REQ - Finance Team | NULL | NULL
MREQ-32840 | 32840 | 2020-08-19 14:55 | Section 2 | Material Requisition | Not on List | Not on List
1 | No | 95 | 95 | Professional Services | 2020-08-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | A14 IDT | 14233 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32840 | REQ - Finance Team | NULL | NULL
MREQ-32846 | 32846 | 2020-08-20 12:42 | Section 5 | Material Requisition | Not on List | Not on List | 34 | each | 0.63 | 21.42 | Miscellaneous | 2020-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SEC5 - Roadworks | 1504 - Technology Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32846 | 32846 | 2020-08-20 12:42 | Section 5 | Material Requisition | Not on List | Not on List | 34 | each | 0.63 | 21.42 | Miscellaneous | 2020-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SEC5 - Roadworks | 1504 - Technology Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32846 | 32846 | 2020-08-20 12:42 | Section 5 | Material Requisition | Not on List | Not on List | 34 | each | 0.25 | 8.5 | Miscellaneous | 2020-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SEC5 - Roadworks | 1504 - Technology Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32850 | 32850 | 2020-08-20 14:46 | Section 4 | Material Requisition | Not on List | Not on List | 40 | Bags | NULL | 0 | Builders Merchants (General) | 2020-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2701 - Accommodation works | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-32851 | 32851 | 2020-08-20 15:08 | Section 4 | Material Requisition | Not on List | Not on List | 46 | NULL | NULL | 0 | Builders Merchants (General) | 2020-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32855 | 32855 | 2020-08-21 07:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Lot | 70000 | 70000 | Miscellaneous | 2020-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32857 | 32857 | 2020-08-21 08:06 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 1606 | 1606 | Miscellaneous | 2020-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 14246 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32857/Request/RE Advice Note - N06-668733.msg | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32857 | REQ - Finance Team | NULL | NULL
MREQ-32857 | 32857 | 2020-08-21 08:06 | Section 5 | Material Requisition | Not on List | Not on List
1 | No | 507.5 | 507.5 | Miscellaneous | 2020-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 14246 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32857/Request/DOC140820-14082020094958.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32857 | REQ - Finance Team | NULL | NULL
MREQ-32857 | 32857 | 2020-08-21 08:06 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 82.6 | 82.6 | Miscellaneous | 2020-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 72 | 72 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32858/Request/DOC140820-14082020094958 (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 120 | 120 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 90 | 90 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 70 | 70 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 72 | 72 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 85 | 85 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 97.75 | 97.75 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 79.5 | 79.5 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 95 | 95 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 386 | 386 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 440.62 | 440.62 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | NULL | 0 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32878 | 32878 | 2020-08-24 08:39 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 1715.2 | 1715.2 | Miscellaneous | 2020-08-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32882 | 32882 | 2020-08-25 07:45 | Section 6 | Material Requisition | Not on List | Not on List | 700 | m | 69.85 | 48895 | Miscellaneous | 2020-09-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32886 | 32886 | 2020-08-25 09:31 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No. | 341.4 | 341.4 | Miscellaneous | 2020-08-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32887 | 32887 | 2020-08-25 11:23 | Section 6 | Material Requisition | Bagged | Sharp Sand Bulk Bag (938208) | 10 | Each | 34.94 | 349.4 | Aggregate | 2020-09-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32887 | 32887 | 2020-08-25 11:23 | Section 6 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 30 | Each | 3.79 | 113.7 | Aggregate | 2020-09-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32888 | 32888 | 2020-08-25 11:25 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-08-26 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-32888 | 32888 | 2020-08-25 11:25 | Section 4 | Material Requisition | Not on List | Not on List | 4 | tubs | NULL | 0 | Builders Merchants (General) | 2020-08-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-32892 | 32892 | 2020-08-25 14:31 | Core | Material Requisition | PPE, Small Tools and Consumables | Helmet Safety Evolite Slip Cr2 Black C/W A14 Logos (13663) | 5 | Each | 11.15 | 55.75 | PPE | 2020-08-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32892 | 32892 | 2020-08-25 14:31 | Core | Material Requisition | PPE, Small Tools and Consumables | Helmet Safety Evolite Slip Cr2 White C/W A14 Logos (13668) | 15 | Each | 11.15 | 167.25 | PPE | 2020-08-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32893 | 32893 | 2020-08-25 15:57 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 60 | Each | 6.45 | 387 | Blocks and Bricks | 2020-08-28 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 130 | 130 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 184.85 | 184.85 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 1654.8 | 1654.8 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20041612180.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 1365 | 1365 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20031910420.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 400.32 | 400.32 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20052716020.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 188.6 | 188.6 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20062914390.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 905.28 | 905.28 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20070110150 (2).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 223.79 | 223.79 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20070710490.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32904 | 32904 | 2020-08-26 11:06 | Section 2 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282)
240 | Each | 2.48 | 595.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-08-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14245 | Keyline Builders Merchants Ltd (1100980) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32904 | REQ - Finance Team | NULL | NULL
MREQ-32906 | 32906 | 2020-08-26 13:23 | Section 4 | Material Requisition | Not on List | Not on List | 56 | No | 5.23 | 292.88 | Builders Merchants (General) | 2020-08-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32939 | 32939 | 2020-09-01 08:45 | Section 4 | Material Requisition | Not on List | Not on List | 8 | number | 177.53 | 1420.24 | Miscellaneous | 2020-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32946 | 32946 | 2020-09-02 07:00 | Section 6 | Material Requisition | Not on List | Not on List | 150 | m3 | 81.3 | 12195 | Ready Mixed Concrete | 2020-09-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 354.93 | 354.93 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 459.41 | 459.41 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 186.34 | 186.34 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 821.72 | 821.72 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 272.38 | 272.38 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 7219.39 | 7219.39 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 305.72 | 305.72 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 7223.39 | 7223.39 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 566.49 | 566.49 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 45.24 | 45.24 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 1276.12 | 1276.12 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 364.51 | 364.51 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 65.16 | 65.16 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 165.42 | 165.42 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 193.6 | 193.6 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 264 | 264 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 4 | No | 2.36 | 9.44 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32960 | 32960 | 2020-09-04 12:53 | Section 6 | Material Requisition | Not on List | Not on List
1 | NULL | 14330.34 | 14330.34 | Electrical | 2020-09-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14250 | UK Power Networks (Operations) (1284772) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32960/Request/S6 - Electrical Wks. for Rd. Lighting-Extg.L.Column Disconnections.zip | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32960 | REQ - Finance Team | NULL | NULL
MREQ-32962 | 32962 | 2020-09-04 13:41 | Section 2 | Material Requisition | Not on List | Not on List | 9 | number | 262 | 2358 | Miscellaneous | 2020-09-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32963 | 32963 | 2020-09-04 13:44 | Section 1 | Material Requisition | Not on List | Not on List | 3 | number | 262 | 786 | Miscellaneous | 2020-09-13 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32964 | 32964 | 2020-09-04 13:46 | Section 3 | Material Requisition | Not on List | Not on List | 10 | number | 262 | 2620 | Miscellaneous | 2020-09-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32967 | 32967 | 2020-09-04 14:14 | Section 4 | Material Requisition | Aggregate | Not on List | 500 | tonnes | 21.75 | 10875 | Builders Merchants (General) | 2020-09-04 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32979 | 32979 | 2020-09-07 08:33 | Section 4 | Material Requisition | Not on List | Not on List | 1 | number | 450 | 450 | Miscellaneous | 2020-09-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32985 | 32985 | 2020-09-07 08:36 | Section 6 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768)
20 | Each | 3.79 | 75.8 | Builders Merchants (General) | 2020-09-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | Skyland Contractors Ltd | op 14254 | Keyline Builders Merchants Ltd (1100980) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32985 | REQ - Finance Team | NULL | NULL
MREQ-32985 | 32985 | 2020-09-07 08:36 | Section 6 | Material Requisition | Bagged | Sharp Sand Bulk Bag (938208) | 2 | Each | 34.94 | 69.88 | Builders Merchants (General) | 2020-09-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 289.52 | 289.52 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 425.52 | 425.52 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 23.61 | 23.61 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 479.22 | 479.22 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 276.45 | 276.45 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 114.72 | 114.72 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 56.1 | 56.1 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32992 | 32992 | 2020-09-07 11:51 | Section 6 | Material Requisition | Not on List | Not on List | 1 | 1 | NULL | 0 | Miscellaneous | 2020-09-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 3030 - Special Ecological Measures | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-32996 | 32996 | 2020-09-07 13:39 | Section 4 | Material Requisition | Kerbs | Not on List | 5 | Units | 8.55 | 42.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-09-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32998 | 32998 | 2020-09-07 15:21 | Section 4 | Material Requisition | Not on List | Not on List | 40 | loads | 140 | 5600 | Builders Merchants (General) | 2020-09-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 608 - Topsoil (place) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33000 | 33000 | 2020-09-07 16:10 | Core | Material Requisition | Waste Management | Not on List | 1 | no | 2500 | 2500 | Waste (Recycling) | 2020-09-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33001 | 33001 | 2020-09-07 16:00 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 224.89 | 224.89 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33005 | 33005 | 2020-09-07 20:03 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 1162.46 | 1162.46 | Office Supplies | 2020-09-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33006 | 33006 | 2020-09-07 20:08 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 1199.14 | 1199.14 | Miscellaneous | 2020-09-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 121 - Phones / Radios / Comms | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33008 | 33008 | 2020-09-08 07:42 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain End Cap 255/305/480 (758897)
4 | Each | 4.67 | 18.68 | Concrete Drainage | 2020-09-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | JP Flynn Construction Ltd | 14258 | Keyline Builders Merchants Ltd (1100980) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33008 | REQ - Finance Team | NULL | NULL
MREQ-33012 | 33012 | 2020-09-08 08:43 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 4456 | 4456 | Damage Charges | 2020-09-08 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33013 | 33013 | 2020-09-08 12:31 | Section 4 | Material Requisition | Not on List | Not on List
25 | ltrs | 0.01 | 0.25 | Gas Oil | 2020-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 1088 | Watson Petroleum Ltd (Hall Fue (1262699) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33013 | REQ - Finance Team | NULL | NULL
MREQ-33014 | 33014 | 2020-09-08 12:38 | Section 3 | Material Requisition | Not on List | Not on List
25 | ltrs | 1 | 25 | Gas Oil | 2020-09-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 3689 | Watson Petroleum Ltd (Hall Fue (1262699) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33014 | REQ - Finance Team | NULL | NULL
MREQ-33015 | 33015 | 2020-09-08 15:10 | Core | Material Requisition | Not on List | Not on List | 3 | no. | 95 | 285 | Surveying Consumables | 2020-09-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33015 | 33015 | 2020-09-08 15:10 | Core | Material Requisition | Not on List | Not on List | 10 | no. | 2 | 20 | Surveying Consumables | 2020-09-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33015 | 33015 | 2020-09-08 15:10 | Core | Material Requisition | Not on List | Not on List | 3 | no. | 75 | 225 | Surveying Consumables | 2020-09-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33015 | 33015 | 2020-09-08 15:10 | Core | Material Requisition | Not on List | Not on List | 5 | No. | 18 | 90 | Surveying Consumables | 2020-09-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33015 | 33015 | 2020-09-08 15:10 | Core | Material Requisition | Not on List | Not on List | 3 | no. | 295 | 885 | Surveying Consumables | 2020-09-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33016 | 33016 | 2020-09-08 16:35 | Section 6 | Material Requisition | Misc | Not on List | 1 | NULL | 1000 | 1000 | Office Supplies | 2020-09-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 111 - Stationery / Postage | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33017 | 33017 | 2020-09-08 16:51 | Section 4 | Material Requisition | Not on List | Not on List | 56 | bags | 3.67 | 205.52 | Builders Merchants (General) | 2020-09-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33021 | 33021 | 2020-09-09 08:32 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 163.83 | 163.83 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33021 | 33021 | 2020-09-09 08:32 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 536.52 | 536.52 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33021 | 33021 | 2020-09-09 08:32 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 373.54 | 373.54 | Miscellaneous | 2020-09-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33021 | 33021 | 2020-09-09 08:32 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 65 | 65 | Miscellaneous | 2020-09-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33021 | 33021 | 2020-09-09 08:32 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 4590.83 | 4590.83 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33025 | 33025 | 2020-09-09 09:00 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 442.7 | 442.7 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33025 | 33025 | 2020-09-09 09:00 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 445.12 | 445.12 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33025 | 33025 | 2020-09-09 09:00 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 850 | 850 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
NULL | 33025 | 2020-09-09 09:00 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 6187.5 | 6187.5 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-33027 | 33027 | 2020-09-09 09:59 | Section 4 | Material Requisition | Kerbs | Not on List | 40 | No. | 2.48 | 99.2 | Builders Merchants (General) | 2020-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33026 | 33026 | 2020-09-09 09:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 1142.97 | 1142.97 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33026 | 33026 | 2020-09-09 09:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 764.7 | 764.7 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33026 | 33026 | 2020-09-09 09:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 589.85 | 589.85 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33026 | 33026 | 2020-09-09 09:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 18257.14 | 18257.14 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33026 | 33026 | 2020-09-09 09:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 4945.14 | 4945.14 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33028 | 33028 | 2020-09-09 10:53 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 67.1 | 67.1 | Miscellaneous | 2020-09-25 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33029 | 33029 | 2020-09-09 14:23 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 4027.24 | 4027.24 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14268 | Gap Group Ltd (1108091) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33029/Request/Fwd claim _254843 2855PH33105040331 COSTAIN SKANSKA-F586337-120 ROLLER- 3194189.msg | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33029 | REQ - Finance Team | NULL | NULL
MREQ-33029 | 33029 | 2020-09-09 14:23 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 3357.6 | 3357.6 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33029 | 33029 | 2020-09-09 14:23 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 2016.43 | 2016.43 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33032 | 33032 | 2020-09-09 17:19 | Section 6 | Material Requisition | Iron Wear | Not on List
26 | each | 58.04 | 1509.04 | Miscellaneous | 2020-09-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | Skyland Contractors Ltd | 14281 | Keyline Builders Merchants Ltd (1100980) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33032 | REQ - Finance Team | NULL | NULL
MREQ-33037 | 33037 | 2020-09-10 09:33 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 770 | 770 | Miscellaneous | 2020-09-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33038 | 33038 | 2020-09-10 09:51 | Section 6 | Material Requisition | Not on List | Not on List | 1500 | NULL | 0.45 | 675 | Office Supplies | 2020-09-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | IMO - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers