MREQ-33045 | 33045 | 2020-09-11 07:04 | Section 6 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 3.79 | 212.24 | Aggregate | 2020-09-14 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33045 | 33045 | 2020-09-11 07:04 | Section 6 | Material Requisition | Bagged | Kiln Dried Sand 25kg (518674) | 20 | Each | 2.31 | 46.2 | Aggregate | 2020-09-14 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33062 | 33062 | 2020-09-14 09:12 | Section 6 | Material Requisition | Misc | Not on List
2 | No. | 120 | 240 | Miscellaneous | 2020-09-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | IMO - Closed | Yes - Approve | Yes - Approve | Yes | Thermometer Point | /sites/BPM/FlowForma/FormDocuments/MREQ33062/IMO-P-Card-Purchase/MREQ33062 -Invoice SI-131194_2020-09-17_17-30-29.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33062 | REQ - Finance Team | NULL | NULL
MREQ-33064 | 33064 | 2020-09-14 15:48 | Section 4 | Material Requisition | Kerbs | Not on List | 20 | No, | 4.42 | 88.4 | Builders Merchants (General) | 2020-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33065 | 33065 | 2020-09-14 15:56 | Section 4 | Material Requisition | Not on List | Not on List | 36 | Number | 8.25 | 297 | Blocks and Bricks | 2020-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-0033071 | 33071 | 2020-09-15 10:57 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | No - Pass Back | NULL | REQ - Buyers
MREQ-0033071 | 33071 | 2020-09-15 10:57 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 253 | 253 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | No - Pass Back | NULL | REQ - Buyers
MREQ-33072 | 33072 | 2020-09-15 11:22 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 3830 | 3830 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33072 | 33072 | 2020-09-15 11:22 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 5136.32 | 5136.32 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33072 | 33072 | 2020-09-15 11:22 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 2184.9 | 2184.9 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33072 | 33072 | 2020-09-15 11:22 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 19617.83 | 19617.83 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33073 | 33073 | 2020-09-15 12:18 | Section 6 | Material Requisition | Combined Drainage | Not on List | 4 | No | 42.74 | 170.96 | Concrete Drainage | 2020-09-18 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-0033080 | 33080 | 2020-09-15 15:24 | Section 3 | Material Requisition | Not on List | Not on List
1 | No | 177.6 | 177.6 | Miscellaneous | 2020-09-16 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | A14 IDT | NULL | NULL | Operational Approval | No - Pass Back | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33080/Request/DOC120820-12082020081706.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33080 | REQ - Finance Team | NULL | NULL
MREQ-33081 | 33081 | 2020-09-15 15:44 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 212.45 | 212.45 | Miscellaneous | 2020-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Passed Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-33081 | 33081 | 2020-09-15 15:44 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 395 | 395 | Miscellaneous | 2020-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Passed Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-33089 | 33089 | 2020-09-17 07:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 528 | 528 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33089 | 33089 | 2020-09-17 07:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 85 | 85 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33090 | 33090 | 2020-09-17 08:18 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 72 | 72 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33091 | 33091 | 2020-09-17 11:06 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 19237.98 | 19237.98 | Miscellaneous | 2020-09-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33092 | 33092 | 2020-09-17 11:18 | Section 6 | Material Requisition | Not on List | Not on List | 1 | NULL | 31317.8 | 31317.8 | Miscellaneous | 2020-09-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | FEE6 - Fee Based Costs inc. insurance | 107 - Insurance | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33106 | 33106 | 2020-09-18 12:57 | Section 6 | Material Requisition | Not on List | Not on List
1 | NULL | 52.36 | 52.36 | Small Tools (Consumables) | 2020-09-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | op 14290 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33106 | REQ - Finance Team | NULL | NULL
MREQ-33120 | 33120 | 2020-09-21 09:53 | Section 6 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 520 | Each | 2.48 | 1289.6 | Blocks and Bricks | 2020-09-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33123 | 33123 | 2020-09-22 07:10 | Section 6 | Material Requisition | Bagged | Sharp Sand Bulk Bag (938208) | 8 | Each | 34.94 | 279.52 | Aggregate | 2020-09-23 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33124 | 33124 | 2020-09-22 08:28 | Section 4 | Material Requisition | Concrete Drainage | Not on List | 3 | No. | 25.17 | 75.51 | Concrete Drainage | 2020-09-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2701 - Accommodation works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33124 | 33124 | 2020-09-22 08:28 | Section 4 | Material Requisition | Concrete Drainage | Not on List | 5 | No. | 100.77 | 503.85 | Concrete Drainage | 2020-09-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2701 - Accommodation works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33125 | 33125 | 2020-09-22 08:45 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 16 | No. | 6.34 | 101.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-09-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33125 | 33125 | 2020-09-22 08:45 | Section 4 | Material Requisition | Misc | Not on List | 3 | No. | 30.26 | 90.78 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-09-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33161 | 33161 | 2020-09-28 07:59 | Core | Material Requisition | Misc | Not on List | 1 | No. | 1200 | 1200 | Professional Services | 2020-09-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33162 | 33162 | 2020-09-28 09:36 | Section 3 | Material Requisition | Aggregate | Not on List | 100 | TM | 34.25 | 3425 | Aggregate | 2020-10-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-33163 | 33163 | 2020-09-28 09:45 | Section 2 | Material Requisition | Misc | Not on List
1 | NULL | NULL | 0 | Damage Charges | 2020-09-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14299 | T & M Plant Hire Ltd (1134413) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33163/Request/BRWA86BAD89A65C_021226.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33163 | REQ - Finance Team | NULL | NULL
MREQ-33171 | 33171 | 2020-09-28 12:22 | Core | Material Requisition | Not on List | Not on List
1 | NULL | 795.06 | 795.06 | Surveying Consumables | 2020-09-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | A14 IDT | 14306 | Korec (1114049) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33171/Request/hun052648 merged.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33171 | REQ - Finance Team | NULL | NULL
MREQ-33174 | 33174 | 2020-09-28 13:20 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 688 | no | 5.52 | 3797.76 | Blocks and Bricks | 2020-09-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33176 | 33176 | 2020-09-28 16:32 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 10 | Each | 8.08 | 80.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-09-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33176 | 33176 | 2020-09-28 16:32 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 10 | Each | 8.08 | 80.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-09-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33177 | 33177 | 2020-09-28 16:52 | Section 6 | Material Requisition | Bagged | Sharp Sand Bulk Bag (938208) | 12 | Each | 34.94 | 419.28 | Builders Merchants (General) | 2020-09-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33177 | 33177 | 2020-09-28 16:52 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 250 | m2 | 34.59 | 8647.5 | Builders Merchants (General) | 2020-09-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33178 | 33178 | 2020-09-28 17:05 | Section 6 | Material Requisition | Aggregate | Not on List | 300 | m3 | 77.33 | 23199 | Aggregate | 2020-09-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33184 | 33184 | 2020-09-29 08:25 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 6187.5 | 6187.5 | Miscellaneous | 2020-09-30 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33186 | 33186 | 2020-09-29 10:23 | Section 3 | Material Requisition | Not on List | Not on List
8 | ea | 58.87 | 470.96 | Flow Control | 2020-09-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | Skyland Contractors Ltd | 14311 | Keyline Builders Merchants Ltd (1100980) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33186 | REQ - Finance Team | NULL | NULL
MREQ-33198 | 33198 | 2020-09-30 12:37 | Core | Material Requisition | Not on List | Not on List | 1 | No | 345 | 345 | Miscellaneous | 2020-09-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33200 | 33200 | 2020-09-30 16:48 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 80 | 80 | Miscellaneous | 2020-09-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 115 - Medical / 1st Aid | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33202 | 33202 | 2020-09-30 14:44 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 310.31 | 310.31 | Miscellaneous | 2020-09-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14309 | UK Power Networks (Operations) (1284772) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33202 | REQ - Finance Team | NULL | NULL
MREQ-33212 | 33212 | 2020-10-01 15:13 | Section 4 | Material Requisition | Kerbs | Not on List | 3 | Tubs | 49 | 147 | Builders Merchants (General) | 2020-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33212 | 33212 | 2020-10-01 15:13 | Section 4 | Material Requisition | Not on List | Not on List | 40 | bags | 3.67 | 146.8 | Builders Merchants (General) | 2020-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1701 - Insitu Concrete | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33217 | 33217 | 2020-10-02 12:54 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 365 | 365 | Miscellaneous | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33217 | 33217 | 2020-10-02 12:54 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 135 | 135 | Miscellaneous | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33217 | 33217 | 2020-10-02 12:54 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 173.19 | 173.19 | Miscellaneous | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33217 | 33217 | 2020-10-02 12:54 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 230 | 230 | Miscellaneous | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33220 | 33220 | 2020-10-02 15:44 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 19304 | 19304 | Builders Merchants (General) | 2020-10-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33221 | 33221 | 2020-10-02 15:34 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33221 | 33221 | 2020-10-02 15:34 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 1365 | 1365 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33221 | 33221 | 2020-10-02 15:34 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33232 | 33232 | 2020-10-05 15:39 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1193.8 | 1193.8 | Miscellaneous | 2020-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33233 | 33233 | 2020-10-05 15:56 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Miscellaneous | 2020-10-30 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-33233 | 33233 | 2020-10-05 15:56 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 138 | 138 | Miscellaneous | 2020-10-30 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-33234 | 33234 | 2020-10-05 16:12 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 350 | 350 | Miscellaneous | 2020-10-30 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33244 | 33244 | 2020-10-07 09:35 | Section 5 | Material Requisition | Not on List | Not on List | 5 | No | 119.44 | 597.2 | Miscellaneous | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33245 | 33245 | 2020-10-07 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 43 | 43 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33245 | 33245 | 2020-10-07 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 288 | 288 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 30.429 | M3 | 10.52 | 320.11 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 1 | No | 6 | 6 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 13.609 | M3 | 10.52 | 143.17 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 1 | No | 6 | 6 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 4.157 | M3 | 10.52 | 43.73 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 1 | No | 6 | 6 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33249 | 33249 | 2020-10-07 15:42 | Section 5 | Material Requisition | Waste Management | Not on List | 5.372 | M3 | 10.52 | 56.51 | Waste (General) | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33250 | 33250 | 2020-10-07 16:05 | Section 2 | Material Requisition | Waste Management | Not on List | 1 | No | 950 | 950 | Waste (General) | 2020-10-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33250 | 33250 | 2020-10-07 16:05 | Section 2 | Material Requisition | Waste Management | Not on List | 1 | No | 950 | 950 | Waste (General) | 2020-10-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33255 | 33255 | 2020-10-08 11:12 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33267 | 33267 | 2020-10-09 10:06 | Section 6 | Material Requisition | Aggregate | Not on List | 8 | M3 | 80.6 | 644.8 | Aggregate | 2020-10-09 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 537.54 | 537.54 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157474(Previously Sent) (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List
2 | No | 0 | 0 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157472(Previously Sent).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 50.15 | 50.15 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157458 (Previously Sent).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 15.17 | 15.17 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157458 (Previously Sent) (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 83.2 | 83.2 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157458 (Previously Sent) (2).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 15.17 | 15.17 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157458 (Previously Sent) (3).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 87.75 | 87.75 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157458 (Previously Sent) (4).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 42.8 | 42.8 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157470(Previously Sent).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 127.47 | 127.47 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157470(Previously Sent) (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List | 4 | No | 724.14 | 2896.56 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 525.1 | 525.1 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | N0 | 708.71 | 708.71 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33280 | 33280 | 2020-10-12 07:48 | Section 6 | Material Requisition | Aggregate | Type 1 | 220 | Tonnes | 21.65 | 4763 | Aggregate | 2020-10-13 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 701 - Sub-base | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33282 | 33282 | 2020-10-12 09:48 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 38.87 | 38.87 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33282/Request/BRW12R2SRV001_BRW_Office_WHL06494_4230_001.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
MREQ-33282 | 33282 | 2020-10-12 09:48 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 332.27 | 332.27 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
MREQ-33282 | 33282 | 2020-10-12 09:48 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 357.81 | 357.81 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
MREQ-33282 | 33282 | 2020-10-12 09:48 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 367.49 | 367.49 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
MREQ-33282 | 33282 | 2020-10-12 09:48 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 712.72 | 712.72 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
MREQ-33282 | 33282 | 2020-10-12 09:48 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 113.3 | 113.3 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
MREQ-33282 | 33282 | 2020-10-12 09:48 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 82.8 | 82.8 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
NULL | 33285 | 2020-10-12 16:03 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1229.69 | 1229.69 | Miscellaneous | 2020-10-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-33286 | 33286 | 2020-10-12 16:11 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Lot | 72228.16 | 72228.16 | Electrical | 2020-10-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1504 - Technology Equipment | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
NULL | 33288 | 2020-10-13 07:53 | Section 4 | Material Requisition | Not on List | Not on List | 56 | number | NULL | 0 | Builders Merchants (General) | 2020-10-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-33289 | 33289 | 2020-10-13 08:46 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 426.97 | 426.97 | Office Supplies | 2020-10-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33293 | 33293 | 2020-10-13 10:09 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 490 | 490 | Professional Services | 2020-10-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 115 - Medical / 1st Aid | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33294 | 33294 | 2020-10-13 10:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 184.17 | 184.17 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33294 | 33294 | 2020-10-13 10:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 187.2 | 187.2 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33294 | 33294 | 2020-10-13 10:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 750 | 750 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33295 | 33295 | 2020-10-13 12:01 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 456 | 456 | Miscellaneous | 2020-10-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33295 | 33295 | 2020-10-13 12:01 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 234 | 234 | Miscellaneous | 2020-10-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33295 | 33295 | 2020-10-13 12:01 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 137 | 137 | Miscellaneous | 2020-10-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 66.7 | 66.7 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33306/Request/20201008135452445.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 38.26 | 38.26 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 58.44 | 58.44 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 34.45 | 34.45 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 5.68 | 5.68 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 98.02 | 98.02 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead PlantHire CoLtd t/a Ev (1315401) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 102.7 | 102.7 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 184.56 | 184.56 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 177.03 | 177.03 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 96.39 | 96.39 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 683.02 | 683.02 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33306 | 33306 | 2020-10-14 08:39 | Section 4 | Material Requisition | Not on List | Not on List
1 | No | 372.22 | 372.22 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33311 | 33311 | 2020-10-14 19:17 | Section 6 | Material Requisition | Not on List | Not on List | 1 | as per attached quotation | 679.11 | 679.11 | Miscellaneous | 2020-10-18 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 154 - Traffic Management and Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33312 | 33312 | 2020-10-14 20:15 | Section 6 | Material Requisition | Bagged | Not on List | 56 | bags | 6.75 | 378 | Builders Merchants (General) | 2020-10-16 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33317 | 33317 | 2020-10-15 12:53 | Section 4 | Material Requisition | Not on List | Not on List | 994 | 1 | 1.33 | 1322.02 | Ductile Drainage | 2020-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33317 | 33317 | 2020-10-15 12:53 | Section 4 | Material Requisition | Kerbs | Not on List | 48 | 1 | 6.34 | 304.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33322 | 33322 | 2020-10-15 16:08 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 425 | 425 | Miscellaneous | 2020-10-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 110 - Welfare Costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33323 | 33323 | 2020-10-16 09:15 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Boot Magnum Sitemaster Comp Toe/Plate M801232 Black (195306) | 1 | Each | 62.53 | 62.53 | PPE | 2020-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33336 | 33336 | 2020-10-19 08:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 182.67 | 182.67 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyers Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33336 | 33336 | 2020-10-19 08:35 | Section 4 | Material Requisition | Not on List | Not on List | 40 | No | 12.21 | 488.4 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyers Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33336 | 33336 | 2020-10-19 08:35 | Section 4 | Material Requisition | Not on List | Not on List | 40 | No | 28.81 | 1152.4 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyers Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33336 | 33336 | 2020-10-19 08:35 | Section 4 | Material Requisition | Not on List | Not on List | 38 | No | 143.87 | 5467.06 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyers Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33338 | 33338 | 2020-10-19 10:50 | Section 2 | Material Requisition | Not on List | Not on List
1 | No | 132.83 | 132.83 | Miscellaneous | 2020-10-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Buyers Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33338/Request/20201008135452445.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33338 | REQ - Finance Team | NULL | NULL
MREQ-33339 | 33339 | 2020-10-19 11:42 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 278.41 | 278.41 | Miscellaneous | 2020-10-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyers Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-33340 | 33340 | 2020-10-19 12:04 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 114 | 114 | Miscellaneous | 2020-10-30 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Buyers Queue | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-33345 | 33345 | 2020-10-20 07:42 | Section 2 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2020-10-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyers Queue | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33349 | 33349 | 2020-10-20 09:13 | Section 6 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-10-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyers Queue | Yes - Approve | Yes - Approve | Req - S6 Buyers