## Sheet1
MREQ_Number | FFID | Date_and_Time_of_Request | Section | Order_Type | Item_Category | Item_Description | Quantity_Required | Unit | Unit_Price | Total_Cost | Category | Date_Required | Delivery_Location | Location_WBS | Activity_WBS | Current_Stage | Operational_Approval | Commercial_Approval | Buyer
MREQ-4915-001 | 4915 | 2018-08-10 09:55 | Section 3 | Material | Aggregate | NULL | 20 | Tonnes | 16 | 320 | Aggregate | 2018-08-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1104 - Footways and Paved Areas | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-4996-0010 | 4996 | 2018-08-13 15:33 | Section 3 | Material | Not on List | NULL | 20 | no | NULL | 0 | NULL | 2018-08-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Rigidrain P/E 150Mm Dia Incl Coup/Sealia | 36 | no | 10.5 | 378 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 30 | Each | 17.45 | 523.5 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21737-001025 | 21737 | 2019-08-02 14:58 | Core | Material | Not on List | Not on List | 1 | No. | 20000 | 20000 | Office Supplies | 2019-08-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21712-001025 | 21712 | 2019-08-02 08:01 | Section 4 | Material | Not on List | Not on List | 4 | rolls | 258.05 | 1032.2 | Builders Merchants (General) | 2019-08-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21741-001025 | 21741 | 2019-08-02 15:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-08-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21748-001025 | 21748 | 2019-08-02 15:45 | Core | Material | Not on List | Not on List | 1 | ea | 8750 | 8750 | Training | 2019-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21748-001025 | 21748 | 2019-08-02 15:45 | Core | Material | Not on List | Not on List | 1 | ea | 473.4 | 473 | Training | 2019-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material/at | Not on List | Not on List | 20 | Each | 10.04 | 200.8 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21755-001025 | 21755 | 2019-08-02 16:39 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 29 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-08-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21719-001025 | 21719 | 2019-08-02 10:01 | Section 5 | Material | Not on List | NULL | 1 | SM | 1779.84 | 1779.84 | Builders Merchants (General) | NULL | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 12 | Each | 24.44 | 293.28 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 10 | Each | 35.52 | 355.2 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21746-001025 | 21746 | 2019-08-02 15:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 2 | Each | 55.41 | 110.82 | Concrete Drainage | 2019-08-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21782-001025 | 21782 | 2019-08-05 08:10 | Core | Material | Not on List | Not on List | 15 | Boxes | 75 | 1125 | Miscellaneous | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21782-001025 | 21782 | 2019-08-05 08:10 | Core | Material | Not on List | Not on List | 4 | Packs | 36 | 144 | Miscellaneous | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21782-001025 | 21782 | 2019-08-05 08:10 | Core | Material | Not on List | Not on List | 35 | Packs | 118.75 | 4156 | Miscellaneous | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21782-001025 | 21782 | 2019-08-05 08:10 | Core | Material | Not on List | Not on List | 2 | Sets | 395 | 790 | Miscellaneous | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21786-001025 | 21786 | 2019-08-05 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 105.91 | 106 | Miscellaneous | 2019-08-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20693-001025 | 20693 | 2019-07-12 14:14 | Core | Material | Not on List | Not on List | 1 | each | 115668.7 | 115668.7 | Miscellaneous | 2019-07-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 40 | Each | 42.1 | 1684 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21817-001025 | 21817 | 2019-08-06 07:00 | Section 4 | Material | Not on List | Not on List | 144 | NULL | 6.29 | 906 | Small Tools (Consumables) | 2019-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-20236-001025 | 20236 | 2019-07-04 11:32 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21825-001025 | 21825 | 2019-08-06 08:42 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-09-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-21827-001025 | 21827 | 2019-08-06 08:24 | Core | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21827-001025 | 21827 | 2019-08-06 08:24 | Core | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21790-001025 | 21790 | 2019-08-05 13:32 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 26 | Each | 29.25 | 760.5 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21798-001025 | 21798 | 2019-08-05 15:02 | Core | Material | NULL | NULL | 1 | Each | 4116 | 4116 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21839-001025 | 21839 | 2019-08-06 11:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | each | NULL | 0 | PPE | 2019-09-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-21842-001025 | 21842 | 2019-08-06 11:46 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5564-00390 | 5564 | 2018-08-23 11:30 | Section 4 | Material | Not on List | Not on List | 75 | bags | 11.43 | 857.25 | Miscellaneous | 2018-10-22 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21846-001025 | 21846 | 2019-08-06 12:09 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21852-001025 | 21852 | 2019-08-06 12:24 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21339-001025 | 21339 | 2019-07-25 12:36 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 10 | Each | 33.5 | 335 | Builders Merchants (General) | 2019-08-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21339-001025 | 21339 | 2019-07-25 12:36 | Section 5 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 2.97 | 118.8 | Builders Merchants (General) | 2019-08-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21774-001025 | 21774 | 2019-08-05 07:41 | Section 2 | Material | Kerbs | Not on List | 140 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-07 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21774-001025 | 21774 | 2019-08-05 07:41 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 5 | Each | 11.94 | 59.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-07 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21774-001025 | 21774 | 2019-08-05 07:41 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 5 | Each | 11.94 | 59.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-07 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 225Mm Ridgidrain Dbl Skt Coupler | 40 | Each | 3.38 | 135.2 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21877-001025 | 21877 | 2019-08-06 15:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-21878-001025 | 21878 | 2019-08-06 16:24 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | NULL | 0 | PPE | 2019-08-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21860-001025 | 21860 | 2019-08-06 13:27 | Section 3 | Material | Aggregate | Type 1 | 7500 | Tonnes | 21.65 | 162375 | Aggregate | 2019-08-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21334-001025 | 21334 | 2019-07-25 11:50 | Section 3 | Material | Not on List | Not on List | 55 | m | 10.9 | 599.5 | Miscellaneous | 2019-07-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21334-001025 | 21334 | 2019-07-25 11:50 | Section 3 | Material | Not on List | Not on List | 95 | No. | 2.16 | 205.2 | Fixings and Fasteners | 2019-07-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 225Mm Ridgidrain Seal | 100 | Each | 1.86 | 186 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21929-001025 | 21929 | 2019-08-07 09:23 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-08-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21823-001025 | 21823 | 2019-08-06 07:34 | Section 5 | Material | Not on List | Not on List | 1 | SM | 2471.04 | 2471.04 | Miscellaneous | 2019-08-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21931-001025 | 21931 | 2019-08-07 10:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21840-001025 | 21840 | 2019-08-06 11:33 | Section 4 | Material | Not on List | Not on List | 144 | Pack Water | 6.29 | 905.76 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21654-001025 | 21654 | 2019-08-01 07:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | NULL | 6.29 | 905.76 | Small Tools (Consumables) | 2019-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21653-001025 | 21653 | 2019-08-01 07:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 905.76 | 905.76 | Small Tools (Consumables) | 2019-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21768-001025 | 21768 | 2019-08-05 07:31 | Section 4 | Material | Not on List | Not on List | 1 | Each | 200.28 | 200.28 | Miscellaneous | 2019-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21670-001025 | 21670 | 2019-08-01 10:21 | Section 4 | Material | Waste Management | Not on List | 1 | NULL | 1199.88 | 1199.88 | Waste (General) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 605 - Disposal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5564-00390 | 5564 | 2018-08-23 11:30 | Section 4 | Material | NULL | NULL | 1 | Each | 1200 | 1200 | Miscellaneous | 2018-10-22 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Not on List | 28 | No | 39.7 | 1111.6 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5570-00392 | 5570 | 2018-08-23 12:15 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.94 | 94 | Concrete Accessories | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21644-001025 | 21644 | 2019-07-31 17:06 | Section 2 | Material | Ducting | Not on List | 6 | length | NULL | 0 | Electrical | 2019-08-06 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21644-001025 | 21644 | 2019-07-31 17:06 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 3 | roll | NULL | 0 | Small Tools (Consumables) | 2019-08-06 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21043-001025 | 21043 | 2019-07-19 11:38 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21939-001025 | 21939 | 2019-08-07 12:17 | Section 1 | Material | Not on List | Not on List | 10 | boxes | NULL | 0 | Miscellaneous | 2019-08-09 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-21947-001025 | 21947 | 2019-08-07 12:46 | Core | Material | Not on List | Not on List | 1000 | NULL | NULL | 0 | Office Supplies | 2019-08-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5570-00392 | 5570 | 2018-08-23 12:15 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.08 | 108 | Concrete Accessories | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21879-001025 | 21879 | 2019-08-06 16:17 | Section 3 | Material | Not on List | Not on List | 15 | each | 718 | 10770 | Miscellaneous | 2019-08-19 | Gate D - 1339643 - BN10 Via Main Compound Entrance | GN3A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21879-001025 | 21879 | 2019-08-06 16:17 | Section 3 | Material | Not on List | Not on List | 6 | Each | 951.7 | 5710.2 | Miscellaneous | 2019-08-19 | Gate D - 1339643 - BN10 Via Main Compound Entrance | GN3B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21949-001025 | 21949 | 2019-08-07 14:15 | Section 5 | Material | Not on List | Not on List | 4 | EA | 39.65 | 158.6 | Plastic Drainage | 2019-08-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21779-001025 | 21779 | 2019-08-05 09:22 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 407.56 | 407.56 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21873-001025 | 21873 | 2019-08-06 15:57 | Section 4 | Material | Not on List | Not on List | 200 | m | 2.43 | 486 | Builders Merchants (General) | 2019-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21341-001025 | 21341 | 2019-07-25 12:48 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21772-001025 | 21772 | 2019-08-05 08:10 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 12102 | 12102 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21953-001025 | 21953 | 2019-08-07 16:07 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-09 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Request - Ops Pass Back | No - Pass Back | NULL | Req - S1 Buyers
MREQ-21844-001025 | 21844 | 2019-08-06 11:56 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 244.86 | 244.86 | Miscellaneous | 2019-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5578-00396 | 5578 | 2018-08-23 15:02 | Section 4 | Material | Not on List | Not on List | 20 | rolls | 110.27 | 2205.4 | Geotextiles | 2018-09-07 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21977-001025 | 21977 | 2019-08-08 08:24 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 3310.75 | 3311 | Miscellaneous | 2019-08-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21983-001025 | 21983 | 2019-08-08 08:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 827.35 | 827 | Small Tools (Consumables) | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-13758-001025 | 13758 | 2019-03-11 10:56 | Core | Material | Not on List | Not on List | 1 | number | 3061.08 | 3061.08 | Professional Services | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18132-001025 | 18132 | 2019-05-28 14:22 | Core | Material | Not on List | Not on List | 110 | people | 58 | 6380 | Miscellaneous | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21935-001025 | 21935 | 2019-08-07 11:15 | Section 5 | Material | Not on List | Not on List | 1 | SM | 4778.45 | 4778.45 | Miscellaneous | 2019-08-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21985-001025 | 21985 | 2019-08-08 09:27 | Core | Material | Not on List | Not on List | 1 | NULL | 10055 | 10055 | Miscellaneous | 2019-08-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 6 | Each | 3.35 | 20.1 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21933-001025 | 21933 | 2019-08-07 10:35 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1965 | 1965 | Waste (General) | 2019-08-09 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21966-001025 | 21966 | 2019-08-07 17:43 | Section 2 | Material | Concrete Drainage | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-08-26 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 20 | Each | 4.5 | 90 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 20 | Each | 5.6 | 112 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 20 | Each | 3.91 | 78.2 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22010-001025 | 22010 | 2019-08-08 14:28 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Concrete Accessories | 2019-08-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21981-001025 | 21981 | 2019-08-08 08:27 | Section 4 | Material | Ducting | Polypipe 94mm x 6m Black Ridgiduct (877654) | 100 | Each | 12.23 | 1223 | Builders Merchants (General) | 2019-08-12 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21981-001025 | 21981 | 2019-08-08 08:27 | Section 4 | Material | Ducting | Polypipe 94mm Ridgiduct Coupler (877674) | 100 | Each | 2.8 | 280 | Builders Merchants (General) | 2019-08-12 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21981-001025 | 21981 | 2019-08-08 08:27 | Section 4 | Material | Ducting | Not on List | 1 | pack | 313.5 | 313.5 | Builders Merchants (General) | 2019-08-12 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 22 | Each | 22.62 | 497.64 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21991-001025 | 21991 | 2019-08-08 11:28 | Core | Material | Not on List | Not on List | 761.85 | Each | 1 | 761.85 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 1 | Each | 325.5 | 325.5 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22064-001025 | 22064 | 2019-08-09 10:25 | Section 3 | Material | Not on List | Not on List | 100 | Anchor | NULL | 0 | Fixings and Fasteners | 2019-08-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22064-001025 | 22064 | 2019-08-09 10:25 | Section 3 | Material | Not on List | Not on List | 100 | Screw | NULL | 0 | Fixings and Fasteners | 2019-08-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22064-001025 | 22064 | 2019-08-09 10:25 | Section 3 | Material | Not on List | Not on List | 2 | Adapter | NULL | 0 | Fixings and Fasteners | 2019-08-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21914-001025 | 21914 | 2019-08-07 07:33 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | ea | 21.3 | 639 | Ductile Drainage | 2019-08-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22052-001025 | 22052 | 2019-08-09 07:43 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 32 | Each | 52.76 | 1688.32 | Plastic Drainage | 2019-08-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22052-001025 | 22052 | 2019-08-09 07:43 | Section 3 | Material | Concrete Drainage | Not on List | 1 | No. | 153.46 | 153.46 | Concrete Drainage | 2019-08-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22052-001025 | 22052 | 2019-08-09 07:43 | Section 3 | Material | Aggregate | Type 1 | 400 | Tonnes | 21.65 | 8660 | Aggregate | 2019-08-12 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5613-00416 | 5613 | 2018-08-24 09:23 | Section 4 | Material | Not on List | Not on List | 1 | Hun | 34.09 | 34.09 | Builders Merchants (General) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22089-001025 | 22089 | 2019-08-09 15:37 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 56 | 112 | Miscellaneous | 2019-08-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | NULL | Yes - Approve | Req - S5 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Not on List | 5 | No | 39.7 | 198.5 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5681-00445 | 5681 | 2018-08-28 12:08 | Section 4 | Material | Not on List | Not on List | 18.147 | tonne | 538 | 9763.09 | Rebar and Mesh | 2018-09-04 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21937-001025 | 21937 | 2019-08-07 11:24 | Section 5 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2019-08-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21937-001025 | 21937 | 2019-08-07 11:24 | Section 5 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 5 | Each | 122.72 | 613.6 | Geotextiles | 2019-08-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21937-001025 | 21937 | 2019-08-07 11:24 | Section 5 | Material | Not on List | Not on List | 1 | SUM | 1340.75 | 1340.75 | Not Sure | 2019-08-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 29 | roll | 177 | 5133 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5753 | 5753 | 2018-08-29 13:27 | Section 4 | Material | Not on List | Not on List | 10000 | NULL | NULL | 0 | Concrete Accessories | 2018-09-05 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 37 | roll | 131 | 4847 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 48 | roll | 188 | 9024 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 56 | roll | 215 | 12040 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 42 | box | 37 | 1554 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 39 | roll | 111.59 | 4352.01 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 1 | each | 107.5 | 107.5 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 750 | each | 42.96 | 32220 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 382 | each | 24.56 | 9381.92 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 2250 | each | 1.41 | 3172.5 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 2264 | each | 0.17 | 384.88 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5758-00463 | 5758 | 2018-08-29 13:49 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Accessories | 2018-09-11 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 1146 | each | 0.71 | 813.66 | Blocks and Bricks | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21778-001025 | 21778 | 2019-08-05 08:49 | Section 4 | Material | Not on List | Not on List | 1 | SUM | 3150 | 3150 | Miscellaneous | 2019-08-16 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22135-001025 | 22135 | 2019-08-12 09:31 | Section 1 | Material | Not on List | Not on List | 1 | EACH | 802.64 | 803 | Miscellaneous | 2019-08-12 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-22136-001025 | 22136 | 2019-08-12 09:33 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 3924.44 | 3924 | Miscellaneous | 2019-08-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5033-0018 | 5033 | 2018-08-14 09:31 | Section 4 | Material | Misc | Kassel Bus Stop Kerb 435*314 (Priced Each Not Mtr) | 15 | no | 112.06 | 1645.43 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | PPE | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 5 | Each | 13 | 65 | PPE | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 10 | Each | 13 | 130 | PPE | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 5mtr/1 (765565) | 5 | Each | 2.7 | 14 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 7.5mtr/2 (765566) | 5 | Each | 5.77 | 29 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 10mtr/3 (765567) | 5 | Each | 12.4 | 62 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Brush Wire 4 Row Heavy Duty C/W Scraper Spartan Pro (504004) | 10 | Each | 0.86 | 9 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-14554-001025 | 14554 | 2019-03-22 13:50 | Section 5 | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289) | 10 | Each | 7.32 | 73 | Small Tools (Consumables) | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-5814-00499 | 5814 | 2018-08-30 14:06 | Section 3 | Material | Not on List | Not on List | 1 | no. | 593.22 | 593.22 | Surveying Consumables | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5810-00488 | 5810 | 2018-08-30 12:49 | Section 3 | Material | Not on List | Not on List | 10 | No | 75 | 750 | Builders Merchants (General) | 2018-09-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 2 | EA | 6.82 | 14 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5766-00464 | 5766 | 2018-08-29 16:47 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 13 | NULL | 27.5 | 357.5 | PPE | 2018-09-07 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 48 | TOTAL | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14611-001025 | 14611 | 2019-03-25 15:01 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | EA | NULL | 0 | Small Tools (Consumables) | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5766-00464 | 5766 | 2018-08-29 16:47 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 34 | NULL | 14.5 | 493 | PPE | 2018-09-07 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14542-001025 | 14542 | 2019-03-22 14:46 | Section 4 | Material | Not on List | Not on List | 52747.62 | Tonne | 5 | 263738.1 | Aggregate | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-5111-00502 | 5111 | 2018-08-15 07:51 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 106.02 | 106.02 | Small Tools (Consumables) | 2018-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14389-001025 | 14389 | 2019-03-20 15:23 | Section 2 | Material | Not on List | Not on List | 10 | item | 0 | 0 | Miscellaneous | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 603 - Processing | IMO Queue | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5506-00494 | 5506 | 2018-08-22 13:55 | Section 3 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2018-08-27 | Gate C - 1339699 - BN08 via Logistics Yard Access | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14641-001025 | 14641 | 2019-03-26 09:09 | Section 2 | Material | Not on List | Not on List | 1500 | number | NULL | 0 | Plastic Drainage | 2019-03-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14642-001025 | 14642 | 2019-03-26 09:07 | Section 6 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-04-02 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 1724 | m2 | 66.88 | 115301.12 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 770 | number | 4.27 | 3287.9 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5506-00494 | 5506 | 2018-08-22 13:55 | Section 3 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2018-08-27 | Gate C - 1339699 - BN08 via Logistics Yard Access | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 770 | roll | 6.31 | 4858.7 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 23 | roll | 177 | 4071 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 14 | roll | 131 | 1834 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 58 | roll | 178 | 10324 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 126 | roll | 215 | 27090 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 232 | roll | 235 | 54520 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 13 | box | 33.57 | 436.41 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 80 | box | 63 | 5040 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 45 | number | 12 | 540 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14613-001025 | 14613 | 2019-03-25 15:44 | Section 4 | Material | NULL | Not on List | 1 | number | 100 | 100 | Blocks and Bricks | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5506-00494 | 5506 | 2018-08-22 13:55 | Section 3 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2018-08-27 | Gate C - 1339699 - BN08 via Logistics Yard Access | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14659-001025 | 14659 | 2019-03-26 11:59 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-14660-001025 | 14660 | 2019-03-26 12:10 | Section 2 | Material | Bricks/Blocks | Not on List | 48 | Number | NULL | 0 | Blocks and Bricks | 2019-03-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14661-001025 | 14661 | 2019-03-26 12:13 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14556-001025 | 14556 | 2019-03-22 16:11 | Section 3 | Material | Not on List | Not on List | 1 | ea | 545.14 | 545.14 | Small Tools (Consumables) | 2019-03-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14556-001025 | 14556 | 2019-03-22 16:11 | Section 3 | Material | Not on List | Not on List | 1 | ea | 248.9 | 248.9 | PPE | 2019-03-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14664-001025 | 14664 | 2019-03-26 12:54 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-14588-001025 | 14588 | 2019-03-25 10:17 | Section 4 | Material | Not on List | Not on List | 30 | Each | 78.44 | 2353.2 | Plastic Drainage | 2019-03-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14588-001025 | 14588 | 2019-03-25 10:17 | Section 4 | Material | Not on List | Not on List | 60 | Each | 4.76 | 285.6 | Plastic Drainage | 2019-03-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5033-0018 | 5033 | 2018-08-14 09:31 | Section 4 | Material | Misc | Kassel Bus Stop Kerb 435*314-Hb Transitn (Priced Each Not Mtr) | 2 | Each | 126.82 | 1645.43 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5506-00494 | 5506 | 2018-08-22 13:55 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Not Sure | 2018-08-27 | Gate C - 1339699 - BN08 via Logistics Yard Access | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14670-001025 | 14670 | 2019-03-26 13:30 | Section 2 | Material | Not on List | Not on List | 5 | rolls | NULL | 0 | Concrete Accessories | 2019-03-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14600-001025 | 14600 | 2019-03-25 13:23 | Section 5 | Material | Concrete Drainage | Not on List | 6 | THOUSAND | 66.02 | 396.12 | Concrete Drainage | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14600-001025 | 14600 | 2019-03-25 13:23 | Section 5 | Material | Concrete Drainage | Not on List | 50 | No | 11.15 | 557.5 | Concrete Drainage | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14600-001025 | 14600 | 2019-03-25 13:23 | Section 5 | Material | Concrete Drainage | Not on List | 60 | No | 2.5 | 150 | Concrete Drainage | 2019-03-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13189-001025 | 13189 | 2019-02-27 15:52 | Core | Material | Not on List | Not on List | 1 | Each | 377.5 | 378 | Miscellaneous | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5815-00500 | 5815 | 2018-08-30 14:03 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 500 | No | 0.85 | 425 | Builders Merchants (General) | 2018-09-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14648-001025 | 14648 | 2019-03-26 10:31 | Section 3 | Material | Not on List | Not on List | 8 | metres | 55.21 | 441.68 | Electrical | 2019-03-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14648-001025 | 14648 | 2019-03-26 10:31 | Section 3 | Material | Concrete Drainage | Not on List | 100 | tubes | 4.97 | 497 | Concrete Accessories | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5815-00500 | 5815 | 2018-08-30 14:03 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 500 | No | 2.75 | 1375 | Builders Merchants (General) | 2018-09-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14527-001025 | 14527 | 2019-03-21 16:10 | Section 4 | Material | Not on List | Not on List | 300 | Each | 4.97 | 1491 | Builders Merchants (General) | 2019-03-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14527-001025 | 14527 | 2019-03-21 16:10 | Section 4 | Material | Not on List | Not on List | 1 | pack | 17.57 | 17.57 | Builders Merchants (General) | 2019-03-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4C - Structures (Culverts) 4C | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14527-001025 | 14527 | 2019-03-21 16:10 | Section 4 | Material | Not on List | Not on List | 2 | Each | 97.14 | 194.28 | Builders Merchants (General) | 2019-03-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13827-001025 | 13827 | 2019-03-12 08:54 | Section 3 | Material | Not on List | Not on List | 1 | number | 46589 | 46589 | Miscellaneous | 2019-03-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14181-001025 | 14181 | 2019-03-18 11:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 15000 | 15000 | Miscellaneous | 2019-03-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13762-001025 | 13762 | 2019-03-11 11:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 349.18 | 349.18 | Miscellaneous | 2019-03-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13835-001025 | 13835 | 2019-03-12 09:51 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1209.4 | 1209.4 | Miscellaneous | 2019-03-13 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14194-001025 | 14194 | 2019-03-18 13:51 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 42.5 | 42.5 | Miscellaneous | 2019-03-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11916-001025 | 11916 | 2019-02-05 09:10 | Section 2 | Material | Not on List | Not on List | 1 | each | 3829.38 | 3829.38 | Not Sure | 2019-02-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-14615-001025 | 14615 | 2019-03-25 15:44 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 3266.08 | 3266.08 | Miscellaneous | 2018-08-22 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14751-001025 | 14751 | 2019-03-27 10:13 | Core | Material | Not on List | Not on List | 1 | NULL | 48424.16 | 48424 | Miscellaneous | 2019-03-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-14757-001025 | 14757 | 2019-03-27 11:25 | Core | Material | Not on List | Not on List | 1 | number | 15.84 | 16 | Surveying Consumables | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14443-001025 | 14443 | 2019-03-21 09:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4495 | 4495 | Miscellaneous | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14443-001025 | 14443 | 2019-03-21 09:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4996 | 4996 | Miscellaneous | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14443-001025 | 14443 | 2019-03-21 09:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1375 | 1375 | Miscellaneous | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14759-001025 | 14759 | 2019-03-27 11:31 | Section 2 | Material | Not on List | Not on List | 150 | number | NULL | 0 | Miscellaneous | 2019-03-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14759-001025 | 14759 | 2019-03-27 11:31 | Section 2 | Material | Not on List | Not on List | 250 | number | NULL | 0 | Miscellaneous | 2019-03-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14759-001025 | 14759 | 2019-03-27 11:31 | Section 2 | Material | Not on List | Not on List | 250 | number | NULL | 0 | Miscellaneous | 2019-03-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12283-001025 | 12283 | 2019-02-12 08:21 | Section 2 | Material | Not on List | Not on List | 12 | Number | NULL | 0 | Fixings and Fasteners | 2019-02-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14679-001025 | 14679 | 2019-03-26 15:11 | Section 3 | Material | PPE, Small Tools and Consumables | Netting Debris Green 50 Metre X 2 Metre Spartan Pro (630025) | 2 | Each | 29.98 | 59.96 | Builders Merchants (General) | 2019-03-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN15 - Connington Road Overbridge | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14716-001025 | 14716 | 2019-03-27 06:55 | Section 5 | Material | NULL | All-In Ballast Bulk Bag (996226) | 2 | Each | 33.5 | 67 | Blocks and Bricks | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14716-001025 | 14716 | 2019-03-27 06:55 | Section 5 | Material | NULL | OP Cement; 25kg bag (767201) | 10 | Each | 2.97 | 29.7 | Blocks and Bricks | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14539-001025 | 14539 | 2019-03-22 12:25 | Section 4 | Material | Not on List | Not on List | 1 | Each | 42588 | 42588 | Miscellaneous | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5198-00503 | 5198 | 2018-08-16 08:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 352 | 352 | PPE | 2018-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14786-001025 | 14786 | 2019-03-27 16:06 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196 | Aggregate | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14786-001025 | 14786 | 2019-03-27 16:06 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142 | Aggregate | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14786-001025 | 14786 | 2019-03-27 16:06 | Section 2 | Material | Twinwall | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14786-001025 | 14786 | 2019-03-27 16:06 | Section 2 | Material | Twinwall | Polypipe 150mm x 25m Ridgiflex (877588) | 6 | Each | 145 | 870 | Plastic Drainage | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5198-00503 | 5198 | 2018-08-16 08:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2018-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14798-001025 | 14798 | 2019-03-27 16:27 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Concrete Accessories | 2019-03-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14464-001025 | 14464 | 2019-03-21 14:57 | Section 4 | Material | NULL | NULL | 1 | Each | 449.99 | 449.99 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-14464-001025 | 14464 | 2019-03-21 14:57 | Section 4 | Material | NULL | NULL | 1 | Each | 255.74 | 255.74 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-14464-001025 | 14464 | 2019-03-21 14:57 | Section 4 | Material | NULL | NULL | 1 | Each | 449.99 | 449.99 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-14464-001025 | 14464 | 2019-03-21 14:57 | Section 4 | Material | NULL | NULL | 1 | Each | 115 | 115 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-11681-001025 | 11681 | 2019-01-30 16:29 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 600 | 600 | Miscellaneous | 2019-02-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5198-00503 | 5198 | 2018-08-16 08:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 532.55 | 532.55 | Small Tools (Consumables) | 2018-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14842-001025 | 14842 | 2019-03-28 09:44 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-01 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5775-00466 | 5775 | 2018-08-29 18:50 | Section 3 | Material | Not on List | Not on List | 1 | EA | 524.75 | 524.75 | PPE | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14843-001025 | 14843 | 2019-03-28 09:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10033-001025 | 10033 | 2018-12-06 10:11 | Section 4 | Material | NULL | Not on List | 2 | bag | 43.57 | 87.14 | Builders Merchants (General) | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10056-001025 | 10056 | 2018-12-06 13:53 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10056-001025 | 10056 | 2018-12-06 13:53 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10057-001025 | 10057 | 2018-12-06 13:46 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 23.49 | 47 | Small Tools (Consumables) | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 11.94 | 11.94 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 11.94 | 11.94 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 7.68 | 7.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 7.68 | 7.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 16 | Each | 5.69 | 91.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 48 | Each | 4.98 | 239.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | NULL | Not on List | 40 | Each | 2.18 | 87.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10057-001025 | 10057 | 2018-12-06 13:46 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 23.49 | 46.98 | Small Tools (Consumables) | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | Each | 110.92 | 110.92 | Miscellaneous | 2018-12-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | Each | 176.09 | 176.09 | Miscellaneous | 2018-12-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 2 | Each | 221.85 | 443.7 | Miscellaneous | 2018-12-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | Each | 221.85 | 221.85 | Miscellaneous | 2018-12-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10059-001025 | 10059 | 2018-12-06 15:12 | Section 4 | Material | Not on List | Not on List | 1 | Each | 221.85 | 221.85 | Miscellaneous | 2018-12-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9994-001025 | 9994 | 2018-12-05 13:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 600 | 600 | Professional Services | 2018-12-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9992-001025 | 9992 | 2018-12-05 12:46 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 4233.75 | 4233.75 | PPE | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10014-001025 | 10014 | 2018-12-05 17:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 25 | Boxes | 27.85 | 696.25 | PPE | 2018-12-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 10 | no. | 285 | 2850 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 100 | no. | 11.35 | 1135 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 1 | box (6 bags) | 83.7 | 83.7 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10032-001025 | 10032 | 2018-12-06 09:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 278.6 | 278.6 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10056-001025 | 10056 | 2018-12-06 13:53 | Section 4 | Material | Not on List | Not on List | 21640.23 | Each | 1 | 21640.23 | Concrete Drainage | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10056-001025 | 10056 | 2018-12-06 13:53 | Section 4 | Material | Not on List | Not on List | 21640.23 | Each | 1 | 21640.23 | Concrete Drainage | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10106-001025 | 10106 | 2018-12-07 13:29 | Section 3 | Material | Not on List | Not on List | 30 | m | NULL | 0 | Concrete Drainage | 2018-12-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10067-001025 | 10067 | 2018-12-06 16:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 187.63 | 187.63 | Miscellaneous | 2018-12-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10108-001025 | 10108 | 2018-12-07 13:50 | Section 4 | Material | Not on List | Not on List | 2 | number | NULL | 0 | Not Sure | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10108-001025 | 10108 | 2018-12-07 13:50 | Section 4 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Not Sure | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10114-001025 | 10114 | 2018-12-07 15:16 | Section 3 | Material | Aggregate | Type 1 | 1300 | Tonnes | 16 | 20800 | Aggregate | 2018-12-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 606 - Import | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10108-001025 | 10108 | 2018-12-07 13:50 | Section 4 | Material | Not on List | Not on List | 2 | number | 9.75 | 19.5 | Plastic Drainage | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10108-001025 | 10108 | 2018-12-07 13:50 | Section 4 | Material | Not on List | Not on List | 1 | number | 336.95 | 336.95 | Plastic Drainage | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10161-001025 | 10161 | 2018-12-10 10:18 | Section 3 | Material | Not on List | Not on List | 1 | EA | 50 | 50 | Miscellaneous | 2018-12-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 50 | meters | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10161-001025 | 10161 | 2018-12-10 10:18 | Section 3 | Material | Not on List | Not on List | 1 | EA | 23.5 | 24 | Miscellaneous | 2018-12-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10097-001025 | 10097 | 2018-12-07 11:27 | Section 4 | Material | Not on List | Not on List | 15 | Each | 290 | 4350 | Plastic Drainage | 2018-12-19 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9807-001025 | 9807 | 2018-11-30 08:29 | Section 4 | Material | Concrete Drainage | Not on List | 150 | Each | 23 | 3450 | Concrete Drainage | 2018-12-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10170-001025 | 10170 | 2018-12-10 11:19 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1 | 1 | Reinforcement | 2019-01-07 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10096-001025 | 10096 | 2018-12-07 11:05 | Section 4 | Material | Not on List | Not on List | 50 | Each | 16.91 | 845.5 | Builders Merchants (General) | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10096-001025 | 10096 | 2018-12-07 11:05 | Section 4 | Material | Not on List | Not on List | 100 | Each | 13.9 | 1390 | Builders Merchants (General) | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10096-001025 | 10096 | 2018-12-07 11:05 | Section 4 | Material | Not on List | Not on List | 20 | Each | 9.44 | 188.8 | Builders Merchants (General) | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10096-001025 | 10096 | 2018-12-07 11:05 | Section 4 | Material | Not on List | Not on List | 50 | Each | 3.46 | 173 | Builders Merchants (General) | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10123-001025 | 10123 | 2018-12-07 16:45 | Section 3 | Material | Not on List | Not on List | 1 | ea | 315.22 | 315.22 | Small Tools (Consumables) | 2018-12-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10170-001025 | 10170 | 2018-12-10 11:19 | Section 4 | Material | Not on List | Not on List | 2.611 | Tonne | 538 | 1404.72 | Rebar and Mesh | 2019-01-07 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | CL4C - Structures (Culverts) 4C | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10205-001025 | 10205 | 2018-12-11 08:02 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | no | NULL | 0 | Office Supplies | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10210-001025 | 10210 | 2018-12-11 08:32 | Section 4 | Material | Aggregate | Not on List | 120 | t | NULL | 0 | Aggregate | 2018-12-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10106-001025 | 10106 | 2018-12-07 13:29 | Section 3 | Material | Not on List | Not on List | 30 | m | 26.58 | 797.4 | Concrete Drainage | 2018-12-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9991-001025 | 9991 | 2018-12-05 12:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1809 | 1809 | Timber Products | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10106-001025 | 10106 | 2018-12-07 13:29 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 26.58 | 265.8 | Concrete Drainage | 2018-12-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10203-001025 | 10203 | 2018-12-11 07:29 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1392.54 | 1392.54 | Miscellaneous | 2018-12-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 772.44 | 772.44 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 951.6 | 951.6 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 457.2 | 457.2 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1524 | 1524 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10224-001025 | 10224 | 2018-12-11 11:19 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2018-12-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10224-001025 | 10224 | 2018-12-11 11:19 | Section 3 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Not Sure | 2018-12-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10205-001025 | 10205 | 2018-12-11 08:02 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | no | NULL | 0 | Office Supplies | 2018-12-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 16 | ea | 1 | 16 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 6 | ea | 1 | 6 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 8 | ea | 1 | 8 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10243-001025 | 10243 | 2018-12-11 15:19 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 167.85 | 168 | Small Tools (Consumables) | 2018-12-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10181-001025 | 10181 | 2018-12-10 15:10 | Section 4 | Material | Not on List | Not on List | 6 | Each | 47.48 | 284.88 | Not Sure | 2018-12-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10181-001025 | 10181 | 2018-12-10 15:10 | Section 4 | Material | Not on List | Not on List | 50 | Each | 21 | 1050 | Not Sure | 2018-12-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10181-001025 | 10181 | 2018-12-10 15:10 | Section 4 | Material | Not on List | Not on List | 50 | Foot & 2 Clips | 6.5 | 325 | Not Sure | 2018-12-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10181-001025 | 10181 | 2018-12-10 15:10 | Section 4 | Material | Not on List | Not on List | 50 | Each | 20.5 | 1025 | Not Sure | 2018-12-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5362-00247 | 5362 | 2018-08-20 14:53 | Section 3 | Material | Not on List | Not on List | 10500 | NULL | NULL | 0 | Miscellaneous | 2018-08-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 16 | ea | 35.46 | 567.36 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 6 | ea | 50.59 | 303.54 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10242-001025 | 10242 | 2018-12-11 15:15 | Section 4 | Material | Not on List | Not on List | 8 | ea | 77.79 | 622.32 | Plastic Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9540-001025 | 9540 | 2018-11-23 12:20 | Section 4 | Material | Not on List | Not on List | 1 | Each | 179.5 | 179.5 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9933-001025 | 9933 | 2018-12-04 08:30 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 15 | Each | 47.04 | 705.6 | Concrete Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9933-001025 | 9933 | 2018-12-04 08:30 | Section 4 | Material | Concrete Drainage | Not on List | 15 | Each | 67.9 | 1018.5 | Concrete Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9933-001025 | 9933 | 2018-12-04 08:30 | Section 4 | Material | NULL | NULL | 1 | Each | 200 | 200 | Concrete Drainage | 2018-12-13 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9997-001025 | 9997 | 2018-12-05 13:55 | Section 4 | Material | Not on List | Not on List | 1 | Annual Subsistence Charge | 1580 | 1580 | Professional Services | 2018-12-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | Each | 120.62 | 6031 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 55 | Each | 17.45 | 959.75 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 110 | Each | 9.04 | 994.4 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 140 | Each | 34.82 | 4874.8 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 160 | Each | 6.54 | 1046.4 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 320 | Each | 2.75 | 880 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | Each | 23.14 | 1157 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 55 | Each | 3.38 | 185.9 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 110 | Each | 1.86 | 204.6 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 40 | Each | 10.5 | 420 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | Each | 1.84 | 92 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.85 | 85 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 40 | Each | 26.94 | 1077.6 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 144 | Each | 0.85 | 122.4 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 12 | Each | 84.41 | 1012.92 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 44 | Each | 9.04 | 397.76 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 35 | Each | 144.91 | 5071.85 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | NULL | Not on List | 70 | Each | 2.75 | 192.5 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | NULL | Not on List | 115 | Each | 1.86 | 213.9 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | NULL | Not on List | 10 | Each | 174.42 | 1744.2 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | NULL | Not on List | 35 | Each | 27.62 | 966.7 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 5 | Each | 67.9 | 339.5 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 2 | Each | 50.92 | 101.84 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 2 | Each | 43.16 | 86.32 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 3 | Each | 35.52 | 106.56 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | Each | 47.04 | 376.32 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 30 | Each | 22 | 660 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | Each | 74.3 | 594.4 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | Each | 121.25 | 970 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | Each | 90.94 | 727.52 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 5 | Each | 80.51 | 402.55 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | Each | 102.82 | 822.56 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9833-001025 | 9833 | 2018-11-30 14:00 | Section 3 | Material | Signage | Not on List | 80 | number | 7.35 | 588 | Miscellaneous | 2018-12-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9833-001025 | 9833 | 2018-11-30 14:00 | Section 3 | Material | Signage | Not on List | 80 | number | 12.84 | 1027.2 | Miscellaneous | 2018-12-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10265-001025 | 10265 | 2018-12-12 09:02 | Section 3 | Material | Bagged | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10226-001025 | 10226 | 2018-12-11 11:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 56 | Each | 2.9 | 162.4 | Miscellaneous | 2018-12-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10226-001025 | 10226 | 2018-12-11 11:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3000 | Each | 0.37 | 1110 | Miscellaneous | 2018-12-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10274-001025 | 10274 | 2018-12-12 11:26 | Section 3 | Material | Kerbs | Not on List | 270 | No | NULL | 0 | Builders Merchants (General) | 2019-01-04 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10274-001025 | 10274 | 2018-12-12 11:26 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 540 | Each | 1.45 | 783 | Builders Merchants (General) | 2019-01-04 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9633-001025 | 9633 | 2018-11-26 16:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 288 | Each | 6.29 | 1811.52 | Miscellaneous | 2018-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9738-001025 | 9738 | 2018-11-28 16:40 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 38.82 | 38.82 | PPE | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10154-001025 | 10154 | 2018-12-10 08:53 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | 20ltr Drum | 55.4 | 277 | Miscellaneous | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28980 | 28980 | 2020-02-07 12:22 | Test Section | Material Requisition | Aggregate | 6F2 | 345 | Tonnes | 13 | 4485 | Blocks and Bricks | 2020-02-29 | Test Location | Test Section | Test Section | Operational Approval | NULL | NULL | Chris Henry
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 150 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 50 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18603-001025 | 18603 | 2019-06-05 14:14 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18599-001025 | 18599 | 2019-06-05 13:55 | Section 4 | Material | Not on List | Not on List | 1 | Each | 280 | 280 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18753-001025 | 18753 | 2019-06-07 11:22 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18120-001025 | 18120 | 2019-05-28 13:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 445.84 | 445.84 | Miscellaneous | 2019-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17972-001025 | 17972 | 2019-05-23 13:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1000 | 1000 | Miscellaneous | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17959-001025 | 17959 | 2019-05-23 11:22 | Section 4 | Material | Not on List | Not on List | 1 | Each | 171.2 | 171.2 | Fuel | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18713-001025 | 18713 | 2019-06-07 07:49 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18783-001025 | 18783 | 2019-06-07 14:44 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 601 - Topsoil Strip, Store, Dispose | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-18750-001025 | 18750 | 2019-06-07 11:12 | Section 3 | Material | Not on List | Not on List | 500000 | Litres | 0.1 | 50000 | Gas Oil | 2019-06-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 17 | 51 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 12 | 36 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 12 | 36 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 17 | 17 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 215 | 215 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18520-001025 | 18520 | 2019-06-04 12:34 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 20 | 20 | Electrical | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18806-001025 | 18806 | 2019-06-10 07:29 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18820-001025 | 18820 | 2019-06-10 08:42 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18820-001025 | 18820 | 2019-06-10 08:42 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18820-001025 | 18820 | 2019-06-10 08:42 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18824-001025 | 18824 | 2019-06-10 08:58 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18780-001025 | 18780 | 2019-06-07 14:37 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18646-001025 | 18646 | 2019-06-06 09:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18046-001025 | 18046 | 2019-05-24 11:26 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18749-001025 | 18749 | 2019-06-07 10:31 | Section 4 | Material | Not on List | Not on List | 512 | Each | 8.25 | 4224 | Concrete Drainage | 2019-06-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18749-001025 | 18749 | 2019-06-07 10:31 | Section 4 | Material | NULL | Not on List | 80 | eACH | 8.25 | 660 | Concrete Drainage | 2019-06-13 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18633-001025 | 18633 | 2019-06-06 07:05 | Section 2 | Material | NULL | Concrete Kerbs Splayed 45deg 125x255 (898227) | 500 | Each | 4.59 | 2295 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-11 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18633-001025 | 18633 | 2019-06-06 07:05 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 3 | Each | 11.94 | 35.82 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-11 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18633-001025 | 18633 | 2019-06-06 07:05 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 3 | Each | 11.94 | 35.82 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-11 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18633-001025 | 18633 | 2019-06-06 07:05 | Section 2 | Material | NULL | Not on List | 20 | no. | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-11 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18633-001025 | 18633 | 2019-06-06 07:05 | Section 2 | Material | NULL | Not on List | 20 | no. | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-11 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18690-001025 | 18690 | 2019-06-06 15:38 | Section 4 | Material | Not on List | Not on List | 8 | Each | 15.52 | 124.16 | Concrete Accessories | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18690-001025 | 18690 | 2019-06-06 15:38 | Section 4 | Material | NULL | Not on List | 1 | Each | 30 | 30 | Concrete Accessories | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18798-001025 | 18798 | 2019-06-07 16:35 | Section 3 | Material | Not on List | Not on List | 20 | No | 21.6 | 432 | Builders Merchants (General) | 2019-06-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18823-001025 | 18823 | 2019-06-10 08:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Small Tools (Consumables) | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18863-001025 | 18863 | 2019-06-10 12:08 | Section 3 | Material | PPE, Small Tools and Consumables | Cones Blue 750mm - No Sleeve Csp (204013) | 120 | Each | 5.3 | 636 | Miscellaneous | 2019-06-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18863-001025 | 18863 | 2019-06-10 12:08 | Section 3 | Material | PPE, Small Tools and Consumables | Sleeve - White C/W Overhead Structures 750mm Csp (204017) | 120 | Each | 2.18 | 262 | Miscellaneous | 2019-06-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18863-001025 | 18863 | 2019-06-10 12:08 | Section 3 | Material | Not on List | Not on List | 10 | Each | 14.4 | 144 | Miscellaneous | 2019-06-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18650-001025 | 18650 | 2019-06-06 09:58 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 40 | Each | 34.82 | 1392.8 | Plastic Drainage | 2019-06-11 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18650-001025 | 18650 | 2019-06-06 09:58 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 12 | Each | 67.9 | 814.8 | Concrete Drainage | 2019-06-11 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18650-001025 | 18650 | 2019-06-06 09:58 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 4 | Each | 43.16 | 172.64 | Concrete Drainage | 2019-06-11 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18650-001025 | 18650 | 2019-06-06 09:58 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 7 | Each | 35.52 | 248.64 | Concrete Drainage | 2019-06-11 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18650-001025 | 18650 | 2019-06-06 09:58 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 47.04 | 470.4 | Concrete Drainage | 2019-06-11 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18846-001025 | 18846 | 2019-06-10 12:07 | Section 2 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-06-13 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18653-001025 | 18653 | 2019-06-06 10:15 | Section 1 | Material | NULL | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-06-12 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-6639-00750 | 6639 | 2018-09-18 09:16 | Section 3 | Material | Plastic Drainage | Not on List | 39 | metres | NULL | 0 | Concrete Accessories | 2018-09-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5218 | 5218 | 2018-08-16 11:54 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-08-29 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18557-001025 | 18557 | 2019-06-04 17:04 | Section 4 | Material | Not on List | Not on List | 4 | Each | 414.32 | 1657.28 | Fixings and Fasteners | 2019-06-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18557-001025 | 18557 | 2019-06-04 17:04 | Section 4 | Material | Not on List | Not on List | 32 | Each | 1.55 | 49.6 | Fixings and Fasteners | 2019-06-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18557-001025 | 18557 | 2019-06-04 17:04 | Section 4 | Material | NULL | Not on List | 1 | Each | 80 | 80 | Fixings and Fasteners | 2019-06-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18412-001025 | 18412 | 2019-06-03 09:18 | Core | Material | Not on List | Not on List | 1 | Ea | 1040.6 | 1040.6 | Miscellaneous | 2019-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5129-00498 | 5129 | 2018-08-15 10:17 | Section 3 | Material | Not on List | Not on List | 4 | 10 Pack | 57.91 | 231.64 | Miscellaneous | 2018-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153c - Temporary Works - Fencing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18420-001025 | 18420 | 2019-06-03 10:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 30.56 | 611.2 | Small Tools (Consumables) | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18300-001025 | 18300 | 2019-05-30 17:05 | Section 3 | Material | Not on List | Not on List | 10 | no | 1004.73 | 10047.3 | Miscellaneous | 2019-06-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18300-001025 | 18300 | 2019-05-30 17:05 | Section 3 | Material | Not on List | Not on List | 1 | no | 367.4 | 367.4 | Miscellaneous | 2019-06-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18531-001025 | 18531 | 2019-06-04 14:24 | Section 2 | Material | Not on List | Not on List | 250000 | litres | 1 | 250000 | Fuel | 2019-06-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18787-001025 | 18787 | 2019-06-07 15:27 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18814-001025 | 18814 | 2019-06-10 08:22 | Section 4 | Material | Not on List | Not on List | 20 | tonne | 33.55 | 671 | Aggregate | 2019-06-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18812-001025 | 18812 | 2019-06-10 08:13 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 49.5 | 297 | Plastic Drainage | 2019-06-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18817-001025 | 18817 | 2019-06-10 08:26 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 3805 | 3805 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18832-001025 | 18832 | 2019-06-10 11:01 | Section 4 | Material | Concrete Drainage | Not on List | 1 | NULL | 1105.39 | 1105.39 | Concrete Drainage | 2019-06-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18771-001025 | 18771 | 2019-06-07 13:57 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Concrete Drainage | 2019-06-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18712-001025 | 18712 | 2019-06-07 07:46 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Concrete Drainage | 2019-06-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18686-001025 | 18686 | 2019-06-06 14:33 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Ductile Drainage | 2019-06-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18645-001025 | 18645 | 2019-06-06 09:21 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Ductile Drainage | 2019-06-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17905-001025 | 17905 | 2019-05-22 14:22 | Section 4 | Material | Waste Management | Not on List | 1 | Each | 825 | 825 | Waste (General) | 2019-05-24 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18901-001025 | 18901 | 2019-06-11 11:58 | Core | Material | Not on List | Not on List | 1 | each | 850 | 850 | Training | 2019-06-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18907-001025 | 18907 | 2019-06-11 13:38 | Section 4 | Material | Not on List | Not on List | 1 | Day | 550 | 550 | Surveying Consumables | 2019-06-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-18911-001025 | 18911 | 2019-06-11 13:27 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Concrete Accessories | 2019-06-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18912-001025 | 18912 | 2019-06-11 14:33 | Section 3 | Material | Not on List | Not on List | 1 | each | 5077.75 | 5078 | Miscellaneous | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18915-001025 | 18915 | 2019-06-11 14:40 | Section 5 | Material | Not on List | Not on List | 1 | each | 525.3 | 525 | Miscellaneous | 2019-06-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18922-001025 | 18922 | 2019-06-11 09:29 | Core | Material | Not on List | Not on List | 1 | NULL | 105.33 | 105 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Finance Approval | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Can Fuel 5ltr Heavy Duty Green Plastic Long Spout Unleaded (706686) | 5 | Each | 5.82 | 29 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Can Fuel 5ltr Heavy Duty Black Plastic Long Spout For Diesel (706684) | 5 | Each | 5.85 | 29 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Tape Gaffa Waterproof Cloth Grey 50mm X 50 Mtr Ref 3160 (964670) | 40 | Each | 1.91 | 76 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Paint Roller And Tray Set 9" Rskit1 (704256) | 20 | Each | 3.42 | 68 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Bucket Galvanised 2 1/2gall/11.42ltr 10"/30cm Dia Spartan (506016) | 20 | Each | 9 | 180 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Hammer Club C/W Fibreglass Handle Spartan Pro 1.1kg(2.5lb) (724107) | 15 | Each | 8.98 | 135 | Small Tools (Consumables) | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18924-001025 | 18924 | 2019-06-11 15:07 | Core | Material | PPE, Small Tools and Consumables | Not on List | 7 | Each | NULL | 0 | PPE | 2019-06-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18678-001025 | 18678 | 2019-06-06 13:46 | Section 4 | Material | NULL | NULL | 7 | 1kg Bag | 2.8 | 19.6 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18933-001025 | 18933 | 2019-06-11 16:58 | Core | Material | Combined Drainage | Not on List | 1 | each | 10665 | 10665 | Flow Control | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Buyers
MREQ-18934-001025 | 18934 | 2019-06-11 16:18 | Core | Material | Not on List | Not on List | 1 | NULL | 317.25 | 317 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18935-001025 | 18935 | 2019-06-11 17:25 | Core | Material | Not on List | Not on List | 1 | NULL | 37.85 | 38 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18935-001025 | 18935 | 2019-06-11 17:25 | Core | Material | Not on List | Not on List | 1 | NULL | 31.65 | 32 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18660-001025 | 18660 | 2019-06-06 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Pack 3 | 6.5 | 26 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18660-001025 | 18660 | 2019-06-06 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | 0.54 | 54 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18660-001025 | 18660 | 2019-06-06 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pairs | 0.52 | 5.2 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18660-001025 | 18660 | 2019-06-06 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 6.5 | 13 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18660-001025 | 18660 | 2019-06-06 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 22.25 | 44.5 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18953-001025 | 18953 | 2019-06-12 08:53 | Section 2 | Material | Not on List | Not on List | 1 | each | 10665 | 10665 | Professional Services | 2019-06-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 501 - Drains | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-18236-001025 | 18236 | 2019-05-30 07:25 | Section 3 | Material | Not on List | Not on List | 70 | NULL | NULL | 0 | Miscellaneous | 2019-06-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18831-001025 | 18831 | 2019-06-10 10:45 | Section 4 | Material | Not on List | Not on List | 10 | 1t Bag | 50.05 | 500.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18978-001025 | 18978 | 2019-06-12 12:30 | Section 1 | Material | Not on List | Not on List | 1 | each | 120.56 | 121 | Miscellaneous | 2019-06-12 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18979-001025 | 18979 | 2019-06-12 12:32 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18993-001025 | 18993 | 2019-06-12 14:51 | Core | Material | Not on List | Not on List | 1 | Each | 850 | 850 | Training | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18994-001025 | 18994 | 2019-06-12 14:54 | Core | Material | Not on List | Not on List | 1 | each | 850 | 850 | Training | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18896-001025 | 18896 | 2019-06-11 11:36 | Section 4 | Material | NULL | Not on List | 3 | Rolles | 72.76 | 218.28 | Miscellaneous | 2019-06-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18894-001025 | 18894 | 2019-06-11 11:15 | Section 4 | Material | NULL | Not on List | 20 | Roll | 6.4 | 128 | Miscellaneous | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18999-001025 | 18999 | 2019-06-12 13:50 | Section 6 | Material | Not on List | Not on List | 1 | number | 995 | 995 | Training | 2019-06-19 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-18969-001025 | 18969 | 2019-06-12 11:01 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18969-001025 | 18969 | 2019-06-12 11:01 | Section 4 | Material | NULL | Not on List | 1 | Each | 15 | 15 | Plastic Drainage | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18897-001025 | 18897 | 2019-06-11 11:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 150 | Each | 1.31 | 196.5 | Small Tools (Consumables) | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18952-001025 | 18952 | 2019-06-12 08:52 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 3723.63 | 3723.63 | Small Tools (Consumables) | 2019-06-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18864-001025 | 18864 | 2019-06-10 15:23 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 3.78 | 7.56 | Rebar and Mesh | 2019-06-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 355 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 220 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 9 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 2 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 4 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 65 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 2 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6824-00751 | 6824 | 2018-09-21 07:52 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 5 | no. | NULL | 0 | Concrete Drainage | 2018-09-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN10 - A1198 Ermine Street Overbridge | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 16 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 1 | no | 95 | 95 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 65 | tonnes | 538 | 34970 | NULL | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 150 | tonnes | 538 | 80700 | NULL | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 35 | tonnes | 538 | 18830 | NULL | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 50 | tonnes | 538 | 26900 | NULL | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | NULL | Not on List | 750 | Each | 2 | 1500 | NULL | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12300-001025 | 12300 | 2019-02-12 11:12 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 88.88 | 88.88 | Small Tools (Consumables) | 2019-02-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12294-001025 | 12294 | 2019-02-12 09:49 | Section 3 | Material | Not on List | Not on List | 80 | 25M Length | 15.5 | 1240 | Miscellaneous | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11649-001025 | 11649 | 2019-01-30 06:51 | Section 4 | Material | Not on List | Not on List | 1 | each | 581.82 | 581.82 | Miscellaneous | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12224-001025 | 12224 | 2019-02-11 10:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 35.6 | 35.6 | Small Tools (Consumables) | 2019-02-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12287-001025 | 12287 | 2019-02-12 08:43 | Section 2 | Material | Not on List | Not on List | 8 | no | 21 | 168 | Concrete Accessories | 2019-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12287-001025 | 12287 | 2019-02-12 08:43 | Section 2 | Material | Not on List | Not on List | 4 | no | 13.75 | 55 | Concrete Accessories | 2019-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12320-001025 | 12320 | 2019-02-12 15:18 | Section 2 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Geotextiles | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5576-00394 | 5576 | 2018-08-23 12:11 | Section 3 | Material | Not on List | Not on List | 50 | Ea | 5.98 | 299 | Miscellaneous | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12330-001025 | 12330 | 2019-02-12 16:13 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 12 | each | 72.5 | 870 | Miscellaneous | 2019-02-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12375-001025 | 12375 | 2019-02-13 11:11 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12379-001025 | 12379 | 2019-02-13 11:33 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12389-001025 | 12389 | 2019-02-13 13:16 | Section 6 | Material | Not on List | Not on List | 1 | number | 1152.96 | 1153 | Miscellaneous | 2019-02-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1201 - Traffic Signs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-12391-001025 | 12391 | 2019-02-13 13:31 | Core | Material | Not on List | Not on List | 1 | unit | 1593.6 | 1594 | Miscellaneous | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-5576-00394 | 5576 | 2018-08-23 12:11 | Section 3 | Material | Not on List | Not on List | 65 | ea | 5.98 | 389 | Miscellaneous | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 200 | EA | 6.9 | 1380 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 150 | EA | 2.18 | 327 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 100 | EA | 2.78 | 278 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 20 | EA | 285 | 5700 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12393-001025 | 12393 | 2019-02-13 14:03 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-02-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-12394-001025 | 12394 | 2019-02-13 13:57 | Section 2 | Material | Not on List | Not on List | 0.782 | t | NULL | 0 | Reinforcement | 2019-02-21 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12396-001025 | 12396 | 2019-02-13 14:46 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12094-001025 | 12094 | 2019-02-07 17:02 | Section 4 | Material | Not on List | Not on List | 10 | Roll | 3674 | 36740 | Concrete Drainage | 2019-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12094-001025 | 12094 | 2019-02-07 17:02 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1000 | 1000 | Concrete Drainage | 2019-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12094-001025 | 12094 | 2019-02-07 17:02 | Section 4 | Material | Not on List | Not on List | 1200 | Each | 2.55 | 3060 | Concrete Drainage | 2019-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12094-001025 | 12094 | 2019-02-07 17:02 | Section 4 | Material | Not on List | Not on List | 1 | Each | 610 | 610 | Concrete Drainage | 2019-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12094-001025 | 12094 | 2019-02-07 17:02 | Section 4 | Material | Not on List | Not on List | 6 | Each | 40.81 | 244.86 | Concrete Drainage | 2019-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12397-001025 | 12397 | 2019-02-13 15:13 | Section 2 | Material | Not on List | Not on List | 15 | NULL | NULL | 0 | Builders Merchants (General) | 2019-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN28 - Ellington Brook Bridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12402-001025 | 12402 | 2019-02-13 15:43 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Ductile Drainage | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12402-001025 | 12402 | 2019-02-13 15:43 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Ductile Drainage | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12404-001025 | 12404 | 2019-02-13 15:54 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12394-001025 | 12394 | 2019-02-13 13:57 | Section 2 | Material | Not on List | Not on List | 0.782 | t | 538 | 420.72 | NULL | 2019-02-21 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12440-001025 | 12440 | 2019-02-14 07:41 | Section 2 | Material | Bagged | Not on List | 4 | NULL | NULL | 0 | Concrete Accessories | 2019-02-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12440-001025 | 12440 | 2019-02-14 07:41 | Section 2 | Material | Bagged | Not on List | 2 | NULL | NULL | 0 | Concrete Accessories | 2019-02-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12453-001025 | 12453 | 2019-02-14 09:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1122 | 1122 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12453-001025 | 12453 | 2019-02-14 09:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 43 | 43 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12454-001025 | 12454 | 2019-02-14 09:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 456 | 456 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12455-001025 | 12455 | 2019-02-14 09:49 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 172.8 | 173 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12457-001025 | 12457 | 2019-02-14 10:02 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 20.4 | 20 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12457-001025 | 12457 | 2019-02-14 10:02 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 312 | 312 | Laboratory Equipment / Certification | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12460-001025 | 12460 | 2019-02-14 10:48 | Core | Material | Not on List | Not on List | 8 | NULL | 37 | 296 | Office Supplies | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12461-001025 | 12461 | 2019-02-14 09:01 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-11712-001025 | 11712 | 2019-01-31 11:53 | Section 4 | Material | Not on List | Not on List | 1 | Each | 350 | 350 | Miscellaneous | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11968-001025 | 11968 | 2019-02-05 17:47 | Section 4 | Material | Not on List | Not on List | 500 | LM | 4.38 | 2190 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12463-001025 | 12463 | 2019-02-14 09:31 | Section 3 | Material | Not on List | Not on List | 10 | no. | NULL | 0 | Concrete Drainage | 2019-02-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12467-001025 | 12467 | 2019-02-14 12:03 | Section 2 | Material | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2019-02-18 | Gate 4 - 1339619 - BN01 via Gate 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12470-001025 | 12470 | 2019-02-14 12:14 | Section 2 | Material | Not on List | Not on List | 2 | each | 12 | 24 | Laboratory Equipment / Certification | 2019-02-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12473-001025 | 12473 | 2019-02-14 12:37 | Section 3 | Material | Not on List | Not on List | 100 | No | NULL | 0 | Builders Merchants (General) | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12476-001025 | 12476 | 2019-02-14 12:34 | Section 4 | Material | Not on List | Not on List | 16 | ea | 1 | 16 | Concrete Drainage | 2019-02-19 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1103 - Linear Drainage Channel Systems | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-12482-001025 | 12482 | 2019-02-14 13:11 | Section 4 | Material | Not on List | Not on List | 4 | EA | 300 | 1200 | Concrete Accessories | 2019-02-19 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 200 | EA | 6.9 | 1380 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 150 | EA | 2.18 | 327 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 100 | EA | 2.78 | 278 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12387-001025 | 12387 | 2019-02-13 11:44 | Section 3 | Material | Not on List | Not on List | 20 | EA | 285 | 5700 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12365-001025 | 12365 | 2019-02-13 09:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1843.2 | 1843.2 | PPE | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-4957-003 | 4957 | 2018-08-10 17:48 | Section 4 | Material | Not on List | NULL | NULL | NULL | 372.83 | 0 | Rebar and Mesh | 2018-08-14 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | CL4B - Structures (Culverts) 4B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12463-001025 | 12463 | 2019-02-14 09:31 | Section 3 | Material | Not on List | Not on List | 10 | no. | 62 | 620 | Concrete Drainage | 2019-02-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12318-001025 | 12318 | 2019-02-12 15:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 588.94 | 588.94 | Small Tools (Consumables) | 2019-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12473-001025 | 12473 | 2019-02-14 12:37 | Section 3 | Material | Not on List | Not on List | 100 | No | 7.1 | 710 | Builders Merchants (General) | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12215-001025 | 12215 | 2019-02-11 09:20 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1649.94 | 1649.94 | Small Tools (Consumables) | 2019-02-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12467-001025 | 12467 | 2019-02-14 12:03 | Section 2 | Material | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2019-02-18 | Gate 4 - 1339619 - BN01 via Gate 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-11701-001025 | 11701 | 2019-01-31 09:11 | Section 4 | Material | Not on List | Not on List | 1 | Each | 670 | 670 | Miscellaneous | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12497-001025 | 12497 | 2019-02-14 15:08 | Section 4 | Material | Not on List | Not on List | 32 | number | NULL | 0 | Reinforcement | 2019-03-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12499-001025 | 12499 | 2019-02-14 14:50 | Core | Material | PPE, Small Tools and Consumables | Cream Pristine After Work Restore 1 Litre Cartridge (548142) | 1 | Each | 10.45 | 10 | Miscellaneous | 2019-02-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12499-001025 | 12499 | 2019-02-14 14:50 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 6 | 6 | Miscellaneous | 2019-02-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12232-001025 | 12232 | 2019-02-11 12:40 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.9 | 450 | Timber Products | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12232-001025 | 12232 | 2019-02-11 12:40 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 200 | Each | 0.3 | 60 | Timber Products | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12396-001025 | 12396 | 2019-02-13 14:46 | Section 3 | Material | Not on List | Not on List | 1 | ea | 1420 | 1420 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12464-001025 | 12464 | 2019-02-14 11:40 | Section 4 | Material | NULL | Not on List | 1 | ea | 23.95 | 23.95 | Plastic Drainage | 2019-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-12464-001025 | 12464 | 2019-02-14 11:40 | Section 4 | Material | NULL | Not on List | 1 | ea | 7.61 | 7.61 | Plastic Drainage | 2019-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-12464-001025 | 12464 | 2019-02-14 11:40 | Section 4 | Material | NULL | Not on List | 1 | ea | 25.82 | 25.82 | Plastic Drainage | 2019-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-11921-001025 | 11921 | 2019-02-05 09:38 | Section 4 | Material | Not on List | Not on List | 1 | each | 1767.13 | 1767.13 | Miscellaneous | 2019-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12520-001025 | 12520 | 2019-02-14 18:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11922-001025 | 11922 | 2019-02-05 09:50 | Section 3 | Material | Not on List | Not on List | 1 | each | 3760.63 | 3760.63 | Miscellaneous | 2019-02-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12101-001025 | 12101 | 2019-02-07 17:37 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 643.99 | 643.99 | PPE | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12330-001025 | 12330 | 2019-02-12 16:13 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 12 | each | 72.5 | 870 | Miscellaneous | 2019-02-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12485-001025 | 12485 | 2019-02-14 13:38 | Section 4 | Material | Not on List | Not on List | 5 | packs 50 | 24.63 | 123.15 | Builders Merchants (General) | 2019-02-18 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12485-001025 | 12485 | 2019-02-14 13:38 | Section 4 | Material | Not on List | Not on List | 5 | packs 50 | 21.96 | 109.8 | Builders Merchants (General) | 2019-02-18 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12344-001025 | 12344 | 2019-02-12 17:15 | Section 4 | Material | Not on List | Not on List | 200 | Each | 3.38 | 676 | Miscellaneous | 2019-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12502-001025 | 12502 | 2019-02-14 15:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | EACH | 28.8 | 864 | PPE | 2019-02-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12502-001025 | 12502 | 2019-02-14 15:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 19 | EACH | 28.8 | 547.2 | PPE | 2019-02-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12155-001025 | 12155 | 2019-02-08 12:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 12 | each | 112 | 1344 | Tanks and Interceptors | 2019-02-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12546-001025 | 12546 | 2019-02-15 09:26 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2019-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN32 - Brampton Equestrian Underpass | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12546-001025 | 12546 | 2019-02-15 09:26 | Section 2 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Miscellaneous | 2019-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN32 - Brampton Equestrian Underpass | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12470-001025 | 12470 | 2019-02-14 12:14 | Section 2 | Material | Not on List | Not on List | 2 | each | 12 | 24 | Laboratory Equipment / Certification | 2019-02-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12456-001025 | 12456 | 2019-02-14 09:52 | Section 4 | Material | Not on List | Not on List | 12 | Each | 166.32 | 1995.84 | Plastic Drainage | 2019-02-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12456-001025 | 12456 | 2019-02-14 09:52 | Section 4 | Material | Not on List | Not on List | 12 | Each | 15.19 | 182.28 | Plastic Drainage | 2019-02-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12456-001025 | 12456 | 2019-02-14 09:52 | Section 4 | Material | Not on List | NULL | 6 | Each | 159.28 | 955.68 | Plastic Drainage | 2019-02-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12456-001025 | 12456 | 2019-02-14 09:52 | Section 4 | Material | Not on List | Not on List | 6 | Each | 10.04 | 60.24 | Plastic Drainage | 2019-02-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | Twinwall | Not on List | 30 | number | NULL | 0 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 30 | Each | 1.84 | 55 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 150 | Each | 0.85 | 128 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | Twinwall | Polypipe 150mm x 150mm 45deg Junction (878010) | 10 | Each | 14.4 | 144 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12551-001025 | 12551 | 2019-02-15 10:22 | Section 2 | Material | Aggregate | 6G | 300 | Tonnes | 22 | 6600 | Aggregate | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12289-001025 | 12289 | 2019-02-12 09:03 | Core | Material | Not on List | Not on List | 2 | each | 228 | 456 | Office Supplies | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12397-001025 | 12397 | 2019-02-13 15:13 | Section 2 | Material | Not on List | Not on List | 15 | NULL | NULL | 0 | Builders Merchants (General) | 2019-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN28 - Ellington Brook Bridge | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12557-001025 | 12557 | 2019-02-15 11:42 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Ea | NULL | 0 | PPE | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12156-001025 | 12156 | 2019-02-08 13:01 | Core | Material | Not on List | Not on List | 3 | number packs | 21.45 | 64 | Office Supplies | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | NULL
MREQ-11907-001025 | 11907 | 2019-02-05 07:50 | Section 4 | Material | Not on List | Not on List | 1 | Each | 133.5 | 133.5 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11910-001025 | 11910 | 2019-02-05 07:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 531.69 | 531.69 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12278-001025 | 12278 | 2019-02-12 07:56 | Section 4 | Material | Not on List | Not on List | 13 | Each | 77.85 | 1012.05 | Concrete Drainage | 2019-02-21 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12278-001025 | 12278 | 2019-02-12 07:56 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2019-02-21 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12278-001025 | 12278 | 2019-02-12 07:56 | Section 4 | Material | NULL | Not on List | 1 | Each | 240 | 240 | Concrete Drainage | 2019-02-21 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11908-001025 | 11908 | 2019-02-05 07:55 | Section 4 | Material | Not on List | Not on List | 1 | Each | 97.5 | 97.5 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12571-001025 | 12571 | 2019-02-15 13:57 | Section 3 | Material | Not on List | Not on List | 100 | No | NULL | 0 | Builders Merchants (General) | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12574-001025 | 12574 | 2019-02-15 13:19 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Tanker and disposal | 2617.55 | 2618 | Miscellaneous | 2019-02-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12573-001025 | 12573 | 2019-02-15 13:53 | Core | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Training | 2019-02-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12482-001025 | 12482 | 2019-02-14 13:11 | Section 4 | Material | Not on List | Not on List | 4 | EA | 300 | 1200 | Concrete Accessories | 2019-02-19 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12497-001025 | 12497 | 2019-02-14 15:08 | Section 4 | Material | Not on List | Not on List | 32 | number | 281.9 | 9020.8 | Rebar and Mesh | 2019-03-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12582-001025 | 12582 | 2019-02-15 15:00 | Section 3 | Material | Not on List | Not on List | 25 | no | 8.8 | 220 | Fixings and Fasteners | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 838.26 | 838.26 | PPE | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 519.12 | 519.12 | Small Tools (Consumables) | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12554-001025 | 12554 | 2019-02-15 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 88.92 | 88.92 | Janitorial | 2019-02-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12520-001025 | 12520 | 2019-02-14 18:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 176.25 | 176.25 | Small Tools (Consumables) | 2019-02-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12615-001025 | 12615 | 2019-02-18 08:58 | Core | Material | Not on List | Not on List | 6 | ea | 214.58 | 1287 | Office Supplies | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12615-001025 | 12615 | 2019-02-18 08:58 | Core | Material | Not on List | Not on List | 6 | ea | 89.17 | 535 | Office Supplies | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25536-001025 | 25536 | 2019-10-22 09:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 8 | 40 | Small Tools (Consumables) | 2019-10-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25536-001025 | 25536 | 2019-10-22 09:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 12.1 | 61 | Small Tools (Consumables) | 2019-10-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 15.67 | 31.34 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25246-001025 | 25246 | 2019-10-16 13:55 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Miscellaneous | 2019-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 5.65 | 33.9 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 5.65 | 33.9 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24668-001025 | 24668 | 2019-10-04 15:33 | Core | Material | Not on List | Not on List | 1 | EA | 592.4 | 592.4 | Miscellaneous | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 4.14 | 8.28 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25590-001025 | 25590 | 2019-10-23 07:06 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-25597-001025 | 25597 | 2019-10-23 08:01 | Section 2 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Miscellaneous | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1901 - Protection of Steelwork Against Corrosion | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25598-001025 | 25598 | 2019-10-23 08:01 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 4.14 | 8.28 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25603-001025 | 25603 | 2019-10-23 08:10 | Core | Material | Not on List | Not on List | 1 | Each | 170.5 | 171 | Miscellaneous | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25573-001025 | 25573 | 2019-10-22 16:07 | Section 5 | Material | Combined Drainage | NULL | 1 | SM | 92362.43 | 92362.43 | Miscellaneous | 2019-10-23 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25499-001025 | 25499 | 2019-10-21 16:13 | Section 5 | Material | Combined Drainage | NULL | 1 | SM | 1071.94 | 1071.94 | Builders Merchants (General) | NULL | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | CPM 1200mm Concrete Pipe 2.5m (249379) | 34 | Each | 483.27 | 16431.18 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | CPM 1200mm Concrete Rocker (249380) | 4 | Each | 579.92 | 2319.68 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7043-001008 | 7043 | 2018-09-26 16:50 | Section 4 | Material | Not on List | Not on List | 6 | Each | 49.24 | 295.44 | Aggregate | 2018-10-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | CPM 1200mm Concrete Socket (249381) | 2 | Each | 579.92 | 1159.84 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 2 | Each | 579.92 | 1159.84 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Saint Gobain Castings | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 3 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25040-001025 | 25040 | 2019-10-14 12:26 | Section 2 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-21 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25618-001025 | 25618 | 2019-10-23 10:08 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 990.59 | 991 | PPE | 2019-10-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7043-001008 | 7043 | 2018-09-26 16:50 | Section 4 | Material | Not on List | Not on List | 6 | Each | 69 | 414 | Aggregate | 2018-10-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25618-001025 | 25618 | 2019-10-23 10:08 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 25.5 | 26 | Janitorial | 2019-10-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25618-001025 | 25618 | 2019-10-23 10:08 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 791.22 | 791 | Small Tools (Consumables) | 2019-10-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25567-001025 | 25567 | 2019-10-22 14:49 | Section 5 | Material | Not on List | NULL | 1 | EA | 176.4 | 176.4 | Miscellaneous | 2019-10-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25442-001025 | 25442 | 2019-10-20 18:33 | Section 5 | Material | Not on List | NULL | 1 | SM | 2815.24 | 2815.24 | Plastic Drainage | 2019-10-25 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1501 - Interface with Existing Communications Network | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25583-001025 | 25583 | 2019-10-22 17:34 | Section 5 | Material | Not on List | NULL | 10 | EA | 156.6 | 1566 | Plastic Drainage | NULL | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25543-001025 | 25543 | 2019-10-22 09:29 | Section 4 | Material | NULL | NULL | 200 | Each | 5.99 | 1198 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25543-001025 | 25543 | 2019-10-22 09:29 | Section 4 | Material | NULL | NULL | 10 | Each | 33.55 | 335.5 | Builders Merchants (General) | 2019-10-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25543-001025 | 25543 | 2019-10-22 09:29 | Section 4 | Material | NULL | NULL | 40 | Each | 2.97 | 118.8 | Builders Merchants (General) | 2019-10-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25543-001025 | 25543 | 2019-10-22 09:29 | Section 4 | Material | NULL | NULL | 14 | Each | 15.75 | 220.5 | Builders Merchants (General) | 2019-10-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25441-001025 | 25441 | 2019-10-20 17:30 | Section 5 | Material | Not on List | NULL | 1 | SM | 5716 | 5716 | Concrete Drainage | 2019-10-25 | 4358007 - EB5/2, Works Access, A14 Eastbound, Just on Jcn 32 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25275-001025 | 25275 | 2019-10-16 17:03 | Section 4 | Material | Not on List | Not on List | 1 | Each | 30000 | 30000 | Miscellaneous | 2019-10-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25276-001025 | 25276 | 2019-10-16 17:09 | Section 4 | Material | Not on List | Not on List | 1 | Each | 15000 | 15000 | Miscellaneous | 2019-10-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25150-001025 | 25150 | 2019-10-16 07:53 | Core | Material | Not on List | Not on List | 1 | Each | NULL | 0 | PPE | 2019-10-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 14 | Each | 23.14 | 323.96 | Plastic Drainage | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 14 | Each | 3.65 | 51.1 | Plastic Drainage | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 42 | Each | 2 | 84 | Plastic Drainage | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Bend 22.5deg (878030) | 3 | Each | 27.62 | 82.86 | Plastic Drainage | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Bend 11.25deg (878029) | 3 | Each | 27.62 | 82.86 | Plastic Drainage | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 1 | Ton | 3.56 | 3.56 | Builders Merchants (General) | 2019-10-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 6 | pairs | NULL | 0 | Builders Merchants (General) | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 4 | pairs | NULL | 0 | Builders Merchants (General) | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 3 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 4 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 2 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25557-001025 | 25557 | 2019-10-22 08:59 | Section 2 | Material | Not on List | Not on List | 4 | Each | NULL | 0 | Concrete Drainage | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25673-001025 | 25673 | 2019-10-24 11:02 | Section 2 | Material | Not on List | Not on List | 20 | Rolls | NULL | 0 | Builders Merchants (General) | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25114-001025 | 25114 | 2019-10-15 13:24 | Core | Material | Not on List | Not on List | 20 | Box 10 | 29.73 | 594.6 | PPE | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25476-001025 | 25476 | 2019-10-21 13:52 | Core | Material | PPE, Small Tools and Consumables | Not on List | 32 | Each | 28.8 | 921.6 | PPE | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25676-001025 | 25676 | 2019-10-24 11:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25539-001025 | 25539 | 2019-10-22 10:28 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25510-001025 | 25510 | 2019-10-21 17:14 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25504-001025 | 25504 | 2019-10-21 16:44 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 694.1 | 694.1 | Small Tools (Consumables) | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25561-001025 | 25561 | 2019-10-22 12:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 5.97 | 119.4 | Janitorial | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25561-001025 | 25561 | 2019-10-22 12:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 23.61 | 236.1 | Janitorial | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25561-001025 | 25561 | 2019-10-22 12:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 24 | NULL | 3.15 | 75.6 | Janitorial | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25608-001025 | 25608 | 2019-10-23 08:53 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1783.06 | 1783.06 | PPE | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25614-001025 | 25614 | 2019-10-23 09:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | NULL | 5.82 | 46.56 | Small Tools (Consumables) | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25614-001025 | 25614 | 2019-10-23 09:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3 | NULL | 13.19 | 39.57 | Small Tools (Consumables) | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25614-001025 | 25614 | 2019-10-23 09:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 3.55 | 71 | Small Tools (Consumables) | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25677-001025 | 25677 | 2019-10-24 11:39 | Section 4 | Material | NULL | NULL | 200 | Each | 16.57 | 3314 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7108-001020 | 7108 | 2018-09-27 17:14 | Section 3 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 1000 | Each | 0.54 | 540 | Miscellaneous | 2018-10-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25591-001025 | 25591 | 2019-10-23 07:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 58.8 | 58.8 | Miscellaneous | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | Not on List | 1 | Each | 0 | 0 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1500x1000 D/S (991900) | 1 | Each | 121.25 | 121.25 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1500X500 D/S (991898) | 1 | Each | 80.51 | 80.51 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7109-001020 | 7109 | 2018-09-27 17:19 | Section 3 | Material | Not on List | Not on List | 10 | Rolls | 32.5 | 325 | Builders Merchants (General) | 2018-10-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 1 | Each | 81.96 | 81.96 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 1 | Each | 53.01 | 53.01 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 1 | Each | 36.62 | 36.62 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25680-001025 | 25680 | 2019-10-24 11:39 | Section 6 | Material | Concrete Drainage | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25631-001 | 25631 | 2019-10-23 14:05 | Section 3 | Material | Not on List | Not on List | 1 | ea | 166.23 | 166.23 | Concrete Drainage | 2019-10-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25674-001025 | 25674 | 2019-10-24 11:06 | Section 2 | Material | Aggregate | 6G | 100 | Tonnes | 22 | 2200 | Aggregate | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7074-001008 | 7074 | 2018-09-27 08:14 | Section 3 | Material | Concrete Drainage | Not on List | 50 | NULL | 1308 | 65400 | Concrete Drainage | 2018-10-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25738-001025 | 25738 | 2019-10-25 10:37 | Core | Material | Not on List | Not on List | 1 | SM | 960 | 960 | Office Supplies | 2019-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25747-001025 | 25747 | 2019-10-25 12:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 90 | 90 | Professional Services | 2019-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1901 - Protection of Steelwork Against Corrosion | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7089-001020 | 7089 | 2018-09-27 12:53 | Section 3 | Material | Not on List | Not on List | 1 | EA | 3993.83 | 3993.83 | Damage Charges | 2018-09-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25672-001025 | 25672 | 2019-10-24 10:49 | Section 4 | Material | NULL | NULL | 4 | Each | 36.36 | 145.44 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25672-001025 | 25672 | 2019-10-24 10:49 | Section 4 | Material | NULL | NULL | 1 | Each | 142.26 | 142.26 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25697-001025 | 25697 | 2019-10-24 14:52 | Section 4 | Material | NULL | NULL | 20 | Each | 31.63 | 632.6 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25697-001025 | 25697 | 2019-10-24 14:52 | Section 4 | Material | NULL | NULL | 65 | Each | 41.2 | 2678 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25697-001025 | 25697 | 2019-10-24 14:52 | Section 4 | Material | NULL | NULL | 20 | Each | 41.2 | 824 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25736-001025 | 25736 | 2019-10-25 10:06 | Section 6 | Material | Bagged | Not on List | 4 | each | NULL | 0 | Builders Merchants (General) | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25736-001025 | 25736 | 2019-10-25 10:06 | Section 6 | Material | Bagged | Building Sand 25kg Bag (996239) | 4 | Each | 1.8 | 7.2 | Builders Merchants (General) | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25736-001025 | 25736 | 2019-10-25 10:06 | Section 6 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 5 | Each | 3.56 | 17.8 | Builders Merchants (General) | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25736-001025 | 25736 | 2019-10-25 10:06 | Section 6 | Material | Twinwall | Polyipipe 150mm Ridgidrain Bend 90deg (878001) | 2 | Each | 8.25 | 16.5 | Plastic Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25736-001025 | 25736 | 2019-10-25 10:06 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain Bend 90deg (878034) | 2 | Each | 27.62 | 55.24 | Plastic Drainage | 2019-10-31 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7089-001020 | 7089 | 2018-09-27 12:53 | Section 3 | Material | Not on List | Not on List | 1 | EA | 218.19 | 218.19 | Damage Charges | 2018-09-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25703-001025 | 25703 | 2019-10-24 15:54 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2019-10-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25710-001025 | 25710 | 2019-10-24 17:11 | Section 3 | Material | Not on List | Not on List | 1 | ea | 67.5 | 67.5 | NULL | 2019-10-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25710-001025 | 25710 | 2019-10-24 17:11 | Section 3 | Material | Not on List | Not on List | 1 | ea | 485 | 485 | Fixings and Fasteners | 2019-10-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25763-001025 | 25763 | 2019-10-25 15:14 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | ea | 22.85 | 69 | Small Tools (Consumables) | 2019-10-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 100 | Each | 11.34 | 1134 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7089-001020 | 7089 | 2018-09-27 12:53 | Section 3 | Material | Not on List | Not on List | 1 | EA | 54.76 | 54.76 | Damage Charges | 2018-09-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 300 | Each | 1.99 | 597 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 150 | Each | 0.92 | 138 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 180 | Each | 24.99 | 4498.2 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 200 | Each | 3.65 | 730 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 400 | Each | 2.01 | 804 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 160 | Each | 37.6 | 6016 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 200 | Each | 7.03 | 1406 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 400 | Each | 2.97 | 1188 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 200 | Each | 130.26 | 26052 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25537-001025 | 25537 | 2019-10-22 09:52 | Section 4 | Material | NULL | NULL | 20 | Each | 147.69 | 2953.8 | Plastic Drainage | 2019-10-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7089-001020 | 7089 | 2018-09-27 12:53 | Section 3 | Material | Not on List | Not on List | 1 | CREDIT | 497.76 | 497.76 | Damage Charges | 2018-09-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25731-001025 | 25731 | 2019-10-25 09:42 | Section 6 | Material | Not on List | Not on List | 50 | Tonne | 538 | 26900 | Rebar and Mesh | 2019-11-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25731-001025 | 25731 | 2019-10-25 09:42 | Section 6 | Material | NULL | Not on List | 200 | Each | 2 | 400 | Rebar and Mesh | 2019-11-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25770-001025 | 25770 | 2019-10-25 17:06 | Section 3 | Material | Aggregate | Type 1 | 400 | Tonnes | 21.65 | 8660 | Aggregate | 2019-10-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-25605-001025 | 25605 | 2019-10-23 08:22 | Section 4 | Material | NULL | NULL | 40 | Each | 12.5 | 500 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25786-001025 | 25786 | 2019-10-28 08:59 | Section 5 | Material | Timber | NULL | 100 | EA | 32.95 | 3295 | Not Sure | 2019-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25786-001025 | 25786 | 2019-10-28 08:59 | Section 5 | Material | Timber | NULL | 50 | EA | 15.95 | 797.5 | Not Sure | 2019-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25786-001025 | 25786 | 2019-10-28 08:59 | Section 5 | Material | Timber | NULL | 500 | MTRS | 0.65 | 325 | Not Sure | 2019-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25789-001025 | 25789 | 2019-10-28 09:28 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1453.2 | Each | 1 | 1453.2 | PPE | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 6 | Each | 50.92 | 305.52 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28804-001025 | 28804 | 2020-02-03 15:13 | Section 5 | Material | Not on List | Not on List | 16.592 | m2 | 54 | 895.97 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28804-001025 | 28804 | 2020-02-03 15:13 | Section 5 | Material | Not on List | Not on List | 2 | Roll | 16.18 | 32.36 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28804-001025 | 28804 | 2020-02-03 15:13 | Section 5 | Material | NULL | NULL | 8 | Roll | 9.62 | 76.96 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28804-001025 | 28804 | 2020-02-03 15:13 | Section 5 | Material | NULL | NULL | 1 | Each | 75 | 75 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28804-001025 | 28804 | 2020-02-03 15:13 | Section 5 | Material | NULL | NULL | 1 | Each | 300 | 300 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28784-001025 | 28784 | 2020-02-03 10:51 | Section 4 | Material | Not on List | Not on List | 384 | Each | 3.52 | 1351.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 8 | Each | 43.16 | 345.28 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28784-001025 | 28784 | 2020-02-03 10:51 | Section 4 | Material | Not on List | Not on List | 384 | Each | 4.59 | 1762.56 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28886-001025 | 28886 | 2020-02-05 16:22 | Section 4 | Material | Aggregate | Not on List | 20 | Tonne | 18.5 | 370 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28436-001025 | 28436 | 2020-01-23 12:43 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1396 | 1396 | Professional Services | 2020-01-27 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28918-001025 | 28918 | 2020-02-06 11:56 | Core | Material | Not on List | Not on List | 1 | ea | 933.22 | 933 | Training | 2020-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-28604-001025 | 28604 | 2020-01-28 17:37 | Section 5 | Material | Not on List | Not on List | 1 | Each | 236.42 | 236.42 | Miscellaneous | 2020-02-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28881-001025 | 28881 | 2020-02-05 12:43 | Section 4 | Material | Not on List | Not on List | 300 | Each | 3.97 | 1191 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28928-001025 | 28928 | 2020-02-06 14:43 | Section 5 | Material | Not on List | Not on List | 12 | no. | NULL | 0 | Builders Merchants (General) | 2020-02-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28928-001025 | 28928 | 2020-02-06 14:43 | Section 5 | Material | Not on List | Not on List | 10 | no. | NULL | 0 | Builders Merchants (General) | 2020-02-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 49.62 | 50 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 105.03 | 105 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-5218-00139 | 5218 | 2018-08-16 11:54 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-08-29 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 10 | Each | 35.52 | 355.2 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 40.67 | 41 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 2254.45 | 2254 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 82.78 | 83 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 1 | No | 37.5 | 38 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28939-001025 | 28939 | 2020-02-06 15:40 | Section 4 | Material | Not on List | Not on List | 0 | NULL | NULL | 0 | Professional Services | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28969-001025 | 28969 | 2020-02-07 09:48 | Section 2 | Material | Waste Management | Not on List | 1 | each | 750 | 750 | Waste (General) | 2020-02-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-28971-001025 | 28971 | 2020-02-07 10:08 | Core | Material | Not on List | Not on List | 1 | NULL | 50 | 50 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-28972-001025 | 28972 | 2020-02-07 10:27 | Core | Material | Not on List | Not on List | 1 | NULL | 802.25 | 802 | Miscellaneous | 2019-06-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-28974-001025 | 28974 | 2020-02-07 10:59 | Core | Material | Not on List | Not on List | 1 | NULL | 49.99 | 50 | Miscellaneous | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-28897 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 65 | Each | 19.61 | 1274.65 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | NULL | NULL | NULL
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 14 | Each | 47.04 | 658.56 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28897-001025 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Bend 30deg (877999) | 65 | Each | 17.03 | 1106.95 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28897-001025 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Bend 45deg (878000) | 65 | Each | 17.03 | 1106.95 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28897-001025 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Bend 15deg (877998) | 65 | Each | 17.03 | 1106.95 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28897-001025 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Not on List | Not on List | 65 | Each | 3.15 | 204.75 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28897-001025 | 28897 | 2020-02-05 18:08 | Section 4 | Material | Not on List | Not on List | 130 | Each | 1.55 | 201.5 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 32 | Each | 16.49 | 527.68 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 16 | Each | 74.3 | 1188.8 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 4 | Each | 99 | 396 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5223-00140 | 5223 | 2018-08-16 12:16 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2018-08-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7265-001022 | 7265 | 2018-10-02 09:27 | Section 3 | Material | Not on List | Not on List | 2 | per day | 316.8 | 633.6 | Miscellaneous | 2018-10-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7412-001022 | 7412 | 2018-10-04 17:26 | Section 3 | Material | Not on List | Not on List | 5 | Number | 42.45 | 212.25 | Concrete Accessories | 2018-10-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN07 - B1043 Offord Road Overbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7346-001022 | 7346 | 2018-10-03 11:37 | Section 3 | Material | Not on List | Not on List | 1 | EA | 90 | 90 | Damage Charges | 2018-10-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7402-001022 | 7402 | 2018-10-04 14:58 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 687.5 | Plastic Drainage | 2018-10-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5122-0045 | 5122 | 2018-08-15 09:11 | Section 4 | Material | Not on List | NULL | 4 | Each | 15.47 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7401-001022 | 7401 | 2018-10-04 14:26 | Section 4 | Material | Not on List | Not on List | 6 | Each | 485 | 2910 | Fixings and Fasteners | 2018-10-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7401-001022 | 7401 | 2018-10-04 14:26 | Section 4 | Material | NULL | NULL | 1 | Each | 195 | 195 | Fixings and Fasteners | 2018-10-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5122-0045 | 5122 | 2018-08-15 09:11 | Section 4 | Material | Not on List | NULL | 4 | Each | 15.47 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6802-001022 | 6802 | 2018-09-20 16:00 | Section 3 | Material | Not on List | Not on List | 20 | no | 5.95 | 119 | Surveying Consumables | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN14 - Hilton Road Overbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 24.12 | 24.12 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 24.12 | 24.12 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 24.12 | 24.12 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 24.12 | 24.12 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 20 | ea | 7.5 | 150 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 66.97 | 66.97 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 66.97 | 66.97 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7512-001022 | 7512 | 2018-10-08 11:30 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 67.9 | 1018.5 | Concrete Drainage | 2018-10-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7512-001022 | 7512 | 2018-10-08 11:30 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 25 | Each | 43.16 | 1079 | Concrete Drainage | 2018-10-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7512-001022 | 7512 | 2018-10-08 11:30 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 50 | Each | 35.52 | 1776 | Concrete Drainage | 2018-10-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7512-001022 | 7512 | 2018-10-08 11:30 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 25 | Each | 47.04 | 1176 | Concrete Drainage | 2018-10-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7512-001022 | 7512 | 2018-10-08 11:30 | Section 4 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 50 | Each | 16.49 | 824.5 | Concrete Drainage | 2018-10-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7426-001022 | 7426 | 2018-10-05 08:51 | Section 4 | Material | Not on List | Not on List | 10 | Each | 42.92 | 429.2 | Concrete Drainage | 2018-10-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7426-001022 | 7426 | 2018-10-05 08:51 | Section 4 | Material | Not on List | Not on List | 3 | Each | 53.28 | 159.84 | Concrete Drainage | 2018-10-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7387-001022 | 7387 | 2018-10-04 11:17 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.45 | 45 | Surveying Consumables | 2018-10-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7514-001022 | 7514 | 2018-10-08 13:22 | Section 4 | Material | NULL | Not on List | 16 | Each | 11.94 | 191.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7577-001023 | 7577 | 2018-10-09 15:12 | Section 4 | Material | Not on List | Not on List | 110 | Each | 3.84 | 422.4 | Timber Products | 2018-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7577-001023 | 7577 | 2018-10-09 15:12 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 0.65 | 650 | Timber Products | 2018-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7577-001023 | 7577 | 2018-10-09 15:12 | Section 4 | Material | Not on List | Not on List | 6 | 1kg Bag 50mm Galv Nails | 3.46 | 20.76 | Timber Products | 2018-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5164-0087 | 5164 | 2018-08-15 13:43 | Section 4 | Material | Not on List | Not on List | 45 | Sheet | 13.44 | 0 | Builders Merchants (General) | 2018-08-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5164-0087 | 5164 | 2018-08-15 13:43 | Section 4 | Material | Not on List | Not on List | 10 | Sheet | 8.47 | 0 | Builders Merchants (General) | 2018-08-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7506-001022 | 7506 | 2018-10-08 09:59 | Section 4 | Material | Not on List | Not on List | 1000 | each | 1.07 | 1070 | Timber Products | 2018-10-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7425-001022 | 7425 | 2018-10-05 08:43 | Section 4 | Material | Not on List | Not on List | 100 | Bag | 8.9 | 890 | Concrete Accessories | 2018-10-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7425-001022 | 7425 | 2018-10-05 08:43 | Section 4 | Material | Not on List | Not on List | 10 | Each | 149.64 | 1496.4 | Concrete Accessories | 2018-10-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7435-001023 | 7435 | 2018-10-05 10:30 | Section 4 | Material | Not on List | Not on List | 51.317 | tonnes | 538 | 27608.55 | Rebar and Mesh | 2018-10-17 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7435-001023 | 7435 | 2018-10-05 10:30 | Section 4 | Material | Not on List | Not on List | 28.947 | tonnes | 538 | 15573.49 | Rebar and Mesh | 2018-10-17 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7223-001021 | 7223 | 2018-10-01 13:58 | Section 4 | Material | Not on List | Not on List | 1 | Each | 689.44 | 689.44 | Damage Charges | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.47 | 47 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 10 | Each | 5.74 | 57.4 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 5 | Each | 18.19 | 90.95 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 5 | Each | 57.92 | 289.6 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 10 | Each | 8.47 | 84.7 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 1 | Each | 149.64 | 149.64 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7478-001022 | 7478 | 2018-10-05 16:52 | Section 4 | Material | Not on List | Not on List | 5 | Each | 42.45 | 212.25 | Builders Merchants (General) | 2018-10-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7508-001022 | 7508 | 2018-10-08 11:03 | Section 4 | Material | Not on List | Not on List | 1600 | Each | 1.45 | 2320 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7508-001022 | 7508 | 2018-10-08 11:03 | Section 4 | Material | NULL | NULL | 1 | Each | 30 | 30 | Miscellaneous | 2018-10-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 20 | Each | 120.62 | 2412.4 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 30 | Each | 17.45 | 523.5 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 60 | Each | 9.04 | 542.4 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 65 | Each | 34.82 | 2263.3 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 75 | Each | 6.54 | 490.5 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 150 | Each | 2.75 | 412.5 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 20 | Each | 10.5 | 210 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 40 | Each | 1.84 | 73.6 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 80 | Each | 0.85 | 68 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5002-0015 | 5002 | 2018-08-13 15:53 | Section 4 | Material | Not on List | NULL | 240 | square meters | NULL | 0 | Blocks and Bricks | 2018-08-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 20 | Each | 14.4 | 288 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 20 | Each | 44.41 | 888.2 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 40 | Each | 7.64 | 305.6 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 40 | Each | 7.64 | 305.6 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7590-001023 | 7590 | 2018-10-09 17:22 | Section 4 | Material | Not on List | Not on List | 10 | Each | 19.72 | 197.2 | Plastic Drainage | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 14 | Each | 67.9 | 950.6 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 3 | Each | 50.92 | 152.76 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 7 | Each | 43.16 | 302.12 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 4 | Each | 35.52 | 142.08 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 12 | Each | 47.04 | 564.48 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 24 | Each | 16.49 | 395.76 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7591-001023 | 7591 | 2018-10-09 17:31 | Section 4 | Material | Not on List | Not on List | 12 | Each | 74.3 | 891.6 | Concrete Drainage | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7666-001023 | 7666 | 2018-10-11 09:48 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2018-10-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7669-001023 | 7669 | 2018-10-11 11:20 | Section 3 | Material | Not on List | Not on List | 1 | SET | NULL | 0 | Not Sure | 2018-10-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7669-001023 | 7669 | 2018-10-11 11:20 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2018-10-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7620-001023 | 7620 | 2018-10-10 14:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 50.4 | 1008 | Small Tools (Consumables) | 2018-10-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7619-001023 | 7619 | 2018-10-10 14:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | EAch | 6.29 | 905.76 | Miscellaneous | 2018-10-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7559-001023 | 7559 | 2018-10-09 11:39 | Section 3 | Material | Not on List | Not on List | 1 | SUM | 601 | 601 | Timber Products | 2018-10-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7540-001023 | 7540 | 2018-10-09 07:48 | Section 3 | Material | Not on List | Not on List | 10 | No | 19.16 | 191.6 | Builders Merchants (General) | 2018-10-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7571-001023 | 7571 | 2018-10-09 13:51 | Section 3 | Material | Not on List | Not on List | 70 | Tonnes | 538 | 37660 | NULL | 2018-10-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7627-001023 | 7627 | 2018-10-10 15:24 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 6 | Each | 42.94 | 257.64 | Builders Merchants (General) | 2018-10-12 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7504-001022 | 7504 | 2018-10-08 08:52 | Section 4 | Material | Concrete Drainage | Not on List | 1 | Each | 3450 | 3450 | Concrete Drainage | 2018-10-29 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5189-00116 | 5189 | 2018-08-16 07:01 | Section 4 | Material | Not on List | Not on List | 400 | 25m Pack | 12.8 | 0 | Miscellaneous | 2018-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5188-00115 | 5188 | 2018-08-15 18:58 | Section 4 | Material | Not on List | Not on List | 1000 | each | 1.07 | 0 | Timber Products | 2018-08-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7787-001023 | 7787 | 2018-10-15 09:37 | Section 3 | Material | Not on List | Not on List | 23 | EA | 212.4 | 4885.2 | Plastic Drainage | 2018-10-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7787-001023 | 7787 | 2018-10-15 09:37 | Section 3 | Material | Not on List | Not on List | 8 | EA | 12.05 | 96.4 | Plastic Drainage | 2018-10-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7787-001023 | 7787 | 2018-10-15 09:37 | Section 3 | Material | Not on List | Not on List | 44 | EA | 31.98 | 1407.12 | Plastic Drainage | 2018-10-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7646-001023 | 7646 | 2018-10-10 18:30 | Section 3 | Material | Not on List | Not on List | 1 | SM | 173.92 | 173.92 | Small Tools (Consumables) | 2018-10-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7519-001023 | 7519 | 2018-10-08 14:47 | Section 4 | Material | Not on List | Not on List | 15 | Each | 55.5 | 832.5 | Not Sure | 2018-10-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 1 | EA | 29.5 | 29.5 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 2 | EA | 47.5 | 95 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 1 | EA | 125 | 125 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 2 | EA | 125 | 250 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 10 | EA | 38.5 | 385 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | NULL | Not on List | 1 | EA | 125 | 125 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20629-001025 | 20629 | 2019-07-11 15:11 | Section 3 | Material | Not on List | Not on List | 500 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20634-001025 | 20634 | 2019-07-11 15:24 | Section 3 | Material | Aggregate | A10 Pipe Bed | 280 | Tonnes | 16.5 | 4620 | Aggregate | 2019-07-17 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20561-001025 | 20561 | 2019-07-10 14:16 | Core | Material | NULL | NULL | 1 | Each | 822.5 | 822.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5142-0070 | 5142 | 2018-08-15 11:34 | Section 3 | Material | Concrete Drainage | Not on List | 14 | Each | 35.52 | 497.28 | Concrete Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | NULL | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20567-001025 | 20567 | 2019-07-10 14:35 | Section 3 | Material | PPE, Small Tools and Consumables | Sleeve - White C/W Overhead Structures 750mm Csp (204017) | 160 | Each | 2.18 | 348.8 | Miscellaneous | 2019-07-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20621-001025 | 20621 | 2019-07-11 13:45 | Section 3 | Material | Not on List | Not on List | 10 | ea | 286.21 | 2862.1 | Miscellaneous | 2019-07-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | NULL | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20655-001025 | 20655 | 2019-07-11 18:38 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-16 | 1358005 - WB5/7 Works Access - 1356563 - A14 Westbound, On Left between Jcn 32 - 31 | SEC5 - Roadworks | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | NULL | Req - S5 Buyers
MREQ-20465-001025 | 20465 | 2019-07-09 08:53 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-20575-001025 | 20575 | 2019-07-10 15:54 | Section 1 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-07-22 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | NULL | Req - S1 Buyers
MREQ-16878-001025 | 16878 | 2019-05-03 13:12 | Section 3 | Material | Not on List | Not on List | 105 | roll | 111.2 | 11676 | Builders Merchants (General) | 2019-05-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16878-001025 | 16878 | 2019-05-03 13:12 | Section 3 | Material | Not on List | Not on List | 850 | No | 1.65 | 1402.5 | Builders Merchants (General) | 2019-05-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16878-001025 | 16878 | 2019-05-03 13:12 | Section 3 | Material | Not on List | Not on List | 17000 | No | 0.3 | 5100 | Builders Merchants (General) | 2019-05-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16878-001025 | 16878 | 2019-05-03 13:12 | Section 3 | Material | Not on List | Not on List | 1500 | m | 0.15 | 225 | Builders Merchants (General) | 2019-05-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20600-001025 | 20600 | 2019-07-11 08:39 | Section 3 | Material | Not on List | Not on List | 1 | Cartridges | 1146.4 | 1146.4 | Builders Merchants (General) | 2019-07-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20600-001025 | 20600 | 2019-07-11 08:39 | Section 3 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Builders Merchants (General) | 2019-07-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | NULL | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20534-001025 | 20534 | 2019-07-10 09:28 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.9 | 450 | Miscellaneous | 2019-07-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20581-001025 | 20581 | 2019-07-10 17:29 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-07-11 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20687-001025 | 20687 | 2019-07-12 10:13 | Core | Material | Not on List | Not on List | 1 | NULL | 1350 | 1350 | Training | 2019-07-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19986-001025 | 19986 | 2019-07-01 09:38 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | NULL | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 198 | ea | 5.6 | 1108.8 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 2.77 | 182.82 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 4.5 | 297 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 3.35 | 221.1 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 5.01 | 330.66 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 3.67 | 242.22 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20645-001025 | 20645 | 2019-07-11 14:22 | Section 4 | Material | Not on List | Not on List | 66 | ea | 3.91 | 258.06 | Fixings and Fasteners | 2019-07-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20674-001025 | 20674 | 2019-07-12 10:46 | Section 5 | Material | NULL | NULL | 2 | ea | 23.22 | 46.44 | NULL | 2019-07-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5380 | 5380 | 2018-08-20 16:43 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Rebar and Mesh | 2018-08-23 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Coverall Flame Retardent Cotton Saturn Fr Reflective Tape (370522) | 2 | Each | 107.6 | 215 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16567-001025 | 16567 | 2019-04-29 12:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 452.88 | 453 | Small Tools (Consumables) | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-16569-001025 | 16569 | 2019-04-29 12:39 | Section 2 | Material | PPE, Small Tools and Consumables | Towel Hand Pristine Z Fold 2ply White Case 3210 Sheet 66955 (539303) | 20 | Each | 26.89 | 538 | Janitorial | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16569-001025 | 16569 | 2019-04-29 12:39 | Section 2 | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 200sheets 517346 (539288) | 20 | Each | 5.97 | 119 | Janitorial | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 120 | Each | 8.55 | 1026 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 120 | Each | 8.55 | 1026 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-5715-00449 | 5715 | 2018-08-29 06:58 | Section 3 | Material | Not on List | Not on List | 1 | No | 2700 | 2700 | Not Sure | 2018-08-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 240 | NULL | NULL | 0 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 240 | NULL | NULL | 0 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | Tissues Uvex Cleaning Box Of 450 Sheets Ref 9991-000 (430589) | 10 | Each | 3.3 | 33 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16574-001025 | 16574 | 2019-04-29 13:14 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | PPE | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-16090-001025 | 16090 | 2019-04-17 17:12 | Section 4 | Material | NULL | Not on List | 10 | EA | 43.57 | 435.7 | Builders Merchants (General) | 2019-04-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16327-001025 | 16327 | 2019-04-24 15:25 | Section 4 | Material | Not on List | Not on List | 100 | Each | 58 | 5800 | Concrete Drainage | 2019-05-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16327-001025 | 16327 | 2019-04-24 15:25 | Section 4 | Material | Not on List | Not on List | 20 | Each | 62 | 1240 | Concrete Drainage | 2019-05-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16327-001025 | 16327 | 2019-04-24 15:25 | Section 4 | Material | NULL | Not on List | 80 | Each | 60 | 4800 | Concrete Drainage | 2019-05-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16327-001025 | 16327 | 2019-04-24 15:25 | Section 4 | Material | NULL | Not on List | 1 | Each | 500 | 500 | Concrete Drainage | 2019-05-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15778-001025 | 15778 | 2019-04-12 14:02 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 21.41 | 42.82 | Laboratory Equipment / Certification | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6373-00677 | 6373 | 2018-09-12 08:07 | Section 3 | Material | Not on List | Not on List | 20 | 10 ltr drums | NULL | 0 | Miscellaneous | 2018-09-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | CL3B - Structures (Culverts) 3B | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16588-001025 | 16588 | 2019-04-29 15:21 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2901.3 | 2901 | Small Tools (Consumables) | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-16590-001025 | 16590 | 2019-04-29 15:16 | Section 2 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 300mm X 4.8mm Pack Of 100 Spartan (230061) | 50 | Each | 1.94 | 97 | Small Tools (Consumables) | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16590-001025 | 16590 | 2019-04-29 15:16 | Section 2 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 370mm X 7.6mm Pack Of 100 Spartan (230065) | 50 | Each | 3.88 | 194 | Small Tools (Consumables) | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16593-001025 | 16593 | 2019-04-29 15:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 303.87 | 304 | PPE | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-16313-001025 | 16313 | 2019-04-24 13:15 | Section 4 | Material | Not on List | Not on List | 200 | Each | 1.19 | 238 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16313-001025 | 16313 | 2019-04-24 13:15 | Section 4 | Material | Not on List | NULL | 3 | Box 10 | 50.43 | 151.29 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16313-001025 | 16313 | 2019-04-24 13:15 | Section 4 | Material | Not on List | NULL | 3 | Box 10 | 43.69 | 131.07 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16313-001025 | 16313 | 2019-04-24 13:15 | Section 4 | Material | Not on List | Not on List | 3 | Box 10 | 33.64 | 100.92 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16345-001025 | 16345 | 2019-04-24 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 361.76 | 361.76 | Small Tools (Consumables) | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16535-001025 | 16535 | 2019-04-29 07:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 770 | 770 | Miscellaneous | 2019-04-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16347-001025 | 16347 | 2019-04-24 16:54 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2869.68 | 2869.68 | PPE | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16416-001025 | 16416 | 2019-04-25 13:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1519 | 1519 | Laboratory Equipment / Certification | 2019-04-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16638-001025 | 16638 | 2019-04-30 10:20 | Section 2 | Material | Not on List | Not on List | 100 | Lengths | NULL | 0 | Concrete Accessories | 2019-04-30 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15103-001025 | 15103 | 2019-04-02 09:48 | Section 4 | Material | Not on List | Not on List | 77 | Rolls | 49.5 | 3811.5 | Fixings and Fasteners | 2019-05-03 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-14851-001025 | 14851 | 2019-03-28 10:37 | Section 4 | Material | Not on List | Not on List | 40 | Each | 49.91 | 1996.4 | Miscellaneous | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14851-001025 | 14851 | 2019-03-28 10:37 | Section 4 | Material | Not on List | Not on List | 100 | Each | 9.58 | 958 | Miscellaneous | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16656-001025 | 16656 | 2019-04-30 13:59 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16659-001025 | 16659 | 2019-04-30 14:23 | Section 4 | Material | Not on List | Not on List | 3200 | Each | 1 | 3200 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 7 | Each | 67.9 | 475 | Concrete Drainage | 2019-05-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 3 | Each | 35.52 | 107 | Concrete Drainage | 2019-05-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 7 | Each | 47.04 | 329 | Concrete Drainage | 2019-05-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 4 | Each | 43.16 | 173 | Concrete Drainage | 2019-04-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Perf (346338) | 50 | Each | 10.66 | 533 | Plastic Drainage | 2019-04-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 90 | Each | 23.14 | 2083 | Plastic Drainage | 2019-05-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16663-001025 | 16663 | 2019-04-30 14:59 | Section 1 | Material | Twinwall | Not on List | 10 | Each | NULL | 0 | Plastic Drainage | 2019-05-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16062-001025 | 16062 | 2019-04-16 15:52 | Section 4 | Material | Not on List | Not on List | 47 | Each | 28 | 1316 | Miscellaneous | 2019-05-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16062-001025 | 16062 | 2019-04-16 15:52 | Section 4 | Material | Not on List | Not on List | 2 | Each | 45 | 90 | Miscellaneous | 2019-05-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16062-001025 | 16062 | 2019-04-16 15:52 | Section 4 | Material | NULL | Not on List | 1 | Each | 97 | 97 | Miscellaneous | 2019-05-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16062-001025 | 16062 | 2019-04-16 15:52 | Section 4 | Material | NULL | Not on List | 6 | Each | 38 | 228 | Miscellaneous | 2019-05-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16062-001025 | 16062 | 2019-04-16 15:52 | Section 4 | Material | NULL | Not on List | 1 | Each | 125 | 125 | Miscellaneous | 2019-05-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | Not on List | Not on List | 230 | Each | 11.51 | 2647.3 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 260 | Each | 1.98 | 514.8 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 520 | Each | 0.91 | 473.2 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | Not on List | Not on List | 24 | Each | 34.6 | 830.4 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 36 | Each | 7.06 | 254.16 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 72 | Each | 2.97 | 213.84 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | Not on List | Not on List | 20 | Each | 164.37 | 3287.4 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | Not on List | Not on List | 20 | Each | 164.37 | 3287.4 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16468-001025 | 16468 | 2019-04-26 08:45 | Section 4 | Material | Not on List | Not on List | 30 | Each | 42.87 | 1286.1 | Plastic Drainage | 2019-05-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16482-001025 | 16482 | 2019-04-26 11:47 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 40 | Each | 52.77 | 2110.8 | Plastic Drainage | 2019-04-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16482-001025 | 16482 | 2019-04-26 11:47 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 80 | Each | 2.97 | 237.6 | Plastic Drainage | 2019-04-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6393-00687 | 6393 | 2018-09-12 10:50 | Section 3 | Material | Plastic Drainage | Not on List | 5 | No | 27.92 | 139.6 | Plastic Drainage | 2018-09-14 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16592-001025 | 16592 | 2019-04-29 15:12 | Section 3 | Material | Aggregate | Not on List | 150 | m3 | 47.05 | 7057.5 | Aggregate | 2019-04-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 10 | Each | 166.43 | 1664 | Plastic Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Twinwall | Not on List | 84 | Each | NULL | 0 | Plastic Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Twinwall | Not on List | 30 | Each | NULL | 0 | Plastic Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 6 | Each | 47.04 | 282 | Concrete Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 9 | Each | 67.9 | 611 | Concrete Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 1 | Each | 50.92 | 51 | Concrete Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 2 | Each | 43.16 | 86 | Concrete Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16670-001025 | 16670 | 2019-04-30 16:07 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 1 | Each | 35.52 | 36 | Concrete Drainage | 2019-05-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16684-001025 | 16684 | 2019-04-30 17:56 | Section 5 | Material | Twinwall | Not on List | 62 | No | NULL | 0 | Plastic Drainage | 2019-05-09 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16684-001025 | 16684 | 2019-04-30 17:56 | Section 5 | Material | Twinwall | Not on List | 10 | No | NULL | 0 | Plastic Drainage | 2019-05-09 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16684-001025 | 16684 | 2019-04-30 17:56 | Section 5 | Material | Twinwall | Not on List | 20 | No | NULL | 0 | Plastic Drainage | 2019-05-09 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16684-001025 | 16684 | 2019-04-30 17:56 | Section 5 | Material | Twinwall | Not on List | 90 | No | NULL | 0 | Plastic Drainage | 2019-05-09 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16674-001025 | 16674 | 2019-04-30 17:02 | Section 3 | Material | Not on List | Not on List | 100 | ea | 2.81 | 281 | Fuel | 2019-05-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16705-001025 | 16705 | 2019-05-01 09:07 | Section 4 | Material | Not on List | Not on List | 24 | Each | 1 | 24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16714-001025 | 16714 | 2019-05-01 10:35 | Core | Material | Not on List | Not on List | 1 | £ | 900 | 900 | Miscellaneous | 2019-05-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 16 | NULL | 85.23 | 1363.68 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 7 | NULL | NULL | 0 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 9 | NULL | NULL | 0 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 49 | NULL | NULL | 0 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 49 | NULL | NULL | 0 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 1 | NULL | 113.55 | 113.55 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 1 | NULL | 79.78 | 79.78 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 3 | NULL | 126.1 | 378.3 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16052-001025 | 16052 | 2019-04-17 09:32 | Section 6 | Material | Concrete Drainage | Not on List | 1 | NULL | 94.57 | 94.57 | Concrete Drainage | 2019-04-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16718-001025 | 16718 | 2019-05-01 11:27 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16725-001025 | 16725 | 2019-05-01 13:12 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 780 | Each | 4.59 | 3580.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-02 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 32 | Each | 3.03 | 96.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-02 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 920 | Each | 1.5 | 1380 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 400 | NULL | 24.09 | 9636 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 408 | Each | 17.3 | 7058.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 4 | Each | 355.81 | 1423.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | Not on List | NULL | 4 | Each | 50.98 | 203.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 4 | Each | 279.41 | 1117.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 3 | Each | 126.04 | 378.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 59.45 | 59.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 13.08 | 13.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16164-001025 | 16164 | 2019-04-18 13:19 | Section 4 | Material | NULL | Not on List | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 426 - Robins Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16736-001025 | 16736 | 2019-05-01 14:21 | Section 4 | Material | Not on List | Not on List | 30 | EA | 5.33 | 159.9 | NULL | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4B - Structures (Culverts) 4B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16736-001025 | 16736 | 2019-05-01 14:21 | Section 4 | Material | Not on List | Not on List | 30 | EA | 0.15 | 4.5 | NULL | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4B - Structures (Culverts) 4B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16325-001025 | 16325 | 2019-04-24 14:39 | Section 4 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 520 | Each | 3.52 | 1830.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16325-001025 | 16325 | 2019-04-24 14:39 | Section 4 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 600 | Each | 1.5 | 900 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16325-001025 | 16325 | 2019-04-24 14:39 | Section 4 | Material | NULL | Concrete Kerbs 125x150x914 BN Straight (753034) | 100 | Each | 3.03 | 303 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16325-001025 | 16325 | 2019-04-24 14:39 | Section 4 | Material | NULL | NULL | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16325-001025 | 16325 | 2019-04-24 14:39 | Section 4 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16516-001025 | 16516 | 2019-04-26 15:51 | Section 3 | Material | Not on List | Not on List | 16 | No. | 34.93 | 558.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16516-001025 | 16516 | 2019-04-26 15:51 | Section 3 | Material | Not on List | Not on List | 26 | No. | 182.61 | 4747.86 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16516-001025 | 16516 | 2019-04-26 15:51 | Section 3 | Material | Not on List | Not on List | 12 | No. | 38.85 | 466.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16769-001025 | 16769 | 2019-05-02 07:40 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Fixings and Fasteners | 2019-05-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16681-001025 | 16681 | 2019-04-30 17:44 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (General) | 2019-05-01 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16712-001025 | 16712 | 2019-05-01 09:54 | Section 4 | Material | Not on List | Not on List | 1500 | EA | 1.34 | 2010 | Miscellaneous | 2019-05-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16739-001025 | 16739 | 2019-05-01 14:31 | Section 4 | Material | Not on List | Not on List | 6 | EA | 650 | 3900 | Miscellaneous | 2019-05-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16748-001025 | 16748 | 2019-05-01 15:44 | Section 3 | Material | PPE, Small Tools and Consumables | Safety Goal Post System Sgps01 (203013) | 15 | Each | 285 | 4275 | Miscellaneous | 2019-05-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16800-001025 | 16800 | 2019-05-02 10:31 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 750 | 750 | Surveying Consumables | 2019-05-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16814-001025 | 16814 | 2019-05-02 11:48 | Section 2 | Material | Not on List | Not on List | 1 | each | 1861 | 1861 | Tanks and Interceptors | 2019-05-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16805-001025 | 16805 | 2019-05-02 10:41 | Section 3 | Material | Not on List | Not on List | 32 | Units | 38.76 | 1240.32 | Miscellaneous | 2019-05-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16805-001025 | 16805 | 2019-05-02 10:41 | Section 3 | Material | Not on List | Not on List | 4 | Units | 44.38 | 177.52 | Miscellaneous | 2019-05-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16805-001025 | 16805 | 2019-05-02 10:41 | Section 3 | Material | Not on List | Not on List | 8 | Units | 95 | 760 | Miscellaneous | 2019-05-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16831-001025 | 16831 | 2019-05-02 15:52 | Section 4 | Material | Bagged | Not on List | 1 | Pallet | NULL | 0 | Builders Merchants (General) | 2019-05-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1103 - Linear Drainage Channel Systems | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 100 | Each | 35.59 | 3559 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 2 | Each | 38.85 | 77.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 5 | Each | 250.64 | 1253.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5432-00279 | 5432 | 2018-08-21 12:34 | Section 4 | Material | Not on List | Not on List | 230.88 | m2 | 66.73 | 15406.62 | Not Sure | 2018-10-08 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20709-001025 | 20709 | 2019-07-12 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-07-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20735-001025 | 20735 | 2019-07-15 06:58 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5432-00279 | 5432 | 2018-08-21 12:34 | Section 4 | Material | Not on List | Not on List | 189.365 | m2 | 66.57 | 12606.03 | Not Sure | 2018-10-08 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20746-001025 | 20746 | 2019-07-15 09:27 | Core | Material | Not on List | Not on List | 1 | NULL | 1350 | 1350 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20658-001025 | 20658 | 2019-07-12 07:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2019-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19393-001025 | 19393 | 2019-06-19 15:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 74 | 74 | Miscellaneous | 2019-06-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20640-001025 | 20640 | 2019-07-11 16:37 | Core | Material | NULL | NULL | 1 | Each | 92.4 | 92.4 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 4 | ea | 178.81 | 715 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 10 | ea | 43.05 | 431 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 1 | ea | 288 | 288 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5437-00281 | 5437 | 2018-08-21 13:45 | Section 4 | Material | Plastic Drainage | P/Pipe 100Mm X 100Mtr Linflex 100 | 30 | Each | 175 | 5250 | Plastic Drainage | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 6 | ea | 16.16 | 97 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 6 | ea | 6.83 | 41 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 6 | ea | 2.49 | 15 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20762-001025 | 20762 | 2019-07-15 11:51 | Core | Material | Not on List | Not on List | 5 | ea | 76 | 380 | Office Supplies | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20764-001025 | 20764 | 2019-07-15 13:01 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20778-001025 | 20778 | 2019-07-15 14:50 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20783-001025 | 20783 | 2019-07-15 15:21 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5439-00282 | 5439 | 2018-08-21 13:48 | Section 4 | Material | Not on List | Not on List | 645 | Each | 4.43 | 2857.35 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19997-001025 | 19997 | 2019-07-01 11:28 | Core | Material | NULL | NULL | 25 | Each | 36.94 | 923.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20789-001025 | 20789 | 2019-07-15 15:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20791-001025 | 20791 | 2019-07-15 16:30 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20798-001025 | 20798 | 2019-07-15 17:28 | Section 3 | Material | Not on List | Not on List | 500 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-23 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 55 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 65 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 10 | Each | 10.5 | 105 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-5439-00282 | 5439 | 2018-08-21 13:48 | Section 4 | Material | Not on List | Not on List | 1344 | Each | 3.4 | 4569.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Twinwall | Polyipipe 150mm Ridgidrain Bend 90deg (878001) | 10 | Each | 8.25 | 83 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Bend 45deg (878000) | 10 | Each | 8.25 | 83 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 38 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 38 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 20 | Each | 0.91 | 18 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-20801-001025 | 20801 | 2019-07-15 14:39 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 10 | Each | 1.98 | 20 | Plastic Drainage | 2019-07-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-5142-0070 | 5142 | 2018-08-15 11:34 | Section 3 | Material | Concrete Drainage | Not on List | 35 | Each | 16.49 | 577.15 | Concrete Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5439-00282 | 5439 | 2018-08-21 13:48 | Section 4 | Material | NULL | NULL | 5 | Each | 30 | 150 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20787-001025 | 20787 | 2019-07-15 15:11 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20817-001025 | 20817 | 2019-07-16 09:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | NULL | NULL | 0 | PPE | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-20823-001025 | 20823 | 2019-07-16 10:25 | Section 2 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 3000 | Each | 0.37 | 1110 | Builders Merchants (General) | 2019-07-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20823-001025 | 20823 | 2019-07-16 10:25 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196 | Builders Merchants (General) | 2019-07-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20823-001025 | 20823 | 2019-07-16 10:25 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 80 | Each | 3.56 | 285 | Builders Merchants (General) | 2019-07-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20823-001025 | 20823 | 2019-07-16 10:25 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-07-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20828-001025 | 20828 | 2019-07-16 11:14 | Core | Material | PPE, Small Tools and Consumables | Not on List | 215.18 | each | 1 | 215 | Miscellaneous | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20834-001025 | 20834 | 2019-07-16 12:14 | Section 5 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-18 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5459-00296 | 5459 | 2018-08-21 12:27 | Section 4 | Material | Plastic Drainage | Not on List | 16 | Each | 45.37 | 725.92 | Plastic Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20405-001025 | 20405 | 2019-07-08 13:51 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 0.9 | 900 | Timber Products | 2019-07-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 5 | EA | 173.24 | 866.2 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | Concrete Drainage | Not on List | 1 | Each | 122.16 | 122.16 | Concrete Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 1 | EA | 39.41 | 39.41 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 1 | EA | 39.41 | 39.41 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 9 | EA | 24.3 | 218.7 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 14 | EA | 18.4 | 257.6 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 3 | EA | 3.13 | 9.39 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 14 | EA | 6.05 | 84.7 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20620-001025 | 20620 | 2019-07-11 13:39 | Section 4 | Material | Not on List | Not on List | 1 | EA | 22.8 | 22.8 | Ductile Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20857-001025 | 20857 | 2019-07-16 16:25 | Section 3 | Material | Not on List | Not on List | 2000 | No | NULL | 0 | Builders Merchants (General) | 2019-07-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | Concrete Drainage | Not on List | 1 | Each | 91.61 | 91.61 | Concrete Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20869-001025 | 20869 | 2019-07-16 17:35 | Section 5 | Material | Not on List | Not on List | 50 | number | NULL | 0 | Builders Merchants (General) | 2019-07-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20836-001025 | 20836 | 2019-07-16 12:22 | Section 3 | Material | Not on List | Not on List | 1 | ea | 6076.8 | 6076.8 | Miscellaneous | 2019-07-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20838-001025 | 20838 | 2019-07-16 12:53 | Section 6 | Material | Aggregate | Class 1A | 5000 | Tonnes | 12.5 | 62500 | Aggregate | 2019-07-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20891-001025 | 20891 | 2019-07-17 09:27 | Section 4 | Material | Not on List | Not on List | 1 | Number | 8950 | 8950 | Surveying Consumables | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-20897-001025 | 20897 | 2019-07-17 10:09 | Core | Material | Not on List | Not on List | 1 | number | 42 | 42 | Surveying Consumables | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20897-001025 | 20897 | 2019-07-17 10:09 | Core | Material | Not on List | Not on List | 10 | packs | 15 | 150 | Surveying Consumables | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20897-001025 | 20897 | 2019-07-17 10:09 | Core | Material | Not on List | Not on List | 10 | packs | 15 | 150 | Surveying Consumables | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | Concrete Drainage | Not on List | 3 | Each | 79.28 | 237.84 | Concrete Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20897-001025 | 20897 | 2019-07-17 10:09 | Core | Material | Not on List | Not on List | 10 | packs | 15 | 150 | Surveying Consumables | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20899-001025 | 20899 | 2019-07-17 10:29 | Section 4 | Material | Not on List | Not on List | 600 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22138-001025 | 22138 | 2019-08-12 09:35 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 3194.21 | 3194 | Miscellaneous | 2019-08-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22140-001025 | 22140 | 2019-08-12 10:12 | Core | Material | Not on List | Not on List | 1 | NULL | 6620.59 | 6621 | Professional Services | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-5824-00514 | 5824 | 2018-08-30 16:28 | Section 4 | Material | Not on List | Not on List | 60 | Each | 4.55 | 273 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22143-001025 | 22143 | 2019-08-12 10:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | 10 | 40 | Surveying Consumables | 2019-08-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22143-001025 | 22143 | 2019-08-12 10:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 0.1 | 1 | Surveying Consumables | 2019-08-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Timber | Not on List | 100 | EA | 32.95 | 3295 | Timber Products | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Timber | Not on List | 150 | EA | 7.23 | 1084.5 | Timber Products | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Timber | Not on List | 86.4 | MT | 1.85 | 159.84 | Timber Products | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Bagged | Not on List | 1 | BG | 6 | 6 | Builders Merchants (General) | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Bagged | Not on List | 1 | BG | 6.5 | 6.5 | Builders Merchants (General) | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21997-001025 | 21997 | 2019-08-08 11:59 | Section 5 | Material | Not on List | Not on List | 1 | SM | 459.96 | 459.96 | Concrete Accessories | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5829-00519 | 5829 | 2018-08-30 15:45 | Section 4 | Material | Not on List | Not on List | 14.311 | Tonnes | 538 | 7699.32 | Rebar and Mesh | 2018-09-13 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21944-001025 | 21944 | 2019-08-07 13:14 | Section 3 | Material | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 32 | Each | 3.03 | 96.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22057-001025 | 22057 | 2019-08-09 10:06 | Core | Material | Not on List | Not on List | 1 | SM | 334.43 | 334.43 | Not Sure | 2019-08-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22058-001025 | 22058 | 2019-08-09 10:09 | Core | Material | Not on List | Not on List | 1 | SM | 500 | 500 | Miscellaneous | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22112-001025 | 22112 | 2019-08-11 14:13 | Section 5 | Material | Twinwall | Not on List | 1 | SM | 734.66 | 734.66 | Plastic Drainage | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5829-00519 | 5829 | 2018-08-30 15:45 | Section 4 | Material | Not on List | Not on List | 14.313 | Tonnes | 538 | 7700.39 | Rebar and Mesh | 2018-09-13 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN20 - Bar Hill Junction West Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22158-001025 | 22158 | 2019-08-12 12:24 | Section 2 | Material | Not on List | Not on List | 1 | no | NULL | 0 | Miscellaneous | 2019-08-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 215 | Each | 3.52 | 756.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Not on List | 6 | Each | 13.78 | 82.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 3 | Each | 10.35 | 31.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 3 | Each | 10.35 | 31.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 3 | Each | 5.44 | 16.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 3 | Each | 5.44 | 16.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22042-001025 | 22042 | 2019-08-08 20:09 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 7 | Each | 5.44 | 38.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5829-00519 | 5829 | 2018-08-30 15:45 | Section 4 | Material | Not on List | Not on List | 14.311 | Tonnes | 538 | 7699.32 | Rebar and Mesh | 2018-09-13 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22124-001025 | 22124 | 2019-08-12 08:00 | Section 6 | Material | Timber | Not on List | 21 | NULL | 8.31 | 174.51 | Timber Products | 2019-08-12 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22124-001025 | 22124 | 2019-08-12 08:00 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 15.45 | 15.45 | Timber Products | 2019-08-12 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22124-001025 | 22124 | 2019-08-12 08:00 | Section 6 | Material | Timber | Not on List | 100 | NULL | 0.95 | 95 | Timber Products | 2019-08-12 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22007-001025 | 22007 | 2019-08-08 14:10 | Core | Material | Not on List | Not on List | 1 | SM | 2548.56 | 2548.56 | Training | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22044-001025 | 22044 | 2019-08-09 07:09 | Core | Material | Not on List | Not on List | 1 | each | 7741.44 | 7741.44 | Miscellaneous | 2019-08-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22011-001025 | 22011 | 2019-08-08 14:44 | Section 4 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 1440 | Each | 1.5 | 2160 | Miscellaneous | 2019-08-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22170-001025 | 22170 | 2019-08-12 09:40 | Section 5 | Material | Not on List | Not on List | 1 | EACH | 1360.42 | 1360 | Miscellaneous | 2019-08-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21999-001025 | 21999 | 2019-08-08 11:10 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 16 | ea | 5.43 | 86.88 | Miscellaneous | 2019-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 16 | ea | 5.43 | 86.88 | Miscellaneous | 2019-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5829-00519 | 5829 | 2018-08-30 15:45 | Section 4 | Material | Not on List | Not on List | 14.313 | Tonnes | 538 | 7700.39 | Rebar and Mesh | 2018-09-13 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN21 - Bar Hill Junction East Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | Kerbs | Not on List | 12 | ea | 5.43 | 65.16 | Miscellaneous | 2019-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | Kerbs | Not on List | 16 | ea | 13.39 | 214.24 | Miscellaneous | 2019-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21834-001025 | 21834 | 2019-08-06 10:06 | Section 4 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21940-001025 | 21940 | 2019-08-07 12:16 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2232.8 | Each | 1 | 2232.8 | PPE | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21870-001025 | 21870 | 2019-08-06 15:21 | Core | Material | PPE, Small Tools and Consumables | Not on List | 519.28 | Each | 1 | 519.28 | Small Tools (Consumables) | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21838-001025 | 21838 | 2019-08-06 10:44 | Core | Material | NULL | NULL | 4 | Each | 5.5 | 22 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5829-00519 | 5829 | 2018-08-30 15:45 | Section 4 | Material | Not on List | Not on List | 40 | coils | 43.05 | 1722 | Rebar and Mesh | 2018-09-05 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22183-001025 | 22183 | 2019-08-12 17:37 | Section 3 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Stores - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22183-001025 | 22183 | 2019-08-12 17:37 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Stores - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22183-001025 | 22183 | 2019-08-12 17:37 | Section 3 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Concrete Drainage | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Stores - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22194-001025 | 22194 | 2019-08-13 08:02 | Section 2 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 4000 | Each | 0.37 | 1480 | Builders Merchants (General) | 2019-08-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21990-001025 | 21990 | 2019-08-08 10:41 | Section 5 | Material | Saint Gobain Castings | 600x600x150 D400 Inter Ax Manhole Cover (766618) | 30 | Each | 94.87 | 2846.1 | Builders Merchants (General) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21990-001025 | 21990 | 2019-08-08 10:41 | Section 5 | Material | Concrete Drainage | Not on List | 75 | EACH | 23.92 | 1794 | Builders Merchants (General) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21990-001025 | 21990 | 2019-08-08 10:41 | Section 5 | Material | Concrete Drainage | Not on List | 25 | EACH | 9.2 | 230 | Builders Merchants (General) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21990-001025 | 21990 | 2019-08-08 10:41 | Section 5 | Material | Concrete Drainage | Not on List | 6 | EACH | 33.38 | 200.28 | Builders Merchants (General) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5841-00529 | 5841 | 2018-08-31 07:50 | Section 4 | Material | Not on List | Not on List | 14 | Each | 16.55 | 231.7 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21990-001025 | 21990 | 2019-08-08 10:41 | Section 5 | Material | Concrete Drainage | Not on List | 8 | EACH | 24.85 | 198.8 | Builders Merchants (General) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22084-001025 | 22084 | 2019-08-09 14:48 | Section 4 | Material | NULL | NULL | 5 | Each | 33.55 | 167.75 | NULL | NULL | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Rocker (890351) | 3 | Each | 253.14 | 759.42 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Not on List | 32 | No | 2.9 | 92.8 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5841-00529 | 5841 | 2018-08-31 07:50 | Section 4 | Material | Not on List | Not on List | 2 | Each | 33.35 | 66.7 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 4 | Each | 43.16 | 172.64 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 8 | Each | 35.52 | 284.16 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 47.04 | 470.4 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22146-001025 | 22146 | 2019-08-12 11:03 | Section 2 | Material | Concrete Drainage | Not on List | 10 | NULL | NULL | 0 | Concrete Drainage | 2019-08-23 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22211-001025 | 22211 | 2019-08-13 10:56 | Core | Material | Not on List | Not on List | 6 | Items | 264 | 1584 | Miscellaneous | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22204-001025 | 22204 | 2019-08-13 09:25 | Section 1 | Material | Concrete Drainage | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-08-26 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-22204-001025 | 22204 | 2019-08-13 09:25 | Section 1 | Material | Concrete Drainage | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-08-26 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-22161-001025 | 22161 | 2019-08-12 14:16 | Section 5 | Material | Not on List | Not on List | 1 | SUM | 58212.47 | 58212.47 | Professional Services | 2019-08-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5841-00529 | 5841 | 2018-08-31 07:50 | Section 4 | Material | Not on List | Not on List | 4 | Each | 21.6 | 86.4 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22172-001025 | 22172 | 2019-08-12 09:21 | Section 4 | Material | Not on List | Not on List | 40 | Each | 10.85 | 434 | Builders Merchants (General) | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22205-001025 | 22205 | 2019-08-13 09:56 | Core | Material | NULL | NULL | 1 | Each | 410 | 410 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22220-001025 | 22220 | 2019-08-13 12:53 | Section 1 | Material | Not on List | Not on List | 6 | boxes | NULL | 0 | Miscellaneous | 2019-08-15 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-5841-00529 | 5841 | 2018-08-31 07:50 | Section 4 | Material | Not on List | Not on List | 2 | Each | 97.14 | 194.28 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22237-001025 | 22237 | 2019-08-13 16:32 | Section 2 | Material | Not on List | Not on List | 90 | single unit | 0 | 0 | Fixings and Fasteners | 2019-08-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-22222-001025 | 22222 | 2019-08-13 13:33 | Section 2 | Material | Concrete Drainage | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-09-09 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22257-001025 | 22257 | 2019-08-14 08:52 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Rebar and Mesh | 2019-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22257-001025 | 22257 | 2019-08-14 08:52 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Rebar and Mesh | 2019-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22257-001025 | 22257 | 2019-08-14 08:52 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Rebar and Mesh | 2019-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5846-00543 | 5846 | 2018-08-31 09:30 | Section 4 | Material | Concrete Drainage | 1200Mm Concrete Pipe | 1 | Each | 459.88 | 459.88 | Concrete Drainage | 2018-09-05 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22134-001025 | 22134 | 2019-08-12 09:29 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22123-001025 | 22123 | 2019-08-12 08:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 827.35 | Each | 1 | 827.35 | Miscellaneous | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22262-001025 | 22262 | 2019-08-14 09:21 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21864-001025 | 21864 | 2019-08-06 14:25 | Core | Material | NULL | NULL | 3 | Each | 34 | 102 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22267-001025 | 22267 | 2019-08-14 08:32 | Core | Material | Not on List | Not on List | 8 | packs | NULL | 0 | Surveying Consumables | 2019-08-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22066-001025 | 22066 | 2019-08-09 11:32 | Section 4 | Material | Not on List | Not on List | 7 | Each | 35 | 245 | Miscellaneous | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22279-001025 | 22279 | 2019-08-14 12:56 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Plastic Drainage | P/Pipe 150Mmx150Mm 45Deg Ridgidrain Junc | 200 | Each | 14.4 | 2880 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22271-001025 | 22271 | 2019-08-14 10:44 | Section 5 | Material | Aggregate | Type 1 | 1182.06 | Tonnes | 21.65 | 25591.6 | Aggregate | 2019-08-14 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22289-001025 | 22289 | 2019-08-14 16:15 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-08-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Plastic Drainage | P/Pipe 150Mm Ridgidrain Dbl Skt Coupler | 100 | Each | 1.84 | 184 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22278-001025 | 22278 | 2019-08-14 13:04 | Core | Material | NULL | NULL | 1 | Each | 393.42 | 393.42 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22268-001025 | 22268 | 2019-08-14 10:46 | Section 4 | Material | NULL | NULL | 1 | Each | 4041.7 | 4041.7 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22312-001025 | 22312 | 2019-08-15 09:31 | Core | Material | Not on List | Not on List | 1 | ea | 850 | 850 | Training | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22312-001025 | 22312 | 2019-08-15 09:31 | Core | Material | Not on List | Not on List | 1 | ea | 580 | 580 | Training | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22201-001025 | 22201 | 2019-08-13 09:12 | Section 4 | Material | Not on List | Not on List | 100 | Each | 33.73 | 3373 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22201-001025 | 22201 | 2019-08-13 09:12 | Section 4 | Material | Not on List | Not on List | 40 | Each | 2.47 | 98.8 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22201-001025 | 22201 | 2019-08-13 09:12 | Section 4 | Material | NULL | Not on List | 50 | Each | 189 | 9450 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22209-001025 | 22209 | 2019-08-13 10:34 | Section 6 | Material | Timber | Not on List | 1 | NULL | NULL | 0 | Timber Products | 2019-08-13 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | NULL | Buyer - Closed | NULL | Yes - Approve | Req - S6 Buyers
MREQ-22209-001025 | 22209 | 2019-08-13 10:34 | Section 6 | Material | Timber | Not on List | 1 | NULL | NULL | 0 | Timber Products | 2019-08-13 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | NULL | Yes - Approve | Req - S6 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Not on List | Not on List | 100 | Each | 7.64 | 764 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 100 | Each | 1.98 | 198 | Plastic Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 80 | Each | 2.97 | 237.6 | Plastic Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 36 | Each | 10.5 | 378 | Plastic Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Twinwall | Not on List | 3 | NULL | NULL | 0 | Plastic Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 80 | Each | 3.56 | 284.8 | Concrete Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22291-001025 | 22291 | 2019-08-14 15:05 | Section 2 | Material | Saint Gobain Castings | Not on List | 40 | NULL | NULL | 0 | Concrete Drainage | 2019-08-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 360 | Each | 4.59 | 1652 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 40 | Each | 3.52 | 141 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 60 | Each | 3.03 | 182 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Not on List | Not on List | 100 | Each | 10.5 | 1050 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 4 | Each | 11.94 | 48 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 4 | Each | 11.94 | 48 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 4 | Each | 10.08 | 40 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 4 | Each | 7.68 | 31 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 4 | Each | 7.68 | 31 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 12 | Each | 115.78 | 1389 | Miscellaneous | 2019-08-20 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22331-001025 | 22331 | 2019-08-15 10:36 | Section 6 | Material | Not on List | Not on List | 200 | each | NULL | 0 | Fixings and Fasteners | 2019-08-20 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Not on List | Not on List | 1 | Each | 64.7 | 64.7 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5921-00566 | 5921 | 2018-09-03 10:47 | Section 4 | Material | Plastic Drainage | P/Pipe 150Mm Ridgidrain Seal | 1000 | Each | 0.85 | 850 | Plastic Drainage | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22212-001025 | 22212 | 2019-08-13 11:09 | Section 4 | Material | Not on List | Not on List | 1 | Each | 35717.31 | 35717.31 | Concrete Accessories | 2019-08-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20978-001025 | 20978 | 2019-07-18 09:20 | Section 4 | Material | Waste Management | Not on List | 1 | Each | 1199.88 | 1199.88 | Fuel | 2019-08-16 | RVP 420 - A14 Eastbound - Opposite Crematorium | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Rigidrain P/E 450Mm Dia Incl Coup/Sealia | 6 | no | 126.66 | 759.96 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5925-00577 | 5925 | 2018-09-03 11:31 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 7.1 | 7100 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22392-001025 | 22392 | 2019-08-16 12:16 | Core | Material | Not on List | Not on List | 4 | Days | 649 | 2596 | Miscellaneous | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-9989-001025 | 9989 | 2018-12-05 12:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 150 | EAch | 5 | 750 | PPE | 2018-12-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10243-001025 | 10243 | 2018-12-11 15:19 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 197.25 | 197.25 | Small Tools (Consumables) | 2018-12-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10087-001025 | 10087 | 2018-12-07 09:45 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 650 | 1300 | Concrete Accessories | 2018-12-12 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10087-001025 | 10087 | 2018-12-07 09:45 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 350 | 350 | Concrete Accessories | 2018-12-12 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 15 | Each | 35.52 | 533 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 2 | Each | 36.62 | 73 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10224-001025 | 10224 | 2018-12-11 11:19 | Section 3 | Material | Not on List | Not on List | 1 | ea | 250 | 250 | Not Sure | 2018-12-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10224-001025 | 10224 | 2018-12-11 11:19 | Section 3 | Material | Not on List | Not on List | 3 | ea | 179.2 | 537.6 | Not Sure | 2018-12-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 100 | Each | 29.28 | 2928 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 20 | Each | 15.43 | 308.6 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 7 | Each | 27.56 | 192.92 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 1 | Each | 27.56 | 27.56 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 1 | Each | 27.56 | 27.56 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 7 | Each | 4.67 | 32.69 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | NULL | NULL | 1 | Each | 115 | 115 | Concrete Drainage | 2018-12-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9957-001025 | 9957 | 2018-12-04 15:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 68.75 | 68.75 | Damage Charges | 2018-12-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9966-001025 | 9966 | 2018-12-04 16:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 175.93 | 175.93 | Damage Charges | 2018-12-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9604-001025 | 9604 | 2018-11-26 10:03 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 440.02 | 440.02 | Electrical | 2018-11-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5451-00291 | 5451 | 2018-08-21 16:03 | Section 4 | Material | Not on List | Not on List | 3 | Pallet | NULL | 0 | Concrete Accessories | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10161-001025 | 10161 | 2018-12-10 10:18 | Section 3 | Material | Not on List | Not on List | 1 | EA | 50 | 50 | Miscellaneous | 2018-12-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10161-001025 | 10161 | 2018-12-10 10:18 | Section 3 | Material | Not on List | Not on List | 1 | EA | 23.5 | 23.5 | Miscellaneous | 2018-12-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10318-001025 | 10318 | 2018-12-13 09:00 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10265-001025 | 10265 | 2018-12-12 09:02 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327.4 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10327-001025 | 10327 | 2018-12-13 10:27 | Section 3 | Material | Not on List | Not on List | 3 | No. | 75 | 225 | Miscellaneous | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10099-001025 | 10099 | 2018-12-07 12:05 | Section 4 | Material | Not on List | Not on List | 50 | Each | 27.5 | 1375 | Fixings and Fasteners | 2018-12-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411 | Concrete Drainage | 2019-01-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 15 | Each | 35.52 | 533 | Concrete Drainage | 2019-01-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5451-00291 | 5451 | 2018-08-21 16:03 | Section 4 | Material | Not on List | Not on List | 6 | Bag | NULL | 0 | Concrete Accessories | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 30 | Each | 67.9 | 2037 | Concrete Drainage | 2019-01-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10281-001025 | 10281 | 2018-12-12 14:28 | Section 4 | Material | Not on List | Not on List | 1 | Each | 580.43 | 580.43 | Damage Charges | 2018-12-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10341-001025 | 10341 | 2018-12-13 14:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 200 | number | NULL | 0 | Surveying Consumables | 2018-12-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10327-001025 | 10327 | 2018-12-13 10:27 | Section 3 | Material | Not on List | Not on List | 3 | No. | 75 | 225 | Miscellaneous | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-5451-00291 | 5451 | 2018-08-21 16:03 | Section 4 | Material | Not on List | Not on List | 4 | Coil | NULL | 0 | Rebar and Mesh | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10318-001025 | 10318 | 2018-12-13 09:00 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 26.55 | 265.5 | Miscellaneous | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10330-001025 | 10330 | 2018-12-13 11:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 300 | number | 7.1 | 2130 | Surveying Consumables | 2018-12-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10351-001025 | 10351 | 2018-12-13 15:42 | Section 3 | Material | Not on List | Not on List | 11 | NULL | 7.96 | 88 | Small Tools (Consumables) | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10351-001025 | 10351 | 2018-12-13 15:42 | Section 3 | Material | Not on List | Not on List | 6 | NULL | 6.11 | 37 | Small Tools (Consumables) | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9947-001025 | 9947 | 2018-12-04 10:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 850 | 850 | Surveying Consumables | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9947-001025 | 9947 | 2018-12-04 10:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 395 | 395 | Surveying Consumables | 2018-12-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10353-001025 | 10353 | 2018-12-13 16:23 | Section 4 | Material | Not on List | Not on List | 36.42 | tonnes | NULL | 0 | Reinforcement | 2019-01-08 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5451-00291 | 5451 | 2018-08-21 16:03 | Section 4 | Material | Not on List | Not on List | 8 | Coil | NULL | 0 | Rebar and Mesh | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10331-001025 | 10331 | 2018-12-13 11:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 108.55 | 108.55 | Miscellaneous | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10351-001025 | 10351 | 2018-12-13 15:42 | Section 3 | Material | Not on List | Not on List | 11 | ea | 7.96 | 87.56 | Small Tools (Consumables) | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10351-001025 | 10351 | 2018-12-13 15:42 | Section 3 | Material | Not on List | Not on List | 6 | ea | 6.11 | 36.66 | Small Tools (Consumables) | 2018-12-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 15 | Each | 35.52 | 532.8 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10292-001025 | 10292 | 2018-12-12 15:56 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 2 | Each | 36.62 | 73.24 | Concrete Drainage | 2018-12-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5347-00243 | 5347 | 2018-08-20 11:52 | Section 4 | Material | Not on List | Not on List | 100 | Each | 20.5 | 0 | Not Sure | 2018-08-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10365-001025 | 10365 | 2018-12-14 10:19 | Section 3 | Material | Not on List | Not on List | 13 | no. of schedule components | NULL | 0 | Fixings and Fasteners | 2019-01-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10087-001025 | 10087 | 2018-12-07 09:45 | Section 4 | Material | Not on List | Not on List | 2 | Each | 650 | 1300 | Concrete Accessories | 2018-12-12 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10087-001025 | 10087 | 2018-12-07 09:45 | Section 4 | Material | Not on List | Not on List | 1 | Each | 350 | 350 | Concrete Accessories | 2018-12-12 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ9885 | 9885 | 2018-12-03 14:19 | Section 4 | Material | Not on List | Not on List | 50.105 | tonne | 538 | 26956.49 | Rebar and Mesh | 2019-01-08 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ9885 | 9885 | 2018-12-03 14:19 | Section 4 | Material | NULL | Not on List | 36.424 | tonne | 538 | 19596.11 | Rebar and Mesh | 2019-01-08 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411.2 | Concrete Drainage | 2019-01-08 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 15 | Each | 35.52 | 532.8 | Concrete Drainage | 2019-01-08 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10328-001025 | 10328 | 2018-12-13 10:22 | Section 4 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 30 | Each | 67.9 | 2037 | Concrete Drainage | 2019-01-08 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10389-001025 | 10389 | 2018-12-14 14:37 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Fixings and Fasteners | 2018-12-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1801 - Structural Steelwork | Requestor - Buyers Pass Back | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10389-001025 | 10389 | 2018-12-14 14:37 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Fixings and Fasteners | 2018-12-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1801 - Structural Steelwork | Requestor - Buyers Pass Back | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10389-001025 | 10389 | 2018-12-14 14:37 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Fixings and Fasteners | 2018-12-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1801 - Structural Steelwork | Requestor - Buyers Pass Back | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10404-001025 | 10404 | 2018-12-17 08:34 | Section 4 | Material | Not on List | Not on List | 20 | Weeks | 550 | 11000 | Miscellaneous | 2018-12-18 | RVP 417 - 1339631 - Girton Compound Huntingdon Rd A1307 | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10345-001025 | 10345 | 2018-12-13 14:35 | Section 4 | Material | Not on List | Not on List | 10 | number cans (750mL) | NULL | 0 | Concrete Accessories | 2019-01-02 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10345-001025 | 10345 | 2018-12-13 14:35 | Section 4 | Material | Not on List | Not on List | 2 | packs (400ml tins) | 132 | 264 | Concrete Accessories | 2019-01-02 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10314-001025 | 10314 | 2018-12-13 08:42 | Section 4 | Material | Not on List | Not on List | 3 | Each | 32 | 96 | Surveying Consumables | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10314-001025 | 10314 | 2018-12-13 08:42 | Section 4 | Material | Not on List | Not on List | 3 | Each | 35 | 105 | Surveying Consumables | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10333-001025 | 10333 | 2018-12-13 10:08 | Section 4 | Material | Not on List | Not on List | 2 | Number | 49.24 | 98.48 | Miscellaneous | 2018-12-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10341-001025 | 10341 | 2018-12-13 14:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 200 | number | NULL | 0 | Surveying Consumables | 2018-12-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 50 | Each | 0.44 | 22 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 50 | Each | 0.5 | 25 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 50 | Eack | 0.43 | 21.5 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 1 | Each | 43 | 43 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.12 | 24 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10356-001025 | 10356 | 2018-12-13 16:29 | Section 4 | Material | Not on List | Not on List | 10 | 15kg Coil | 46.5 | 465 | Not Sure | 2019-01-03 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10339-001025 | 10339 | 2018-12-13 12:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4717.86 | 4717.86 | Miscellaneous | 2018-12-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10429-001025 | 10429 | 2018-12-17 16:01 | Section 4 | Material | Not on List | Not on List | 20 | Box | NULL | 0 | Miscellaneous | 2018-12-20 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10430-001025 | 10430 | 2018-12-17 16:11 | Section 4 | Material | Not on List | Not on List | 20 | Box | 7.94 | 158.8 | Miscellaneous | 2018-12-20 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10433-001025 | 10433 | 2018-12-17 16:21 | Section 4 | Material | Not on List | Not on List | 20 | EA | 110.51 | 2210.2 | Miscellaneous | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10334-001025 | 10334 | 2018-12-13 12:23 | Section 4 | Material | Not on List | Not on List | 1 | Each | 911.26 | 911.26 | Miscellaneous | 2018-12-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10464-001025 | 10464 | 2018-12-18 16:41 | Section 3 | Material | Not on List | Not on List | 1 | Each | 56 | 56 | Damage Charges | 2018-12-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10375-001025 | 10375 | 2018-12-14 12:18 | Section 4 | Material | Not on List | Not on List | 20 | Each | 17.56 | 351.2 | Not Sure | 2019-01-03 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10455-001025 | 10455 | 2018-12-18 11:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 5.97 | 119.4 | Janitorial | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10455-001025 | 10455 | 2018-12-18 11:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 40.92 | 818.4 | Janitorial | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10455-001025 | 10455 | 2018-12-18 11:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 125 | Each | 0.77 | 96.25 | Miscellaneous | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10464-001025 | 10464 | 2018-12-18 16:41 | Section 3 | Material | Not on List | Not on List | 1 | Each | 56 | 56 | Damage Charges | 2018-12-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10477-001025 | 10477 | 2018-12-19 08:56 | Section 3 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 2000 | Each | 0.37 | 740 | Miscellaneous | 2019-01-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10418-001025 | 10418 | 2018-12-17 11:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 140.74 | 140.74 | Damage Charges | 2018-12-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1601 - Piling and attendances | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10421-001025 | 10421 | 2018-12-17 12:23 | Section 4 | Material | Not on List | Not on List | 1 | Each | 362.26 | 362.26 | Miscellaneous | 2018-12-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10490-001025 | 10490 | 2018-12-19 16:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 200 | NULL | 2.18 | 436 | Miscellaneous | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10481-001025 | 10481 | 2018-12-19 09:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2306.68 | Each | 1 | 2306.68 | PPE | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10065-001025 | 10065 | 2018-12-06 15:28 | Section 4 | Material | NULL | Not on List | 12 | no | 4.13 | 49.56 | Builders Merchants (General) | 2018-12-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10065-001025 | 10065 | 2018-12-06 15:28 | Section 4 | Material | NULL | Not on List | 30 | no | 0.6 | 18 | Builders Merchants (General) | 2018-12-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10065-001025 | 10065 | 2018-12-06 15:28 | Section 4 | Material | Not on List | Not on List | 75 | m2 | NULL | 0 | Builders Merchants (General) | 2018-12-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 40 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 20 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 240 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 47 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 47 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 1430 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | Kerbs | Not on List | 26 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 80 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10508-001025 | 10508 | 2018-12-20 13:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 700 | Each | 6.35 | 4445 | PPE | 2019-01-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 35 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 45 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5192-00118 | 5192 | 2018-08-16 08:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1071 | 0 | Damage Charges | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 90 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 112 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 75 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 91 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5775-00466 | 5775 | 2018-08-29 18:50 | Section 3 | Material | Not on List | Not on List | 1 | ea | 727.08 | 727.08 | Miscellaneous | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14847-001025 | 14847 | 2019-03-28 10:17 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14853-001025 | 14853 | 2019-03-28 10:40 | Section 2 | Material | Kerbs | Not on List | 500 | metres | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5775-00466 | 5775 | 2018-08-29 18:50 | Section 3 | Material | Not on List | Not on List | 1 | ea | 80.8 | 80.8 | Miscellaneous | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14609-001025 | 14609 | 2019-03-25 15:10 | Section 3 | Material | NULL | Not on List | 6 | No | 179.55 | 1077.3 | Builders Merchants (General) | 2019-03-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14874-001025 | 14874 | 2019-03-28 14:36 | Section 2 | Material | Not on List | Not on List | 5 | Number | NULL | 0 | Concrete Accessories | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN32 - Brampton Equestrian Underpass | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14630-001025 | 14630 | 2019-03-26 07:24 | Section 4 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5780-00469 | 5780 | 2018-08-29 23:10 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 174.27 | 174.27 | Janitorial | 2018-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14856-001025 | 14856 | 2019-03-28 11:04 | Section 2 | Material | Not on List | Not on List | 0.465 | Tonnes | 538 | 250.17 | NULL | 2019-04-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14857-001025 | 14857 | 2019-03-28 11:29 | Section 2 | Material | Not on List | Not on List | 12500 | NULL | NULL | 0 | Miscellaneous | 2019-03-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5780-00469 | 5780 | 2018-08-29 23:10 | Section 3 | Material | Not on List | Not on List | 5 | ea | 10.45 | 52.25 | Miscellaneous | 2018-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14764-001025 | 14764 | 2019-03-27 13:16 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 1178.1 | 23562 | Concrete Accessories | 2019-04-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14734-001025 | 14734 | 2019-03-27 08:40 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 235 | 470 | Concrete Drainage | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14734-001025 | 14734 | 2019-03-27 08:40 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 39.5 | 237 | Concrete Drainage | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14838-001025 | 14838 | 2019-03-28 09:28 | Section 4 | Material | NULL | Building Sand Bulk Bag (938155) | 5 | Each | 32.74 | 163.7 | Builders Merchants (General) | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14865-001025 | 14865 | 2019-03-28 12:49 | Section 4 | Material | NULL | NULL | 100 | NULL | 4.97 | 497 | NULL | NULL | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | Janitorial | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5849-00544 | 5849 | 2018-08-31 10:07 | Section 3 | Material | Not on List | Not on List | 100 | ea | 0.48 | 48 | Fixings and Fasteners | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | Janitorial | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Broom 11" Stiff Bass Bracketed 48" X 15/16" Handle (502216) | 12 | Each | 7.14 | 86 | Miscellaneous | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EACH | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EACH | NULL | 0 | PPE | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EACH | NULL | 0 | Miscellaneous | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 24 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | PACKS | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | Aggregate | Not on List | 2 | EACH | NULL | 0 | Aggregate | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | NULL | 0 | Aggregate | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14935-001025 | 14935 | 2019-03-29 09:10 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | NULL | 0 | Small Tools (Consumables) | 2019-04-04 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14678-001025 | 14678 | 2019-03-26 14:41 | Section 5 | Material | Not on List | Not on List | 15 | number | 3.62 | 54.3 | Builders Merchants (General) | 2019-03-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14678-001025 | 14678 | 2019-03-26 14:41 | Section 5 | Material | Not on List | Not on List | 4 | NUMBER | 2.5 | 10 | Builders Merchants (General) | 2019-03-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14678-001025 | 14678 | 2019-03-26 14:41 | Section 5 | Material | Not on List | Not on List | 20 | number | 10.56 | 211.2 | Builders Merchants (General) | 2019-03-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14678-001025 | 14678 | 2019-03-26 14:41 | Section 5 | Material | Not on List | Not on List | 20 | number | 42.2 | 844 | Builders Merchants (General) | 2019-03-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14827-001025 | 14827 | 2019-03-28 07:40 | Section 2 | Material | NULL | Not on List | 270 | metres | NULL | 0 | Ductile Drainage | 2019-04-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14827-001025 | 14827 | 2019-03-28 07:40 | Section 2 | Material | NULL | Not on List | 16 | Number | NULL | 0 | Ductile Drainage | 2019-04-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14827-001025 | 14827 | 2019-03-28 07:40 | Section 2 | Material | NULL | Not on List | 2 | Number | NULL | 0 | Ductile Drainage | 2019-04-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14763-001025 | 14763 | 2019-03-27 13:04 | Section 4 | Material | Not on List | Not on List | 200 | NULL | 9.32 | 1864 | Builders Merchants (General) | 2019-03-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14859-001025 | 14859 | 2019-03-28 12:14 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 25.13 | 150.78 | Plastic Drainage | 2019-04-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5822-00513 | 5822 | 2018-08-30 15:50 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 400 | meters | 1160 | 464000 | Miscellaneous | 2018-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14867-001025 | 14867 | 2019-03-28 13:14 | Section 4 | Material | Not on List | Not on List | 100 | NULL | 16.72 | 1672 | Concrete Accessories | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14867-001025 | 14867 | 2019-03-28 13:14 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 139 | 139 | Concrete Accessories | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 128 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 1 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 4 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 8 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 2 | Each | 11.94 | 23.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 2 | Each | 11.94 | 23.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5113-0043 | 5113 | 2018-08-15 07:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 748.47 | 0 | Small Tools (Consumables) | 2018-08-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Transition Kerbs 125x255 (947297) | 3 | Each | 10.08 | 30.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Transition Kerbs 125x255 (947297) | 4 | Each | 10.08 | 40.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 12 | Metres | 6 | 72 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14706-001025 | 14706 | 2019-03-26 16:34 | Section 2 | Material | NULL | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 32 | Metres | 6 | 192 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14784-001025 | 14784 | 2019-03-27 15:58 | Section 2 | Material | NULL | Not on List | 34 | rolls | 177 | 6018 | Geotextiles | 2019-04-02 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 607 - Compaction | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14784-001025 | 14784 | 2019-03-27 15:58 | Section 2 | Material | NULL | Not on List | 40 | rolls | 181 | 7240 | Geotextiles | 2019-04-02 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 607 - Compaction | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14784-001025 | 14784 | 2019-03-27 15:58 | Section 2 | Material | NULL | Not on List | 45 | rolls | 188 | 8460 | Geotextiles | 2019-04-02 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 607 - Compaction | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14784-001025 | 14784 | 2019-03-27 15:58 | Section 2 | Material | NULL | Not on List | 4 | rolls | 215 | 860 | Geotextiles | 2019-04-02 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 607 - Compaction | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14784-001025 | 14784 | 2019-03-27 15:58 | Section 2 | Material | NULL | Not on List | 10 | rolls | 417 | 4170 | Geotextiles | 2019-04-02 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 607 - Compaction | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5840-00527 | 5840 | 2018-08-31 07:11 | Section 3 | Material | Not on List | Not on List | 20 | NULL | 9 | 180 | Fixings and Fasteners | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14939-001025 | 14939 | 2019-03-29 12:17 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | 2 | 425 | 850 | Small Tools (Consumables) | 2019-04-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14790-001025 | 14790 | 2019-03-27 16:38 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 4603 | 4603 | Concrete Accessories | 2019-04-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14677-001025 | 14677 | 2019-03-26 14:14 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 6956 | 20868 | Surveying Consumables | 2019-03-29 | NULL | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14693-001025 | 14693 | 2019-03-26 15:52 | Section 4 | Material | Not on List | Not on List | 200 | NULL | 0.15 | 30 | Surveying Consumables | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5840-00527 | 5840 | 2018-08-31 07:11 | Section 3 | Material | Not on List | Not on List | 4 | NULL | 18.84 | 75.36 | Miscellaneous | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | CL3B - Structures (Culverts) 3B | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14693-001025 | 14693 | 2019-03-26 15:52 | Section 4 | Material | Not on List | Not on List | 5 | NULL | 36 | 180 | Surveying Consumables | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14693-001025 | 14693 | 2019-03-26 15:52 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 18.5 | 55.5 | Surveying Consumables | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14997-001025 | 14997 | 2019-04-01 08:12 | Section 2 | Material | Not on List | Not on List | 2 | number | 65 | 130 | Small Tools (Consumables) | 2019-04-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14997-001025 | 14997 | 2019-04-01 08:12 | Section 2 | Material | Not on List | Not on List | 2 | number | 61.5 | 123 | Small Tools (Consumables) | 2019-04-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14892-001025 | 14892 | 2019-03-28 15:28 | Section 4 | Material | Not on List | Not on List | 2 | coil | 261.07 | 522.14 | Miscellaneous | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14892-001025 | 14892 | 2019-03-28 15:28 | Section 4 | Material | Not on List | Not on List | 25 | NULL | 8.08 | 202 | Miscellaneous | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14892-001025 | 14892 | 2019-03-28 15:28 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 11.83 | 236.6 | Miscellaneous | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14892-001025 | 14892 | 2019-03-28 15:28 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 22.85 | 22.85 | Miscellaneous | 2019-04-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15019-001025 | 15019 | 2019-04-01 10:01 | Section 2 | Material | Kerbs | Not on List | 4 | No. | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-02 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15019-001025 | 15019 | 2019-04-01 10:01 | Section 2 | Material | Kerbs | Not on List | 4 | No. | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-02 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14863-001025 | 14863 | 2019-03-28 12:41 | Section 3 | Material | Aggregate | Not on List | 880 | m3 | 47.05 | 41404 | Aggregate | 2019-04-02 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14886-001025 | 14886 | 2019-03-28 16:02 | Section 3 | Material | Not on List | Not on List | 1 | number | 44100 | 44100 | Miscellaneous | 2019-03-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-14926-001025 | 14926 | 2019-03-29 09:48 | Section 3 | Material | Not on List | Not on List | 390 | unit | 50 | 19500 | Ductile Drainage | 2019-04-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14926-001025 | 14926 | 2019-03-29 09:48 | Section 3 | Material | Not on List | Not on List | 1 | unit | 60 | 60 | Ductile Drainage | 2019-04-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14926-001025 | 14926 | 2019-03-29 09:48 | Section 3 | Material | Not on List | Not on List | 1 | unit | 60 | 60 | Ductile Drainage | 2019-04-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14926-001025 | 14926 | 2019-03-29 09:48 | Section 3 | Material | Not on List | Not on List | 4 | unit | 650 | 2600 | Ductile Drainage | 2019-04-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14787-001025 | 14787 | 2019-03-27 15:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 82.5 | 82.5 | Miscellaneous | 2019-04-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14968-001025 | 14968 | 2019-03-29 16:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 966.06 | 966.06 | Small Tools (Consumables) | 2019-04-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14968-001025 | 14968 | 2019-03-29 16:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 146.58 | 146.58 | Janitorial | 2019-04-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14968-001025 | 14968 | 2019-03-29 16:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 270.9 | 270.9 | PPE | 2019-04-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14955-001025 | 14955 | 2019-03-29 14:41 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain Bend 45deg (878085) | 10 | Each | 48.86 | 488.6 | Plastic Drainage | 2019-04-01 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14955-001025 | 14955 | 2019-03-29 14:41 | Section 2 | Material | NULL | Polypipe 225mm Ridgidrain Bend 45deg (878031) | 10 | Each | 27.62 | 276.2 | Plastic Drainage | 2019-04-01 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14940-001025 | 14940 | 2019-03-29 11:27 | Section 3 | Material | Not on List | Not on List | 196 | tube | 4.55 | 891.8 | Ductile Drainage | 2019-04-11 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14887-001025 | 14887 | 2019-03-28 16:07 | Section 2 | Material | Not on List | Not on List | 1 | number | 65520 | 65520 | Miscellaneous | 2019-03-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15024-001025 | 15024 | 2019-04-01 10:47 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 40 cubic yard | 1 | Each | 370 | 370 | Waste (General) | 2019-04-02 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14785-001025 | 14785 | 2019-03-27 16:14 | Section 4 | Material | Not on List | Not on List | 9 | NULL | 1659.85 | 14938.65 | Concrete Accessories | 2019-04-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14785-001025 | 14785 | 2019-03-27 16:14 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Accessories | 2019-04-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14821-001025 | 14821 | 2019-03-27 19:08 | Section 3 | Material | NULL | Not on List | 6 | Rolls | 670 | 4020 | Geotextiles | 2019-04-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15025-001025 | 15025 | 2019-04-01 09:22 | Section 3 | Material | Not on List | Not on List | 25 | Drum | 20.25 | 506.25 | Miscellaneous | 2019-04-02 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15025-001025 | 15025 | 2019-04-01 09:22 | Section 3 | Material | Not on List | Not on List | 10 | Drum | 57.92 | 579.2 | Miscellaneous | 2019-04-02 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14888-001025 | 14888 | 2019-03-28 16:01 | Section 3 | Material | Not on List | Not on List | 1 | See Attached Component List | 4877.9 | 4877.9 | Fixings and Fasteners | 2019-04-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14593-001025 | 14593 | 2019-03-25 11:36 | Section 4 | Material | Not on List | Not on List | 10 | Each | 89.39 | 893.9 | Concrete Drainage | 2019-03-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15071-001025 | 15071 | 2019-04-02 07:31 | Section 1 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 10 | Each | 24.32 | 243 | Timber Products | 2019-04-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | BN33 - Ellington Brook Accommodation Bridge | 1703 - Formwork | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S1 Buyers
MREQ-15077-001025 | 15077 | 2019-04-02 08:09 | Section 2 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Surveying Consumables | 2019-04-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14893-001025 | 14893 | 2019-03-28 17:16 | Section 2 | Material | NULL | Not on List | 100 | metres | NULL | 0 | Geotextiles | 2019-04-01 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 602 - Excavation (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14893-001025 | 14893 | 2019-03-28 17:16 | Section 2 | Material | NULL | Not on List | 100 | metres | NULL | 0 | Geotextiles | 2019-04-01 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15085-001025 | 15085 | 2019-04-02 08:24 | Section 2 | Material | Twinwall | Polypipe Road Gully 450mm x 750mm (573006) | 40 | Each | 15.71 | 628 | Plastic Drainage | 2019-04-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15085-001025 | 15085 | 2019-04-02 08:24 | Section 2 | Material | Twinwall | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2019-04-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15085-001025 | 15085 | 2019-04-02 08:24 | Section 2 | Material | Twinwall | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2019-04-03 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14585-001025 | 14585 | 2019-03-25 09:34 | Section 3 | Material | Not on List | Not on List | 1 | ea | 1519 | 1519 | Professional Services | 2019-04-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25808-001025 | 25808 | 2019-10-28 13:13 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 56 | Each | 6.5 | 364 | Miscellaneous | 2019-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25815-001025 | 25815 | 2019-10-28 15:42 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25791-001025 | 25791 | 2019-10-28 09:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25817-001025 | 25817 | 2019-10-28 15:47 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25734-001025 | 25734 | 2019-10-25 09:45 | Section 2 | Material | Not on List | Not on List | 4 | each | 950 | 3800 | Miscellaneous | 2019-10-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25798-001025 | 25798 | 2019-10-28 12:08 | Section 5 | Material | Concrete Drainage | NULL | 1 | SM | 661.5 | 661.5 | Concrete Drainage | 2019-10-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25843-001025 | 25843 | 2019-10-29 10:12 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25845-001025 | 25845 | 2019-10-29 10:22 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25753-001025 | 25753 | 2019-10-25 13:18 | Section 4 | Material | Kerbs | Not on List | 8 | Each | 7.52 | 60.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25753-001025 | 25753 | 2019-10-25 13:18 | Section 4 | Material | Kerbs | Not on List | 8 | Each | 7.52 | 60.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25753-001025 | 25753 | 2019-10-25 13:18 | Section 4 | Material | Kerbs | Not on List | 18 | Each | 11.68 | 210.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25316-001025 | 25316 | 2019-10-17 10:16 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7079-001013 | 7079 | 2018-09-27 09:10 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1929 | 1929 | Timber Products | 2018-10-01 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25863-001025 | 25863 | 2019-10-29 14:44 | Section 5 | Material | Hazardous Waste | Not on List | 1 | NULL | 352 | 352 | Waste (General) | 2019-11-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 300 | Each | 7.1 | 2130 | Surveying Consumables | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 400 | Each | 8.28 | 3312 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 560 | Each | 21.01 | 11765.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 3 | Each | 151.94 | 455.82 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 2 | Each | 36.67 | 73.34 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5753 | 5753 | 2018-08-29 13:27 | Section 4 | Material | Not on List | Not on List | 10000 | NULL | NULL | 0 | Concrete Accessories | 2018-09-05 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 1 | Each | 36.67 | 36.67 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 593 | Each | 22.84 | 13544.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 30 | Each | 35.47 | 1064.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 1607 | Each | 24.09 | 38712.63 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 6 | Each | 359.42 | 2156.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 1 | Each | 282.24 | 282.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 6 | Each | 282.24 | 1693.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25698-001025 | 25698 | 2019-10-24 14:38 | Section 4 | Material | NULL | NULL | 8 | Each | 30 | 240 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25833-001025 | 25833 | 2019-10-29 09:07 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18724-001025 | 18724 | 2019-06-07 09:11 | Core | Material | Not on List | Not on List | 1 | NULL | 100 | 100 | Miscellaneous | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25502-001025 | 25502 | 2019-10-21 16:41 | Section 3 | Material | Aggregate | Type 1 | 400 | Tonnes | 21.65 | 8660 | Aggregate | 2019-10-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25914-001025 | 25914 | 2019-10-30 14:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-25922-001025 | 25922 | 2019-10-30 14:33 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25821-001025 | 25821 | 2019-10-28 16:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 1.92 | 19.2 | Small Tools (Consumables) | 2019-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25859-001025 | 25859 | 2019-10-29 14:11 | Section 4 | Material | Not on List | Not on List | 2 | Each | 19.71 | 39.42 | Builders Merchants (General) | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25859-001025 | 25859 | 2019-10-29 14:11 | Section 4 | Material | Not on List | Not on List | 2 | Each | 2.86 | 5.72 | Builders Merchants (General) | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25846-001025 | 25846 | 2019-10-29 10:29 | Core | Material | PPE, Small Tools and Consumables | Not on List | 375.78 | each | 1 | 375.78 | Small Tools (Consumables) | 2019-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25655-001025 | 25655 | 2019-10-23 20:26 | Section 4 | Material | Not on List | Not on List | 2 | Each | 1965 | 3930 | Miscellaneous | 2019-10-25 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25167-001025 | 25167 | 2019-10-16 09:24 | Core | Material | NULL | NULL | 20 | Each | 17.78 | 355.6 | NULL | 2019-10-21 | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25927-001025 | 25927 | 2019-10-30 15:54 | Core | Material | Not on List | Not on List | 10 | Packs of 100 | NULL | 0 | Surveying Consumables | 2019-11-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25927-001025 | 25927 | 2019-10-30 15:54 | Core | Material | Not on List | Not on List | 10 | Packs of 100 | NULL | 0 | Surveying Consumables | 2019-11-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7150-001020 | 7150 | 2018-09-28 12:06 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Perf (346346) | 67 | Each | 34.08 | 2283.36 | Plastic Drainage | 2018-10-02 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25935-001025 | 25935 | 2019-10-30 16:32 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-25568-001025 | 25568 | 2019-10-22 14:53 | Section 2 | Material | Not on List | Not on List | 65 | ea | 28 | 1820 | Concrete Accessories | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25568-001025 | 25568 | 2019-10-22 14:53 | Section 2 | Material | Not on List | Not on List | 54 | ea | 28 | 1512 | Concrete Accessories | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7150-001020 | 7150 | 2018-09-28 12:06 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Perf (346341) | 42 | Each | 24.82 | 1042.44 | Plastic Drainage | 2018-10-02 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25568-001025 | 25568 | 2019-10-22 14:53 | Section 2 | Material | Not on List | Not on List | 12 | ea | 28 | 336 | Concrete Accessories | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25568-001025 | 25568 | 2019-10-22 14:53 | Section 2 | Material | Not on List | Not on List | 43 | ea | 28 | 1204 | Concrete Accessories | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25568-001025 | 25568 | 2019-10-22 14:53 | Section 2 | Material | Not on List | Not on List | 30 | ea | 4.79 | 143.7 | Concrete Accessories | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25754-001025 | 25754 | 2019-10-25 13:39 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25796-001025 | 25796 | 2019-10-28 12:05 | Core | Material | NULL | NULL | 10000 | Each | 1 | 10000 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25953-001025 | 25953 | 2019-10-31 08:40 | Section 1 | Material | Not on List | Not on List | 1 | No. | 3430.14 | 3430 | Miscellaneous | 2019-11-11 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1807 - Modification of existing gantries | Stores - Closed | Yes - Approve | NULL | Req - S1 Buyers
MREQ-25953-001025 | 25953 | 2019-10-31 08:40 | Section 1 | Material | Not on List | Not on List | 1 | No. | 2927.95 | 2928 | Miscellaneous | 2019-11-11 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1807 - Modification of existing gantries | Stores - Closed | Yes - Approve | NULL | Req - S1 Buyers
MREQ-25681-001025 | 25681 | 2019-10-24 12:38 | Core | Material | Not on List | NULL | 1 | SM | 2085 | 2085 | Not Sure | 2019-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25901-001025 | 25901 | 2019-10-30 08:21 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 180 | Each | 4.59 | 826.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-01 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25901-001025 | 25901 | 2019-10-30 08:21 | Section 2 | Material | Kerbs | Not on List | 54 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-01 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25860-001025 | 25860 | 2019-10-29 14:18 | Section 4 | Material | Not on List | Not on List | 30 | Each | 25 | 750 | Fixings and Fasteners | 2019-11-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25664-001025 | 25664 | 2019-10-24 08:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 3.96 | 79.2 | Small Tools (Consumables) | 2019-11-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25962-001025 | 25962 | 2019-10-31 11:33 | Core | Material | Not on List | Not on List | 1 | Number | 595 | 595 | Surveying Consumables | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25962-001025 | 25962 | 2019-10-31 11:33 | Core | Material | Not on List | Not on List | 1 | Number | 390 | 390 | Surveying Consumables | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25962-001025 | 25962 | 2019-10-31 11:33 | Core | Material | Not on List | Not on List | 1 | Number | 390 | 390 | Surveying Consumables | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25962-001025 | 25962 | 2019-10-31 11:33 | Core | Material | Not on List | Not on List | 1 | Number | 595 | 595 | Surveying Consumables | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25962-001025 | 25962 | 2019-10-31 11:33 | Core | Material | Not on List | Not on List | 1 | Number | 425 | 425 | Surveying Consumables | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25964-001025 | 25964 | 2019-10-31 12:10 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25669-001025 | 25669 | 2019-10-24 10:00 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | 20kg Bag | 7.9 | 237 | Miscellaneous | 2019-11-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25966-001025 | 25966 | 2019-10-31 12:39 | Section 4 | Material | Combined Drainage | Kerb Drain 480 Access Unit (947299) | 7 | Each | 34.55 | 242 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25966-001025 | 25966 | 2019-10-31 12:39 | Section 4 | Material | Combined Drainage | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25934-001025 | 25934 | 2019-10-30 16:30 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25628-001025 | 25628 | 2019-10-23 12:57 | Core | Material | Not on List | NULL | 1 | SM | 1362 | 1362 | Miscellaneous | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25933-001025 | 25933 | 2019-10-30 16:22 | Section 5 | Material | Not on List | NULL | 1 | SM | 581 | 581 | Builders Merchants (General) | 2019-11-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25970-001025 | 25970 | 2019-10-31 14:02 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 14272.4 | 14272 | Miscellaneous | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2704 - Works on behalf of Designers | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-24758-001025 | 24758 | 2019-10-08 09:11 | Section 4 | Material | Not on List | Not on List | 1 | Each | 5182 | 5182 | Flow Control | 2019-11-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24758-001025 | 24758 | 2019-10-08 09:11 | Section 4 | Material | NULL | Not on List | 1 | Each | 240 | 240 | Flow Control | 2019-11-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25850-001025 | 25850 | 2019-10-29 10:18 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 7 | Each | 67.9 | 475.3 | Concrete Drainage | 2019-10-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25850-001025 | 25850 | 2019-10-29 10:18 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 8 | Each | 35.52 | 284.16 | Concrete Drainage | 2019-10-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25850-001025 | 25850 | 2019-10-29 10:18 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 6 | Each | 47.04 | 282.24 | Concrete Drainage | 2019-10-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7019-00752 | 7019 | 2018-09-26 11:46 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 12 | Each | 115.78 | 1389.36 | Geotextiles | 2018-10-01 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25850-001025 | 25850 | 2019-10-29 10:18 | Section 2 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 6 | Each | 81.73 | 490.38 | Builders Merchants (General) | 2019-10-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25941-001025 | 25941 | 2019-10-30 16:57 | Section 2 | Material | Timber | Not on List | 5 | No | 10.57 | 52.85 | Timber Products | 2019-11-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25941-001025 | 25941 | 2019-10-30 16:57 | Section 2 | Material | Timber | Not on List | 3 | No | 3.6 | 10.8 | Timber Products | 2019-11-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25941-001025 | 25941 | 2019-10-30 16:57 | Section 2 | Material | Timber | Not on List | 2 | No | 12 | 24 | Timber Products | 2019-11-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25941-001025 | 25941 | 2019-10-30 16:57 | Section 2 | Material | Not on List | Not on List | 1 | ea | 27.6 | 27.6 | Miscellaneous | 2019-11-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25950-001025 | 25950 | 2019-10-31 08:08 | Section 5 | Material | Not on List | NULL | 1 | SM | 631.82 | 631.82 | Miscellaneous | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25960-001025 | 25960 | 2019-10-31 11:06 | Section 5 | Material | Not on List | Not on List | 250 | m cube | 73.31 | 18327.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-04 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25865-001025 | 25865 | 2019-10-29 14:52 | Section 4 | Material | Not on List | Not on List | 14 | Each | 439.64 | 6154.96 | Rebar and Mesh | 2019-11-01 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25921-001025 | 25921 | 2019-10-30 14:05 | Section 5 | Material | NULL | NULL | 137.12 | Each | 1 | 137.12 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25921-001025 | 25921 | 2019-10-30 14:05 | Section 5 | Material | NULL | NULL | 372.8 | Each | 1 | 372.8 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7211-001020 | 7211 | 2018-10-01 11:36 | Section 3 | Material | NULL | Not on List | 300 | EA | 2.75 | 825 | Timber Products | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25884-001025 | 25884 | 2019-10-29 17:40 | Section 4 | Material | Not on List | Not on List | 22 | Each | 126.49 | 2782.78 | Plastic Drainage | 2019-11-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26005-001025 | 26005 | 2019-11-01 08:41 | Core | Material | NULL | NULL | 748.31 | Each | 1 | 748.31 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26005-001025 | 26005 | 2019-11-01 08:41 | Core | Material | NULL | NULL | 532.32 | Each | 1 | 532.32 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26005-001025 | 26005 | 2019-11-01 08:41 | Core | Material | NULL | NULL | 337.2 | Each | 1 | 337.2 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26032-001025 | 26032 | 2019-11-01 14:10 | Section 4 | Material | Not on List | Not on List | 1 | No. | 8183.1 | 8183 | Miscellaneous | 2019-11-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-26042-001025 | 26042 | 2019-11-01 14:36 | Section 2 | Material | Bagged | Not on List | 3 | NULL | NULL | 0 | Ready Mixed Concrete | 2019-11-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26042-001025 | 26042 | 2019-11-01 14:36 | Section 2 | Material | Bagged | Not on List | 3 | NULL | NULL | 0 | Ready Mixed Concrete | 2019-11-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26042-001025 | 26042 | 2019-11-01 14:36 | Section 2 | Material | Bagged | Not on List | 3 | NULL | NULL | 0 | Ready Mixed Concrete | 2019-11-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26042-001025 | 26042 | 2019-11-01 14:36 | Section 2 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Accessories | 2019-11-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26042-001025 | 26042 | 2019-11-01 14:36 | Section 2 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Accessories | 2019-11-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26048-001025 | 26048 | 2019-11-01 15:42 | Section 3 | Material | Bagged | Not on List | 100 | NULL | NULL | 0 | Aggregate | 2019-11-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 2701 - Accommodation works | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26048-001025 | 26048 | 2019-11-01 15:42 | Section 3 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Aggregate | 2019-11-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 2701 - Accommodation works | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26004-001025 | 26004 | 2019-11-01 08:45 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 2 | Each | 48.86 | 97.72 | Plastic Drainage | 2019-11-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26082-001025 | 26082 | 2019-11-04 08:15 | Section 2 | Material | Not on List | Not on List | 41 | Each | 13 | 533 | Miscellaneous | 2019-11-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1504 - Technology Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25620-001025 | 25620 | 2019-10-23 10:20 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25918-001025 | 25918 | 2019-10-30 14:29 | Core | Material | Not on List | NULL | 6 | EA | 44 | 264 | Not Sure | 2019-11-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26087-001025 | 26087 | 2019-11-04 09:08 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Fixings and Fasteners | 2019-11-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26087-001025 | 26087 | 2019-11-04 09:08 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Fixings and Fasteners | 2019-11-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25956-001025 | 25956 | 2019-10-31 08:57 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26104-001025 | 26104 | 2019-11-04 11:23 | Section 6 | Material | Not on List | Not on List | 5 | Boxes | NULL | 0 | Miscellaneous | 2019-11-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25955-001025 | 25955 | 2019-10-31 08:58 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 41.93 | 167.72 | Small Tools (Consumables) | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25955-001025 | 25955 | 2019-10-31 08:58 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | 58.3 | 174.9 | Small Tools (Consumables) | 2019-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25974-001025 | 25974 | 2019-10-31 15:35 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 40 cubic yard | 1 | Each | 250 | 250 | Waste (General) | 2019-11-04 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25932-001025 | 25932 | 2019-10-30 16:17 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2541.6 | each | 1 | 2541.6 | PPE | 2019-11-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26112-001025 | 26112 | 2019-11-04 15:01 | Section 4 | Material | Not on List | Not on List | 20 | Each | 50.5 | 1010 | Builders Merchants (General) | 2019-11-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26135-001025 | 26135 | 2019-11-04 18:30 | Section 2 | Material | Not on List | Not on List | 5 | NULL | 66 | 330 | Concrete Accessories | 2019-11-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26110-001025 | 26110 | 2019-11-04 14:51 | Section 6 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 5 | Each | 115.78 | 578.9 | Geotextiles | 2019-11-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25882-001025 | 25882 | 2019-10-29 17:33 | Section 4 | Material | Not on List | Not on List | 5 | 20ltr | 56.2 | 281 | Miscellaneous | 2019-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26107-001025 | 26107 | 2019-11-04 14:09 | Section 4 | Material | Not on List | Not on List | 120 | Each | 31.37 | 3764.4 | Ductile Drainage | 2019-11-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26089-001025 | 26089 | 2019-11-04 09:30 | Section 4 | Material | Not on List | Not on List | 10 | Each | 81.12 | 811.2 | Plastic Drainage | 2019-11-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25979-001025 | 25979 | 2019-10-31 16:20 | Core | Material | Not on List | NULL | 1 | SM | 19825.83 | 19825.83 | Miscellaneous | 2019-11-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26008-001025 | 26008 | 2019-11-01 09:42 | Section 4 | Material | Not on List | Not on List | 20 | Each | 4.97 | 99.4 | Builders Merchants (General) | 2019-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26008-001025 | 26008 | 2019-11-01 09:42 | Section 4 | Material | Not on List | Not on List | 200 | Each | 4.97 | 994 | Builders Merchants (General) | 2019-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26008-001025 | 26008 | 2019-11-01 09:42 | Section 4 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 400 | Each | 0.35 | 140 | Blocks and Bricks | 2019-11-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-7519-001023 | 7519 | 2018-10-08 14:47 | Section 4 | Material | Not on List | Not on List | 39 | m2 | 11.95 | 466.05 | Not Sure | 2018-10-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7519-001023 | 7519 | 2018-10-08 14:47 | Section 4 | Material | Not on List | Not on List | 15 | Each | 30.68 | 460.2 | Not Sure | 2018-10-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7519-001023 | 7519 | 2018-10-08 14:47 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1659.86 | 1659.86 | Not Sure | 2018-10-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7674-001023 | 7674 | 2018-10-11 13:02 | Section 3 | Material | Not on List | Not on List | 4 | NULL | 51.93 | 207.72 | Small Tools (Consumables) | 2018-10-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-4999-0013 | 4999 | 2018-08-13 16:19 | Section 4 | Material | Not on List | NULL | 1000 | NULL | 2 | 0 | Rebar and Mesh | 2018-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7680-001023 | 7680 | 2018-10-11 14:29 | Section 3 | Material | NULL | Not on List | 300 | EA | 2.75 | 825 | Timber Products | 2018-10-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7765-001023 | 7765 | 2018-10-12 15:55 | Section 3 | Material | NULL | Concrete Kerbs 125x150x914 HB Straight (898181) | 135 | Each | 4.26 | 575.1 | Builders Merchants (General) | 2018-10-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7765-001023 | 7765 | 2018-10-12 15:55 | Section 3 | Material | NULL | Not on List | 3 | each | 20.11 | 60.33 | Builders Merchants (General) | 2018-10-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7765-001023 | 7765 | 2018-10-12 15:55 | Section 3 | Material | NULL | Not on List | 45 | each | 5.69 | 256.05 | Builders Merchants (General) | 2018-10-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | Not on List | Not on List | 40 | No | 15.71 | 628.4 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | Not on List | Not on List | 2 | No | 66.17 | 132.34 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | Not on List | Not on List | 40 | No | 3.9 | 156 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | Not on List | Not on List | 76 | NO | 13.19 | 1002.44 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | Not on List | Not on List | 10 | No | 175 | 1750 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | NULL | Not on List | 42 | No | 72.46 | 3043.32 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7769-001023 | 7769 | 2018-10-12 16:20 | Section 3 | Material | NULL | Not on List | 4 | No | 72.46 | 289.84 | Plastic Drainage | 2018-10-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7799-001023 | 7799 | 2018-10-15 14:46 | Section 3 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2018-10-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 604 - Deposition | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7799-001023 | 7799 | 2018-10-15 14:46 | Section 3 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Geotextiles | 2018-10-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 604 - Deposition | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 8 | NULL | 120.62 | 964.96 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 8 | NULL | 17.45 | 139.6 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 16 | NULL | 9.04 | 144.64 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 70 | NULL | 10.66 | 746.2 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 70 | NULL | 1.84 | 128.8 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 30 | NULL | 14.4 | 432 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 30 | NULL | 7.64 | 229.2 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 39.7 | 794 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 44.11 | 882.2 | Plastic Drainage | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | NULL | 270 | NULL | 0.85 | 229.5 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | NULL | 40 | NULL | 1.86 | 74.4 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7773-001023 | 7773 | 2018-10-12 17:01 | Section 4 | Material | Not on List | NULL | 40 | NULL | 2.75 | 110 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7574-001023 | 7574 | 2018-10-09 14:59 | Section 4 | Material | NULL | Not on List | 12 | Each | 70 | 840 | Ductile Drainage | 2018-10-23 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7814-001023 | 7814 | 2018-10-15 16:58 | Section 4 | Material | Not on List | Not on List | 40 | Panels | NULL | 0 | Not Sure | 2018-11-12 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-7818-001023 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 30 | No | NULL | 0 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7818-001023 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 20 | No | NULL | 0 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7823-001023 | 7823 | 2018-10-16 07:35 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-7767-001023 | 7767 | 2018-10-12 16:06 | Section 4 | Material | NULL | Concrete Kerbs Splayed 45deg 125x255 (898227) | 462 | Each | 4.43 | 2046.66 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7767-001023 | 7767 | 2018-10-12 16:06 | Section 4 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 462 | Each | 3.4 | 1570.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7767-001023 | 7767 | 2018-10-12 16:06 | Section 4 | Material | Not on List | Not on List | 58 | NULL | 12 | 696 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7767-001023 | 7767 | 2018-10-12 16:06 | Section 4 | Material | Not on List | NULL | 1 | NULL | 55 | 55 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7767-001023 | 7767 | 2018-10-12 16:06 | Section 4 | Material | Not on List | NULL | 3 | NULL | 30 | 90 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7757-001023 | 7757 | 2018-10-12 14:39 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 200 | No | 7.1 | 1420 | Surveying Consumables | 2018-10-17 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7800-001023 | 7800 | 2018-10-15 14:52 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 250 | no | 7.1 | 1775 | Small Tools (Consumables) | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7806-001023 | 7806 | 2018-10-15 15:12 | Section 4 | Material | Not on List | Not on List | 15 | NULL | 175 | 2625 | Plastic Drainage | 2018-10-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7806-001023 | 7806 | 2018-10-15 15:12 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 1.21 | 24.2 | Plastic Drainage | 2018-10-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7806-001023 | 7806 | 2018-10-15 15:12 | Section 4 | Material | Not on List | Not on List | 40 | NULL | 14.93 | 597.2 | Plastic Drainage | 2018-10-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7806-001023 | 7806 | 2018-10-15 15:12 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 7.64 | 152.8 | Plastic Drainage | 2018-10-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7806-001023 | 7806 | 2018-10-15 15:12 | Section 4 | Material | Not on List | NULL | 200 | NULL | 0.33 | 66 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7771-001023 | 7771 | 2018-10-12 16:51 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1157.8 | Builders Merchants (General) | 2018-10-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7662-001023 | 7662 | 2018-10-11 08:53 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Bundle | 10 | 200 | Surveying Consumables | 2018-10-12 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7662-001023 | 7662 | 2018-10-11 08:53 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No. | 37 | 37 | Surveying Consumables | 2018-10-12 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5002-0015 | 5002 | 2018-08-13 15:53 | Section 4 | Material | Not on List | NULL | 241 | square meters | 11.21 | 0 | Blocks and Bricks | 2018-08-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7843-001023 | 7843 | 2018-10-16 13:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1166.02 | 1166 | Small Tools (Consumables) | 2018-10-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7716-001023 | 7716 | 2018-10-12 10:44 | Section 4 | Material | NULL | Concrete Kerbs Splayed 45deg 125x255 (898227) | 1000 | Each | 4.43 | 4430 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7770-001023 | 7770 | 2018-10-12 16:37 | Section 4 | Material | Not on List | Not on List | 825 | sqm | 4.34 | 3580.5 | Builders Merchants (General) | 2018-11-05 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7770-001023 | 7770 | 2018-10-12 16:37 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 79 | 316 | Builders Merchants (General) | 2018-11-05 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7770-001023 | 7770 | 2018-10-12 16:37 | Section 4 | Material | Not on List | Not on List | 20 | NULL | 8.5 | 170 | Builders Merchants (General) | 2018-11-05 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7770-001023 | 7770 | 2018-10-12 16:37 | Section 4 | Material | NULL | NULL | 6 | NULL | 5 | 30 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7770-001023 | 7770 | 2018-10-12 16:37 | Section 4 | Material | NULL | NULL | 1 | NULL | 240 | 240 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7858-001023 | 7858 | 2018-10-16 17:00 | Section 4 | Material | NULL | Tensar TX160 4m x 75m (150563) | 15 | Each | 535 | 8025 | Geotextiles | 2018-10-17 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7886-001023 | 7886 | 2018-10-17 09:48 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-10-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-7740-001023 | 7740 | 2018-10-12 12:20 | Section 4 | Material | Not on List | Not on List | 10 | ea | 498 | 4980 | Not Sure | 2018-10-17 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7871-001023 | 7871 | 2018-10-17 07:09 | Section 4 | Material | NULL | Building Sand Bulk Bag (938155) | 5 | Each | 32.74 | 163.7 | Miscellaneous | 2018-10-22 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7796-001023 | 7796 | 2018-10-15 13:53 | Section 3 | Material | Not on List | Not on List | 160 | no. | 10.1 | 1616 | Fixings and Fasteners | 2018-10-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5012-0017 | 5012 | 2018-08-13 17:58 | Section 3 | Material | Aggregate | 6N ( 6P ) | 2000 | Tonnes | 15 | 30000 | NULL | 2018-08-15 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 606 - Import | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 2030 | Each | 1.45 | 2943.5 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs 125x150x914 BN Straight (753034) | 0 | Each | 2.93 | 0 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5223-00140 | 5223 | 2018-08-16 12:16 | Section 4 | Material | Not on List | Not on List | 50 | Each | 22 | 0 | Timber Products | 2018-08-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs 125x150x914 HB Straight (898181) | 100 | Each | 2.93 | 293 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 45 | Each | 3.4 | 153 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs Splayed 45deg 125x255 (898227) | 700 | Each | 4.43 | 3101 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 12 | Each | 11.94 | 143.28 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 12 | Each | 11.94 | 143.28 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Not on List | 3 | Each | 9.72 | 29.16 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Not on List | 3 | Each | 9.72 | 29.16 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Not on List | 0 | Each | NULL | 0 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Not on List | 40 | Each | 5.25 | 210 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7761-001023 | 7761 | 2018-10-12 14:59 | Section 3 | Material | NULL | Not on List | 30 | Each | 5.79 | 173.7 | Builders Merchants (General) | 2018-10-24 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7818 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 30 | No | 34 | 1020 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7818 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 20 | No | 31.37 | 627.4 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7818 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 30 | No | 34 | 1020 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7818 | 7818 | 2018-10-15 16:43 | Section 3 | Material | Not on List | Not on List | 20 | No | 31.37 | 627.4 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7962-001023 | 7962 | 2018-10-18 13:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1680 | 1680 | Not Sure | 2018-11-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5242-00154 | 5242 | 2018-08-16 15:20 | Section 4 | Material | Not on List | Not on List | 40 | NULL | 64 | 2560 | Not Sure | 2018-08-17 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | Not on List | Not on List | 3.352 | tonnes | 538 | 1803.38 | Rebar and Mesh | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | Not on List | Not on List | 3.349 | tonnes | 538 | 1801.76 | Rebar and Mesh | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | Not on List | Not on List | 3.352 | tonnes | 538 | 1803.38 | Rebar and Mesh | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | Not on List | Not on List | 5.686 | tonnes | 538 | 3059.07 | Rebar and Mesh | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | Not on List | Not on List | 3.352 | tonnes | 538 | 1803.38 | Rebar and Mesh | 2018-10-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7920-001023 | 7920 | 2018-10-17 15:24 | Section 4 | Material | NULL | Not on List | 1 | NULL | 125 | 125 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7892-001023 | 7892 | 2018-10-17 11:03 | Section 4 | Material | Misc | NULL | 112 | Bag | 2.9 | 324.8 | Not Sure | 2018-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7924-001023 | 7924 | 2018-10-17 16:25 | Section 4 | Material | Not on List | Not on List | 10 | packs | 168.35 | 1683.5 | Not Sure | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7924-001023 | 7924 | 2018-10-17 16:25 | Section 4 | Material | Not on List | Not on List | 5 | packs | 3.85 | 19.25 | Not Sure | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7924-001023 | 7924 | 2018-10-17 16:25 | Section 4 | Material | Not on List | Not on List | 7 | packs | 11 | 77 | Not Sure | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7960-001023 | 7960 | 2018-10-18 12:32 | Section 4 | Material | Not on List | Not on List | 10 | 25ltr Drum | 57.92 | 579.2 | Concrete Accessories | 2018-10-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7915-001023 | 7915 | 2018-10-17 14:58 | Section 4 | Material | Not on List | Not on List | 10 | rolls | 3.6 | 36 | Not Sure | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7915-001023 | 7915 | 2018-10-17 14:58 | Section 4 | Material | Not on List | Not on List | 300 | no | 1.32 | 396 | NULL | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7915-001023 | 7915 | 2018-10-17 14:58 | Section 4 | Material | NULL | Polypipe 110mm x 50m Ridgiduct Coil Purple (877806) | 6 | Each | 105.04 | 630.24 | Not Sure | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7915-001023 | 7915 | 2018-10-17 14:58 | Section 4 | Material | NULL | Polypipe 110mm x 50m Ridgiduct Coil Orange S/L (877804) | 3 | Each | 105.04 | 315.12 | Not Sure | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7915-001023 | 7915 | 2018-10-17 14:58 | Section 4 | Material | NULL | Polypipe 110mm Ridgiduct Coupler (877674) | 100 | Each | 2.6 | 260 | Not Sure | 2018-10-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7926-001023 | 7926 | 2018-10-17 16:45 | Section 4 | Material | Not on List | Not on List | 13 | 10ltr | 18.84 | 244.92 | Not Sure | 2018-10-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7926-001023 | 7926 | 2018-10-17 16:45 | Section 4 | Material | Not on List | Not on List | 6 | 25ltr | 57.92 | 347.52 | Not Sure | 2018-10-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7925-001023 | 7925 | 2018-10-17 16:18 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 101091.26 | 101091.26 | Not Sure | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7872-001023 | 7872 | 2018-10-17 07:14 | Section 4 | Material | Not on List | Not on List | 100 | Each | 3.46 | 346 | Builders Merchants (General) | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7872-001023 | 7872 | 2018-10-17 07:14 | Section 4 | Material | Not on List | Not on List | 5 | Each | 11.9 | 59.5 | Builders Merchants (General) | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7872-001023 | 7872 | 2018-10-17 07:14 | Section 4 | Material | Not on List | Not on List | 50 | Each | 0.33 | 16.5 | Builders Merchants (General) | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7872-001023 | 7872 | 2018-10-17 07:14 | Section 4 | Material | Not on List | Not on List | 20 | Each | 8.2 | 164 | Builders Merchants (General) | 2018-10-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7948-001023 | 7948 | 2018-10-18 09:25 | Section 3 | Material | Not on List | Not on List | 1 | Visit | 136.69 | 136.69 | Professional Services | 2018-10-19 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7668-001023 | 7668 | 2018-10-11 10:25 | Section 4 | Material | Not on List | Not on List | 8 | U | 31.35 | 250.8 | Concrete Accessories | 2018-10-22 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7668-001023 | 7668 | 2018-10-11 10:25 | Section 4 | Material | NULL | NULL | 1 | NULL | 25 | 25 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7830-001023 | 7830 | 2018-10-16 09:59 | Section 4 | Material | Not on List | Not on List | 600 | m | 29.28 | 17568 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7830-001023 | 7830 | 2018-10-16 09:59 | Section 4 | Material | Not on List | Not on List | 6 | ea | 3.59 | 21.54 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7830-001023 | 7830 | 2018-10-16 09:59 | Section 4 | Material | Not on List | Not on List | 5 | ea | 27.56 | 137.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8019-001023 | 8019 | 2018-10-19 10:24 | Section 3 | Material | NULL | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2018-10-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8019-001023 | 8019 | 2018-10-19 10:24 | Section 3 | Material | Not on List | Not on List | 20 | Rolls | 11.15 | 223 | Concrete Drainage | 2018-10-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7841-001023 | 7841 | 2018-10-16 12:58 | Section 4 | Material | Not on List | Not on List | 10 | 1t Bag | 32.5 | 325 | Builders Merchants (General) | 2018-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7841-001023 | 7841 | 2018-10-16 12:58 | Section 4 | Material | Not on List | Not on List | 112 | Bag | 2.26 | 253.12 | Builders Merchants (General) | 2018-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8015-001023 | 8015 | 2018-10-19 10:13 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 892.78 | 892.78 | Small Tools (Consumables) | 2018-10-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8039-001023 | 8039 | 2018-10-19 14:21 | Section 4 | Material | Not on List | Not on List | 200 | no | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-24 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-7985-001023 | 7985 | 2018-10-19 07:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 5054.62 | 5054.62 | PPE | 2018-10-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7953-001023 | 7953 | 2018-10-18 11:00 | Section 3 | Material | Not on List | Not on List | 40 | Ton | 69 | 2760 | Not Sure | 2018-10-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7807-001023 | 7807 | 2018-10-15 15:57 | Section 3 | Material | Not on List | Not on List | 24 | No | 32.08 | 769.92 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | BN07 - B1043 Offord Road Overbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12156-001025 | 12156 | 2019-02-08 13:01 | Core | Material | Not on List | Not on List | 3 | number packs | 21.45 | 64 | Office Supplies | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | NULL
MREQ-12629-001025 | 12629 | 2019-02-18 12:56 | Core | Material | Not on List | Not on List | 100 | number | 0.4 | 40 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12629-001025 | 12629 | 2019-02-18 12:56 | Core | Material | Not on List | Not on List | 200 | number | 0.22 | 44 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12571-001025 | 12571 | 2019-02-15 13:57 | Section 3 | Material | Not on List | Not on List | 100 | No | 7.1 | 710 | Builders Merchants (General) | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 16 | EA | 14.4 | 230 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 3 | EA | 10.12 | 30 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 2 | EA | 10.12 | 20 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 30 | EA | 5.92 | 178 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12639-001025 | 12639 | 2019-02-18 14:45 | Section 2 | Material | Not on List | Not on List | 52 | Tub | 63.22 | 3287 | Miscellaneous | 2019-02-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | NULL | Not on List | 30 | number | NULL | 0 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 30 | Each | 1.84 | 55.2 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 150 | Each | 0.85 | 127.5 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12549-001025 | 12549 | 2019-02-15 09:38 | Section 2 | Material | NULL | Polypipe 150mm x 150mm 45deg Junction (878010) | 10 | Each | 14.4 | 144 | Plastic Drainage | 2019-02-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12629-001025 | 12629 | 2019-02-18 12:56 | Core | Material | Not on List | Not on List | 100 | number | 0.4 | 40 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12629-001025 | 12629 | 2019-02-18 12:56 | Core | Material | Not on List | Not on List | 200 | number | 0.22 | 44 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12642-001025 | 12642 | 2019-02-18 15:53 | Core | Material | Not on List | Not on List | 1 | number | 6995 | 6995 | Professional Services | 2019-02-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 15 | Each | 175 | 2625 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 15 | Each | 10.5 | 158 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 100 | Each | 23.14 | 2314 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 100 | Each | 3.38 | 338 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 20 | Each | 34.82 | 696 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 3 | Each | 47.04 | 141 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 2 | Each | 67.9 | 136 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 3 | Each | 43.16 | 129 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 3 | Each | 35.52 | 107 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12652-001025 | 12652 | 2019-02-18 16:28 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Miscellaneous | 2019-03-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12582-001025 | 12582 | 2019-02-15 15:00 | Section 3 | Material | Not on List | Not on List | 25 | no | 8.8 | 220 | Fixings and Fasteners | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 16 | EA | 14.4 | 230.4 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 3 | EA | 10.12 | 30.36 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 2 | EA | 10.12 | 20.24 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12518-001025 | 12518 | 2019-02-14 16:55 | Section 3 | Material | Not on List | Not on List | 30 | EA | 5.92 | 177.6 | Miscellaneous | 2019-02-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5355-00246 | 5355 | 2018-08-20 14:08 | Section 3 | Material | Not on List | Not on List | 37 | NULL | NULL | 0 | Office Supplies | 2018-08-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12664-001025 | 12664 | 2019-02-19 08:38 | Core | Material | Not on List | Not on List | 1 | ea | 42200 | 42200 | Office Supplies | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12669-001025 | 12669 | 2019-02-19 09:41 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12242-001025 | 12242 | 2019-02-11 14:13 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1320 | 1320 | Laboratory Equipment / Certification | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12032-001025 | 12032 | 2019-02-07 07:04 | Section 4 | Material | Not on List | Not on List | 1 | Each | 396 | 396 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12687-001025 | 12687 | 2019-02-19 12:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12692-001025 | 12692 | 2019-02-19 12:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 180 | metres | 3.52 | 634 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 6 | Each | 7.68 | 46 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 5 | Each | 7.68 | 38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 903 | metres | 1.5 | 1355 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5539-00352 | 5539 | 2018-08-22 16:19 | Section 3 | Material | Not on List | Not on List | 600 | ea | 0.08 | 48 | Blocks and Bricks | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 30 | metres | 3.03 | 91 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Not on List | 540 | metres | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Not on List | 18 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Not on List | 18 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Not on List | 90 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12693-001025 | 12693 | 2019-02-19 13:48 | Section 2 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 40 | Each | 24.32 | 973 | Timber Products | 2019-02-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12700-001025 | 12700 | 2019-02-19 14:07 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 3 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12700-001025 | 12700 | 2019-02-19 14:07 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | PPE | 2019-02-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12700-001025 | 12700 | 2019-02-19 14:07 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | PPE | 2019-02-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5539-00352 | 5539 | 2018-08-22 16:19 | Section 3 | Material | Not on List | Not on List | 500 | ea | 0.63 | 315 | Blocks and Bricks | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 30 | Each | 3.52 | 106 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 15 | Each | 5.43 | 81 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 10 | Each | 7.68 | 77 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 10 | Each | 7.68 | 77 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12388-001025 | 12388 | 2019-02-13 13:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2623.5 | 2623.5 | Miscellaneous | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12371-001025 | 12371 | 2019-02-13 10:19 | Section 4 | Material | Not on List | Not on List | 1 | Each | 57.02 | 57.02 | Miscellaneous | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1800 x 1000 D/S (528457) | 1 | Each | 155.88 | 156 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5539-00352 | 5539 | 2018-08-22 16:19 | Section 3 | Material | Not on List | Not on List | 10 | ea | 43.05 | 430.5 | Fixings and Fasteners | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1800 x 750 D/S (528456) | 1 | Each | 116.91 | 117 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM 1800 Cover Slab 600x600 Opening (985438) | 1 | Each | 144.04 | 144 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | Not on List | 20 | NULL | NULL | 0 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 7 | Each | 67.9 | 475 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 432 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11944-001025 | 11944 | 2019-02-05 15:29 | Core | Material | Not on List | Not on List | 1 | each | 516 | 516 | Office Supplies | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12718-001025 | 12718 | 2019-02-19 15:35 | Section 2 | Material | Not on List | Not on List | 100 | m | NULL | 0 | Concrete Accessories | 2019-02-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Skip 12 cubic yard | 3 | Each | 195 | 585 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5539-00352 | 5539 | 2018-08-22 16:19 | Section 3 | Material | Not on List | Not on List | 10 | ea | 95.62 | 956.2 | Electrical | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 9 | Each | 370 | 3330 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 2 | Each | 150 | 300 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 2.54 | Each | 115 | 292 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11947-001025 | 11947 | 2019-02-05 15:41 | Core | Material | Not on List | Not on List | 1 | number | 1892.5 | 1892.5 | Office Supplies | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12044-001025 | 12044 | 2019-02-07 10:11 | Core | Material | Not on List | Not on List | 1 | NULL | 226.4 | 226.4 | Laboratory Equipment / Certification | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12499-001025 | 12499 | 2019-02-14 14:50 | Core | Material | PPE, Small Tools and Consumables | Cream Pristine After Work Restore 1 Litre Cartridge (548142) | 1 | Each | 10.45 | 10.45 | Miscellaneous | 2019-02-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12499-001025 | 12499 | 2019-02-14 14:50 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 6 | 6 | Miscellaneous | 2019-02-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12721-001025 | 12721 | 2019-02-19 15:44 | Section 3 | Material | Concrete Drainage | Not on List | 700 | No. | NULL | 0 | Concrete Drainage | 2019-02-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5539-00352 | 5539 | 2018-08-22 16:19 | Section 3 | Material | Not on List | Not on List | 3 | ea | 57.54 | 172.62 | Electrical | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12721-001025 | 12721 | 2019-02-19 15:44 | Section 3 | Material | Concrete Drainage | Not on List | 76 | No. | NULL | 0 | Ductile Drainage | 2019-02-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | Combined Drainage | Not on List | 9 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | Combined Drainage | Not on List | 13 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | Combined Drainage | Not on List | 20 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | Combined Drainage | Not on List | 40 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12734-001025 | 12734 | 2019-02-19 16:49 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 643.99 | 3863.94 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 20.24 | 121.44 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 10.13 | 10.13 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 82.08 | 82.08 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 14.99 | 14.99 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10151-001025 | 10151 | 2018-12-10 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 11.7 | 70.2 | PPE | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12759-001025 | 12759 | 2019-02-20 08:46 | Section 2 | Material | Bagged | Not on List | 20 | Units | NULL | 0 | Builders Merchants (General) | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12759-001025 | 12759 | 2019-02-20 08:46 | Section 2 | Material | Bagged | Not on List | 20 | Bucket | NULL | 0 | Builders Merchants (General) | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12389-001025 | 12389 | 2019-02-13 13:16 | Section 6 | Material | Not on List | Not on List | 1 | sum | 960.8 | 960.8 | Miscellaneous | 2019-02-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-12764-001025 | 12764 | 2019-02-20 09:46 | Section 2 | Material | Not on List | Not on List | 50 | number | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12764-001025 | 12764 | 2019-02-20 09:46 | Section 2 | Material | Not on List | Not on List | 5 | number | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12764-001025 | 12764 | 2019-02-20 09:46 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12764-001025 | 12764 | 2019-02-20 09:46 | Section 2 | Material | Not on List | Not on List | 5 | number | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12764-001025 | 12764 | 2019-02-20 09:46 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 150 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12659-001025 | 12659 | 2019-02-19 07:50 | Section 4 | Material | Not on List | Not on List | 1 | Each | 318.78 | 318.78 | Gas Oil | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 15 | Each | 175 | 2625 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 15 | Each | 10.5 | 157.5 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 100 | Each | 23.14 | 2314 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 100 | Each | 3.38 | 338 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 20 | Each | 34.82 | 696.4 | Plastic Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 3 | Each | 47.04 | 141.12 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 2 | Each | 67.9 | 135.8 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 3 | Each | 43.16 | 129.48 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12643-001025 | 12643 | 2019-02-18 15:51 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 3 | Each | 35.52 | 106.56 | Concrete Drainage | 2019-02-22 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12771-001025 | 12771 | 2019-02-20 11:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No | NULL | 0 | Builders Merchants (General) | 2019-02-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12551-001025 | 12551 | 2019-02-15 10:22 | Section 2 | Material | Aggregate | 6G | 300 | Tonnes | 22 | 6600 | Aggregate | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12722-001025 | 12722 | 2019-02-19 15:43 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 4602.1 | Each | 1 | 4602.1 | Waste (General) | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12722-001025 | 12722 | 2019-02-19 15:43 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 1405 | Each | 1 | 1405 | Waste (General) | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12776-001025 | 12776 | 2019-02-20 13:16 | Section 2 | Material | Not on List | Not on List | 30 | Rolls | NULL | 0 | Concrete Accessories | 2019-02-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12407-001025 | 12407 | 2019-02-13 16:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1062.5 | 1062.5 | Miscellaneous | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18873-001025 | 18873 | 2019-06-10 14:57 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-19 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18605-001025 | 18605 | 2019-06-05 14:55 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 2041.62 | 2041.62 | Miscellaneous | 2019-06-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 250 | no. | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 5 | no. | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 4 | no. | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 9 | no. | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 1 | no. | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18879-001025 | 18879 | 2019-06-11 07:08 | Section 2 | Material | NULL | Not on List | 40 | roll | NULL | 0 | Concrete Drainage | 2019-06-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19031-001025 | 19031 | 2019-06-13 08:29 | Section 2 | Material | Not on List | Not on List | 1.132 | tonnes | NULL | 0 | NULL | 2019-06-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18904-001025 | 18904 | 2019-06-11 12:30 | Core | Material | Not on List | Not on List | 1 | NULL | 1230 | 1230 | Miscellaneous | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18593-001025 | 18593 | 2019-06-05 12:31 | Section 4 | Material | Not on List | Not on List | 1 | Each | 457.78 | 457.78 | Concrete Drainage | 2019-06-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18593-001025 | 18593 | 2019-06-05 12:31 | Section 4 | Material | NULL | Not on List | 1 | Each | 50 | 50 | Concrete Drainage | 2019-06-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19041-001025 | 19041 | 2019-06-13 12:22 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Surveying Consumables | 2019-06-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18444-001025 | 18444 | 2019-06-03 14:15 | Section 4 | Material | Not on List | Not on List | 100 | 5m | 6.3 | 630 | Concrete Accessories | 2019-06-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19033-001025 | 19033 | 2019-06-13 09:01 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 15 | Each | 48.86 | 732.9 | Plastic Drainage | 2019-06-17 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19049-001025 | 19049 | 2019-06-13 14:40 | Core | Material | Not on List | Not on List | 1 | each | 350 | 350 | Training | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19049-001025 | 19049 | 2019-06-13 14:40 | Core | Material | Not on List | Not on List | 1 | each | 200 | 200 | Training | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18893-001025 | 18893 | 2019-06-11 11:07 | Section 4 | Material | Not on List | Not on List | 12 | EA | 47.89 | 574.68 | Electrical | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18893-001025 | 18893 | 2019-06-11 11:07 | Section 4 | Material | Not on List | Not on List | 6 | EA | 62.45 | 374.7 | Electrical | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19030-001025 | 19030 | 2019-06-13 08:29 | Section 4 | Material | Not on List | Not on List | 175 | Each | 16.06 | 2810.5 | Concrete Accessories | 2019-06-25 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18996-001025 | 18996 | 2019-06-12 15:20 | Section 2 | Material | Not on List | Not on List | 24 | Pallets | NULL | 0 | Blocks and Bricks | 2019-06-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19061-001025 | 19061 | 2019-06-13 16:13 | Section 4 | Material | Not on List | Not on List | 10000 | m3 | NULL | 0 | Miscellaneous | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19064-001025 | 19064 | 2019-06-13 16:17 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-06-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19064-001025 | 19064 | 2019-06-13 16:17 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-06-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19064-001025 | 19064 | 2019-06-13 16:17 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-06-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18908-001025 | 18908 | 2019-06-11 13:45 | Section 4 | Material | Not on List | Not on List | 100 | number | 0.56 | 56 | Concrete Accessories | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19000-001025 | 19000 | 2019-06-12 14:53 | Section 4 | Material | Not on List | Not on List | 25 | Each | 10.5 | 262.5 | Builders Merchants (General) | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 36 | Each | 24.99 | 899.64 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 108 | Each | 2.65 | 286.2 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 216 | Each | 2 | 432 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 60 | Each | 37.6 | 2256 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 180 | Each | 7.06 | 1270.8 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 360 | Each | 2.97 | 1069.2 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 110 | Each | 130.26 | 14328.6 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 330 | Each | 18.84 | 6217.2 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 660 | Each | 9.76 | 6441.6 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 60 | Each | 125.94 | 7556.4 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 180 | Each | 18.87 | 3396.6 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 360 | Each | 10.84 | 3902.4 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 60 | Each | 179.74 | 10784.4 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 180 | Each | 38.36 | 6904.8 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 360 | Each | 22.36 | 8049.6 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Bend 45deg (878000) | 100 | Each | 8.25 | 825 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Bend 30deg (877999) | 100 | Each | 8.25 | 825 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 400 | Each | 0.91 | 364 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Bend 11.25deg (878082) | 1 | Each | 52.76 | 52.76 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Bend 22.5deg (878083) | 3 | Each | 52.76 | 158.28 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 20 | Each | 52.76 | 1055.2 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18997-001025 | 18997 | 2019-06-12 14:35 | Section 4 | Material | Not on List | Not on List | 2 | Each | 112.41 | 224.82 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 94 | lengths (3m) | 24.1 | 2265.4 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 96 | lengths (3m) | 5.6 | 537.6 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 8 | lengths (3m) | 3.35 | 26.8 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 8 | lengths (3m) | 2.77 | 22.16 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 72 | lengths (3m) | 4.5 | 324 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 16 | lengths (3m) | 5.01 | 80.16 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 16 | lengths (3m) | 3.67 | 58.72 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 72 | lengths (3m) | 3.91 | 281.52 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 2 | Hun | 32.76 | 65.52 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 2 | Hun | 3.6 | 7.2 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18434-001025 | 18434 | 2019-06-03 11:44 | Section 4 | Material | Not on List | Not on List | 2 | Hun | 0.81 | 1.62 | Fixings and Fasteners | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18843-001025 | 18843 | 2019-06-10 11:51 | Section 3 | Material | Not on List | Not on List | 1 | No | 953.87 | 953.87 | Rebar and Mesh | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19027-001025 | 19027 | 2019-06-13 08:14 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18869-001025 | 18869 | 2019-06-10 16:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 7107.32 | 7107.32 | PPE | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19058-001025 | 19058 | 2019-06-13 16:05 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 8.66 | 34.64 | Small Tools (Consumables) | 2019-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | Not on List | 2 | NULL | 38.08 | 76.16 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | Not on List | 1 | NULL | 63.93 | 63.93 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | Not on List | 6 | NULL | 85.23 | 511.38 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | Not on List | 6 | NULL | 48.02 | 288.12 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 60 | Each | 165.1 | 9906 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | NULL | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 5 | Each | 235 | 1175 | Plastic Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18919-001025 | 18919 | 2019-06-11 14:21 | Section 6 | Material | Concrete Drainage | Not on List | 10 | NULL | 6.76 | 67.6 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17359-001025 | 17359 | 2019-05-14 09:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 150 | Each | 1.31 | 196.5 | Small Tools (Consumables) | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-19034-001025 | 19034 | 2019-06-13 09:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 11.03 | 110.3 | Small Tools (Consumables) | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17507-001025 | 17507 | 2019-05-16 09:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 305.98 | 305.98 | Small Tools (Consumables) | 2019-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18895-001025 | 18895 | 2019-06-11 11:33 | Section 4 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 3 | Each | 165.1 | 495.3 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18895-001025 | 18895 | 2019-06-11 11:33 | Section 4 | Material | Concrete Drainage | CPM 750mm Concrete Rocker (249360) | 4 | Each | 198.12 | 792.48 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18895-001025 | 18895 | 2019-06-11 11:33 | Section 4 | Material | Concrete Drainage | CPM 750mm Concrete Socket (890395) | 2 | Each | 198.12 | 396.24 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18895-001025 | 18895 | 2019-06-11 11:33 | Section 4 | Material | Not on List | Not on List | 2 | Each | 198.12 | 396.24 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19012-001025 | 19012 | 2019-06-12 17:31 | Section 4 | Material | Not on List | Not on List | 2 | Each | 1086.46 | 2172.92 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6797-00751 | 6797 | 2018-09-20 15:46 | Section 3 | Material | Not on List | Not on List | 2000 | NULL | 2 | 4000 | NULL | 2018-09-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19050-001025 | 19050 | 2019-06-13 15:14 | Section 4 | Material | Concrete Drainage | CPM 1800mm Concrete Socket (890407) | 1 | Each | 1086.46 | 1086.46 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19050-001025 | 19050 | 2019-06-13 15:14 | Section 4 | Material | Concrete Drainage | CPM 1800mm Concrete Spigot (890384) | 1 | Each | 1086.46 | 1086.46 | Concrete Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18763-001025 | 18763 | 2019-06-07 12:46 | Section 4 | Material | Not on List | Not on List | 110 | Each | 130.26 | 14328.6 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18763-001025 | 18763 | 2019-06-07 12:46 | Section 4 | Material | Not on List | Not on List | 220 | Each | 18.84 | 4144.8 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18763-001025 | 18763 | 2019-06-07 12:46 | Section 4 | Material | Not on List | Not on List | 550 | Each | 9.76 | 5368 | Plastic Drainage | 2019-06-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6776-00751 | 6776 | 2018-09-20 13:14 | Section 3 | Material | Not on List | Not on List | 50 | NULL | 1.8 | 90 | PPE | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-19125-001025 | 19125 | 2019-06-14 12:13 | Section 3 | Material | Not on List | Not on List | 100 | No | NULL | 0 | Builders Merchants (General) | 2019-06-19 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19141-001025 | 19141 | 2019-06-14 12:54 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Reinforcement | 2019-06-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6776-00751 | 6776 | 2018-09-20 13:14 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1124.61 | 1124.61 | Small Tools (Consumables) | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-19112-001025 | 19112 | 2019-06-14 10:56 | Section 5 | Material | Not on List | Not on List | 10 | rolls | 0 | 0 | Builders Merchants (General) | 2019-06-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19074-001025 | 19074 | 2019-06-13 18:48 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 60 | EA | 46.55 | 2793 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 2 | EA | 50.96 | 101.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 1 | EA | 66.64 | 66.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 2 | EA | 66.64 | 133.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 1 | EA | 128 | 128 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6690-00750 | 6690 | 2018-09-18 16:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1263.47 | 1263.47 | PPE | 2018-09-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 8 | EA | 14.95 | 119.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 1 | EA | 38 | 38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 5 | EA | 38 | 190 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19059-001025 | 19059 | 2019-06-13 15:59 | Section 4 | Material | NULL | Not on List | 1 | EA | 125 | 125 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18687-001025 | 18687 | 2019-06-06 14:38 | Section 4 | Material | Not on List | Not on List | 15 | Each | 15.96 | 239.4 | Small Tools (Consumables) | 2019-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18687-001025 | 18687 | 2019-06-06 14:38 | Section 4 | Material | Not on List | Not on List | 15 | Each | 15.96 | 239.4 | Small Tools (Consumables) | 2019-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6690-00750 | 6690 | 2018-09-18 16:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 473.47 | 473.47 | Janitorial | 2018-09-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19212-001025 | 19212 | 2019-06-17 10:45 | Section 3 | Material | Not on List | Not on List | 6 | No | NULL | 0 | Builders Merchants (General) | 2019-06-19 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19213-001025 | 19213 | 2019-06-17 11:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 160 | NULL | 16.57 | 2651 | Small Tools (Consumables) | 2019-06-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-19215-001025 | 19215 | 2019-06-17 11:21 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19192-001025 | 19192 | 2019-06-17 07:37 | Section 5 | Material | Plastic Drainage | Not on List | NULL | 1 | 645.65 | 0 | NULL | NULL | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19222-001025 | 19222 | 2019-06-17 13:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19225-001025 | 19225 | 2019-06-17 14:08 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19234-001025 | 19234 | 2019-06-17 15:17 | Section 2 | Material | Waste Management | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19040-001025 | 19040 | 2019-06-13 12:02 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 32 | No. | NULL | 0 | Miscellaneous | 2019-06-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19066-001025 | 19066 | 2019-06-13 16:24 | Section 2 | Material | Not on List | Not on List | 11 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19066-001025 | 19066 | 2019-06-13 16:24 | Section 2 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19042-001025 | 19042 | 2019-06-13 08:43 | Section 6 | Material | Concrete Drainage | Not on List | 26 | NULL | 58 | 1508 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19042-001025 | 19042 | 2019-06-13 08:43 | Section 6 | Material | Concrete Drainage | Not on List | 5 | NULL | 6.76 | 33.8 | Concrete Drainage | 2019-06-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19247-001025 | 19247 | 2019-06-17 15:57 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-06-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19268-001025 | 19268 | 2019-06-18 09:07 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-06-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19230-001025 | 19230 | 2019-06-17 14:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | 3.88 | 194 | Small Tools (Consumables) | 2019-06-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19221-001025 | 19221 | 2019-06-17 13:45 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 229.62 | 229.62 | Small Tools (Consumables) | 2019-06-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19124-001025 | 19124 | 2019-06-14 12:01 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Ductile Drainage | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19124-001025 | 19124 | 2019-06-14 12:01 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Ductile Drainage | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19124-001025 | 19124 | 2019-06-14 12:01 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Ductile Drainage | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19124-001025 | 19124 | 2019-06-14 12:01 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Ductile Drainage | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 1 | Each | 39.22 | 39.22 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 1 | Each | 39.22 | 39.22 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16319-001025 | 16319 | 2019-04-24 09:46 | Section 4 | Material | NULL | NULL | 5 | Each | 34.93 | 174.65 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 3 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16677-001025 | 16677 | 2019-04-30 15:54 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-08 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16320-001025 | 16320 | 2019-04-24 14:16 | Section 4 | Material | NULL | NULL | 3 | Each | 35.91 | 107.73 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16320-001025 | 16320 | 2019-04-24 14:16 | Section 4 | Material | Not on List | NULL | 5 | Each | 250.64 | 1253.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16320-001025 | 16320 | 2019-04-24 14:16 | Section 4 | Material | NULL | NULL | 1 | Each | 170 | 170 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16830-001025 | 16830 | 2019-05-02 15:51 | Section 3 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 400 | Each | 2.31 | 924 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16835-001025 | 16835 | 2019-05-02 16:40 | Section 3 | Material | Not on List | Not on List | 1000 | No | NULL | 0 | Builders Merchants (General) | 2019-05-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16835-001025 | 16835 | 2019-05-02 16:40 | Section 3 | Material | Not on List | Not on List | 1000 | No | NULL | 0 | Builders Merchants (General) | 2019-05-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16322-001025 | 16322 | 2019-04-24 14:27 | Section 4 | Material | NULL | NULL | 110 | Each | 30.73 | 3380.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16322-001025 | 16322 | 2019-04-24 14:27 | Section 4 | Material | NULL | NULL | 2 | EA | 36.31 | 72.62 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16322-001025 | 16322 | 2019-04-24 14:27 | Section 4 | Material | NULL | NULL | 2 | EA | 250.64 | 501.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 100 | Each | 24.32 | 2432 | Timber Products | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 50 | Each | 6.82 | 341 | Timber Products | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | Timber | Not on List | 50 | Each | NULL | 0 | Timber Products | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | Not on List | Not on List | 5 | Packs | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6330-00670 | 6330 | 2018-09-11 13:21 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 198 | Each | 7.9 | 1564.2 | Miscellaneous | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16838-001025 | 16838 | 2019-05-02 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16633-001025 | 16633 | 2019-04-30 10:29 | Section 4 | Material | NULL | NULL | 3400 | Each | 19.96 | 67864 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16633-001025 | 16633 | 2019-04-30 10:29 | Section 4 | Material | NULL | NULL | 27 | Each | 250.64 | 6767.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16633-001025 | 16633 | 2019-04-30 10:29 | Section 4 | Material | NULL | NULL | 16 | Each | 40.16 | 642.56 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16633-001025 | 16633 | 2019-04-30 10:29 | Section 4 | Material | NULL | NULL | 4 | Each | 4.9 | 19.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16633-001025 | 16633 | 2019-04-30 10:29 | Section 4 | Material | NULL | NULL | 200 | Each | 12.5 | 2500 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16851-001025 | 16851 | 2019-05-03 08:06 | Section 5 | Material | Twinwall | Not on List | 42 | No | NULL | 0 | Plastic Drainage | 2019-05-07 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6329-00688 | 6329 | 2018-09-11 13:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 156 | Each | 15.37 | 2397.72 | Miscellaneous | 2018-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16851-001025 | 16851 | 2019-05-03 08:06 | Section 5 | Material | Twinwall | Not on List | 7 | No | NULL | 0 | Plastic Drainage | 2019-05-07 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16851-001025 | 16851 | 2019-05-03 08:06 | Section 5 | Material | Twinwall | Not on List | 55 | No | NULL | 0 | Plastic Drainage | 2019-05-07 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16851-001025 | 16851 | 2019-05-03 08:06 | Section 5 | Material | Twinwall | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-05-07 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16780-001025 | 16780 | 2019-05-02 08:10 | Section 4 | Material | Not on List | Not on List | 50 | Each | 4.95 | 247.5 | Concrete Accessories | 2019-05-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16780-001025 | 16780 | 2019-05-02 08:10 | Section 4 | Material | Not on List | Not on List | 8 | Each | 166.22 | 1329.76 | Concrete Accessories | 2019-05-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-6329-00688 | 6329 | 2018-09-11 13:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 156 | Each | 15.37 | 2397.72 | Miscellaneous | 2018-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | NULL | NULL | 0 | PPE | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Bucket Flexi Tub 26 Litre Black (506342) | 20 | Each | 7.42 | 148 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Bucket Flexi Tub 26 Litre Black (506342) | 20 | Each | 7.42 | 148 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289) | 5 | Each | 7.32 | 37 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Box | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16871-001025 | 16871 | 2019-05-03 10:30 | Section 5 | Material | Timber | 2440x1220x12mm Shuttering Ply (638572) | 1 | Load | 16.5 | 17 | Small Tools (Consumables) | 2019-05-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-15626-001025 | 15626 | 2019-04-10 15:46 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 72 | Each | 11.34 | 816.48 | Plastic Drainage | 2019-04-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15626-001025 | 15626 | 2019-04-10 15:46 | Section 3 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 10 | Each | 42.87 | 428.7 | Plastic Drainage | 2019-04-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15626-001025 | 15626 | 2019-04-10 15:46 | Section 3 | Material | Not on List | Not on List | 5 | rolls | 37.6 | 188 | Plastic Drainage | 2019-04-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16793-001025 | 16793 | 2019-05-02 09:25 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 0 | Each | 47.04 | 0 | Concrete Drainage | 2019-05-07 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16793-001025 | 16793 | 2019-05-02 09:25 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 30 | Each | 36.94 | 1108.2 | Concrete Drainage | 2019-05-07 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16882-001025 | 16882 | 2019-05-03 13:49 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-05-07 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16858-001025 | 16858 | 2019-05-03 08:55 | Section 3 | Material | Not on List | Not on List | 10 | ea | 36 | 360 | Small Tools (Consumables) | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16860-001025 | 16860 | 2019-05-03 09:34 | Core | Material | Not on List | Not on List | 96 | ea | 2.5 | 240 | Miscellaneous | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16865-001025 | 16865 | 2019-05-03 10:55 | Section 3 | Material | Not on List | Not on List | 30 | NULL | 0.68 | 20.4 | Miscellaneous | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 9 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 10 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 28 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 12 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 10 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5931-00580 | 5931 | 2018-09-03 11:55 | Section 4 | Material | Not on List | Not on List | 90 | Each | 4 | 360 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 24 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5931-00580 | 5931 | 2018-09-03 11:55 | Section 4 | Material | Not on List | Not on List | 208 | Each | 3.4 | 707.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22393-001025 | 22393 | 2019-08-15 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22432-001025 | 22432 | 2019-08-19 07:12 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22440-001025 | 22440 | 2019-08-19 07:57 | Core | Material | PPE, Small Tools and Consumables | Stake Marking Out Wooden 1200mm Nominal C.r.code Swcoc004463 (740904) | 50 | Each | 1.07 | 54 | Surveying Consumables | 2019-08-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5931-00580 | 5931 | 2018-09-03 11:55 | Section 4 | Material | Not on List | Not on List | 290 | Each | 36.9 | 10701 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22443-001025 | 22443 | 2019-08-19 08:04 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21542-001025 | 21542 | 2019-07-30 10:44 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21547-001025 | 21547 | 2019-07-30 11:10 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22259-001025 | 22259 | 2019-08-14 09:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Small Tools (Consumables) | 2019-08-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5931-00580 | 5931 | 2018-09-03 11:55 | Section 4 | Material | Not on List | Not on List | 2 | Each | 30 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22332-001025 | 22332 | 2019-08-15 14:36 | Section 1 | Material | Concrete Drainage | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-09-09 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-22176-001025 | 22176 | 2019-08-12 17:09 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 30.24 | 302.4 | Small Tools (Consumables) | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22324-001025 | 22324 | 2019-08-15 13:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1400 | Each | 0.37 | 518 | Miscellaneous | 2019-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6072-00608 | 6072 | 2018-09-05 12:09 | Section 4 | Material | Not on List | Not on List | 50 | Each | 3.12 | 156 | Builders Merchants (General) | 2018-09-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22234-001025 | 22234 | 2019-08-13 16:20 | Section 4 | Material | Not on List | Not on List | 3 | Number | 275 | 825 | Surveying Consumables | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22462-001025 | 22462 | 2019-08-19 11:46 | Core | Material | Not on List | Not on List | 1 | Sum | 6758.41 | 6758 | Miscellaneous | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6195-00639 | 6195 | 2018-09-07 11:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 35.5 | 71 | Small Tools (Consumables) | 2018-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22255-001025 | 22255 | 2019-08-14 08:53 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2401 | 2401 | Miscellaneous | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22252-001025 | 22252 | 2019-08-14 08:38 | Section 4 | Material | Not on List | Not on List | 1 | Each | 142.5 | 142.5 | Miscellaneous | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22139-001025 | 22139 | 2019-08-12 09:37 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 2889.15 | 2889.15 | Miscellaneous | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22422-001025 | 22422 | 2019-08-18 14:09 | Section 5 | Material | Twinwall | Not on List | 8 | No | 193.09 | 1544.72 | Plastic Drainage | 2019-09-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22422-001025 | 22422 | 2019-08-18 14:09 | Section 5 | Material | Twinwall | Not on List | 14 | No | 130.26 | 1823.64 | Plastic Drainage | 2019-09-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22422-001025 | 22422 | 2019-08-18 14:09 | Section 5 | Material | Twinwall | Not on List | 22 | No | 125.94 | 2770.68 | Plastic Drainage | 2019-09-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6209-00640 | 6209 | 2018-09-07 13:26 | Section 4 | Material | Not on List | Not on List | 2 | Each | 9.54 | 19.08 | Miscellaneous | 2018-09-14 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22422-001025 | 22422 | 2019-08-18 14:09 | Section 5 | Material | Twinwall | Not on List | 20 | No | 10.84 | 216.8 | Plastic Drainage | 2019-09-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22422-001025 | 22422 | 2019-08-18 14:09 | Section 5 | Material | Twinwall | Not on List | 30 | No | 9.76 | 292.8 | Plastic Drainage | 2019-09-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21491-001025 | 21491 | 2019-07-29 11:10 | Section 4 | Material | Waste Management | Not on List | 1 | Each | 468.65 | 468.65 | Waste (General) | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22385-001025 | 22385 | 2019-08-16 09:50 | Core | Material | NULL | NULL | 1 | Each | 406 | 406 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21932-001025 | 21932 | 2019-08-07 10:12 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2292.65 | 2292.65 | Miscellaneous | 2019-08-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22195-001025 | 22195 | 2019-08-13 08:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1500.74 | 1500.74 | Miscellaneous | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22197-001025 | 22197 | 2019-08-13 08:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1583.44 | 1583.44 | Miscellaneous | 2019-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22495-001025 | 22495 | 2019-08-19 16:44 | Core | Material | Not on List | Not on List | 6 | EA | 55 | 330 | Miscellaneous | 2019-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22141-001025 | 22141 | 2019-08-12 09:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 20 | 80 | Surveying Consumables | 2019-08-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6209-00640 | 6209 | 2018-09-07 13:26 | Section 4 | Material | Not on List | Not on List | 2 | Each | 138.54 | 277.08 | Miscellaneous | 2018-09-14 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22141-001025 | 22141 | 2019-08-12 09:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 200 | Each | 0.8 | 160 | Surveying Consumables | 2019-08-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22465-001025 | 22465 | 2019-08-19 12:59 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1019.85 | Each | 1 | 1019.85 | PPE | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22515-001025 | 22515 | 2019-08-20 07:39 | Section 5 | Material | Timber | Not on List | 50 | Each | NULL | 0 | PPE | 2019-08-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-22515-001025 | 22515 | 2019-08-20 07:39 | Section 5 | Material | Timber | Not on List | 40 | Each | NULL | 0 | PPE | 2019-08-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-22389-001025 | 22389 | 2019-08-16 11:34 | Core | Material | NULL | NULL | 10 | Pack 2 | 1.1 | 11 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6209-00640 | 6209 | 2018-09-07 13:26 | Section 4 | Material | Not on List | Not on List | 2 | Each | 88.92 | 177.84 | Miscellaneous | 2018-09-14 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22466-001025 | 22466 | 2019-08-19 13:17 | Section 3 | Material | Kerbs | Not on List | 4 | No | 7.96 | 31.84 | Builders Merchants (General) | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22466-001025 | 22466 | 2019-08-19 13:17 | Section 3 | Material | Kerbs | Not on List | 4 | No | 7.96 | 31.84 | Builders Merchants (General) | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22221-001025 | 22221 | 2019-08-13 12:38 | Section 3 | Material | Not on List | Not on List | 4 | 3m lengths | 1.77 | 7.08 | Miscellaneous | 2019-08-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1506 - Detector Installations | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22221-001025 | 22221 | 2019-08-13 12:38 | Section 3 | Material | Not on List | Not on List | 4 | 3m lengths | 9.36 | 37.44 | Miscellaneous | 2019-08-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1506 - Detector Installations | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22337-001025 | 22337 | 2019-08-15 13:33 | Section 4 | Material | NULL | NULL | 500 | Each | 7.1 | 3550 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22337-001025 | 22337 | 2019-08-15 13:33 | Section 4 | Material | NULL | NULL | 4 | Each | 9 | 36 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22337-001025 | 22337 | 2019-08-15 13:33 | Section 4 | Material | NULL | NULL | 120 | Each | 17.9 | 2148 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22355-001025 | 22355 | 2019-08-15 08:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 7.24 | 7.24 | Miscellaneous | 2019-08-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Not on List | 8 | no | 145 | 1160 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6267 | 6267 | 2018-09-10 13:49 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.8 | 160 | Surveying Consumables | 2018-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22355-001025 | 22355 | 2019-08-15 08:06 | Section 4 | Material | Not on List | Not on List | 2 | Each | 13.95 | 27.9 | Miscellaneous | 2019-08-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22388-001025 | 22388 | 2019-08-16 10:47 | Section 3 | Material | Not on List | Not on List | 1 | No. | 1660 | 1660 | Flow Control | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22388-001025 | 22388 | 2019-08-16 10:47 | Section 3 | Material | Not on List | Not on List | 2 | No. | 3320 | 6640 | Flow Control | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22388-001025 | 22388 | 2019-08-16 10:47 | Section 3 | Material | Not on List | Not on List | 1 | No. | 1765 | 1765 | Flow Control | 2019-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-22530-001025 | 22530 | 2019-08-20 14:33 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Buyers
MREQ-22532-001025 | 22532 | 2019-08-20 14:52 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-08-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6268-00654 | 6268 | 2018-09-10 14:32 | Section 4 | Material | Not on List | Not on List | 5 | Roll | 241.07 | 1205.35 | Electrical | 2018-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22554-001025 | 22554 | 2019-08-20 17:41 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22573-001025 | 22573 | 2019-08-21 06:37 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-22574-001025 | 22574 | 2019-08-21 06:44 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-22575-001025 | 22575 | 2019-08-21 06:52 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-6268-00654 | 6268 | 2018-09-10 14:32 | Section 4 | Material | Not on List | Not on List | 53 | Each | 8.8 | 466.4 | Electrical | 2018-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22593-001025 | 22593 | 2019-08-21 09:44 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-22529-001025 | 22529 | 2019-08-20 14:25 | Section 4 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 200 | Each | 24.99 | 4998 | Plastic Drainage | 2019-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22529-001025 | 22529 | 2019-08-20 14:25 | Section 4 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 400 | Each | 3.65 | 1460 | Plastic Drainage | 2019-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22529-001025 | 22529 | 2019-08-20 14:25 | Section 4 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 800 | Each | 2 | 1600 | Plastic Drainage | 2019-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22529-001025 | 22529 | 2019-08-20 14:25 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 40 | Each | 48.92 | 1956.8 | Concrete Drainage | 2019-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22518-001025 | 22518 | 2019-08-20 11:33 | Section 5 | Material | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 142 | Each | 4.42 | 627.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6271-00656 | 6271 | 2018-09-10 13:35 | Section 4 | Material | Not on List | Not on List | 3.74 | Tonnes | 538 | 2012.12 | Rebar and Mesh | 2018-09-21 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22518-001025 | 22518 | 2019-08-20 11:33 | Section 5 | Material | Kerbs | Not on List | 2 | NULL | 22.4 | 44.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22518-001025 | 22518 | 2019-08-20 11:33 | Section 5 | Material | Kerbs | Not on List | 2 | NULL | 18.45 | 36.9 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22518-001025 | 22518 | 2019-08-20 11:33 | Section 5 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 4 | Each | 9.75 | 39 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22600-001025 | 22600 | 2019-08-21 11:16 | Section 6 | Material | Aggregate | Class 1A | 5000 | Tonnes | 12.5 | 62500 | Aggregate | 2019-08-27 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 604 - Deposition (excl topsoil) | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-22602-001025 | 22602 | 2019-08-21 11:21 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 15120 | 15120 | Professional Services | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-22613-001025 | 22613 | 2019-08-21 09:54 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 1 | full pallet | 24.32 | 24 | Timber Products | 2019-08-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22613-001025 | 22613 | 2019-08-21 09:54 | Section 5 | Material | Timber | Not on List | 30 | Each | NULL | 0 | Timber Products | 2019-08-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22456-001025 | 22456 | 2019-08-19 07:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 196 | 196 | Surveying Consumables | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22456-001025 | 22456 | 2019-08-19 07:39 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.32 | 132 | Builders Merchants (General) | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22456-001025 | 22456 | 2019-08-19 07:39 | Section 4 | Material | Not on List | Not on List | 250 | Each | 0.67 | 167.5 | Builders Merchants (General) | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6315-00658 | 6315 | 2018-09-11 10:18 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Visit | 2749.65 | 2749.65 | Miscellaneous | 2018-09-12 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22456-001025 | 22456 | 2019-08-19 07:39 | Section 4 | Material | Ducting | Polypipe 110mm x 50m Ridgiduct Coil Orange S/L (877804) | 2 | Each | 113.44 | 226.88 | Builders Merchants (General) | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22456-001025 | 22456 | 2019-08-19 07:39 | Section 4 | Material | Ducting | Polypipe 110mm x 50m Ridgiduct Coil Purple (877806) | 2 | Each | 113.44 | 226.88 | Builders Merchants (General) | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22615-001025 | 22615 | 2019-08-21 14:03 | Section 5 | Material | PPE, Small Tools and Consumables | Pad Maintenance Black And White Economy Ecospill 40cm X 50cm (534067) | 200 | Each | 0.54 | 108 | Miscellaneous | 2019-08-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22616-001025 | 22616 | 2019-08-21 14:08 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-22616-001025 | 22616 | 2019-08-21 14:08 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-22616-001025 | 22616 | 2019-08-21 14:08 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-22525-001025 | 22525 | 2019-08-20 13:39 | Core | Material | NULL | NULL | 3 | Each | 95 | 285 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22467-001025 | 22467 | 2019-08-19 13:21 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 214.23 | Each | 1 | 214.23 | Small Tools (Consumables) | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22619-001025 | 22619 | 2019-08-21 14:24 | Core | Material | Not on List | Not on List | 45 | NULL | 63 | 2835 | Professional Services | 2019-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | NULL | Yes - Approve | REQ - Buyers
MREQ-22558-001025 | 22558 | 2019-08-20 18:17 | Section 4 | Material | Not on List | Not on List | 150 | Each | 1.32 | 198 | Builders Merchants (General) | 2019-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6317-00659 | 6317 | 2018-09-11 11:05 | Section 4 | Material | Misc | Comms Duct 100Mm | 6 | Each | 105.04 | 630.24 | Electrical | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22588-001025 | 22588 | 2019-08-21 09:00 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 304.6 | Each | 1 | 304.6 | Small Tools (Consumables) | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22449-001025 | 22449 | 2019-08-19 09:22 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.9 | 450 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22448-001025 | 22448 | 2019-08-19 09:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2750 | 2750 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22448-001025 | 22448 | 2019-08-19 09:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 40 | 40 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22448-001025 | 22448 | 2019-08-19 09:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 220 | 220 | Miscellaneous | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22523-001025 | 22523 | 2019-08-20 13:22 | Section 4 | Material | Not on List | Not on List | 1 | Number | 145 | 145 | Surveying Consumables | 2019-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22630-001025 | 22630 | 2019-08-21 16:06 | Section 4 | Material | Signage | NULL | 1 | SM | 1288.29 | 1288.29 | Not Sure | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6317-00659 | 6317 | 2018-09-11 11:05 | Section 4 | Material | Misc | Comms Duct 100Mm | 1 | Each | 105.04 | 105.04 | Electrical | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22384-001025 | 22384 | 2019-08-16 09:04 | Section 2 | Material | Not on List | Not on List | 8 | each | 7613.6 | 60908.8 | Miscellaneous | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22384-001025 | 22384 | 2019-08-16 09:04 | Section 2 | Material | Not on List | Not on List | 5 | each | 3590 | 17950 | Miscellaneous | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22534-001025 | 22534 | 2019-08-20 15:32 | Section 4 | Material | Waste Management | Not on List | 1 | NULL | 234.32 | 234.32 | Waste (General) | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22151-001025 | 22151 | 2019-08-12 11:58 | Core | Material | NULL | NULL | 50 | Each | 28.8 | 1440 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22151-001025 | 22151 | 2019-08-12 11:58 | Core | Material | NULL | NULL | 10 | Each | 28.8 | 288 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22157-001025 | 22157 | 2019-08-12 13:49 | Core | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | 28.8 | 1152 | PPE | 2019-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 28 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 16 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 16 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 12 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 14 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 32 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 8 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 16 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16905-001025 | 16905 | 2019-05-06 18:06 | Section 5 | Material | Twinwall | Not on List | 2 | No | NULL | 0 | Plastic Drainage | 2019-05-13 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16929-001025 | 16929 | 2019-05-07 08:58 | Section 4 | Material | Not on List | Not on List | 100 | ea | 10 | 1000 | Miscellaneous | 2019-05-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16806-001025 | 16806 | 2019-05-02 11:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 11.57 | 23.14 | Laboratory Equipment / Certification | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16806-001025 | 16806 | 2019-05-02 11:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 6.96 | 139.2 | Laboratory Equipment / Certification | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16806-001025 | 16806 | 2019-05-02 11:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 0.86 | 17.2 | Laboratory Equipment / Certification | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16806-001025 | 16806 | 2019-05-02 11:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 55.92 | 279.6 | Laboratory Equipment / Certification | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16591-001025 | 16591 | 2019-04-29 15:26 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 370 | 370 | Laboratory Equipment / Certification | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16812-001025 | 16812 | 2019-05-02 11:28 | Core | Material | Not on List | Not on List | 1 | NULL | 329.46 | 329.46 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16938-001025 | 16938 | 2019-05-07 10:27 | Core | Material | Not on List | Not on List | 1 | number | 2500 | 2500 | Office Supplies | 2019-05-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-16849-001025 | 16849 | 2019-05-03 07:36 | Core | Material | Not on List | Not on List | 1 | No | 51.4 | 51.4 | Janitorial | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16849-001025 | 16849 | 2019-05-03 07:36 | Core | Material | Not on List | Not on List | 1 | No | 367.4 | 367.4 | Small Tools (Consumables) | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16849-001025 | 16849 | 2019-05-03 07:36 | Core | Material | Not on List | Not on List | 1 | No | 278.79 | 278.79 | PPE | 2019-05-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16948-001025 | 16948 | 2019-05-07 14:14 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 5 | Each | 11.94 | 60 | Builders Merchants (General) | 2019-05-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16952-001025 | 16952 | 2019-05-07 14:18 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 25.13 | 251 | Miscellaneous | 2019-05-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16807-001025 | 16807 | 2019-05-02 10:58 | Core | Material | Not on List | Not on List | 1 | NULL | 329.46 | 329 | Miscellaneous | 2019-05-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16828-001025 | 16828 | 2019-05-02 15:38 | Core | Material | Not on List | Not on List | 1 | NULL | 478 | 478 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16956-001025 | 16956 | 2019-05-07 15:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2447.01 | 2447 | PPE | 2019-05-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16957-001025 | 16957 | 2019-05-07 15:29 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-16958-001025 | 16958 | 2019-05-07 15:38 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16886-001025 | 16886 | 2019-05-03 14:35 | Section 4 | Material | Not on List | Not on List | 5 | Box 50 | 28.84 | 144.2 | Small Tools (Consumables) | 2019-05-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16959-001025 | 16959 | 2019-05-07 15:55 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16942-001025 | 16942 | 2019-05-07 10:56 | Section 2 | Material | Not on List | Not on List | 2 | Number | 236 | 472 | Plastic Drainage | 2019-05-10 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-16942-001025 | 16942 | 2019-05-07 10:56 | Section 2 | Material | Not on List | Not on List | 8 | Number | 42.75 | 342 | Plastic Drainage | 2019-05-10 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-16942-001025 | 16942 | 2019-05-07 10:56 | Section 2 | Material | Not on List | Not on List | 4 | Number | 23.4 | 94 | Plastic Drainage | 2019-05-10 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-16942-001025 | 16942 | 2019-05-07 10:56 | Section 2 | Material | Not on List | Not on List | 2 | Number | 21.5 | 43 | Plastic Drainage | 2019-05-17 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-16965-001025 | 16965 | 2019-05-07 16:22 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1364.52 | 1365 | Surveying Consumables | 2019-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16979-001025 | 16979 | 2019-05-07 16:59 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-6384-00680 | 6384 | 2018-09-12 09:14 | Section 3 | Material | Not on List | Not on List | 1 | EA | 1539.4 | 1539.4 | PPE | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16981-001025 | 16981 | 2019-05-07 17:09 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16985-001025 | 16985 | 2019-05-07 17:38 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20899-001025 | 20899 | 2019-07-17 10:29 | Section 4 | Material | Not on List | Not on List | 700 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20899-001025 | 20899 | 2019-07-17 10:29 | Section 4 | Material | Not on List | Not on List | 350 | NULL | NULL | 0 | Fixings and Fasteners | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20772-001025 | 20772 | 2019-07-15 14:05 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | Each | 2.97 | 332.64 | Miscellaneous | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20772-001025 | 20772 | 2019-07-15 14:05 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 11.5 | 115 | Miscellaneous | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20839-001025 | 20839 | 2019-07-16 13:02 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-07-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | Concrete Drainage | Not on List | 2 | Each | 92.06 | 184.12 | Concrete Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20845-001025 | 20845 | 2019-07-16 14:05 | Section 3 | Material | Aggregate | 6G | 120 | Tonnes | 32.9 | 3948 | Aggregate | 2019-07-22 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20830-001025 | 20830 | 2019-07-16 11:20 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1557.05 | each | 1 | 1557.05 | PPE | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20901-001025 | 20901 | 2019-07-17 10:52 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | 28.8 | 864 | PPE | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20555-001025 | 20555 | 2019-07-10 14:02 | Section 4 | Material | Not on List | Not on List | 1 | each | 2441.5 | 2441.5 | Miscellaneous | 2019-07-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20854-001025 | 20854 | 2019-07-16 16:18 | Section 1 | Material | Concrete Drainage | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-07-29 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | NULL | NULL | 32 | Each | 3.17 | 101.44 | Plastic Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20934-001025 | 20934 | 2019-07-17 15:52 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3216.2 | each | 1 | 3216 | Miscellaneous | 2019-07-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Buyers
MREQ-20871-001025 | 20871 | 2019-07-16 17:38 | Section 4 | Material | NULL | NULL | 20 | Each | 41.2 | 824 | Concrete Drainage | 2019-07-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20871-001025 | 20871 | 2019-07-16 17:38 | Section 4 | Material | NULL | NULL | 4 | Each | 59.57 | 238.28 | Miscellaneous | 2019-07-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20755-001025 | 20755 | 2019-07-15 11:01 | Core | Material | NULL | NULL | 1 | Eack | 837 | 837 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5459 | 5459 | 2018-08-21 12:27 | Section 4 | Material | NULL | NULL | 16 | Each | 5.74 | 91.84 | Plastic Drainage | 2018-08-30 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5492-00323 | 5492 | 2018-08-22 10:58 | Section 4 | Material | Not on List | Not on List | 8 | Each | 66 | 528 | Concrete Accessories | 2018-09-28 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20960-001025 | 20960 | 2019-07-18 08:06 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Accessories | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20960-001025 | 20960 | 2019-07-18 08:06 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Accessories | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5492-00323 | 5492 | 2018-08-22 10:58 | Section 4 | Material | Not on List | Not on List | 8 | Each | 72 | 576 | Concrete Accessories | 2018-08-28 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20981-001025 | 20981 | 2019-07-18 10:03 | Section 3 | Material | PPE, Small Tools and Consumables | Rope Blue Polypropylene 6mm X 500m (approx)on Drum (746415) | 15 | Each | 25.13 | 377 | Miscellaneous | 2019-07-22 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-20909-001025 | 20909 | 2019-07-17 12:11 | Section 4 | Material | Not on List | Not on List | 600 | Box 100 | 45.04 | 27024 | Fixings and Fasteners | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20909-001025 | 20909 | 2019-07-17 12:11 | Section 4 | Material | Not on List | Not on List | 1000 | Box 100 | 83.15 | 83150 | Fixings and Fasteners | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20918-001025 | 20918 | 2019-07-17 14:20 | Section 4 | Material | Not on List | Not on List | 219 | 3.2m Tube | 24.1 | 5277.9 | Fixings and Fasteners | 2019-07-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5144-0075 | 5144 | 2018-08-15 11:44 | Section 3 | Material | Not on List | NULL | 16 | No | 74.3 | 1188.8 | Builders Merchants (General) | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5492-00323 | 5492 | 2018-08-22 10:58 | Section 4 | Material | Not on List | Not on List | 2 | rolls | 3.6 | 7.2 | Concrete Accessories | 2018-08-28 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20843-001025 | 20843 | 2019-07-16 13:39 | Section 4 | Material | Not on List | Not on List | 4 | Box 100 | 4.9 | 19.6 | Surveying Consumables | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20910-001025 | 20910 | 2019-07-17 12:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | EACH | 7.23 | 361.5 | Builders Merchants (General) | 2019-07-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20910-001025 | 20910 | 2019-07-17 12:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | EACH | 16 | 16 | Builders Merchants (General) | 2019-07-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20910-001025 | 20910 | 2019-07-17 12:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | BOX | 2.4 | 12 | Builders Merchants (General) | 2019-07-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20995-001025 | 20995 | 2019-07-18 12:56 | Core | Material | Not on List | Not on List | 1 | NULL | 259.6 | 260 | PPE | 2019-07-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20995-001025 | 20995 | 2019-07-18 12:56 | Core | Material | Not on List | Not on List | 1 | NULL | 539.28 | 539 | Small Tools (Consumables) | 2019-07-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Saint Gobain Castings | 454x454x100 D400 Watershed GG&F (257790) | 40 | Each | 58.04 | 2321.6 | Concrete Drainage | 2019-07-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 40 | EACH | 4.29 | 171.6 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 40 | EACH | 5.95 | 238 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 10 | EACH | 189 | 1890 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 483 | Rolls | 49.5 | 23908.5 | Blocks and Bricks | 2018-10-15 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 30 | EACH | 125.94 | 3778.2 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 10 | EACH | 18.89 | 188.9 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Twinwall | Not on List | 50 | EACH | 10.84 | 542 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Not on List | Not on List | 20 | EACH | 79.41 | 1588.2 | Plastic Drainage | 2019-07-17 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20954-001025 | 20954 | 2019-07-17 17:10 | Section 5 | Material | Saint Gobain Castings | 380x230x125 D400 Surface Box (376797) | 20 | Each | 34 | 680 | Plastic Drainage | 2019-07-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20911-001025 | 20911 | 2019-07-17 12:57 | Section 4 | Material | Not on List | Not on List | 20 | Each | 12.18 | 243.6 | Concrete Accessories | 2019-07-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 8 | Rolls | 139 | 1112 | Blocks and Bricks | 2018-10-15 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20980-001025 | 20980 | 2019-07-18 09:49 | Section 3 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 17 | Each | 179.74 | 3055.58 | Ductile Drainage | 2019-07-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20980-001025 | 20980 | 2019-07-18 09:49 | Section 3 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 6 | Each | 125.94 | 755.64 | Ductile Drainage | 2019-07-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20980-001025 | 20980 | 2019-07-18 09:49 | Section 3 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 20 | Each | 10.5 | 210 | Ductile Drainage | 2019-07-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20980-001025 | 20980 | 2019-07-18 09:49 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 30 | Each | 34.82 | 1044.6 | Ductile Drainage | 2019-07-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20980-001025 | 20980 | 2019-07-18 09:49 | Section 3 | Material | Twinwall | Not on List | 8 | Each | NULL | 0 | Ductile Drainage | 2019-07-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20849-001025 | 20849 | 2019-07-16 14:28 | Section 3 | Material | Not on List | Not on List | 25 | Rolls | 196 | 4900 | Tanks and Interceptors | 2019-07-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20849-001025 | 20849 | 2019-07-16 14:28 | Section 3 | Material | Not on List | Not on List | 1 | Bx of 900 | 40.8 | 40.8 | Tanks and Interceptors | 2019-07-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20849-001025 | 20849 | 2019-07-16 14:28 | Section 3 | Material | Not on List | Not on List | 300 | ea | 2.55 | 765 | Tanks and Interceptors | 2019-07-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20946-001025 | 20946 | 2019-07-17 17:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Bag 1000 | 55 | 55 | Rebar and Mesh | 2019-07-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.22 | 110 | Blocks and Bricks | 2018-10-15 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20549-001025 | 20549 | 2019-07-10 12:30 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 600 | 600 | Miscellaneous | 2019-07-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20959-001025 | 20959 | 2019-07-18 07:52 | Section 5 | Material | Not on List | Not on List | 1 | SUM | 1078.5 | 1078.5 | Concrete Accessories | 2019-07-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21029-001025 | 21029 | 2019-07-19 09:16 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | 36 | 144 | Small Tools (Consumables) | 2019-07-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21029-001025 | 21029 | 2019-07-19 09:16 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 36 | NULL | 2.5 | 90 | Surveying Consumables | 2019-07-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20945-001025 | 20945 | 2019-07-17 17:09 | Core | Material | PPE, Small Tools and Consumables | Not on List | 32 | EA | 28.8 | 921.6 | PPE | 2019-07-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20943-001025 | 20943 | 2019-07-17 17:04 | Core | Material | PPE, Small Tools and Consumables | Not on List | 326.2 | Each | 1 | 326.2 | Miscellaneous | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21026-001025 | 21026 | 2019-07-19 09:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 35 | 350 | Surveying Consumables | 2019-07-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | GR ENVIROPAD - M10 (MEDIUM) GRR 520210 EPAD (534283) | 5 | Each | 110.18 | 551 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 1 | Pack | 1335 | 1335 | Blocks and Bricks | 2018-10-15 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Shovel No2 Solid Socket Square Mouth Myd Handle Spartan (762570) | 10 | Each | 10.19 | 102 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Sprayer 20oz Bottle C/W Adjust Trigger Spray Spartan (510900) | 3 | Each | 2.6 | 8 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Blade Replacement Utility/Trimming Knife 10 Pk Spartan Pro (740081) | 10 | Each | 1.21 | 12 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Sealant Gp Silicone Hansil Contractor Clear 300ml (546650) | 48 | Each | 1.13 | 54 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Nipper Work Pro End-cutting Pliers Size 175mm // 7" (742894) | 10 | Each | 14.79 | 148 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Jerrican Metal 20 Litre Capacity Spartan Pro (708622) | 5 | Each | 13.19 | 66 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 650 | 650 | Blocks and Bricks | 2018-10-15 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21037-001025 | 21037 | 2019-07-19 09:14 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-23 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 300 | 300 | Blocks and Bricks | 2018-10-01 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21039-001025 | 21039 | 2019-07-19 11:14 | Core | Material | Not on List | Not on List | 1 | number | 99.99 | 100 | Electrical | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21039-001025 | 21039 | 2019-07-19 11:14 | Core | Material | Not on List | Not on List | 1 | number | 41.49 | 41 | Electrical | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20937-001025 | 20937 | 2019-07-17 16:28 | Section 4 | Material | Not on List | Not on List | 684 | ea | 4.13 | 2824.92 | Miscellaneous | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21044-001025 | 21044 | 2019-07-19 11:47 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 44.45 | 44 | Small Tools (Consumables) | 2019-07-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 105 - Site Security | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 500 | 500 | Blocks and Bricks | 2018-10-01 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5496-00327 | 5496 | 2018-08-22 12:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 450 | 450 | Blocks and Bricks | 2018-10-01 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21077-001025 | 21077 | 2019-07-19 15:15 | Core | Material | Not on List | Not on List | 4 | Days | 649 | 2596 | Professional Services | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20920-001025 | 20920 | 2019-07-17 14:50 | Section 3 | Material | Not on List | Not on List | 20 | No | 21.29 | 425.8 | Builders Merchants (General) | 2019-07-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20920-001025 | 20920 | 2019-07-17 14:50 | Section 3 | Material | Not on List | Not on List | 10 | No | 33.55 | 335.5 | Builders Merchants (General) | 2019-07-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5500-00331 | 5500 | 2018-08-22 13:36 | Section 4 | Material | Not on List | Not on List | 40 | Each | 112.06 | 4482.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21113-001025 | 21113 | 2019-07-22 10:43 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21119-001025 | 21119 | 2019-07-22 11:14 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21125-001025 | 21125 | 2019-07-22 11:24 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21126-001025 | 21126 | 2019-07-22 11:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20759-001025 | 20759 | 2019-07-15 11:34 | Core | Material | NULL | NULL | 1 | Each | 491 | 491 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20963-001025 | 20963 | 2019-07-18 08:27 | Core | Material | NULL | NULL | 1 | Each | 272 | 272 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5144-0075 | 5144 | 2018-08-15 11:44 | Section 3 | Material | Not on List | NULL | 28 | No | 31.37 | 878.36 | Builders Merchants (General) | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5500-00331 | 5500 | 2018-08-22 13:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 126.82 | 253.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21133-001025 | 21133 | 2019-07-22 12:11 | Section 3 | Material | Not on List | Not on List | 28 | NULL | NULL | 0 | Miscellaneous | 2019-07-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21133-001025 | 21133 | 2019-07-22 12:11 | Section 3 | Material | Not on List | Not on List | 41 | NULL | NULL | 0 | Miscellaneous | 2019-07-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21133-001025 | 21133 | 2019-07-22 12:11 | Section 3 | Material | Not on List | Not on List | 19 | NULL | NULL | 0 | Miscellaneous | 2019-07-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21133-001025 | 21133 | 2019-07-22 12:11 | Section 3 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Miscellaneous | 2019-07-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21111-001025 | 21111 | 2019-07-22 09:34 | Section 4 | Material | Not on List | Not on List | 28 | number | 1.37 | 38.36 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21111-001025 | 21111 | 2019-07-22 09:34 | Section 4 | Material | Not on List | Not on List | 56 | number | 0.26 | 14.56 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21111-001025 | 21111 | 2019-07-22 09:34 | Section 4 | Material | Not on List | Not on List | 56 | number | 0.17 | 9.52 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21111-001025 | 21111 | 2019-07-22 09:34 | Section 4 | Material | Not on List | Not on List | 6 | number | 32.18 | 193.08 | Miscellaneous | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17235-001025 | 17235 | 2019-05-13 08:36 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20856-001025 | 20856 | 2019-07-16 16:25 | Core | Material | NULL | NULL | 1 | Each | 7984.5 | 7984.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5500-00331 | 5500 | 2018-08-22 13:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 126.82 | 253.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18585-001025 | 18585 | 2019-06-05 11:16 | Core | Material | NULL | NULL | 1 | Each | 3115 | 3115 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18586-001025 | 18586 | 2019-06-05 11:21 | Core | Material | NULL | NULL | 1 | Each | 2358 | 2358 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20998-001025 | 20998 | 2019-07-18 14:19 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 100 | Each | 1.98 | 198 | Plastic Drainage | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20998-001025 | 20998 | 2019-07-18 14:19 | Section 2 | Material | Twinwall | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20998-001025 | 20998 | 2019-07-18 14:19 | Section 2 | Material | Not on List | Not on List | 120 | NULL | NULL | 0 | Concrete Drainage | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5501-00334 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 525 | Each | 4.43 | 2325.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20998-001025 | 20998 | 2019-07-18 14:19 | Section 2 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 20 | Each | 81.73 | 1634.6 | Concrete Drainage | 2019-07-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20990-001025 | 20990 | 2019-07-18 11:44 | Core | Material | NULL | NULL | 1 | Each | 116 | 116 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 70 | NULL | NULL | 0 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 86 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 106 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5126-0051 | 5126 | 2018-08-15 09:16 | Section 3 | Material | Not on List | NULL | 8 | no. | NULL | 0 | Geotextiles | 2018-08-20 | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 15 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 110 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 254 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 242 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 477 | NULL | NULL | 0 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 35 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 41 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 34 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 55 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 63 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 22 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 15 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 18 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 82 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 36 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5397-00263 | 5397 | 2018-08-21 08:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1304.51 | 0 | Small Tools (Consumables) | 2018-08-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 98 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 345 | NULL | NULL | 0 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 44 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 22 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 36 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 150 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 36 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5478-00302 | 5478 | 2018-08-22 07:29 | Section 3 | Material | Plastic Drainage | Not on List | 40 | No. | NULL | 0 | Plastic Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 16 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 40 | No | 243.87 | 9754.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 5 | EA | 59.17 | 295.85 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 20 | No | 46.35 | 927 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 240 | No | 34.1 | 8184 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 47 | No | 29.01 | 1363.47 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 47 | No | 29.01 | 1363.47 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 1430 | No | 29.28 | 41870.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10504-001025 | 10504 | 2018-12-20 11:07 | Section 3 | Material | NULL | Not on List | 26 | No | 4.67 | 121.42 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10429-001025 | 10429 | 2018-12-17 16:01 | Section 4 | Material | Not on List | Not on List | 20 | Box | NULL | 0 | Miscellaneous | 2018-12-20 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 100 | Each | 6.35 | 635 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 36 | Each | 6.35 | 229 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 24 | Each | 6.35 | 152 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 5 | EA | 232.01 | 1160.05 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10490-001025 | 10490 | 2018-12-19 16:00 | Section 3 | Material | Not on List | Not on List | 1 | ea | 861 | 861 | Miscellaneous | 2018-12-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | Kerbs | Not on List | 9 | Packs | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | Kerbs | Not on List | 3 | Packs | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | Kerbs | Not on List | 3 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | Kerbs | Not on List | 3 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 200 | ea | 2.18 | 436 | Miscellaneous | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | ea | 309.24 | 309.24 | Janitorial | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | ea | 128.89 | 128.89 | Small Tools (Consumables) | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10498-001025 | 10498 | 2018-12-19 17:53 | Section 3 | Material | Not on List | Not on List | 1 | ea | 65.7 | 65.7 | PPE | 2019-01-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10581-001025 | 10581 | 2019-01-04 09:11 | Section 3 | Material | Not on List | Not on List | 2 | packs | NULL | 0 | Plastic Drainage | 2019-01-11 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 8 | EA | 81.96 | 655.68 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 100 | Each | 6.35 | 635 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 36 | Each | 6.35 | 228.6 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10555-001 | 10555 | 2019-01-03 09:55 | Section 3 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 24 | Each | 6.35 | 152.4 | PPE | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10587-001025 | 10587 | 2019-01-04 11:13 | Section 4 | Material | Not on List | Not on List | 1 | each | 1276.63 | 1277 | Not Sure | 2019-01-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10588-001025 | 10588 | 2019-01-04 11:19 | Section 3 | Material | Not on List | Not on List | 1 | each | 2288.78 | 2289 | Not Sure | 2019-01-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10616-001025 | 10616 | 2019-01-04 15:44 | Section 3 | Material | Not on List | Not on List | 1 | Each | 5 | 5 | Waste (Recycling) | 2019-01-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10588-001025 | 10588 | 2019-01-04 11:19 | Section 3 | Material | Not on List | Not on List | 1 | each | 2288.78 | 2288.78 | Not Sure | 2019-01-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10581-001025 | 10581 | 2019-01-04 09:11 | Section 3 | Material | Not on List | Not on List | 2 | packs | 1377 | 2754 | Plastic Drainage | 2019-01-11 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 5 | EA | 61.48 | 307.4 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10499-001025 | 10499 | 2018-12-19 18:11 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1709.6 | 1709.6 | Miscellaneous | 2018-12-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10477-001025 | 10477 | 2018-12-19 08:56 | Section 3 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 2000 | Each | 0.49 | 980 | Miscellaneous | 2019-01-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10589-001025 | 10589 | 2019-01-04 11:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 4.2 | 16.8 | Small Tools (Consumables) | 2019-01-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10589-001025 | 10589 | 2019-01-04 11:25 | Section 4 | Material | Not on List | Not on List | 10 | Each | 27.98 | 279.8 | Small Tools (Consumables) | 2019-01-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10489-001025 | 10489 | 2018-12-19 15:17 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10682-001025 | 10682 | 2019-01-08 09:12 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10683-001025 | 10683 | 2019-01-08 09:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 5 | EA | 53.01 | 265.05 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10365-001025 | 10365 | 2018-12-14 10:19 | Section 3 | Material | Not on List | Not on List | 13 | no. of schedule components | 258.04 | 3354.52 | Fixings and Fasteners | 2019-01-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10690-001025 | 10690 | 2019-01-08 10:23 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-01-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10692-001025 | 10692 | 2019-01-08 10:22 | Section 4 | Material | Not on List | Not on List | 13.21 | tonne | NULL | 0 | Reinforcement | 2019-01-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10692-001025 | 10692 | 2019-01-08 10:22 | Section 4 | Material | Not on List | Not on List | 8 | number | NULL | 0 | Reinforcement | 2019-01-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10699-001025 | 10699 | 2019-01-08 11:45 | Section 3 | Material | Concrete Drainage | Not on List | 9 | No. | NULL | 0 | Concrete Drainage | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10659-001025 | 10659 | 2019-01-07 16:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2089.48 | Each | 1 | 2089.48 | PPE | 2019-01-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | Each | 166.43 | 3328.6 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | Each | 20.71 | 414.2 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 40 | Each | 34.82 | 1392.8 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 15 | EA | 47.04 | 705.6 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 80 | Each | 6.54 | 523.2 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 20 | Each | 48.86 | 977.2 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 200 | Each | 2.75 | 550 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 12 | Each | 314.15 | 3769.8 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26172-001025 | 26172 | 2019-11-05 16:54 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26173-001025 | 26173 | 2019-11-05 17:16 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26179-001025 | 26179 | 2019-11-05 17:30 | Core | Material | Not on List | Not on List | 40 | swabs | 118.75 | 4750 | Miscellaneous | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26179-001025 | 26179 | 2019-11-05 17:30 | Core | Material | Not on List | Not on List | 3 | tubes | 36 | 108 | Miscellaneous | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26180-001025 | 26180 | 2019-11-05 18:18 | Section 3 | Material | Bagged | OP Cement; 25kg bag (767201) | 50 | Each | 2.9 | 145 | Aggregate | 2019-11-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26181-001025 | 26181 | 2019-11-05 18:18 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26192-001025 | 26192 | 2019-11-06 08:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26196-001025 | 26196 | 2019-11-06 08:23 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26132-001025 | 26132 | 2019-11-04 17:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 25.15 | 251.5 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25939-001025 | 25939 | 2019-10-30 16:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 50.4 | 504 | Miscellaneous | 2019-11-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26157-001025 | 26157 | 2019-11-05 14:47 | Section 4 | Material | Not on List | Not on List | 1 | Each | 413.21 | 413.21 | Miscellaneous | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26211-001025 | 26211 | 2019-11-06 11:38 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 33.6 | 168 | Small Tools (Consumables) | 2019-11-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26211-001025 | 26211 | 2019-11-06 11:38 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 53.2 | 53 | Small Tools (Consumables) | 2019-11-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26219-001025 | 26219 | 2019-11-06 14:29 | Core | Material | Not on List | Not on List | 1 | ea | 486 | 486 | Training | 2019-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26225-001025 | 26225 | 2019-11-06 14:55 | Core | Material | Hazardous Waste | Not on List | 2 | containers | 40 | 80 | Miscellaneous | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26197-001025 | 26197 | 2019-11-06 08:23 | Section 5 | Material | Not on List | Not on List | 1 | sm | 606 | 606 | Not Sure | 2019-11-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1403 - Feeder Pillars & Earth Electrodes | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26243-001025 | 26243 | 2019-11-06 17:08 | Section 2 | Material | PPE, Small Tools and Consumables | Abso Net Plus 20 Ltr Clay Granules (534317) | 40 | Each | 11.24 | 450 | Miscellaneous | 2019-11-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26244-001025 | 26244 | 2019-11-06 17:13 | Section 6 | Material | PPE, Small Tools and Consumables | Abso Net Plus 20 Ltr Clay Granules (534317) | 40 | Each | 7.9 | 316 | Miscellaneous | 2019-11-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26245-001025 | 26245 | 2019-11-06 17:11 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 450 | 450 | Professional Services | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1601 - Piling and attendances | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-25952-001025 | 25952 | 2019-10-31 08:31 | Section 4 | Material | Not on List | Not on List | 166 | units | 29.05 | 4822.3 | Builders Merchants (General) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25952-001025 | 25952 | 2019-10-31 08:31 | Section 4 | Material | Not on List | Not on List | 4 | units | 46.78 | 187.12 | Builders Merchants (General) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25952-001025 | 25952 | 2019-10-31 08:31 | Section 4 | Material | Not on List | Not on List | 4 | units | 106.25 | 425 | Builders Merchants (General) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7200-001020 | 7200 | 2018-10-01 07:53 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 72 | Each | 6.29 | 452.88 | Miscellaneous | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25952-001025 | 25952 | 2019-10-31 08:31 | Section 4 | Material | Not on List | Not on List | 2 | units | 106.25 | 212.5 | Builders Merchants (General) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25952-001025 | 25952 | 2019-10-31 08:31 | Section 4 | Material | Not on List | Not on List | 20 | units | 37.92 | 758.4 | Builders Merchants (General) | 2019-11-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7207-001020 | 7207 | 2018-10-01 10:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 50 | each | 3.42 | 171 | Small Tools (Consumables) | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26262-001025 | 26262 | 2019-11-07 08:57 | Core | Material | Not on List | Not on List | 10 | Packs of 100 | NULL | 0 | Surveying Consumables | 2019-11-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26186-001025 | 26186 | 2019-11-06 07:33 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | 1.31 | 78.6 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26186-001025 | 26186 | 2019-11-06 07:33 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 3.7 | 18.5 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26255-001025 | 26255 | 2019-11-06 21:22 | Section 4 | Material | Not on List | Not on List | 1 | Each | 58.24 | 58.24 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1203 - Traffic Signal Installations | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26255-001025 | 26255 | 2019-11-06 21:22 | Section 4 | Material | Not on List | NULL | 1 | Each | 31.36 | 31.36 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1203 - Traffic Signal Installations | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26264-001025 | 26264 | 2019-11-07 09:07 | Section 4 | Material | Kerbs | Not on List | 10 | Ea | 4.9 | 49 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 1 | Each | 102.82 | 102.82 | Concrete Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 18 | Each | 166.43 | 2995.74 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain Seal (346400) | 38 | Each | 20.71 | 786.98 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Not on List | 2 | each | NULL | 0 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Not on List | 8 | each | NULL | 0 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Not on List | 1 | each | NULL | 0 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 36 | Each | 10.5 | 378 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7220-001021 | 7220 | 2018-10-01 13:53 | Section 3 | Material | Not on List | Not on List | 16 | No. | NULL | 0 | Plastic Drainage | 2018-10-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 72 | Each | 0.91 | 65.52 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 36 | Each | 1.98 | 71.28 | Plastic Drainage | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26258-001025 | 26258 | 2019-11-07 07:50 | Section 2 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 4000 | Each | 0.37 | 1480 | Builders Merchants (General) | 2019-11-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25874-001025 | 25874 | 2019-10-29 16:24 | Section 5 | Material | Not on List | NULL | 1 | EA | 157 | 157 | Surveying Consumables | 2019-11-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26285-001025 | 26285 | 2019-11-07 13:59 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-26290-001025 | 26290 | 2019-11-07 14:32 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 271.44 | 271 | Janitorial | 2019-11-11 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26290-001025 | 26290 | 2019-11-07 14:32 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 248.03 | 248 | PPE | 2019-11-11 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26290-001025 | 26290 | 2019-11-07 14:32 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 621.33 | 621 | Small Tools (Consumables) | 2019-11-11 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26293-001025 | 26293 | 2019-11-07 14:38 | Section 3 | Material | Kerbs | Not on List | 42 | NULL | NULL | 0 | Concrete Drainage | 2019-11-11 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26293-001025 | 26293 | 2019-11-07 14:38 | Section 3 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-11-11 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26293-001025 | 26293 | 2019-11-07 14:38 | Section 3 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-11-11 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26293-001025 | 26293 | 2019-11-07 14:38 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-11-11 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26293-001025 | 26293 | 2019-11-07 14:38 | Section 3 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-11-11 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26333-001025 | 26333 | 2019-11-08 07:59 | Section 6 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 30 | Each | 24.32 | 730 | Timber Products | 2019-11-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26333-001025 | 26333 | 2019-11-08 07:59 | Section 6 | Material | Not on List | Not on List | 5 | Each | NULL | 0 | Timber Products | 2019-11-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26337-001025 | 26337 | 2019-11-08 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | ea | 13.38 | 54 | Small Tools (Consumables) | 2019-11-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25811-001025 | 25811 | 2019-10-28 14:19 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2019-10-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 401 - Safety Barriers | IMO Queue | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6957-00752 | 6957 | 2018-09-25 11:46 | Section 4 | Material | Not on List | Not on List | 1 | Each | 6.8 | 6.8 | Miscellaneous | 2018-10-10 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26385-001025 | 26385 | 2019-11-08 15:25 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 49.5 | 50 | Concrete Accessories | 2019-11-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26385-001025 | 26385 | 2019-11-08 15:25 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 26.5 | 27 | Fixings and Fasteners | 2019-11-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26392-001025 | 26392 | 2019-11-11 07:39 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26187-001025 | 26187 | 2019-11-06 07:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 25.13 | 251.3 | Miscellaneous | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26408-001025 | 26408 | 2019-11-11 10:54 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26354-001025 | 26354 | 2019-11-08 12:53 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26267-001025 | 26267 | 2019-11-07 08:42 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26248-001025 | 26248 | 2019-11-06 17:34 | Section 4 | Material | Not on List | Not on List | 1 | Each | 880.88 | 880.88 | Miscellaneous | 2019-11-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26343-001025 | 26343 | 2019-11-08 11:13 | Section 5 | Material | NULL | NULL | 4 | Each | 50.86 | 203.44 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7153-001020 | 7153 | 2018-09-28 12:53 | Section 4 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 112 | Each | 3.56 | 398.72 | Concrete Drainage | 2018-10-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26343-001025 | 26343 | 2019-11-08 11:13 | Section 5 | Material | NULL | NULL | 2 | Each | 11.95 | 23.9 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26343-001025 | 26343 | 2019-11-08 11:13 | Section 5 | Material | NULL | NULL | 5 | Each | 36 | 180 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26343-001025 | 26343 | 2019-11-08 11:13 | Section 5 | Material | NULL | NULL | 50 | Each | 1.75 | 87.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26427-001025 | 26427 | 2019-11-11 14:23 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-26399-001025 | 26399 | 2019-11-11 08:43 | Section 2 | Material | Not on List | Not on List | 2.118 | T | NULL | 0 | Rebar and Mesh | 2019-11-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26423-001025 | 26423 | 2019-11-11 13:32 | Section 4 | Material | NULL | NULL | 96 | Ea | 12 | 1152 | Small Tools (Consumables) | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26423-001025 | 26423 | 2019-11-11 13:32 | Section 4 | Material | NULL | NULL | 1 | ea | 30 | 30 | Small Tools (Consumables) | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25743-001025 | 25743 | 2019-10-25 11:50 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Office Supplies | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26164-001025 | 26164 | 2019-11-05 15:40 | Section 6 | Material | Not on List | Not on List | 55 | each | 18.97 | 1043.35 | Builders Merchants (General) | 2019-11-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7212-001020 | 7212 | 2018-10-01 12:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1108.8 | 1108.8 | Miscellaneous | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26164-001025 | 26164 | 2019-11-05 15:40 | Section 6 | Material | Not on List | Not on List | 1 | Pallet | 0.92 | 0.92 | Builders Merchants (General) | 2019-11-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26215-001025 | 26215 | 2019-11-06 12:40 | Section 4 | Material | Not on List | Not on List | 1 | Each | 323.78 | 323.78 | Miscellaneous | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7156-001020 | 7156 | 2018-09-28 13:21 | Section 4 | Material | Hazardous Waste | Oil/water/diesel - 205L drum | 43 | Each | 195 | 8385 | Waste (General) | 2018-10-02 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26109-001025 | 26109 | 2019-11-04 14:48 | Section 5 | Material | Not on List | Not on List | 1 | SM | 246 | 246 | Fixings and Fasteners | 2019-11-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26470-001025 | 26470 | 2019-11-12 11:32 | Core | Material | Not on List | Not on List | 1 | EACH | 835.86 | 836 | Miscellaneous | 2019-11-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26471-001025 | 26471 | 2019-11-12 11:35 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 1088.14 | 1088 | Miscellaneous | 2019-11-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26472-001025 | 26472 | 2019-11-12 11:28 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2055.14 | each | 1 | 2055 | Janitorial | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7156-001020 | 7156 | 2018-09-28 13:21 | Section 4 | Material | Hazardous Waste | Oil/water/diesel - 205L drum | 8 | Hr | 75 | 600 | Waste (General) | 2018-10-02 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26473-001025 | 26473 | 2019-11-12 11:37 | Section 5 | Material | Not on List | Not on List | 1 | EACH | 1370.43 | 1370 | Miscellaneous | 2019-11-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26474-001025 | 26474 | 2019-11-12 11:40 | Section 6 | Material | Not on List | Not on List | 1 | EACH | 289.29 | 289 | Miscellaneous | 2019-11-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26418-001025 | 26418 | 2019-11-11 12:15 | Section 4 | Material | Kerbs | Not on List | 5 | Each | 151.94 | 759.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26418-001025 | 26418 | 2019-11-11 12:15 | Section 4 | Material | Bagged | Not on List | 20 | Each | 31.85 | 637 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26418-001025 | 26418 | 2019-11-11 12:15 | Section 4 | Material | NULL | Not on List | 1 | Each | 115 | 115 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26437-001025 | 26437 | 2019-11-11 16:52 | Section 5 | Material | Saint Gobain Castings | NULL | 1 | SM | 1091.14 | 1091.14 | Ductile Drainage | 2019-11-29 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26482-001025 | 26482 | 2019-11-12 12:02 | Section 4 | Material | Not on List | Not on List | 32 | Each | 6.9 | 220.8 | Concrete Drainage | 2019-11-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26495-001025 | 26495 | 2019-11-12 15:28 | Core | Material | Not on List | Not on List | 1 | ea | 920 | 920 | Training | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26496-001025 | 26496 | 2019-11-12 15:06 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 308.59 | 309 | Small Tools (Consumables) | 2019-11-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26496-001025 | 26496 | 2019-11-12 15:06 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 1089.7 | 1090 | PPE | 2019-11-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26496-001025 | 26496 | 2019-11-12 15:06 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 56.76 | 57 | Janitorial | 2019-11-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26433-001025 | 26433 | 2019-11-11 16:23 | Section 5 | Material | Combined Drainage | NULL | 1 | SM | 20770 | 20770 | Miscellaneous | 2019-11-12 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26497-001025 | 26497 | 2019-11-12 16:03 | Core | Material | Not on List | Not on List | 1 | NULL | 96.75 | 97 | Miscellaneous | 2019-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26510-001025 | 26510 | 2019-11-12 17:38 | Core | Material | Not on List | Not on List | 1 | ea | 687.61 | 688 | Office Supplies | 2019-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26511-001025 | 26511 | 2019-11-12 17:50 | Core | Material | Not on List | Not on List | 1 | ea | 84.76 | 85 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26512-001025 | 26512 | 2019-11-12 17:52 | Core | Material | Not on List | Not on List | 1 | ea | 1597.5 | 1598 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26513-001025 | 26513 | 2019-11-12 17:54 | Core | Material | Not on List | Not on List | 1 | ea | 270.18 | 270 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26514-001025 | 26514 | 2019-11-12 17:57 | Core | Material | Not on List | Not on List | 1 | ea | 208.04 | 208 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26516-001025 | 26516 | 2019-11-12 17:59 | Core | Material | Not on List | Not on List | 1 | ea | 215.94 | 216 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26517-001025 | 26517 | 2019-11-12 18:01 | Core | Material | Not on List | Not on List | 1 | ea | 135 | 135 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26518-001025 | 26518 | 2019-11-12 18:03 | Core | Material | Not on List | Not on List | 1 | ea | 572.4 | 572 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 2 | Each | 212.27 | 424.54 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 1 | Each | 871.8 | 871.8 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 30 | Each | 70.62 | 2118.6 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 15 | Each | 52.97 | 794.55 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 15 | Each | 44.89 | 673.35 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 30 | Each | 48.92 | 1467.6 | Concrete Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 30 | Each | 189 | 5670 | Plastic Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26406-001025 | 26406 | 2019-11-11 09:42 | Section 4 | Material | Not on List | Not on List | 200 | Each | 2.47 | 494 | Plastic Drainage | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26519-001025 | 26519 | 2019-11-12 18:05 | Core | Material | Not on List | Not on List | 1 | ea | 771.38 | 771 | Office Supplies | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26531-001025 | 26531 | 2019-11-13 08:35 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-26533-001025 | 26533 | 2019-11-13 09:16 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26131-001025 | 26131 | 2019-11-04 10:03 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Fixings and Fasteners | 2019-11-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | IMO Queue | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26537-001025 | 26537 | 2019-11-13 10:16 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 2675.07 | 2675 | Miscellaneous | 2019-11-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26455-001025 | 26455 | 2019-11-12 08:10 | Section 4 | Material | Not on List | Not on List | 270 | Each | 36.24 | 9784.8 | Miscellaneous | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26455-001025 | 26455 | 2019-11-12 08:10 | Section 4 | Material | NULL | Not on List | 1 | Each | 550 | 550 | Miscellaneous | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26540-001025 | 26540 | 2019-11-13 12:33 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4605.14 | each | 1 | 4605 | PPE | 2019-11-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-26484-001025 | 26484 | 2019-11-12 13:25 | Section 4 | Material | Not on List | Not on List | 5 | Each | 50 | 250 | Electrical | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7807-001023 | 7807 | 2018-10-15 15:57 | Section 3 | Material | Not on List | Not on List | 16 | No | 36.75 | 588 | Builders Merchants (General) | 2018-11-02 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7968-001023 | 7968 | 2018-10-18 16:06 | Section 4 | Material | Not on List | Not on List | 16 | Each | 110.27 | 1764.32 | Geotextiles | 2018-10-22 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 604 - Deposition | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 4 | EA | 376.8 | 1507.2 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8083-001023 | 8083 | 2018-10-22 14:06 | Section 4 | Material | Not on List | Not on List | 76 | number | NULL | 0 | Reinforcement | 2018-10-26 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8083-001023 | 8083 | 2018-10-22 14:06 | Section 4 | Material | Not on List | Not on List | 16 | number | NULL | 0 | Reinforcement | 2018-10-26 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7931-001023 | 7931 | 2018-10-17 18:31 | Section 4 | Material | Not on List | Not on List | 1 | Each | 7711.17 | 7711.17 | Damage Charges | 2018-10-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8086-001023 | 8086 | 2018-10-22 15:28 | Section 4 | Material | Not on List | Not on List | 1 | Weekly | 550 | 550 | Miscellaneous | 2018-06-01 | RVP 417 - 1339631 - Girton Compound Huntingdon Rd A1307 | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8087-001023 | 8087 | 2018-10-22 15:48 | Section 4 | Material | Not on List | Not on List | 1 | Deployment Charge | 1519 | 1519 | Miscellaneous | 2018-10-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8059-001023 | 8059 | 2018-10-22 09:00 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pack | 3.79 | 37.9 | Miscellaneous | 2018-10-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7437-001022 | 7437 | 2018-10-05 10:39 | Section 4 | Material | Not on List | Not on List | 6 | boxes of 5 | 11.23 | 67.38 | Not Sure | 2018-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8095-001023 | 8095 | 2018-10-22 16:02 | Section 3 | Material | Aggregate | Not on List | 3500 | m3 | 43.08 | 150780 | Aggregate | 2018-10-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 2 | EA | 452.16 | 904.32 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8095-001023 | 8095 | 2018-10-22 16:02 | Section 3 | Material | Aggregate | Not on List | 3500 | m3 | 43.08 | 150780 | Aggregate | 2018-10-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7959-001023 | 7959 | 2018-10-18 12:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 294.2 | 294.2 | PPE | 2018-10-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7959-001023 | 7959 | 2018-10-18 12:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 337.97 | 337.97 | Small Tools (Consumables) | 2018-10-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8073-001023 | 8073 | 2018-10-22 11:17 | Section 4 | Material | Not on List | Not on List | 10 | Each | NULL | 0 | Not Sure | 2018-10-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8126-001023 | 8126 | 2018-10-23 11:16 | Section 4 | Material | Not on List | Not on List | 300 | NULL | NULL | 0 | Concrete Drainage | 2018-10-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8106-001023 | 8106 | 2018-10-23 07:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 401.56 | 401.56 | Janitorial | 2018-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 3 | EA | 452.16 | 1356.48 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8086-001023 | 8086 | 2018-10-22 15:28 | Section 4 | Material | Not on List | Not on List | 1 | Weekly | 550 | 550 | Miscellaneous | 2018-06-01 | RVP 417 - 1339631 - Girton Compound Huntingdon Rd A1307 | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8108-001023 | 8108 | 2018-10-23 07:36 | Section 4 | Material | Not on List | Not on List | 4 | number | 6.75 | 27 | Not Sure | 2018-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8126-001023 | 8126 | 2018-10-23 11:16 | Section 4 | Material | Not on List | Not on List | 300 | Each | 31.37 | 9411 | Concrete Drainage | 2018-11-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8083-001023 | 8083 | 2018-10-22 14:06 | Section 4 | Material | Not on List | Not on List | 76 | Each | 93.93 | 7138.68 | Concrete Accessories | 2018-10-26 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8083-001023 | 8083 | 2018-10-22 14:06 | Section 4 | Material | Not on List | Not on List | 16 | Each | 51.87 | 829.92 | Concrete Accessories | 2018-10-26 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | NULL | 0 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | NULL | 0 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8087-001023 | 8087 | 2018-10-22 15:48 | Section 4 | Material | Not on List | Not on List | 1 | Deployment Charge | 1519 | 1519 | Miscellaneous | 2018-10-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8039-001023 | 8039 | 2018-10-19 14:21 | Section 4 | Material | Not on List | Not on List | 200 | Each | 6.98 | 1396 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-25 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 1 | EA | 452.16 | 452.16 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500x1000 D/S (991900) | 2 | Each | 121.25 | 243 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500x750 D/S (991899) | 1 | Each | 90.94 | 91 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500X500 D/S (991898) | 1 | Each | 80.51 | 81 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 1 | Each | 102.82 | 103 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 100 | Each | 16.49 | 1649 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 7 | Each | 53.01 | 371 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 750 D/S (913226) | 7 | Each | 61.48 | 430 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | Not on List | 7 | NULL | NULL | 0 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8186-001023 | 8186 | 2018-10-24 08:34 | Section 4 | Material | Not on List | Not on List | 0.068 | Tonne | NULL | 0 | Reinforcement | 2018-10-26 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN20 - Bar Hill Junction West Bridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8186-001023 | 8186 | 2018-10-24 08:34 | Section 4 | Material | Not on List | Not on List | 0.068 | Tonne | NULL | 0 | Reinforcement | 2018-10-26 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN21 - Bar Hill Junction East Bridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 1 | EA | 577.15 | 577.15 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8192-001023 | 8192 | 2018-10-24 11:16 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-10-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8143-001023 | 8143 | 2018-10-23 15:28 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.45 | 147 | Surveying Consumables | 2018-10-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8123-001023 | 8123 | 2018-10-23 09:14 | Section 4 | Material | Not on List | Not on List | 4 | Each | 39.03 | 156.12 | Builders Merchants (General) | 2018-10-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | 16.84 | 134.72 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | 39.7 | 317.6 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8125-001023 | 8125 | 2018-10-23 10:26 | Section 4 | Material | Not on List | Not on List | 550 | LM | 0.46 | 253 | Miscellaneous | 2018-10-25 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8003-001023 | 8003 | 2018-10-19 09:12 | Section 4 | Material | Not on List | Not on List | 20 | 25kg Bag | 9.34 | 186.8 | Not Sure | 2018-10-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500x1000 D/S (991900) | 2 | Each | 121.25 | 242.5 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500x750 D/S (991899) | 1 | Each | 90.94 | 90.94 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1500X500 D/S (991898) | 1 | Each | 80.51 | 80.51 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 1 | EA | 271.01 | 271.01 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 1 | Each | 102.82 | 102.82 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 100 | Each | 16.49 | 1649 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 7 | Each | 53.01 | 371.07 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 750 D/S (913226) | 7 | Each | 61.48 | 430.36 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8177-001023 | 8177 | 2018-10-24 08:07 | Section 3 | Material | Concrete Drainage | Not on List | 7 | ea | 232.01 | 1624.07 | Concrete Drainage | 2018-10-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | 16.84 | 134.72 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8155-001023 | 8155 | 2018-10-23 17:13 | Section 3 | Material | Not on List | Not on List | 8 | no | 39.7 | 317.6 | Builders Merchants (General) | 2018-10-26 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8204-001023 | 8204 | 2018-10-24 16:14 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No. | NULL | 0 | Small Tools (Consumables) | 2018-10-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | Saint Gobain Castings | Not on List | 96 | no | 31.37 | 3012 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5162-0080 | 5162 | 2018-08-15 13:18 | Section 4 | Material | Concrete Drainage | Not on List | 1 | EA | 248.57 | 248.57 | Concrete Drainage | 2018-08-29 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | Saint Gobain Castings | Not on List | 26 | no | 31.37 | 816 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 50 | Each | 81.73 | 4087 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8209-001023 | 8209 | 2018-10-24 17:18 | Section 4 | Material | Not on List | Not on List | 48 | NULL | NULL | 0 | Concrete Accessories | 2018-10-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8009-001023 | 8009 | 2018-10-19 09:27 | Section 4 | Material | Not on List | Not on List | 150 | Each | 15.77 | 2365.5 | Plastic Drainage | 2018-10-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8009-001023 | 8009 | 2018-10-19 09:27 | Section 4 | Material | Not on List | Not on List | 150 | Each | 15.77 | 2365.5 | Plastic Drainage | 2018-10-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8009-001023 | 8009 | 2018-10-19 09:27 | Section 4 | Material | Not on List | Not on List | 200 | Each | 2.92 | 584 | Plastic Drainage | 2018-10-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5190-00117 | 5190 | 2018-08-16 07:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 768.16 | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8009-001023 | 8009 | 2018-10-19 09:27 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 1.44 | 1440 | Plastic Drainage | 2018-10-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8234-001023 | 8234 | 2018-10-25 11:22 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1130.86 | 1130.86 | Small Tools (Consumables) | 2018-10-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8227-001023 | 8227 | 2018-10-25 09:31 | Section 4 | Material | PPE, Small Tools and Consumables | Paint Roller And Tray Set 9" Rskit1 (704256) | 50 | Each | 3.42 | 171 | Small Tools (Consumables) | 2018-10-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | NULL | Not on List | 96 | no | 31.37 | 3011.52 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | NULL | Not on List | 26 | no | 31.37 | 815.62 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8221-001023 | 8221 | 2018-10-25 07:44 | Section 4 | Material | NULL | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 50 | Each | 74.3 | 3715 | Ductile Drainage | 2018-11-09 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8240-001023 | 8240 | 2018-10-25 13:42 | Section 3 | Material | Not on List | Not on List | 1 | EA | 71.99 | 71.99 | Miscellaneous | 2018-10-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8282-001023 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 18 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8301-001023 | 8301 | 2018-10-26 11:16 | Section 3 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 36 | Each | 24.32 | 876 | Builders Merchants (General) | 2018-10-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7962 | 7962 | 2018-10-18 13:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1680 | 1680 | Not Sure | 2018-11-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8301-001023 | 8301 | 2018-10-26 11:16 | Section 3 | Material | NULL | 2440x1220x18mm Shuttering Ply (683573) | 36 | Each | 24.32 | 875.52 | Builders Merchants (General) | 2018-10-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8311-001023 | 8311 | 2018-10-26 13:11 | Section 4 | Material | Not on List | Not on List | 3 | boxes | NULL | 0 | Not Sure | 2018-10-31 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 6 | number | NULL | 0 | Not Sure | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Concrete Accessories | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 6 | number | NULL | 0 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Signage | Directional Signage - 390 x 510 | 8 | Each | 7.9441 | 64 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Signage | Directional Signage - 390 x 510 | 6 | Each | 7.9441 | 48 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8236-001023 | 8236 | 2018-10-25 11:30 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2518 | 2518 | PPE | 2018-10-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 32 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8367-001023 | 8367 | 2018-10-29 13:07 | Section 4 | Material | Not on List | Not on List | 3 | polybottles | NULL | 0 | Not Sure | 2018-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8192-001023 | 8192 | 2018-10-24 11:16 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 350.58 | 350.58 | Small Tools (Consumables) | 2018-10-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8434-001023 | 8434 | 2018-10-30 10:30 | Section 3 | Material | Not on List | Not on List | 50 | Rolls | NULL | 0 | Builders Merchants (General) | 2018-11-01 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8439-001023 | 8439 | 2018-10-30 11:24 | Section 4 | Material | Bagged | Building Sand Bulk Bag (938155) | 4 | Each | 32.74 | 131 | Builders Merchants (General) | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8311-001023 | 8311 | 2018-10-26 13:11 | Section 4 | Material | Not on List | Not on List | 3 | Box | 63 | 189 | Fixings and Fasteners | 2018-10-31 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8311-001023 | 8311 | 2018-10-26 13:11 | Section 4 | Material | NULL | Not on List | 1 | Each | 30 | 30 | Fixings and Fasteners | 2018-10-31 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8367-001023 | 8367 | 2018-10-29 13:07 | Section 4 | Material | Not on List | Not on List | 3 | Each | 28 | 84 | Concrete Accessories | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8367-001023 | 8367 | 2018-10-29 13:07 | Section 4 | Material | NULL | Not on List | 1 | Each | 40 | 40 | Concrete Accessories | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 55.35 | 55 | PPE | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 20 | NULL | 6.29 | 126 | Miscellaneous | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 16 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8398-001023 | 8398 | 2018-10-29 16:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3000 | Each | 0.37 | 1110 | Miscellaneous | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8391-001023 | 8391 | 2018-10-29 16:26 | Section 4 | Material | NULL | OP Cement; 25kg bag (767201) | 56 | Each | 2.9 | 162.4 | Miscellaneous | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8373-001023 | 8373 | 2018-10-29 12:08 | Section 4 | Material | Not on List | Not on List | 10 | boxes | NULL | 0 | PPE | 2018-11-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8373-001023 | 8373 | 2018-10-29 12:08 | Section 4 | Material | Not on List | Not on List | 100 | each | NULL | 0 | PPE | 2018-11-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8434-001023 | 8434 | 2018-10-30 10:30 | Section 3 | Material | Not on List | Not on List | 50 | Rolls | 6.1 | 305 | Builders Merchants (General) | 2018-11-01 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7972-001023 | 7972 | 2018-10-18 16:28 | Section 4 | Material | Not on List | Not on List | 1 | Each | 69.21 | 69.21 | Plastic Drainage | 2018-11-01 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8464-001023 | 8464 | 2018-10-30 18:14 | Section 3 | Material | PPE, Small Tools and Consumables | Helmet Attachment-jsp Navy Blue Helmet Warmer (271301) | 31 | Each | 5.43 | 168 | PPE | 2018-11-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8471-001023 | 8471 | 2018-10-30 21:48 | Section 4 | Material | Aggregate | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8471-001023 | 8471 | 2018-10-30 21:48 | Section 4 | Material | Aggregate | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8471-001023 | 8471 | 2018-10-30 21:48 | Section 4 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 1 | Price Per Thousand | 345 | 345 | Builders Merchants (General) | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8471-001023 | 8471 | 2018-10-30 21:48 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Builders Merchants (General) | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8472-001023 | 8472 | 2018-10-30 22:32 | Section 4 | Material | Bagged | OP Cement; 25kg bag (767201) | 24 | Each | 2.9 | 70 | Miscellaneous | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8472-001023 | 8472 | 2018-10-30 22:32 | Section 4 | Material | Bagged | Not on List | 12 | NULL | NULL | 0 | Miscellaneous | 2018-10-31 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-8475-001023 | 8475 | 2018-10-31 07:41 | Section 4 | Material | Not on List | Not on List | 15 | number | NULL | 0 | Not Sure | 2018-11-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-8475-001023 | 8475 | 2018-10-31 07:41 | Section 4 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Not Sure | 2018-11-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-8475-001023 | 8475 | 2018-10-31 07:41 | Section 4 | Material | Not on List | Not on List | 4 | number | NULL | 0 | Not Sure | 2018-11-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 358.12 | 358.12 | Small Tools (Consumables) | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 10 | NULL | 650.69 | 6506.9 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 72 | 72 | PPE | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 20 | NULL | 6.29 | 125.8 | Miscellaneous | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8443-001023 | 8443 | 2018-10-30 10:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 153.86 | 153.86 | Janitorial | 2018-11-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15098-001025 | 15098 | 2019-04-02 09:12 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-4997-0011 | 4997 | 2018-08-13 15:45 | Section 4 | Material | Not on List | Not on List | 9 | Each | 183.3 | 20 | Not Sure | 2018-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14645-001025 | 14645 | 2019-03-26 10:00 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 510 | 510 | Laboratory Equipment / Certification | 2019-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14844-001025 | 14844 | 2019-03-28 09:39 | Core | Material | Not on List | Not on List | 25 | Bundles | 9 | 225 | Surveying Consumables | 2019-04-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14844-001025 | 14844 | 2019-03-28 09:39 | Core | Material | Not on List | Not on List | 10 | Bundles | 9 | 90 | Surveying Consumables | 2019-04-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14844-001025 | 14844 | 2019-03-28 09:39 | Core | Material | Not on List | Not on List | 10 | Bundles | 9 | 90 | Surveying Consumables | 2019-04-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14844-001025 | 14844 | 2019-03-28 09:39 | Core | Material | Not on List | Not on List | 15 | Bundles | 9 | 135 | Surveying Consumables | 2019-04-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14528-001025 | 14528 | 2019-03-22 12:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | 162.11 | 324.22 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | CPM 1800 Cover Slab 600x600 Opening (985438) | 1 | Each | 149.9 | 149.9 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 1 | Each | 165.1 | 165.1 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | CPM 750mm Concrete Rocker (249360) | 2 | Each | 198.12 | 396.24 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | CPM 750mm Concrete Socket (890395) | 1 | Each | 198.12 | 198.12 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 198.12 | 198.12 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | CPM 675mm Concrete Pipe 2.5m (249358) | 1 | Each | 148.8 | 148.8 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | Not on List | 1 | Each | 3540 | 3540 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | Not on List | 3000 | No | 1.85 | 5550 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14638-001025 | 14638 | 2019-03-26 06:53 | Section 5 | Material | Concrete Drainage | Not on List | 2000 | No | 0.31 | 620 | Concrete Drainage | 2019-03-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14671-001025 | 14671 | 2019-03-26 13:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 123.3 | 246.6 | Small Tools (Consumables) | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5895-00560 | 5895 | 2018-08-31 14:00 | Section 3 | Material | Not on List | Not on List | 1 | ea | 567.63 | 567.63 | Damage Charges | 2018-09-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5739-00526 | 5739 | 2018-08-29 09:54 | Section 3 | Material | Not on List | Not on List | 1 | EA | 5440.13 | 5440.13 | Damage Charges | 2018-08-30 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5884-00563 | 5884 | 2018-08-31 14:48 | Section 3 | Material | Not on List | Not on List | 2 | ea | 55.44 | 110.88 | Miscellaneous | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15112-001025 | 15112 | 2019-04-02 11:11 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15112-001025 | 15112 | 2019-04-02 11:11 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5884-00563 | 5884 | 2018-08-31 14:48 | Section 3 | Material | Not on List | Not on List | 2 | ea | 43.12 | 86.24 | Miscellaneous | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14768-001025 | 14768 | 2019-03-27 14:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2104.45 | 2104.45 | Small Tools (Consumables) | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15116-001025 | 15116 | 2019-04-02 11:29 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 12.84 | 13 | Electrical | 2019-04-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | IMO - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14975-001025 | 14975 | 2019-04-01 07:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 18.95 | 189.5 | Small Tools (Consumables) | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14975-001025 | 14975 | 2019-04-01 07:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 63.91 | 639.1 | NULL | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 380 | meters | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 90 | number | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 90 | number | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-5884-00563 | 5884 | 2018-08-31 14:48 | Section 3 | Material | Not on List | Not on List | 1 | ea | 24.64 | 24.64 | Miscellaneous | 2018-09-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15122-001025 | 15122 | 2019-04-02 12:31 | Section 2 | Material | Not on List | Not on List | 90 | number | NULL | 0 | Miscellaneous | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15127-001025 | 15127 | 2019-04-02 13:29 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 6 | Metres | 5.43 | 33 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14978-001025 | 14978 | 2019-04-01 07:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 217.8 | 217.8 | PPE | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15137-001025 | 15137 | 2019-04-02 14:29 | Section 5 | Material | Not on List | Not on List | 1 | EACH | 331.05 | 331 | Miscellaneous | 2019-04-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15139-001025 | 15139 | 2019-04-02 14:32 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 5619.3 | 5619 | Miscellaneous | 2019-04-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14562-001025 | 14562 | 2019-03-23 13:33 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-03-25 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15015-001025 | 15015 | 2019-04-01 09:47 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 268.8 | 268.8 | PPE | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15108-001025 | 15108 | 2019-04-02 11:00 | Section 3 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 500 | Each | 3.04 | 1520 | Miscellaneous | 2019-04-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5828-00517 | 5828 | 2018-08-30 17:05 | Section 4 | Material | Not on List | Not on List | 2 | tonnes | 32.74 | 65.48 | Builders Merchants (General) | 2018-08-07 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15108-001025 | 15108 | 2019-04-02 11:00 | Section 3 | Material | Not on List | Not on List | 1 | Each | 24.45 | 24.45 | Miscellaneous | 2019-04-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15106-001025 | 15106 | 2019-04-02 10:12 | Section 4 | Material | Not on List | Not on List | 1 | pack of 100 | 76.5 | 76.5 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15106-001025 | 15106 | 2019-04-02 10:12 | Section 4 | Material | Not on List | Not on List | 1 | pack of 100 | 38.97 | 38.97 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15106-001025 | 15106 | 2019-04-02 10:12 | Section 4 | Material | Not on List | Not on List | 1 | pack of 100 | 29.32 | 29.32 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5828-00517 | 5828 | 2018-08-30 17:05 | Section 4 | Material | Not on List | Not on List | 1 | 25 litre | 41.81 | 41.81 | Builders Merchants (General) | 2018-08-07 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15100-001025 | 15100 | 2019-04-02 09:31 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 16 | Each | 116.88 | 1870.08 | Geotextiles | 2019-04-09 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15109-001025 | 15109 | 2019-04-02 11:09 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | 3.42 | 205.2 | Small Tools (Consumables) | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15136-001025 | 15136 | 2019-04-02 14:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 809.78 | 809.78 | Small Tools (Consumables) | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15182-001025 | 15182 | 2019-04-03 07:11 | Section 2 | Material | Bagged | Sharp Sand Bulk Bag (938208) | 1 | Each | 32.74 | 33 | Builders Merchants (General) | 2019-04-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 601 - Topsoil Strip, Store, Dispose | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15182-001025 | 15182 | 2019-04-03 07:11 | Section 2 | Material | Bagged | OP Cement; 25kg bag (767201) | 20 | Each | 2.9 | 58 | Builders Merchants (General) | 2019-04-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 601 - Topsoil Strip, Store, Dispose | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15145-001025 | 15145 | 2019-04-02 14:47 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 3623.1 | 3623.1 | Miscellaneous | 2019-04-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14937-001025 | 14937 | 2019-03-29 11:57 | Section 4 | Material | Not on List | Not on List | 40 | Each | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14599-001025 | 14599 | 2019-03-25 13:48 | Core | Material | Not on List | Not on List | 1 | Number | 386 | 386 | Office Supplies | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15059-001025 | 15059 | 2019-04-01 17:00 | Section 3 | Material | Not on List | Not on List | 50 | No. | 52.76 | 2638 | Plastic Drainage | 2019-04-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15059-001025 | 15059 | 2019-04-01 17:00 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 687.5 | Plastic Drainage | 2019-04-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15059-001025 | 15059 | 2019-04-01 17:00 | Section 3 | Material | Not on List | Not on List | 30 | No. | 37.6 | 1128 | Plastic Drainage | 2019-04-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15062-001025 | 15062 | 2019-04-01 15:29 | Section 5 | Material | Not on List | Not on List | 1 | each | 103.11 | 103.11 | Waste (General) | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15062-001025 | 15062 | 2019-04-01 15:29 | Section 5 | Material | Not on List | Not on List | 2 | each | 485.3 | 970.6 | Professional Services | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15062-001025 | 15062 | 2019-04-01 15:29 | Section 5 | Material | Not on List | Not on List | 70 | EACH | 17.49 | 1224.3 | Timber Products | 2019-04-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15062-001025 | 15062 | 2019-04-01 15:29 | Section 5 | Material | Not on List | Not on List | 200 | M2 | 3.25 | 650 | Miscellaneous | 2019-04-04 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 9 | No | 70.61 | 635.49 | Concrete Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | 52.95 | 105.9 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 8 | No | 44.88 | 359.04 | Concrete Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 14 | No | 36.94 | 517.16 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 48.92 | 489.2 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 8 | No | 85.23 | 681.84 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | 63.93 | 127.86 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 6 | No | 55.13 | 330.78 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 10 | No | 38.08 | 380.8 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 8 | Each | 61.53 | 492.24 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 119.52 | 119.52 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 89.64 | 89.64 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 126.1 | 126.1 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 4 | NULL | 94.57 | 378.28 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 4 | NULL | 83.73 | 334.92 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 4 | NULL | 106.96 | 427.84 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 5 | Each | 162.11 | 810.55 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 121.58 | 121.58 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 1 | NULL | 149.8 | 149.8 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | CPM 1800 Cover Slab 600x600 Opening (985438) | 1 | Each | 149.8 | 149.8 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15029-001025 | 15029 | 2019-04-01 12:16 | Section 5 | Material | Concrete Drainage | Not on List | 15 | No Carton's | 40.61 | 609.15 | Concrete Drainage | 2019-04-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5864-00556 | 5864 | 2018-08-31 13:42 | Section 3 | Material | Not on List | Not on List | 20 | no | 8.8 | 176 | Electrical | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14793-001025 | 14793 | 2019-03-27 16:49 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1050.43 | 1050.43 | PPE | 2019-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15151-001025 | 15151 | 2019-04-02 15:34 | Section 3 | Material | Not on List | Not on List | 1 | No | 100.23 | 100.23 | Damage Charges | 2019-04-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 48 | Each | 24.99 | 1199.52 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 106 | Each | 3.65 | 386.9 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 220 | Each | 2 | 440 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 84 | Each | 37.6 | 3158.4 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 180 | Each | 7.06 | 1270.8 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 375 | Each | 2.97 | 1113.75 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 38 | NULL | 130.26 | 4949.88 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5864-00556 | 5864 | 2018-08-31 13:42 | Section 3 | Material | Not on List | Not on List | 100 | lm | 9.64 | 964 | Electrical | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 85 | NULL | 18.84 | 1601.4 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 180 | NULL | 9.76 | 1756.8 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 225mm x 225mm Ridgdrain 45deg Junction (878042) | 6 | Each | 56.17 | 337.02 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 10 | NULL | 156.5 | 1565 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 6 | NULL | 188.37 | 1130.22 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 9 | NULL | 131.32 | 1181.88 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 300mm x 150mm Ridgidrain 45deg Junction (878090) | 8 | Each | 47.96 | 383.68 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 45deg Junction (878038) | 8 | Each | 42.87 | 342.96 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 199.28 | 398.56 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 52.77 | 105.54 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5952-00585 | 5952 | 2018-09-03 09:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Ltrs | 2.77 | 277 | Miscellaneous | 2018-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 27 | NULL | 179.74 | 4852.98 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 60 | NULL | 38.36 | 2301.6 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 135 | NULL | 22.36 | 3018.6 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 7 | NULL | 164.37 | 1150.59 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 4 | NULL | 145 | 580 | Plastic Drainage | 2019-04-05 | EB5/10 Works Access, A14 Eastbound, Central Reservation between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15069-001025 | 15069 | 2019-04-02 06:37 | Section 5 | Material | Not on List | Not on List | 8 | NULL | 21.29 | 170.32 | Plastic Drainage | 2019-04-05 | EB5/12 Stockyard Access, A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14820-001025 | 14820 | 2019-03-27 18:55 | Section 5 | Material | Not on List | Not on List | 4 | No | 38.09 | 152.36 | Concrete Drainage | 2019-04-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15123-001025 | 15123 | 2019-04-02 13:00 | Section 4 | Material | Not on List | Not on List | 100 | Each | 7.5 | 750 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15118-001025 | 15118 | 2019-04-02 11:41 | Section 4 | Material | NULL | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 1 | Pack 504 | 173.88 | 173.88 | Blocks and Bricks | 2019-04-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15176-001025 | 15176 | 2019-04-02 17:22 | Section 4 | Material | Not on List | Not on List | 112 | Each | 38.09 | 4266.08 | Builders Merchants (General) | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15176-001025 | 15176 | 2019-04-02 17:22 | Section 4 | Material | Not on List | Not on List | 30 | Each | 2.97 | 89.1 | Builders Merchants (General) | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15132-001025 | 15132 | 2019-04-02 14:09 | Core | Material | Not on List | Not on List | 8 | NULL | 37 | 296 | Office Supplies | 2019-04-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14658-001025 | 14658 | 2019-03-26 11:33 | Section 2 | Material | Aggregate | Type 1 | 1000 | Tonnes | 21.65 | 21650 | Aggregate | 2019-03-31 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14039-001025 | 14039 | 2019-03-14 13:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1000 | 1000 | Miscellaneous | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14262-001025 | 14262 | 2019-03-19 11:09 | Section 2 | Material | Waste Management | Not on List | 1 | NULL | NULL | 0 | Tanks and Interceptors | 2019-03-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14463-001025 | 14463 | 2019-03-21 14:40 | Core | Material | Not on List | Not on List | 1 | Each | 495 | 495 | Training | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15165-001025 | 15165 | 2019-04-02 16:56 | Section 2 | Material | NULL | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 18 | Each | 166.43 | 2995.74 | Plastic Drainage | 2019-04-04 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12459-001025 | 12459 | 2019-02-14 10:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2390 | 2390 | Miscellaneous | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12382-001025 | 12382 | 2019-02-13 11:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 336.28 | 336.28 | Miscellaneous | 2019-02-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12785-001025 | 12785 | 2019-02-20 15:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12732-001025 | 12732 | 2019-02-19 16:34 | Section 4 | Material | Waste Management | Dry Mixed Recycling - Wheelie Bin 660 Litre | 6 | Each | 61.8 | 370.8 | Waste (General) | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12156-001025 | 12156 | 2019-02-08 13:01 | Core | Material | Not on List | Not on List | 3 | number packs | 21.45 | 64 | Office Supplies | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | 111 - Stationery /Postage | IMO - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12790-001025 | 12790 | 2019-02-20 16:16 | Section 1 | Material | Aggregate | Type 1 | 15000 | Tonnes | 21.65 | 324750 | Aggregate | 2019-02-25 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-12791-001025 | 12791 | 2019-02-20 15:56 | Section 2 | Material | Twinwall | Not on List | 15 | Units | NULL | 0 | Plastic Drainage | 2019-02-25 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12791-001025 | 12791 | 2019-02-20 15:56 | Section 2 | Material | Twinwall | Not on List | 1 | unit | NULL | 0 | Plastic Drainage | 2019-02-25 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12791-001025 | 12791 | 2019-02-20 15:56 | Section 2 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 13 | Each | 116.62 | 1516 | Plastic Drainage | 2019-02-25 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12791-001025 | 12791 | 2019-02-20 15:56 | Section 2 | Material | Concrete Drainage | Not on List | 100 | Units | NULL | 0 | Plastic Drainage | 2019-02-25 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12792-001025 | 12792 | 2019-02-20 16:24 | Section 2 | Material | Not on List | Not on List | 12.553 | NULL | NULL | 0 | Reinforcement | 2019-03-04 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12652-001025 | 12652 | 2019-02-18 16:28 | Section 4 | Material | Not on List | Not on List | 5 | Each | 83 | 415 | Miscellaneous | 2019-03-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12811-001025 | 12811 | 2019-02-21 07:07 | Section 2 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Miscellaneous | 2019-02-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 30 | Each | 3.52 | 105.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Concrete Kerbs 125x255 HB External Radius (947297) | 15 | Each | 5.43 | 81.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 10 | Each | 7.68 | 76.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 10 | Each | 7.68 | 76.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12704-001025 | 12704 | 2019-02-19 13:44 | Section 3 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12687-001025 | 12687 | 2019-02-19 12:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 62.75 | 62.75 | Small Tools (Consumables) | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12692-001025 | 12692 | 2019-02-19 12:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 522.72 | 522.72 | Small Tools (Consumables) | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12708-001025 | 12708 | 2019-02-19 14:09 | Section 4 | Material | Not on List | Not on List | 20 | Each | 41.2 | 824 | Miscellaneous | 2019-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3010 - Ground Preparation, Cultivation and Mulching | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12734-001025 | 12734 | 2019-02-19 16:49 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 261.84 | 261.84 | Janitorial | 2019-02-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12816-001025 | 12816 | 2019-02-21 08:18 | Section 2 | Material | Not on List | Not on List | 300 | meters | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 150 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12769-001025 | 12769 | 2019-02-20 10:45 | Section 2 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Miscellaneous | 2019-02-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12045-001025 | 12045 | 2019-02-07 10:45 | Core | Material | Not on List | Not on List | 1 | ea | 1265.37 | 1265.37 | Training | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12296-001025 | 12296 | 2019-02-12 10:04 | Core | Material | Not on List | Not on List | 1 | ea | 41504 | 41504 | Office Supplies | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12573-001025 | 12573 | 2019-02-15 13:53 | Core | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Training | 2019-02-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12830-001025 | 12830 | 2019-02-21 09:40 | Section 2 | Material | Not on List | Not on List | 250000 | £ | 1 | 250000 | Fuel | 2019-02-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12831-001025 | 12831 | 2019-02-21 09:01 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 346.49 | 346 | Damage Charges | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-12721-001025 | 12721 | 2019-02-19 15:44 | Section 3 | Material | Concrete Drainage | Not on List | 700 | No. | 18.43 | 12901 | Concrete Drainage | 2019-02-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1800 x 1000 D/S (528457) | 1 | Each | 155.88 | 155.88 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12721-001025 | 12721 | 2019-02-19 15:44 | Section 3 | Material | Concrete Drainage | Not on List | 76 | No. | 74.3 | 5646.8 | Ductile Drainage | 2019-02-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1800 x 750 D/S (528456) | 1 | Each | 116.91 | 116.91 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM 1800 Cover Slab 600x600 Opening (985438) | 1 | Each | 144.04 | 144.04 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | Not on List | 20 | NULL | 209.43 | 4188.6 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411.2 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 7 | Each | 67.9 | 475.3 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509.2 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12716-001025 | 12716 | 2019-02-19 15:16 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2019-02-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5625-00424 | 5625 | 2018-08-24 11:29 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 4652 | 4652 | Professional Services | 2018-08-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11827 | 11827 | 2019-02-01 15:45 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12081-001025 | 12081 | 2019-02-07 16:08 | Core | Material | Not on List | Not on List | 1 | number | 180 | 180 | Office Supplies | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | NULL | 110 - Welfare Costs | IMO - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12842-001025 | 12842 | 2019-02-21 11:37 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Plastic Drainage | 2019-02-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12850-001025 | 12850 | 2019-02-21 13:23 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Request - Ops Pass Back | No - Pass Back | NULL | Req - S2 Buyers
MREQ-12792-001025 | 12792 | 2019-02-20 16:24 | Section 2 | Material | Not on List | Not on List | 12.553 | NULL | NULL | 0 | NULL | 2019-03-04 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12389-001025 | 12389 | 2019-02-13 13:16 | Section 6 | Material | Not on List | Not on List | 1 | sum | 960.8 | 960.8 | Miscellaneous | 2019-02-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-12574-001025 | 12574 | 2019-02-15 13:19 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Tanker and disposal | 2617.55 | 2617.55 | Miscellaneous | 2019-02-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12860-001025 | 12860 | 2019-02-21 15:21 | Section 5 | Material | Not on List | Not on List | 1 | NULL | 466.88 | 467 | Damage Charges | 2019-02-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-12785-001025 | 12785 | 2019-02-20 15:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 406.28 | 406.28 | Small Tools (Consumables) | 2019-02-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12865-001025 | 12865 | 2019-02-21 15:44 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 1597.71 | 1598 | Miscellaneous | 2019-02-22 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | FEE6 - Fee Based Costs inc. insurance | 107 - Insurance | Buyer - Closed | NULL | Yes - Approve | Req - S6 Buyers
MREQ-12877-001025 | 12877 | 2019-02-21 16:39 | Core | Material | Not on List | Not on List | 1 | Number | 394.8 | 395 | Office Supplies | 2019-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | NULL | Not on List | 9 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | NULL | Not on List | 13 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | NULL | Not on List | 20 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12725-001025 | 12725 | 2019-02-19 15:06 | Section 2 | Material | NULL | Not on List | 40 | Number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 270 | metres | 3.52 | 950.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 9 | Each | 7.68 | 69.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 8 | Each | 7.68 | 61.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 903 | metres | 1.5 | 1354.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Concrete Kerbs 125x150x914 BN Straight (753034) | 30 | metres | 3.03 | 90.9 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Not on List | 450 | metres | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Not on List | 15 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Not on List | 15 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Not on List | 75 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12662-001025 | 12662 | 2019-02-19 08:16 | Section 2 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12760-001025 | 12760 | 2019-02-20 08:49 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | number | 6.74 | 404.4 | Miscellaneous | 2019-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12761-001025 | 12761 | 2019-02-20 09:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 4056.35 | 4056.35 | Small Tools (Consumables) | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12763-001025 | 12763 | 2019-02-20 09:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 173 | 173 | PPE | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12821-001025 | 12821 | 2019-02-21 08:53 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 72 | Each | 6.29 | 452.88 | Miscellaneous | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12664-001025 | 12664 | 2019-02-19 08:38 | Core | Material | Not on List | Not on List | 1 | ea | 42200 | 42200 | Office Supplies | 2019-02-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12933-001025 | 12933 | 2019-02-22 08:35 | Core | Material | Not on List | Not on List | 1 | number | 40 | 40 | Miscellaneous | 2019-02-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12842-001025 | 12842 | 2019-02-21 11:37 | Section 4 | Material | Plastic Drainage | Not on List | 4 | 50M | 79.05 | 316.2 | Plastic Drainage | 2019-02-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12947-001025 | 12947 | 2019-02-22 11:23 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1915.2 | 1915 | Laboratory Equipment / Certification | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6321-00661 | 6321 | 2018-09-11 11:19 | Section 4 | Material | Not on List | Not on List | 5.691 | Tonne | 538 | 3061.76 | Rebar and Mesh | 2018-09-27 | RVP 419 - 1340880 - A14 Westbound (West of Junction 28) | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22223-001025 | 22223 | 2019-08-13 13:36 | Core | Material | NULL | NULL | 1 | Each | 109 | 109 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22670-001025 | 22670 | 2019-08-22 12:16 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-22175-001025 | 22175 | 2019-08-12 17:06 | Core | Material | NULL | NULL | 1 | Each | 1959 | 1959 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | No - Reject | REQ - Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Not on List | 6 | EACH | 18.45 | 110.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 16 | Each | 10.8 | 172.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 12 | Each | 10.8 | 129.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 6 | Each | 11.94 | 71.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 6 | Each | 7.96 | 47.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6321-00661 | 6321 | 2018-09-11 11:19 | Section 4 | Material | Not on List | Not on List | 3.376 | Tonne | 538 | 1816.29 | Rebar and Mesh | 2018-09-27 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 6 | Each | 7.96 | 47.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 30 | Each | 10.8 | 324 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22444-001025 | 22444 | 2019-08-19 07:46 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 30 | Each | 10.8 | 324 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22577-001025 | 22577 | 2019-08-20 17:17 | Section 4 | Material | Signage | Not on List | 4 | Each | 13.95 | 55.8 | Builders Merchants (General) | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6322-00663 | 6322 | 2018-09-11 11:38 | Section 4 | Material | Not on List | Not on List | 50 | Each | 1.32 | 66 | Concrete Accessories | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22681-001025 | 22681 | 2019-08-22 16:11 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | 36 | 144 | Small Tools (Consumables) | 2019-08-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22681-001025 | 22681 | 2019-08-22 16:11 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 0.68 | 7 | Miscellaneous | 2019-08-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22662-001025 | 22662 | 2019-08-22 10:50 | Section 5 | Material | Not on List | Not on List | 3 | EA | 435 | 1305 | Miscellaneous | 2019-08-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22690-001025 | 22690 | 2019-08-22 17:33 | Section 5 | Material | Aggregate | Type 1 | 4500 | Tonnes | 21.65 | 97425 | Aggregate | NULL | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 604 - Deposition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5091-0039 | 5091 | 2018-08-14 17:07 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 2410.5 | 2410.5 | Damage Charges | 2018-08-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6322-00663 | 6322 | 2018-09-11 11:38 | Section 4 | Material | Not on List | Not on List | 50 | Each | 0.85 | 42.5 | Concrete Accessories | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22676-001025 | 22676 | 2019-08-22 14:33 | Core | Material | Not on List | Not on List | 1 | EA | 1000 | 1000 | Small Tools (Consumables) | NULL | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22624-001025 | 22624 | 2019-08-21 15:39 | Section 2 | Material | Twinwall | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-08-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22712-001025 | 22712 | 2019-08-23 08:17 | Section 4 | Material | Not on List | Not on List | 1 | EA | 11935.84 | 11935.84 | Concrete Accessories | 2019-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21727-001025 | 21727 | 2019-08-01 14:17 | Section 4 | Material | Kerbs | NULL | 16 | ea | 28.41 | 454.56 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21727-001025 | 21727 | 2019-08-01 14:17 | Section 4 | Material | Kerbs | NULL | 16 | ea | 11.68 | 186.88 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21727-001025 | 21727 | 2019-08-01 14:17 | Section 4 | Material | Kerbs | NULL | 16 | ea | 11.68 | 186.88 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6322-00663 | 6322 | 2018-09-11 11:38 | Section 4 | Material | Not on List | Not on List | 10 | Coil | 43.05 | 430.5 | Concrete Accessories | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21727-001025 | 21727 | 2019-08-01 14:17 | Section 4 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 16 | Each | 7.68 | 122.88 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21727-001025 | 21727 | 2019-08-01 14:17 | Section 4 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 16 | Each | 11.94 | 191.04 | Miscellaneous | 2019-08-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22479-001025 | 22479 | 2019-08-19 15:13 | Section 4 | Material | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 384 | Each | 3.52 | 1351.68 | Miscellaneous | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22479-001025 | 22479 | 2019-08-19 15:13 | Section 4 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 390 | Each | 4.59 | 1790.1 | Miscellaneous | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22454-001025 | 22454 | 2019-08-19 09:33 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 49 | Each | 37.6 | 1842.4 | Ductile Drainage | 2019-08-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22454-001025 | 22454 | 2019-08-19 09:33 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 57 | Each | 7.06 | 402.42 | Ductile Drainage | 2019-08-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22454-001025 | 22454 | 2019-08-19 09:33 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 57 | Each | 2.97 | 169.29 | Ductile Drainage | 2019-08-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22678-001025 | 22678 | 2019-08-22 15:49 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 10 | Each | 37.6 | 376 | Plastic Drainage | 2019-08-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22416-001025 | 22416 | 2019-08-16 15:10 | Section 3 | Material | Not on List | Not on List | 50 | No. | 43.2 | 2160 | Flow Control | 2019-08-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22416-001025 | 22416 | 2019-08-16 15:10 | Section 3 | Material | Not on List | Not on List | 1 | Roll | 75 | 75 | Flow Control | 2019-08-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6337 | 6337 | 2018-09-11 14:42 | Section 4 | Material | Not on List | Not on List | 10 | u | NULL | 0 | Rebar and Mesh | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22512-001025 | 22512 | 2019-08-20 10:00 | Section 3 | Material | Kerbs | Not on List | 8 | No. | 39.22 | 313.76 | Builders Merchants (General) | 2019-08-21 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22584-001025 | 22584 | 2019-08-21 08:23 | Section 3 | Material | Kerbs | Not on List | 1 | No. | 39.22 | 39.22 | Builders Merchants (General) | 2019-08-22 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22705-001025 | 22705 | 2019-08-23 07:25 | Section 2 | Material | Not on List | Not on List | 80 | NULL | NULL | 0 | Miscellaneous | 2019-08-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22304-001025 | 22304 | 2019-08-15 08:02 | Section 3 | Material | Not on List | Not on List | 1 | Each | 3920 | 3920 | Concrete Drainage | 2019-08-22 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22753-001025 | 22753 | 2019-08-25 09:28 | Section 6 | Material | Aggregate | Class 1A | 2000 | Tonnes | 12.5 | 25000 | Aggregate | 2019-08-27 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6353-00673 | 6353 | 2018-09-11 16:46 | Section 4 | Material | Not on List | Not on List | 125 | Each | 0.3 | 37.5 | Builders Merchants (General) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22663-001025 | 22663 | 2019-08-22 10:58 | Core | Material | NULL | NULL | 12 | Each | 11.57 | 138.84 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22672-001025 | 22672 | 2019-08-22 14:00 | Core | Material | NULL | NULL | 20 | Pair | 0.52 | 10.4 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22716-001025 | 22716 | 2019-08-23 08:46 | Section 4 | Material | Not on List | Not on List | 60 | sheet | 18.5 | 1110 | Builders Merchants (General) | 2019-08-28 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22596-001025 | 22596 | 2019-08-21 10:17 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20428-001025 | 20428 | 2019-07-08 16:53 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20505-001025 | 20505 | 2019-07-09 14:14 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20521-001025 | 20521 | 2019-07-09 20:09 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-6353-00673 | 6353 | 2018-09-11 16:46 | Section 4 | Material | Not on List | NULL | 1 | Each | 7.95 | 7.95 | Builders Merchants (General) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21253-001025 | 21253 | 2019-07-24 09:54 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22008-001025 | 22008 | 2019-08-08 14:22 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22019-001025 | 22019 | 2019-08-08 15:17 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22673-001025 | 22673 | 2019-08-22 14:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 825 | 825 | Miscellaneous | 2019-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22686-001025 | 22686 | 2019-08-22 16:42 | Section 4 | Material | Not on List | Not on List | 1 | No. | 65 | 65 | Surveying Consumables | 2019-08-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22686-001025 | 22686 | 2019-08-22 16:42 | Section 4 | Material | Not on List | Not on List | 12 | No. | 25 | 300 | Surveying Consumables | 2019-08-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6391-00686 | 6391 | 2018-09-12 10:32 | Section 4 | Material | Not on List | Not on List | 200 | Each | 4.37 | 874 | Miscellaneous | 2018-09-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22818-001025 | 22818 | 2019-08-27 16:13 | Section 5 | Material | PPE, Small Tools and Consumables | Water Natural Mineral Ideal Still 500ml Bottle Case Of 24 (744570) | 72 | Each | 6.29 | 453 | PPE | 2019-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22842-001025 | 22842 | 2019-08-27 18:51 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 27 | 27 | Surveying Consumables | 2019-08-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1804 - Portal Gantries | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-22854-001025 | 22854 | 2019-08-28 07:44 | Section 2 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Concrete Accessories | 2019-08-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22645-001025 | 22645 | 2019-08-22 07:39 | Section 4 | Material | Signage | Not on List | 100 | Each | 5.8 | 580 | Miscellaneous | 2019-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22797-001025 | 22797 | 2019-08-27 10:08 | Section 5 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 9.75 | 546 | Builders Merchants (General) | 2019-08-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6403-00693 | 6403 | 2018-09-12 12:53 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 0.89 | 890 | Timber Products | 2018-09-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6405-00694 | 6405 | 2018-09-12 12:56 | Section 4 | Material | Not on List | Not on List | 4 | Each | 258.05 | 1032.2 | Not Sure | 2018-09-24 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 5mtr/1 (765565) | 5 | Each | 2.7 | 14 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 7.5mtr/2 (765566) | 5 | Each | 5.77 | 29 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 10mtr/3 (765567) | 5 | Each | 12.4 | 62 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22864-001025 | 22864 | 2019-08-27 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22815-001025 | 22815 | 2019-08-27 14:34 | Section 5 | Material | Kerbs | NULL | 1 | SM | 2631 | 2631 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22788-001025 | 22788 | 2019-08-27 09:16 | Section 5 | Material | Not on List | Not on List | 18 | ROLL | 9.6 | 172.8 | Concrete Accessories | 2019-08-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6405-00694 | 6405 | 2018-09-12 12:56 | Section 4 | Material | NULL | NULL | 1 | Each | 85 | 85 | NULL | 2018-09-24 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22789-001025 | 22789 | 2019-08-27 09:29 | Section 5 | Material | Bagged | Not on List | 1 | SM | 1779.28 | 1779.28 | Builders Merchants (General) | 2019-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22282-001025 | 22282 | 2019-08-14 14:08 | Core | Material | Not on List | Not on List | 243.92 | Each | 1 | 243.92 | NULL | NULL | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6405-00694 | 6405 | 2018-09-12 12:56 | Section 4 | Material | NULL | NULL | 4 | Each | 10.5 | 42 | NULL | 2018-09-24 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22282-001025 | 22282 | 2019-08-14 14:08 | Core | Material | Not on List | Not on List | 431.77 | Each | 1 | 431.77 | NULL | NULL | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22799-001025 | 22799 | 2019-08-27 10:45 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | NULL | 6.29 | 905.76 | Small Tools (Consumables) | 2019-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22674-001025 | 22674 | 2019-08-22 13:38 | Section 4 | Material | Not on List | Not on List | 3 | Each | 67.58 | 202.74 | Miscellaneous | 2019-08-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22674-001025 | 22674 | 2019-08-22 13:38 | Section 4 | Material | Not on List | Not on List | 1 | Each | 130.68 | 130.68 | Miscellaneous | 2019-08-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22674-001025 | 22674 | 2019-08-22 13:38 | Section 4 | Material | Not on List | Not on List | 1 | Each | 45 | 45 | Miscellaneous | 2019-08-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5108-0042 | 5108 | 2018-08-15 07:26 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 161.16 | 161.16 | Damage Charges | 2018-08-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6405-00694 | 6405 | 2018-09-12 12:56 | Section 4 | Material | NULL | NULL | 1 | Each | 312 | 312 | NULL | 2018-09-24 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22885-001025 | 22885 | 2019-08-28 12:18 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6410-00696 | 6410 | 2018-09-12 13:24 | Section 4 | Material | Not on List | Not on List | 14 | sheets | 8.47 | 118.58 | Not Sure | 2018-09-23 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22893-001025 | 22893 | 2019-08-28 15:29 | Section 2 | Material | Not on List | Not on List | 20 | 600ml sausage | NULL | 0 | Ductile Drainage | 2019-09-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22893-001025 | 22893 | 2019-08-28 15:29 | Section 2 | Material | Not on List | Not on List | 2 | no. | NULL | 0 | Ductile Drainage | 2019-09-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22894-001025 | 22894 | 2019-08-28 15:38 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 461.48 | 461 | Miscellaneous | 2019-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22894-001025 | 22894 | 2019-08-28 15:38 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 395.53 | 396 | PPE | 2019-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22895-001025 | 22895 | 2019-08-28 16:08 | Section 5 | Material | Not on List | Not on List | 10 | boxes | NULL | 0 | Builders Merchants (General) | 2019-08-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-22908-001025 | 22908 | 2019-08-29 07:09 | Section 2 | Material | Not on List | Not on List | 500 | metres | NULL | 0 | Concrete Accessories | 2019-09-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-22908-001025 | 22908 | 2019-08-29 07:09 | Section 2 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 25 | Each | 6.82 | 171 | Concrete Accessories | 2019-09-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-22908-001025 | 22908 | 2019-08-29 07:09 | Section 2 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 25 | Each | 10.08 | 252 | Concrete Accessories | 2019-09-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-6451-00701 | 6451 | 2018-09-12 18:28 | Section 3 | Material | Not on List | Not on List | 1 | SM | 203.79 | 203.79 | Damage Charges | 2018-09-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16813-001025 | 16813 | 2019-05-02 11:43 | Core | Material | Not on List | Not on List | 1 | NULL | 162.8 | 163 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22877-001025 | 22877 | 2019-08-28 13:13 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2260.93 | Each | 1 | 2260.93 | PPE | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22878-001025 | 22878 | 2019-08-28 13:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1031.07 | Each | 1 | 1031.07 | Janitorial | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22924-001025 | 22924 | 2019-08-29 10:07 | Core | Material | Not on List | Not on List | 1 | ea | 1000 | 1000 | Office Supplies | 2019-09-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Buyers
MREQ-21788-001025 | 21788 | 2019-08-05 13:28 | Section 2 | Material | Not on List | Not on List | 1 | NULL | 9.99 | 10 | Small Tools (Consumables) | 2019-08-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12956-001025 | 12956 | 2019-02-22 12:36 | Section 2 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12956-001025 | 12956 | 2019-02-22 12:36 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 15 | Each | 10.5 | 158 | Plastic Drainage | 2019-02-28 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12830-001025 | 12830 | 2019-02-21 09:40 | Section 2 | Material | Not on List | Not on List | 250000 | £ | 1 | 250000 | Fuel | 2019-02-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-12983-001025 | 12983 | 2019-02-22 14:54 | Section 2 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-02-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12994-001025 | 12994 | 2019-02-23 07:52 | Section 3 | Material | Not on List | Not on List | 15 | NULL | NULL | 0 | Miscellaneous | 2019-02-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13003-001025 | 13003 | 2019-02-25 08:50 | Core | Material | Not on List | Not on List | 2 | Number | NULL | 0 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13006-001025 | 13006 | 2019-02-25 09:36 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12994-001025 | 12994 | 2019-02-23 07:52 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 210.6 | 210.6 | Miscellaneous | 2019-02-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13018-001025 | 13018 | 2019-02-25 12:07 | Core | Material | Not on List | Not on List | 1 | n | 478.99 | 479 | Janitorial | 2019-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 119 - Cleaning Sub.Con | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12870-001025 | 12870 | 2019-02-21 16:13 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 80 | Each | 1.31 | 104.8 | Small Tools (Consumables) | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13024-001025 | 13024 | 2019-02-25 11:59 | Section 5 | Material | Not on List | Not on List | 48 | kg | NULL | 0 | Builders Merchants (General) | 2019-02-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13024-001025 | 13024 | 2019-02-25 11:59 | Section 5 | Material | Not on List | Not on List | 1 | bag | NULL | 0 | Builders Merchants (General) | 2019-02-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13027-001025 | 13027 | 2019-02-25 13:05 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 15 | Packs | 11 | 165 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 11 | Packs | 1.88 | 21 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 11 | Packs | 1.55 | 17 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13041-001025 | 13041 | 2019-02-25 15:06 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Electrical | 2019-02-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-02-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN19 - Robins Lane Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-02-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-02-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-04-12 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN20 - Bar Hill Junction West Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 3000 | 3000 | Miscellaneous | 2019-02-25 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5113-0043 | 5113 | 2018-08-15 07:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5619-00423 | 5619 | 2018-08-24 11:01 | Section 3 | Material | Plastic Drainage | Not on List | 40 | No | 15.71 | 628.4 | Builders Merchants (General) | 2018-08-31 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | Kerbs | Not on List | 80 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | Kerbs | Not on List | 1 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | Kerbs | Not on List | 1 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13074-001025 | 13074 | 2019-02-26 07:40 | Core | Material | Not on List | Not on List | 100 | each | 0 | 0 | Office Supplies | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13087-001025 | 13087 | 2019-02-26 09:15 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Pipe 2.5m (249364) | 38 | Each | 210.95 | 8016 | Concrete Drainage | 2019-03-07 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13087-001025 | 13087 | 2019-02-26 09:15 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Spigot (890375) | 1 | Each | 253.14 | 253 | Concrete Drainage | 2019-03-07 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13091-001025 | 13091 | 2019-02-26 09:27 | Section 5 | Material | Aggregate | 6F5 | 20000 | Tonnes | 14.65 | 293000 | Aggregate | 2019-02-26 | Stockyard, Gate 2 - 1346365 - Off A14 Eastbound between Jcn 32 – 33 | SEC5 - Roadworks | 602 - Excavation (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13099-001025 | 13099 | 2019-02-26 10:47 | Section 5 | Material | Not on List | Not on List | 1 | number | 333.35 | 333 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-5600-00397 | 5600 | 2018-08-23 20:33 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 33.35 | 200.1 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13108-001025 | 13108 | 2019-02-26 12:21 | Section 2 | Material | Not on List | Not on List | 0.472 | t | 538 | 254 | Rebar and Mesh | 2019-02-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13108-001025 | 13108 | 2019-02-26 12:21 | Section 2 | Material | Not on List | Not on List | 4 | ea | 2 | 8 | Rebar and Mesh | 2019-02-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13108-001025 | 13108 | 2019-02-26 12:21 | Section 2 | Material | Not on List | Not on List | 1 | ea | 25.96 | 26 | Rebar and Mesh | 2019-02-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13108-001025 | 13108 | 2019-02-26 12:21 | Section 2 | Material | Not on List | Not on List | 1 | ea | 75 | 75 | Rebar and Mesh | 2019-02-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13091-001025 | 13091 | 2019-02-26 09:27 | Section 5 | Material | Aggregate | 6F5 | 20000 | Tonnes | 14.65 | 293000 | Aggregate | 2019-02-26 | Stockyard, Gate 2 - 1346365 - Off A14 Eastbound between Jcn 32 – 33 | SEC5 - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13113-001025 | 13113 | 2019-02-26 13:35 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-13114-001025 | 13114 | 2019-02-26 13:54 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-13115-001025 | 13115 | 2019-02-26 14:08 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-5600-00397 | 5600 | 2018-08-23 20:33 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 21.6 | 129.6 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5600-00397 | 5600 | 2018-08-23 20:33 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 0.33 | 1.98 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13029-001025 | 13029 | 2019-02-25 13:10 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | 28.8 | 1728 | PPE | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13160-001025 | 13160 | 2019-02-27 08:56 | Core | Material | Not on List | Not on List | 1 | job lot | 13265.58 | 13266 | Miscellaneous | 2019-03-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 15 | Packs | 11 | 165 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 11 | Packs | 1.88 | 20.68 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13031-001025 | 13031 | 2019-02-25 13:12 | Section 3 | Material | Not on List | Not on List | 11 | Packs | 1.55 | 17.05 | Fixings and Fasteners | 2019-02-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19239-001025 | 19239 | 2019-06-17 15:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | 20ltr Bag | 16.57 | 662.8 | Small Tools (Consumables) | 2019-06-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19216-001025 | 19216 | 2019-06-17 11:47 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | 20ltr Drum | 56.2 | 281 | Small Tools (Consumables) | 2019-06-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19283-001025 | 19283 | 2019-06-18 08:53 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-06-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19294-001025 | 19294 | 2019-06-18 11:13 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18962-001025 | 18962 | 2019-06-12 09:21 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 62.76 | 62.76 | Laboratory Equipment / Certification | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19208-001025 | 19208 | 2019-06-17 09:47 | Section 5 | Material | Aggregate | NULL | 180 | TON | 32.9 | 5922 | Aggregate | 2019-06-18 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18667-001025 | 18667 | 2019-06-06 12:36 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 61 | 61 | Laboratory Equipment / Certification | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19317-001025 | 19317 | 2019-06-18 13:54 | Section 3 | Material | Not on List | Not on List | 7 | No | NULL | 0 | Builders Merchants (General) | 2019-06-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19317-001025 | 19317 | 2019-06-18 13:54 | Section 3 | Material | Not on List | Not on List | 50 | No | NULL | 0 | Builders Merchants (General) | 2019-06-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19317-001025 | 19317 | 2019-06-18 13:54 | Section 3 | Material | Not on List | Not on List | 1 | No | NULL | 0 | Builders Merchants (General) | 2019-06-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19317-001025 | 19317 | 2019-06-18 13:54 | Section 3 | Material | Not on List | Not on List | 2 | No | NULL | 0 | Builders Merchants (General) | 2019-06-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19317-001025 | 19317 | 2019-06-18 13:54 | Section 3 | Material | Not on List | Not on List | 1 | No | NULL | 0 | Builders Merchants (General) | 2019-06-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 200 | NULL | 14.36 | 2872 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 4 | NULL | 35.91 | 143.64 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 4 | NULL | 201.59 | 806.36 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 4 | NULL | 33.06 | 132.24 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 4 | NULL | 33.06 | 132.24 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18959-001025 | 18959 | 2019-06-12 07:53 | Section 3 | Material | Concrete Drainage | Not on List | 230 | NULL | 29.28 | 6734.4 | Concrete Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19341-001025 | 19341 | 2019-06-18 17:26 | Section 5 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Miscellaneous | 2019-06-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19083-001025 | 19083 | 2019-06-14 07:43 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19355-001025 | 19355 | 2019-06-19 06:25 | Core | Material | PPE, Small Tools and Consumables | Not on List | 36 | NULL | NULL | 0 | Surveying Consumables | 2019-06-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17070-001025 | 17070 | 2019-05-09 08:38 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 884.03 | 884.03 | Laboratory Equipment / Certification | 2019-05-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19134-001025 | 19134 | 2019-06-14 12:23 | Section 2 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Fixings and Fasteners | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19134-001025 | 19134 | 2019-06-14 12:23 | Section 2 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Fixings and Fasteners | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19134-001025 | 19134 | 2019-06-14 12:23 | Section 2 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Fixings and Fasteners | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19134-001025 | 19134 | 2019-06-14 12:23 | Section 2 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Fixings and Fasteners | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19134-001025 | 19134 | 2019-06-14 12:23 | Section 2 | Material | Not on List | Not on List | 2 | number | NULL | 0 | Plastic Drainage | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19360-001025 | 19360 | 2019-06-19 09:34 | Section 2 | Material | Not on List | Not on List | 1 | £ | 18289.75 | 18290 | Professional Services | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19362-001025 | 19362 | 2019-06-19 10:15 | Core | Material | Not on List | Not on List | 1 | NULL | 3000 | 3000 | Professional Services | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19368-001025 | 19368 | 2019-06-19 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-06-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19374-001025 | 19374 | 2019-06-19 11:26 | Core | Material | Not on List | Not on List | 1 | NULL | 25200 | 25200 | Miscellaneous | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Stores - Closed | NULL | Yes - Approve | REQ - Buyers
MREQ-19334-001025 | 19334 | 2019-06-18 16:02 | Section 2 | Material | Not on List | Not on List | 145 | linear meters | NULL | 0 | Blocks and Bricks | 2019-06-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19310-001025 | 19310 | 2019-06-18 12:56 | Section 4 | Material | Not on List | Not on List | 4 | Each | 32.15 | 128.6 | Builders Merchants (General) | 2019-06-20 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | NULL | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19303-001025 | 19303 | 2019-06-18 12:27 | Section 4 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 2 | Roll | 122.72 | 245.44 | Geotextiles | 2019-06-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19228-001025 | 19228 | 2019-06-17 14:32 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1447.4 | 1447.4 | Miscellaneous | 2019-06-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18913-001025 | 18913 | 2019-06-11 14:38 | Section 4 | Material | Not on List | Not on List | 1 | each | 3216.78 | 3216.78 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19266-001025 | 19266 | 2019-06-18 08:26 | Section 4 | Material | NULL | NULL | 60 | Each | 5.17 | 310.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17451-001025 | 17451 | 2019-05-15 12:26 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 2392.25 | 2392.25 | Miscellaneous | 2019-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18084-001025 | 18084 | 2019-05-27 09:19 | Section 5 | Material | Not on List | NULL | 1 | EACH | 11768.8 | 11768.8 | Not Sure | 2019-08-02 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19323-001025 | 19323 | 2019-06-18 15:24 | Section 2 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 20 | Each | 24.32 | 486.4 | Concrete Accessories | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19323-001025 | 19323 | 2019-06-18 15:24 | Section 2 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 10 | Each | 10.08 | 100.8 | Concrete Accessories | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19323-001025 | 19323 | 2019-06-18 15:24 | Section 2 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 15 | Each | 6.82 | 102.3 | Concrete Accessories | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19226-001025 | 19226 | 2019-06-17 14:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4762.15 | 4762.15 | Miscellaneous | 2019-06-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19349-001025 | 19349 | 2019-06-19 06:24 | Section 5 | Material | Signage | NULL | 1 | SM | 580.92 | 580.92 | NULL | 2019-06-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6814-00751 | 6814 | 2018-09-20 16:43 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 12 | Ea | 7.96 | 95.52 | Miscellaneous | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19263-001025 | 19263 | 2019-06-18 08:06 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | No - Reject | Req - S5 Buyers
MREQ-18674-001025 | 18674 | 2019-06-06 12:41 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1122.28 | 1122.28 | Miscellaneous | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19020-001025 | 19020 | 2019-06-13 07:20 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 709.92 | 709.92 | Miscellaneous | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19395-001025 | 19395 | 2019-06-19 16:25 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19396-001025 | 19396 | 2019-06-19 16:23 | Core | Material | Not on List | Not on List | 15 | Bundle | 9 | 135 | Surveying Consumables | 2019-06-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19396-001025 | 19396 | 2019-06-19 16:23 | Core | Material | Not on List | Not on List | 15 | Bundle | 9 | 135 | Surveying Consumables | 2019-06-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19396-001025 | 19396 | 2019-06-19 16:23 | Core | Material | Not on List | Not on List | 10 | Bundle | 9 | 90 | Surveying Consumables | 2019-06-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19396-001025 | 19396 | 2019-06-19 16:23 | Core | Material | Not on List | Not on List | 10 | Bundle | 9 | 90 | Surveying Consumables | 2019-06-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19367-001025 | 19367 | 2019-06-19 11:00 | Section 4 | Material | Not on List | Not on List | 10 | EA | 69.14 | 691.4 | Rebar and Mesh | 2019-06-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6814-00751 | 6814 | 2018-09-20 16:43 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 12 | ea | 6.11 | 73.32 | Miscellaneous | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19399-001025 | 19399 | 2019-06-19 17:13 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19422-001025 | 19422 | 2019-06-20 09:35 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19151-001025 | 19151 | 2019-06-14 13:33 | Section 5 | Material | Not on List | Not on List | 50 | 7.1 | NULL | 0 | Surveying Consumables | 2019-06-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-19151-001025 | 19151 | 2019-06-14 13:33 | Section 5 | Material | Not on List | Not on List | 5 | 45 | NULL | 0 | Surveying Consumables | 2019-06-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-19151-001025 | 19151 | 2019-06-14 13:33 | Section 5 | Material | Not on List | Not on List | 1 | 65 | NULL | 0 | Surveying Consumables | 2019-06-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-19151-001025 | 19151 | 2019-06-14 13:33 | Section 5 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Surveying Consumables | 2019-06-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-19424-001025 | 19424 | 2019-06-20 10:33 | Section 3 | Material | Not on List | Not on List | 4000 | No | NULL | 0 | Builders Merchants (General) | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Rope Blue Polypropylene 6mm X 500m (approx)on Drum (746415) | 9 | Each | 25.13 | 226 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 7.5mtr/2 (765566) | 10 | Each | 5.77 | 58 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 10mtr/3 (765567) | 5 | Each | 12.4 | 62 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Scraper First Task 75mm Stripping Knife Ref 14003020 (746838) | 5 | Each | 5.55 | 28 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Filler Foam Expanding Hansil Contractor 750ml (546678) | 10 | Each | 3.17 | 32 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 200mm X 4.8mm Pack Of 100 (230062) | 15 | Each | 1.65 | 25 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 300mm X 4.8mm Pack Of 100 Spartan (230061) | 20 | Each | 1.94 | 39 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 370mm X 7.6mm Pack Of 100 Spartan (230065) | 15 | Each | 3.88 | 58 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Gun Skeleton Metal Suitable For 310/380/400ml Catridges (546684) | 5 | Each | 5.8 | 29 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19427-001025 | 19427 | 2019-06-20 10:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19311-001025 | 19311 | 2019-06-18 11:57 | Core | Material | Not on List | Not on List | 2 | EA | 85 | 170 | Miscellaneous | 2019-06-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18834-001025 | 18834 | 2019-06-10 11:06 | Section 3 | Material | Not on List | Not on List | 5 | ea | 324 | 1620 | Plastic Drainage | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18834-001025 | 18834 | 2019-06-10 11:06 | Section 3 | Material | Not on List | Not on List | 4 | ea | 133.87 | 535.48 | Plastic Drainage | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18834-001025 | 18834 | 2019-06-10 11:06 | Section 3 | Material | NULL | Polypipe 400mm Seal (346394) | 10 | Each | 9.04 | 90.4 | Plastic Drainage | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18834-001025 | 18834 | 2019-06-10 11:06 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 8 | Each | 2.97 | 23.76 | Plastic Drainage | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18970-001025 | 18970 | 2019-06-12 11:03 | Section 3 | Material | Not on List | Not on List | 10 | No | 24.47 | 244.7 | Miscellaneous | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18970-001025 | 18970 | 2019-06-12 11:03 | Section 3 | Material | Not on List | Not on List | 30 | No | 37.81 | 1134.3 | Plastic Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19443-001025 | 19443 | 2019-06-20 15:15 | Section 3 | Material | Not on List | Not on List | 4 | No | NULL | 0 | Builders Merchants (General) | 2019-06-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19443-001025 | 19443 | 2019-06-20 15:15 | Section 3 | Material | Not on List | Not on List | 6 | No | NULL | 0 | Builders Merchants (General) | 2019-06-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19443-001025 | 19443 | 2019-06-20 15:15 | Section 3 | Material | Not on List | Not on List | 2 | No | NULL | 0 | Builders Merchants (General) | 2019-06-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19211-001025 | 19211 | 2019-06-17 10:35 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 6 | Each | 33.55 | 201.3 | Blocks and Bricks | 2019-06-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19452-001025 | 19452 | 2019-06-20 16:45 | Core | Material | Not on List | Not on List | 3 | NULL | 90 | 270 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19454-001025 | 19454 | 2019-06-20 16:55 | Core | Material | Not on List | Not on List | 3 | £ | 90 | 270 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 48 | Each | 5.43 | 260.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 48 | Each | 5.43 | 260.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 48 | Each | 3.03 | 145.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 32 | Each | 5.43 | 173.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 32 | Each | 10.35 | 331.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 32 | Each | 10.35 | 331.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 64 | Each | 6 | 384 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 32 | Each | 5.43 | 173.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 16 | Each | 11.95 | 191.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 32 | Each | 5.43 | 173.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 16 | Each | 11.95 | 191.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19060-001025 | 19060 | 2019-06-13 15:56 | Section 4 | Material | NULL | NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 10 | Each | 85.23 | 852.3 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 78.9 | 78.9 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 3 | Each | 63.93 | 191.79 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16949-001025 | 16949 | 2019-05-07 14:16 | Core | Material | Not on List | Not on List | 1 | Each | 2850 | 2850 | Laboratory Equipment / Certification | 2019-05-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17007-001025 | 17007 | 2019-05-08 09:42 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 938.75 | 939 | PPE | 2019-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-16913-001025 | 16913 | 2019-05-07 07:36 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain Bend 15deg (877998) | 5 | Each | 8.25 | 41.25 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16913-001025 | 16913 | 2019-05-07 07:36 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain Bend 30deg (877999) | 5 | Each | 8.25 | 41.25 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16913-001025 | 16913 | 2019-05-07 07:36 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain Bend 45deg (878000) | 5 | Each | 8.25 | 41.25 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16811-001025 | 16811 | 2019-05-02 11:23 | Core | Material | Not on List | Not on List | 1 | ea | 3032 | 3032 | Training | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Not on List | 40 | NULL | 11.51 | 460.4 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 52 | Each | 1.98 | 102.96 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6384-00680 | 6384 | 2018-09-12 09:14 | Section 3 | Material | Not on List | Not on List | 1 | EA | 660.24 | 660.24 | Small Tools (Consumables) | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 52 | Each | 0.91 | 47.32 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 15 | Each | 24.99 | 374.85 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 22 | Each | 3.65 | 80.3 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 22 | Each | 2 | 44 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 10 | Each | 37.6 | 376 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 18 | Each | 7.06 | 127.08 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16921-001025 | 16921 | 2019-05-07 07:49 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 18 | Each | 2.97 | 53.46 | Plastic Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16927-001025 | 16927 | 2019-05-07 08:14 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 15 | Each | 48.92 | 733.8 | Concrete Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16927-001025 | 16927 | 2019-05-07 08:14 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 70.61 | 1059.15 | Concrete Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16927-001025 | 16927 | 2019-05-07 08:14 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 7 | Each | 52.95 | 370.65 | Concrete Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6384-00680 | 6384 | 2018-09-12 09:14 | Section 3 | Material | Not on List | Not on List | 1 | EA | 706.72 | 706.72 | Janitorial | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16927-001025 | 16927 | 2019-05-07 08:14 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16927-001025 | 16927 | 2019-05-07 08:14 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 5 | Each | 36.94 | 184.7 | Concrete Drainage | 2019-05-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16179-001025 | 16179 | 2019-04-18 14:44 | Core | Material | Not on List | Not on List | 1 | No. | 19.99 | 20 | Surveying Consumables | 2019-04-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | 113 - Survey Equipment Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17015-001025 | 17015 | 2019-05-08 11:21 | Core | Material | Not on List | Not on List | 1 | number | 1030 | 1030 | Office Supplies | 2019-05-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-17018-001025 | 17018 | 2019-05-08 11:13 | Core | Material | Not on List | Not on List | 1 | 1 | 799.22 | 799 | Professional Services | 2019-05-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-15663-001025 | 15663 | 2019-04-11 09:44 | Section 4 | Material | Not on List | Not on List | 5000 | Each | 1 | 5000 | Miscellaneous | 2019-04-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15855-001025 | 15855 | 2019-04-15 12:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 700 | Each | 0.47 | 329 | Small Tools (Consumables) | 2019-04-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17023-001025 | 17023 | 2019-05-08 13:06 | Section 6 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Fixings and Fasteners | 2019-05-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 301 - Fencing, Gates & Stiles | Commercial Approval | Yes - Approve | NULL | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 45deg Junction (878038) | 6 | Each | 39.7 | 238.2 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 13 | Each | 39.7 | 516.1 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6431-00700 | 6431 | 2018-09-12 16:22 | Section 3 | Material | Plastic Drainage | Not on List | 15 | No. | 48.86 | 732.9 | Plastic Drainage | 2018-09-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 300mm x 150mm Ridgidrain 90deg Junction (878089) | 3 | Each | 44.41 | 133.23 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 70 | Each | 3.65 | 255.5 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 30 | Each | 1.98 | 59.4 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 10 | Each | 7.06 | 70.6 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 400mm Coupler (346401) | 25 | Each | 17.45 | 436.25 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 60 | Each | 0.91 | 54.6 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 150 | Each | 2 | 300 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 20 | Each | 2.97 | 59.4 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe 400mm Seal (346394) | 50 | Each | 9.04 | 452 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | Concrete Drainage | Not on List | 70 | Each | NULL | 0 | Concrete Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6344-00672 | 6344 | 2018-09-11 14:32 | Section 3 | Material | Signage | Not on List | 100 | ea | 5.98 | 598 | Miscellaneous | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | NULL | Polypipe Lubricant 2.5kg (574788) | 6 | Each | 19.72 | 118.32 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16549-001025 | 16549 | 2019-04-29 07:30 | Section 6 | Material | Plastic Drainage | Not on List | 1 | Each | 1050 | 1050 | Plastic Drainage | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17025-001025 | 17025 | 2019-05-08 13:49 | Core | Material | Not on List | Not on List | 1 | £ | 384.3 | 384 | Office Supplies | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-17027-001025 | 17027 | 2019-05-08 13:52 | Section 3 | Material | Aggregate | Bedding Sand | 200 | Tonnes | 11.5 | 2300 | Aggregate | 2019-05-09 | Gate F - 1339645 - BN11 Near Mere Way | SC3A - Roadworks | 1103 - Linear Drainage Channel Systems | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-17028-001025 | 17028 | 2019-05-08 14:14 | Section 3 | Material | Not on List | Not on List | 1 | No. | 657.86 | 658 | Surveying Consumables | 2019-05-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 701 - Sub-base | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17029-001025 | 17029 | 2019-05-08 14:11 | Section 5 | Material | Bricks/Blocks | Not on List | 120 | NULL | NULL | 0 | Blocks and Bricks | 2019-05-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE24 - Histon Jct East Bridge | 2401 - Brickwork, Blockwork and Stonework | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-17033-001025 | 17033 | 2019-05-08 14:36 | Section 3 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1103 - Linear Drainage Channel Systems | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 1200 | Each | 1.5 | 1800 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 80 | Each | 3.03 | 242 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 105 | Each | 3.52 | 370 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-6401-00692 | 6401 | 2018-09-12 12:41 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 140 | 140 | Small Tools (Consumables) | 2018-09-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 420 | Each | 4.59 | 1928 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 4 | Each | 10.08 | 40 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 4 | Each | 10.08 | 40 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 3 | Each | 7.68 | 23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 3 | Each | 7.68 | 23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 7 | Each | 11.94 | 84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17034-001025 | 17034 | 2019-05-08 13:34 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 5 | Each | 11.94 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17036-001025 | 17036 | 2019-05-08 14:22 | Section 5 | Material | Bricks/Blocks | Not on List | 120 | NULL | NULL | 0 | Blocks and Bricks | 2019-05-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE24 - Histon Jct East Bridge | 2401 - Brickwork, Blockwork and Stonework | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-17036-001025 | 17036 | 2019-05-08 14:22 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 2 | Each | 32.74 | 65 | Builders Merchants (General) | 2019-05-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE24 - Histon Jct East Bridge | 2401 - Brickwork, Blockwork and Stonework | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-17036-001025 | 17036 | 2019-05-08 14:22 | Section 5 | Material | Bagged | Post Mix 25kg (348099) | 40 | Each | 3.45 | 138 | Builders Merchants (General) | 2019-05-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE24 - Histon Jct East Bridge | 2401 - Brickwork, Blockwork and Stonework | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-6316-00665 | 6316 | 2018-09-11 09:52 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 29.2 | 58.4 | Timber Products | 2018-09-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17039 | 17039 | 2019-05-08 15:08 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Surveying Consumables | 2019-05-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-17039 | 17039 | 2019-05-08 15:08 | Core | Material | Not on List | Not on List | 1 | number | 491.27 | 491 | Surveying Consumables | 2019-05-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-16954-001025 | 16954 | 2019-05-07 14:36 | Section 4 | Material | Not on List | Not on List | 3 | Boxes (x 150) | 12 | 36 | Surveying Consumables | 2019-05-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17596-001025 | 17596 | 2019-05-17 10:28 | Section 2 | Material | Concrete Drainage | Not on List | 200 | NULL | NULL | 0 | Concrete Drainage | 2019-05-21 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17596-001025 | 17596 | 2019-05-17 10:28 | Section 2 | Material | NULL | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-05-21 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6316-00665 | 6316 | 2018-09-11 09:52 | Section 3 | Material | Not on List | Not on List | 12 | NULL | 11.29 | 135.48 | Timber Products | 2018-09-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17596-001025 | 17596 | 2019-05-17 10:28 | Section 2 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 5 | Each | 175 | 875 | Plastic Drainage | 2019-05-21 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17611-001025 | 17611 | 2019-05-17 12:16 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Surveying Consumables | 2019-05-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17393-001025 | 17393 | 2019-05-14 15:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 479.95 | 479.95 | Small Tools (Consumables) | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17394-001025 | 17394 | 2019-05-14 16:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Pack of 12 | 6.29 | 905.76 | Small Tools (Consumables) | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17619-001025 | 17619 | 2019-05-17 13:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 22 | 220 | PPE | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17602-001025 | 17602 | 2019-05-17 10:48 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Pack | 18 | 72 | Laboratory Equipment / Certification | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17443-001025 | 17443 | 2019-05-15 11:02 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2000 | Each | 0.51 | 1020 | Laboratory Equipment / Certification | 2019-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17365-001025 | 17365 | 2019-05-14 11:13 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 858 | 858 | Laboratory Equipment / Certification | 2019-05-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6316-00665 | 6316 | 2018-09-11 09:52 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 41.6 | 83.2 | Builders Merchants (General) | 2018-09-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17513-001025 | 17513 | 2019-05-16 09:09 | Section 3 | Material | Not on List | Not on List | 75 | Mtr | 0.89 | 66.75 | Builders Merchants (General) | 2019-05-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17513-001025 | 17513 | 2019-05-16 09:09 | Section 3 | Material | Not on List | Not on List | 5 | No | 12.88 | 64.4 | Builders Merchants (General) | 2019-05-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17513-001025 | 17513 | 2019-05-16 09:09 | Section 3 | Material | Not on List | Not on List | 200 | No | 3.56 | 712 | Builders Merchants (General) | 2019-05-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17452-001025 | 17452 | 2019-05-15 12:28 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Tape Gaffa Waterproof Cloth Grey 50mm X 50 Mtr Ref 3160 (964670) | 3 | Boxes | 1.91 | 6 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 24 | number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Keys Hexagonal/Allen Metric Set Of 10 1.5mm To 10mm (662405) | 3 | sets | 5.45 | 16 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Box | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Helmet Safety Jsp Evolite Skyworker White (272558) | 2 | Boxes | 29.82 | 60 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6485-00724 | 6485 | 2018-09-13 14:47 | Section 3 | Material | Plastic Drainage | Not on List | 10 | No | NULL | 0 | Builders Merchants (General) | 2018-09-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 12 | Number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 12 | Number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 12 | Number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 12 | Number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 12 | Number | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17756-001025 | 17756 | 2019-05-20 11:51 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Boxes | NULL | 0 | PPE | 2019-05-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17542-001025 | 17542 | 2019-05-16 10:07 | Core | Material | Not on List | Not on List | 16 | ea | 81.04 | 1296.64 | Janitorial | 2019-05-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17542-001025 | 17542 | 2019-05-16 10:07 | Core | Material | Not on List | Not on List | 10 | ea | 33.98 | 339.8 | Janitorial | 2019-05-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17415-001025 | 17415 | 2019-05-14 17:36 | Core | Material | Not on List | Not on List | 1 | ea | 1633.18 | 1633.18 | PPE | 2019-05-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17415-001025 | 17415 | 2019-05-14 17:36 | Core | Material | Not on List | Not on List | 1 | ea | 470.25 | 470.25 | Small Tools (Consumables) | 2019-05-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17415-001025 | 17415 | 2019-05-14 17:36 | Core | Material | Not on List | Not on List | 1 | ea | 183.24 | 183.24 | Small Tools (Consumables) | 2019-05-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17716-001025 | 17716 | 2019-05-20 09:14 | Section 3 | Material | Not on List | Not on List | 15 | Sheets | 10.44 | 156.6 | Builders Merchants (General) | 2019-05-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17591-001025 | 17591 | 2019-05-17 10:01 | Section 3 | Material | NULL | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 42 | Each | 74.3 | 3120.6 | Ductile Drainage | 2019-05-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17764-001025 | 17764 | 2019-05-20 16:02 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17769-001025 | 17769 | 2019-05-20 16:19 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-22 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17770-001025 | 17770 | 2019-05-20 16:18 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17771-001025 | 17771 | 2019-05-20 16:22 | Section 5 | Material | PPE, Small Tools and Consumables | Spill Kit Maintenance In Two Wheel Bin Lubetech 120 Litres (534202) | 6 | Each | 195.66 | 1174 | Miscellaneous | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15487-001025 | 15487 | 2019-04-08 17:34 | Section 4 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17531-001025 | 17531 | 2019-05-16 12:19 | Section 4 | Material | NULL | NULL | 150 | Each | 7.5 | 1125 | Surveying Consumables | 2019-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17652-001025 | 17652 | 2019-05-17 16:08 | Section 3 | Material | Concrete Drainage | Not on List | 1 | ea | 677.13 | 677.13 | Ductile Drainage | 2019-05-22 | Gate C - 1339702 - BN06 (East Coast Railway) Via Logistics Yard Access | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17761-001025 | 17761 | 2019-05-20 15:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 6 | EA | 3.05 | 18.3 | PPE | 2019-05-22 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17801-001025 | 17801 | 2019-05-21 10:28 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Builders Merchants (General) | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17801-001025 | 17801 | 2019-05-21 10:28 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17801-001025 | 17801 | 2019-05-21 10:28 | Section 2 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17802-001025 | 17802 | 2019-05-21 10:56 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 3645 | 3645 | Surveying Consumables | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-17571-001025 | 17571 | 2019-05-16 17:44 | Section 4 | Material | Not on List | Not on List | 20 | Each | 4.97 | 99.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-17767-001025 | 17767 | 2019-05-20 16:11 | Section 4 | Material | Not on List | Not on List | 1 | Each | 245 | 245 | Miscellaneous | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17516-001025 | 17516 | 2019-05-16 09:28 | Section 4 | Material | Not on List | Not on List | 1 | Permit | 1959 | 1959 | Miscellaneous | 2019-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26484-001025 | 26484 | 2019-11-12 13:25 | Section 4 | Material | NULL | Not on List | 6 | Each | 15 | 90 | Electrical | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26484-001025 | 26484 | 2019-11-12 13:25 | Section 4 | Material | NULL | Not on List | 1 | Each | 16 | 16 | Electrical | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26549-001025 | 26549 | 2019-11-13 11:25 | Section 2 | Material | Not on List | Not on List | 2 | NULL | 1305 | 2610 | Concrete Accessories | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-26549-001025 | 26549 | 2019-11-13 11:25 | Section 2 | Material | Not on List | Not on List | 2 | NULL | 1305 | 2610 | Concrete Accessories | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-26549-001025 | 26549 | 2019-11-13 11:25 | Section 2 | Material | Not on List | Not on List | 2 | NULL | 1612.5 | 3225 | Concrete Accessories | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-26549-001025 | 26549 | 2019-11-13 11:25 | Section 2 | Material | Not on List | Not on List | 2 | NULL | 1612.5 | 3225 | Concrete Accessories | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-26577-001025 | 26577 | 2019-11-14 08:45 | Section 2 | Material | Not on List | Not on List | 1 | each | 6000 | 6000 | Professional Services | 2019-11-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26579-001025 | 26579 | 2019-11-14 09:12 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26188-001025 | 26188 | 2019-11-06 07:41 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1016.66 | Each | 1 | 1016.66 | PPE | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26189-001025 | 26189 | 2019-11-06 07:44 | Core | Material | PPE, Small Tools and Consumables | Not on List | 585.1 | Each | 1 | 585.1 | Janitorial | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26206-001025 | 26206 | 2019-11-06 07:50 | Core | Material | PPE, Small Tools and Consumables | Not on List | 726.88 | Each | 1 | 726.88 | Small Tools (Consumables) | 2019-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7246-001021 | 7246 | 2018-10-01 17:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3427.35 | Each | 1 | 3427.35 | Small Tools (Consumables) | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26111-001025 | 26111 | 2019-11-04 14:57 | Core | Material | NULL | NULL | 1 | EA | 151.91 | 151.91 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26095-001025 | 26095 | 2019-11-04 10:56 | Core | Material | Not on List | NULL | 1 | EA | 239.52 | 239.52 | Miscellaneous | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26158-001025 | 26158 | 2019-11-05 14:48 | Core | Material | NULL | NULL | 1 | Each | 2713 | 2713 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26498-001025 | 26498 | 2019-11-12 15:47 | Core | Material | Not on List | NULL | 1 | SM | 285 | 285 | Miscellaneous | 2019-11-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 1900 | Each | 21.01 | 39919 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 23 | Each | 151.94 | 3494.62 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 20 | Each | 201.59 | 4031.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 10 | Each | 4.9 | 49 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 1 | Each | 34.84 | 34.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7309-001022 | 7309 | 2018-10-02 17:26 | Section 4 | Material | Waste Management | Construction Waste - Skip 12 cubic yard | 1 | Each | 195 | 195 | Not Sure | 2018-10-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26463-001025 | 26463 | 2019-11-12 08:24 | Section 4 | Material | Kerbs | Not on List | 32 | Each | 6 | 192 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26500-001025 | 26500 | 2019-11-12 16:31 | Core | Material | NULL | NULL | 2 | Each | 55 | 110 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26420-001025 | 26420 | 2019-11-11 12:04 | Section 5 | Material | PPE, Small Tools and Consumables | NULL | 1 | EA | 282.81 | 282.81 | Miscellaneous | 2019-11-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26590-001025 | 26590 | 2019-11-14 11:56 | Section 3 | Material | Aggregate | Type 1 | 114 | Tonnes | 21.65 | 2468 | Aggregate | 2019-11-15 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-26578-001025 | 26578 | 2019-11-13 12:33 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4605.14 | each | 1 | 4605.14 | PPE | 2019-11-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26544-001025 | 26544 | 2019-11-13 14:57 | Section 5 | Material | Not on List | NULL | 40 | EA | 24.5 | 980 | Miscellaneous | 2019-11-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26591-001025 | 26591 | 2019-11-14 12:24 | Core | Material | NULL | NULL | 1 | Each | 920 | 920 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26580-001025 | 26580 | 2019-11-14 09:10 | Section 5 | Material | Not on List | NULL | 1 | SM | 124.5 | 124.5 | Surveying Consumables | 2019-11-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26585-001025 | 26585 | 2019-11-14 09:48 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | each | 4605.14 | 4605.14 | PPE | 2019-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26603-001025 | 26603 | 2019-11-14 14:43 | Section 2 | Material | Twinwall | Not on List | 2 | NULL | NULL | 0 | Plastic Drainage | 2019-11-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26616-001025 | 26616 | 2019-11-14 16:29 | Section 6 | Material | Not on List | Not on List | 110 | Meters | NULL | 0 | Builders Merchants (General) | 2019-11-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26545-001025 | 26545 | 2019-11-13 15:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 2165 | 4330 | Concrete Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26545-001025 | 26545 | 2019-11-13 15:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 1840 | 3680 | Concrete Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26545-001025 | 26545 | 2019-11-13 15:05 | Section 4 | Material | Not on List | Not on List | 3 | Each | 2490 | 7470 | Concrete Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26545-001025 | 26545 | 2019-11-13 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2555 | 2555 | Concrete Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26545-001025 | 26545 | 2019-11-13 15:05 | Section 4 | Material | NULL | Not on List | 1 | Each | 655 | 655 | Concrete Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26630-001025 | 26630 | 2019-11-15 08:42 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 12.87 | 64 | Small Tools (Consumables) | 2019-11-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | NULL | Yes - Approve | Req - S5 Buyers
MREQ-26630-001025 | 26630 | 2019-11-15 08:42 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | ea | 2.05 | 41 | Small Tools (Consumables) | 2019-11-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | NULL | Yes - Approve | Req - S5 Buyers
MREQ-26641-001025 | 26641 | 2019-11-15 11:29 | Section 5 | Material | Timber | NULL | 1 | SM | 3673.36 | 3673.36 | Timber Products | 2019-11-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26641-001025 | 26641 | 2019-11-15 11:29 | Section 5 | Material | Not on List | NULL | 300 | EA | 0.23 | 69 | Miscellaneous | 2019-11-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26649-001025 | 26649 | 2019-11-15 14:57 | Section 5 | Material | Not on List | Not on List | 1 | NULL | 1365 | 1365 | Miscellaneous | 2019-11-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7298-001022 | 7298 | 2018-10-02 16:05 | Section 4 | Material | Not on List | Not on List | 3000 | Each | 1 | 3000 | Waste (General) | 2018-10-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26655-001025 | 26655 | 2019-11-15 16:27 | Core | Material | Not on List | Not on List | 1 | NULL | 1650 | 1650 | Miscellaneous | 2019-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26688-001025 | 26688 | 2019-11-18 14:21 | Section 6 | Material | Not on List | Not on List | 1 | No. | 8310 | 8310 | Miscellaneous | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26689-001025 | 26689 | 2019-11-18 14:10 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 7123 | 7123 | Miscellaneous | 2019-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | Not on List | Not on List | 2 | Each | 395.57 | 791.14 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | Not on List | Not on List | 2 | Each | 272.12 | 544.24 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | Not on List | Not on List | 2 | Each | 780.31 | 1560.62 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | Not on List | Not on List | 2 | Each | 162.27 | 324.54 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26622-001025 | 26622 | 2019-11-14 17:53 | Section 4 | Material | NULL | Not on List | 1 | Each | 55 | 55 | Concrete Drainage | 2019-11-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26715-001025 | 26715 | 2019-11-19 08:13 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | ea | 89.25 | 179 | Concrete Accessories | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26730-001025 | 26730 | 2019-11-19 10:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 50.5 | 51 | Surveying Consumables | 2019-11-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26297-001025 | 26297 | 2019-11-07 15:54 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26487 | 26487 | 2019-10-08 15:08 | Core | Material | Not on List | Not on List | 1 | ea | 179 | 179 | Training | 2019-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-26276-001025 | 26276 | 2019-11-07 10:34 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26653-001025 | 26653 | 2019-11-15 15:18 | Section 5 | Material | Not on List | Not on List | 6 | ea | 53.79 | 322.74 | Builders Merchants (General) | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26653-001025 | 26653 | 2019-11-15 15:18 | Section 5 | Material | Not on List | Not on List | 14 | ea | 84.98 | 1189.72 | Builders Merchants (General) | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26653-001025 | 26653 | 2019-11-15 15:18 | Section 5 | Material | Not on List | Not on List | 5 | ea | 58.54 | 292.7 | Builders Merchants (General) | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26653-001025 | 26653 | 2019-11-15 15:18 | Section 5 | Material | Not on List | Not on List | 2 | ea | 30.93 | 61.86 | Builders Merchants (General) | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26653-001025 | 26653 | 2019-11-15 15:18 | Section 5 | Material | Not on List | Not on List | 1 | ea | 16.96 | 16.96 | Builders Merchants (General) | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26738-001025 | 26738 | 2019-11-19 12:22 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 250 | No | NULL | 0 | Surveying Consumables | 2019-11-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26351-001025 | 26351 | 2019-11-08 13:17 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7234-001021 | 7234 | 2018-10-01 15:11 | Section 4 | Material | Not on List | Not on List | 40 | number | 23.15 | 926 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26742-001025 | 26742 | 2019-11-19 12:57 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26744-001025 | 26744 | 2019-11-19 13:08 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26749-001025 | 26749 | 2019-11-19 13:44 | Core | Material | Not on List | Not on List | 9 | number | 295 | 2655 | Surveying Consumables | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26749-001025 | 26749 | 2019-11-19 13:44 | Core | Material | Not on List | Not on List | 10 | number | 700 | 7000 | Surveying Consumables | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26721-001025 | 26721 | 2019-11-19 08:00 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.98 | 196 | Surveying Consumables | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26721-001025 | 26721 | 2019-11-19 08:00 | Section 4 | Material | Not on List | Not on List | 300 | Each | 0.5 | 150 | Surveying Consumables | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26753-001025 | 26753 | 2019-11-19 15:52 | Core | Material | Not on List | Not on List | 1 | no | 20000 | 20000 | Office Supplies | 2019-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | Pack | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 35 | linier m | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 35 | linier m | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7234-001021 | 7234 | 2018-10-01 15:11 | Section 4 | Material | Not on List | Not on List | 40 | number | 9.6 | 384 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 40 | no | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | PAck | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | Pack | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | Pack | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | Pack | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26755-001025 | 26755 | 2019-11-19 15:51 | Section 6 | Material | Not on List | Not on List | 1 | Pack | NULL | 0 | Concrete Accessories | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25645-001025 | 25645 | 2019-10-23 16:34 | Core | Material | NULL | NULL | 1 | Each | 50 | 50 | Miscellaneous | 2019-11-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25645-001025 | 25645 | 2019-10-23 16:34 | Core | Material | NULL | NULL | 1 | Each | 753.36 | 753.36 | Miscellaneous | 2019-11-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25645-001025 | 25645 | 2019-10-23 16:34 | Core | Material | NULL | NULL | 1 | Each | 720 | 720 | Miscellaneous | 2019-11-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7234-001021 | 7234 | 2018-10-01 15:11 | Section 4 | Material | Not on List | Not on List | 40 | number | 5.9 | 236 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26783-001025 | 26783 | 2019-11-20 07:47 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26791-001025 | 26791 | 2019-11-20 08:50 | Section 5 | Material | Not on List | Not on List | 5 | each | 450 | 2250 | Miscellaneous | 2019-11-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26793-001025 | 26793 | 2019-11-20 09:33 | Core | Material | Not on List | Not on List | 1 | ea | 4668 | 4668 | Office Supplies | 2019-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26794-001025 | 26794 | 2019-11-20 09:26 | Section 6 | Material | Not on List | Not on List | 1 | No | NULL | 0 | Surveying Consumables | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26795-001025 | 26795 | 2019-11-20 09:05 | Core | Material | Not on List | Not on List | 1 | NULL | 874.07 | 874 | Miscellaneous | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26800-001025 | 26800 | 2019-11-20 10:56 | Core | Material | Not on List | Not on List | 1 | NULL | 850 | 850 | Miscellaneous | 2019-11-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26684-001025 | 26684 | 2019-11-18 13:45 | Core | Material | PPE, Small Tools and Consumables | Not on List | 879.72 | each | 1 | 879.72 | Small Tools (Consumables) | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26801-001025 | 26801 | 2019-11-20 10:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 446.26 | 446 | Janitorial | 2019-11-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7234-001021 | 7234 | 2018-10-01 15:11 | Section 4 | Material | Not on List | Not on List | 40 | number | 13.9 | 556 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26801-001025 | 26801 | 2019-11-20 10:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 105.78 | 106 | Small Tools (Consumables) | 2019-11-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26801-001025 | 26801 | 2019-11-20 10:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 253.88 | 254 | PPE | 2019-11-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26576-001025 | 26576 | 2019-11-14 08:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | each | 22.5 | 45 | Small Tools (Consumables) | 2019-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26576-001025 | 26576 | 2019-11-14 08:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | each | 66 | 132 | Small Tools (Consumables) | 2019-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26576-001025 | 26576 | 2019-11-14 08:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | each | 78.4 | 78.4 | Small Tools (Consumables) | 2019-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26565-001025 | 26565 | 2019-11-13 16:23 | Section 4 | Material | Waste Management | Not on List | 2 | Each | 1965 | 3930 | Miscellaneous | 2019-11-15 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26534-001025 | 26534 | 2019-11-13 09:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 136.8 | 136.8 | Miscellaneous | 2019-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26535-001025 | 26535 | 2019-11-13 10:12 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 3677.71 | 3677.71 | Miscellaneous | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26573-001025 | 26573 | 2019-11-13 18:35 | Section 4 | Material | Not on List | Not on List | 24 | Each | 12.8 | 307.2 | Miscellaneous | 2019-11-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2702 - Works by the Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7234-001021 | 7234 | 2018-10-01 15:11 | Section 4 | Material | Not on List | Not on List | 40 | number | 6.05 | 242 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26396-001025 | 26396 | 2019-11-11 07:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 165.35 | 165.35 | Miscellaneous | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26771-001025 | 26771 | 2019-11-19 17:48 | Section 4 | Material | Not on List | Not on List | 1 | Each | 555 | 555 | Miscellaneous | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26572-001025 | 26572 | 2019-11-14 07:47 | Section 4 | Material | Not on List | Not on List | 1 | Each | 336 | 336 | Miscellaneous | 2019-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26491-001025 | 26491 | 2019-11-12 14:34 | Section 4 | Material | Not on List | Not on List | 40 | Bag | 31.63 | 1265.2 | Concrete Accessories | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26491-001025 | 26491 | 2019-11-12 14:34 | Section 4 | Material | Not on List | Not on List | 150 | KG | 3.1 | 465 | Rebar and Mesh | 2019-11-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26718-001025 | 26718 | 2019-11-19 08:18 | Section 4 | Material | Not on List | Not on List | 1 | Each | 682.06 | 682.06 | Miscellaneous | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26638-001025 | 26638 | 2019-11-15 10:19 | Core | Material | Not on List | Not on List | 1 | NULL | 1700 | 1700 | Miscellaneous | 2019-11-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7296-001022 | 7296 | 2018-10-02 15:48 | Section 4 | Material | Not on List | Not on List | 2 | Polybottles (5 litre each) | 33.88 | 67.76 | Miscellaneous | 2018-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1705 - Repairs to Existing Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26827-001025 | 26827 | 2019-11-21 07:04 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26830-001025 | 26830 | 2019-11-21 07:33 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7300-001022 | 7300 | 2018-10-02 16:33 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 808.5 | 808.5 | Small Tools (Consumables) | 2018-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26593-001025 | 26593 | 2019-11-14 12:24 | Section 4 | Material | Not on List | Not on List | 200 | Each | 9.92 | 1984 | Miscellaneous | 2019-11-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26834-001025 | 26834 | 2019-11-21 08:13 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26836-001025 | 26836 | 2019-11-21 08:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26728-001025 | 26728 | 2019-11-19 09:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 3320 | 3320 | Concrete Accessories | 2019-11-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN06 - ECML Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26837-001025 | 26837 | 2019-11-21 09:01 | Section 5 | Material | Not on List | Not on List | 10 | bags | NULL | 0 | Builders Merchants (General) | 2019-11-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26654-001025 | 26654 | 2019-11-15 10:38 | Section 5 | Material | NULL | NULL | NULL | ea | NULL | 0 | NULL | 2019-11-22 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26282-001025 | 26282 | 2019-11-07 13:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | each | 2.97 | 332.64 | Builders Merchants (General) | 2019-11-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 12 | Each | 114 | 1368 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10505-001025 | 10505 | 2018-12-20 12:50 | Section 4 | Material | Not on List | Not on List | 18000 | M2 | 7.5 | 135000 | Plastic Drainage | 2019-01-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | NULL | Not on List | 9 | Packs | 54.4 | 489.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | NULL | Not on List | 3 | Packs | 54.4 | 163.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | NULL | Not on List | 3 | No | 10.35 | 31.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10560-001025 | 10560 | 2019-01-03 14:25 | Section 3 | Material | NULL | Not on List | 3 | No | 10.35 | 31.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-11 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 15 | EA | 209.35 | 3140.25 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 5 | Each | 149.45 | 747.25 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 10 | Each | 24.44 | 244.4 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 35 | Each | 116.62 | 4081.7 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 45 | Each | 17.48 | 786.6 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 90 | Each | 34.82 | 3133.8 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 112 | Each | 6.54 | 732.48 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 75 | Each | 23.14 | 1735.5 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 91 | Each | 3.38 | 307.58 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 86 | Each | 10.5 | 903 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 106 | Each | 1.84 | 195.04 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 20 | EA | 67.9 | 1358 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 19.72 | 394.4 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | Each | 15.71 | 942.6 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | Each | 4.9 | 294 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 60 | Each | 10.5 | 630 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 30 | Each | 14.4 | 432 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 30 | Each | 39.7 | 1191 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 15 | Each | 44.41 | 666.15 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 20 | EA | 50.92 | 1018.4 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 10 | Each | 84.41 | 844.1 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 15.19 | 303.8 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 110 | Each | 10.04 | 1104.4 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 254 | Each | 2.75 | 698.5 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 242 | Each | 1.86 | 450.12 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10513-001025 | 10513 | 2018-12-21 09:20 | Section 4 | Material | Not on List | Not on List | 477 | Each | 0.85 | 405.45 | Plastic Drainage | 2019-01-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10682-001025 | 10682 | 2019-01-08 09:12 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | no | 877.51 | 877.51 | Miscellaneous | 2019-01-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10699-001025 | 10699 | 2019-01-08 11:45 | Section 3 | Material | Concrete Drainage | Not on List | 9 | No. | 2339.56 | 21056.04 | Concrete Drainage | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10690-001025 | 10690 | 2019-01-08 10:23 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-01-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5427-00264 | 5427 | 2018-08-21 11:14 | Section 3 | Material | Concrete Drainage | Not on List | 20 | EA | 43.16 | 863.2 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10747-001025 | 10747 | 2019-01-09 10:32 | Section 4 | Material | Twinwall | Not on List | 20 | no | NULL | 0 | Plastic Drainage | 2019-01-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10747-001025 | 10747 | 2019-01-09 10:32 | Section 4 | Material | Twinwall | Not on List | 20 | no | NULL | 0 | Plastic Drainage | 2019-01-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10747-001025 | 10747 | 2019-01-09 10:32 | Section 4 | Material | Twinwall | Not on List | 10 | no | NULL | 0 | Plastic Drainage | 2019-01-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10747-001025 | 10747 | 2019-01-09 10:32 | Section 4 | Material | Saint Gobain Castings | Not on List | 15 | no | NULL | 0 | Ductile Drainage | 2019-01-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1502 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10750-001025 | 10750 | 2019-01-09 10:47 | Section 3 | Material | Not on List | Not on List | 5 | Bags | NULL | 0 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10750-001025 | 10750 | 2019-01-09 10:47 | Section 3 | Material | Not on List | Not on List | 120 | kg | NULL | 0 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 35 | Each | 149.45 | 5230.75 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 41 | Each | 24.44 | 1002.04 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 30 | Each | 23.14 | 694.2 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 34 | Each | 3.38 | 114.92 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 55 | Each | 10.5 | 577.5 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 63 | Each | 1.84 | 115.92 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 5 | Each | 19.72 | 98.6 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | Each | 15.71 | 785.5 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | Each | 4.9 | 245 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 50 | Each | 10.5 | 525 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 22 | Each | 14.4 | 316.8 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 15 | Each | 39.7 | 595.5 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 18 | Each | 258.72 | 4656.96 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 82 | Each | 15.19 | 1245.58 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 36 | Each | 10.04 | 361.44 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 98 | Each | 1.86 | 182.28 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10514-001025 | 10514 | 2018-12-21 09:49 | Section 4 | Material | Not on List | Not on List | 345 | Each | 0.85 | 293.25 | Plastic Drainage | 2019-01-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10759-001025 | 10759 | 2019-01-09 12:47 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 145 | 145 | Surveying Consumables | 2019-01-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Boot Wellington Safety Toe And Midsole Black S5 Tuf (165022) | 3 | Each | 10.95 | 33 | PPE | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Scraper Boot Galvanised C/W Brushes (746900) | 10 | Each | 10.19 | 102 | Miscellaneous | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 0.39 | 4 | Miscellaneous | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10761-001025 | 10761 | 2019-01-09 13:06 | Section 3 | Material | Not on List | Not on List | 12 | No | NULL | 0 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 690 | 690 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 555 | 555 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 420 | 420 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 60 | Number | NULL | 0 | Concrete Accessories | 2019-01-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 2302 - Sealing of gaps | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 200 | Number | NULL | 0 | Concrete Accessories | 2019-01-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10746-001025 | 10746 | 2019-01-09 10:43 | Section 4 | Material | Not on List | Not on List | 13.209 | tonne | 538 | 7106.44 | Rebar and Mesh | 2019-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10687-001025 | 10687 | 2019-01-08 10:08 | Section 4 | Material | Not on List | Not on List | 32 | no | 6.26 | 200.32 | Concrete Accessories | 2019-01-14 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10771-001025 | 10771 | 2019-01-09 14:56 | Section 4 | Material | Timber | Not on List | 500 | NULL | NULL | 0 | Timber Products | 2019-01-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1703 - Formwork | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 105 | Each | 23.14 | 2430 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 53 | Each | 3.38 | 179 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 106 | Each | 1.86 | 197 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 36 | Each | NULL | 0 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Twinwall | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 8 | Each | 39.7 | 318 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5468-00301 | 5468 | 2018-08-21 17:45 | Section 4 | Material | Not on List | Not on List | 1 | Each | 404.45 | 404.45 | Damage Charges | 2018-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 3 | Each | NULL | 0 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Twinwall | Polypipe 150mm x 25m Ridgiflex (877588) | 4 | Each | 145 | 580 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 21 | Each | 67.9 | 1426 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 6 | Each | 43.16 | 259 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 16 | Each | 35.52 | 568 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 21 | Each | 47.04 | 988 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 50 | Each | 16.49 | 824 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Saint Gobain Castings | Not on List | 10 | Each | NULL | 0 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 21 | Each | 81.73 | 1716 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 10 | Each | NULL | 0 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10677-001025 | 10677 | 2019-01-08 08:06 | Section 4 | Material | Not on List | Not on List | 120 | 2m | 211.66 | 25399.2 | Ductile Drainage | 2019-01-14 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | Not on List | 30 | NULL | NULL | 0 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 67.9 | 1019 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 15 | Each | 50.92 | 764 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 15 | Each | 43.16 | 647 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 5 | Each | 35.52 | 178 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10741-001025 | 10741 | 2019-01-09 07:44 | Section 4 | Material | Not on List | Not on List | 20 | rolls | 9.29 | 185.8 | Not Sure | 2019-01-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10793-001025 | 10793 | 2019-01-09 16:22 | Section 3 | Material | Ducting | Not on List | 1 | no | 837.68 | 838 | Damage Charges | 2019-01-10 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10694-001025 | 10694 | 2019-01-08 10:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1431.54 | Each | 1 | 1431.54 | Small Tools (Consumables) | 2019-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10799-001025 | 10799 | 2019-01-10 07:35 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10780-001025 | 10780 | 2019-01-09 16:11 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 20 | Each | 110.27 | 2205.4 | Geotextiles | 2019-01-11 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 604 - Deposition | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10805-001025 | 10805 | 2019-01-10 08:36 | Section 3 | Material | Not on List | Not on List | 5 | T | NULL | 0 | Builders Merchants (General) | 2019-01-17 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10828-001025 | 10828 | 2019-01-10 12:44 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10777-001025 | 10777 | 2019-01-09 15:53 | Section 4 | Material | NULL | Not on List | 9 | Each | 87.99 | 791.91 | Plastic Drainage | 2019-01-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | Each | 240 | 240 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | Each | 67.9 | 203.7 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | Each | 50.92 | 152.76 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | Each | 43.16 | 43.16 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 6 | Each | 47.04 | 282.24 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 24 | Each | 22 | 528 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 6 | Each | 74.3 | 445.8 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 1 | Each | 121.25 | 121.25 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 3 | Each | 90.94 | 272.82 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 80.51 | 322.04 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 102.82 | 411.28 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 16 | Each | 22 | 352 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10516-001025 | 10516 | 2018-12-21 10:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 74.3 | 297.2 | Concrete Drainage | 2019-01-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 4 | Each | 240 | 960 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 44 | Each | 67.9 | 2987.6 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 400 | Each | 3.4 | 1360 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 2 | Each | 34.82 | 69.64 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 5 | Each | 1.98 | 9.9 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 5 | Each | 7.06 | 35.3 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 12 | Each | 0.91 | 10.92 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 12 | Each | 2.97 | 35.64 | Plastic Drainage | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 250 | NULL | NULL | 0 | Concrete Accessories | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 35 | NULL | NULL | 0 | Rebar and Mesh | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21060-001025 | 21060 | 2019-07-19 11:03 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Rebar and Mesh | 2019-07-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21187-001025 | 21187 | 2019-07-23 11:18 | Section 3 | Material | PPE, Small Tools and Consumables | Refill Air Care Pristine Wild Berries Air Fragrance 270ml (539229) | 8 | Each | 3.1 | 25 | Janitorial | 2019-07-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 160 | Each | 3.4 | 544 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21127-001025 | 21127 | 2019-07-22 11:23 | Core | Material | Not on List | Not on List | 72 | case | 6.5 | 468 | Miscellaneous | 2019-07-24 | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21190-001025 | 21190 | 2019-07-23 11:54 | Section 4 | Material | Timber | Not on List | 2 | each | NULL | 0 | Builders Merchants (General) | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20589-001025 | 20589 | 2019-07-10 18:34 | Section 3 | Material | Not on List | Not on List | 112 | Bags | 2.97 | 332.64 | Builders Merchants (General) | 2019-07-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20589-001025 | 20589 | 2019-07-10 18:34 | Section 3 | Material | Not on List | Not on List | 56 | Bags | 2.97 | 166.32 | Builders Merchants (General) | 2019-07-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20589-001025 | 20589 | 2019-07-10 18:34 | Section 3 | Material | Not on List | Not on List | 12 | Plates | 219.65 | 2635.8 | Miscellaneous | 2019-08-05 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20589-001025 | 20589 | 2019-07-10 18:34 | Section 3 | Material | Not on List | Not on List | 4 | Plates | 183.04 | 732.16 | Miscellaneous | 2019-08-05 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20589-001025 | 20589 | 2019-07-10 18:34 | Section 3 | Material | Not on List | Not on List | 4 | Plates | 95.74 | 382.96 | Miscellaneous | 2019-08-05 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20892-001025 | 20892 | 2019-07-17 09:27 | Section 3 | Material | Not on List | Not on List | 4 | ea | 8.17 | 32.68 | Miscellaneous | 2019-07-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21202-001025 | 21202 | 2019-07-23 12:30 | Section 3 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-07-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21202-001025 | 21202 | 2019-07-23 12:30 | Section 3 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2019-07-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 12 | Each | 5.24 | 62.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | Kerbs | Not on List | 70 | No | NULL | 0 | Builders Merchants (General) | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | Kerbs | Not on List | 30 | No | NULL | 0 | Builders Merchants (General) | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 760 | Each | 1.5 | 1140 | Builders Merchants (General) | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 2 | Each | 7.68 | 15.36 | Builders Merchants (General) | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 2 | Each | 7.68 | 15.36 | Builders Merchants (General) | 2019-07-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20732-001025 | 20732 | 2019-07-14 05:05 | Section 3 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21210-001025 | 21210 | 2019-07-23 13:57 | Section 2 | Material | Timber | Not on List | 20 | NULL | NULL | 0 | Timber Products | 2019-07-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21114-001025 | 21114 | 2019-07-22 10:32 | Section 3 | Material | Not on List | Not on List | 6520 | No | 2.72 | 17734.4 | Builders Merchants (General) | 2019-07-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21114-001025 | 21114 | 2019-07-22 10:32 | Section 3 | Material | Not on List | Not on List | 200 | No | 3.12 | 624 | Builders Merchants (General) | 2019-07-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 64 | Each | 2.93 | 187.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21213-001025 | 21213 | 2019-07-23 14:21 | Core | Material | Not on List | Not on List | 6 | number | NULL | 0 | Surveying Consumables | 2019-08-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21213-001025 | 21213 | 2019-07-23 14:21 | Core | Material | Not on List | Not on List | 2 | number | NULL | 0 | Surveying Consumables | 2019-08-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21146-001025 | 21146 | 2019-07-22 14:53 | Section 3 | Material | Not on List | Not on List | 6 | Beam | 5308.36 | 31850.16 | Miscellaneous | 2019-04-22 | RVP 419 (S3) - 1340880 - A14 Westbound (West of Junction 28) | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21173-001025 | 21173 | 2019-07-23 08:04 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | NULL | 0.63 | 9.45 | Small Tools (Consumables) | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21104-001025 | 21104 | 2019-07-22 08:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Pack 24 Bottled Water | 6.29 | 905.76 | Small Tools (Consumables) | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21217-001025 | 21217 | 2019-07-23 16:03 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21108-001025 | 21108 | 2019-07-22 09:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 70.5 | 70.5 | Miscellaneous | 2019-07-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21118-001025 | 21118 | 2019-07-22 10:53 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | 0.79 | 31.6 | Small Tools (Consumables) | 2019-07-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21178-001025 | 21178 | 2019-07-23 09:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 226.18 | 226.18 | Small Tools (Consumables) | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21180-001025 | 21180 | 2019-07-23 09:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 466.34 | 466.34 | Small Tools (Consumables) | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 5 | Each | 5.25 | 26.25 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21174-001025 | 21174 | 2019-07-23 08:31 | Core | Material | Not on List | Not on List | 1 | No | 67.2 | 67.2 | Office Supplies | 2019-07-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21223-001025 | 21223 | 2019-07-23 17:20 | Section 5 | Material | PPE, Small Tools and Consumables | Water Natural Mineral Ideal Still 500ml Bottle Case Of 24 (744570) | 50 | Each | 6.29 | 315 | Small Tools (Consumables) | 2019-07-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21231-001025 | 21231 | 2019-07-24 06:58 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-21232-001025 | 21232 | 2019-07-24 07:11 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21207-001025 | 21207 | 2019-07-23 13:40 | Section 4 | Material | Waste Management | Plastic - Roll On Roll Off 20 cubic yard | 1 | Each | 360 | 360 | Waste (Recycling) | 2019-07-24 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21235-001025 | 21235 | 2019-07-24 07:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 3 | Each | 50 | 150 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21240-001025 | 21240 | 2019-07-24 08:26 | Section 3 | Material | Not on List | Not on List | 8 | No. | NULL | 0 | Fixings and Fasteners | 2019-07-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | CL3B - Structures (Culverts) 3B | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21240-001025 | 21240 | 2019-07-24 08:26 | Section 3 | Material | Not on List | Not on List | 15 | No. | NULL | 0 | Fixings and Fasteners | 2019-07-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | CL3B - Structures (Culverts) 3B | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21061-001025 | 21061 | 2019-07-19 13:32 | Section 4 | Material | NULL | NULL | 500 | Each | 7.5 | 3750 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21110-001025 | 21110 | 2019-07-22 09:23 | Section 4 | Material | NULL | NULL | 1 | Each | 35.6 | 35.6 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21249-001025 | 21249 | 2019-07-24 10:04 | Section 3 | Material | Not on List | Not on List | 10 | No. | NULL | 0 | Geotextiles | 2019-07-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 400 | Each | 1.45 | 580 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21249-001025 | 21249 | 2019-07-24 10:04 | Section 3 | Material | Not on List | Not on List | 1 | No. of Rolls | NULL | 0 | Geotextiles | 2019-07-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | CL3B - Structures (Culverts) 3B | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18791-001025 | 18791 | 2019-06-07 15:37 | Core | Material | Not on List | Not on List | 8 | licenses | 284.63 | 2277.04 | Miscellaneous | 2019-06-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20156-001025 | 20156 | 2019-07-03 12:20 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20159-001025 | 20159 | 2019-07-03 12:47 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19858-001025 | 19858 | 2019-06-27 15:52 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20977-001025 | 20977 | 2019-07-18 09:19 | Section 4 | Material | Waste Management | Plastic - Roll On Roll Off 20 cubic yard | 1 | Each | 360 | 360 | Waste (General) | 2019-07-22 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20977-001025 | 20977 | 2019-07-18 09:19 | Section 4 | Material | Bagged | Not on List | 20 | Number | 4.95 | 99 | Builders Merchants (General) | 2019-07-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20977-001025 | 20977 | 2019-07-18 09:19 | Section 4 | Material | Bagged | Not on List | 2 | Number | 166.22 | 332.44 | Builders Merchants (General) | 2019-07-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21260-001025 | 21260 | 2019-07-24 11:38 | Core | Material | Not on List | Not on List | 1 | Pack of 100 | 22 | 22 | Surveying Consumables | 2019-08-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Rigidrain P/E 225Mm Dia Incl Coup/Sealia | 1 | no | 4233.6 | 4233.6 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5501 | 5501 | 2018-08-22 13:39 | Section 4 | Material | Not on List | Not on List | 5 | Each | 5.25 | 26.25 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-28 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21260-001025 | 21260 | 2019-07-24 11:38 | Core | Material | Not on List | Not on List | 2 | number | NULL | 0 | Surveying Consumables | 2019-08-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21260-001025 | 21260 | 2019-07-24 11:38 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Surveying Consumables | 2019-08-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21236-001025 | 21236 | 2019-07-24 07:55 | Section 3 | Material | Not on List | Not on List | 20 | roll | 26.25 | 525 | Geotextiles | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20841-001025 | 20841 | 2019-07-16 13:32 | Section 4 | Material | Not on List | Not on List | 3 | Number | 20 | 60 | Surveying Consumables | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20749-001025 | 20749 | 2019-07-15 09:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 9950 | 9950 | Miscellaneous | 2019-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21278-001025 | 21278 | 2019-07-24 15:18 | Core | Material | Not on List | Not on List | 1 | number | 199.6 | 200 | Office Supplies | 2019-07-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20765-001025 | 20765 | 2019-07-15 13:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 693.74 | 693.74 | Miscellaneous | 2019-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21303-001025 | 21303 | 2019-07-25 06:54 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 300Mm X 6M Ridgidrain Plain Ended | 230 | Each | 34.82 | 8008.6 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21304-001025 | 21304 | 2019-07-25 07:14 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21305-001025 | 21305 | 2019-07-25 07:22 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-27 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-21306-001025 | 21306 | 2019-07-25 07:55 | Section 3 | Material | Not on List | Not on List | 5000 | No | NULL | 0 | Builders Merchants (General) | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21238-001025 | 21238 | 2019-07-24 08:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 10.5 | 105 | Surveying Consumables | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21238-001025 | 21238 | 2019-07-24 08:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 10.5 | 105 | Surveying Consumables | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21238-001025 | 21238 | 2019-07-24 08:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 10.5 | 105 | Surveying Consumables | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21326-001025 | 21326 | 2019-07-25 11:24 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 300Mm Ridgidrain Dbl Skt Coupler | 260 | Each | 6.54 | 1700.4 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21330-001025 | 21330 | 2019-07-25 11:37 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21332-001025 | 21332 | 2019-07-25 11:46 | Core | Material | Not on List | Not on List | 1 | 1215.2 | 1215.2 | 1215 | Miscellaneous | 2019-07-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21144-001025 | 21144 | 2019-07-22 14:40 | Section 3 | Material | Not on List | Not on List | 100 | ea | 3.38 | 338 | Rebar and Mesh | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21144-001025 | 21144 | 2019-07-22 14:40 | Section 3 | Material | Not on List | Not on List | 1000 | ea | 1.96 | 1960 | Rebar and Mesh | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21144-001025 | 21144 | 2019-07-22 14:40 | Section 3 | Material | Not on List | Not on List | 35 | ea | 1.78 | 62.3 | Concrete Accessories | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21144-001025 | 21144 | 2019-07-22 14:40 | Section 3 | Material | Not on List | Not on List | 100 | ea | 0.34 | 34 | Concrete Accessories | 2019-07-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 300Mm Ridgidrain Seal | 520 | Each | 2.75 | 1430 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21340-001025 | 21340 | 2019-07-25 12:40 | Core | Material | Not on List | Not on List | 1 | NULL | 1865 | 1865 | Professional Services | 2019-07-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21244-001025 | 21244 | 2019-07-24 09:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Small Tools (Consumables) | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21344-001025 | 21344 | 2019-07-25 13:45 | Section 4 | Material | Not on List | Not on List | 1 | Number | 186.09 | 186 | Surveying Consumables | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21317-001025 | 21317 | 2019-07-25 09:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 119.32 | 119.32 | Small Tools (Consumables) | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21351-001025 | 21351 | 2019-07-25 14:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 165.65 | 166 | PPE | 2019-07-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21351-001025 | 21351 | 2019-07-25 14:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 854.18 | 854 | Small Tools (Consumables) | 2019-07-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21351-001025 | 21351 | 2019-07-25 14:19 | Core | Material | Not on List | Not on List | 1 | NULL | 109 | 109 | Janitorial | 2019-07-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21322-001025 | 21322 | 2019-07-25 11:08 | Section 4 | Material | NULL | NULL | 120 | Each | 16.57 | 1988.4 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 400Mm X 6M R-Drain Unperf + Coup | 120 | Each | 120.62 | 14474.4 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21359-001025 | 21359 | 2019-07-25 14:58 | Section 2 | Material | Hazardous Waste | Not on List | 1 | each | 1280 | 1280 | Waste (General) | 2019-07-31 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Concrete Drainage | Cpm 1050X1000 C/W Steps | 30 | Each | 67.9 | 2037 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21247-001025 | 21247 | 2019-07-24 10:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 33.95 | 271.6 | Small Tools (Consumables) | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21042-001025 | 21042 | 2019-07-19 11:44 | Section 5 | Material | Not on List | Not on List | 1 | SM | 52583 | 52583 | Not Sure | 2019-07-29 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 55 | NULL | 179.74 | 9885.7 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 65 | NULL | 22.36 | 1453.4 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 131.32 | 787.92 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Not on List | Not on List | 180 | Each | 9.04 | 1627.2 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 38.36 | 230.16 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 10 | NULL | 125.94 | 1259.4 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 10 | NULL | 125.94 | 1259.4 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 10 | NULL | 10.84 | 108.4 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 5 | NULL | 18.87 | 94.35 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 35 | NULL | 130.26 | 4559.1 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 35 | NULL | 9.76 | 341.6 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21354-001025 | 21354 | 2019-07-25 13:50 | Section 4 | Material | Not on List | Not on List | 12 | NULL | 18.84 | 226.08 | Plastic Drainage | 2019-08-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21008-001025 | 21008 | 2019-07-18 17:51 | Section 5 | Material | Not on List | Not on List | 300 | No | 7.5 | 2250 | Surveying Consumables | 2019-07-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21176-001025 | 21176 | 2019-07-23 08:47 | Core | Material | Not on List | Not on List | 6 | ea | 37 | 222 | Office Supplies | 2019-07-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Not on List | Not on List | 11 | Each | 50.92 | 560.12 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21393-001025 | 21393 | 2019-07-26 08:05 | Core | Material | NULL | NULL | 1 | Eack | 393.42 | 393.42 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21280-001025 | 21280 | 2019-07-24 14:29 | Core | Material | NULL | NULL | 2000 | Each | 0.51 | 1020 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21434-001025 | 21434 | 2019-07-26 13:18 | Section 2 | Material | Not on List | Not on List | 2 | 5ltr Tubs | NULL | 0 | Blocks and Bricks | 2019-07-31 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN02 - Grafham Road Bridge | 2401 - Brickwork, Blockwork and Stonework | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-8483-001023 | 8483 | 2018-10-31 09:14 | Section 4 | Material | Not on List | Not on List | 80 | U | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8483-001023 | 8483 | 2018-10-31 09:14 | Section 4 | Material | Not on List | Not on List | 20 | U | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8487-001023 | 8487 | 2018-10-31 09:22 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8489-001023 | 8489 | 2018-10-31 10:03 | Section 4 | Material | Not on List | Not on List | 5 | NULL | 145 | 725 | Surveying Consumables | 2018-11-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8376-001023 | 8376 | 2018-10-29 14:03 | Section 4 | Material | Not on List | Not on List | 400 | Each | 0.48 | 192 | Concrete Accessories | 2018-10-31 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8440-001023 | 8440 | 2018-10-30 11:31 | Section 4 | Material | Not on List | Not on List | 10 | 1t Bag | 32.74 | 327.4 | Builders Merchants (General) | 2018-11-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8439-001023 | 8439 | 2018-10-30 11:24 | Section 4 | Material | NULL | Building Sand Bulk Bag (938155) | 4 | Each | 32.74 | 130.96 | Builders Merchants (General) | 2018-10-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8446-001023 | 8446 | 2018-10-30 11:21 | Section 4 | Material | NULL | Kiln Dried Sand 25kg (518674) | 80 | Each | 2.26 | 180.8 | Builders Merchants (General) | 2018-11-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8495-001023 | 8495 | 2018-10-31 12:11 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Drainage | 2018-11-05 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8511-001023 | 8511 | 2018-10-31 15:25 | Section 3 | Material | Aggregate | Not on List | 1500 | m3 | 43.08 | 64620 | Aggregate | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8516-001023 | 8516 | 2018-10-31 15:46 | Section 3 | Material | Signage | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8532-001023 | 8532 | 2018-10-31 18:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-11-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 6 | number | 310.05 | 1860.3 | Not Sure | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 10 | number | 32.15 | 321.5 | Concrete Accessories | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Not on List | Not on List | 6 | number | 89.6 | 537.6 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Signage | Directional Signage - 390 x 510 | 8 | Each | 7.9441 | 63.55 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8317-001023 | 8317 | 2018-10-26 13:46 | Section 3 | Material | Signage | Directional Signage - 390 x 510 | 6 | Each | 7.9441 | 47.66 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8537-001023 | 8537 | 2018-11-01 07:38 | Section 3 | Material | Concrete Drainage | Not on List | 20 | Units | 1346 | 26920 | Concrete Drainage | 2018-11-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8464-001023 | 8464 | 2018-10-30 18:14 | Section 3 | Material | PPE, Small Tools and Consumables | Helmet Attachment-jsp Navy Blue Helmet Warmer (271301) | 31 | Each | 5.43 | 168.33 | PPE | 2018-11-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8516-001023 | 8516 | 2018-10-31 15:46 | Section 3 | Material | Signage | Not on List | 1 | number | 252.85 | 252.85 | Miscellaneous | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN06 - ECML Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8566-001023 | 8566 | 2018-11-01 12:43 | Section 3 | Material | Not on List | Not on List | 1 | Number | 3253.2 | 3253 | Miscellaneous | 2018-11-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8511-001023 | 8511 | 2018-10-31 15:25 | Section 3 | Material | Aggregate | Not on List | 1500 | m3 | 43.08 | 64620 | Aggregate | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8532-001023 | 8532 | 2018-10-31 18:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 902 | 902 | Damage Charges | 2018-11-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8537-001023 | 8537 | 2018-11-01 07:38 | Section 3 | Material | Concrete Drainage | Not on List | 20 | Units | 1346 | 26920 | Concrete Drainage | 2018-11-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8487-001023 | 8487 | 2018-10-31 09:22 | Section 3 | Material | Aggregate | NULL | 10 | roll | 24.3 | 243 | Miscellaneous | 2018-11-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8578-001023 | 8578 | 2018-11-01 15:23 | Section 4 | Material | Not on List | Not on List | 25 | NULL | NULL | 0 | Not Sure | 2018-11-05 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8597-001023 | 8597 | 2018-11-01 16:15 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 5993.59 | 5994 | Miscellaneous | 2018-11-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8597-001023 | 8597 | 2018-11-01 16:15 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 5993.59 | 5993.59 | Miscellaneous | 2018-11-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8578-001023 | 8578 | 2018-11-01 15:23 | Section 4 | Material | Not on List | Not on List | 25 | NULL | NULL | 0 | Not Sure | 2018-11-05 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | PPE, Small Tools and Consumables | Stake Marking Out Wooden 1200mm Nominal C.r.code Swcoc004463 (740904) | 500 | Each | 1.07 | 535 | Surveying Consumables | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | NULL | 0 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 941 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 67.9 | 1019 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 432 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | Not on List | 10 | NULL | NULL | 0 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 10 | Each | 59.17 | 592 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8494-001023 | 8494 | 2018-10-31 10:54 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 200 | Each | 0.5 | 100 | Miscellaneous | 2018-11-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8458-001023 | 8458 | 2018-10-30 16:02 | Section 4 | Material | PPE, Small Tools and Consumables | Granules Ice Melt 10kg Bag Ref: 110160 (500258) | 80 | Each | 18.03 | 1442.4 | Miscellaneous | 2018-11-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8503-001023 | 8503 | 2018-10-31 13:28 | Section 4 | Material | Not on List | Not on List | 7 | Each | 15125 | 105875 | Electrical | 2018-11-01 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8483-001023 | 8483 | 2018-10-31 09:14 | Section 4 | Material | Not on List | Not on List | 80 | U | 2.18 | 174.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8483-001023 | 8483 | 2018-10-31 09:14 | Section 4 | Material | Not on List | Not on List | 20 | U | 5.84 | 116.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8544-001023 | 8544 | 2018-11-01 08:56 | Section 4 | Material | Hazardous Waste | Not on List | 1 | 8 yard hazardous waste Skip | 655 | 655 | Waste (General) | 2018-11-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 3.352 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 3.352 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 3.394 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 0.125 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 2 | tonne | NULL | 0 | Reinforcement | 2018-11-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8415-001023 | 8415 | 2018-10-30 06:33 | Section 4 | Material | Not on List | Not on List | 3 | 20ltr Case | 145.9 | 437.7 | Miscellaneous | 2018-11-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8495-001023 | 8495 | 2018-10-31 12:11 | Section 4 | Material | Not on List | Not on List | 10 | NULL | 361.34 | 3613.4 | Concrete Drainage | 2018-11-05 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8457-001023 | 8457 | 2018-10-30 15:47 | Section 4 | Material | NULL | Not on List | 1 | 100 Number | 675 | 675 | Timber Products | 2018-11-02 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8662-001023 | 8662 | 2018-11-05 07:56 | Section 3 | Material | Not on List | Not on List | 1 | ea | 96.8 | 97 | Damage Charges | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8676-001023 | 8676 | 2018-11-05 09:55 | Section 4 | Material | Not on List | Not on List | 30 | no | NULL | 0 | Miscellaneous | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | Not on List | Not on List | 1 | no | NULL | 0 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | Not on List | Not on List | 6 | no | NULL | 0 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | Not on List | Not on List | 1 | no | NULL | 0 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5034-0020 | 5034 | 2018-08-14 09:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 920 | NULL | NULL | 0 | Surveying Consumables | 2018-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5213-00119 | 5213 | 2018-08-16 10:28 | Section 4 | Material | Plastic Drainage | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6694-001023 | 6694 | 2018-09-18 17:31 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | Concrete Drainage | Not on List | 10 | U | NULL | 0 | Concrete Drainage | 2018-11-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | Concrete Drainage | Not on List | 12 | U | NULL | 0 | Concrete Drainage | 2018-11-08 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8712-001024 | 8712 | 2018-11-05 16:20 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Timber Products | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1703 - Formwork | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8712-001024 | 8712 | 2018-11-05 16:20 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Timber Products | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1703 - Formwork | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8712-001024 | 8712 | 2018-11-05 16:20 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Timber Products | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1703 - Formwork | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-5246-00160 | 5246 | 2018-08-16 16:02 | Section 4 | Material | Not on List | Not on List | 2000 | NULL | 0.03 | 60 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8714-001024 | 8714 | 2018-11-05 16:38 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8295-001023 | 8295 | 2018-10-26 10:26 | Section 3 | Material | Not on List | Not on List | 3 | Visits | 950 | 2850 | Professional Services | 2018-10-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8295-001023 | 8295 | 2018-10-26 10:26 | Section 3 | Material | Not on List | Not on List | 1 | Visit | 136.69 | 136.69 | Professional Services | 2018-10-30 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8690-001024 | 8690 | 2018-11-05 11:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8690-001024 | 8690 | 2018-11-05 11:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1000 | EA | 1.07 | 1070 | Miscellaneous | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8736-001024 | 8736 | 2018-11-06 09:00 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-11-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8737-001024 | 8737 | 2018-11-06 08:59 | Section 4 | Material | Concrete Drainage | Not on List | 2 | U | NULL | 0 | Concrete Drainage | 2018-11-09 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8739-001024 | 8739 | 2018-11-06 09:51 | Section 4 | Material | Not on List | Not on List | 0 | NULL | NULL | 0 | Miscellaneous | 2018-11-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-5246-00160 | 5246 | 2018-08-16 16:02 | Section 4 | Material | Not on List | Not on List | 700 | NULL | 0.05 | 35 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8698-001024 | 8698 | 2018-11-05 13:46 | Section 4 | Material | NULL | Building Sand Bulk Bag (938155) | 5 | Each | 32.74 | 163.7 | Builders Merchants (General) | 2018-11-08 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | Ducting | Not on List | 9 | U | NULL | 0 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | Ducting | Not on List | 10 | U | NULL | 0 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | Ducting | Not on List | 20 | U | NULL | 0 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-8602-001023 | 8602 | 2018-11-02 07:26 | Section 4 | Material | Not on List | Not on List | 15 | Each | 36.96 | 554.4 | Small Tools (Consumables) | 2018-11-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8749-001024 | 8749 | 2018-11-06 11:33 | Section 4 | Material | Not on List | Not on List | 75 | (25kg bags) | NULL | 0 | Not Sure | 2018-12-14 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN23 - Structure BN23 | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8623-001023 | 8623 | 2018-11-02 09:17 | Section 4 | Material | Not on List | Not on List | 12.851 | tonne | 538 | 6913.84 | Rebar and Mesh | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7666 | 7666 | 2018-10-11 09:48 | Section 4 | Material | Not on List | Not on List | 2198 | Each | 1.85 | 4066.3 | Professional Services | 2018-10-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Concrete Drainage | Not on List | 18 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | PPE, Small Tools and Consumables | Stake Marking Out Wooden 1200mm Nominal C.r.code Swcoc004463 (740904) | 500 | Each | 1.07 | 535 | Surveying Consumables | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 940.8 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 67.9 | 1018.5 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509.2 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | Not on List | 10 | Ea | 232.01 | 2320.1 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8610-001023 | 8610 | 2018-11-02 08:32 | Section 3 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 10 | Each | 59.17 | 591.7 | Concrete Drainage | 2018-11-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8489-001023 | 8489 | 2018-10-31 10:03 | Section 4 | Material | Not on List | Not on List | 5 | Each | 145 | 725 | Surveying Consumables | 2018-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8760-001024 | 8760 | 2018-11-06 14:20 | Section 3 | Material | PPE, Small Tools and Consumables | Jacket A14 Logod Regatta Seal Grey Octagon Ii Mens Softshell (16318) | 21 | Each | 27.5 | 578 | PPE | 2018-11-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Concrete Drainage | Not on List | 4 | NULL | 1259.25 | 5037 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8761-001024 | 8761 | 2018-11-06 14:34 | Section 4 | Material | Aggregate | A40 Pipe Bed | 100 | Tonnes | 20.95 | 2095 | Aggregate | 2018-11-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8763-001024 | 8763 | 2018-11-06 14:51 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2239.35 | 2239 | Not Sure | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8766-001024 | 8766 | 2018-11-06 15:04 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2584.57 | 2585 | Not Sure | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8749-001024 | 8749 | 2018-11-06 11:33 | Section 4 | Material | Not on List | Not on List | 75 | Each | 14.43 | 1082.25 | Miscellaneous | 2018-12-14 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8712-001024 | 8712 | 2018-11-05 16:20 | Section 4 | Material | Not on List | Not on List | 1 | Lot | 765 | 765 | Timber Products | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8755-001024 | 8755 | 2018-11-06 13:57 | Section 4 | Material | Not on List | Not on List | 40 | Each | 44.92 | 1796.8 | Miscellaneous | 2018-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8806-001024 | 8806 | 2018-11-07 08:05 | Section 3 | Material | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Plastic Drainage | 2018-11-12 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Concrete Drainage | Not on List | 12 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8806-001024 | 8806 | 2018-11-07 08:05 | Section 3 | Material | Aggregate | A10 Pipe Bed | 200 | Tonnes | 16.5 | 3300 | Plastic Drainage | 2018-11-12 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8760-001024 | 8760 | 2018-11-06 14:20 | Section 3 | Material | PPE, Small Tools and Consumables | Jacket A14 Logod Regatta Seal Grey Octagon Ii Mens Softshell (16318) | 21 | Each | 27.5 | 577.5 | PPE | 2018-11-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8763-001024 | 8763 | 2018-11-06 14:51 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2239.35 | 2239.35 | Not Sure | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8829-001024 | 8829 | 2018-11-07 14:10 | Section 4 | Material | Not on List | Not on List | 1 | No. | NULL | 0 | Concrete Drainage | 2018-11-07 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8806-001024 | 8806 | 2018-11-07 08:05 | Section 3 | Material | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Plastic Drainage | 2018-11-12 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8806-001024 | 8806 | 2018-11-07 08:05 | Section 3 | Material | Aggregate | A10 Pipe Bed | 200 | Tonnes | 16.5 | 3300 | Plastic Drainage | 2018-11-12 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8834-001024 | 8834 | 2018-11-07 14:22 | Section 3 | Material | Not on List | Not on List | 8 | ea | 41.74 | 334 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Concrete Drainage | Not on List | 15 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8662-001023 | 8662 | 2018-11-05 07:56 | Section 3 | Material | Not on List | Not on List | 1 | ea | 96.8 | 96.8 | Damage Charges | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8766-001024 | 8766 | 2018-11-06 15:04 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2584.57 | 2584.57 | Not Sure | 2018-11-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8837-001024 | 8837 | 2018-11-07 14:46 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 50 | Each | 48.86 | 2443 | Plastic Drainage | 2018-11-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22937-001025 | 22937 | 2019-08-29 10:37 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Full Pallet | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-22938-001025 | 22938 | 2019-08-29 12:16 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Full Pallet | NULL | 0 | Small Tools (Consumables) | 2019-09-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 2 | Each | 2.9 | 5.8 | Builders Merchants (General) | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22919-001025 | 22919 | 2019-08-29 09:39 | Section 5 | Material | Not on List | NULL | 4 | EA | 51.77 | 207.08 | Builders Merchants (General) | 2019-08-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22891-001025 | 22891 | 2019-08-28 15:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 374.44 | Each | 1 | 374.44 | Small Tools (Consumables) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22889-001025 | 22889 | 2019-08-28 15:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | Bag | 2.97 | 332.64 | Builders Merchants (General) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22888-001025 | 22888 | 2019-08-28 15:19 | Section 4 | Material | Not on List | Not on List | 1 | Each | 255.25 | 255.25 | Miscellaneous | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22921-001025 | 22921 | 2019-08-29 09:09 | Section 4 | Material | Not on List | NULL | 8 | EA | 1895 | 15160 | Not Sure | 2019-09-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22868-001025 | 22868 | 2019-08-28 11:12 | Section 4 | Material | Not on List | Not on List | 9170 | Each | 1 | 9170 | Gas Oil | 2019-09-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 15 | Each | 81.73 | 1225.95 | Concrete Drainage | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 45 | Each | 13.44 | 604.8 | Builders Merchants (General) | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 4000 | Each | 0.37 | 1480 | Builders Merchants (General) | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Tubs | NULL | 0 | Builders Merchants (General) | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | Concrete Drainage | Not on List | 60 | each | NULL | 0 | Concrete Drainage | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | Not on List | Not on List | 500 | metres | NULL | 0 | Builders Merchants (General) | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22876-001025 | 22876 | 2019-08-28 11:33 | Section 2 | Material | Concrete Drainage | Not on List | 20 | tubs | NULL | 0 | Concrete Drainage | 2019-09-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-22830-001025 | 22830 | 2019-08-27 17:09 | Section 4 | Material | NULL | NULL | 20 | EAch | 41.2 | 824 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 10 | Each | 116.62 | 1166.2 | Plastic Drainage | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22907-001025 | 22907 | 2019-08-29 07:26 | Section 4 | Material | Not on List | Not on List | 1 | Each | 620 | 620 | Electrical | 2019-08-30 | RVP 420 - A14 Eastbound - Opposite Crematorium | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22890-001025 | 22890 | 2019-08-28 15:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1225.16 | 1225.16 | Small Tools (Consumables) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22860-001025 | 22860 | 2019-08-28 08:40 | Section 5 | Material | Not on List | Not on List | 30 | number | 125.22 | 3756.6 | Concrete Accessories | 2019-08-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22954-001025 | 22954 | 2019-08-29 14:38 | Section 5 | Material | Combined Drainage | NULL | 1 | SM | 7355.55 | 7355.55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-30 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22960-001025 | 22960 | 2019-08-29 16:02 | Section 5 | Material | Not on List | NULL | 6 | EA | 16.5 | 99 | Not Sure | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 40 | Each | 13.86 | 554.4 | Plastic Drainage | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22798-001025 | 22798 | 2019-08-27 10:19 | Section 5 | Material | Not on List | NULL | 1075.8 | SM | 24.88 | 26765.9 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-03 | 1358005 - WB5/7 Works Access - 1356563 - A14 Westbound, On Left between Jcn 32 - 31 | SEC5 - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22838-001025 | 22838 | 2019-08-27 17:32 | Section 5 | Material | Not on List | Not on List | 260 | m2 | 17.66 | 4591.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-03 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22838-001025 | 22838 | 2019-08-27 17:32 | Section 5 | Material | Not on List | Not on List | 25 | EA | 29.44 | 736 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-03 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22946-001025 | 22946 | 2019-08-29 13:03 | Section 2 | Material | Bricks/Blocks | Not on List | 170 | Kerbs | NULL | 0 | Blocks and Bricks | 2019-09-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 22 | Each | 9.04 | 198.88 | Plastic Drainage | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23035-001025 | 23035 | 2019-09-02 08:54 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Tanks and Interceptors | 2019-09-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 3 Buyers
MREQ-22680-001025 | 22680 | 2019-08-22 15:58 | Core | Material | Not on List | Not on List | 45 | each | 63 | 2835 | Miscellaneous | 2019-08-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22958-001025 | 22958 | 2019-08-29 15:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 78 | Each | 1 | 78 | PPE | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6461-00706 | 6461 | 2018-09-13 08:54 | Section 4 | Material | Not on List | Not on List | 6 | Each | 120.62 | 723.72 | Plastic Drainage | 2018-09-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22949-001025 | 22949 | 2019-08-29 14:01 | Section 6 | Material | Not on List | Not on List | 1 | No. | 246407.52 | 246407.52 | Miscellaneous | 2019-09-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-22807-001025 | 22807 | 2019-08-27 11:58 | Core | Material | Not on List | Not on List | 1 | ea | 1737.5 | 1737.5 | Training | 2019-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22813-001025 | 22813 | 2019-08-27 13:38 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2019-09-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 107 - Fee based costs including insurance | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22333-001025 | 22333 | 2019-08-15 14:29 | Section 5 | Material | Not on List | NULL | 1 | SM | 1183.86 | 1183.86 | Miscellaneous | 2019-08-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-22959-001025 | 22959 | 2019-08-29 15:39 | Core | Material | PPE, Small Tools and Consumables | Not on List | 445.12 | Each | 1 | 445.12 | Small Tools (Consumables) | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23001-001025 | 23001 | 2019-08-30 14:34 | Section 2 | Material | Combined Drainage | Not on List | 60 | number | NULL | 0 | Ductile Drainage | 2019-09-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23001-001025 | 23001 | 2019-08-30 14:34 | Section 2 | Material | Combined Drainage | Not on List | 60 | number | NULL | 0 | Ductile Drainage | 2019-09-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6470-00712 | 6470 | 2018-09-13 11:02 | Section 4 | Material | Not on List | Not on List | 3.394 | Tonne | 538 | 1825.97 | Rebar and Mesh | 2018-09-27 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23001-001025 | 23001 | 2019-08-30 14:34 | Section 2 | Material | Combined Drainage | Not on List | 72 | number | NULL | 0 | Ductile Drainage | 2019-09-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23001-001025 | 23001 | 2019-08-30 14:34 | Section 2 | Material | Combined Drainage | Not on List | 1 | number | NULL | 0 | Ductile Drainage | 2019-09-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23003-001025 | 23003 | 2019-08-30 14:59 | Section 3 | Material | Aggregate | 6G | 200 | Tonnes | 32.9 | 6580 | Aggregate | 2019-08-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22982-001025 | 22982 | 2019-08-30 09:36 | Section 6 | Material | Aggregate | Class 1A | 2500 | Tonnes | 4 | 10000 | Aggregate | 2019-09-02 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23055-001025 | 23055 | 2019-09-02 11:15 | Section 5 | Material | Ducting | NULL | 3 | EA | 156.6 | 469.8 | Plastic Drainage | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23043-001025 | 23043 | 2019-09-02 09:57 | Section 5 | Material | Ducting | NULL | 16 | EA | 10.42 | 166.72 | Builders Merchants (General) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23043-001025 | 23043 | 2019-09-02 09:57 | Section 5 | Material | Ducting | NULL | 2 | EA | 23.65 | 47.3 | Builders Merchants (General) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23043-001025 | 23043 | 2019-09-02 09:57 | Section 5 | Material | Ducting | NULL | 1 | EA | 25 | 25 | Builders Merchants (General) | 2019-09-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5138-0066 | 5138 | 2018-08-15 11:27 | Section 3 | Material | Not on List | NULL | 10 | No | 67.24 | 672.4 | Builders Merchants (General) | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6470-00712 | 6470 | 2018-09-13 11:02 | Section 4 | Material | Not on List | Not on List | 3.394 | Tonne | 538 | 1825.97 | Rebar and Mesh | 2018-09-27 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 36 | Each | 34.82 | 1253.52 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 152 | Each | 2.97 | 451.44 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 21 | Each | 3.65 | 76.65 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 42 | Each | 2 | 84 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 4 | Each | 116.62 | 466.48 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23033-001025 | 23033 | 2019-09-02 08:32 | Section 2 | Material | Twinwall | Polypipe 450mm Ridgidrain Seal (346396) | 4 | Each | 10.04 | 40.16 | Plastic Drainage | 2019-09-05 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23066-001025 | 23066 | 2019-09-02 13:38 | Section 3 | Material | PPE, Small Tools and Consumables | Pendant Barrier Marker 32 X 26m Long Approx (200040) | 25 | Each | 10.7 | 267.5 | Miscellaneous | 2019-09-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6470-00712 | 6470 | 2018-09-13 11:02 | Section 4 | Material | Not on List | Not on List | 3.394 | Tonne | 538 | 1825.97 | Rebar and Mesh | 2018-09-27 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23049-001025 | 23049 | 2019-09-02 10:13 | Section 3 | Material | Not on List | Not on List | 1 | No | NULL | 0 | Professional Services | 2019-09-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-22665-001025 | 22665 | 2019-08-22 11:01 | Section 4 | Material | Not on List | Not on List | 12 | Rolls | 49.5 | 594 | Miscellaneous | 2019-08-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22665-001025 | 22665 | 2019-08-22 11:01 | Section 4 | Material | NULL | Not on List | 1 | Each | 650 | 650 | Miscellaneous | 2019-08-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23069-001025 | 23069 | 2019-09-02 14:13 | Core | Material | Not on List | Not on List | 20 | Packs of 100 | 10.5 | 210 | Surveying Consumables | 2019-09-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23069-001025 | 23069 | 2019-09-02 14:13 | Core | Material | Not on List | Not on List | 10 | Packs of 100 | 10.5 | 105 | Surveying Consumables | 2019-09-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21988-001025 | 21988 | 2019-08-08 10:56 | Core | Material | Not on List | Not on List | 1 | Each | 515 | 515 | Miscellaneous | 2019-08-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23124-001025 | 23124 | 2019-09-03 10:24 | Section 4 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 1 | full load | 0 | 0 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-6498-00725 | 6498 | 2018-09-13 16:38 | Section 4 | Material | Not on List | Not on List | 60 | Each | 1.91 | 114.6 | Concrete Accessories | 2018-09-18 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23124-001025 | 23124 | 2019-09-03 10:24 | Section 4 | Material | Not on List | Not on List | 1 | no. | NULL | 0 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23129-001025 | 23129 | 2019-09-03 11:51 | Core | Material | Not on List | Not on List | 6 | boxes | 16.89 | 101 | Miscellaneous | 2019-09-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22217-001025 | 22217 | 2019-08-13 12:01 | Section 4 | Material | Not on List | Not on List | 12 | Each | 848.6 | 10183.2 | Concrete Accessories | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22217-001025 | 22217 | 2019-08-13 12:01 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1016.89 | 1016.89 | Concrete Accessories | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22217-001025 | 22217 | 2019-08-13 12:01 | Section 4 | Material | Not on List | Not on List | 1 | Each | 204.64 | 204.64 | Concrete Accessories | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22217-001025 | 22217 | 2019-08-13 12:01 | Section 4 | Material | Not on List | Not on List | 1 | Each | 79.02 | 79.02 | Concrete Accessories | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22217-001025 | 22217 | 2019-08-13 12:01 | Section 4 | Material | NULL | Not on List | 1 | Each | 50 | 50 | Concrete Accessories | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22508-001025 | 22508 | 2019-08-20 07:44 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20982-001025 | 20982 | 2019-07-18 09:59 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6498-00725 | 6498 | 2018-09-13 16:38 | Section 4 | Material | Not on List | Not on List | 60 | Each | 0.61 | 36.6 | Concrete Accessories | 2018-09-18 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22346-001025 | 22346 | 2019-08-15 15:31 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22976-001025 | 22976 | 2019-08-30 07:45 | Section 4 | Material | Not on List | Not on List | 5 | Each | 13.95 | 69.75 | Builders Merchants (General) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22976-001025 | 22976 | 2019-08-30 07:45 | Section 4 | Material | Not on List | Not on List | 4 | Each | 13.95 | 55.8 | Builders Merchants (General) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22976-001025 | 22976 | 2019-08-30 07:45 | Section 4 | Material | Not on List | Not on List | 4 | Each | 13.95 | 55.8 | Builders Merchants (General) | 2019-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23126-001025 | 23126 | 2019-09-03 10:27 | Section 5 | Material | Not on List | NULL | 12 | PK (25) | 27.5 | 330 | Miscellaneous | 2019-09-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23118-001025 | 23118 | 2019-09-03 09:29 | Section 5 | Material | Saint Gobain Castings | 600x600x150 V Shaped Aquamax (376797) | 12 | Each | 114 | 1368 | Concrete Drainage | 2019-09-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23153-001025 | 23153 | 2019-09-03 16:33 | Section 4 | Material | Not on List | Not on List | 250 | each | NULL | 0 | Miscellaneous | 2019-09-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23153-001025 | 23153 | 2019-09-03 16:33 | Section 4 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-09-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-6498-00725 | 6498 | 2018-09-13 16:38 | Section 4 | Material | Not on List | Not on List | 36 | Each | 9.78 | 352.08 | Concrete Accessories | 2018-09-18 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23103-001025 | 23103 | 2019-09-03 06:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Small Tools (Consumables) | 2019-09-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22646-001025 | 22646 | 2019-08-22 07:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 18087.27 | 18087.27 | Fuel | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21299-001025 | 21299 | 2019-07-24 17:53 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6498-00725 | 6498 | 2018-09-13 16:38 | Section 4 | Material | Not on List | Not on List | 120 | Each | 1.75 | 210 | Timber Products | 2018-09-18 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23191-001025 | 23191 | 2019-09-04 12:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23192-001025 | 23192 | 2019-09-04 12:12 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23198-001025 | 23198 | 2019-09-04 12:41 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Surveying Consumables | 2019-09-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23200-001025 | 23200 | 2019-09-04 12:42 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23023-001025 | 23023 | 2019-09-02 06:51 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 84 | Each | 3.03 | 254.52 | Small Tools (Consumables) | 2019-09-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23023-001025 | 23023 | 2019-09-02 06:51 | Section 4 | Material | PPE, Small Tools and Consumables | NULL | 84 | Each | 3.03 | 254.52 | Small Tools (Consumables) | 2019-09-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23167-001025 | 23167 | 2019-09-04 07:26 | Section 4 | Material | Not on List | Not on List | 30000 | Ltrs | 0.6 | 18000 | Fuel | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6553-00744 | 6553 | 2018-09-14 14:11 | Section 4 | Material | Not on List | Not on List | 75 | Each | 2.18 | 163.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23181-001025 | 23181 | 2019-09-04 09:34 | Section 4 | Material | Not on List | Not on List | 1040 | Hours | 21.61 | 22474.4 | Professional Services | 2019-09-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22533-001025 | 22533 | 2019-08-20 15:00 | Section 4 | Material | Not on List | Not on List | 1 | Each | 372.8 | 372.8 | Fuel | 2019-08-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22951-001025 | 22951 | 2019-08-29 14:18 | Section 4 | Material | Not on List | Not on List | 130 | Each | 8.95 | 1163.5 | Concrete Accessories | 2019-09-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22913-001025 | 22913 | 2019-08-29 07:50 | Section 3 | Material | Not on List | Not on List | 3 | No | 352.89 | 1058.67 | Builders Merchants (General) | 2019-08-29 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6553-00744 | 6553 | 2018-09-14 14:11 | Section 4 | Material | Not on List | Not on List | 6 | Each | 5.84 | 35.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23235-001025 | 23235 | 2019-09-05 06:55 | Core | Material | PPE, Small Tools and Consumables | Not on List | 32 | NULL | 28.8 | 922 | PPE | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Buyers
MREQ-21243-001025 | 21243 | 2019-07-24 09:44 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22585-001025 | 22585 | 2019-08-21 08:43 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23238-001025 | 23238 | 2019-09-05 07:53 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23242-001025 | 23242 | 2019-09-05 08:40 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23183-001025 | 23183 | 2019-09-04 09:58 | Section 6 | Material | Not on List | Not on List | 5 | NULL | 80 | 400 | Waste (Recycling) | 2019-09-04 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6575-00749 | 6575 | 2018-09-17 09:24 | Section 4 | Material | Not on List | Not on List | 240 | KG | 2.87 | 688.8 | Concrete Accessories | 2018-09-19 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23244-001025 | 23244 | 2019-09-05 09:09 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23186-001025 | 23186 | 2019-09-04 11:23 | Core | Material | NULL | NULL | 1 | Each | 1119.2 | 1119.2 | NULL | NULL | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23254-001025 | 23254 | 2019-09-05 08:38 | Section 6 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Miscellaneous | 2019-09-09 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23254-001025 | 23254 | 2019-09-05 08:38 | Section 6 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Miscellaneous | 2019-09-09 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23098-001025 | 23098 | 2019-09-02 17:24 | Section 4 | Material | NULL | NULL | 500 | meters | NULL | 0 | Miscellaneous | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23190-001025 | 23190 | 2019-09-04 11:48 | Core | Material | NULL | NULL | 2 | Each | 69.83 | 139.66 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6594-00749 | 6594 | 2018-09-17 13:20 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.18 | 143.6 | Builders Merchants (General) | 2018-09-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23241-001025 | 23241 | 2019-09-05 08:26 | Section 5 | Material | Not on List | Not on List | 30 | EA | 10.06 | 301.8 | Builders Merchants (General) | 2019-09-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23149-001025 | 23149 | 2019-09-03 16:20 | Section 4 | Material | NULL | NULL | 5 | Each | 33.55 | 167.75 | Builders Merchants (General) | 2019-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22621-001025 | 22621 | 2019-08-21 15:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 73.07 | 146.14 | Miscellaneous | 2019-08-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23201-001025 | 23201 | 2019-09-04 13:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 500.29 | 500.29 | Miscellaneous | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23236-001025 | 23236 | 2019-09-05 07:42 | Section 4 | Material | Not on List | Not on List | 1 | Each | 570.39 | 570.39 | Miscellaneous | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23057-001025 | 23057 | 2019-09-02 11:57 | Section 3 | Material | Not on List | Not on List | 1 | EA | 1910 | 1910 | Miscellaneous | 2019-09-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5138-0066 | 5138 | 2018-08-15 11:27 | Section 3 | Material | Not on List | NULL | 37 | no | 13.9 | 514.3 | Builders Merchants (General) | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15165-001025 | 15165 | 2019-04-02 16:56 | Section 2 | Material | NULL | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 9 | Each | 166.43 | 1497.87 | Plastic Drainage | 2019-04-04 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15102-001025 | 15102 | 2019-04-02 09:39 | Section 2 | Material | Not on List | Not on List | 1 | 20 x 700 rolls | 756.25 | 756 | Office Supplies | 2019-04-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 603 - Processing | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15252-001025 | 15252 | 2019-04-04 06:45 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-04-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1801 - Structural Steelwork | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-15209-001025 | 15209 | 2019-04-03 12:44 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15267-001025 | 15267 | 2019-04-04 08:52 | Core | Material | Not on List | Not on List | 1 | each | 10665 | 10665 | Professional Services | 2019-04-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 153 - Temporary Works | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-15275-001025 | 15275 | 2019-04-04 10:03 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-05 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S1 Buyers
MREQ-15190-001025 | 15190 | 2019-04-03 08:46 | Section 4 | Material | NULL | NULL | 32 | NULL | 6.9 | 220.8 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14873-001025 | 14873 | 2019-03-28 11:41 | Section 4 | Material | Not on List | Not on List | 250 | NULL | 4.42 | 1105 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15285-001025 | 15285 | 2019-04-04 11:11 | Section 4 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BES4 - Existing Structures | 1601 - Piling and attendances | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15207-001025 | 15207 | 2019-04-03 12:25 | Core | Material | Not on List | Not on List | 126 | Each | 16.68 | 2101.68 | Miscellaneous | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15138-001025 | 15138 | 2019-04-02 14:34 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1727.5 | 1727.5 | PPE | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5871-00558 | 5871 | 2018-08-31 14:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 72 | Each | 6.29 | 452.88 | Miscellaneous | 2018-09-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15289-001025 | 15289 | 2019-04-04 12:05 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15142-001025 | 15142 | 2019-04-02 14:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Small Tools (Consumables) | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15142-001025 | 15142 | 2019-04-02 14:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4000 | Each | 0.37 | 1480 | Miscellaneous | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15146-001025 | 15146 | 2019-04-02 15:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 5.8 | 46.4 | Small Tools (Consumables) | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15146-001025 | 15146 | 2019-04-02 15:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 5.82 | 46.56 | Small Tools (Consumables) | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15146-001025 | 15146 | 2019-04-02 15:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 32 | Each | 1.91 | 61.12 | Small Tools (Consumables) | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15299-001025 | 15299 | 2019-04-04 14:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 301.88 | 302 | PPE | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15148-001025 | 15148 | 2019-04-02 15:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 203.22 | 203.22 | PPE | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5852-00545 | 5852 | 2018-08-31 10:57 | Section 4 | Material | Not on List | Not on List | 4 | 1t Bag | 32.74 | 130.96 | Concrete Drainage | 2018-09-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14765-001025 | 14765 | 2019-03-27 12:56 | Section 5 | Material | Not on List | Not on List | 36 | No | 43.65 | 1571.4 | Concrete Drainage | 2019-04-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14765-001025 | 14765 | 2019-03-27 12:56 | Section 5 | Material | Not on List | Not on List | 8 | No | 53 | 424 | Concrete Drainage | 2019-04-02 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15269-001025 | 15269 | 2019-04-04 09:20 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15256-001025 | 15256 | 2019-04-04 07:56 | Section 4 | Material | Not on List | Not on List | 250 | Each | 0.98 | 245 | Miscellaneous | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15273-001025 | 15273 | 2019-04-04 09:47 | Section 4 | Material | Not on List | Not on List | 500000 | Each | 1 | 500000 | Gas Oil | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15334-001025 | 15334 | 2019-04-05 06:49 | Section 2 | Material | Not on List | Not on List | 20 | rolls | NULL | 0 | Concrete Accessories | 2019-04-07 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14848-001025 | 14848 | 2019-03-28 10:00 | Section 4 | Material | Signage | Not on List | 200 | Each | 6.9 | 1380 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14848-001025 | 14848 | 2019-03-28 10:00 | Section 4 | Material | Signage | Not on List | 25 | Rolls | NULL | 0 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14848-001025 | 14848 | 2019-03-28 10:00 | Section 4 | Material | Signage | Not on List | 25 | Each | 2.15 | 53.75 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14848-001025 | 14848 | 2019-03-28 10:00 | Section 4 | Material | Signage | Not on List | 40 | Pack 100 | 9 | 360 | Surveying Consumables | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15296-001025 | 15296 | 2019-04-04 13:42 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2061.98 | 2061.98 | Miscellaneous | 2019-04-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Insulation White Pvc 33m X 19mm Contractor (230006) | 15 | Each | 0.86 | 13 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Insulation Red Pvc 33m X 19mm Contractor (230007) | 15 | Each | 0.86 | 13 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Insulation Blue Pvc 33m X 19mm Contractor (230008) | 15 | Each | 0.86 | 13 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Insulation Yellow Pvc 33m X 19mm Contractor (230009) | 15 | Each | 0.86 | 13 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Insulation Black Pvc 33m X 19mm Contractor (230015) | 15 | Each | 0.86 | 13 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Rake Asphalt/Tarmac Flat Tooth Metal Handle Spartan Pro (762583) | 10 | Each | 17.28 | 173 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Sign 5mph Rigid Plastic Ref 1 7501 (249727) | 40 | Each | 17 | 680 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Hammer Club C/W Fibreglass Handle Spartan Pro 1.1kg(2.5lb) (724107) | 20 | Each | 8.98 | 180 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | DE-ICER CLEANLINE WINDSCREEN 400ML AEROSOL (710091) | 20 | Each | 2.43 | 49 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 55 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Helmet Attachment-jsp Navy Blue Helmet Warmer (271301) | 15 | Each | 5.43 | 81 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 5mtr/1 (765565) | 10 | Each | 2.7 | 27 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 7.5mtr/2 (765566) | 10 | Each | 5.77 | 58 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Measuring Pocket Spartan Pro 10mtr/3 (765567) | 10 | Each | 12.4 | 124 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Paint Roller And Tray Set 9" Rskit1 (704256) | 10 | Each | 3.42 | 34 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Filler Foam Expanding Hansil Contractor 750ml (546678) | 20 | Each | 3.17 | 63 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15344-001025 | 15344 | 2019-04-05 08:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15250-001025 | 15250 | 2019-04-04 06:33 | Section 4 | Material | Not on List | Not on List | 1 | Each | 310.06 | 310.06 | Miscellaneous | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15250-001025 | 15250 | 2019-04-04 06:33 | Section 4 | Material | Not on List | Not on List | 1 | Each | 561.72 | 561.72 | Miscellaneous | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15161-001025 | 15161 | 2019-04-02 16:30 | Section 4 | Material | Not on List | Not on List | 2 | Each | 72 | 144 | Surveying Consumables | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15161-001025 | 15161 | 2019-04-02 16:30 | Section 4 | Material | Not on List | Not on List | 2 | Each | 128 | 256 | Surveying Consumables | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15357-001025 | 15357 | 2019-04-05 10:16 | Section 2 | Material | Twinwall | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2019-04-08 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15357-001025 | 15357 | 2019-04-05 10:16 | Section 2 | Material | Concrete Drainage | Not on List | 8 | NULL | NULL | 0 | Plastic Drainage | 2019-04-08 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15094-001025 | 15094 | 2019-04-02 08:54 | Section 4 | Material | Not on List | Not on List | 3 | Each | 221.85 | 665.55 | Blocks and Bricks | 2019-04-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15094-001025 | 15094 | 2019-04-02 08:54 | Section 4 | Material | Not on List | Not on List | 9 | Each | 221.85 | 1996.65 | Blocks and Bricks | 2019-04-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5985-00586 | 5985 | 2018-09-04 07:16 | Section 3 | Material | Not on List | Not on List | 1 | no | 1920 | 1920 | Aggregate | 2018-09-05 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15094-001025 | 15094 | 2019-04-02 08:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 176.09 | 176.09 | Blocks and Bricks | 2019-04-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15094-001025 | 15094 | 2019-04-02 08:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 274.1 | 274.1 | Blocks and Bricks | 2019-04-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15200-001025 | 15200 | 2019-04-03 10:30 | Section 3 | Material | Not on List | Not on List | 1 | ea | 2542.17 | 2542.17 | Miscellaneous | 2019-04-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15378-001025 | 15378 | 2019-04-05 11:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 186 | 186 | PPE | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15378-001025 | 15378 | 2019-04-05 11:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 302 | 302 | PPE | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15120-001025 | 15120 | 2019-04-02 12:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 497.86 | 497.86 | Miscellaneous | 2019-04-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15230-001025 | 15230 | 2019-04-03 14:37 | Core | Material | Not on List | Not on List | 250 | number | 0.95 | 237.5 | Surveying Consumables | 2019-04-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5989-00588 | 5989 | 2018-09-04 08:52 | Section 3 | Material | Misc | Not on List | 4 | rolls | 11.01 | 44.04 | Builders Merchants (General) | 2018-09-07 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15230-001025 | 15230 | 2019-04-03 14:37 | Core | Material | Not on List | Not on List | 250 | number | 0.56 | 140 | Surveying Consumables | 2019-04-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15435-001025 | 15435 | 2019-04-08 08:43 | Section 2 | Material | Not on List | Not on List | 2 | Number | NULL | 0 | Surveying Consumables | 2019-04-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-15395-001025 | 15395 | 2019-04-05 14:34 | Section 3 | Material | Not on List | Not on List | 13 | No. | 5.34 | 69.42 | Plastic Drainage | 2019-04-08 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15338-001025 | 15338 | 2019-04-05 07:46 | Core | Material | Not on List | Not on List | 1 | Pack 1000 & Deliver | 198 | 198 | Office Supplies | 2019-04-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5988-00587 | 5988 | 2018-09-04 09:02 | Section 3 | Material | Not on List | Not on List | 4 | Cases | 68.74 | 274.96 | Miscellaneous | 2018-09-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15309-001025 | 15309 | 2019-04-04 15:52 | Core | Material | Not on List | Not on List | 11 | NULL | 5.25 | 57.75 | Office Supplies | 2019-04-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15309-001025 | 15309 | 2019-04-04 15:52 | Core | Material | Not on List | Not on List | 2 | NULL | 5.95 | 11.9 | Office Supplies | 2019-04-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15309-001025 | 15309 | 2019-04-04 15:52 | Core | Material | Not on List | Not on List | 1 | NULL | 9.95 | 9.95 | Office Supplies | 2019-04-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15315-001025 | 15315 | 2019-04-04 16:47 | Core | Material | Not on List | Not on List | 1 | Each | 850 | 850 | Training | 2019-05-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15452-001025 | 15452 | 2019-04-08 12:56 | Section 4 | Material | Not on List | Not on List | 100 | Each | 7.5 | 750 | Surveying Consumables | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15307-001025 | 15307 | 2019-04-04 15:45 | Section 2 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 960 | Metres | 1.5 | 1440 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15454-001025 | 15454 | 2019-04-08 13:08 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-04-09 | RVP 403 - 1339621 - Borrow Pit 5 A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15455-001025 | 15455 | 2019-04-08 13:14 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-04-09 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15312-001025 | 15312 | 2019-04-04 16:21 | Section 4 | Material | Not on List | Not on List | 5 | Each | 9.84 | 49.2 | Builders Merchants (General) | 2019-04-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15312-001025 | 15312 | 2019-04-04 16:21 | Section 4 | Material | Not on List | Not on List | 20 | sheet | 24.28 | 485.6 | Builders Merchants (General) | 2019-04-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15465-001025 | 15465 | 2019-04-08 14:02 | Core | Material | Not on List | Not on List | 1 | each | 200 | 200 | Training | 2019-05-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15478-001025 | 15478 | 2019-04-08 16:22 | Core | Material | Not on List | Not on List | 1 | NULL | 2322 | 2322 | Laboratory Equipment / Certification | 2019-04-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 50 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 1500 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 1500 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 1500 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15502-001025 | 15502 | 2019-04-09 07:42 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Concrete Accessories | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15460-001025 | 15460 | 2019-04-08 13:46 | Section 2 | Material | Not on List | Not on List | 11.292 | tonnes | NULL | 0 | NULL | 2019-04-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15514-001025 | 15514 | 2019-04-09 09:56 | Core | Material | Not on List | Not on List | 1 | number | 12.99 | 13 | Miscellaneous | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15514-001025 | 15514 | 2019-04-09 09:56 | Core | Material | Not on List | Not on List | 1 | number | 41.19 | 41 | Miscellaneous | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15523-001025 | 15523 | 2019-04-09 10:48 | Section 2 | Material | Aggregate | Not on List | 1 | each | 56 | 56 | Aggregate | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15453-001025 | 15453 | 2019-04-08 11:00 | Core | Material | Not on List | Not on List | 1 | ea | 5972.37 | 5972.37 | Training | 2019-04-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15461-001025 | 15461 | 2019-04-08 13:27 | Core | Material | Not on List | Not on List | 1 | ea | 3250 | 3250 | Training | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15531-001025 | 15531 | 2019-04-09 12:39 | Section 2 | Material | Not on List | Not on List | 100 | pegs | NULL | 0 | Surveying Consumables | 2019-04-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15531-001025 | 15531 | 2019-04-09 12:39 | Section 2 | Material | Not on List | Not on List | 100 | boards | NULL | 0 | Surveying Consumables | 2019-04-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15506-001025 | 15506 | 2019-04-09 08:33 | Section 2 | Material | NULL | Not on List | 6 | BOXES | NULL | 0 | Blocks and Bricks | 2019-04-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15506-001025 | 15506 | 2019-04-09 08:33 | Section 2 | Material | NULL | Not on List | 4 | BOXES | NULL | 0 | Blocks and Bricks | 2019-04-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15178-001025 | 15178 | 2019-04-02 17:27 | Section 5 | Material | Not on List | Not on List | 100 | EACH | 19.8 | 1980 | Miscellaneous | 2019-04-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15222-001025 | 15222 | 2019-04-03 15:41 | Core | Material | Not on List | Not on List | 1 | NULL | 135.66 | 136 | Office Supplies | 2019-04-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | NULL | 114 - Office Furniture | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6007-00591 | 6007 | 2018-09-04 14:23 | Section 3 | Material | Not on List | Not on List | 4 | no | 439 | 1756 | Not Sure | 2018-09-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15521-001025 | 15521 | 2019-04-09 10:40 | Section 2 | Material | Aggregate | Not on List | 1 | each | 1500 | 1500 | Aggregate | 2019-04-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15457-001025 | 15457 | 2019-04-08 13:19 | Section 4 | Material | Waste Management | Plastic - Roll On Roll Off 40 cubic yard | 1 | Each | 360 | 360 | Waste (Recycling) | 2019-04-09 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15451-001025 | 15451 | 2019-04-08 12:52 | Section 2 | Material | NULL | Not on List | 26 | m | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14545-001025 | 14545 | 2019-03-22 14:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 26.25 | 525 | Builders Merchants (General) | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 201 - Site Clearance | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-15467-001025 | 15467 | 2019-04-08 14:58 | Section 3 | Material | Not on List | Not on List | 45 | rolls | NULL | 0 | Builders Merchants (General) | 2019-04-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6007-00591 | 6007 | 2018-09-04 14:23 | Section 3 | Material | Not on List | Not on List | 2 | no | 95 | 190 | Not Sure | 2018-09-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15430-001025 | 15430 | 2019-04-08 08:11 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 6 | Each | 12.39 | 74.34 | Builders Merchants (General) | 2019-04-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15430-001025 | 15430 | 2019-04-08 08:11 | Section 3 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 7 | Each | 12.39 | 86.73 | Builders Merchants (General) | 2019-04-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15533-001025 | 15533 | 2019-04-09 13:00 | Section 4 | Material | Waste Management | Plastic - Roll On Roll Off 40 cubic yard | 1 | Each | 360 | 360 | Waste (Recycling) | 2019-04-10 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6007-00591 | 6007 | 2018-09-04 14:23 | Section 3 | Material | Not on List | Not on List | 1 | no | 95 | 95 | Not Sure | 2018-09-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15525-001025 | 15525 | 2019-04-09 11:41 | Section 4 | Material | Not on List | Not on List | 30 | Sheets | 13.5 | 405 | Builders Merchants (General) | 2019-04-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15599-001025 | 15599 | 2019-04-10 11:21 | Section 2 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 40 | Each | 81.73 | 3269 | Builders Merchants (General) | 2019-04-15 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15599-001025 | 15599 | 2019-04-10 11:21 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142 | Builders Merchants (General) | 2019-04-15 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15599-001025 | 15599 | 2019-04-10 11:21 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 30 | Each | 35.52 | 1066 | Concrete Drainage | 2019-04-15 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15599-001025 | 15599 | 2019-04-10 11:21 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 5 | Each | 36.62 | 183 | Concrete Drainage | 2019-04-15 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15162-001025 | 15162 | 2019-04-02 16:30 | Section 2 | Material | Saint Gobain Castings | Not on List | 2 | No. | NULL | 0 | Miscellaneous | 2019-04-09 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | NULL | Not on List | 80 | No | 11.05 | 884 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | NULL | Not on List | 1 | No | 25.5 | 25.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5601-00400 | 5601 | 2018-08-23 20:40 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13046-001025 | 13046 | 2019-02-25 15:12 | Section 3 | Material | NULL | Not on List | 1 | No | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13165-001025 | 13165 | 2019-02-27 10:37 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Electrical | 2019-03-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13165-001025 | 13165 | 2019-02-27 10:37 | Section 2 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Electrical | 2019-03-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13167-001025 | 13167 | 2019-02-27 11:09 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-04 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-13167-001025 | 13167 | 2019-02-27 11:09 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-04 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-13186-001025 | 13186 | 2019-02-27 14:57 | Section 2 | Material | Waste Management | Clinical Waste - 4 Litre Sharps Disposal Unit (4 Collections Per Annum) | 11 | Each | 500 | 5500 | Waste (General) | 2019-02-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13096-001025 | 13096 | 2019-02-26 10:06 | Section 4 | Material | Not on List | Not on List | 1 | unit | 2589.47 | 2589.47 | Miscellaneous | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5601-00400 | 5601 | 2018-08-23 20:40 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13196-001025 | 13196 | 2019-02-27 17:21 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 80 | Each | 3.56 | 285 | Builders Merchants (General) | 2019-03-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13196-001025 | 13196 | 2019-02-27 17:21 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 30 | Each | 10.5 | 315 | Plastic Drainage | 2019-03-04 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5601-00400 | 5601 | 2018-08-23 20:40 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13220-001025 | 13220 | 2019-02-28 09:16 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12720-001025 | 12720 | 2019-02-19 15:39 | Section 4 | Material | Not on List | Not on List | 200 | Each | 2.18 | 436 | Miscellaneous | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13082-001025 | 13082 | 2019-02-26 08:19 | Section 4 | Material | Not on List | Not on List | 400 | 25m Pack | 12.8 | 5120 | Miscellaneous | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12495-001025 | 12495 | 2019-02-14 15:23 | Section 4 | Material | Signage | Not on List | 12 | EA | 9.58 | 114.96 | Miscellaneous | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13238-001025 | 13238 | 2019-02-28 11:25 | Core | Material | Not on List | Not on List | 1 | ea | 104 | 104 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5601-00400 | 5601 | 2018-08-23 20:40 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Builders Merchants (General) | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 5 | No. | 120.62 | 603.1 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 45 | No. | 34.82 | 1566.9 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 57 | No. | 6.54 | 372.78 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 4 | No. | 17.45 | 69.8 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 16 | No. | 9.04 | 144.64 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13200-001025 | 13200 | 2019-02-27 16:42 | Section 3 | Material | Not on List | Not on List | 114 | No. | 2.75 | 313.5 | Plastic Drainage | 2019-03-04 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 2 | NULL | 145 | 290 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13110-001025 | 13110 | 2019-02-26 13:05 | Section 4 | Material | Not on List | Not on List | 10 | Each | 258.35 | 2583.5 | Miscellaneous | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12790-001025 | 12790 | 2019-02-20 16:16 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-13256-001025 | 13256 | 2019-02-28 13:06 | Section 6 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Fixings and Fasteners | 2019-02-04 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 105 - Site Security | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 25 | NULL | 2.92 | 73 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13163-001025 | 13163 | 2019-02-27 09:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 481.18 | each | 1 | 481.18 | Small Tools (Consumables) | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13183-001025 | 13183 | 2019-02-27 14:40 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2000 | Each | 0.37 | 740 | Miscellaneous | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13101-001025 | 13101 | 2019-02-26 11:10 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 0 | 0 | PPE | 2019-03-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13250-001025 | 13250 | 2019-02-28 12:37 | Section 3 | Material | Not on List | Not on List | 60 | Ea | 2.5 | 150 | Surveying Consumables | 2019-03-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5083-0038 | 5083 | 2018-08-14 15:19 | Section 4 | Material | Not on List | NULL | 1 | tonne | 357.77 | 357.77 | Rebar and Mesh | 2018-08-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | CL4B - Structures (Culverts) 4B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 25 | NULL | 1.44 | 36 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13250-001025 | 13250 | 2019-02-28 12:37 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 88.88 | 88.88 | Small Tools (Consumables) | 2019-03-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12615-001025 | 12615 | 2019-02-18 08:58 | Core | Material | Not on List | Not on List | 6 | ea | 214.58 | 3645 | Office Supplies | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12615-001025 | 12615 | 2019-02-18 08:58 | Core | Material | Not on List | Not on List | 6 | ea | 89.17 | 3645 | Office Supplies | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13169-001025 | 13169 | 2019-02-27 11:22 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | each | 33.03 | 495.45 | Plastic Drainage | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 25 | NULL | 27.32 | 683 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13209-001025 | 13209 | 2019-02-28 07:24 | Section 4 | Material | Not on List | Not on List | 200 | Each | 2.18 | 436 | Miscellaneous | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13290-001025 | 13290 | 2019-02-28 16:45 | Core | Material | Not on List | Not on List | 1 | NULL | 345.01 | 345 | Miscellaneous | 2019-03-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-12877-001025 | 12877 | 2019-02-21 16:39 | Core | Material | Not on List | Not on List | 1 | Number | 394.8 | 394.8 | Office Supplies | 2019-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13272-001025 | 13272 | 2019-02-28 14:48 | Section 3 | Material | Aggregate | Not on List | 11500 | Ton | 4 | 46000 | Aggregate | 2019-03-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13260-001025 | 13260 | 2019-02-28 13:25 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 550.78 | 550.78 | PPE | 2019-03-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13260-001025 | 13260 | 2019-02-28 13:25 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 333.24 | 333.24 | Miscellaneous | 2019-03-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 191 | No. | 42.14 | 8048.74 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 17 | No. | 33.41 | 567.97 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 27 | No. | 30.78 | 831.06 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 25 | NULL | 5.95 | 148.75 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 9 | No. | 23.52 | 211.68 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 10 | No. | 56.84 | 568.4 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13287-001025 | 13287 | 2019-02-28 16:20 | Section 3 | Material | Not on List | Not on List | 18 | No. | 58.8 | 1058.4 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13203-001025 | 13203 | 2019-02-27 18:04 | Section 4 | Material | Aggregate | Not on List | 50 | Load | 380 | 19000 | Aggregate | 2019-03-04 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13203-001025 | 13203 | 2019-02-27 18:04 | Section 4 | Material | Aggregate | Not on List | 25 | Load | 380 | 9500 | Aggregate | 2019-03-05 | RVP 403 - 1339621 - Borrow Pit 5 A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13270-001025 | 13270 | 2019-02-28 14:34 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1863.37 | each | 1 | 1863.37 | PPE | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5605-00404 | 5605 | 2018-08-24 07:44 | Section 4 | Material | Plastic Drainage | Not on List | 50 | NULL | 22.52 | 1126 | Plastic Drainage | 2018-09-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13239-001025 | 13239 | 2019-02-28 11:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 224.88 | 224.88 | Concrete Drainage | 2019-03-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13239-001025 | 13239 | 2019-02-28 11:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 176.4 | 176.4 | Concrete Drainage | 2019-03-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13222-001025 | 13222 | 2019-02-28 09:36 | Section 4 | Material | Not on List | Not on List | 1 | ea | 1585.07 | 1585.07 | Miscellaneous | 2019-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3010 - Ground Preparation, Cultivation and Mulching | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12841-001025 | 12841 | 2019-02-21 09:56 | Core | Material | Not on List | Not on List | 2 | number | 38 | 76 | Miscellaneous | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13124-001025 | 13124 | 2019-02-26 15:34 | Section 3 | Material | Not on List | Not on List | 1 | No | NULL | 0 | NULL | 2019-03-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN08 - Corpus Christi Accommodation Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13003-001025 | 13003 | 2019-02-25 08:50 | Core | Material | Not on List | Not on List | 2 | Number | 22 | 44 | Surveying Consumables | 2019-03-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 900 | No | 35.59 | 32031 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 10 | No | 38.85 | 388.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5658-00428 | 5658 | 2018-08-24 17:16 | Section 3 | Material | Not on List | Not on List | 1 | EA | 136.86 | 136.86 | Damage Charges | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 40 | No | 39.22 | 1568.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 40 | No | 39.22 | 1568.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 140 | No | 34.93 | 4890.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 40 | No | 34.93 | 1397.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 20 | No | 4.9 | 98 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 64 | No | 5.78 | 369.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 100 | No | 11.05 | 1105 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13118-001025 | 13118 | 2019-02-26 12:56 | Section 3 | Material | NULL | Not on List | 5 | No | 22.5 | 112.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13319-001025 | 13319 | 2019-03-01 09:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3000 | each | 0.37 | 1110 | Miscellaneous | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13319-001025 | 13319 | 2019-03-01 09:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1500 | each | 0.9 | 1350 | Surveying Consumables | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13319-001025 | 13319 | 2019-03-01 09:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | each | 2.97 | 332.64 | Miscellaneous | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13384-001025 | 13384 | 2019-03-04 09:32 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13386-001025 | 13386 | 2019-03-04 10:14 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 600 | 600 | Laboratory Equipment / Certification | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-5625 | 5625 | 2018-08-24 11:29 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 4652 | 4652 | Professional Services | 2018-08-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13335-001025 | 13335 | 2019-03-01 11:48 | Section 3 | Material | Not on List | Not on List | 100000 | NULL | 1 | 100000 | Gas Oil | 2019-03-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13335-001025 | 13335 | 2019-03-01 11:48 | Section 3 | Material | Not on List | Not on List | 7500 | NULL | 1 | 7500 | Fuel | 2019-03-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13345-001025 | 13345 | 2019-03-01 13:19 | Section 4 | Material | Not on List | Not on List | 16 | 4.5x100m Roll | 116.88 | 1870.08 | Geotextiles | 2019-03-05 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5522-00347 | 5522 | 2018-08-22 16:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 5775.5 | 5775.5 | Damage Charges | 2018-08-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13419-001025 | 13419 | 2019-03-04 14:57 | Core | Material | Not on List | Not on List | 64 | each | 28.8 | 1843 | PPE | 2019-03-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 103 - Staff | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-13425-001025 | 13425 | 2019-03-04 16:15 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 4180.8 | 4181 | Laboratory Equipment / Certification | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-13429-001025 | 13429 | 2019-03-04 16:30 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 900 | 900 | Laboratory Equipment / Certification | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-13450-001025 | 13450 | 2019-03-04 16:08 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13450-001025 | 13450 | 2019-03-04 16:08 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13460-001025 | 13460 | 2019-03-05 08:17 | Section 3 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 500 | Each | 3.04 | 1520 | Miscellaneous | 2019-03-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13463-001025 | 13463 | 2019-03-05 09:19 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5698-00448 | 5698 | 2018-08-28 15:16 | Section 4 | Material | Aggregate | Not on List | 60 | Tonne | NULL | 0 | Blocks and Bricks | 2018-08-30 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | BN17 - Swavesey Junction | 2401 - Brickwork, Blockwork and Stonework | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13418-001025 | 13418 | 2019-03-04 15:29 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-03-04 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13399-001025 | 13399 | 2019-03-04 12:49 | Section 2 | Material | Not on List | Not on List | 4 | Boxes of 12 | 144 | 576 | Blocks and Bricks | 2019-03-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13399-001025 | 13399 | 2019-03-04 12:49 | Section 2 | Material | Not on List | Not on List | 1 | ea | 30 | 30 | Blocks and Bricks | 2019-03-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5122-0045 | 5122 | 2018-08-15 09:11 | Section 4 | Material | Not on List | NULL | 4 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Concrete Kerbs 125x255 HB External Radius (947297) | 16 | Each | 7.97 | 127.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Concrete Kerbs 125x255 HB External Radius (947297) | 16 | Each | 7.97 | 127.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 1 | Each | 7.97 | 7.97 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 1 | Each | 7.97 | 7.97 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 12.38 | 12.38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13473-001025 | 13473 | 2019-03-05 11:23 | Section 4 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 12.38 | 12.38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13505-001025 | 13505 | 2019-03-05 14:00 | Section 5 | Material | Not on List | Not on List | 1 | as per list | NULL | 0 | Builders Merchants (General) | 2019-03-11 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13024-001025 | 13024 | 2019-02-25 11:59 | Section 5 | Material | Not on List | Not on List | 48 | kg | 2.08 | 99.84 | Builders Merchants (General) | 2019-02-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13024-001025 | 13024 | 2019-02-25 11:59 | Section 5 | Material | Not on List | Not on List | 1 | bag | 19.8 | 19.8 | Builders Merchants (General) | 2019-02-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13403-001025 | 13403 | 2019-03-04 13:35 | Section 4 | Material | Not on List | Not on List | 1 | Each | 110 | 110 | Miscellaneous | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13403-001025 | 13403 | 2019-03-04 13:35 | Section 4 | Material | Not on List | Not on List | 1 | Each | 175 | 175 | Miscellaneous | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5645-00426 | 5645 | 2018-08-24 13:34 | Section 3 | Material | Not on List | Not on List | 1 | Each | 727.4 | 727.4 | Miscellaneous | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13538-001025 | 13538 | 2019-03-06 11:09 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 2172.5 | 2173 | Miscellaneous | 2019-03-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13541-001025 | 13541 | 2019-03-06 11:18 | Section 5 | Material | Not on List | Not on List | 1 | EACH | 372 | 372 | Miscellaneous | 2019-03-06 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13390-001025 | 13390 | 2019-03-04 10:37 | Section 4 | Material | Not on List | Not on List | 1 | order | 1495.4 | 1495.4 | Miscellaneous | 2019-03-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5576-00394 | 5576 | 2018-08-23 12:11 | Section 3 | Material | Not on List | Not on List | 50 | Ea | 5.98 | 299 | Miscellaneous | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13246-001025 | 13246 | 2019-02-28 12:08 | Core | Material | Not on List | Not on List | 1 | ea | 13725 | 13725 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13246-001025 | 13246 | 2019-02-28 12:08 | Core | Material | Not on List | Not on List | 1 | ea | 3500 | 3500 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13246-001025 | 13246 | 2019-02-28 12:08 | Core | Material | Not on List | Not on List | 1 | ea | 1000 | 1000 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13246-001025 | 13246 | 2019-02-28 12:08 | Core | Material | Not on List | Not on List | 1 | ea | 8975 | 8975 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13246-001025 | 13246 | 2019-02-28 12:08 | Core | Material | Not on List | Not on List | 1 | ea | 3750 | 3750 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13562-001025 | 13562 | 2019-03-06 13:54 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-08 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S1 Buyers
MREQ-13229-001025 | 13229 | 2019-02-28 08:04 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5576-00394 | 5576 | 2018-08-23 12:11 | Section 3 | Material | Not on List | Not on List | 65 | ea | 5.98 | 388.7 | Miscellaneous | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13563-001025 | 13563 | 2019-03-06 14:05 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-03-08 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S1 Buyers
MREQ-13500-001025 | 13500 | 2019-03-05 13:42 | Section 4 | Material | Not on List | Not on List | 1 | number | 1080 | 1080 | Office Supplies | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26645-001025 | 26645 | 2019-11-15 12:36 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26284-001025 | 26284 | 2019-11-07 13:34 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | each | 26.25 | 525 | Builders Merchants (General) | 2019-11-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4C - Structures (Culverts) 4C | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26845-001025 | 26845 | 2019-11-21 12:38 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 5.3 | 27 | Miscellaneous | 2019-11-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | No - Reject | REQ - Buyers
MREQ-26845-001025 | 26845 | 2019-11-21 12:38 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | ea | 11.15 | 45 | Small Tools (Consumables) | 2019-11-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | No - Reject | REQ - Buyers
MREQ-26468-001025 | 26468 | 2019-11-12 11:09 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | each | 21.3 | 639 | Miscellaneous | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26469-001025 | 26469 | 2019-11-12 11:20 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | each | 34.65 | 34.65 | PPE | 2019-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7266-001022 | 7266 | 2018-10-02 10:09 | Section 4 | Material | Not on List | Not on List | 600 | bags | 0.12 | 72 | Concrete Accessories | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26817-001025 | 26817 | 2019-11-20 16:15 | Section 4 | Material | Not on List | Not on List | 25 | Each | 42.17 | 1054.25 | Plastic Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26817-001025 | 26817 | 2019-11-20 16:15 | Section 4 | Material | Not on List | Not on List | 36 | Each | 26.41 | 950.76 | Plastic Drainage | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26848-001025 | 26848 | 2019-11-21 14:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 11.63 | 116 | Small Tools (Consumables) | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26848-001025 | 26848 | 2019-11-21 14:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 11.63 | 116 | Small Tools (Consumables) | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 55 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 11 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 11 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-7291-001022 | 7291 | 2018-10-02 15:27 | Section 4 | Material | Not on List | Not on List | 550 | Each | 59.46 | 32703 | Concrete Accessories | 2018-10-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26853-001025 | 26853 | 2019-11-21 16:43 | Section 4 | Material | Not on List | Not on List | 550 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-26854-001025 | 26854 | 2019-11-21 17:03 | Section 5 | Material | Not on List | Not on List | 1 | no. | NULL | 0 | Builders Merchants (General) | 2019-11-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26832-001025 | 26832 | 2019-11-21 07:14 | Section 3 | Material | Bricks/Blocks | Not on List | 675 | BNO7 WB | 0 | 0 | Blocks and Bricks | 2019-11-22 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | BN10 - A1198 Ermine Street Overbridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7309-001022 | 7309 | 2018-10-02 17:26 | Section 4 | Material | Waste Management | Construction Waste - Skip 12 cubic yard | 1 | Each | 195 | 195 | Not Sure | 2018-10-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26821-001025 | 26821 | 2019-11-20 18:55 | Section 4 | Material | Not on List | Not on List | 16 | Each | NULL | 0 | Miscellaneous | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1301 - Road Lighting Columns and Brackets | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26821-001025 | 26821 | 2019-11-20 18:55 | Section 4 | Material | Not on List | Not on List | 16 | Each | NULL | 0 | Miscellaneous | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1301 - Road Lighting Columns and Brackets | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26821-001025 | 26821 | 2019-11-20 18:55 | Section 4 | Material | Not on List | Not on List | 16 | Each | NULL | 0 | Miscellaneous | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1301 - Road Lighting Columns and Brackets | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26821-001025 | 26821 | 2019-11-20 18:55 | Section 4 | Material | Not on List | Not on List | 16 | Each | NULL | 0 | Miscellaneous | 2019-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1301 - Road Lighting Columns and Brackets | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26926-001025 | 26926 | 2019-11-25 08:01 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26899-001025 | 26899 | 2019-11-22 14:06 | Section 4 | Material | NULL | NULL | 1 | Each | 982.98 | 982.98 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26936-001025 | 26936 | 2019-11-25 09:10 | Section 6 | Material | Bagged | Sharp Sand Bulk Bag (938208) | 1 | Each | 32.74 | 33 | Builders Merchants (General) | 2019-11-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26936-001025 | 26936 | 2019-11-25 09:10 | Section 6 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 10 | Each | 3.56 | 36 | Builders Merchants (General) | 2019-11-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26822-001025 | 26822 | 2019-11-20 20:16 | Section 4 | Material | Not on List | Not on List | 160 | 25 meters | 12.8 | 2048 | Miscellaneous | 2019-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1502 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26822-001025 | 26822 | 2019-11-20 20:16 | Section 4 | Material | Not on List | Not on List | 10 | box 100 | 10.5 | 105 | Surveying Consumables | 2019-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26822-001025 | 26822 | 2019-11-20 20:16 | Section 4 | Material | Not on List | Not on List | 10 | box 100 | 10.5 | 105 | Surveying Consumables | 2019-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26702-001025 | 26702 | 2019-11-18 14:49 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 2100 x 1000 D/S (890448) | 2 | Each | 283.24 | 566.48 | Concrete Drainage | 2019-11-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26702-001025 | 26702 | 2019-11-18 14:49 | Section 6 | Material | Concrete Drainage | Not on List | 2 | Each | NULL | 0 | Concrete Drainage | 2019-11-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26702-001025 | 26702 | 2019-11-18 14:49 | Section 6 | Material | Saint Gobain Castings | Not on List | 2 | Each | NULL | 0 | Concrete Drainage | 2019-11-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26702-001025 | 26702 | 2019-11-18 14:49 | Section 6 | Material | Geotextile | Not on List | 12 | Rolls | NULL | 0 | Geotextiles | 2019-11-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26702-001025 | 26702 | 2019-11-18 14:49 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-11-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7283-001022 | 7283 | 2018-10-02 13:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 3066 | 3066 | Damage Charges | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26842-001025 | 26842 | 2019-11-21 12:02 | Section 4 | Material | Not on List | Not on List | 1000 | each | 0.98 | 980 | Surveying Consumables | 2019-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1502 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26828-001025 | 26828 | 2019-11-21 07:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1048.38 | 1048.38 | Miscellaneous | 2019-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 555 | Each | 4.59 | 2547.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 192 | Each | 3.03 | 581.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 2 | Each | 5.43 | 10.86 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 2 | Each | 5.43 | 10.86 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 2 | Each | 30 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26860-001025 | 26860 | 2019-11-21 18:00 | Section 4 | Material | NULL | NULL | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 30 | Each | 39.22 | 1176.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 10 | Each | 36.31 | 363.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 55 | Each | 39.22 | 2157.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 11 | Each | 34.93 | 384.23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 11 | Each | 34.93 | 384.23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 10 | Each | 39.22 | 392.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 2 | Each | 28.92 | 57.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26858-001025 | 26858 | 2019-11-21 17:25 | Section 4 | Material | NULL | NULL | 2 | Each | 28.92 | 57.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26951-001025 | 26951 | 2019-11-25 14:17 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 201 - Site Clearance | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-26952-001025 | 26952 | 2019-11-25 14:43 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26761-001025 | 26761 | 2019-11-19 16:35 | Section 2 | Material | Timber | Not on List | 2 | NULL | NULL | 0 | Timber Products | 2019-11-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26893-001025 | 26893 | 2019-11-22 13:02 | Core | Material | Not on List | Not on List | 1 | Each | 2724 | 2724 | Miscellaneous | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26846-001025 | 26846 | 2019-11-21 13:43 | Section 2 | Material | Not on List | Not on List | 1 | each | 249.07 | 249.07 | Professional Services | 2019-11-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26949-001025 | 26949 | 2019-11-25 13:42 | Section 4 | Material | NULL | NULL | 1 | Each | 2810.75 | 2810.75 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26970-001025 | 26970 | 2019-11-26 08:35 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Gas Oil | 2019-11-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26980-001025 | 26980 | 2019-11-26 11:43 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26803-001025 | 26803 | 2019-11-20 11:40 | Core | Material | NULL | NULL | 100 | Pairs | 0.52 | 52 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26981-001025 | 26981 | 2019-11-26 11:51 | Core | Material | NULL | NULL | NULL | NULL | 12600 | 0 | NULL | NULL | NULL | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27022-001025 | 27022 | 2019-11-27 07:14 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26989-001025 | 26989 | 2019-11-26 13:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 646.86 | each | 1 | 646.86 | Small Tools (Consumables) | 2019-12-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27034-001025 | 27034 | 2019-11-27 10:18 | Section 5 | Material | Aggregate | Not on List | 6000 | tons | NULL | 0 | Aggregate | 2019-11-28 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 602 - Excavation (excl topsoil) | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-26735-001025 | 26735 | 2019-11-19 11:33 | Section 4 | Material | Not on List | Not on List | 3 | Each | 900 | 2700 | Miscellaneous | 2019-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27042-001025 | 27042 | 2019-11-27 12:19 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27048-001025 | 27048 | 2019-11-27 14:16 | Section 3 | Material | Not on List | Not on List | 6 | ea | 192 | 1152 | Miscellaneous | 2019-12-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 102 - Compound running costs | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 3 Buyers
MREQ-27051-001025 | 27051 | 2019-11-27 15:36 | Section 5 | Material | Not on List | Not on List | 36 | NULL | NULL | 0 | Plastic Drainage | 2019-12-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-27053-001025 | 27053 | 2019-11-27 15:29 | Section 3 | Material | Not on List | Not on List | 1 | EA | 2200 | 2200 | Miscellaneous | 2019-12-05 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-27053-001025 | 27053 | 2019-11-27 15:29 | Section 3 | Material | Not on List | Not on List | 1 | EA | 2666.6 | 2667 | Miscellaneous | 2019-12-05 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-27053-001025 | 27053 | 2019-11-27 15:29 | Section 3 | Material | Not on List | Not on List | 1 | EA | 2810.75 | 2811 | Miscellaneous | 2019-12-05 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-27053-001025 | 27053 | 2019-11-27 15:29 | Section 3 | Material | Not on List | Not on List | 1 | EA | 729.66 | 730 | Miscellaneous | 2019-12-05 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-27053-001025 | 27053 | 2019-11-27 15:29 | Section 3 | Material | Not on List | Not on List | 1 | EA | 4074.01 | 4074 | Miscellaneous | 2019-12-05 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-27086-001025 | 27086 | 2019-11-28 09:36 | Core | Material | Not on List | Not on List | 1 | ea | 6125 | 6125 | Office Supplies | 2019-12-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27086-001025 | 27086 | 2019-11-28 09:36 | Core | Material | Not on List | Not on List | 1 | ea | 1790 | 1790 | Office Supplies | 2019-12-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27087-001025 | 27087 | 2019-11-28 09:46 | Core | Material | Not on List | Not on List | 1 | ea | 5775 | 5775 | Office Supplies | 2019-12-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26937-001025 | 26937 | 2019-11-25 09:20 | Core | Material | Not on List | Not on List | 1 | Each | 6216 | 6216 | Training | 2019-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26937-001025 | 26937 | 2019-11-25 09:20 | Core | Material | Not on List | Not on List | 1 | Each | 2864.38 | 2864.38 | Training | 2019-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27013-001025 | 27013 | 2019-11-26 17:59 | Section 2 | Material | Not on List | Not on List | 2 | Unit | 3136 | 6272 | Miscellaneous | 2019-12-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27013-001025 | 27013 | 2019-11-26 17:59 | Section 2 | Material | Not on List | Not on List | 2 | Unit | 3136 | 6272 | Miscellaneous | 2019-12-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27096-001025 | 27096 | 2019-11-28 11:18 | Section 2 | Material | Concrete Drainage | Not on List | 10 | each | NULL | 0 | Concrete Drainage | 2019-11-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27096-001025 | 27096 | 2019-11-28 11:18 | Section 2 | Material | Concrete Drainage | Not on List | 4 | each | NULL | 0 | Builders Merchants (General) | 2019-11-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26993-001025 | 26993 | 2019-11-26 14:30 | Section 3 | Material | Timber | Not on List | 85.8 | mtrs | 2.86 | 245.39 | Timber Products | 2019-11-27 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN3B - Gantry structures | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26705-001025 | 26705 | 2019-11-18 16:30 | Section 3 | Material | Twinwall | Not on List | 17 | each | NULL | 0 | Plastic Drainage | 2019-11-21 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26177-001025 | 26177 | 2019-11-05 17:41 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-11-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-26939-001025 | 26939 | 2019-11-25 09:58 | Section 5 | Material | Not on List | Not on List | 1 | No | 280.25 | 280.25 | Damage Charges | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26939-001025 | 26939 | 2019-11-25 09:58 | Section 5 | Material | Not on List | Not on List | 1 | No | 461.89 | 461.89 | Damage Charges | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26939-001025 | 26939 | 2019-11-25 09:58 | Section 5 | Material | Not on List | Not on List | 1 | No | 559.55 | 559.55 | Damage Charges | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26939-001025 | 26939 | 2019-11-25 09:58 | Section 5 | Material | Not on List | Not on List | 1 | No | 519.71 | 519.71 | Damage Charges | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-26939-001025 | 26939 | 2019-11-25 09:58 | Section 5 | Material | Not on List | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24468-001025 | 24468 | 2019-10-01 15:48 | Core | Material | Not on List | Not on List | 50 | posters | 1 | 50 | Miscellaneous | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 115 - Medical / 1st Aid | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27101-001025 | 27101 | 2019-11-28 13:59 | Section 4 | Material | Not on List | Not on List | 2 | Each | 128.26 | 256.52 | Plastic Drainage | 2019-11-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27101-001025 | 27101 | 2019-11-28 13:59 | Section 4 | Material | NULL | Not on List | 1 | Each | 15 | 15 | Plastic Drainage | 2019-11-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26477-001025 | 26477 | 2019-11-12 12:18 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26840-001025 | 26840 | 2019-11-21 11:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 708.33 | 708.33 | Miscellaneous | 2019-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27109-001025 | 27109 | 2019-11-28 15:47 | Core | Material | Not on List | Not on List | 60 | Number | NULL | 0 | Surveying Consumables | 2019-12-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27119-001025 | 27119 | 2019-11-28 17:36 | Section 4 | Material | Not on List | Not on List | 1 | roll | NULL | 0 | Geotextiles | 2019-12-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1503 - Cables, Joints & Terminations | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-27076-001025 | 27076 | 2019-11-28 07:20 | Section 4 | Material | Not on List | Not on List | 1 | Each | 136.8 | 136.8 | Miscellaneous | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27077-001025 | 27077 | 2019-11-28 07:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 555 | 555 | Miscellaneous | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-26729-001025 | 26729 | 2019-11-19 10:02 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-27139-001025 | 27139 | 2019-11-29 12:29 | Core | Material | PPE, Small Tools and Consumables | Not on List | 933.22 | Each | 1 | 933 | Small Tools (Consumables) | 2019-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27100-001025 | 27100 | 2019-11-28 13:06 | Section 4 | Material | Aggregate | Type 1 | 36000 | Tonnes | 22.1 | 795600 | Aggregate | 2019-12-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27153-001025 | 27153 | 2019-11-29 13:49 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1739.82 | each | 1 | 1740 | PPE | 2019-12-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27156-001025 | 27156 | 2019-11-29 14:24 | Section 6 | Material | Not on List | Not on List | 1 | n/a | 38880 | 38880 | Professional Services | 2019-12-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153a - Temporary Works Viaduct - MPD | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27170-001025 | 27170 | 2019-11-29 16:07 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2019-11-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27173-001025 | 27173 | 2019-11-29 17:48 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 103 - Staff | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-27173-001025 | 27173 | 2019-11-29 17:48 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 103 - Staff | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-27180-001025 | 27180 | 2019-12-01 20:26 | Section 5 | Material | Not on List | Not on List | 130 | litres | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S5 Buyers
MREQ-27200-001025 | 27200 | 2019-12-02 12:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 131.71 | 132 | Small Tools (Consumables) | 2019-12-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27200-001025 | 27200 | 2019-12-02 12:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 640.11 | 640 | PPE | 2019-12-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27206-001025 | 27206 | 2019-12-02 14:26 | Section 5 | Material | Not on List | Not on List | 5 | ea | 5.3 | 27 | Miscellaneous | 2019-12-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27206-001025 | 27206 | 2019-12-02 14:26 | Section 5 | Material | Not on List | Not on List | 4 | ea | 11.15 | 45 | Small Tools (Consumables) | 2019-12-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27208-001025 | 27208 | 2019-12-02 14:44 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 84 | ea | 2.5 | 210 | Surveying Consumables | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27208-001025 | 27208 | 2019-12-02 14:44 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | ea | 0.6 | 18 | Small Tools (Consumables) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27208-001025 | 27208 | 2019-12-02 14:44 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 8 | ea | 36 | 288 | Small Tools (Consumables) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27222-001025 | 27222 | 2019-12-02 12:20 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27222-001025 | 27222 | 2019-12-02 12:20 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27222-001025 | 27222 | 2019-12-02 12:20 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27222-001025 | 27222 | 2019-12-02 12:20 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27232-001025 | 27232 | 2019-12-03 07:46 | Section 5 | Material | PPE, Small Tools and Consumables | Plant Nappy 1000mm X 685mm All Blue (600200) | 6 | Each | 101.96 | 612 | Miscellaneous | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 8 | Each | 61.53 | 492.24 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 314.62 | 629.24 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 211.68 | 211.68 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 784.62 | 784.62 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 4 | Each | 126.1 | 504.4 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 4 | Each | 94.57 | 378.28 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 4 | Each | 83.73 | 334.92 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | Not on List | Not on List | 4 | Each | 106.92 | 427.68 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | NULL | Not on List | 4 | Each | 6.05 | 24.2 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18991-001025 | 18991 | 2019-06-12 14:05 | Section 4 | Material | NULL | Not on List | 1 | Each | 80.7 | 80.7 | Concrete Drainage | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6662-00750 | 6662 | 2018-09-18 11:47 | Section 3 | Material | Concrete Drainage | Not on List | 40 | No. | 209.35 | 8374 | Concrete Drainage | 2018-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19489-001025 | 19489 | 2019-06-21 09:58 | Core | Material | Not on List | Not on List | 6 | ea | 2000 | 12000 | Office Supplies | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6165 | 6165 | 2018-09-07 08:25 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 1 | 2 | Rebar and Mesh | 2018-09-21 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-17478-001025 | 17478 | 2019-05-15 16:51 | Core | Material | Not on List | Not on List | 1 | NULL | 9060.2 | 9060.2 | Miscellaneous | 2019-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | NULL | Yes - Approve | REQ - Buyers
MREQ-19485-001025 | 19485 | 2019-06-21 09:27 | Section 5 | Material | PPE, Small Tools and Consumables | NULL | 1 | EA | 185 | 185 | NULL | 2019-06-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | No - Reject | Req - S5 Buyers
MREQ-19490-001025 | 19490 | 2019-06-21 10:01 | Core | Material | Not on List | Not on List | 1 | EA | 185 | 185 | Surveying Consumables | 2019-06-24 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5164-0087 | 5164 | 2018-08-15 13:43 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2018-08-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6860-00751 | 6860 | 2018-09-21 11:43 | Section 3 | Material | Not on List | Not on List | 1 | ea | 173.44 | 173.44 | Damage Charges | 2018-09-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6701-00750 | 6701 | 2018-09-19 08:33 | Section 4 | Material | Not on List | Not on List | 1 | Each | 126.96 | 126.96 | Damage Charges | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-19544-001025 | 19544 | 2019-06-21 13:54 | Core | Material | Not on List | Not on List | 2 | NULL | 410 | 820 | Professional Services | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-19229-001025 | 19229 | 2019-06-17 14:20 | Section 6 | Material | Aggregate | A20 Pipe Bed | 300 | Tonnes | 24.5 | 7350 | Concrete Drainage | 2019-06-17 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19229-001025 | 19229 | 2019-06-17 14:20 | Section 6 | Material | Aggregate | Type 1 | 200 | Tonnes | 21.65 | 4330 | Aggregate | 2019-06-17 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19229-001025 | 19229 | 2019-06-17 14:20 | Section 6 | Material | Aggregate | Type 1 | 100 | Tonnes | 21.65 | 2165 | Aggregate | 2019-06-17 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19235-001025 | 19235 | 2019-06-17 15:29 | Section 6 | Material | Aggregate | A20 Pipe Bed | 500 | Tonnes | 24.5 | 12250 | Aggregate | 2019-06-25 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19431-001025 | 19431 | 2019-06-20 12:13 | Section 6 | Material | Aggregate | Type 1 | 14000 | Tonnes | 21.65 | 303100 | Aggregate | 2019-06-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19431-001025 | 19431 | 2019-06-20 12:13 | Section 6 | Material | Aggregate | A20 Pipe Bed | 400 | Tonnes | 24.5 | 9800 | Aggregate | 2019-06-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19431-001025 | 19431 | 2019-06-20 12:13 | Section 6 | Material | Aggregate | A20 Pipe Bed | 300 | Tonnes | 24.5 | 7350 | Aggregate | 2019-06-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19431-001025 | 19431 | 2019-06-20 12:13 | Section 6 | Material | Aggregate | A20 Pipe Bed | 300 | Tonnes | 24.5 | 7350 | Aggregate | 2019-06-27 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19431-001025 | 19431 | 2019-06-20 12:13 | Section 6 | Material | Aggregate | Type 1 | 13000 | Tonnes | 21.65 | 281450 | Aggregate | 2019-06-27 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 25 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 25 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 0 | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 10 | Each | 18.37 | 184 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 15 | Each | 18.37 | 276 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 20 | Each | 18.37 | 367 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 20 | Each | 18.37 | 367 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 15 | Each | 18.37 | 276 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Reg Leg Ct01-o (302021) | 15 | Each | 18.37 | 276 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Short Leg Ct01-o (302033) | 5 | Each | 18.37 | 92 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Short Leg Ct01-o (302033) | 5 | Each | 18.37 | 92 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Short Leg Ct01-o (302033) | 5 | Each | 18.37 | 92 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Short Leg Ct01-o (302033) | 2 | Each | 18.37 | 37 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Orange Short Leg Ct01-o (302033) | 2 | Each | 18.37 | 37 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5634-00425 | 5634 | 2018-08-24 11:45 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1710.3 | 1710.3 | Miscellaneous | 2018-08-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19571-001025 | 19571 | 2019-06-21 16:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | NULL | 0 | PPE | 2019-06-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19585-001025 | 19585 | 2019-06-24 08:48 | Core | Material | Not on List | Not on List | 1 | 1 | 79 | 79 | Office Supplies | 2019-06-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 2 | Each | 158.75 | 317.5 | Concrete Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Pipe 2.5m (249364) | 54 | Each | 210.95 | 11391.3 | Concrete Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Rocker (890351) | 3 | Each | 253.14 | 759.42 | Concrete Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Socket (890396) | 6 | Each | 253.14 | 1518.84 | Concrete Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 15 | Each | 166.43 | 2496.45 | Plastic Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6675-00750 | 6675 | 2018-09-18 14:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 173.78 | 173.78 | Janitorial | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19538-001025 | 19538 | 2019-06-21 08:56 | Section 2 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 3 | Each | 116.62 | 349.86 | Plastic Drainage | 2019-06-25 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6675-00750 | 6675 | 2018-09-18 14:30 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 51.59 | 51.59 | Miscellaneous | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19599-001025 | 19599 | 2019-06-24 11:05 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19600-001025 | 19600 | 2019-06-24 11:14 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19602-001025 | 19602 | 2019-06-24 11:31 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19603-001025 | 19603 | 2019-06-24 11:43 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19296-001025 | 19296 | 2019-06-18 11:01 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | NULL | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6675-00750 | 6675 | 2018-09-18 14:30 | Section 4 | Material | Not on List | Not on List | 2 | Pack 10 | 11.35 | 22.7 | Miscellaneous | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19491-001025 | 19491 | 2019-06-21 10:11 | Section 4 | Material | NULL | NULL | 60 | Each | 7.95 | 477 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-26 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 8 | Each | 61.53 | 492.24 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Not on List | Not on List | 14 | Each | 85.23 | 1193.22 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Not on List | Not on List | 5 | Each | 63.93 | 319.65 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Not on List | Not on List | 5 | Each | 55.13 | 275.65 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 33 | Each | 48.92 | 1614.36 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Not on List | Not on List | 35 | Each | 70.61 | 2471.35 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19507-001025 | 19507 | 2019-06-21 12:17 | Section 4 | Material | Not on List | Not on List | 11 | Each | 52.95 | 582.45 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6763-00751 | 6763 | 2018-09-20 11:03 | Section 4 | Material | Not on List | Not on List | 10 | Each | 30.24 | 302.4 | Small Tools (Consumables) | 2018-09-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1601 - Piling and attendances | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19658-001025 | 19658 | 2019-06-25 08:47 | Core | Material | Not on List | Not on List | 1 | NULL | 5.25 | 5 | Office Supplies | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19658-001025 | 19658 | 2019-06-25 08:47 | Core | Material | Not on List | Not on List | 1 | NULL | 5.25 | 5 | Office Supplies | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19658-001025 | 19658 | 2019-06-25 08:47 | Core | Material | Not on List | Not on List | 1 | NULL | 3.5 | 4 | Miscellaneous | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19231-001025 | 19231 | 2019-06-17 14:49 | Section 3 | Material | Not on List | Not on List | 320 | No | 6.22 | 1990.4 | Rebar and Mesh | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19231-001025 | 19231 | 2019-06-17 14:49 | Section 3 | Material | Not on List | Not on List | 2430 | No | 4.33 | 10521.9 | Rebar and Mesh | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19231-001025 | 19231 | 2019-06-17 14:49 | Section 3 | Material | Not on List | Not on List | 940 | No | 2.67 | 2509.8 | Rebar and Mesh | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19231-001025 | 19231 | 2019-06-17 14:49 | Section 3 | Material | Not on List | Not on List | 320 | No | 0.16 | 51.2 | Rebar and Mesh | 2019-06-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5164-0087 | 5164 | 2018-08-15 13:43 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Builders Merchants (General) | 2018-08-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6693-00750 | 6693 | 2018-09-18 17:39 | Section 3 | Material | Misc | Not on List | 1 | number | 173.05 | 173.05 | Miscellaneous | 2018-09-20 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19669-001025 | 19669 | 2019-06-25 09:42 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Surveying Consumables | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 110 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 110 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 110 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 700 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 700 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 700 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 105 | m | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 720 | m | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 3185 | m2 | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 30 | m2 | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 235 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19593-001025 | 19593 | 2019-06-24 09:15 | Section 2 | Material | Not on List | Not on List | 235 | no | NULL | 0 | Concrete Accessories | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19483-001025 | 19483 | 2019-06-21 09:29 | Section 4 | Material | Not on List | Not on List | 120 | 2m Length | 5 | 600 | NULL | 2019-06-25 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19678-001025 | 19678 | 2019-06-25 13:20 | Section 4 | Material | Not on List | Not on List | 1 | no | 0 | 0 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-19678-001025 | 19678 | 2019-06-25 13:20 | Section 4 | Material | Not on List | Not on List | 0 | no | 0 | 0 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-19475-001025 | 19475 | 2019-06-21 08:22 | Section 4 | Material | NULL | NULL | 12 | Each | 39.94 | 479.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19439-001025 | 19439 | 2019-06-20 14:49 | Section 4 | Material | NULL | NULL | 50 | Tubes | 4.97 | 248.5 | Concrete Drainage | 2019-06-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19685-001025 | 19685 | 2019-06-25 13:44 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 10 | Each | 5.9 | 59 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 30 | Each | 5.9 | 177 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 2 | Each | 12.39 | 24.78 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 1 | Each | 12.39 | 12.39 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 2 | Each | 12.39 | 24.78 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19638-001025 | 19638 | 2019-06-24 18:24 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 1 | Each | 12.39 | 12.39 | Miscellaneous | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19691-001025 | 19691 | 2019-06-25 14:50 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19692-001025 | 19692 | 2019-06-25 14:46 | Core | Material | Not on List | Not on List | 9 | NULL | 28.86 | 260 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-19693-001025 | 19693 | 2019-06-25 14:47 | Core | Material | Not on List | Not on List | 1 | NULL | 850 | 850 | Miscellaneous | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | NULL | REQ - Buyers
MREQ-19223-001025 | 19223 | 2019-06-17 13:49 | Section 3 | Material | NULL | Not on List | 20 | ea | 37.81 | 756.2 | Plastic Drainage | 2019-06-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19699-001025 | 19699 | 2019-06-25 15:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19700-001025 | 19700 | 2019-06-25 16:06 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19706-001025 | 19706 | 2019-06-25 16:17 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19486-001025 | 19486 | 2019-06-21 09:12 | Section 3 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 8 | Rolls | 189 | 1512 | Plastic Drainage | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19486-001025 | 19486 | 2019-06-21 09:12 | Section 3 | Material | Ducting | Not on List | 16 | Each | 40 | 640 | Electrical | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19473-001025 | 19473 | 2019-06-21 07:45 | Section 4 | Material | NULL | NULL | 127 | M2 | 19.5 | 2476.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18424-001025 | 18424 | 2019-06-03 10:44 | Section 3 | Material | Not on List | Not on List | 300 | No | 6.22 | 1866 | Builders Merchants (General) | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18424-001025 | 18424 | 2019-06-03 10:44 | Section 3 | Material | Not on List | Not on List | 200 | No | 4.33 | 866 | Builders Merchants (General) | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18424-001025 | 18424 | 2019-06-03 10:44 | Section 3 | Material | Not on List | Not on List | 100 | No | 8.9 | 890 | Builders Merchants (General) | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19732-001025 | 19732 | 2019-06-26 08:45 | Section 4 | Material | Not on List | Not on List | 803 | Kilos | NULL | 0 | Reinforcement | 2019-06-28 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 10 | Each | 44.65 | 446.5 | Concrete Drainage | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 70.99 | 709.9 | Concrete Drainage | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17348-001025 | 17348 | 2019-05-14 08:35 | Core | Material | Not on List | Not on List | 12 | Boxes | 159 | 1908 | Miscellaneous | 2019-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17351-001025 | 17351 | 2019-05-14 08:33 | Core | Material | Not on List | Not on List | 1 | ea | 12000 | 12000 | Office Supplies | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17289-001025 | 17289 | 2019-05-13 14:32 | Section 4 | Material | NULL | NULL | 1 | Roll | 364 | 364 | Geotextiles | 2019-05-22 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17466-001025 | 17466 | 2019-05-15 15:47 | Core | Material | PPE, Small Tools and Consumables | Towel Hand Pristine Z Fold 2ply White Case 3210 Sheet 66955 (539303) | 20 | Each | 26.89 | 537.8 | Office Supplies | 2019-05-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17466-001025 | 17466 | 2019-05-15 15:47 | Core | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289) | 10 | Each | 7.32 | 73.2 | Office Supplies | 2019-05-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17466-001025 | 17466 | 2019-05-15 15:47 | Core | Material | PPE, Small Tools and Consumables | Brush Paint Spartan Pro Triple Pack 1" + 2" + 3" 123 (704041) | 84 | Each | 8.96 | 752.64 | Office Supplies | 2019-05-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17815-001025 | 17815 | 2019-05-21 13:17 | Section 3 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-05-24 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-17710-001025 | 17710 | 2019-05-20 08:14 | Section 4 | Material | Not on List | Not on List | 13 | Each | 41.7 | 542.1 | Timber Products | 2019-05-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17710-001025 | 17710 | 2019-05-20 08:14 | Section 4 | Material | Not on List | Not on List | 5 | Each | 10.56 | 52.8 | Timber Products | 2019-05-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17710-001025 | 17710 | 2019-05-20 08:14 | Section 4 | Material | Not on List | Not on List | 10 | Each | 9.36 | 93.6 | Timber Products | 2019-05-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17710-001025 | 17710 | 2019-05-20 08:14 | Section 4 | Material | Not on List | Not on List | 50 | Each | 0.95 | 47.5 | Timber Products | 2019-05-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17599-001025 | 17599 | 2019-05-17 09:44 | Section 4 | Material | Concrete Drainage | Not on List | 3 | Each | 180.12 | 540.36 | Concrete Drainage | 2019-05-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17599-001025 | 17599 | 2019-05-17 09:44 | Section 4 | Material | Concrete Drainage | Not on List | 3 | Each | 153.46 | 460.38 | Concrete Drainage | 2019-05-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17599-001025 | 17599 | 2019-05-17 09:44 | Section 4 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 2 | Each | 195.69 | 391.38 | Concrete Drainage | 2019-05-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17599-001025 | 17599 | 2019-05-17 09:44 | Section 4 | Material | Concrete Drainage | Not on List | 2 | Each | 225.3 | 450.6 | Concrete Drainage | 2019-05-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17599-001025 | 17599 | 2019-05-17 09:44 | Section 4 | Material | Concrete Drainage | Not on List | 5 | Each | 105.52 | 527.6 | Concrete Drainage | 2019-05-23 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17120-001025 | 17120 | 2019-05-09 10:03 | Section 4 | Material | NULL | NULL | 80 | Each | 7.95 | 636 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17786-001025 | 17786 | 2019-05-20 12:28 | Section 3 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 189 | 1890 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17121-001025 | 17121 | 2019-05-09 11:48 | Section 4 | Material | NULL | NULL | 252 | m2 | 19.5 | 4914 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-23 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17526-001025 | 17526 | 2019-05-16 11:12 | Section 3 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Perf (346338) | 26 | Each | 10.66 | 277.16 | Plastic Drainage | 2019-05-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17526-001025 | 17526 | 2019-05-16 11:12 | Section 3 | Material | NULL | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 8 | Each | 166.43 | 1331.44 | Plastic Drainage | 2019-05-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 140 | Each | 58.5 | 8190 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 140 | Each | 38 | 5320 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 38 | 38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 58.5 | 58.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 65 | 65 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6417-00698 | 6417 | 2018-09-12 14:28 | Section 4 | Material | Not on List | Not on List | 1 | Each | 392.6 | 392.6 | Not Sure | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 45 | 45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 2 | Each | 500 | 1000 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 2 | Each | 650 | 1300 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 58.5 | 58.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 38 | 38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-03 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17569-001025 | 17569 | 2019-05-16 17:24 | Section 4 | Material | NULL | NULL | 1 | Each | 650 | 650 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-23 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17851-001025 | 17851 | 2019-05-22 06:34 | Section 5 | Material | Not on List | Not on List | 4000 | No | NULL | 0 | Fixings and Fasteners | 2019-05-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17851-001025 | 17851 | 2019-05-22 06:34 | Section 5 | Material | Not on List | Not on List | 4000 | No | NULL | 0 | Fixings and Fasteners | 2019-05-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6417-00698 | 6417 | 2018-09-12 14:28 | Section 4 | Material | Not on List | Not on List | 1 | Each | 35 | 35 | Not Sure | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17251-001025 | 17251 | 2019-05-13 09:46 | Section 5 | Material | Not on List | Not on List | 3 | 2019-09-30 | 45 | 135 | Surveying Consumables | 2019-05-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17862-001025 | 17862 | 2019-05-22 08:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17833-001025 | 17833 | 2019-05-21 16:43 | Section 2 | Material | Not on List | Not on List | 2.3 | Tonne | NULL | 0 | Rebar and Mesh | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17871-001025 | 17871 | 2019-05-22 08:58 | Section 5 | Material | Signage | Not on List | 9 | number | 56.49 | 508 | Miscellaneous | 2019-05-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17872-001025 | 17872 | 2019-05-22 08:54 | Core | Material | Not on List | Not on List | 1 | Sum | 1000 | 1000 | Professional Services | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Buyers
MREQ-6398-00691 | 6398 | 2018-09-12 11:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | number | 13.3 | 532 | PPE | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Coverall Hivis Yellow Protal Inherent Fr Fra63 Regular Leg31 (370489) | 3 | Each | 97.85 | 294 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Coverall Hivis Yellow Protal Inherent Fr Fra63 Regular Leg31 (370489) | 3 | Each | 97.85 | 294 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Coverall Hivis Yellow Protal Inherent Fr Fra63 Regular Leg31 (370489) | 3 | Each | 97.85 | 294 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-6508-00729 | 6508 | 2018-09-13 17:34 | Section 4 | Material | Not on List | Not on List | 1 | Number | 531.2 | 531.2 | Not Sure | 2018-09-18 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 10 | Each | 8.55 | 86 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 10 | Each | 8.55 | 86 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 10 | Each | 8.55 | 86 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 10 | Each | 8.55 | 86 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Spanner/Wrench Adjustable 250mm/10" Spartan Pro (760620) | 15 | Each | 9.09 | 136 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 300 | Each | 3.04 | 912 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 75 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 75 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 39.95 | 39.95 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycottn En471cl1 Saturn Regular Ct01-y (302019) | 10 | Each | 13 | 130 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycottn En471cl1 Saturn Regular Ct01-y (302019) | 10 | Each | 13 | 130 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 19.95 | 19.95 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17546-001025 | 17546 | 2019-05-16 10:53 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-05-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-17726-001025 | 17726 | 2019-05-20 10:36 | Section 4 | Material | NULL | NULL | 112 | Each | 5.17 | 579.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-31 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 9.95 | 9.95 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17879-001025 | 17879 | 2019-05-22 09:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17850-001025 | 17850 | 2019-05-22 00:52 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Number | 46.5 | 279 | Miscellaneous | 2019-05-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 3 | Each | 9.95 | 29.85 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17882-001025 | 17882 | 2019-05-22 10:52 | Core | Material | Not on List | Not on List | 1 | 250 | 752 | 752 | Miscellaneous | 2019-05-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 121 - Phones / Radios / Comms | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17448-001025 | 17448 | 2019-05-15 12:20 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-17832-001025 | 17832 | 2019-05-21 16:45 | Section 4 | Material | Not on List | Not on List | 20 | Each | 380.66 | 7613.2 | Fixings and Fasteners | 2019-05-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17449-001025 | 17449 | 2019-05-15 12:23 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 4895.2 | 4895.2 | Miscellaneous | 2019-05-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17894-001025 | 17894 | 2019-05-22 12:23 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-23 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17894-001025 | 17894 | 2019-05-22 12:23 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-23 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17894-001025 | 17894 | 2019-05-22 12:23 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-23 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17894-001025 | 17894 | 2019-05-22 12:23 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-23 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17865-001025 | 17865 | 2019-05-22 08:14 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 50 | 50 | Laboratory Equipment / Certification | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 5.79 | 5.79 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17827-001025 | 17827 | 2019-05-21 15:34 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 3115 | 3115 | Laboratory Equipment / Certification | 2019-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17899-001025 | 17899 | 2019-05-22 13:13 | Section 2 | Material | Not on List | Not on List | 25 | Number | NULL | 0 | Builders Merchants (General) | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-17828-001025 | 17828 | 2019-05-21 16:04 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 9.34 | 140.1 | Small Tools (Consumables) | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17908-001025 | 17908 | 2019-05-22 14:23 | Section 5 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 2 | Price Per Thousand | 345 | 690 | Blocks and Bricks | 2019-05-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17908-001025 | 17908 | 2019-05-22 14:23 | Section 5 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 17.91 | 17.91 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17908-001025 | 17908 | 2019-05-22 14:23 | Section 5 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 2 | Each | 1.5 | 3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17908-001025 | 17908 | 2019-05-22 14:23 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 3 | Each | 32.74 | 98 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17908-001025 | 17908 | 2019-05-22 14:23 | Section 5 | Material | Bagged | OP Cement; 25kg bag (767201) | 1 | Each | 2.9 | 3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17910-001025 | 17910 | 2019-05-22 14:49 | Section 4 | Material | Waste Management | Construction Waste - Skip 6 cubic yard | 1 | Each | 825 | 825 | Waste (General) | 2019-05-24 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 602 - Excavation (excl topsoil) | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-17842-001025 | 17842 | 2019-05-21 17:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | Each | 2.97 | 332.64 | Small Tools (Consumables) | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17842-001025 | 17842 | 2019-05-21 17:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 33.03 | 495.45 | Small Tools (Consumables) | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17911-001025 | 17911 | 2019-05-22 15:01 | Core | Material | Not on List | Not on List | 1 | Sum | 2500 | 2500 | Miscellaneous | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 8 | Each | 50.92 | 407.36 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 22 | Each | 43.16 | 949.52 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 8 | Each | 35.52 | 284.16 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 36 | Each | 47.04 | 1693.44 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 150 | Each | 22 | 3300 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 36 | Each | 74.3 | 2674.8 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 10 | Each | 121.25 | 1212.5 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 2 | Each | 90.94 | 181.88 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 4 | Each | 80.51 | 322.04 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 6 | Each | 102.82 | 616.92 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 24 | Each | 22 | 528 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10515-001025 | 10515 | 2018-12-21 10:15 | Section 4 | Material | Not on List | Not on List | 6 | Each | 74.3 | 445.8 | Concrete Drainage | 2019-01-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10757-001025 | 10757 | 2019-01-09 12:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 4473.35 | 4473.35 | Small Tools (Consumables) | 2019-01-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 81 | Each | 34.82 | 2820.42 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 12 | Each | 10.66 | 127.92 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 9 | Each | 10.5 | 94.5 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 23 | Each | 1.84 | 42.32 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 83 | Each | 6.54 | 542.82 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 48 | Each | 0.85 | 40.8 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 164 | Each | 2.75 | 451 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 3 | Each | 7.64 | 22.92 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 5 | Each | 48.86 | 244.3 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 3 | Each | 7.64 | 22.92 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 2 | Each | 75.44 | 150.88 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 3 | Each | 44.41 | 133.23 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 3 | Each | 68.43 | 205.29 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10730-001025 | 10730 | 2019-01-08 16:38 | Section 4 | Material | NULL | Not on List | 5 | Each | 19.72 | 98.6 | Plastic Drainage | 2019-01-21 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10750-001025 | 10750 | 2019-01-09 10:47 | Section 3 | Material | Not on List | Not on List | 5 | Bags | 7.65 | 38.25 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10750-001025 | 10750 | 2019-01-09 10:47 | Section 3 | Material | Not on List | Not on List | 120 | kg | 3.1 | 372 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | Not on List | 30 | ea | 209.35 | 6280.5 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 15 | Each | 67.9 | 1018.5 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 15 | Each | 50.92 | 763.8 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 15 | Each | 43.16 | 647.4 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10789-001025 | 10789 | 2019-01-09 16:41 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 5 | Each | 35.52 | 177.6 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10761-001025 | 10761 | 2019-01-09 13:06 | Section 3 | Material | Not on List | Not on List | 12 | No | 35 | 420 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10868-001025 | 10868 | 2019-01-11 10:39 | Section 4 | Material | Not on List | Not on List | 16 | Rolls | NULL | 0 | Not Sure | 2019-01-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Boot Wellington Safety Toe And Midsole Black S5 Tuf (165022) | 3 | Each | 10.95 | 32.85 | PPE | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Scraper Boot Galvanised C/W Brushes (746900) | 10 | Each | 10.19 | 101.9 | Miscellaneous | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10758-001025 | 10758 | 2019-01-09 12:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 0.39 | 3.9 | Miscellaneous | 2019-01-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10890-001025 | 10890 | 2019-01-11 13:49 | Section 4 | Material | Not on List | Not on List | 1 | no | NULL | 0 | Concrete Drainage | 2019-01-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10869-001025 | 10869 | 2019-01-11 08:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 720.52 | Each | 1 | 720.52 | Janitorial | 2019-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10869-001025 | 10869 | 2019-01-11 08:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 934.38 | Each | 1 | 934.38 | Small Tools (Consumables) | 2019-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10869-001025 | 10869 | 2019-01-11 08:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1420.2 | Each | 1 | 1420.2 | PPE | 2019-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 930 | Each | 4.43 | 4120 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 15 | Each | 5.79 | 87 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 45 | Each | 5.79 | 261 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 1320 | Each | 1.45 | 1914 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Kerbs 125x150 BN External Radius (947297) | 15 | Each | 5.25 | 79 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Concrete Kerbs 125x150 BN External Radius (947297) | 15 | Each | 5.25 | 79 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Not on List | 14 | Each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10897-001025 | 10897 | 2019-01-11 13:25 | Section 3 | Material | Kerbs | Not on List | 14 | Each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10793-001025 | 10793 | 2019-01-09 16:22 | Section 3 | Material | NULL | Not on List | 1 | no | 837.68 | 837.68 | Damage Charges | 2019-01-10 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10972-001025 | 10972 | 2019-01-14 14:19 | Section 4 | Material | Not on List | Not on List | 3 | EA | NULL | 0 | Concrete Accessories | 2019-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 105 | Each | 23.14 | 2429.7 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 53 | Each | 3.38 | 179.14 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 106 | Each | 1.86 | 197.16 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 36 | Each | 38.7 | 1393.2 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 8 | Each | 39.7 | 317.6 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 3 | Each | 19.72 | 59.16 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Polypipe 150mm x 25m Ridgiflex (877588) | 4 | Each | 145 | 580 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 21 | Each | 67.9 | 1425.9 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 6 | Each | 43.16 | 258.96 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 16 | Each | 35.52 | 568.32 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 21 | Each | 47.04 | 987.84 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 50 | Each | 16.49 | 824.5 | Concrete Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | Not on List | 10 | Each | 34 | 340 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | NULL | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 21 | Each | 74.3 | 1560.3 | Builders Merchants (General) | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10782-001025 | 10782 | 2019-01-09 14:20 | Section 3 | Material | Not on List | Not on List | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-01-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10975-001025 | 10975 | 2019-01-14 15:03 | Section 4 | Material | Not on List | Not on List | 0.827 | tonnes | NULL | 0 | Reinforcement | 2019-02-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10976-001025 | 10976 | 2019-01-14 14:05 | Section 3 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Miscellaneous | 2019-01-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10978-001025 | 10978 | 2019-01-14 15:40 | Section 4 | Material | Not on List | Not on List | 40 | ea | 1 | 40 | Builders Merchants (General) | 2019-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10996-001025 | 10996 | 2019-01-15 07:28 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-11000-001025 | 11000 | 2019-01-15 09:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 762 | Each | 1 | 762 | PPE | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11002-001025 | 11002 | 2019-01-15 09:23 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11008-001025 | 11008 | 2019-01-15 10:41 | Section 4 | Material | Timber | Not on List | 24 | NULL | NULL | 0 | Timber Products | 2019-01-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-10805-001025 | 10805 | 2019-01-10 08:36 | Section 3 | Material | Not on List | Not on List | 5 | T | NULL | 0 | Builders Merchants (General) | 2019-01-17 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11013-001025 | 11013 | 2019-01-15 11:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 4660.5 | 4661 | Laboratory Equipment / Certification | 2019-01-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN13 - West Brook Underbridge | 1901 - Protection of Steelwork Against Corrosion | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10616-001025 | 10616 | 2019-01-04 15:44 | Section 3 | Material | Not on List | Not on List | 1 | Each | 5 | 5 | Waste (Recycling) | 2019-01-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Staples Replacement 12mm For Staple Gun Box Of 1000 (770200) | 1 | NULL | 2.6 | 3 | Small Tools (Consumables) | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Refill Air Care Pristine Wild Berries Air Fragrance 270ml (539229) | 6 | Each | 3.1 | 19 | Janitorial | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11026-001025 | 11026 | 2019-01-15 14:18 | Section 4 | Material | Not on List | Not on List | 38 | packs | NULL | 0 | Reinforcement | 2019-01-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11026-001025 | 11026 | 2019-01-15 14:18 | Section 4 | Material | Not on List | Not on List | 30 | packs | NULL | 0 | Reinforcement | 2019-01-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11026-001025 | 11026 | 2019-01-15 14:18 | Section 4 | Material | Not on List | Not on List | 25 | packs | NULL | 0 | Reinforcement | 2019-01-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10976-001025 | 10976 | 2019-01-14 14:05 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 26.55 | 265.5 | Miscellaneous | 2019-01-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11030-001025 | 11030 | 2019-01-15 15:42 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 14.7 | 59 | Small Tools (Consumables) | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11030-001025 | 11030 | 2019-01-15 15:42 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | 0.24 | 12 | Fixings and Fasteners | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11047-001025 | 11047 | 2019-01-16 07:17 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11048-001025 | 11048 | 2019-01-16 07:44 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Pipe 2.5m (249384) | 14 | Each | 535.92 | 7503 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Rocker (249385) | 2 | Each | 643.11 | 1286 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Socket (890401) | 1 | Each | 643.11 | 643 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Spigot (890382) | 1 | Each | 643.11 | 643 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11013-001025 | 11013 | 2019-01-15 11:48 | Section 3 | Material | Not on List | Not on List | 1 | No | 4660.5 | 4660.5 | Laboratory Equipment / Certification | 2019-01-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11058-001025 | 11058 | 2019-01-16 09:36 | Core | Material | Not on List | Not on List | 1 | Cabinet and Installation | 5450 | 5450 | Professional Services | 2019-01-17 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11059-001025 | 11059 | 2019-01-16 09:54 | Section 4 | Material | Not on List | Not on List | 60 | meter | NULL | 0 | Concrete Accessories | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN24 - Girton Interchange Bridge C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11061-001025 | 11061 | 2019-01-16 10:54 | Section 4 | Material | Not on List | Not on List | 25 | number | NULL | 0 | Rebar and Mesh | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10799-001025 | 10799 | 2019-01-10 07:35 | Section 3 | Material | Not on List | Not on List | 1 | No | 8041 | 8041 | Professional Services | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11066-001025 | 11066 | 2019-01-16 12:34 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11070-001025 | 11070 | 2019-01-16 13:34 | Section 4 | Material | Bagged | Not on List | 15 | EA | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-21 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11073-001025 | 11073 | 2019-01-16 14:29 | Section 4 | Material | Not on List | Not on List | 20 | rolls | NULL | 0 | Not Sure | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10828-001025 | 10828 | 2019-01-10 12:44 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 47.04 | 1411.2 | Concrete Drainage | 2019-01-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11058-001025 | 11058 | 2019-01-16 09:36 | Core | Material | Not on List | Not on List | 1 | Cabinet and Installation | 5450 | 5450 | Professional Services | 2019-01-17 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8282 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Finance Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Pipe 2.5m (249384) | 14 | Each | 643.92 | 9014.88 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Rocker (249385) | 2 | Each | 722.86 | 1445.72 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Socket (890401) | 1 | Each | 722.86 | 722.86 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11050-001025 | 11050 | 2019-01-16 07:46 | Section 4 | Material | Concrete Drainage | CPM 1350mm Concrete Spigot (890382) | 1 | Each | 722.86 | 722.86 | Concrete Drainage | 2019-01-24 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11073-001025 | 11073 | 2019-01-16 14:29 | Section 4 | Material | Not on List | Not on List | 20 | rolls | 110.27 | 2205.4 | Not Sure | 2019-01-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 16 | items | NULL | 0 | Fixings and Fasteners | 2019-08-05 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 180 | items | NULL | 0 | Fixings and Fasteners | 2019-08-05 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 50 | items | NULL | 0 | Fixings and Fasteners | 2019-01-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 50 | items | NULL | 0 | Fixings and Fasteners | 2019-01-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5490-00309 | 5490 | 2018-08-22 10:10 | Section 3 | Material | Plastic Drainage | Not on List | 160 | No. | 19.72 | 3155.2 | Plastic Drainage | 2019-03-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 100 | items | NULL | 0 | Fixings and Fasteners | 2019-01-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 180 | items | NULL | 0 | Fixings and Fasteners | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11119-001025 | 11119 | 2019-01-17 07:31 | Section 4 | Material | Not on List | Not on List | 148 | items | NULL | 0 | Fixings and Fasteners | 2019-02-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11061-001025 | 11061 | 2019-01-16 10:54 | Section 4 | Material | Not on List | Not on List | 25 | number | 31.36 | 784 | Rebar and Mesh | 2019-01-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10759-001025 | 10759 | 2019-01-09 12:47 | Section 4 | Material | Not on List | Not on List | 1 | ea | 145 | 145 | Surveying Consumables | 2019-01-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-17870-001025 | 17870 | 2019-05-22 08:52 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1139.6 | 1139.6 | PPE | 2019-05-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17913-001025 | 17913 | 2019-05-22 15:49 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Office Supplies | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 5.84 | 5.84 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 19.95 | 19.95 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6594-00749 | 6594 | 2018-09-17 13:20 | Section 4 | Material | Not on List | Not on List | 10 | Each | 8.49 | 84.9 | Builders Merchants (General) | 2018-09-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23217-001025 | 23217 | 2019-09-04 16:33 | Section 2 | Material | Saint Gobain Castings | Not on List | 3 | each | NULL | 0 | Concrete Drainage | 2019-09-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23217-001025 | 23217 | 2019-09-04 16:33 | Section 2 | Material | Combined Drainage | Not on List | 6 | each | NULL | 0 | Concrete Drainage | 2019-09-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23268-001025 | 23268 | 2019-09-05 13:49 | Section 4 | Material | NULL | NULL | 1 | Each | 5177.12 | 5177.12 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23312-001025 | 23312 | 2019-09-06 09:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EA | NULL | 0 | Small Tools (Consumables) | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23312-001025 | 23312 | 2019-09-06 09:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EA | NULL | 0 | Small Tools (Consumables) | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6597-00749 | 6597 | 2018-09-17 14:13 | Section 4 | Material | Not on List | Not on List | 30 | Each | 104.64 | 3139.2 | Plastic Drainage | 2018-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23312-001025 | 23312 | 2019-09-06 09:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EA | NULL | 0 | Small Tools (Consumables) | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23312-001025 | 23312 | 2019-09-06 09:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | EA | NULL | 0 | Janitorial | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23312-001025 | 23312 | 2019-09-06 09:36 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | PKS | NULL | 0 | Janitorial | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23203-001025 | 23203 | 2019-09-04 12:38 | Section 3 | Material | Concrete Drainage | Not on List | 8 | No | 59 | 472 | Builders Merchants (General) | 2019-09-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23309-001025 | 23309 | 2019-09-06 08:51 | Section 5 | Material | Concrete Drainage | NULL | 1 | SM | 2907.8 | 2907.8 | Concrete Drainage | 2019-09-09 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23257-001025 | 23257 | 2019-09-05 10:41 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 3.51 | 70.2 | Small Tools (Consumables) | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23257-001025 | 23257 | 2019-09-05 10:41 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 3.86 | 77.2 | Small Tools (Consumables) | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23257-001025 | 23257 | 2019-09-05 10:41 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 4.81 | 96.2 | Small Tools (Consumables) | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23303-001025 | 23303 | 2019-09-06 06:48 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Ductile Drainage | 2019-09-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6629-00750 | 6629 | 2018-09-18 08:18 | Section 4 | Material | Not on List | Not on List | 50 | Each | 19.5 | 975 | Timber Products | 2018-09-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22061-001025 | 22061 | 2019-08-09 10:45 | Section 4 | Material | NULL | NULL | 320 | Each | 3.52 | 1126.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22061-001025 | 22061 | 2019-08-09 10:45 | Section 4 | Material | NULL | NULL | 1640 | Each | 1.5 | 2460 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22061-001025 | 22061 | 2019-08-09 10:45 | Section 4 | Material | NULL | NULL | 252 | Each | 4.13 | 1040.76 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22061-001025 | 22061 | 2019-08-09 10:45 | Section 4 | Material | NULL | NULL | 2 | Each | 30 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22061-001025 | 22061 | 2019-08-09 10:45 | Section 4 | Material | NULL | NULL | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6629-00750 | 6629 | 2018-09-18 08:18 | Section 4 | Material | Not on List | Not on List | 120 | Each | 1.2 | 144 | Timber Products | 2018-09-21 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23138-001025 | 23138 | 2019-09-03 13:58 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23196-001025 | 23196 | 2019-09-04 12:33 | Core | Material | NULL | NULL | 1 | Each | 738 | 738 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23323-001025 | 23323 | 2019-09-06 12:31 | Section 3 | Material | Not on List | Not on List | 500 | No | NULL | 0 | Builders Merchants (General) | 2019-09-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23187-001025 | 23187 | 2019-09-04 11:35 | Section 4 | Material | Not on List | Not on List | 10 | Each | 37.13 | 371.3 | Plastic Drainage | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23187-001025 | 23187 | 2019-09-04 11:35 | Section 4 | Material | Not on List | Not on List | 10 | Each | 60.38 | 603.8 | Plastic Drainage | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6648-00750 | 6648 | 2018-09-18 10:12 | Section 4 | Material | Not on List | Not on List | 20 | Each | 132.3 | 2646 | Builders Merchants (General) | 2018-09-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23187-001025 | 23187 | 2019-09-04 11:35 | Section 4 | Material | NULL | Not on List | 1 | Each | 15 | 15 | Plastic Drainage | 2019-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23282-001025 | 23282 | 2019-09-05 15:37 | Section 4 | Material | Ducting | Not on List | 4 | Each | 1.77 | 7.08 | Electrical | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1506 - Detector Installations | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23282-001025 | 23282 | 2019-09-05 15:37 | Section 4 | Material | NULL | Not on List | 4 | Each | 9.36 | 37.44 | Electrical | 2019-09-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1506 - Detector Installations | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23316-001025 | 23316 | 2019-09-06 11:17 | Section 4 | Material | Not on List | Not on List | 4 | Each | 25 | 100 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6648-00750 | 6648 | 2018-09-18 10:12 | Section 4 | Material | NULL | NULL | 1 | Each | 140 | 140 | NULL | 2018-09-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | EA | 103.08 | 206.16 | PPE | 2019-09-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | EA | 3.17 | 19.02 | Small Tools (Consumables) | 2019-09-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 24 | EA | 3.03 | 72.72 | Small Tools (Consumables) | 2019-09-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 24 | EA | 3.03 | 72.72 | Small Tools (Consumables) | 2019-09-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 50 | Each | 25.78 | 1289 | Timber Products | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | Timber | Not on List | 36 | EACH | 44.5 | 1602 | Timber Products | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 192 | LM | 6.28 | 1205.76 | Timber Products | 2019-09-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23213-001025 | 23213 | 2019-09-04 15:35 | Section 5 | Material | Timber | Not on List | 192 | LM | 1.33 | 255.36 | Timber Products | 2019-09-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6655-00750 | 6655 | 2018-09-18 11:15 | Section 4 | Material | Not on List | Not on List | 2 | Each | 79.35 | 158.7 | Miscellaneous | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23390-001025 | 23390 | 2019-09-09 10:28 | Core | Material | Not on List | Not on List | 1 | Sum | 30000 | 30000 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 153 - Temporary Works | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-23402-001025 | 23402 | 2019-09-09 15:44 | Section 3 | Material | Not on List | Not on List | 4 | No. | 75 | 300 | Small Tools (Consumables) | 2019-09-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23320-001025 | 23320 | 2019-09-06 12:08 | Section 3 | Material | Not on List | Not on List | 4 | No | 85 | 340 | Builders Merchants (General) | 2019-09-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6664-00750 | 6664 | 2018-09-18 11:52 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2290.84 | 2290.84 | Concrete Drainage | 2018-10-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23426-001025 | 23426 | 2019-09-10 08:11 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-11 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 2701 - Accommodation works | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-23427-001025 | 23427 | 2019-09-10 08:36 | Core | Material | Not on List | Not on List | 3 | each | 10.3 | 31 | Miscellaneous | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-23427-001025 | 23427 | 2019-09-10 08:36 | Core | Material | Not on List | Not on List | 1 | each | 10.99 | 11 | Miscellaneous | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-23260-001025 | 23260 | 2019-09-05 11:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 13310 | 13310 | Miscellaneous | 2019-09-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23037-001025 | 23037 | 2019-09-02 09:04 | Section 4 | Material | Not on List | Not on List | 1 | Each | 12212.44 | 12212.44 | Tanks and Interceptors | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6664-00750 | 6664 | 2018-09-18 11:52 | Section 4 | Material | Not on List | Not on List | 1 | Each | 252.38 | 252.38 | Concrete Drainage | 2018-10-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23400-001025 | 23400 | 2019-09-09 15:28 | Section 2 | Material | Ducting | Not on List | 2 | No. | 10.23 | 20.46 | Electrical | 2019-09-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23400-001025 | 23400 | 2019-09-09 15:28 | Section 2 | Material | Ducting | Not on List | 2 | No. | 1.77 | 3.54 | Electrical | 2019-09-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23446-001025 | 23446 | 2019-09-10 13:24 | Section 6 | Material | Not on List | Not on List | 1 | each | 117.67 | 118 | Miscellaneous | 2019-09-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6664-00750 | 6664 | 2018-09-18 11:52 | Section 4 | Material | NULL | NULL | 1 | Each | 210 | 210 | Concrete Drainage | 2018-10-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 6 | Roll | 237 | 1422 | Geotextiles | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Geotextiles | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 2 | Roll | 465 | 930 | Geotextiles | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 2 | Roll | 207 | 414 | Geotextiles | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 1 | Box | 18 | 18 | Geotextiles | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23431-001025 | 23431 | 2019-09-10 10:00 | Section 4 | Material | Not on List | Not on List | 1 | Delivery | 100 | 100 | Miscellaneous | 2019-09-16 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23450-001025 | 23450 | 2019-09-10 14:43 | Core | Material | Not on List | Not on List | 1 | EACH | 50 | 50 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-23448-001025 | 23448 | 2019-09-10 13:00 | Section 4 | Material | Aggregate | Not on List | 20000 | Tonne | 5 | 100000 | Aggregate | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-4997-0011 | 4997 | 2018-08-13 15:45 | Section 4 | Material | Not on List | Not on List | 1 | 1 | 1 | 1 | Gas Oil | 2018-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5138-0066 | 5138 | 2018-08-15 11:27 | Section 3 | Material | Not on List | NULL | 5 | 5L Tub | 17.1 | 85.5 | Builders Merchants (General) | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 400 | Each | 16.49 | 6596 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23489-001025 | 23489 | 2019-09-11 08:15 | Section 4 | Material | Not on List | Not on List | 1 | pack | NULL | 0 | Miscellaneous | 2019-09-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | SP x BN RH Drop Kerb Direct | 14 | Each | 5.43 | 76.02 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | SP x BN RH Drop Kerb Direct | 14 | Each | 5.43 | 76.02 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | SP x BN RH Drop Kerb Direct | 5 | Each | 5.43 | 27.15 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | SP X BN LH Drop Kerb Direct | 5 | Each | 5.43 | 27.15 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | Not on List | 40 | ea | 4.59 | 183.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 30 | Each | 20 | 600 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 45 | Each | 4.59 | 206.55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 10 | Each | 10.35 | 103.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23361-001025 | 23361 | 2019-09-06 17:34 | Section 2 | Material | Kerbs | Not on List | 40 | ea | 4.59 | 183.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23445-001025 | 23445 | 2019-09-10 13:14 | Core | Material | NULL | NULL | 1 | each | 824.94 | 824.94 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23497-001025 | 23497 | 2019-09-11 10:49 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23281-001025 | 23281 | 2019-09-05 15:15 | Core | Material | Not on List | Not on List | 1 | box | 72 | 72 | Miscellaneous | 2019-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23503-001025 | 23503 | 2019-09-11 11:34 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Iron Wear | Not on List | 5 | Each | 102 | 510 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs 125x150 BN External Radius (947297) | 15 | m | 5.43 | 81.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 15 | Each | 6 | 90 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 4 | Each | 11.95 | 47.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 4 | Each | 11.95 | 47.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Drop Kerb HB x BN LH (897468) | 5 | Each | 11.95 | 59.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Drop Kerb HB x BN RH (897464) | 5 | Each | 11.95 | 59.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs 125x150 BN External Radius (947297) | 20 | Each | 5.43 | 108.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23319-001025 | 23319 | 2019-09-06 11:42 | Section 6 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 15 | Each | 3.52 | 52.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-13 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23512-001025 | 23512 | 2019-09-11 12:38 | Section 2 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Concrete Accessories | 2019-09-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2302 - Sealing of gaps | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 100 | Each | 74.3 | 7430 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23394-001025 | 23394 | 2019-09-09 13:42 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 3.72 | 37.2 | Janitorial | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23442-001025 | 23442 | 2019-09-10 13:04 | Core | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | 0.83 | 83 | NULL | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23443-001025 | 23443 | 2019-09-10 13:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 64.38 | 257.52 | Miscellaneous | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 3 | Each | 29 | 87 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23318-001025 | 23318 | 2019-09-06 11:41 | Section 5 | Material | Not on List | Not on List | 20 | ea | 33.55 | 671 | Builders Merchants (General) | 2019-09-11 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23523-001025 | 23523 | 2019-09-11 14:22 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 3945.43 | 3945 | Miscellaneous | 2019-09-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23524-001025 | 23524 | 2019-09-11 14:26 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 3237.6 | 3238 | Miscellaneous | 2019-09-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23470-001025 | 23470 | 2019-09-10 18:06 | Section 5 | Material | Ducting | Not on List | 6 | EA | 11.05 | 66.3 | Not Sure | 2019-09-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23392-001025 | 23392 | 2019-09-09 12:27 | Core | Material | Not on List | Not on List | 1 | EA | 317 | 317 | Office Supplies | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-22595-001025 | 22595 | 2019-08-21 10:09 | Core | Material | NULL | NULL | NULL | NULL | 392.75 | 0 | Miscellaneous | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23441-001025 | 23441 | 2019-09-10 12:42 | Section 3 | Material | Not on List | Not on List | 200 | ea | 4.97 | 994 | Miscellaneous | 2019-09-16 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23526-001025 | 23526 | 2019-09-11 15:32 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 50 | Each | 24.32 | 1216 | Timber Products | 2019-09-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 1 | Each | 162.27 | 162.27 | Concrete Drainage | 2018-10-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23454-001025 | 23454 | 2019-09-10 14:38 | Section 4 | Material | Aggregate | Type 1 | 10000 | Tonnes | 21.65 | 216500 | Aggregate | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23454-001025 | 23454 | 2019-09-10 14:38 | Section 4 | Material | Aggregate | 6G | 900 | Tonnes | 32.9 | 29610 | Aggregate | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23447-001025 | 23447 | 2019-09-10 13:28 | Section 5 | Material | NULL | NULL | 1 | Each | 1221.03 | 1221.03 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23553-001025 | 23553 | 2019-09-12 08:41 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-09-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-23515-001025 | 23515 | 2019-09-11 13:08 | Section 4 | Material | Not on List | Not on List | 50 | Each | 42.86 | 2143 | Miscellaneous | 2019-09-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23482-001025 | 23482 | 2019-09-11 07:47 | Core | Material | PPE, Small Tools and Consumables | Not on List | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6667-00750 | 6667 | 2018-09-18 12:24 | Section 4 | Material | Not on List | Not on List | 1 | Each | 323.4 | 323.4 | Concrete Drainage | 2018-10-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 1920 | no | 3.4 | 6528 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23528-001025 | 23528 | 2019-09-11 15:54 | Core | Material | Not on List | Not on List | 1 | SM | 1390.37 | 1390.37 | Not Sure | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23525-001025 | 23525 | 2019-09-11 15:28 | Core | Material | Not on List | Not on List | 1 | SM | 158.33 | 158.33 | Miscellaneous | 2019-09-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 160 | no | 3.4 | 544 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23491-001025 | 23491 | 2019-09-11 09:39 | Core | Material | Not on List | Not on List | 2 | EA | 95 | 190 | Laboratory Equipment / Certification | 2019-09-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23514-001025 | 23514 | 2019-09-11 12:56 | Section 6 | Material | Not on List | Not on List | 50 | load | 80 | 4000 | Waste (Recycling) | 2019-09-11 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 10 | no | 5.25 | 52.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23395-001025 | 23395 | 2019-09-09 14:00 | Section 2 | Material | Not on List | Not on List | 1 | each | 174.58 | 174.58 | Professional Services | 2019-09-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23548-001025 | 23548 | 2019-09-12 08:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 9975 | 9975 | Concrete Drainage | 2019-09-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23548-001025 | 23548 | 2019-09-12 08:07 | Section 4 | Material | NULL | Not on List | 1 | Each | 340 | 340 | Concrete Drainage | 2019-09-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5138-0066 | 5138 | 2018-08-15 11:27 | Section 3 | Material | Not on List | NULL | 30 | tubs | 61.94 | 1858.2 | Builders Merchants (General) | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8817-001024 | 8817 | 2018-11-07 10:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 546.98 | 546.98 | Janitorial | 2018-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8839-001024 | 8839 | 2018-11-07 15:38 | Section 3 | Material | Aggregate | Not on List | 300 | Te | NULL | 0 | Aggregate | 2018-11-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8839-001024 | 8839 | 2018-11-07 15:38 | Section 3 | Material | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Aggregate | 2018-11-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8839-001024 | 8839 | 2018-11-07 15:38 | Section 3 | Material | Aggregate | 6F5 | 1000 | Tonnes | 14.65 | 14650 | Aggregate | 2018-11-15 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3B - Roadworks | 701 - Sub-base | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.15 | m | 1751.24 | 7268 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.15 | m | 2126.99 | 8827 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.67 | m | 1751.24 | 8178 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Concrete Drainage | Not on List | 50 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.67 | m | 2126.99 | 9933 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 8.82 | m | 314 | 2769 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 8.82 | m | 314 | 2769 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1340 | 1340 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1340 | 1340 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1100 | 1100 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1100 | 1100 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8849-001024 | 8849 | 2018-11-07 17:16 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8852-001024 | 8852 | 2018-11-07 11:34 | Section 4 | Material | Ducting | Not on List | 1 | U | NULL | 0 | Plastic Drainage | 2018-11-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8853-001024 | 8853 | 2018-11-07 17:37 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8737-001024 | 8737 | 2018-11-06 08:59 | Section 4 | Material | Concrete Drainage | Not on List | 6 | Each | 150 | 900 | Concrete Drainage | 2018-11-09 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8737-001024 | 8737 | 2018-11-06 08:59 | Section 4 | Material | NULL | Not on List | 1 | Each | 120 | 120 | Concrete Drainage | 2018-11-09 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8852-001024 | 8852 | 2018-11-07 11:34 | Section 4 | Material | NULL | Not on List | 1 | Each | 180 | 180 | Plastic Drainage | 2018-11-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8852-001024 | 8852 | 2018-11-07 11:34 | Section 4 | Material | NULL | Not on List | 1 | Each | 50 | 50 | Plastic Drainage | 2018-11-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8714-001024 | 8714 | 2018-11-05 16:38 | Section 4 | Material | Not on List | Not on List | 40 | Each | 4.3 | 172 | Builders Merchants (General) | 2018-11-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8837-001024 | 8837 | 2018-11-07 14:46 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 50 | Each | 48.86 | 2443 | Plastic Drainage | 2018-11-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8834-001024 | 8834 | 2018-11-07 14:22 | Section 3 | Material | Not on List | Not on List | 8 | ea | 41.74 | 333.92 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8866-001024 | 8866 | 2018-11-08 09:04 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 688 | Plastic Drainage | 2018-11-12 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8601-001023 | 8601 | 2018-11-02 06:10 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2179.8 | 2179.8 | Small Tools (Consumables) | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5217-00132 | 5217 | 2018-08-16 11:23 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2018-08-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8829-001024 | 8829 | 2018-11-07 14:10 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1308 | 1308 | Concrete Drainage | 2018-11-07 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8694-001024 | 8694 | 2018-11-05 12:13 | Section 4 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Rebar and Mesh | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8878-001024 | 8878 | 2018-11-08 10:57 | Section 4 | Material | Not on List | Not on List | 3 | NULL | 1395.2 | 4186 | Concrete Drainage | 2018-11-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8879-001024 | 8879 | 2018-11-08 11:07 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 1173.5 | 4694 | Concrete Drainage | 2018-11-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8676-001023 | 8676 | 2018-11-05 09:55 | Section 4 | Material | Not on List | Not on List | 10 | EA | 58 | 580 | Miscellaneous | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8676-001023 | 8676 | 2018-11-05 09:55 | Section 4 | Material | NULL | Not on List | 1 | Ea | 80 | 80 | Miscellaneous | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8882-001024 | 8882 | 2018-11-08 12:23 | Section 4 | Material | Aggregate | Not on List | 300 | ton | NULL | 0 | Aggregate | 2018-11-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | NULL | Not on List | 9 | Each | 26.09 | 234.81 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | NULL | Not on List | 10 | Each | 2.92 | 29.2 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ8743 | 8743 | 2018-11-06 10:03 | Section 4 | Material | NULL | Not on List | 20 | Each | 1.44 | 28.8 | Plastic Drainage | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 11.6 | 12 | PPE | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 9.51 | 95 | Janitorial | 2018-11-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.45 | 147 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8866-001024 | 8866 | 2018-11-08 09:04 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 687.5 | Plastic Drainage | 2018-11-12 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8903-001024 | 8903 | 2018-11-08 16:35 | Section 3 | Material | Aggregate | 6G | 120 | Tonnes | 22 | 2640 | Aggregate | 2018-11-12 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | CL3B - Structures (Culverts) 3B | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8903-001024 | 8903 | 2018-11-08 16:35 | Section 3 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 15 | Each | 115.78 | 1737 | Geotextiles | 2018-11-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8904-001024 | 8904 | 2018-11-08 16:41 | Section 3 | Material | Aggregate | Not on List | 900 | m3 | 43.08 | 38772 | Aggregate | 2018-11-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8909-001024 | 8909 | 2018-11-09 01:12 | Section 3 | Material | Not on List | Not on List | 1 | Each | 67.58 | 68 | Miscellaneous | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8903-001024 | 8903 | 2018-11-08 16:35 | Section 3 | Material | Aggregate | 6G | 120 | Tonnes | 22 | 2640 | Aggregate | 2018-11-12 | Gate K - 1339703 - Access to BN13-BN12 & Hilton Rd, Plant Crossing gates | CL3B - Structures (Culverts) 3B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8903-001024 | 8903 | 2018-11-08 16:35 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 15 | Each | 115.78 | 1736.7 | Geotextiles | 2018-11-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8904-001024 | 8904 | 2018-11-08 16:41 | Section 3 | Material | Aggregate | Not on List | 900 | m3 | 43.08 | 38772 | Aggregate | 2018-11-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8937-001024 | 8937 | 2018-11-09 13:31 | Section 4 | Material | Not on List | Not on List | 5 | boxes | NULL | 0 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8938-001024 | 8938 | 2018-11-09 13:36 | Section 4 | Material | Not on List | Not on List | 2 | boxes | NULL | 0 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8909-001024 | 8909 | 2018-11-09 01:12 | Section 3 | Material | Not on List | Not on List | 1 | Each | 67.58 | 67.58 | Miscellaneous | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8882-001024 | 8882 | 2018-11-08 12:23 | Section 4 | Material | Aggregate | Not on List | 15 | Load | 370 | 5550 | Aggregate | 2018-11-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8878-001024 | 8878 | 2018-11-08 10:57 | Section 4 | Material | Not on List | Not on List | 3 | Each | 1395.2 | 4185.6 | Concrete Drainage | 2018-11-09 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8879-001024 | 8879 | 2018-11-08 11:07 | Section 4 | Material | Not on List | Not on List | 4 | Each | 1173.5 | 4694 | Concrete Drainage | 2018-11-09 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 5 | boxes | 63 | 315 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 24 | tubes | 12 | 288 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 1 | delivery | 60 | 60 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8736-001024 | 8736 | 2018-11-06 09:00 | Section 4 | Material | Not on List | Not on List | 100 | Each | 54 | 5400 | Plastic Drainage | 2018-11-16 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8985-001024 | 8985 | 2018-11-12 08:46 | Section 3 | Material | Bagged | Post Mix 25kg (348099) | 60 | Each | 3.45 | 207 | Builders Merchants (General) | 2018-11-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 200 | EA | 1 | 200 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 10 | ea | 1 | 10 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 5 | ea | 1 | 5 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8985-001024 | 8985 | 2018-11-12 08:46 | Section 3 | Material | NULL | Post Mix 25kg (348099) | 60 | Each | 3.45 | 207 | Builders Merchants (General) | 2018-11-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9023-001024 | 9023 | 2018-11-12 15:05 | Section 3 | Material | Concrete Drainage | Not on List | 80 | No. | NULL | 0 | Concrete Drainage | 2018-11-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | Concrete Drainage | Not on List | 10 | Each | 31.13 | 311.3 | Concrete Drainage | 2018-11-19 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | Concrete Drainage | Not on List | 12 | Each | 31.13 | 373.56 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2018-11-19 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8697-001024 | 8697 | 2018-11-05 12:59 | Section 4 | Material | NULL | Not on List | 1 | Each | 50 | 50 | Concrete Drainage | 2018-11-19 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-8883-001024 | 8883 | 2018-11-08 12:42 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 16 | Each | 110.27 | 1764.32 | Geotextiles | 2018-11-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 604 - Deposition | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8895-001024 | 8895 | 2018-11-08 14:45 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Bags 100 | 22.05 | 66.15 | Small Tools (Consumables) | 2018-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8832-001024 | 8832 | 2018-11-07 14:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1405.35 | 1405.35 | Small Tools (Consumables) | 2018-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8830-001024 | 8830 | 2018-11-07 14:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1565.34 | 1565.34 | PPE | 2018-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.15 | m | 1751.24 | 7267.65 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.15 | m | 2126.99 | 8827.01 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.67 | m | 1751.24 | 8178.29 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 4.67 | m | 2126.99 | 9933.04 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 8.82 | m | 314 | 2769.48 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 8.82 | m | 314 | 2769.48 | Not Sure | 2019-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1340 | 1340 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1340 | 1340 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1100 | 1100 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8846-001024 | 8846 | 2018-11-07 16:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1100 | 1100 | Not Sure | 2018-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 5 | boxes | 63 | 315 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 24 | tubes | 12 | 288 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8962-001024 | 8962 | 2018-11-09 16:01 | Section 4 | Material | Not on List | Not on List | 1 | delivery | 60 | 60 | Not Sure | 2018-11-13 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 200 | Roll | 3.31 | 662 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 50 | Roll | 11.15 | 557.5 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9016-001024 | 9016 | 2018-11-12 10:45 | Section 4 | Material | Not on List | Not on List | 480 | Metre | 0.29 | 139.2 | Concrete Drainage | 2018-11-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5271-00173 | 5271 | 2018-08-17 07:48 | Section 4 | Material | Not on List | Not on List | 1 | ea | 869.95 | 869.95 | Rebar and Mesh | 2018-08-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8910-001024 | 8910 | 2018-11-09 07:24 | Section 4 | Material | Not on List | Not on List | 5 | Each | 86 | 430 | Miscellaneous | 2018-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9059-001024 | 9059 | 2018-11-13 08:55 | Section 3 | Material | Timber | Not on List | 300 | NULL | NULL | 0 | Miscellaneous | 2018-11-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5132-0055 | 5132 | 2018-08-15 10:09 | Section 4 | Material | Not on List | Not on List | 3 | Each | 650 | 1950 | Professional Services | 2018-10-22 | NULL | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9074-001025 | 9074 | 2018-11-13 12:06 | Section 3 | Material | Not on List | Not on List | 4 | No | NULL | 0 | Builders Merchants (General) | 2018-11-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9078-001025 | 9078 | 2018-11-13 12:54 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2018-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9023-001024 | 9023 | 2018-11-12 15:05 | Section 3 | Material | Concrete Drainage | Not on List | 80 | No. | 24 | 1920 | Concrete Drainage | 2018-11-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9078-001025 | 9078 | 2018-11-13 12:54 | Section 4 | Material | Not on List | Not on List | 2 | Each | 159 | 318 | Miscellaneous | 2018-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9091-001025 | 9091 | 2018-11-13 15:59 | Section 3 | Material | Not on List | Not on List | 28 | NULL | NULL | 0 | Miscellaneous | 2018-11-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5190-00117 | 5190 | 2018-08-16 07:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 576.16 | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9059-001024 | 9059 | 2018-11-13 08:55 | Section 3 | Material | NULL | Not on List | 300 | No | 0.95 | 285 | Miscellaneous | 2018-11-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9074-001025 | 9074 | 2018-11-13 12:06 | Section 3 | Material | Not on List | Not on List | 4 | No | 105.04 | 420.16 | Builders Merchants (General) | 2018-11-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Pipe 2.5m (249379) | 9 | Each | 483.27 | 4349 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Socket (249381) | 2 | Each | 579.92 | 1160 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 2 | Each | 579.92 | 1160 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9133-001025 | 9133 | 2018-11-14 12:05 | Section 3 | Material | Not on List | Not on List | 30 | m | NULL | 0 | Miscellaneous | 2018-11-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN06 - ECML Bridge | 1705 - Repairs to Existing Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5239-00148 | 5239 | 2018-08-16 14:33 | Section 4 | Material | Not on List | Not on List | 225 | NULL | 10.66 | 2398.5 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8849-001024 | 8849 | 2018-11-07 17:16 | Section 3 | Material | Not on List | Not on List | 1 | No | 589.18 | 589.18 | Damage Charges | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1714.02 | 1714.02 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 266 | 266 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 4 | Each | 1714.02 | 6856.08 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 4 | Each | 305 | 1220 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 2013.9 | 2013.9 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 305 | 305 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 2013.9 | 2013.9 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 305 | 305 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 1926.68 | 1926.68 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5239-00148 | 5239 | 2018-08-16 14:33 | Section 4 | Material | Not on List | Not on List | 225 | NULL | 6.65 | 1496.25 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 465 | 465 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20458-001025 | 20458 | 2019-07-09 10:00 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21465-001025 | 21465 | 2019-07-26 17:22 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2019-07-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 450Mm X 6M R-Drain Unperf + Coup | 100 | Each | 116.62 | 11662 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21488-001025 | 21488 | 2019-07-29 10:00 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Surveying Consumables | 2019-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21219-001025 | 21219 | 2019-07-23 16:32 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21481-001025 | 21481 | 2019-07-29 07:33 | Section 6 | Material | Not on List | Not on List | 2 | No. | 14965 | 29930 | Miscellaneous | 2019-09-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21477-001025 | 21477 | 2019-07-28 15:20 | Section 5 | Material | Twinwall | Not on List | 28 | No | 265.2 | 7425.6 | Plastic Drainage | 2019-08-02 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21477-001025 | 21477 | 2019-07-28 15:20 | Section 5 | Material | Twinwall | Not on List | 28 | NO | 22.36 | 626.08 | Plastic Drainage | 2019-08-02 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21500-001025 | 21500 | 2019-07-29 12:33 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-07-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Not on List | Not on List | 20 | Each | 43.16 | 863.2 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | NULL | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | NULL | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 30 | Each | 8.55 | 257 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 50 | Each | 8.55 | 428 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 50 | Each | 8.55 | 428 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5137-0058 | 5137 | 2018-08-15 10:55 | Section 3 | Material | Plastic Drainage | Not on List | 32 | No | 15.71 | 502.72 | Plastic Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 450Mm Ridgidrain Seal | 100 | Each | 10.04 | 1004 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Respirator Disposable 3m 8833 Ffp3 Valved Box Of 10 (292498) | 3 | Each | 33.81 | 101 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21501-001025 | 21501 | 2019-07-29 08:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | NULL | 0 | PPE | 2019-08-01 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21381-001025 | 21381 | 2019-07-25 17:15 | Section 4 | Material | Not on List | Not on List | 110 | EA | 16.83 | 1851.3 | NULL | 2019-08-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21508-001025 | 21508 | 2019-07-29 14:13 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21490-001025 | 21490 | 2019-07-29 10:58 | Section 5 | Material | Combined Drainage | Not on List | 4 | No | 96.19 | 384.76 | Plastic Drainage | 2019-07-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21511-001025 | 21511 | 2019-07-29 14:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Concrete Drainage | Cpm 1050 Slab 600X600 Access | 27 | Each | 47.04 | 1270.08 | Concrete Accessories | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21524-001025 | 21524 | 2019-07-29 16:50 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 656 | 656 | PPE | 2019-07-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21027-001025 | 21027 | 2019-07-19 08:40 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21541-001025 | 21541 | 2019-07-30 09:55 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21379-001025 | 21379 | 2019-07-25 16:45 | Section 4 | Material | Not on List | Not on List | 35 | EA | 51 | 1785 | Miscellaneous | 2019-08-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21379-001025 | 21379 | 2019-07-25 16:45 | Section 4 | Material | Not on List | Not on List | 2 | EA | 139 | 278 | Miscellaneous | 2019-08-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21379-001025 | 21379 | 2019-07-25 16:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 2202.5 | 2202.5 | Miscellaneous | 2019-08-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21379-001025 | 21379 | 2019-07-25 16:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 650 | 650 | Miscellaneous | 2019-08-08 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19493-001025 | 19493 | 2019-06-21 10:30 | Core | Material | Not on List | Not on List | 1 | ea | 947.85 | 948 | Office Supplies | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 500Mm X 6M R-Drain Unperf + Coup | 45 | Each | 149.45 | 6725.25 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21479-001025 | 21479 | 2019-07-29 07:30 | Section 4 | Material | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 240 | Each | 4.42 | 1060.8 | NULL | 2019-08-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21558-001025 | 21558 | 2019-07-30 13:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1021.63 | 1022 | Small Tools (Consumables) | 2019-08-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21499-001025 | 21499 | 2019-07-29 12:31 | Section 5 | Material | Not on List | Not on List | 1 | EA | 95 | 95 | Not Sure | 2019-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | No - Pass Back | Req - S5 Buyers
MREQ-21561-001025 | 21561 | 2019-07-30 13:45 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21568-001025 | 21568 | 2019-07-30 15:34 | Section 5 | Material | PPE, Small Tools and Consumables | Spill Kit Maintenance In Two Wheel Bin Lubetech 120 Litres (534202) | 5 | Each | 195.66 | 978 | Miscellaneous | 2019-08-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21572-001025 | 21572 | 2019-07-30 17:04 | Section 2 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 25 | Each | 10.08 | 252 | Timber Products | 2019-08-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21579-001025 | 21579 | 2019-07-31 06:45 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Accessories | 2019-08-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | Req - S2 Buyers
MREQ-21554-001025 | 21554 | 2019-07-30 12:30 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 1 | Each | 55.41 | 55.41 | Concrete Drainage | 2019-08-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Concrete Drainage | Cpm 1200X1000 C/W Steps | 10 | Each | 81.96 | 819.6 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21554-001025 | 21554 | 2019-07-30 12:30 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 1 | Each | 82.45 | 82.45 | Concrete Drainage | 2019-08-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21591-001025 | 21591 | 2019-07-31 08:59 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 211.44 | 211 | Small Tools (Consumables) | 2019-08-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19842-001025 | 19842 | 2019-06-27 11:33 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21615-001025 | 21615 | 2019-07-31 14:25 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | number | NULL | 0 | Small Tools (Consumables) | 2019-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1705 - Repairs to Existing Concrete | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 500Mm Ridgidrain Seal | 75 | Each | 15.19 | 1139.25 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21615-001025 | 21615 | 2019-07-31 14:25 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | number | NULL | 0 | Small Tools (Consumables) | 2019-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1705 - Repairs to Existing Concrete | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-21613-001025 | 21613 | 2019-07-31 13:59 | Section 5 | Material | PPE, Small Tools and Consumables | NULL | 1 | EA | 25.4 | 25.4 | Miscellaneous | 2019-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21613-001025 | 21613 | 2019-07-31 13:59 | Section 5 | Material | PPE, Small Tools and Consumables | NULL | 2 | EA | 53.16 | 106.32 | PPE | 2019-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21520-001025 | 21520 | 2019-07-29 15:42 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 2 | Each | 241.48 | 482.96 | Concrete Drainage | 2019-08-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21520-001025 | 21520 | 2019-07-29 15:42 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 4 | Each | 48.92 | 195.68 | Concrete Drainage | 2019-08-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21520-001025 | 21520 | 2019-07-29 15:42 | Section 3 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 2 | Each | 313.2 | 626.4 | Plastic Drainage | 2019-08-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21464-001025 | 21464 | 2019-07-26 17:03 | Section 3 | Material | Combined Drainage | Kerb Drain 405 Channel 1000mm (947299) | 182 | 7717344434 | 35.59 | 6477.38 | Concrete Drainage | 2019-07-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21464-001025 | 21464 | 2019-07-26 17:03 | Section 3 | Material | Kerbs | Not on List | 1 | 7717344434 | 39.22 | 39.22 | Concrete Drainage | 2019-07-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21464-001025 | 21464 | 2019-07-26 17:03 | Section 3 | Material | Not on List | Not on List | 5 | 7717344434 | 243.87 | 1219.35 | Concrete Drainage | 2019-07-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Not on List | Not on List | 6 | Each | 59.17 | 355.02 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21648-001025 | 21648 | 2019-08-01 06:20 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 77.5 | 155 | Small Tools (Consumables) | 2019-08-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21648-001025 | 21648 | 2019-08-01 06:20 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 51.93 | 104 | Small Tools (Consumables) | 2019-08-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21648-001025 | 21648 | 2019-08-01 06:20 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 0.68 | 7 | Miscellaneous | 2019-08-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-21649-001025 | 21649 | 2019-08-01 06:36 | Core | Material | PPE, Small Tools and Consumables | Not on List | 36 | NULL | 2.5 | 90 | Surveying Consumables | 2019-08-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 600Mm X 6M R-Drain Unperf + Coup | 30 | Each | 166.43 | 4992.9 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21641-001025 | 21641 | 2019-07-31 17:24 | Section 5 | Material | Concrete Drainage | Not on List | 3 | EA | 318.91 | 956.73 | Concrete Drainage | 2019-08-01 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21641-001025 | 21641 | 2019-07-31 17:24 | Section 5 | Material | Concrete Drainage | Not on List | 1 | EA | 24.09 | 24.09 | Concrete Drainage | 2019-08-01 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21673-001025 | 21673 | 2019-08-01 11:40 | Section 1 | Material | Geotextile | Not on List | 12 | packs | 39.5 | 474 | Geotextiles | 2019-08-05 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-21680-001025 | 21680 | 2019-08-01 13:02 | Core | Material | Not on List | Not on List | 1 | NULL | 1072.2 | 1072 | Miscellaneous | 2019-08-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-21685-001025 | 21685 | 2019-08-01 15:44 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 210 | 210 | Office Supplies | 2019-08-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21685-001025 | 21685 | 2019-08-01 15:44 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 120 | 120 | Office Supplies | 2019-08-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Not on List | Not on List | 2 | Each | 61.48 | 122.96 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5559-00362 | 5559 | 2018-08-23 08:47 | Section 4 | Material | Plastic Drainage | P/Pipe 600Mm Ridgidrain Seal | 50 | Each | 20.71 | 1035.5 | Plastic Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21691-001025 | 21691 | 2019-08-01 10:19 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21643-001025 | 21643 | 2019-07-31 16:28 | Section 5 | Material | Not on List | Not on List | 3.864 | TON | 538 | 2078.83 | Rebar and Mesh | 2019-08-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21710-001025 | 21710 | 2019-08-02 07:29 | Section 4 | Material | Not on List | Not on List | 1 | SM | 11149.86 | 11149.86 | Miscellaneous | 2019-08-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21682-001025 | 21682 | 2019-08-01 14:13 | Section 4 | Material | Bagged | Sharp Sand Bulk Bag (938208) | 5 | Each | 33.55 | 167.75 | Aggregate | NULL | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5560-00381 | 5560 | 2018-08-23 09:52 | Section 4 | Material | Not on List | Not on List | 4 | Each | 53.01 | 212.04 | Concrete Drainage | 2018-08-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18957-001025 | 18957 | 2019-06-12 09:04 | Core | Material | Not on List | Not on List | 1 | NULL | 11040 | 11040 | Miscellaneous | 2019-06-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Finance Approval | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13278-001025 | 13278 | 2019-02-28 15:28 | Core | Material | Not on List | Not on List | 8 | ea | 7.76 | 677 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13278-001025 | 13278 | 2019-02-28 15:28 | Core | Material | Not on List | Not on List | 8 | ea | 18.54 | 677 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13278-001025 | 13278 | 2019-02-28 15:28 | Core | Material | Not on List | Not on List | 8 | ea | 1.89 | 677 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13417-001025 | 13417 | 2019-03-04 15:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | 533.46 | NULL | 0 | Small Tools (Consumables) | 2019-03-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13575-001025 | 13575 | 2019-03-06 15:43 | Section 2 | Material | Not on List | Not on List | 10 | each | NULL | 0 | Concrete Accessories | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-5745-00455 | 5745 | 2018-08-29 11:33 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 395 | 1580 | Miscellaneous | 2018-09-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-13474-001025 | 13474 | 2019-03-05 11:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 134.99 | each | 1 | 134.99 | Small Tools (Consumables) | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11135-001025 | 11135 | 2019-01-17 14:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 779 | 779 | Not Sure | 2019-01-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | pair | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 1 | Pallet | 24.32 | 24 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 150 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13582-001025 | 13582 | 2019-03-06 14:15 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5753-00459 | 5753 | 2018-08-29 13:27 | Section 4 | Material | Not on List | Not on List | 10000 | NULL | NULL | 0 | Concrete Accessories | 2018-09-05 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5122-0045 | 5122 | 2018-08-15 09:11 | Section 4 | Material | Not on List | NULL | 4 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5748-00456 | 5748 | 2018-08-29 11:34 | Section 3 | Material | Waste Management | Dry Mixed Recycling - Wheelie Bin 1100 Litre | 200 | Each | 7 | 1400 | Waste (Recycling) | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5748-00456 | 5748 | 2018-08-29 11:34 | Section 3 | Material | Waste Management | Not on List | 200 | NULL | 14.25 | 2850 | Waste (Recycling) | 2018-08-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5748-00456 | 5748 | 2018-08-29 11:34 | Section 3 | Material | Waste Management | Food Waste - Wheelie Bin 240 Litre | 140 | Each | 10 | 1400 | Waste (Recycling) | 2018-08-31 | Gate D - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13552-001025 | 13552 | 2019-03-06 12:21 | Section 2 | Material | Not on List | Not on List | 20 | number | NULL | 0 | Concrete Accessories | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 5 | EA | 250.9 | 1254.5 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 2 | EA | 250.9 | 501.8 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 3 | EA | 250.9 | 752.7 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 250.9 | 250.9 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 10 | EA | 49.5 | 495 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 1 | BAG | 409 | 409 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 625 | 625 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13526-001025 | 13526 | 2019-03-06 08:45 | Section 4 | Material | Not on List | Not on List | 4 | EA | 650 | 2600 | Miscellaneous | 2019-03-18 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13640-001025 | 13640 | 2019-03-08 08:40 | Section 2 | Material | Not on List | Not on List | 6.798 | ton | NULL | 0 | NULL | 2019-03-18 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13623-001025 | 13623 | 2019-03-07 16:07 | Section 2 | Material | Not on List | Not on List | 59.726 | tonnes | NULL | 0 | NULL | 2019-03-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13349-001025 | 13349 | 2019-03-01 14:29 | Section 2 | Material | Not on List | Not on List | 4550 | Units | NULL | 0 | Concrete Accessories | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13349-001025 | 13349 | 2019-03-01 14:29 | Section 2 | Material | Not on List | Not on List | 390 | Units | NULL | 0 | Concrete Accessories | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13638-001025 | 13638 | 2019-03-08 08:23 | Section 5 | Material | Not on List | Not on List | 40 | kg | 0 | 0 | Builders Merchants (General) | 2019-03-09 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13725-001025 | 13725 | 2019-03-11 07:24 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-13495-001025 | 13495 | 2019-03-05 12:11 | Section 5 | Material | Not on List | Not on List | 24 | kg | NULL | 0 | Builders Merchants (General) | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13495-001025 | 13495 | 2019-03-05 12:11 | Section 5 | Material | Not on List | Not on List | 3 | LITRE | NULL | 0 | Builders Merchants (General) | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13495-001025 | 13495 | 2019-03-05 12:11 | Section 5 | Material | Not on List | Not on List | 3200 | kg | NULL | 0 | Builders Merchants (General) | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13633-001025 | 13633 | 2019-03-08 07:35 | Section 4 | Material | Not on List | Not on List | 1000 | NULL | NULL | 0 | Miscellaneous | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12152-001025 | 12152 | 2019-02-08 12:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 750 | 750 | Builders Merchants (General) | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13759-001025 | 13759 | 2019-03-11 10:57 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 75 | 75 | Damage Charges | 2019-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13644-001025 | 13644 | 2019-03-08 09:11 | Section 4 | Material | Not on List | Not on List | 10 | Each | 42.31 | 423.1 | Miscellaneous | 2019-03-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5041-0026 | 5041 | 2018-08-14 10:19 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 2181 | 0 | Office Supplies | 2018-09-06 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13448-001025 | 13448 | 2019-03-05 06:53 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 0.9 | 900 | Miscellaneous | 2019-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13764-001025 | 13764 | 2019-03-11 11:32 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 6.35 | 127 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 6.35 | 127 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 6.35 | 127 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 6.35 | 127 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | EACH | 1.78 | 89 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | EACH | 3.84 | 153.6 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | 1.94 | 29.1 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5562-00389 | 5562 | 2018-08-23 10:51 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 98 | 98 | Damage Charges | 2018-08-28 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | 1.65 | 24.75 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | 4.42 | 44.2 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | 3.64 | 36.4 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | EACH | 0.89 | 35.6 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 7.67 | 153.4 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | EACH | 1.91 | 76.4 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | 44.95 | 449.5 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | 7.54 | 75.4 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | EACH | 10 | 100 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 0 | EACH | NULL | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5791-00472 | 5791 | 2018-08-30 08:44 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Geotextiles | 2018-09-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Commercial - Rejected | NULL | No - Reject | REQ - Section 4 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | 0.81 | 12.15 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | 1.2 | 24 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | EACH | 9.99 | 49.95 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | 10.83 | 0 | 0 | Miscellaneous | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | NULL | 2440x1220x18mm Shuttering Ply (683573) | 100 | EACH | 25.78 | 2578 | Miscellaneous | 2019-03-11 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13524-001025 | 13524 | 2019-03-06 07:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | EACH | 0.83 | 83 | Concrete Accessories | 2019-03-08 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13765-001025 | 13765 | 2019-03-11 11:39 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13664-001025 | 13664 | 2019-03-08 11:45 | Section 3 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 108 | Each | 3.56 | 384.48 | Builders Merchants (General) | 2019-03-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 5 | No. | 20 | 100 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-13673-001025 | 13673 | 2019-03-08 13:17 | Section 3 | Material | NULL | Not on List | 5 | T | 32.74 | 163.7 | Builders Merchants (General) | 2019-03-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13772-001025 | 13772 | 2019-03-11 12:04 | Core | Material | Not on List | Not on List | 1 | NUMBER | 46588.5 | 46589 | Miscellaneous | 2019-03-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-13576-001025 | 13576 | 2019-03-06 15:45 | Section 2 | Material | NULL | Not on List | 8 | 30Kg Packs | NULL | 0 | Miscellaneous | 2019-03-13 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13527-001025 | 13527 | 2019-03-06 09:06 | Section 3 | Material | Not on List | Not on List | 14 | no | 32 | 448 | Small Tools (Consumables) | 2019-03-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 10 | boxes | 9 | 90 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-13670-001025 | 13670 | 2019-03-08 13:10 | Section 4 | Material | Not on List | Not on List | 400 | Each | 5.34 | 2136 | Plastic Drainage | 2019-03-14 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13466-001025 | 13466 | 2019-03-05 10:36 | Section 4 | Material | Not on List | Not on List | 20 | Each | 85.23 | 1704.6 | Concrete Drainage | 2019-03-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13466-001025 | 13466 | 2019-03-05 10:36 | Section 4 | Material | Not on List | Not on List | 6 | Each | 63.93 | 383.58 | Concrete Drainage | 2019-03-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13466-001025 | 13466 | 2019-03-05 10:36 | Section 4 | Material | Not on List | Not on List | 5 | Each | 55.13 | 275.65 | Concrete Drainage | 2019-03-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13466-001025 | 13466 | 2019-03-05 10:36 | Section 4 | Material | Not on List | Not on List | 10 | Each | 61.53 | 615.3 | Concrete Drainage | 2019-03-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 10 | Packs | 10.5 | 105 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | Not on List | Not on List | 30 | Each | 6.2 | 186 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | Not on List | Not on List | 20 | Each | 17.9 | 358 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | Not on List | Not on List | 10 | Each | 88 | 880 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | Not on List | Not on List | 10 | Each | 6.35 | 63.5 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | Not on List | Not on List | 10 | Each | 6.35 | 63.5 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13469-001025 | 13469 | 2019-03-05 11:00 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2019-03-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13568-001025 | 13568 | 2019-03-06 08:39 | Section 3 | Material | NULL | Not on List | 22 | No | 62.58 | 1376.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13605-001025 | 13605 | 2019-03-06 18:32 | Section 4 | Material | Not on List | Not on List | 1 | Each | 6108.88 | 6108.88 | Miscellaneous | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 220 | No | 22.84 | 5024.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 10 | Packs | 10.5 | 105 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 200 | No | 24 | 4800 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 30 | No | 60.46 | 1813.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 4 | No | 35.96 | 143.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 4 | No | 35.96 | 143.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 4 | No | 7.68 | 30.72 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 4 | No | 7.68 | 30.72 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 1 | No | 282.24 | 282.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 1 | No | 359.42 | 359.42 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-15603-001025 | 15603 | 2019-04-10 13:20 | Section 2 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 100 | Each | 16.49 | 1649 | Concrete Drainage | 2019-04-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15610-001025 | 15610 | 2019-04-10 13:43 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-04-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15512-001025 | 15512 | 2019-04-09 09:37 | Section 3 | Material | Not on List | Not on List | 1 | No | 7175 | 7175 | Flow Control | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15512-001025 | 15512 | 2019-04-09 09:37 | Section 3 | Material | Not on List | Not on List | 4 | No | 6960 | 27840 | Flow Control | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15512-001025 | 15512 | 2019-04-09 09:37 | Section 3 | Material | Not on List | Not on List | 2 | No | 4758 | 9516 | Flow Control | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15512-001025 | 15512 | 2019-04-09 09:37 | Section 3 | Material | Not on List | Not on List | 7 | No | 982 | 6874 | Flow Control | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15512-001025 | 15512 | 2019-04-09 09:37 | Section 3 | Material | Not on List | Not on List | 7 | No | 787 | 5509 | Flow Control | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15398-001025 | 15398 | 2019-04-05 15:16 | Section 2 | Material | NULL | Not on List | 26 | number | NULL | 0 | Ductile Drainage | 2019-04-10 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15398-001025 | 15398 | 2019-04-05 15:16 | Section 2 | Material | PPE, Small Tools and Consumables | Polythene Pifa Dpm 250 Micron Black Regr/Vir 4x25m 6/8 (606095) | 2 | Each | 59 | 118 | Miscellaneous | 2019-04-10 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15135-001025 | 15135 | 2019-04-02 14:25 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-6076-00609 | 6076 | 2018-09-05 13:29 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-09-05 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Trowel Plastering Spartan Pro 275mm X 113mm (11" X 4 1/2 (767506) | 10 | Each | 6.88 | 69 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Headtorch 3 Led Bulb C/W 3 X Lr03/Aaa Batts Spartan Pro (740434) | 15 | Each | 9.34 | 140 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15551-001025 | 15551 | 2019-04-09 15:57 | Section 2 | Material | NULL | 454x454x100 D400 Watershed GG&F (257790) | 25 | Each | 63.84 | 1596 | Ductile Drainage | 2019-04-16 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15551-001025 | 15551 | 2019-04-09 15:57 | Section 2 | Material | NULL | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-04-16 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 150 | Each | 3.04 | 456 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Cones Blue 750mm - No Sleeve Csp (204013) | 100 | Each | 6.9 | 690 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Sign Plastic 600x200m-warning High Voltage Cables Overhead (249677) | 10 | Each | 11.88 | 119 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycottn En471cl1 Saturn Regular Ct01-y (302019) | 5 | Each | 13 | 65 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycottn En471cl1 Saturn Regular Ct01-y (302019) | 5 | Each | 13 | 65 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Jacket 321136 Keepsafe Yellow Bomber C/W A14 Logos (13047) | 3 | Each | 13.4 | 40 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Jacket 321136 Keepsafe Yellow Bomber C/W A14 Logos (13047) | 3 | Each | 13.4 | 40 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Jacket 321136 Keepsafe Yellow Bomber C/W A14 Logos (13047) | 3 | Each | 13.4 | 40 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Coverall Flame Retardent Cotton Saturn Fr Reflective Tape (370522) | 3 | Each | 107.6 | 323 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Coverall Flame Retardent Cotton Saturn Fr Reflective Tape (370522) | 3 | Each | 107.6 | 323 | PPE | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15624-001025 | 15624 | 2019-04-10 11:33 | Section 5 | Material | PPE, Small Tools and Consumables | Keep Safe First Aid Kit - Burns Dispenser Kit (254960) | 10 | Each | 11.64 | 116 | Small Tools (Consumables) | 2019-04-12 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15601-001025 | 15601 | 2019-04-10 12:24 | Section 2 | Material | Not on List | Not on List | 12 | NULL | 150 | 1800 | Miscellaneous | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1503 - Cables, Joints & Terminations | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15588-001025 | 15588 | 2019-04-10 09:17 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | 350 | 1400 | Laboratory Equipment / Certification | 2019-04-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15646-001025 | 15646 | 2019-04-10 17:52 | Section 5 | Material | Not on List | Not on List | 7 | NULL | 150 | 1050 | Miscellaneous | 2019-05-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1503 - Cables, Joints & Terminations | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15589-001025 | 15589 | 2019-04-10 09:34 | Section 4 | Material | Not on List | Not on List | 80 | NULL | 13.95 | 1116 | Concrete Accessories | 2019-04-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15636-001025 | 15636 | 2019-04-10 16:54 | Section 4 | Material | NULL | Building Sand Bulk Bag (938155) | 5 | Each | 33.55 | 167.75 | Aggregate | 2019-04-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15149-001025 | 15149 | 2019-04-02 15:20 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 2710.29 | 2710.29 | Miscellaneous | 2019-04-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-15446-001025 | 15446 | 2019-04-08 12:25 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-04-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15439-001025 | 15439 | 2019-04-08 09:24 | Section 4 | Material | Not on List | Not on List | 5000 | Each | 1 | 5000 | Miscellaneous | 2019-04-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15444-001025 | 15444 | 2019-04-08 12:20 | Core | Material | Not on List | Not on List | 1 | number | 973 | 973 | Office Supplies | 2019-04-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15541-001025 | 15541 | 2019-04-09 14:48 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | each | 130 | 520 | Surveying Consumables | 2019-04-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 12 | No. | 74.74 | 896.88 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 6 | No. | 19.61 | 117.66 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 36 | No. | 20.68 | 744.48 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6089-00611 | 6089 | 2018-09-05 13:52 | Section 3 | Material | Not on List | Not on List | 20 | EA | 284.69 | 5693.8 | Miscellaneous | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 72 | No. | 3.15 | 226.8 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 6 | No. | 29.09 | 174.54 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 180 | No. | 1.55 | 279 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 6 | No. | 29.09 | 174.54 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 10 | No. | 17.03 | 170.3 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 2 | No. | 17.03 | 34.06 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15539-001025 | 15539 | 2019-04-09 14:06 | Section 5 | Material | Not on List | Not on List | 10 | No. | 15.15 | 151.5 | Builders Merchants (General) | 2019-04-23 | Fisheries Access - 1350308 - Jcn 32 Off Slip, A14 Eastbound | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15476-001025 | 15476 | 2019-04-08 16:17 | Section 4 | Material | Not on List | Not on List | 18 | Each | 17.9 | 322.2 | Surveying Consumables | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15476-001025 | 15476 | 2019-04-08 16:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 45 | 45 | Surveying Consumables | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6085-00610 | 6085 | 2018-09-05 14:49 | Section 3 | Material | Not on List | Not on List | 1 | no. | 1437.42 | 1437.42 | Miscellaneous | 2018-09-07 | Gate D - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15597-001025 | 15597 | 2019-04-10 10:38 | Section 4 | Material | Waste Management | Plastic - Roll On Roll Off 40 cubic yard | 1 | Each | 360 | 360 | Waste (General) | 2019-04-22 | RVP 426 - Robins Lane A14 Eastbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15251-001025 | 15251 | 2019-04-04 06:28 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 40 cubic yard | 1 | Each | 370 | 370 | Waste (General) | 2019-04-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15471-001025 | 15471 | 2019-04-08 15:32 | Core | Material | Not on List | Not on List | 2 | number | 40 | 80 | Surveying Consumables | 2019-04-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15518-001025 | 15518 | 2019-04-09 09:55 | Section 3 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 2.97 | 166.32 | Builders Merchants (General) | 2019-04-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15518-001025 | 15518 | 2019-04-09 09:55 | Section 3 | Material | Not on List | Not on List | 100 | No | 6.38 | 638 | Plastic Drainage | 2019-04-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15518-001025 | 15518 | 2019-04-09 09:55 | Section 3 | Material | Not on List | Not on List | 50 | No | 0.35 | 17.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15518-001025 | 15518 | 2019-04-09 09:55 | Section 3 | Material | Not on List | Not on List | 60 | No | 1.98 | 118.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15449-001025 | 15449 | 2019-04-08 12:51 | Core | Material | Not on List | Not on List | 1 | NULL | 34.95 | 35 | Miscellaneous | 2019-04-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15517-001025 | 15517 | 2019-04-09 10:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 536.28 | 536.28 | Small Tools (Consumables) | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6057-00604 | 6057 | 2018-09-05 09:33 | Section 3 | Material | Not on List | Not on List | 1 | Activity | 10000 | 10000 | Concrete Drainage | 2018-09-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6111-00612 | 6111 | 2018-09-05 18:45 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 581.84 | 581.84 | PPE | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15202-001025 | 15202 | 2019-04-03 10:56 | Section 4 | Material | Not on List | Not on List | 1 | Each | 86.2 | 86.2 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15634-001025 | 15634 | 2019-04-10 16:41 | Section 4 | Material | Not on List | Not on List | 30 | NULL | 189 | 5670 | Plastic Drainage | 2019-04-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15634-001025 | 15634 | 2019-04-10 16:41 | Section 4 | Material | Not on List | Not on List | 40 | NULL | 2.38 | 95.2 | Plastic Drainage | 2019-04-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15290-001025 | 15290 | 2019-04-04 12:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1049.59 | 1049.59 | Miscellaneous | 2019-04-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6111-00612 | 6111 | 2018-09-05 18:45 | Section 3 | Material | Misc | Not on List | 1 | EA | 52.8 | 52.8 | Miscellaneous | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | Not on List | Not on List | 100 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | Not on List | Not on List | 50 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 48 | Each | 6.82 | 327 | Timber Products | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15686-001025 | 15686 | 2019-04-11 12:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-6133-00619 | 6133 | 2018-09-06 11:30 | Section 3 | Material | Not on List | Not on List | 200 | ea | 12.81 | 2562 | Miscellaneous | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-15631-001025 | 15631 | 2019-04-10 16:32 | Section 3 | Material | Not on List | Not on List | 50 | No | 1.2 | 60 | Miscellaneous | 2019-04-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15672-001025 | 15672 | 2019-04-11 10:33 | Section 2 | Material | NULL | Polypipe 125mm x 6m Black Ridgiduct (877724) | 2 | Each | 20.32 | 40.64 | Plastic Drainage | 2019-04-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15672-001025 | 15672 | 2019-04-11 10:33 | Section 2 | Material | NULL | Not on List | 12 | Each | 28.46 | 341.52 | Plastic Drainage | 2019-04-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15622-001025 | 15622 | 2019-04-10 15:12 | Section 3 | Material | Not on List | Not on List | 1 | ea | 558.09 | 558.09 | Small Tools (Consumables) | 2019-04-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15622-001025 | 15622 | 2019-04-10 15:12 | Section 3 | Material | Not on List | Not on List | 1 | ea | 1303.6 | 1303.6 | PPE | 2019-04-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15622-001025 | 15622 | 2019-04-10 15:12 | Section 3 | Material | Not on List | Not on List | 1 | ea | 57.68 | 57.68 | Janitorial | 2019-04-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15724-001025 | 15724 | 2019-04-11 17:21 | Section 5 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 2701 - Accommodation works | Stores - Closed | Yes - Approve | NULL | Req - S5 Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 4 | number | 18.91 | 75.64 | Not Sure | 2018-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15731-001025 | 15731 | 2019-04-12 07:09 | Section 4 | Material | NULL | NULL | 1 | NULL | 31197.22 | 31197.22 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 216 | ea | 45 | 9720 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 1 | ea | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 1 | ea | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 2 | number | 28.55 | 57.1 | Not Sure | 2018-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 4 | ea | 55 | 220 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 4 | ea | 55 | 220 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 1 | ea | 45 | 45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 1 | ea | 45 | 45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 40 | ea | 13 | 520 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 24 | ea | 8 | 192 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15754-001025 | 15754 | 2019-04-12 11:31 | Section 4 | Material | Not on List | Not on List | 1 | ea | 35 | 35 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-15755-001025 | 15755 | 2019-04-12 11:36 | Section 2 | Material | Not on List | Not on List | 10 | number | NULL | 0 | Miscellaneous | 2019-04-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-15755-001025 | 15755 | 2019-04-12 11:36 | Section 2 | Material | Not on List | Not on List | 70 | number | NULL | 0 | Miscellaneous | 2019-04-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 1 | number | 50 | 50 | Not Sure | 2018-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15755-001025 | 15755 | 2019-04-12 11:36 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Miscellaneous | 2019-04-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 40 | number | 20.82 | 832.8 | Not Sure | 2018-09-10 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15608-001025 | 15608 | 2019-04-10 09:15 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Builders Merchants (General) | 2019-04-15 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 45 | number | 5.25 | 236.25 | Not Sure | 2018-09-10 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15744-001025 | 15744 | 2019-04-12 09:04 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 78.4 | 156.8 | Miscellaneous | 2019-04-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15753-001025 | 15753 | 2019-04-12 11:39 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 290.3 | 290.3 | Small Tools (Consumables) | 2019-04-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15592-001025 | 15592 | 2019-04-10 09:36 | Section 4 | Material | Not on List | Not on List | 2 | Number | 22.24 | 44.48 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15592-001025 | 15592 | 2019-04-10 09:36 | Section 4 | Material | Not on List | Not on List | 2 | Number | 59.05 | 118.1 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15592-001025 | 15592 | 2019-04-10 09:36 | Section 4 | Material | Not on List | Not on List | 2 | Number | 64.9 | 129.8 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15836-001025 | 15836 | 2019-04-15 10:08 | Section 3 | Material | Not on List | Not on List | 2 | No sets | NULL | 0 | Builders Merchants (General) | 2019-04-17 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15831-001025 | 15831 | 2019-04-15 09:28 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 6 | Each | 122.72 | 736.32 | Geotextiles | 2019-04-17 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3B - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15097-001025 | 15097 | 2019-04-02 09:01 | Core | Material | Not on List | Not on List | 1 | EACH | 726 | 726 | Miscellaneous | 2019-04-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Finance Approval | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6024-00598 | 6024 | 2018-09-04 14:10 | Section 4 | Material | Not on List | Not on List | 80 | number | 0.55 | 44 | Not Sure | 2018-09-10 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15683-001025 | 15683 | 2019-04-11 12:41 | Core | Material | Not on List | Not on List | 1 | number | 15856.68 | 15856.68 | Professional Services | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15683-001025 | 15683 | 2019-04-11 12:41 | Core | Material | Not on List | Not on List | 1 | number | 4910.8 | 4910.8 | Professional Services | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 107 - Fee based costs including insurance | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15683-001025 | 15683 | 2019-04-11 12:41 | Core | Material | Not on List | Not on List | 1 | number | 9260.56 | 9260.56 | Professional Services | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 107 - Fee based costs including insurance | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6008-00594 | 6008 | 2018-09-04 08:14 | Section 3 | Material | Not on List | Not on List | 6 | Rolls | 258.05 | 1548.3 | Not Sure | 2018-09-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15847-001025 | 15847 | 2019-04-15 11:53 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 99.6 | 199 | Surveying Consumables | 2019-04-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15850-001025 | 15850 | 2019-04-15 12:03 | Core | Material | Not on List | Not on List | 4 | NULL | 1249.99 | 5000 | Miscellaneous | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Operations Rejected | No - Reject | NULL | REQ - Buyers
MREQ-27233-001025 | 27233 | 2019-12-03 07:45 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-26359-001025 | 26359 | 2019-11-08 13:39 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27244-001025 | 27244 | 2019-12-03 09:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 26.5 | 133 | Miscellaneous | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27252-001025 | 27252 | 2019-12-03 10:48 | Section 3 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Fixings and Fasteners | 2019-12-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 1201 - Traffic Signs | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-27252-001025 | 27252 | 2019-12-03 10:48 | Section 3 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Fixings and Fasteners | 2019-12-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 1201 - Traffic Signs | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-27254-001025 | 27254 | 2019-12-03 11:00 | Core | Material | Not on List | Not on List | 35 | nUMBER | 275 | 9625 | Surveying Consumables | 2020-01-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | NULL | Yes - Approve | REQ - Buyers
MREQ-27256-001025 | 27256 | 2019-12-03 11:17 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27204-001025 | 27204 | 2019-12-02 13:56 | Section 4 | Material | Not on List | Not on List | 15 | Each | 41.85 | 627.75 | Plastic Drainage | 2019-12-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27262-001025 | 27262 | 2019-12-03 11:34 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27263-001025 | 27263 | 2019-12-03 11:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27266-001025 | 27266 | 2019-12-03 12:04 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27270-001025 | 27270 | 2019-12-03 13:41 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-27273-001025 | 27273 | 2019-12-03 14:18 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-27274-001025 | 27274 | 2019-12-03 14:29 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27247-001025 | 27247 | 2019-12-03 09:42 | Section 4 | Material | NULL | NULL | 1 | Each | 1859.61 | 1859.61 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27248-001025 | 27248 | 2019-12-03 09:49 | Section 4 | Material | NULL | NULL | 40 | Pack 100 | 10.5 | 420 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27248-001025 | 27248 | 2019-12-03 09:49 | Section 4 | Material | NULL | NULL | 120 | Each | 17.9 | 2148 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27248-001025 | 27248 | 2019-12-03 09:49 | Section 4 | Material | NULL | NULL | 500 | Each | 7.5 | 3750 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27229-001025 | 27229 | 2019-12-03 06:52 | Section 6 | Material | Timber | Not on List | 10 | Lengths | 10.68 | 106.8 | Timber Products | 2019-12-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27229-001025 | 27229 | 2019-12-03 06:52 | Section 6 | Material | Timber | Not on List | 10 | Lengths | 7.23 | 72.3 | Timber Products | 2019-12-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 74 | Each | 36.9 | 2730.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 4 | Each | 124.86 | 499.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 6 | Each | 42.5 | 255 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 2 | Each | 17.5 | 35 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 6 | Each | 21.23 | 127.38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 40 | Each | 13.08 | 523.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 7 | Each | 126.04 | 882.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 2 | Each | 59.45 | 118.9 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 1 | Each | 80 | 80 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 1 | Each | 272.25 | 272.25 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27181-001025 | 27181 | 2019-12-01 21:03 | Section 5 | Material | NULL | NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-10 | 1358009 - EB5/4, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27272-001025 | 27272 | 2019-12-03 13:46 | Section 4 | Material | Not on List | Not on List | 32 | Each | 14.29 | 457.28 | Builders Merchants (General) | 2019-12-06 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27049-001025 | 27049 | 2019-11-27 15:12 | Section 3 | Material | Not on List | Not on List | 3 | ea | 40.33 | 120.99 | Miscellaneous | 2019-12-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27049-001025 | 27049 | 2019-11-27 15:12 | Section 3 | Material | Not on List | Not on List | 3 | ea | 36.71 | 110.13 | Miscellaneous | 2019-12-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27297-001025 | 27297 | 2019-12-03 17:37 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27304-001025 | 27304 | 2019-12-04 06:50 | Section 6 | Material | Timber | Not on List | 100 | linier m | NULL | 0 | Timber Products | 2019-12-05 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-26996-001025 | 26996 | 2019-11-26 14:35 | Section 2 | Material | Not on List | Not on List | 3 | ea | 26.25 | 78.75 | Small Tools (Consumables) | 2019-11-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27134-001025 | 27134 | 2019-11-29 09:40 | Section 2 | Material | Not on List | Not on List | 1 | ea | 628 | 628 | Concrete Accessories | 2019-12-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27122-001 | 27122 | 2019-11-29 07:44 | Section 6 | Material | Not on List | Not on List | 5 | Tubs | 36.9 | 184.5 | Builders Merchants (General) | 2019-12-05 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27321-001025 | 27321 | 2019-12-04 11:42 | Core | Material | Not on List | Not on List | 1 | No. | 3000 | 3000 | Miscellaneous | 2019-12-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7264-001021 | 7264 | 2018-10-02 08:56 | Section 3 | Material | Not on List | Not on List | 1 | EA | 836 | 836 | Miscellaneous | 2018-10-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2702 - Works by the Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27152-001025 | 27152 | 2019-11-29 13:47 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27326-001025 | 27326 | 2019-12-04 14:45 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27329-001025 | 27329 | 2019-12-04 15:17 | Section 4 | Material | Aggregate | Type 1 | 1500 | Tonnes | 21.65 | 32475 | Aggregate | 2019-12-05 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27330-001025 | 27330 | 2019-12-04 15:17 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27332-001025 | 27332 | 2019-12-04 15:34 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-27333-001025 | 27333 | 2019-12-04 15:44 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27336-001025 | 27336 | 2019-12-04 16:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26972-001025 | 26972 | 2019-11-26 09:00 | Section 3 | Material | Kerbs | Not on List | 82 | ea | 4.42 | 362.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-11-28 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | BN10 - A1198 Ermine Street Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7318-001022 | 7318 | 2018-10-02 18:07 | Section 3 | Material | Not on List | Not on List | 5 | number | 33.15 | 165.75 | Concrete Accessories | 2018-10-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN07 - B1043 Offord Road Overbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27339-001025 | 27339 | 2019-12-04 16:21 | Section 4 | Material | Aggregate | Not on List | 600000 | tons | 5 | 3000000 | Aggregate | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-27129-001025 | 27129 | 2019-11-29 08:59 | Section 2 | Material | Not on List | Not on List | 2 | ea | 182.9 | 365.8 | Miscellaneous | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27129-001025 | 27129 | 2019-11-29 08:59 | Section 2 | Material | Not on List | Not on List | 2 | ea | 182.9 | 365.8 | Miscellaneous | 2019-12-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27328-001025 | 27328 | 2019-12-04 15:13 | Section 2 | Material | Not on List | Not on List | 3 | No. | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1201 - Traffic Signs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7357-001022 | 7357 | 2018-10-03 15:55 | Section 4 | Material | Not on List | Not on List | 1 | Each | 679.03 | 679.03 | Damage Charges | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27340-001025 | 27340 | 2019-12-04 16:36 | Section 2 | Material | Not on List | Not on List | 15 | Tins | 19.51 | 292.65 | Concrete Accessories | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27370-001025 | 27370 | 2019-12-05 09:25 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-27371-001025 | 27371 | 2019-12-05 09:35 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27376-001025 | 27376 | 2019-12-05 11:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 276.09 | 276 | Small Tools (Consumables) | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27386-001025 | 27386 | 2019-12-05 14:17 | Section 2 | Material | Not on List | Not on List | 2 | each | 81.8 | 164 | Laboratory Equipment / Certification | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27389-001025 | 27389 | 2019-12-05 15:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | EACH | 466.01 | 466 | PPE | 2019-12-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7353-001022 | 7353 | 2018-10-03 12:30 | Section 4 | Material | NULL | Not on List | 1280 | Each | 4.16 | 5324.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-08 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-26159-001025 | 26159 | 2019-11-05 14:53 | Core | Material | NULL | NULL | 1 | Each | 606 | 606 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27392-001025 | 27392 | 2019-12-05 15:39 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3778.79 | Each | 1 | 3779 | PPE | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27234-001025 | 27234 | 2019-12-03 07:57 | Section 2 | Material | Not on List | Not on List | 6 | no. | 1050.83 | 6304.98 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27179-001025 | 27179 | 2019-12-01 16:08 | Section 5 | Material | NULL | NULL | 48 | Each | 0.21 | 10.08 | Fixings and Fasteners | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27179-001025 | 27179 | 2019-12-01 16:08 | Section 5 | Material | NULL | NULL | 24 | Each | 0.71 | 17.04 | Fixings and Fasteners | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27179-001025 | 27179 | 2019-12-01 16:08 | Section 5 | Material | NULL | NULL | 48 | Each | 0.76 | 36.48 | Fixings and Fasteners | 2019-12-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27309-001025 | 27309 | 2019-12-04 08:38 | Section 4 | Material | NULL | NULL | 195 | Each | 5.17 | 1008.15 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27309-001025 | 27309 | 2019-12-04 08:38 | Section 4 | Material | NULL | NULL | 32 | Each | 11.68 | 373.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 60 | Each | 241.48 | 14488.8 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 10 | Each | 289.77 | 2897.7 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7353-001022 | 7353 | 2018-10-03 12:30 | Section 4 | Material | NULL | NULL | 4 | Each | 30 | 120 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-08 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 10 | Each | 289.77 | 2897.7 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 6 | Each | 289.77 | 1738.62 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 5 | Each | 294.58 | 1472.9 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 1 | Each | 220.93 | 220.93 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27194-001025 | 27194 | 2019-12-02 10:50 | Section 5 | Material | NULL | NULL | 3 | Each | 317.77 | 953.31 | Concrete Drainage | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27360-001025 | 27360 | 2019-12-05 07:57 | Section 4 | Material | Aggregate | Type 1 | 5000 | Tonnes | 20 | 100000 | Aggregate | 2019-12-09 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27417-001025 | 27417 | 2019-12-06 07:58 | Section 5 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142 | Builders Merchants (General) | 2019-12-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27317-001025 | 27317 | 2019-12-04 09:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 421.1 | each | 1 | 421.1 | Miscellaneous | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27342-001025 | 27342 | 2019-12-04 16:35 | Section 2 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 40 | Each | 10.08 | 403.2 | Builders Merchants (General) | 2019-12-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27342-001025 | 27342 | 2019-12-04 16:35 | Section 2 | Material | Timber | Not on List | 100 | Each | 1.1 | 110 | Builders Merchants (General) | 2019-12-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27342-001025 | 27342 | 2019-12-04 16:35 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | boxes | 14.85 | 29.7 | Builders Merchants (General) | 2019-12-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27312-001025 | 27312 | 2019-12-04 08:51 | Section 3 | Material | Not on List | Not on List | 210 | meters | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27312-001025 | 27312 | 2019-12-04 08:51 | Section 3 | Material | Not on List | Not on List | 2 | no. | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27312-001025 | 27312 | 2019-12-04 08:51 | Section 3 | Material | Not on List | Not on List | 2 | no. | NULL | 0 | Miscellaneous | 2019-12-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27347-001025 | 27347 | 2019-12-04 17:36 | Section 4 | Material | Aggregate | Not on List | 60000 | ton | 5 | 300000 | Aggregate | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27427-001025 | 27427 | 2019-12-06 10:43 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27318-001025 | 27318 | 2019-12-04 10:04 | Section 4 | Material | Not on List | Not on List | 1 | 74 | 1895.21 | 1895.21 | Miscellaneous | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27426-001025 | 27426 | 2019-12-06 09:56 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 3 | Each | 32.74 | 98.22 | Concrete Accessories | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7289-001022 | 7289 | 2018-10-02 14:44 | Section 3 | Material | Not on List | Not on List | 1 | EA | 709.58 | 709.58 | PPE | 2018-10-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27426-001025 | 27426 | 2019-12-06 09:56 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142.4 | Concrete Accessories | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27230-001025 | 27230 | 2019-12-03 07:16 | Section 4 | Material | Not on List | Not on List | 1 | Each | 764.28 | 764.28 | Miscellaneous | 2019-12-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25410-001025 | 25410 | 2019-10-18 15:22 | Section 4 | Material | NULL | NULL | 1 | Each | 369 | 369 | Miscellaneous | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27264-001025 | 27264 | 2019-12-03 11:46 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 162.49 | 162.49 | Miscellaneous | 2019-12-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27430-001025 | 27430 | 2019-12-06 11:28 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-12-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27276-001025 | 27276 | 2019-12-03 14:52 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 2200.56 | 2200.56 | Miscellaneous | 2019-12-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7289-001022 | 7289 | 2018-10-02 14:44 | Section 3 | Material | Not on List | Not on List | 1 | EA | 929.69 | 929.69 | Small Tools (Consumables) | 2018-10-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7322-001022 | 7322 | 2018-10-03 07:30 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4000 | 4000 | Not Sure | 2018-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27441-001025 | 27441 | 2019-12-06 14:06 | Section 2 | Material | Not on List | Not on List | 50 | sets | 3.4 | 170 | Fixings and Fasteners | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7311-001022 | 7311 | 2018-10-02 16:57 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2018-10-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27435-001025 | 27435 | 2019-12-06 13:06 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Number | 40.19 | 40.19 | Small Tools (Consumables) | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27475-001025 | 27475 | 2019-12-09 11:02 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327 | Builders Merchants (General) | 2019-12-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27486-001025 | 27486 | 2019-12-09 13:30 | Core | Material | Not on List | Not on List | 2 | No. | 100 | 200 | Miscellaneous | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27490-001025 | 27490 | 2019-12-09 15:54 | Section 4 | Material | Aggregate | 6G | 25 | Tonnes | 22 | 550 | Aggregate | 2019-12-12 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27362-001025 | 27362 | 2019-12-05 08:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 303.21 | each | 1 | 303.21 | Miscellaneous | 2019-12-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27516-001025 | 27516 | 2019-12-10 08:21 | Core | Material | Not on List | Not on List | 1 | NULL | 3250 | 3250 | Professional Services | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27473-001025 | 27473 | 2019-12-09 10:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | EACH | 3970.79 | 3970.79 | Small Tools (Consumables) | 2019-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27135-001025 | 27135 | 2019-11-29 09:54 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | Bag | 2.97 | 332.64 | Miscellaneous | 2019-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27443-001025 | 27443 | 2019-12-06 14:09 | Section 2 | Material | Not on List | Not on List | 2 | each | 545 | 1090 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27443-001025 | 27443 | 2019-12-06 14:09 | Section 2 | Material | Not on List | Not on List | 2 | each | 545 | 1090 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27443-001025 | 27443 | 2019-12-06 14:09 | Section 2 | Material | Not on List | Not on List | 2 | each | 61.25 | 122.5 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27443-001025 | 27443 | 2019-12-06 14:09 | Section 2 | Material | Not on List | Not on List | 2 | each | 61.25 | 122.5 | Miscellaneous | 2019-12-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27517-001025 | 27517 | 2019-12-10 08:30 | Section 6 | Material | Not on List | Not on List | 1 | Each | 63.02 | 63.02 | Miscellaneous | 2019-12-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27350-001025 | 27350 | 2019-12-04 18:25 | Core | Material | Not on List | Not on List | 1 | 1 | 94.99 | 95 | Office Supplies | 2019-12-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27350-001025 | 27350 | 2019-12-04 18:25 | Core | Material | Not on List | Not on List | 2 | 1 | 24.99 | 50 | Office Supplies | 2019-12-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27345-001025 | 27345 | 2019-12-04 17:11 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 974.05 | 974.05 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27532-001025 | 27532 | 2019-12-10 12:36 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | PPE | 2019-12-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27532-001025 | 27532 | 2019-12-10 12:36 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | PPE | 2019-12-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27532-001025 | 27532 | 2019-12-10 12:36 | Section 6 | Material | Not on List | Not on List | 10 | Each | NULL | 0 | PPE | 2019-12-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27532-001025 | 27532 | 2019-12-10 12:36 | Section 6 | Material | Not on List | Not on List | 10 | Each | NULL | 0 | PPE | 2019-12-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27538-001025 | 27538 | 2019-12-10 14:31 | Section 5 | Material | Not on List | Not on List | 20 | Number | NULL | 0 | Builders Merchants (General) | 2019-12-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27539-001025 | 27539 | 2019-12-10 14:07 | Section 3 | Material | Not on List | Not on List | 1 | No. | NULL | 0 | Miscellaneous | 2019-12-10 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 501 - Drains | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 4 | no | 5.25 | 21 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23595-001025 | 23595 | 2019-09-12 16:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23579-001025 | 23579 | 2019-09-12 14:06 | Section 3 | Material | Not on List | Not on List | 1 | EA | 415.51 | 415.51 | Miscellaneous | 2019-09-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 16 | no | 5.25 | 84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23571-001025 | 23571 | 2019-09-12 12:34 | Section 4 | Material | Not on List | Not on List | 1 | Each | 500000 | 500000 | Gas Oil | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23500-001025 | 23500 | 2019-09-11 11:22 | Section 4 | Material | Not on List | Not on List | 1 | Each | 621.27 | 621.27 | Miscellaneous | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23492-001025 | 23492 | 2019-09-11 09:53 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 45 | 45 | Surveying Consumables | 2019-09-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23581-001025 | 23581 | 2019-09-12 14:25 | Core | Material | Not on List | Not on List | 2 | EA | 850 | 1700 | Not Sure | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23586-001025 | 23586 | 2019-09-12 15:40 | Section 5 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 4 | Each | 158.65 | 634.6 | Ductile Drainage | 2019-09-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23621-001025 | 23621 | 2019-09-13 06:44 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 1 | Each | 370 | 370 | Waste (General) | 2019-09-16 | RVP 403 - 1339621 - Borrow Pit 5 A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 24 | no | 5.25 | 126 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23568-001025 | 23568 | 2019-09-12 12:09 | Section 4 | Material | Not on List | Not on List | 1 | lot | 232.14 | 232.14 | Miscellaneous | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23568-001025 | 23568 | 2019-09-12 12:09 | Section 4 | Material | Not on List | Not on List | 1 | lot | 1308.96 | 1308.96 | Miscellaneous | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23630-001025 | 23630 | 2019-09-13 08:24 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-23565-001025 | 23565 | 2019-09-12 11:17 | Section 2 | Material | Not on List | Not on List | 1 | 1 | 1 | 1 | Rebar and Mesh | 2019-09-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23641-001025 | 23641 | 2019-09-13 10:01 | Section 5 | Material | Not on List | Not on List | 1 | SM | 307.96 | 307.96 | Concrete Accessories | 2019-09-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 4 | no | 14.1 | 56.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23687-001025 | 23687 | 2019-09-14 08:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23687-001025 | 23687 | 2019-09-14 08:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23687-001025 | 23687 | 2019-09-14 08:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 10 | no | 5.25 | 52.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23688-001025 | 23688 | 2019-09-14 10:02 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23701-001025 | 23701 | 2019-09-16 07:51 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 16 | no | 2.93 | 46.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23583-001025 | 23583 | 2019-09-12 13:23 | Section 4 | Material | Not on List | Not on List | 14 | NULL | NULL | 0 | NULL | 2019-09-20 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23717-001025 | 23717 | 2019-09-16 10:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Twinwall | Polypipe 225mm Ridgidrain Bend 22.5deg (878030) | 4 | Each | 29.82 | 119.28 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Not on List | Not on List | 70 | Easch | 26.8 | 1876 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 70 | Each | 3.65 | 255.5 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Not on List | Not on List | 134 | Each | 42.87 | 5744.58 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6692-00750 | 6692 | 2018-09-18 17:08 | Section 4 | Material | Not on List | Not on List | 4 | Each | 185 | 740 | Not Sure | 2018-09-26 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 134 | Each | 7.06 | 946.04 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23560-001025 | 23560 | 2019-09-12 09:41 | Section 4 | Material | Not on List | Not on List | 60 | Each | 172.02 | 10321.2 | Plastic Drainage | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23718-001025 | 23718 | 2019-09-16 10:28 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No. | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23718-001025 | 23718 | 2019-09-16 10:28 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No. | NULL | 0 | Small Tools (Consumables) | 2019-09-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23535-001025 | 23535 | 2019-09-11 16:56 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 66 | Each | 37.6 | 2481.6 | Plastic Drainage | 2019-09-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23535-001025 | 23535 | 2019-09-11 16:56 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 66 | Each | 7.06 | 465.96 | Plastic Drainage | 2019-09-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23535-001025 | 23535 | 2019-09-11 16:56 | Section 3 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 20 | Each | 2.97 | 59.4 | Plastic Drainage | 2019-09-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23564-001025 | 23564 | 2019-09-12 11:25 | Section 4 | Material | Not on List | Not on List | 0.892 | Tonne | 538 | 479.9 | Rebar and Mesh | 2019-09-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | Not on List | Not on List | 832 | no | 4.43 | 3685.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23513 | 23513 | 2019-09-11 12:41 | Core | Material | Not on List | Not on List | 1 | SM | 6000 | 6000 | Miscellaneous | 2019-09-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-23589-001025 | 23589 | 2019-09-12 16:04 | Section 3 | Material | Not on List | Not on List | 2 | 7717344434 | 122.5 | 245 | Ductile Drainage | 2019-09-16 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6692-00750 | 6692 | 2018-09-18 17:08 | Section 4 | Material | NULL | NULL | 1 | Each | 65 | 65 | Not Sure | 2018-09-26 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23697-001025 | 23697 | 2019-09-16 06:26 | Core | Material | PPE, Small Tools and Consumables | Not on List | 929.4 | Each | 1 | 929.4 | Janitorial | 2019-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23713-001025 | 23713 | 2019-09-16 09:17 | Section 3 | Material | Not on List | Not on List | 2 | EA | 10.23 | 20.46 | Miscellaneous | 2019-09-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23713-001025 | 23713 | 2019-09-16 09:17 | Section 3 | Material | Not on List | Not on List | 4 | EA | 1.77 | 7.08 | Miscellaneous | 2019-09-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | NULL | NULL | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23440-001025 | 23440 | 2019-09-10 12:33 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6681-00750 | 6681 | 2018-09-18 15:26 | Section 4 | Material | NULL | NULL | 8 | Each | 30 | 240 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23769-001025 | 23769 | 2019-09-17 08:05 | Section 2 | Material | Saint Gobain Castings | Not on List | 3 | units | NULL | 0 | Concrete Drainage | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23769-001025 | 23769 | 2019-09-17 08:05 | Section 2 | Material | Saint Gobain Castings | Not on List | 3 | units | NULL | 0 | Concrete Drainage | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23769-001025 | 23769 | 2019-09-17 08:05 | Section 2 | Material | Not on List | Not on List | 10 | rolls | NULL | 0 | Builders Merchants (General) | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23769-001025 | 23769 | 2019-09-17 08:05 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Tonne | 32.74 | 196.44 | Concrete Drainage | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23769-001025 | 23769 | 2019-09-17 08:05 | Section 2 | Material | Combined Drainage | Not on List | 10 | boxes | NULL | 0 | Concrete Drainage | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23724-001025 | 23724 | 2019-09-16 11:24 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23726-001025 | 23726 | 2019-09-16 12:22 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23585-001025 | 23585 | 2019-09-12 15:05 | Section 4 | Material | Not on List | Not on List | 250 | Load | 95 | 23750 | Aggregate | 2019-09-12 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23585-001025 | 23585 | 2019-09-12 15:05 | Section 4 | Material | Not on List | Not on List | 1370 | Load | 65 | 89050 | Aggregate | 2019-09-12 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23585-001025 | 23585 | 2019-09-12 15:05 | Section 4 | Material | Not on List | Not on List | 400 | Load | 95 | 38000 | Aggregate | 2019-09-12 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | SC4A - Roadworks - Swavesey to Robins Lane | 702 - Pavement | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-6710-00750 | 6710 | 2018-09-19 11:34 | Section 4 | Material | Iron Wear | Not on List | 113 | Each | 44 | 4972 | Ductile Drainage | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23585-001025 | 23585 | 2019-09-12 15:05 | Section 4 | Material | Not on List | Not on List | 850 | Load | 100 | 85000 | Aggregate | 2019-09-12 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 606 - Import | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-23776-001025 | 23776 | 2019-09-17 11:05 | Section 2 | Material | Not on List | Not on List | 1 | NULL | 4545.54 | 4546 | Professional Services | 2019-09-19 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2A - Roadworks - A1 | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-23648-001025 | 23648 | 2019-09-13 11:46 | Section 4 | Material | Concrete Drainage | CPM 1050mm Concrete Rocker (890352) | 1 | Each | 384.68 | 384.68 | Concrete Drainage | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23648-001025 | 23648 | 2019-09-13 11:46 | Section 4 | Material | Concrete Drainage | CPM 1050mm Concrete Spigot (890380) | 1 | Each | 384.68 | 384.68 | Concrete Drainage | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23648-001025 | 23648 | 2019-09-13 11:46 | Section 4 | Material | Concrete Drainage | Not on List | 1 | Each | 289.78 | 289.78 | Concrete Drainage | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23648-001025 | 23648 | 2019-09-13 11:46 | Section 4 | Material | NULL | NULL | 1 | Each | 200 | 200 | Concrete Drainage | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23682-001025 | 23682 | 2019-09-13 16:28 | Section 5 | Material | Not on List | Not on List | 100 | EA | 4.97 | 497 | Builders Merchants (General) | 2019-09-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23682-001025 | 23682 | 2019-09-13 16:28 | Section 5 | Material | Not on List | Not on List | 10 | PK | 11.9 | 119 | Builders Merchants (General) | 2019-09-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23750-001025 | 23750 | 2019-09-16 17:50 | Section 5 | Material | Saint Gobain Castings | Not on List | 16 | EA | 58.04 | 928.64 | Builders Merchants (General) | 2019-09-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6710-00750 | 6710 | 2018-09-19 11:34 | Section 4 | Material | Iron Wear | Not on List | 1 | Each | 44 | 44 | Ductile Drainage | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23708-001025 | 23708 | 2019-09-16 08:54 | Section 3 | Material | Not on List | Not on List | 5 | Sheets | 10.44 | 52.2 | Builders Merchants (General) | 2019-09-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23781-001025 | 23781 | 2019-09-17 13:27 | Core | Material | Not on List | Not on List | 1 | each | 6637.86 | 6638 | Professional Services | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Buyers
MREQ-23747-001025 | 23747 | 2019-09-16 17:35 | Section 5 | Material | Not on List | NULL | 200 | EA | 7.5 | 1500 | Surveying Consumables | 2019-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23754-001025 | 23754 | 2019-09-16 18:24 | Section 5 | Material | Not on List | NULL | 8 | EA | 28.28 | 226.24 | Plastic Drainage | 2019-09-19 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23753-001025 | 23753 | 2019-09-16 18:04 | Section 5 | Material | Not on List | NULL | 1 | SM | 2828.92 | 2828.92 | Plastic Drainage | 2019-09-19 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6710-00750 | 6710 | 2018-09-19 11:34 | Section 4 | Material | Iron Wear | Not on List | 2 | Each | 50 | 100 | Ductile Drainage | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6710-00750 | 6710 | 2018-09-19 11:34 | Section 4 | Material | Iron Wear | Not on List | 4 | Each | 250 | 1000 | Ductile Drainage | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23517-001025 | 23517 | 2019-09-11 13:55 | Core | Material | NULL | NULL | 1 | EACH | 5630.75 | 5630.75 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6713-00750 | 6713 | 2018-09-19 11:32 | Section 4 | Material | Not on List | Not on List | 36 | Each | 4.55 | 163.8 | Miscellaneous | 2018-09-20 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6714-00750 | 6714 | 2018-09-19 12:37 | Section 4 | Material | Not on List | Not on List | 1 | Each | 94.19 | 94.19 | Concrete Drainage | 2018-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23832-001025 | 23832 | 2019-09-18 08:28 | Section 4 | Material | Not on List | Not on List | 2 | Each | NULL | 0 | Miscellaneous | 2019-09-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23835-001025 | 23835 | 2019-09-18 09:18 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-21183-001025 | 21183 | 2019-07-23 10:02 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23836-001025 | 23836 | 2019-09-18 09:31 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-09-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23788-001025 | 23788 | 2019-09-17 14:36 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-09-18 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23839-001025 | 23839 | 2019-09-18 10:36 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Surveying Consumables | 2019-09-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | IMO Queue | Yes - Approve | NULL | REQ - Buyers
MREQ-6714-00750 | 6714 | 2018-09-19 12:37 | Section 4 | Material | NULL | NULL | 2 | Each | 6 | 12 | Concrete Drainage | 2018-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-22092-001025 | 22092 | 2019-08-09 15:43 | Core | Material | Not on List | Not on List | 6 | NULL | 3.95 | 24 | Miscellaneous | 2019-08-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | NULL | 115 - Medical / 1st Aid | IMO Queue | Yes - Approve | NULL | REQ - Buyers
MREQ-23784-001025 | 23784 | 2019-09-17 13:50 | Section 4 | Material | Not on List | Not on List | 2 | Number | 8.67 | 17.34 | Surveying Consumables | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23784-001025 | 23784 | 2019-09-17 13:50 | Section 4 | Material | Not on List | Not on List | 2 | Number | 22 | 44 | Surveying Consumables | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23735-001025 | 23735 | 2019-09-16 14:37 | Core | Material | NULL | NULL | 5000 | EA | 0.51 | 2550 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23722-001025 | 23722 | 2019-09-16 11:17 | Core | Material | NULL | NULL | 1 | Each | 1378.5 | 1378.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23768-001025 | 23768 | 2019-09-17 08:09 | Section 3 | Material | Not on List | Not on List | 30 | No | 53.75 | 1612.5 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6714-00750 | 6714 | 2018-09-19 12:37 | Section 4 | Material | NULL | NULL | 2 | Each | 6 | 12 | Concrete Drainage | 2018-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23768-001025 | 23768 | 2019-09-17 08:09 | Section 3 | Material | Not on List | Not on List | 1 | roll 700mtrs | 73.5 | 73.5 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23821-001025 | 23821 | 2019-09-18 07:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 49.16 | 49.16 | Fuel | 2019-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23829-001025 | 23829 | 2019-09-18 08:23 | Section 4 | Material | Not on List | Not on List | 200 | Each | 6.75 | 1350 | Concrete Drainage | 2019-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23569-001025 | 23569 | 2019-09-12 12:16 | Section 4 | Material | NULL | NULL | 45 | Eachch | 6 | 270 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23569-001025 | 23569 | 2019-09-12 12:16 | Section 4 | Material | NULL | NULL | 15 | Each | 6 | 90 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23569-001025 | 23569 | 2019-09-12 12:16 | Section 4 | Material | NULL | NULL | 80 | Each | 3.03 | 242.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23569-001025 | 23569 | 2019-09-12 12:16 | Section 4 | Material | NULL | NULL | 2 | Each | 31.85 | 63.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23569-001025 | 23569 | 2019-09-12 12:16 | Section 4 | Material | NULL | NULL | 80 | Each | 3.03 | 242.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-09-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6714-00750 | 6714 | 2018-09-19 12:37 | Section 4 | Material | NULL | NULL | 1 | Each | 80 | 80 | Concrete Drainage | 2018-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23837-001025 | 23837 | 2019-09-18 09:48 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.69 | 345 | Builders Merchants (General) | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23837-001025 | 23837 | 2019-09-18 09:48 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.31 | 131 | Builders Merchants (General) | 2019-09-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23871-001025 | 23871 | 2019-09-18 16:32 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5057-0022 | 5057 | 2018-08-14 12:26 | Section 4 | Material | Not on List | Not on List | 48 | Each | 6.45 | 0 | Miscellaneous | 2018-08-19 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6715-00750 | 6715 | 2018-09-19 12:34 | Section 4 | Material | Concrete Drainage | Not on List | 100 | Roll | 13.9 | 1390 | Builders Merchants (General) | 2018-09-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23871-001025 | 23871 | 2019-09-18 16:32 | Section 4 | Material | Not on List | Not on List | 28 | NULL | NULL | 0 | Plastic Drainage | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 13.44 | 201.6 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 35.35 | 353.5 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-11126-001025 | 11126 | 2019-01-17 12:25 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.79 | 167 | Miscellaneous | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11131-001025 | 11131 | 2019-01-17 13:34 | Section 3 | Material | Not on List | Not on List | 12 | NULL | 7.96 | 96 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11131-001025 | 11131 | 2019-01-17 13:34 | Section 3 | Material | Not on List | Not on List | 7 | NULL | 6.11 | 43 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8282 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Finance Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11070-001025 | 11070 | 2019-01-16 13:34 | Section 4 | Material | NULL | Not on List | 15 | EA | 23.9 | 358.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-21 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5508-00343 | 5508 | 2018-08-22 14:52 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Office Supplies | 2018-10-31 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11133-001025 | 11133 | 2019-01-17 14:24 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1061.42 | Each | 1 | 1061 | PPE | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 79.8 | 79.8 | Janitorial | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1424.48 | 1424.48 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11053-001025 | 11053 | 2019-01-16 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 273.89 | 273.89 | PPE | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Staples Replacement 12mm For Staple Gun Box Of 1000 (770200) | 1 | NULL | 2.6 | 2.6 | Small Tools (Consumables) | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 19.8 | 19.8 | Small Tools (Consumables) | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11020-001025 | 11020 | 2019-01-15 12:54 | Section 3 | Material | PPE, Small Tools and Consumables | Refill Air Care Pristine Wild Berries Air Fragrance 270ml (539229) | 6 | Each | 3.1 | 18.6 | Janitorial | 2019-01-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11126-001025 | 11126 | 2019-01-17 12:25 | Section 3 | Material | Not on List | Not on List | 60 | tins | 2.79 | 167.4 | Miscellaneous | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11135-001025 | 11135 | 2019-01-17 14:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 779 | 779 | Not Sure | 2019-01-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN10 - A1198 Ermine Street Overbridge | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11140-001025 | 11140 | 2019-01-17 16:08 | Section 3 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 20 | Each | 535 | 10700 | Geotextiles | 2019-01-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5491-00320 | 5491 | 2018-08-22 10:49 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 154.76 | 154.76 | Small Tools (Consumables) | 2018-08-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11154-001025 | 11154 | 2019-01-17 15:32 | Section 3 | Material | Not on List | Not on List | 1 | Each | 114.5 | 115 | Miscellaneous | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11162-001025 | 11162 | 2019-01-17 20:58 | Section 3 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 5 | Each | 535 | 2675 | Geotextiles | 2019-01-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10890-001025 | 10890 | 2019-01-11 13:49 | Section 4 | Material | Not on List | Not on List | 1 | no | 2267.6 | 2267.6 | Concrete Drainage | 2019-01-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11171-001025 | 11171 | 2019-01-18 09:16 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 650 | 2600 | Miscellaneous | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11131-001025 | 11131 | 2019-01-17 13:34 | Section 3 | Material | Not on List | Not on List | 12 | NULL | 7.96 | 95.52 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11131-001025 | 11131 | 2019-01-17 13:34 | Section 3 | Material | Not on List | Not on List | 7 | NULL | 6.11 | 42.77 | Small Tools (Consumables) | 2019-01-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11059-001025 | 11059 | 2019-01-16 09:54 | Section 4 | Material | Not on List | Not on List | 6 | 10m Roll | 76.1 | 456.6 | Concrete Accessories | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN24 - Girton Interchange Bridge C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11140-001025 | 11140 | 2019-01-17 16:08 | Section 3 | Material | NULL | Tensar TX160 4m x 75m (150563) | 20 | Each | 535 | 10700 | Geotextiles | 2019-01-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11162-001025 | 11162 | 2019-01-17 20:58 | Section 3 | Material | NULL | Tensar TX160 4m x 75m (150563) | 5 | Each | 535 | 2675 | Geotextiles | 2019-01-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-11140-001025 | 11140 | 2019-01-17 16:08 | Section 3 | Material | NULL | Tensar TX160 4m x 75m (150563) | 20 | Each | 535 | 10700 | Geotextiles | 2019-01-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5491-00320 | 5491 | 2018-08-22 10:49 | Section 3 | Material | Not on List | Not on List | 25 | EA | 0.91 | 22.75 | Small Tools (Consumables) | 2018-08-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11182-001025 | 11182 | 2019-01-18 12:31 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-01-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Rocker (249380) | 4 | Each | 579.92 | 2320 | Concrete Drainage | 2019-01-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Socket (249381) | 2 | Each | 579.92 | 1160 | Concrete Drainage | 2019-01-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 3 | Each | 579.92 | 1740 | Concrete Drainage | 2019-01-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10868-001025 | 10868 | 2019-01-11 10:39 | Section 4 | Material | Not on List | Not on List | 16 | Rolls | 215 | 3440 | Not Sure | 2019-01-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11201-001025 | 11201 | 2019-01-18 14:37 | Section 4 | Material | Not on List | Not on List | 8 | boxes | NULL | 0 | Not Sure | 2019-01-22 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11242-001025 | 11242 | 2019-01-21 11:04 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1701 - Insitu Concrete | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11244-001025 | 11244 | 2019-01-21 11:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 889.5 | Each | 1 | 890 | PPE | 2019-01-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 20 | no. | NULL | 0 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 5 | no. | NULL | 0 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5491-00320 | 5491 | 2018-08-22 10:49 | Section 3 | Material | Not on List | Not on List | 2 | ea | 87 | 174 | Small Tools (Consumables) | 2018-08-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 2 | bags | NULL | 0 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 450 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 8 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 15 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 15 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 80 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | Kerbs | Not on List | 10 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | Not on List | Not on List | 2 | Rolls | NULL | 0 | Concrete Accessories | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | Not on List | Not on List | 1 | palett | NULL | 0 | Concrete Accessories | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Builders Merchants (General) | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 2 | Each | 59.17 | 118 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11295-001025 | 11295 | 2019-01-22 09:47 | Section 3 | Material | Not on List | Not on List | 70 | tonne | NULL | 0 | Reinforcement | 2019-02-24 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | BN16 - New Barns Lane Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11298-001025 | 11298 | 2019-01-22 10:28 | Section 3 | Material | Not on List | Not on List | 12 | No | NULL | 0 | Builders Merchants (General) | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5441-00286 | 5441 | 2018-08-21 14:38 | Section 4 | Material | Not on List | Not on List | 1050 | MT | 0.11 | 115.5 | Concrete Accessories | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11305-001025 | 11305 | 2019-01-22 11:08 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2019-01-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11182-001025 | 11182 | 2019-01-18 12:31 | Section 4 | Material | Not on List | Not on List | 1 | Each | 553.53 | 553.53 | Concrete Drainage | 2019-01-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11182-001025 | 11182 | 2019-01-18 12:31 | Section 4 | Material | NULL | Not on List | 1 | Each | 15 | 15 | Concrete Drainage | 2019-01-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 42 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11322-001025 | 11322 | 2019-01-22 16:03 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11334-001025 | 11334 | 2019-01-22 17:20 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Surveying Consumables | 2019-01-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11201-001025 | 11201 | 2019-01-18 14:37 | Section 4 | Material | Not on List | Not on List | 8 | Box | 63 | 504 | Not Sure | 2019-01-24 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Rocker (249380) | 4 | Each | 579.92 | 2319.68 | Concrete Drainage | 2019-01-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5441-00286 | 5441 | 2018-08-21 14:38 | Section 4 | Material | Not on List | Not on List | 96 | 2.5ltr | 17.64 | 1693.44 | Concrete Accessories | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Socket (249381) | 2 | Each | 579.92 | 1159.84 | Concrete Drainage | 2019-01-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 3 | Each | 579.92 | 1739.76 | Concrete Drainage | 2019-01-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11183-001025 | 11183 | 2019-01-18 12:38 | Section 4 | Material | NULL | NULL | 1 | Each | 200 | 200 | Concrete Drainage | 2019-01-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 450 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 8 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 15 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 15 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 80 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 10 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 450 | No | 35.59 | 16015.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5441-00286 | 5441 | 2018-08-21 14:38 | Section 4 | Material | Not on List | Not on List | 2 | 5ltr | 81 | 162 | Concrete Accessories | 2018-08-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 8 | No | 38.85 | 310.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 15 | No | 39.22 | 588.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 15 | No | 39.22 | 588.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 80 | No | 39.22 | 3137.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11256-001025 | 11256 | 2019-01-21 12:58 | Section 3 | Material | NULL | Not on List | 10 | No | 4.9 | 49 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-01-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11342-001025 | 11342 | 2019-01-23 08:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Number | NULL | 0 | PPE | 2019-01-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2701 - Accommodation works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11345-001025 | 11345 | 2019-01-23 08:36 | Section 3 | Material | Not on List | Not on List | 4 | no | NULL | 0 | Electrical | 2019-01-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | GN3B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11353-001025 | 11353 | 2019-01-23 10:26 | Section 3 | Material | Aggregate | Type 1 | 1000 | Tonnes | 16 | 16000 | Aggregate | 2019-01-24 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | BN16 - New Barns Lane Overbridge | 1601 - Piling and attendances | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11305-001025 | 11305 | 2019-01-22 11:08 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 524.25 | 524.25 | Damage Charges | 2019-01-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Miscellaneous | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5440-00285 | 5440 | 2018-08-21 14:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 6.87 | 137.4 | Concrete Accessories | 2018-08-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Miscellaneous | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11366-001025 | 11366 | 2019-01-23 13:39 | Section 3 | Material | Geotextile | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 22 | Each | 110.27 | 2426 | Geotextiles | 2019-01-25 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | BN16 - New Barns Lane Overbridge | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11372-001025 | 11372 | 2019-01-23 15:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3922.74 | Each | 1 | 3923 | PPE | 2019-01-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 5 | Each | 90.48 | 452.4 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 10 | Each | 12.48 | 124.8 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 20 | Each | 5.51 | 110.2 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 7 | Each | 149.45 | 1046.15 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 7 | Each | 15.19 | 106.33 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 2 | Each | 92.06 | 184.12 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 3 | Each | 122.16 | 366.48 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 2 | Each | 79.28 | 158.56 | Concrete Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 42 | Each | 24.82 | 1042.44 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 50 | Each | 3.38 | 169 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11289-001025 | 11289 | 2019-01-22 08:02 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.86 | 186 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 42 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2019-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11312-001025 | 11312 | 2019-01-22 12:43 | Section 4 | Material | NULL | Not on List | NULL | NULL | NULL | 0 | NULL | NULL | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11345-001025 | 11345 | 2019-01-23 08:36 | Section 3 | Material | Not on List | Not on List | 4 | no | 241.07 | 964.28 | Electrical | 2019-01-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | GN3B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11397-001025 | 11397 | 2019-01-24 08:05 | Section 3 | Material | Not on List | Not on List | 12580 | Ton | 4 | 50320 | Aggregate | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8682-001023 | 8682 | 2018-11-05 10:06 | Section 4 | Material | NULL | Not on List | 1 | Each | 540 | 540 | Concrete Drainage | 2018-11-19 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8853-001024 | 8853 | 2018-11-07 17:37 | Section 3 | Material | Not on List | Not on List | 1 | No | 879.45 | 879.45 | Damage Charges | 2018-11-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9150-001025 | 9150 | 2018-11-14 15:04 | Section 3 | Material | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 128 | Each | 2.93 | 375 | Builders Merchants (General) | 2018-11-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8855-001024 | 8855 | 2018-11-08 07:22 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.35 | 70 | Miscellaneous | 2018-11-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9133-001025 | 9133 | 2018-11-14 12:05 | Section 3 | Material | Not on List | Not on List | 30 | m | 0.64 | 19.2 | Miscellaneous | 2018-11-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN06 - ECML Bridge | 1705 - Repairs to Existing Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5057-0022 | 5057 | 2018-08-14 12:26 | Section 4 | Material | Not on List | Not on List | 4 | boxes | NULL | 0 | Miscellaneous | 2018-08-19 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5239-00148 | 5239 | 2018-08-16 14:33 | Section 4 | Material | Not on List | Not on List | 225 | NULL | 56 | 12600 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9128-001025 | 9128 | 2018-11-14 10:42 | Section 4 | Material | Not on List | Not on List | 2 | Pack 100 | 76.5 | 153 | Miscellaneous | 2018-11-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9043-001024 | 9043 | 2018-11-13 07:16 | Section 4 | Material | Not on List | Not on List | 100 | Each | 21 | 2100 | Miscellaneous | 2018-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9043-001024 | 9043 | 2018-11-13 07:16 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.5 | 100 | Miscellaneous | 2018-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9043-001024 | 9043 | 2018-11-13 07:16 | Section 4 | Material | Not on List | Not on List | 75 | Each | 5.5 | 412.5 | Miscellaneous | 2018-11-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9137-001025 | 9137 | 2018-11-14 13:02 | Section 4 | Material | Not on List | Not on List | 1 | each | 796.45 | 796.45 | Damage Charges | 2018-11-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | Kerbs | Not on List | 4 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | Kerbs | Not on List | 4 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9091-001025 | 9091 | 2018-11-13 15:59 | Section 3 | Material | Not on List | Not on List | 14 | NULL | 32 | 448 | Miscellaneous | 2018-11-15 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8800-001024 | 8800 | 2018-11-07 07:41 | Section 4 | Material | Not on List | Not on List | 1 | Each | 114.41 | 114.41 | Damage Charges | 2018-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5239-00148 | 5239 | 2018-08-16 14:33 | Section 4 | Material | Not on List | Not on List | 225 | NULL | 9.33 | 2099.25 | Miscellaneous | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Pipe 2.5m (249379) | 9 | Each | 483.27 | 4349.43 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Socket (249381) | 2 | Each | 579.92 | 1159.84 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9112-001025 | 9112 | 2018-11-14 07:55 | Section 3 | Material | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 2 | Each | 579.92 | 1159.84 | Concrete Drainage | 2018-11-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9150-001025 | 9150 | 2018-11-14 15:04 | Section 3 | Material | NULL | Concrete Kerbs 125x150x914 HB Straight (898181) | 128 | Each | 2.93 | 375.04 | Builders Merchants (General) | 2018-11-16 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9188-001025 | 9188 | 2018-11-15 08:49 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 343.36 | 343.36 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 166.15 | 166.15 | Small Tools (Consumables) | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 211.34 | 211.34 | Janitorial | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 719.5 | 719.5 | PPE | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 11.6 | 11.6 | PPE | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5239-00148 | 5239 | 2018-08-16 14:33 | Section 4 | Material | Not on List | Not on List | 22 | NULL | NULL | 0 | NULL | 2018-08-22 | RVP 427 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 9.51 | 95.1 | Janitorial | 2018-11-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8893-001024 | 8893 | 2018-11-08 12:32 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.45 | 147 | Miscellaneous | 2018-11-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8769-001024 | 8769 | 2018-11-06 15:08 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 2159 | 2159 | Not Sure | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9195-001025 | 9195 | 2018-11-15 10:50 | Section 3 | Material | Not on List | Not on List | 4 | Number | NULL | 0 | Miscellaneous | 2018-11-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9195-001025 | 9195 | 2018-11-15 10:50 | Section 3 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2018-11-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9195-001025 | 9195 | 2018-11-15 10:50 | Section 3 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2018-11-21 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8765-001024 | 8765 | 2018-11-06 14:57 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 3687.55 | 3687.55 | Not Sure | 2018-11-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 298.96 | 298.96 | Janitorial | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 203.8 | 203.8 | PPE | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5287-00223 | 5287 | 2018-08-17 12:25 | Section 4 | Material | Plastic Drainage | Not on List | 10 | no | NULL | 0 | Plastic Drainage | 2018-08-20 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9147-001025 | 9147 | 2018-11-14 14:48 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 491.15 | 491.15 | Small Tools (Consumables) | 2018-11-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8759-001024 | 8759 | 2018-11-06 14:10 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1882.92 | 1882.92 | Damage Charges | 2018-11-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9200-001025 | 9200 | 2018-11-15 11:23 | Section 3 | Material | Not on List | Not on List | 4 | No | NULL | 0 | Builders Merchants (General) | 2018-11-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9205-001025 | 9205 | 2018-11-15 14:52 | Section 3 | Material | Not on List | Not on List | 1 | No. | 281.1 | 281 | Small Tools (Consumables) | 2018-11-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8734-001024 | 8734 | 2018-11-06 08:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 3615 | 3615 | Damage Charges | 2018-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8726-001024 | 8726 | 2018-11-06 07:50 | Section 4 | Material | Not on List | Not on List | 1 | Each | 864.64 | 864.64 | Damage Charges | 2018-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9210-001025 | 9210 | 2018-11-15 16:17 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Box | NULL | 0 | Miscellaneous | 2018-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9213-001025 | 9213 | 2018-11-15 16:19 | Section 3 | Material | Not on List | Not on List | 120 | kg | NULL | 0 | Miscellaneous | 2018-11-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9213-001025 | 9213 | 2018-11-15 16:19 | Section 3 | Material | Not on List | Not on List | 480 | no. | NULL | 0 | Miscellaneous | 2018-11-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5289-00224 | 5289 | 2018-08-17 13:08 | Section 4 | Material | Misc | Not on List | 1 | no | NULL | 0 | Small Tools (Consumables) | 2018-08-20 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8663-001023 | 8663 | 2018-11-05 07:57 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1324 | 1324 | Damage Charges | 2018-11-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9218-001025 | 9218 | 2018-11-15 16:36 | Section 4 | Material | Kerbs | Not on List | 30 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9188-001025 | 9188 | 2018-11-15 08:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 86.25 | 86.25 | Concrete Drainage | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9188-001025 | 9188 | 2018-11-15 08:49 | Section 4 | Material | NULL | Not on List | 1 | Each | 55 | 55 | Concrete Drainage | 2018-11-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9200-001025 | 9200 | 2018-11-15 11:23 | Section 3 | Material | Not on List | Not on List | 4 | No | 26.94 | 107.76 | Builders Merchants (General) | 2018-11-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9210-001025 | 9210 | 2018-11-15 16:17 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Box | NULL | 0 | Miscellaneous | 2018-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9213-001025 | 9213 | 2018-11-15 16:19 | Section 3 | Material | Not on List | Not on List | 120 | kg | 3.1 | 372 | Miscellaneous | 2018-11-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9213-001025 | 9213 | 2018-11-15 16:19 | Section 3 | Material | Not on List | Not on List | 480 | no. | 1.04 | 499.2 | Miscellaneous | 2018-11-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6694-001023 | 6694 | 2018-09-18 17:31 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9205-001025 | 9205 | 2018-11-15 14:52 | Section 3 | Material | Not on List | Not on List | 1 | No. | 281.1 | 281.1 | Small Tools (Consumables) | 2018-11-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | Not on List | Not on List | 13.12 | t | NULL | 0 | Reinforcement | 2018-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | Not on List | Not on List | 8 | number | NULL | 0 | Reinforcement | 2018-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9274-001025 | 9274 | 2018-11-16 12:04 | Section 4 | Material | Not on List | Not on List | 45 | number | NULL | 0 | Not Sure | 2018-12-09 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9195-001025 | 9195 | 2018-11-15 10:50 | Section 3 | Material | Not on List | Not on List | 20 | Number | 130 | 2600 | Miscellaneous | 2018-11-21 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9273-001025 | 9273 | 2018-11-16 11:40 | Section 4 | Material | Not on List | Not on List | 1965 | Each | 1 | 1965 | Waste (General) | 2018-11-19 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9273-001025 | 9273 | 2018-11-16 11:40 | Section 4 | Material | Not on List | Not on List | 3930 | Each | 1 | 3930 | Waste (General) | 2018-11-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9349-001025 | 9349 | 2018-11-20 08:00 | Section 3 | Material | Not on List | Not on List | 4 | No | NULL | 0 | Builders Merchants (General) | 2018-11-22 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9349-001025 | 9349 | 2018-11-20 08:00 | Section 3 | Material | Not on List | Not on List | 4 | No | 105.04 | 420.16 | Builders Merchants (General) | 2018-11-22 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3A - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 200 | Each | 16.95 | 3390 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 1 | Each | 33.28 | 33.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 4 | Each | 33.28 | 133.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 4 | Each | 33.28 | 133.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 25 | Each | 33.28 | 832 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7857-001023 | 7857 | 2018-10-16 16:46 | Section 4 | Material | Not on List | Not on List | 5 | Each | 192.08 | 960.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9362-001025 | 9362 | 2018-11-20 11:19 | Section 3 | Material | Not on List | Not on List | 500 | no. | NULL | 0 | Miscellaneous | 2018-11-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | NULL | Not on List | 10 | Each | 7.06 | 70.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | NULL | Not on List | 4 | Each | 6.73 | 26.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5323-00228 | 5323 | 2018-08-20 08:32 | Section 4 | Material | Not on List | NULL | 2.28 | Tonnes | 538 | 1226.64 | Rebar and Mesh | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9186-001025 | 9186 | 2018-11-15 08:27 | Section 4 | Material | NULL | Not on List | 4 | Each | 6.73 | 26.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9362-001025 | 9362 | 2018-11-20 11:19 | Section 3 | Material | Not on List | Not on List | 500 | no. | 0.09 | 45 | Miscellaneous | 2018-11-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5324-00229 | 5324 | 2018-08-20 08:36 | Section 4 | Material | Not on List | NULL | 0.411 | Tonnes | 538 | 221.12 | Rebar and Mesh | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9367-001025 | 9367 | 2018-11-20 13:27 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 3133.04 | 3133.04 | Janitorial | 2018-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9218-001025 | 9218 | 2018-11-15 16:36 | Section 4 | Material | NULL | Not on List | 30 | Each | 19.02 | 570.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9218-001025 | 9218 | 2018-11-15 16:36 | Section 4 | Material | NULL | Not on List | 1 | Each | 115 | 115 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9385-001025 | 9385 | 2018-11-20 16:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9385-001025 | 9385 | 2018-11-20 16:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9385-001025 | 9385 | 2018-11-20 16:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 320.65 | 320.65 | Small Tools (Consumables) | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9385-001025 | 9385 | 2018-11-20 16:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 407.8 | 407.8 | PPE | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9408-001025 | 9408 | 2018-11-21 10:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5057-0022 | 5057 | 2018-08-14 12:26 | Section 4 | Material | Not on List | Not on List | 2 | number | NULL | 0 | Miscellaneous | 2018-08-19 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5225-00143 | 5225 | 2018-08-16 10:37 | Section 4 | Material | Not on List | Not on List | 72 | NULL | 3.41 | 245.52 | Not Sure | 2018-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9374-001025 | 9374 | 2018-11-20 15:04 | Section 4 | Material | Not on List | Not on List | 2 | Pack (100) | 38.97 | 77.94 | Miscellaneous | 2018-11-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9411-001025 | 9411 | 2018-11-21 10:15 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1730 | 1730 | Professional Services | 2018-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9327-001025 | 9327 | 2018-11-19 11:25 | Section 4 | Material | Not on List | Not on List | 120 | Each | 3.46 | 415.2 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9327-001025 | 9327 | 2018-11-19 11:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 42.45 | 169.8 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9327-001025 | 9327 | 2018-11-19 11:25 | Section 4 | Material | Not on List | Not on List | 10 | Each | 8.2 | 82 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9327-001025 | 9327 | 2018-11-19 11:25 | Section 4 | Material | Not on List | Not on List | 4 | Each | 52 | 208 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9327-001025 | 9327 | 2018-11-19 11:25 | Section 4 | Material | Not on List | Not on List | 3 | Each | 88.88 | 266.64 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9379-001025 | 9379 | 2018-11-20 14:42 | Section 4 | Material | Not on List | Not on List | 2 | coils | 44.8 | 89.6 | Not Sure | 2018-11-23 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9379-001025 | 9379 | 2018-11-20 14:42 | Section 4 | Material | Not on List | Not on List | 20 | coils | 46.5 | 930 | Not Sure | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9372-001025 | 9372 | 2018-11-20 14:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Box 10 | 32.72 | 981.6 | Miscellaneous | 2018-11-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5225-00143 | 5225 | 2018-08-16 10:37 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 18.08 | 72.32 | Not Sure | 2018-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9372-001025 | 9372 | 2018-11-20 14:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | 0.73 | 73 | Miscellaneous | 2018-11-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9376-001025 | 9376 | 2018-11-20 15:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 398.6 | 398.6 | Janitorial | 2018-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9417-001025 | 9417 | 2018-11-21 12:04 | Section 3 | Material | Not on List | Not on List | 7 | NULL | 38.95 | 273 | Miscellaneous | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9377-001025 | 9377 | 2018-11-20 15:38 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 523.14 | 523.14 | Small Tools (Consumables) | 2018-11-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9391-001025 | 9391 | 2018-11-20 17:07 | Section 4 | Material | Not on List | Not on List | 400 | 25m rolls | 12.8 | 5120 | Miscellaneous | 2018-11-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9423-001025 | 9423 | 2018-11-21 14:12 | Section 3 | Material | Not on List | Not on List | 1 | ea | 447.5 | 448 | Damage Charges | 2018-11-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9380-001025 | 9380 | 2018-11-20 16:01 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 30.24 | 604.8 | Small Tools (Consumables) | 2018-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5225-00143 | 5225 | 2018-08-16 10:37 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 214.53 | 214.53 | Not Sure | 2018-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9371-001025 | 9371 | 2018-11-20 14:40 | Section 4 | Material | Not on List | Not on List | 6 | Each | 79.99 | 479.94 | Miscellaneous | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | Not on List | Not on List | 24.967 | Tonne | 538 | 13432.25 | Rebar and Mesh | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | Not on List | Not on List | 8 | Each | 5.16 | 41.28 | Rebar and Mesh | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | NULL | Not on List | 16 | Each | 3.25 | 52 | Rebar and Mesh | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9271-001025 | 9271 | 2018-11-16 11:30 | Section 4 | Material | NULL | Not on List | 16 | Each | 2.78 | 44.48 | Rebar and Mesh | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9454-001025 | 9454 | 2018-11-22 07:32 | Section 3 | Material | Bagged | Not on List | 1 | palette | NULL | 0 | Builders Merchants (General) | 2018-11-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5289-00224 | 5289 | 2018-08-17 13:08 | Section 4 | Material | Misc | Not on List | 1 | no | 429 | 0 | Small Tools (Consumables) | 2018-08-20 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9458-001025 | 9458 | 2018-11-22 08:11 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-11-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 941 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11398-001025 | 11398 | 2019-01-24 08:31 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 42 | 25kg Bag | 9.48 | 398 | Miscellaneous | 2019-01-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 24 | NULL | 5.98 | 143.52 | Miscellaneous | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 24 | NULL | 5.98 | 143.52 | Miscellaneous | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11359-001025 | 11359 | 2019-01-23 11:54 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 12.32 | 12.32 | Miscellaneous | 2019-01-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11295-001025 | 11295 | 2019-01-22 09:47 | Section 3 | Material | Not on List | Not on List | 70 | tonne | 538 | 37660 | NULL | 2019-02-24 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | BN16 - New Barns Lane Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11366-001025 | 11366 | 2019-01-23 13:39 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 22 | Each | 110.27 | 2425.94 | Geotextiles | 2019-01-25 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | PLM3 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Concrete Drainage | Not on List | 60 | Each | 17.14 | 1028.4 | Concrete Drainage | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | NULL | Each | 81.73 | 0 | Miscellaneous | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Saint Gobain Castings | 430x370x100 D400 Watershed GG&F (376797) | 12 | Each | 34 | 408 | Miscellaneous | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Twinwall | Not on List | 25 | Each | 37.18 | 929.5 | Plastic Drainage | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Not on List | Not on List | 12 | Rolls | 6.4 | 76.8 | Fixings and Fasteners | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Ducting | Polypipe 94mm x 6m Black Ridgiduct (877654) | 45 | Each | 11.33 | 509.85 | Electrical | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Ducting | Not on List | 105 | each | 0.36 | 37.8 | Electrical | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19437-001025 | 19437 | 2019-06-20 12:59 | Section 3 | Material | Not on List | Not on List | 30 | Each | 3.36 | 100.8 | Miscellaneous | 2019-06-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19492-001025 | 19492 | 2019-06-21 10:14 | Section 3 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 40 | Each | 81.73 | 3269.2 | Ductile Drainage | 2019-06-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19492-001025 | 19492 | 2019-06-21 10:14 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 40 | Each | 18.43 | 737.2 | Concrete Drainage | 2019-06-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19747-001025 | 19747 | 2019-06-26 10:29 | Section 3 | Material | Waste Management | Dry Mixed Recycling - Wheelie Bin 1100 Litre | 100 | Each | 7 | 700 | Waste (Recycling) | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19747-001025 | 19747 | 2019-06-26 10:29 | Section 3 | Material | Waste Management | Municipal Waste - Wheelie Bin 1100 Litre | 100 | Each | 14.25 | 1425 | Waste (General) | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19747-001025 | 19747 | 2019-06-26 10:29 | Section 3 | Material | Waste Management | Food Waste - Wheelie Bin 240 Litre | 10 | Each | 10 | 100 | Waste (Recycling) | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19748-001025 | 19748 | 2019-06-26 10:02 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19451-001025 | 19451 | 2019-06-20 16:11 | Section 4 | Material | Not on List | Not on List | 2 | Number | 968.26 | 1936.52 | Small Tools (Consumables) | 2019-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19664-001025 | 19664 | 2019-06-25 09:57 | Section 4 | Material | Not on List | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19665-001025 | 19665 | 2019-06-25 10:00 | Section 4 | Material | Not on List | Not on List | 32 | Each | 28.8 | 921.6 | PPE | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19667-001025 | 19667 | 2019-06-25 10:04 | Section 4 | Material | Not on List | Not on List | 829.44 | Each | 1 | 829.44 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15789-001025 | 15789 | 2019-04-12 14:55 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 1 | Each | 370 | 370 | Waste (General) | 2019-04-15 | RVP 420 - A14 Eastbound - Opposite Crematorium | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19759-001025 | 19759 | 2019-06-26 12:21 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19761-001025 | 19761 | 2019-06-26 12:30 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19762-001025 | 19762 | 2019-06-26 12:41 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19778-001025 | 19778 | 2019-06-26 14:51 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19778-001025 | 19778 | 2019-06-26 14:51 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 1 | Load | 24.32 | 24 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19730-001025 | 19730 | 2019-06-26 08:33 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-06-27 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5098-0041 | 5098 | 2018-08-14 17:59 | Section 3 | Material | Not on List | Not on List | 1 | each | 321.52 | 321.52 | Damage Charges | 2018-08-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19796-001025 | 19796 | 2019-06-26 14:59 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-6919-00751 | 6919 | 2018-09-24 13:27 | Section 3 | Material | Not on List | Not on List | 6 | Frames | 2166.3 | 12997.8 | Fixings and Fasteners | 2018-10-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19796-001025 | 19796 | 2019-06-26 14:59 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19796-001025 | 19796 | 2019-06-26 14:59 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19796-001025 | 19796 | 2019-06-26 14:59 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19724-001025 | 19724 | 2019-06-26 08:02 | Section 4 | Material | Not on List | Not on List | 12 | EA | 13.5 | 162 | Builders Merchants (General) | 2019-06-28 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Level Spirit Heavy Duty Aluminium Spartan Pro 1200mm/4 (740561) | 5 | Each | 14.99 | 75 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289) | 10 | Each | 7.32 | 73 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Tank Dust Suppression Duro 13 Litre Ref Dp-dst-13l (766568) | 4 | Each | 33.95 | 136 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Rake Asphalt/Tarmac Flat Tooth Metal Handle Spartan Pro (762583) | 15 | Each | 17.28 | 259 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-6919-00751 | 6919 | 2018-09-24 13:27 | Section 3 | Material | Not on List | Not on List | 16 | Frames | 4357 | 69712 | Fixings and Fasteners | 2018-10-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Scraper First Task 75mm Stripping Knife Ref 14003020 (746838) | 10 | Each | 5.55 | 56 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Strap Lashing 8m Ratchet Hvy Duty 2 Tonne Load 5 Tonne Break (746483) | 15 | Each | 21.34 | 320 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-17781-001025 | 17781 | 2019-05-20 17:15 | Section 3 | Material | NULL | Not on List | 84 | No | 39.22 | 3294.48 | Concrete Drainage | 2019-05-22 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17946-001025 | 17946 | 2019-05-23 09:08 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Office Supplies | 2019-05-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17896-001025 | 17896 | 2019-05-22 13:13 | Section 4 | Material | Not on List | Not on List | 800 | EA | 0.04 | 32 | Concrete Accessories | 2019-05-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17896-001025 | 17896 | 2019-05-22 13:13 | Section 4 | Material | Not on List | Not on List | 3 | Pack 100 | 8.35 | 25.05 | Concrete Accessories | 2019-05-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17900-001025 | 17900 | 2019-05-22 13:23 | Section 4 | Material | Not on List | Not on List | 120 | EA | 8.43 | 1011.6 | Concrete Accessories | 2019-05-24 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17950-001025 | 17950 | 2019-05-23 09:31 | Section 1 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Rotproof 31" X 13" 7.5oz (746640) | 2000 | Each | 0.37 | 740 | Builders Merchants (General) | 2019-05-27 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-5803-00479 | 5803 | 2018-08-30 11:07 | Section 4 | Material | Not on List | Not on List | 2 | Each | 9.48 | 18.96 | Not Sure | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17518-001025 | 17518 | 2019-05-16 09:56 | Core | Material | Not on List | Not on List | 1 | NULL | 831.27 | 831.27 | Training | 2019-05-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17518-001025 | 17518 | 2019-05-16 09:56 | Core | Material | Not on List | Not on List | 1 | NULL | 3207.03 | 3207.03 | Training | 2019-05-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17518-001025 | 17518 | 2019-05-16 09:56 | Core | Material | Not on List | Not on List | 1 | NULL | 8494.53 | 8494.53 | Training | 2019-05-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17518-001025 | 17518 | 2019-05-16 09:56 | Core | Material | Not on List | Not on List | 1 | NULL | 140 | 140 | Training | 2019-05-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17919-001025 | 17919 | 2019-05-22 16:56 | Section 3 | Material | Aggregate | Class 1A | 51 | Loads | 80 | 4080 | Aggregate | 2019-05-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6406-00695 | 6406 | 2018-09-12 12:51 | Section 3 | Material | Not on List | Not on List | 72 | ea | 2.45 | 176.4 | Miscellaneous | 2018-09-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17961-001025 | 17961 | 2019-05-23 10:37 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17961-001025 | 17961 | 2019-05-23 10:37 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17961-001025 | 17961 | 2019-05-23 10:37 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17966-001025 | 17966 | 2019-05-23 12:12 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-05-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17973-001025 | 17973 | 2019-05-23 13:09 | Section 2 | Material | Saint Gobain Castings | Not on List | 11 | number | NULL | 0 | Concrete Drainage | 2019-05-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17857-001025 | 17857 | 2019-05-22 07:51 | Section 3 | Material | NULL | Not on List | 60 | number | 2.47 | 148.2 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17784-001025 | 17784 | 2019-05-20 17:08 | Section 2 | Material | Not on List | Not on List | 25 | m | NULL | 0 | Plastic Drainage | 2019-05-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17784-001025 | 17784 | 2019-05-20 17:08 | Section 2 | Material | NULL | Polyipipe 150mm Ridgidrain Bend 90deg (878001) | 2 | Each | 8.25 | 16.5 | Plastic Drainage | 2019-05-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17784-001025 | 17784 | 2019-05-20 17:08 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 2 | Each | 1.98 | 3.96 | Plastic Drainage | 2019-05-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17784-001025 | 17784 | 2019-05-20 17:08 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2019-05-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17808-001025 | 17808 | 2019-05-21 12:40 | Section 4 | Material | Not on List | Not on List | 1 | No. | 240.77 | 240.77 | Surveying Consumables | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17812-001025 | 17812 | 2019-05-21 12:58 | Section 4 | Material | Not on List | Not on List | 1 | Each | 495 | 495 | Miscellaneous | 2019-05-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17854-001025 | 17854 | 2019-05-22 07:42 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1501.34 | 1501.34 | Miscellaneous | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17971-001025 | 17971 | 2019-05-23 12:43 | Section 4 | Material | Not on List | Not on List | 1 | Each | 91.14 | 91.14 | Miscellaneous | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18009-001025 | 18009 | 2019-05-24 07:30 | Core | Material | Not on List | Not on List | 1 | £ | 55 | 55 | Miscellaneous | 2019-05-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6452-00702 | 6452 | 2018-09-12 18:55 | Section 4 | Material | Not on List | Not on List | 1 | Each | 689.44 | 689.44 | Damage Charges | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18025-001025 | 18025 | 2019-05-24 09:36 | Section 5 | Material | Not on List | Not on List | 20 | no | NULL | 0 | Plastic Drainage | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 7 | Each | 32.74 | 229.18 | Blocks and Bricks | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | Not on List | Not on List | 1500 | number | 0.31 | 465 | Concrete Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | Not on List | Not on List | 200 | number | 2.47 | 494 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | Not on List | Not on List | 115 | ea | 11.51 | 1323.65 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 100 | Each | 2 | 200 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 50 | Each | 48.86 | 2443 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 90 | Each | 34.82 | 3133.8 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | Not on List | Not on List | 50 | ea | 13.75 | 687.5 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | Not on List | Not on List | 20 | ea | 36.8 | 736 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6510-00730 | 6510 | 2018-09-13 18:36 | Section 3 | Material | Not on List | Not on List | 300 | EA | 1.75 | 525 | Timber Products | 2018-09-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 401 - Safety Barriers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17914-001025 | 17914 | 2019-05-22 15:25 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 60 | Each | 23.14 | 1388.4 | Plastic Drainage | 2019-05-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17787-001025 | 17787 | 2019-05-20 17:36 | Section 5 | Material | Concrete Drainage | NULL | 9 | NULL | 289 | 2601 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18038-001025 | 18038 | 2019-05-24 10:43 | Section 5 | Material | Not on List | Not on List | 12 | rolls | NULL | 0 | Builders Merchants (General) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | NULL | Req - S5 Buyers
MREQ-18042-001025 | 18042 | 2019-05-24 10:24 | Section 5 | Material | Not on List | Not on List | 4 | No | NULL | 0 | Plastic Drainage | 2019-05-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18043-001025 | 18043 | 2019-05-24 11:21 | Core | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Electrical | 2019-05-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-6467-00711 | 6467 | 2018-09-13 10:31 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2273.5 | 2273.5 | Damage Charges | 2018-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18051-001025 | 18051 | 2019-05-24 12:27 | Section 2 | Material | Waste Management | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2019-05-31 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 5 | bundles | 9 | 45 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 5 | bundles | 9 | 45 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 5 | Bundles | 9 | 45 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 5 | Bundles | 9 | 45 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 5 | Bundles | 9 | 45 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6518-00730 | 6518 | 2018-09-14 07:20 | Section 3 | Material | Not on List | Not on List | 60 | Kerbs | 5.75 | 345 | Builders Merchants (General) | 2018-09-19 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 10 | Boxes | 10 | 100 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 100 | No. | 7.5 | 750 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 2 | Reels | 10 | 20 | Surveying Consumables | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 100 | No. | 1.5 | 150 | Surveying Consumables | 2019-05-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18061-001025 | 18061 | 2019-05-24 12:30 | Section 6 | Material | Not on List | Not on List | 100 | No. | 1 | 100 | Surveying Consumables | 2019-05-29 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17998-001025 | 17998 | 2019-05-23 16:51 | Section 4 | Material | Not on List | Not on List | 46 | Pack | 168.35 | 7744.1 | Concrete Accessories | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17998-001025 | 17998 | 2019-05-23 16:51 | Section 4 | Material | Not on List | Not on List | 52 | Pack | 11 | 572 | Concrete Accessories | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17998-001025 | 17998 | 2019-05-23 16:51 | Section 4 | Material | Not on List | Not on List | 40 | Hun | 1.88 | 75.2 | Concrete Accessories | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17998-001025 | 17998 | 2019-05-23 16:51 | Section 4 | Material | Not on List | Not on List | 40 | Hun | 1.88 | 75.2 | Concrete Accessories | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18071-001025 | 18071 | 2019-05-24 14:38 | Core | Material | Not on List | Not on List | 1 | NULL | 198 | 198 | Miscellaneous | 2019-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6388-00683 | 6388 | 2018-09-12 10:04 | Section 3 | Material | Not on List | Not on List | 1 | EA | 803.63 | 803.63 | Damage Charges | 2018-09-13 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17606-001025 | 17606 | 2019-05-17 11:40 | Section 4 | Material | Not on List | Not on List | 230 | Each | 43.39 | 9979.7 | Miscellaneous | 2019-05-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17606-001025 | 17606 | 2019-05-17 11:40 | Section 4 | Material | Not on List | Not on List | 50 | Each | 31.44 | 1572 | Miscellaneous | 2019-05-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17606-001025 | 17606 | 2019-05-17 11:40 | Section 4 | Material | NULL | Not on List | 1 | Each | 600 | 600 | Miscellaneous | 2019-05-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17852-001025 | 17852 | 2019-05-22 07:08 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18100-001025 | 18100 | 2019-05-28 09:25 | Core | Material | Not on List | Not on List | 1 | ea | 1081 | 1081 | Training | 2019-05-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17955-001025 | 17955 | 2019-05-23 10:06 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | 5ltre | 16.57 | 66.28 | Laboratory Equipment / Certification | 2019-05-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18102-001025 | 18102 | 2019-05-28 10:14 | Section 2 | Material | Not on List | Not on List | 0.436 | t | NULL | 0 | Rebar and Mesh | 2019-05-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | 9.58 | 191.6 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | 9.58 | 191.6 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 10 | each | 9.58 | 95.8 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 4 | each | 21.57 | 86.28 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | 7.1 | 142 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | 7.1 | 142 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 10 | each | NULL | 0 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | 3 | 60 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 10 | each | 3 | 30 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 10 | each | 9.58 | 95.8 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Signage | Not on List | 20 | each | NULL | 0 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Bags | 7.9 | 158 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | 20 Fire Buckets | 342.5 | 342.5 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | PPE, Small Tools and Consumables | Scraper Boot Galvanised C/W Brushes (746900) | 15 | Each | 10.19 | 152.85 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | PPE, Small Tools and Consumables | Plant Nappy 1000mm X 685mm All Blue (600200) | 10 | Each | 101.96 | 1019.6 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 51.48 | 102.96 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | Not on List | Not on List | 10 | Number | 3.54 | 35.4 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | NULL | Not on List | 150 | Each | 3.04 | 456 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | NULL | Not on List | 4 | Each | 67.2 | 268.8 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16176-001025 | 16176 | 2019-04-18 12:57 | Section 4 | Material | NULL | Not on List | 6 | Each | 44.92 | 269.52 | Miscellaneous | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18096-001025 | 18096 | 2019-05-28 07:18 | Section 2 | Material | NULL | Not on List | 165 | no. | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-05 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | Concrete Drainage | Not on List | 14 | NULL | 95.74 | 1340.36 | Concrete Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | Concrete Drainage | Not on List | 14 | NULL | 93.5 | 1309 | Concrete Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 45deg Junction (878038) | 10 | Each | 39.7 | 397 | Plastic Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | NULL | Polypipe 150mm x 150mm 90deg Junction (878008) | 3 | Each | 14.4 | 43.2 | Plastic Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 10 | Each | 1.98 | 19.8 | Plastic Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 30 | Each | 3.65 | 109.5 | Plastic Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6577-00749 | 6577 | 2018-09-17 10:27 | Section 3 | Material | Not on List | Not on List | 61 | NULL | 538 | 32818 | NULL | 2018-09-27 | Gate C - 1339702 - BN06 (East Coast Railway) Via Logistics Yard Access | BN06 - ECML Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17992-001025 | 17992 | 2019-05-23 14:23 | Section 6 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 6 | Each | 7.06 | 42.36 | Plastic Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-17940-001025 | 17940 | 2019-05-23 08:39 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 661.1 | 661.1 | Small Tools (Consumables) | 2019-05-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17875-001025 | 17875 | 2019-05-22 09:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 543.64 | 543.64 | Small Tools (Consumables) | 2019-05-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18117-001025 | 18117 | 2019-05-28 12:34 | Section 5 | Material | Waste Management | Construction Waste - Skip 12 cubic yard | 1 | Each | 2400 | 2400 | Waste (General) | 2019-05-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-17993-001025 | 17993 | 2019-05-23 16:06 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 11 | 55 | Laboratory Equipment / Certification | 2019-05-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6416-00697 | 6416 | 2018-09-12 13:56 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 50 | 50 | Professional Services | 2018-09-12 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN16 - New Barns Lane Overbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18128-001025 | 18128 | 2019-05-28 15:11 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18131-001025 | 18131 | 2019-05-28 15:31 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-05-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18131-001025 | 18131 | 2019-05-28 15:31 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-05-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18131-001025 | 18131 | 2019-05-28 15:31 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-05-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17884-001025 | 17884 | 2019-05-22 10:09 | Section 4 | Material | Not on List | Not on List | 5 | boxes 200 | 36 | 180 | Surveying Consumables | 2019-05-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17954-001025 | 17954 | 2019-05-23 09:50 | Section 4 | Material | NULL | Not on List | 8 | EA | 47.89 | 383.12 | Electrical | 2019-05-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 2301 - Bridge Deck Expansion Joints | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17954-001025 | 17954 | 2019-05-23 09:50 | Section 4 | Material | NULL | Not on List | 6 | EA | 47.89 | 287.34 | Electrical | 2019-05-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 2301 - Bridge Deck Expansion Joints | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18119-001025 | 18119 | 2019-05-28 12:57 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18119-001025 | 18119 | 2019-05-28 12:57 | Section 6 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-05-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18144-001025 | 18144 | 2019-05-28 17:21 | Core | Material | Not on List | Not on List | 1 | NULL | 852 | 852 | Miscellaneous | 2019-05-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18083-001025 | 18083 | 2019-05-27 06:44 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18116-001025 | 18116 | 2019-05-28 12:04 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-05-29 | RVP 424 - Grange Farm – A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18122-001025 | 18122 | 2019-05-28 13:48 | Section 4 | Material | Aggregate | Not on List | 60 | ton | 21.65 | 1299 | Aggregate | 2019-05-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18133-001025 | 18133 | 2019-05-28 15:58 | Section 4 | Material | Not on List | Not on List | 5 | Ea | 69.14 | 345.7 | Rebar and Mesh | 2019-06-19 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 240 | Tubes | 24.1 | 5784 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 65 | No. | 24.84 | 1614.6 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 40 | No. | 21.78 | 871.2 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 50 | No. | 5.6 | 280 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 45 | No. | 3.91 | 175.95 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19807-001025 | 19807 | 2019-06-26 16:55 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-19814-001025 | 19814 | 2019-06-27 07:32 | Core | Material | Not on List | Not on List | 1 | NULL | 189.6 | 190 | Miscellaneous | 2019-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-18426-001025 | 18426 | 2019-06-03 10:54 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | No - Reject | REQ - Buyers
MREQ-19726-001025 | 19726 | 2019-06-26 08:06 | Section 5 | Material | Concrete Drainage | Not on List | 10 | ea | 148.8 | 1488 | Concrete Drainage | 2019-07-01 | NULL | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19829-001025 | 19829 | 2019-06-27 08:52 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 134 | Each | 37.6 | 5038.4 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 134 | Each | 7.06 | 946.04 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 268 | Each | 2.97 | 795.96 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 182 | ea | 130.26 | 23707.32 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | NULL | ea | NULL | 0 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 182 | ea | 9.76 | 1776.32 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 140 | ea | 167.88 | 23503.2 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | NULL | NULL | NULL | 0 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6952-00752 | 6952 | 2018-09-25 08:33 | Section 3 | Material | Not on List | Not on List | 2 | Ea | 4.35 | 8.7 | Miscellaneous | 2018-09-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 140 | ea | 16.41 | 2297.4 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 132 | ea | 11.51 | 1519.32 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 132 | ea | 1.98 | 261.36 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19524-001025 | 19524 | 2019-06-21 12:29 | Section 4 | Material | Not on List | Not on List | 264 | ea | 0.91 | 240.24 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19753-001025 | 19753 | 2019-06-26 11:02 | Section 5 | Material | Kerbs | NULL | 18 | ea | 27.9 | 502.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-01 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19791-001025 | 19791 | 2019-06-26 16:06 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19709-001025 | 19709 | 2019-06-25 17:08 | Section 3 | Material | Not on List | Not on List | 1 | No. | 455.2 | 455.2 | Surveying Consumables | 2019-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19821-001025 | 19821 | 2019-06-27 08:11 | Section 5 | Material | Not on List | NULL | 50 | EA | 6.31 | 315.5 | Builders Merchants (General) | 2019-06-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19844-001025 | 19844 | 2019-06-27 11:58 | Section 2 | Material | Not on List | Not on List | 1 | each | 268.5 | 269 | Miscellaneous | 2019-06-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6978-00752 | 6978 | 2018-09-25 15:31 | Section 4 | Material | Aggregate | 6F5 | 1500 | Tonnes | 14.65 | 21975 | Aggregate | 2018-09-27 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 606 - Import | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | EACH | NULL | 0 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 15 | Each | 8.55 | 128 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 15 | Each | 8.55 | 128 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 15 | Each | 8.55 | 128 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19848-001025 | 19848 | 2019-06-26 17:37 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 15 | Each | 8.55 | 128 | PPE | 2019-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19797-001025 | 19797 | 2019-06-26 16:35 | Section 3 | Material | Not on List | Not on List | 56 | No | 2.31 | 129.36 | Builders Merchants (General) | 2019-06-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6978-00752 | 6978 | 2018-09-25 15:31 | Section 4 | Material | Aggregate | 6F5 | 1500 | Tonnes | 14.65 | 21975 | Aggregate | 2018-09-28 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 606 - Import | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-19696-001025 | 19696 | 2019-06-25 14:54 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 920 | Each | 2.31 | 2125.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19659-001025 | 19659 | 2019-06-25 08:43 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 4 | Each | 70.99 | 283.96 | Concrete Drainage | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-19659-001025 | 19659 | 2019-06-25 08:43 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 10 | Each | 44.64 | 446.4 | Concrete Drainage | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-19659-001025 | 19659 | 2019-06-25 08:43 | Section 3 | Material | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 70 | Each | 17.14 | 1199.8 | Concrete Drainage | 2019-06-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-19839-001025 | 19839 | 2019-06-27 10:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 650 | Each | 1 | 650 | PPE | 2019-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19742-001025 | 19742 | 2019-06-26 09:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 509 | 509 | Laboratory Equipment / Certification | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19742-001025 | 19742 | 2019-06-26 09:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 220 | 220 | Laboratory Equipment / Certification | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19742-001025 | 19742 | 2019-06-26 09:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 485 | 485 | Laboratory Equipment / Certification | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19742-001025 | 19742 | 2019-06-26 09:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 315 | 315 | Laboratory Equipment / Certification | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19742-001025 | 19742 | 2019-06-26 09:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 350 | 350 | Laboratory Equipment / Certification | 2019-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19734-001025 | 19734 | 2019-06-26 08:58 | Core | Material | NULL | NULL | 1 | EAch | 1806.3 | 1806.3 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19899-001025 | 19899 | 2019-06-28 08:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 199 | 199 | Miscellaneous | 2019-07-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-19749-001025 | 19749 | 2019-06-26 10:47 | Section 4 | Material | Not on List | Not on List | 1 | Each | 67.5 | 67.5 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19764-001025 | 19764 | 2019-06-26 13:13 | Section 4 | Material | Not on List | Not on List | 25 | Number | 158.88 | 3972 | Miscellaneous | 2019-07-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19764-001025 | 19764 | 2019-06-26 13:13 | Section 4 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 16 | Each | 116.88 | 1870.08 | Geotextiles | 2019-07-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19721-001025 | 19721 | 2019-06-26 07:44 | Section 2 | Material | Not on List | Not on List | 25 | pots | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19721-001025 | 19721 | 2019-06-26 07:44 | Section 2 | Material | Not on List | Not on List | 5 | 500ml tin | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19721-001025 | 19721 | 2019-06-26 07:44 | Section 2 | Material | Not on List | Not on List | 3 | 25l drum | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19721-001025 | 19721 | 2019-06-26 07:44 | Section 2 | Material | Not on List | Not on List | 2 | number | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19739-001025 | 19739 | 2019-06-26 09:25 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-19915-001025 | 19915 | 2019-06-28 10:23 | Section 6 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Miscellaneous | 2019-07-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-19837-001025 | 19837 | 2019-06-27 10:17 | Section 4 | Material | Signage | Not on List | 3 | Each | 19.1712 | 57.51 | Miscellaneous | 2019-07-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5096-0040 | 5096 | 2018-08-14 17:48 | Section 3 | Material | Not on List | Not on List | 1 | each | 552.2 | 552.2 | Damage Charges | 2018-08-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6970-00752 | 6970 | 2018-09-25 14:06 | Section 3 | Material | Not on List | Not on List | 8 | ea | 57.5 | 460 | Damage Charges | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19177-001025 | 19177 | 2019-06-14 16:59 | Section 2 | Material | NULL | 2440x1220x18mm Shuttering Ply (683573) | 20 | Each | 24.32 | 486.4 | Concrete Accessories | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19177-001025 | 19177 | 2019-06-14 16:59 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Concrete Accessories | 2019-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19840-001025 | 19840 | 2019-06-27 11:23 | Section 2 | Material | Not on List | Not on List | 50 | Sheets | NULL | 0 | Concrete Accessories | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19784-001025 | 19784 | 2019-06-26 15:40 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-06-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-19788-001025 | 19788 | 2019-06-26 15:57 | Section 4 | Material | Not on List | Not on List | 50 | rolls | 189 | 9450 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19788-001025 | 19788 | 2019-06-26 15:57 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 100 | Each | 10.5 | 1050 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19788-001025 | 19788 | 2019-06-26 15:57 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 200 | Each | 1.98 | 396 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19788-001025 | 19788 | 2019-06-26 15:57 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 400 | Each | 0.91 | 364 | Plastic Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19882-001025 | 19882 | 2019-06-28 07:37 | Section 5 | Material | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 16 | Each | 4.42 | 70.72 | Not Sure | 2019-07-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19936-001025 | 19936 | 2019-06-28 14:53 | Section 2 | Material | Not on List | Not on List | 1 | each | 46 | 46 | Laboratory Equipment / Certification | 2019-07-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19942-001025 | 19942 | 2019-06-28 14:59 | Section 6 | Material | Signage | Not on List | 2 | each | 240.55 | 481 | Professional Services | 2019-07-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19942-001025 | 19942 | 2019-06-28 14:59 | Section 6 | Material | Signage | Not on List | 2 | each | 240.55 | 481 | Professional Services | 2019-07-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-19608-001025 | 19608 | 2019-06-24 13:18 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19795-001025 | 19795 | 2019-06-26 16:36 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16961-001025 | 16961 | 2019-05-07 15:53 | Section 4 | Material | Not on List | Not on List | 1 | Each | 21895.35 | 21895.35 | Miscellaneous | 2019-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19930-001025 | 19930 | 2019-06-28 14:16 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 22.5deg (878083) | 2 | Each | 81.47 | 162.94 | Plastic Drainage | 2019-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19930-001025 | 19930 | 2019-06-28 14:16 | Section 4 | Material | Twinwall | Not on List | 1 | Each | 214.39 | 214.39 | Plastic Drainage | 2019-07-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20004-001025 | 20004 | 2019-07-01 12:44 | Section 1 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Geotextiles | 2019-07-02 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 606 - Import | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | NULL | Not on List | 1 | No | 13.08 | 13.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 10 | Packs | 10.5 | 105 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-13802-001025 | 13802 | 2019-03-11 16:07 | Section 5 | Material | Signage | Not on List | 1 | each | 2597.16 | 2597.16 | Miscellaneous | 2019-03-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13591-001025 | 13591 | 2019-03-06 16:48 | Section 4 | Material | Not on List | Not on List | 1 | Each | 661.38 | 661.38 | Miscellaneous | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13786-001025 | 13786 | 2019-03-11 14:44 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 1 | Each | 150 | 150 | Waste (General) | 2019-03-18 | RVP 403 - 1339621 - Borrow Pit 5 A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13820-001025 | 13820 | 2019-03-12 07:07 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 50 | NULL | 3.59 | 180 | Miscellaneous | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13581-001025 | 13581 | 2019-03-06 16:08 | Core | Material | Not on List | Not on List | 1 | Each | 7750.5 | 7750.5 | Laboratory Equipment / Certification | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13794-001025 | 13794 | 2019-03-11 15:11 | Section 3 | Material | PPE, Small Tools and Consumables | Helmet Safety Jsp Evolite Skyworker White (272558) | 80 | Each | 28.8 | 2304 | PPE | 2019-03-13 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13770-001025 | 13770 | 2019-03-11 11:46 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 457.69 | 457.69 | PPE | 2019-03-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13770-001025 | 13770 | 2019-03-11 11:46 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 503.53 | 503.53 | Small Tools (Consumables) | 2019-03-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5793-00473 | 5793 | 2018-08-30 09:01 | Section 3 | Material | Not on List | Not on List | 10 | Packs | 10.5 | 105 | Surveying Consumables | 2018-09-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 3 Buyers
MREQ-13567-001025 | 13567 | 2019-03-06 14:56 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 28.8 | 288 | Small Tools (Consumables) | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13775-001025 | 13775 | 2019-03-11 12:32 | Section 3 | Material | Not on List | Not on List | 1 | EA | 382.07 | 382.07 | Damage Charges | 2019-03-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12933-001025 | 12933 | 2019-02-22 08:35 | Core | Material | Not on List | Not on List | 1 | number | 40 | 40 | Miscellaneous | 2019-02-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 110 - Welfare Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13531-001025 | 13531 | 2019-03-06 09:56 | Section 4 | Material | Not on List | Not on List | 1 | Each | 464.16 | 464.16 | Miscellaneous | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13496-001025 | 13496 | 2019-03-05 12:57 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1972 | 1972 | Miscellaneous | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13837-001025 | 13837 | 2019-03-12 09:55 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13839-001025 | 13839 | 2019-03-12 10:03 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-13 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S1 Buyers
MREQ-13840-001025 | 13840 | 2019-03-12 10:09 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13540-001025 | 13540 | 2019-03-06 11:15 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 3484 | 3484 | Miscellaneous | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13573-001025 | 13573 | 2019-03-06 15:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 626.39 | 626.39 | Miscellaneous | 2019-03-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13774-001025 | 13774 | 2019-03-11 12:24 | Core | Material | Not on List | Not on List | 1 | Each | 795 | 795 | Training | 2019-04-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12848-001025 | 12848 | 2019-02-21 12:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1158.07 | 1158.07 | Miscellaneous | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13851-001025 | 13851 | 2019-03-12 11:39 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13853-001025 | 13853 | 2019-03-12 11:50 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-4994-009 | 4994 | 2018-08-13 15:28 | Section 3 | Material | Not on List | NULL | 4 | No. | 82.5 | 0 | Builders Merchants (General) | 2018-08-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12845-001025 | 12845 | 2019-02-21 12:09 | Section 4 | Material | Not on List | Not on List | 1 | Each | 423.38 | 423.38 | Miscellaneous | 2019-02-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13784-001025 | 13784 | 2019-03-11 14:09 | Section 3 | Material | Not on List | Not on List | 50 | sht | 22.5 | 1125 | Timber Products | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13784-001025 | 13784 | 2019-03-11 14:09 | Section 3 | Material | Not on List | Not on List | 30 | ea | 4.08 | 122.4 | Timber Products | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13784-001025 | 13784 | 2019-03-11 14:09 | Section 3 | Material | Not on List | Not on List | 30 | ea | 5.95 | 178.5 | Timber Products | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13862-001025 | 13862 | 2019-03-12 13:12 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Miscellaneous | 2019-03-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13862-001025 | 13862 | 2019-03-12 13:12 | Section 4 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Miscellaneous | 2019-03-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13862-001025 | 13862 | 2019-03-12 13:12 | Section 4 | Material | Not on List | Not on List | 20 | m | NULL | 0 | Miscellaneous | 2019-03-25 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12602-001025 | 12602 | 2019-02-18 07:18 | Section 4 | Material | Not on List | Not on List | 1 | Each | 6231.62 | 6231.62 | Miscellaneous | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Waste (Recycling) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Dustpan And Brush Set Blue Ref P.8003/P (540001) | 15 | Each | 0.75 | 11 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Boxes | NULL | 0 | PPE | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pack | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27526-001025 | 27526 | 2019-12-10 11:22 | Section 4 | Material | Not on List | Not on List | 10 | Number. | 11.5 | 115 | Surveying Consumables | 2019-12-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27526-001025 | 27526 | 2019-12-10 11:22 | Section 4 | Material | Not on List | Not on List | 10 | Number. | 9 | 90 | Surveying Consumables | 2019-12-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27541-001025 | 27541 | 2019-12-10 15:28 | Section 4 | Material | Not on List | Not on List | 4 | NULL | 243 | 972 | Builders Merchants (General) | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27549-001025 | 27549 | 2019-12-10 17:28 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 176.22 | 176 | Small Tools (Consumables) | 2019-12-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27549-001025 | 27549 | 2019-12-10 17:28 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 193.4 | 193 | PPE | 2019-12-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27549-001025 | 27549 | 2019-12-10 17:28 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 180.93 | 181 | Janitorial | 2019-12-13 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27568-001025 | 27568 | 2019-12-11 10:45 | Section 6 | Material | Not on List | Not on List | 2 | NULL | 153.68 | 307 | Miscellaneous | 2019-12-19 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27572-001025 | 27572 | 2019-12-11 13:02 | Section 2 | Material | Not on List | Not on List | 1 | ea | 2838.55 | 2839 | Professional Services | 2019-11-29 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27573-001025 | 27573 | 2019-12-11 13:15 | Section 5 | Material | Not on List | Not on List | 1 | ea | 805.24 | 805 | Professional Services | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27574-001025 | 27574 | 2019-12-11 13:24 | Core | Material | Not on List | Not on List | 1 | No | 397.58 | 398 | Professional Services | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27576-001025 | 27576 | 2019-12-11 14:13 | Section 4 | Material | Not on List | Not on List | 1 | no | 5521.63 | 5522 | Professional Services | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27555-001025 | 27555 | 2019-12-11 07:40 | Section 4 | Material | Not on List | Not on List | 40 | Each | 19.51 | 780.4 | Builders Merchants (General) | 2019-12-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27555-001025 | 27555 | 2019-12-11 07:40 | Section 4 | Material | Not on List | Not on List | 2 | Each | 33.35 | 66.7 | Builders Merchants (General) | 2019-12-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27585-001025 | 27585 | 2019-12-11 16:15 | Section 6 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-12-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27606-001025 | 27606 | 2019-12-12 10:15 | Section 5 | Material | Not on List | Not on List | 1 | No | 183.27 | 183 | Professional Services | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27607-001025 | 27607 | 2019-12-12 10:40 | Section 5 | Material | Not on List | Not on List | 1 | No | 483.47 | 483 | Professional Services | 2019-11-29 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27617-001025 | 27617 | 2019-12-12 12:00 | Section 4 | Material | Not on List | Not on List | 1 | No | 1297.76 | 1298 | Professional Services | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27619-001025 | 27619 | 2019-12-12 12:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 25 | NULL | 1.2 | 30 | Small Tools (Consumables) | 2019-12-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27619-001025 | 27619 | 2019-12-12 12:27 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | 11.52 | 58 | Small Tools (Consumables) | 2019-12-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27622-001025 | 27622 | 2019-12-12 13:39 | Section 5 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 80 | Each | 3.56 | 285 | Builders Merchants (General) | 2019-12-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27623-001025 | 27623 | 2019-12-12 13:42 | Section 4 | Material | Not on List | Not on List | 25 | NULL | NULL | 0 | Plastic Drainage | 2020-01-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-27623-001025 | 27623 | 2019-12-12 13:42 | Section 4 | Material | Not on List | Not on List | 25 | NULL | NULL | 0 | Plastic Drainage | 2020-01-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-27623-001025 | 27623 | 2019-12-12 13:42 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2020-01-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-27496-001025 | 27496 | 2019-12-09 15:54 | Section 4 | Material | Not on List | Not on List | 2 | Each | 162.11 | 324.22 | Concrete Drainage | 2019-12-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27496-001025 | 27496 | 2019-12-09 15:54 | Section 4 | Material | NULL | Not on List | 1 | Each | 95 | 95 | Concrete Drainage | 2019-12-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27631-001025 | 27631 | 2019-12-12 16:25 | Core | Material | Not on List | Not on List | 1 | NULL | 67.2 | 67 | Office Supplies | 2019-12-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27600-001025 | 27600 | 2019-12-12 08:29 | Section 6 | Material | Not on List | Not on List | 2 | ea | 90.14 | 180.28 | Concrete Accessories | 2019-12-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 1 | Each | 812.44 | 812.44 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 1 | Each | 230.22 | 230.22 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 1 | Each | 738.67 | 738.67 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 1 | Each | 265.78 | 265.78 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 2 | Each | 80 | 160 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27590-001025 | 27590 | 2019-12-11 16:30 | Section 5 | Material | NULL | NULL | 1 | Each | 75 | 75 | Concrete Drainage | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 42 | Each | 10.34 | 434.28 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 30 | Each | 1.98 | 59.4 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 121 | Each | 24.99 | 3023.79 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 200 | Each | 3.65 | 730 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 460 | Each | 2 | 920 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 41 | Each | 37.6 | 1541.6 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 80 | Each | 7.06 | 564.8 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 190 | Each | 2.97 | 564.3 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 25 | Each | 130.26 | 3256.5 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 225mm x 150mm Ridgidrain 45deg Junction (878038) | 20 | Each | 42.87 | 857.4 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 10 | Each | 42.87 | 428.7 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Not on List | 12 | Each | 42.88 | 514.56 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 300mm x 150mm Ridgidrain 45deg Junction (878090) | 23 | Each | 47.96 | 1103.08 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Polypipe 300mm x 150mm Ridgidrain 90deg Junction (878089) | 5 | Each | 44.41 | 222.05 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Not on List | 2 | Each | 47.96 | 95.92 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27458-001025 | 27458 | 2019-12-08 09:51 | Section 6 | Material | Twinwall | Not on List | 5 | Each | 177.52 | 887.6 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | CPM 1500 Cover Slab 750x600 Opening (528492) | 37 | Each | 61.54 | 2276.98 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 25 | Each | 38.08 | 952 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 14 | Each | 55.13 | 771.82 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 750 D/S (913226) | 2 | Each | 63.93 | 127.86 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | Not on List | 45 | Each | 257.78 | 11600.1 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | Not on List | 120 | Each | 17.15 | 2058 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Concrete Drainage | Not on List | 5 | Each | 33.32 | 166.6 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Saint Gobain Castings | Not on List | 31 | Each | 102 | 3162 | Concrete Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Twinwall | Polypipe Road Gully 450mm x 900mm (573005) | 70 | Each | 15.17 | 1061.9 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Twinwall | Not on List | 90 | Each | 5.95 | 535.5 | Plastic Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27459-001025 | 27459 | 2019-12-08 11:19 | Section 6 | Material | Saint Gobain Castings | 430x370x100 D400 Watershed GG&F (923947) | 90 | Each | 31.37 | 2823.3 | Ductile Drainage | 2019-12-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27628-001025 | 27628 | 2019-12-12 15:27 | Section 5 | Material | NULL | NULL | 2 | Each | 112 | 224 | Miscellaneous | 2020-01-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27628-001025 | 27628 | 2019-12-12 15:27 | Section 5 | Material | NULL | NULL | 2 | Each | 364 | 728 | Miscellaneous | 2020-01-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27567-001025 | 27567 | 2019-12-11 09:43 | Section 5 | Material | NULL | NULL | 1 | Each | 4140 | 4140 | Miscellaneous | 2019-12-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27491-001025 | 27491 | 2019-12-09 15:50 | Section 5 | Material | Aggregate | Not on List | 8425.2 | Tonne | 5.5 | 46338.6 | Aggregate | 2019-12-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27065-001025 | 27065 | 2019-11-27 16:57 | Section 3 | Material | Kerbs | Not on List | 1 | No | 1200 | 1200 | Professional Services | 2019-11-28 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | BN13 - West Brook Underbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27243-001025 | 27243 | 2019-12-03 09:10 | Core | Material | NULL | NULL | 1 | Each | 675 | 675 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27249-001025 | 27249 | 2019-12-03 09:50 | Core | Material | NULL | NULL | 1 | Each | 160 | 160 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27687-001025 | 27687 | 2019-12-16 10:37 | Core | Material | Not on List | Not on List | 1 | NULL | 487.5 | 488 | Miscellaneous | 2019-12-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27300-001025 | 27300 | 2019-12-03 17:41 | Core | Material | NULL | NULL | 1 | Each | 1137.5 | 1138 | Surveying Consumables | 2019-12-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 113 - Survey Equipment Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26943-001025 | 26943 | 2019-11-25 12:22 | Core | Material | Not on List | Not on List | 1 | application | 515 | 515 | Miscellaneous | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27334-001025 | 27334 | 2019-12-04 14:50 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27715-001025 | 27715 | 2019-12-17 08:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 4 | Each | 58.27 | 233.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-16 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 4 | Each | 13.08 | 52.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-16 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 1 | Each | 80 | 80 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-16 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 2 | Each | 164.35 | 328.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-12-16 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 2 | Each | 30.44 | 60.88 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 4 | Each | 17.32 | 69.28 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 46 | Each | 12 | 552 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 2 | Each | 21.5 | 43 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27618-001025 | 27618 | 2019-12-12 11:47 | Section 5 | Material | NULL | NULL | 1 | Each | 35 | 35 | Concrete Hard Landscaping (Kerbs, Slabs) | NULL | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27732-001025 | 27732 | 2019-12-17 14:15 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 289.03 | 289 | PPE | 2019-12-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27732-001025 | 27732 | 2019-12-17 14:15 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 185.08 | 185 | Small Tools (Consumables) | 2019-12-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27732-001025 | 27732 | 2019-12-17 14:15 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 109.98 | 110 | Janitorial | 2019-12-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27692-001025 | 27692 | 2019-12-16 07:24 | Section 4 | Material | Not on List | Not on List | 204 | Each | 14.43 | 2943.72 | Builders Merchants (General) | 2020-01-31 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27692-001025 | 27692 | 2019-12-16 07:24 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1200 | 1200 | Builders Merchants (General) | 2019-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 208 | Each | 7.5 | 1560 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 208 | Each | 49.95 | 10389.6 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 26 | Each | 39.6 | 1029.6 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 1 | Each | 600 | 600 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 120 | Each | 95 | 11400 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 50 | Each | 85 | 4250 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27056-001025 | 27056 | 2019-11-27 15:56 | Core | Material | NULL | NULL | 1 | Each | 350 | 350 | Miscellaneous | 2019-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7312-001022 | 7312 | 2018-10-02 17:29 | Section 4 | Material | Not on List | Not on List | 30 | Each | 44 | 1320 | Not Sure | 2018-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27759-001025 | 27759 | 2019-12-18 11:23 | Section 4 | Material | Not on List | Not on List | 1 | Number. | 630.54 | 631 | Surveying Consumables | 2019-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27763-001025 | 27763 | 2019-12-18 12:05 | Section 4 | Material | Not on List | Not on List | 1 | ea | 883 | 883 | Professional Services | 2019-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27680-001025 | 27680 | 2019-12-16 08:06 | Section 4 | Material | Not on List | Not on List | 1 | Each | 187687.9 | 187687.9 | Professional Services | 2019-12-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27758-001025 | 27758 | 2019-12-18 10:58 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 48.92 | 489.2 | Concrete Drainage | 2020-01-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27758-001025 | 27758 | 2019-12-18 10:58 | Section 4 | Material | Not on List | Not on List | 10 | Each | 70.62 | 706.2 | Concrete Drainage | 2020-01-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27758-001025 | 27758 | 2019-12-18 10:58 | Section 4 | Material | Not on List | Not on List | 5 | Each | 162.11 | 810.55 | Concrete Drainage | 2020-01-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27793-001025 | 27793 | 2019-12-19 12:03 | Core | Material | PPE, Small Tools and Consumables | Not on List | 200 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27794-001025 | 27794 | 2019-12-19 12:05 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-12-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27808-001025 | 27808 | 2019-12-19 16:21 | Section 6 | Material | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 19 | Each | 241.48 | 4588.12 | Concrete Drainage | 2020-01-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27814-001025 | 27814 | 2019-12-20 13:31 | Section 4 | Material | Not on List | Not on List | 1 | No | 4141.26 | 4141 | Professional Services | 2019-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27858-001025 | 27858 | 2020-01-06 09:59 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 60 | 60 | Surveying Consumables | 2020-01-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27861-001025 | 27861 | 2020-01-06 11:15 | Core | Material | Not on List | Not on List | 1 | NULL | 414 | 414 | Miscellaneous | 2020-01-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27864-001025 | 27864 | 2020-01-06 11:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-01-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27896-001025 | 27896 | 2020-01-07 09:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 228.6 | 229 | PPE | 2020-01-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27896-001025 | 27896 | 2020-01-07 09:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 524.1 | 524 | Janitorial | 2020-01-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27896-001025 | 27896 | 2020-01-07 09:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 405.6 | 406 | Small Tools (Consumables) | 2020-01-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27900-001025 | 27900 | 2020-01-07 11:23 | Core | Material | Not on List | Not on List | 4 | Number | 295 | 1180 | Surveying Consumables | 2020-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27906-001025 | 27906 | 2020-01-07 13:35 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27916-001025 | 27916 | 2020-01-07 16:35 | Section 4 | Material | Not on List | Not on List | 5 | Number | 8.67 | 43 | Surveying Consumables | 2020-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27916-001025 | 27916 | 2020-01-07 16:35 | Section 4 | Material | Not on List | Not on List | 5 | Number | 22 | 110 | Surveying Consumables | 2020-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27922-001025 | 27922 | 2020-01-07 19:45 | Section 4 | Material | Not on List | Not on List | 160 | each | NULL | 0 | Miscellaneous | 2020-01-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27927-001025 | 27927 | 2020-01-08 07:33 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 1 | pack | 24.32 | 24 | Timber Products | 2020-01-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27931-001025 | 27931 | 2020-01-08 08:50 | Section 2 | Material | Not on List | Not on List | 10 | ea | NULL | 0 | Concrete Accessories | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27932-001025 | 27932 | 2020-01-08 09:08 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-01-13 | 1333676 Swavesey Main Compound, J28 A14, High St Boxworth, CB23 4NG | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27933-001025 | 27933 | 2020-01-08 10:28 | Section 4 | Material | Aggregate | Not on List | 20 | Tonne | NULL | 0 | Aggregate | 2020-01-09 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27777-001025 | 27777 | 2019-12-18 15:00 | Section 5 | Material | Not on List | Not on List | 1 | No | 300.24 | 300.24 | Professional Services | 2019-12-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27815-001025 | 27815 | 2019-12-20 13:37 | Section 5 | Material | Not on List | Not on List | 1 | No | 297.16 | 297.16 | Professional Services | 2019-12-20 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27816-001025 | 27816 | 2019-12-20 13:48 | Core | Material | Not on List | Not on List | 1 | No | 344.58 | 344.58 | Professional Services | 2019-12-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27944-001025 | 27944 | 2020-01-08 16:08 | Section 6 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 6 | Each | 115.78 | 695 | Geotextiles | 2020-01-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-27716-001025 | 27716 | 2019-12-17 08:59 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13876-001025 | 13876 | 2019-03-12 14:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13138-001025 | 13138 | 2019-02-26 17:14 | Section 2 | Material | NULL | Not on List | 160 | units | NULL | 0 | Concrete Drainage | 2019-03-17 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13882-001025 | 13882 | 2019-03-12 15:39 | Section 5 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 3 | Price Per Thousand | 345 | 1035 | Blocks and Bricks | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13882-001025 | 13882 | 2019-03-12 15:39 | Section 5 | Material | Bricks/Blocks | Not on List | 1 | NULL | NULL | 0 | Blocks and Bricks | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13807-001025 | 13807 | 2019-03-11 16:23 | Section 2 | Material | NULL | Not on List | 65.9 | m2 | NULL | 0 | Blocks and Bricks | 2019-03-15 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2A - Roadworks - A1 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13801-001025 | 13801 | 2019-03-11 15:53 | Section 2 | Material | Not on List | Not on List | 12.097 | tonnes | NULL | 0 | NULL | 2019-03-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13401-001025 | 13401 | 2019-03-04 13:09 | Section 4 | Material | Not on List | Not on List | 10.5 | Each | 35 | 367.5 | Miscellaneous | 2019-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13896-001025 | 13896 | 2019-03-12 18:01 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 2 | Each | 32.74 | 65 | Blocks and Bricks | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13897-001025 | 13897 | 2019-03-13 06:42 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13900-001025 | 13900 | 2019-03-13 07:01 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-14 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-13589-001025 | 13589 | 2019-03-06 16:36 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 11.6 | 69.6 | PPE | 2019-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13756-001025 | 13756 | 2019-03-11 10:33 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1465.34 | 1465.34 | Small Tools (Consumables) | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13748-001025 | 13748 | 2019-03-11 09:01 | Section 2 | Material | Not on List | Not on List | 3 | NULL | 150 | 450 | Miscellaneous | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1503 - Cables, Joints & Terminations | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13870-001025 | 13870 | 2019-03-12 14:33 | Section 4 | Material | Not on List | Not on List | 2 | Bag | 8.35 | 16.7 | Builders Merchants (General) | 2019-03-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13870-001025 | 13870 | 2019-03-12 14:33 | Section 4 | Material | Not on List | Not on List | 150 | Each | 0.04 | 6 | Builders Merchants (General) | 2019-03-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13870-001025 | 13870 | 2019-03-12 14:33 | Section 4 | Material | Not on List | Not on List | 150 | Each | 0.06 | 9 | Builders Merchants (General) | 2019-03-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13899-001025 | 13899 | 2019-03-13 06:51 | Section 2 | Material | Concrete Drainage | Not on List | 90 | linier m | NULL | 0 | Concrete Drainage | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13906-001025 | 13906 | 2019-03-13 08:23 | Section 3 | Material | Aggregate | Type 1 | 6000 | Tonnes | 21.65 | 129900 | Aggregate | 2019-03-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13274-001025 | 13274 | 2019-02-28 15:07 | Core | Material | Not on List | Not on List | 1 | ea | 24000 | 24000 | Office Supplies | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13828-001025 | 13828 | 2019-03-12 08:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 748.68 | 748.68 | Small Tools (Consumables) | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Skip 12 cubic yard | 3 | Each | 195 | 585 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 9 | Each | 370 | 3330 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 2 | Each | 150 | 300 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 2.54 | Each | 115 | 292.1 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12719-001025 | 12719 | 2019-02-19 14:57 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (General) | 2019-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13825-001025 | 13825 | 2019-03-12 08:12 | Section 3 | Material | Not on List | Not on List | 16 | Tabs | 59.14 | 946.24 | Builders Merchants (General) | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | 162.11 | 162.11 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | 121.58 | 121.58 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Concrete Drainage | CPM 1800 Cover Slab 600x600 Opening (985438) | 1 | Each | 149.8 | 149.8 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Concrete Drainage | CPM 675mm Concrete Rocker (249355) | 2 | Each | 178.55 | 357.1 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Concrete Drainage | CPM 675mm Concrete Socket (890394) | 1 | Each | 178.55 | 178.55 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13898-001025 | 13898 | 2019-03-13 06:27 | Section 5 | Material | Not on List | NULL | 1 | SUM | 200 | 200 | Concrete Drainage | 2019-03-14 | WB5/6 Works Access, A14 Westbound, On Left at Jcn 32 | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13599-001025 | 13599 | 2019-03-06 17:42 | Section 2 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 20 | Rolls | 175 | 3500 | Plastic Drainage | 2019-03-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13599-001025 | 13599 | 2019-03-06 17:42 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 54 | single pipes | 34.82 | 1880.28 | Plastic Drainage | 2019-03-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13599-001025 | 13599 | 2019-03-06 17:42 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 70 | Each | 6.54 | 457.8 | Plastic Drainage | 2019-03-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13599-001025 | 13599 | 2019-03-06 17:42 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 100 | single pipes | 10.5 | 1050 | Plastic Drainage | 2019-03-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13599-001025 | 13599 | 2019-03-06 17:42 | Section 2 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 100 | Each | 1.84 | 184 | Plastic Drainage | 2019-03-12 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13958-001025 | 13958 | 2019-03-13 15:05 | Section 2 | Material | Not on List | Not on List | 1 | 1 no. | NULL | 0 | Miscellaneous | 2019-03-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | IMO - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13908-001025 | 13908 | 2019-03-13 08:27 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 551.76 | 551.76 | Small Tools (Consumables) | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5072-0027 | 5072 | 2018-08-14 14:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 72 | Each | 6.29 | 0 | Miscellaneous | 2018-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13974-001025 | 13974 | 2019-03-13 17:18 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 8 | NULL | NULL | 0 | Builders Merchants (General) | 2019-03-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 96 | Each | 5.43 | 521.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 64 | Each | 5.43 | 347.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 14.33 | 57.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 12 | Each | 5.43 | 65.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 208 | Each | 5.43 | 1129.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 28 | Each | 5.43 | 152.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 55 | Each | 5.43 | 298.65 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 32 | Each | 5.43 | 173.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 12 | Each | 5.43 | 65.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 96 | Each | 5.43 | 521.28 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 20 | Each | 5.43 | 108.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 14.33 | 57.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 5600 | Each | 3.52 | 19712 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 10.08 | 40.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 10.08 | 40.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 20 | Each | 5.43 | 108.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 10 | Each | 11.71 | 117.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 11.71 | 46.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 20 | Each | 5.43 | 108.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 10 | Each | 11.71 | 117.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4 | Each | 11.71 | 46.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-03-18 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 96 | Each | 4.22 | 405.12 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 14 | Each | 14.81 | 207.34 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 4600 | Each | 1.5 | 6900 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 8 | Each | 14.81 | 118.48 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13738-001025 | 13738 | 2019-03-11 08:39 | Section 4 | Material | NULL | NULL | 19 | Each | 30 | 570 | NULL | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13988-001025 | 13988 | 2019-03-14 06:58 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-13994-001025 | 13994 | 2019-03-14 08:19 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Waste (General) | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-13961-001025 | 13961 | 2019-03-13 15:30 | Section 2 | Material | NULL | Not on List | 12 | rolls | 136 | 1632 | Geotextiles | 2019-03-14 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13961-001025 | 13961 | 2019-03-13 15:30 | Section 2 | Material | NULL | Not on List | 12 | no | 7.17 | 86.04 | NULL | NULL | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13961-001025 | 13961 | 2019-03-13 15:30 | Section 2 | Material | NULL | Not on List | 1 | NO | 120 | 120 | NULL | NULL | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13937-001025 | 13937 | 2019-03-13 12:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 650 | 650 | Concrete Accessories | 2019-03-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13937-001025 | 13937 | 2019-03-13 12:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 570 | 570 | Concrete Accessories | 2019-03-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14007-001025 | 14007 | 2019-03-14 09:05 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-15 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S1 Buyers
MREQ-14011-001025 | 14011 | 2019-03-14 09:10 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1000 | number | NULL | 0 | Concrete Accessories | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14011-001025 | 14011 | 2019-03-14 09:10 | Section 2 | Material | Not on List | Not on List | 4 | number | NULL | 0 | Concrete Accessories | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14011-001025 | 14011 | 2019-03-14 09:10 | Section 2 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Concrete Accessories | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15851-001025 | 15851 | 2019-04-15 12:13 | Core | Material | Not on List | Not on List | 4 | NULL | 60.81 | 243 | Miscellaneous | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Operations Rejected | No - Reject | NULL | REQ - Buyers
MREQ-15858-001025 | 15858 | 2019-04-15 12:53 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Builders Merchants (General) | 2019-04-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-15787-001025 | 15787 | 2019-04-12 14:24 | Section 3 | Material | Not on List | Not on List | 16 | 2.5L can | 64.41 | 1030.56 | Builders Merchants (General) | 2019-04-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 28 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15870-001025 | 15870 | 2019-04-15 13:33 | Section 5 | Material | Not on List | Not on List | 62 | NULL | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15868-001025 | 15868 | 2019-04-15 14:35 | Section 4 | Material | NULL | NULL | NULL | NULL | 7858.5 | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6165-00629 | 6165 | 2018-09-07 08:25 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 1 | 2 | Rebar and Mesh | 2018-09-21 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-15880-001025 | 15880 | 2019-04-15 16:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Office Supplies | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15859-001025 | 15859 | 2019-04-15 13:33 | Section 3 | Material | Not on List | Not on List | 5 | tonne | 538 | 2690 | NULL | 2019-04-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN16 - New Barns Lane Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15747-001025 | 15747 | 2019-04-12 09:53 | Section 4 | Material | Not on List | Not on List | 5 | Each | 80 | 400 | Builders Merchants (General) | 2019-04-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15889-001025 | 15889 | 2019-04-15 15:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-04-26 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15889-001025 | 15889 | 2019-04-15 15:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | PPE | 2019-04-26 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15889-001025 | 15889 | 2019-04-15 15:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-04-26 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15889-001025 | 15889 | 2019-04-15 15:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | PPE | 2019-04-26 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15904-001025 | 15904 | 2019-04-16 07:37 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Concrete Accessories | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15905-001025 | 15905 | 2019-04-16 07:35 | Section 1 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Flow Control | 2019-04-17 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Operations Rejected | No - Reject | NULL | Req - S1 Buyers
MREQ-15916-001025 | 15916 | 2019-04-16 08:51 | Section 5 | Material | Not on List | Not on List | 1 | number | 708 | 708 | Miscellaneous | 2019-04-16 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15922-001025 | 15922 | 2019-04-16 09:07 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 100 | Each | 24.32 | 2432 | Timber Products | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15922-001025 | 15922 | 2019-04-16 09:07 | Section 5 | Material | Timber | Not on List | 300 | m | NULL | 0 | Timber Products | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15922-001025 | 15922 | 2019-04-16 09:07 | Section 5 | Material | Not on List | Not on List | 100 | litres | NULL | 0 | Builders Merchants (General) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15922-001025 | 15922 | 2019-04-16 09:07 | Section 5 | Material | Not on List | Not on List | 4 | each | NULL | 0 | Builders Merchants (General) | 2019-04-17 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15923-001025 | 15923 | 2019-04-16 09:27 | Section 5 | Material | Not on List | Not on List | 60 | No | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15923-001025 | 15923 | 2019-04-16 09:27 | Section 5 | Material | Not on List | Not on List | 60 | No | NULL | 0 | Plastic Drainage | 2019-04-23 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15948-001025 | 15948 | 2019-04-16 13:24 | Section 3 | Material | Not on List | Not on List | 6 | NULL | 11.19 | 67 | Miscellaneous | 2019-04-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15948-001025 | 15948 | 2019-04-16 13:24 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-04-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15948-001025 | 15948 | 2019-04-16 13:24 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15948-001025 | 15948 | 2019-04-16 13:24 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-04-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15957-001025 | 15957 | 2019-04-16 15:34 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15958-001025 | 15958 | 2019-04-16 15:31 | Section 6 | Material | Not on List | Not on List | 15 | number | 7.25 | 109 | Surveying Consumables | 2019-04-23 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15958-001025 | 15958 | 2019-04-16 15:31 | Section 6 | Material | Not on List | Not on List | 15 | number | 6.75 | 101 | Surveying Consumables | 2019-04-23 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15583-001025 | 15583 | 2019-04-10 08:50 | Section 4 | Material | Waste Management | General Mixed - Skip 8 cubic yard | 2 | Each | 150 | 300 | Waste (Recycling) | 2019-04-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15657-001025 | 15657 | 2019-04-11 08:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2517.86 | 2517.86 | PPE | 2019-04-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15544-001025 | 15544 | 2019-04-09 15:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Pack of 10 Tear Off Visors | 14.82 | 29.64 | PPE | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15544-001025 | 15544 | 2019-04-09 15:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 14.02 | 280.4 | PPE | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16008-001025 | 16008 | 2019-04-17 07:43 | Section 2 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Concrete Accessories | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16014-001025 | 16014 | 2019-04-17 08:01 | Section 2 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Miscellaneous | 2019-04-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15375-001025 | 15375 | 2019-04-05 11:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EAch | 33.6 | 134.4 | Miscellaneous | 2019-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15659-001025 | 15659 | 2019-04-11 08:40 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2061.84 | 2061.84 | Small Tools (Consumables) | 2019-04-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15857-001025 | 15857 | 2019-04-15 12:57 | Section 4 | Material | Not on List | Not on List | 15 | Each | 46.5 | 697.5 | Builders Merchants (General) | 2019-04-17 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15839-001025 | 15839 | 2019-04-15 10:26 | Section 2 | Material | Not on List | Not on List | 25 | Sheets | NULL | 0 | Rebar and Mesh | 2019-04-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15679 | 15679 | 2019-04-11 11:35 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 8695 | 17390 | Surveying Consumables | 2019-04-14 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15679 | 15679 | 2019-04-11 11:35 | Section 5 | Material | Not on List | Not on List | 1 | NULL | 5250 | 5250 | Surveying Consumables | 2019-04-14 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-15781-001025 | 15781 | 2019-04-12 14:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 25 | 25 | Laboratory Equipment / Certification | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16035-001025 | 16035 | 2019-04-17 10:04 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15946-001025 | 15946 | 2019-04-16 13:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 572 | 572 | Miscellaneous | 2019-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15693-001025 | 15693 | 2019-04-11 14:38 | Section 4 | Material | Not on List | Not on List | 12 | each | 97.3 | 1167.6 | Miscellaneous | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Concrete Kerbs 125x150x914 BN Straight (753034) | 15 | Each | 3.03 | 45.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Drop Kerb HB x BN RH (897464) | 5 | Each | 5.44 | 27.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Drop Kerb HB x BN LH (897468) | 5 | Each | 5.44 | 27.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Not on List | 1 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Not on List | 1 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Concrete Kerbs 125x150 BN External Radius (947297) | 1 | Each | 5.43 | 5.43 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6157-00627 | 6157 | 2018-09-07 01:23 | Section 3 | Material | Not on List | Not on List | 150000 | ea | 1 | 150000 | Gas Oil | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15846-001025 | 15846 | 2019-04-15 11:24 | Section 6 | Material | NULL | Concrete Kerbs 125x150 BN Internal Radius (947297) | 1 | Each | 5.43 | 5.43 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15660-001025 | 15660 | 2019-04-11 08:46 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 50.4 | 756 | Small Tools (Consumables) | 2019-04-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16051-001025 | 16051 | 2019-04-17 13:31 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15936-001025 | 15936 | 2019-04-16 10:31 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Bags | 98.14 | 294.42 | Concrete Accessories | 2019-04-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15936-001025 | 15936 | 2019-04-16 10:31 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Coils | 46.5 | 232.5 | Fixings and Fasteners | 2019-04-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16046-001025 | 16046 | 2019-04-17 12:23 | Section 3 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 8 | Each | 165.1 | 1320.8 | Concrete Drainage | 2019-04-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6157-00627 | 6157 | 2018-09-07 01:23 | Section 3 | Material | Not on List | Not on List | 2899 | ea | 0.69 | 2000.31 | Gas Oil | 2018-09-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16047-001025 | 16047 | 2019-04-17 12:28 | Section 3 | Material | Not on List | Not on List | 1 | No | 1263.25 | 1263.25 | Professional Services | 2019-04-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15745-001025 | 15745 | 2019-04-12 09:07 | Section 2 | Material | NULL | Not on List | 128 | number | NULL | 0 | Blocks and Bricks | 2019-04-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-15877-001025 | 15877 | 2019-04-15 15:46 | Section 3 | Material | Not on List | Not on List | 50 | No. | 81.47 | 4073.5 | Plastic Drainage | 2019-04-18 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15877-001025 | 15877 | 2019-04-15 15:46 | Section 3 | Material | Not on List | Not on List | 25 | No. | 74.74 | 1868.5 | Plastic Drainage | 2019-04-18 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15877-001025 | 15877 | 2019-04-15 15:46 | Section 3 | Material | Not on List | Not on List | 50 | No. | 5.14 | 257 | Plastic Drainage | 2019-04-18 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15877-001025 | 15877 | 2019-04-15 15:46 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327.4 | Plastic Drainage | 2019-04-18 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15977-001025 | 15977 | 2019-04-16 16:53 | Section 3 | Material | Not on List | Not on List | 25 | Roll | 11.51 | 287.75 | Miscellaneous | 2019-04-25 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15977-001025 | 15977 | 2019-04-16 16:53 | Section 3 | Material | Not on List | Not on List | 20 | No. | 37.5 | 750 | Miscellaneous | 2019-04-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16079-001025 | 16079 | 2019-04-17 16:40 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16107-001025 | 16107 | 2019-04-18 07:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 857.61 | 857.61 | Small Tools (Consumables) | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 2000 | m | 1 | 2000 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 2000 | m | 1 | 2000 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 2000 | m | 1 | 2000 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 200 | m | 1 | 200 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 2 | m | 1 | 2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16124-001025 | 16124 | 2019-04-18 08:06 | Section 4 | Material | Not on List | Not on List | 2 | m | 1 | 2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-17 | RVP 424 - Grange Farm – A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16106-001025 | 16106 | 2019-04-18 07:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2467.5 | 2467.5 | PPE | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15742-001025 | 15742 | 2019-04-12 09:03 | Section 3 | Material | Not on List | Not on List | 30 | EA | 4.09 | 123 | Miscellaneous | 2019-05-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15073-001025 | 15073 | 2019-04-02 08:02 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-14336-001025 | 14336 | 2019-03-20 07:37 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Wheelbarrow 90ltr Galvanised Puncture Proof (700403) | 2 | Each | 53.17 | 106 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6188-00633 | 6188 | 2018-09-07 10:45 | Section 3 | Material | Concrete Drainage | Not on List | 6 | No. | 209.35 | 1256.1 | Concrete Drainage | 2018-09-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 370mm X 7.6mm Pack Of 100 Spartan (230065) | 15 | Each | 3.88 | 58 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Bucket Galvanised 2 1/2gall/11.42ltr 10"/30cm Dia Spartan (506016) | 5 | Each | 9 | 45 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 150 | Each | 3.04 | 456 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6188-00633 | 6188 | 2018-09-07 10:45 | Section 3 | Material | Concrete Drainage | Not on List | 6 | No. | 232.01 | 1392.06 | Concrete Drainage | 2018-09-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 150 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16129-001025 | 16129 | 2019-04-17 14:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16130-001025 | 16130 | 2019-04-18 10:20 | Section 5 | Material | Combined Drainage | Not on List | 12 | NULL | NULL | 0 | Concrete Drainage | 2019-04-23 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16078-001025 | 16078 | 2019-04-17 16:18 | Section 3 | Material | Not on List | Not on List | 27.212 | Tonne | 538 | 14640.06 | NULL | 2019-04-17 | Gate D - 1339643 - BN10 Via Main Compound Entrance | CL3B - Structures (Culverts) 3B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16078-001025 | 16078 | 2019-04-17 16:18 | Section 3 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 3.64 | 203.84 | Builders Merchants (General) | 2019-04-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16137-001025 | 16137 | 2019-04-18 08:14 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-04-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6188-00633 | 6188 | 2018-09-07 10:45 | Section 3 | Material | Concrete Drainage | Not on List | 6 | No. | 47.04 | 282.24 | Concrete Drainage | 2018-09-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-16074-001025 | 16074 | 2019-04-17 16:23 | Section 3 | Material | PPE, Small Tools and Consumables | Refill Air Care Pristine Wild Berries Air Fragrance 270ml (539229) | 8 | Each | 3.1 | 24.8 | Janitorial | 2019-04-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 12 | Each | 232.2 | 2786.4 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Spigot (249371) | 2 | Each | 278.64 | 557.28 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Socket (249372) | 2 | Each | 278.64 | 557.28 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6188-00633 | 6188 | 2018-09-07 10:45 | Section 3 | Material | Concrete Drainage | Not on List | 6 | No. | 59.17 | 355.02 | Concrete Drainage | 2018-09-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 25 | Each | 35.52 | 888 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 940.8 | Concrete Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | 1.77 | 88.5 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | 5.43 | 162.9 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 17.75 | 177.5 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 17.75 | 177.5 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 17.75 | 177.5 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | 76.36 | 229.08 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | 76.36 | 229.08 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6715-00750 | 6715 | 2018-09-19 12:34 | Section 4 | Material | Concrete Drainage | Not on List | 4 | Each | 18.35 | 73.4 | Builders Merchants (General) | 2018-09-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 68.46 | 68.46 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23563-001025 | 23563 | 2019-09-12 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 88.37 | 88.37 | Small Tools (Consumables) | 2019-09-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23734-001025 | 23734 | 2019-09-16 14:15 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 30 | Each | 48.92 | 1467.6 | Concrete Drainage | 2019-09-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23734-001025 | 23734 | 2019-09-16 14:15 | Section 4 | Material | Not on List | Not on List | 10 | Each | 162.27 | 1622.7 | Ductile Drainage | 2019-09-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23734-001025 | 23734 | 2019-09-16 14:15 | Section 4 | Material | Not on List | Not on List | 15 | Each | 225.3 | 3379.5 | Concrete Drainage | 2019-09-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 21 | Each (lengths) | 23.14 | 485.94 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SEC6 - Huntingdon Viaduct works | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6715-00750 | 6715 | 2018-09-19 12:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.18 | 143.6 | Builders Merchants (General) | 2018-09-24 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4B - Structures (Culverts) 4B | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 4 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 26 | Each | 3.65 | 94.9 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 52 | Each | 2 | 104 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 22 | Each | 34.82 | 766.04 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 50 | Each | 120.62 | 6031 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 12 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 10 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 20 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 2 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 4 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6720-00750 | 6720 | 2018-09-19 13:44 | Section 4 | Material | Not on List | Not on List | 15 | Each | 175 | 2625 | Plastic Drainage | 2018-09-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23798-001025 | 23798 | 2019-09-17 14:29 | Section 6 | Material | Twinwall | Not on List | 8 | Each | NULL | 0 | Plastic Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23845-001025 | 23845 | 2019-09-18 12:21 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pack 100 | 10.5 | 105 | Surveying Consumables | 2019-09-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23845-001025 | 23845 | 2019-09-18 12:21 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pack 100 | 10.5 | 105 | Surveying Consumables | 2019-09-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23792-001025 | 23792 | 2019-09-17 15:33 | Core | Material | NULL | NULL | 1 | Each | 288 | 288 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23905-001025 | 23905 | 2019-09-19 09:48 | Core | Material | Not on List | Not on List | 1 | No. | NULL | 0 | Office Supplies | 2019-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23516-001025 | 23516 | 2019-09-11 13:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 25 | NULL | 30.24 | 756 | Small Tools (Consumables) | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23516-001025 | 23516 | 2019-09-11 13:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 12.78 | 25.56 | Small Tools (Consumables) | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6724-00750 | 6724 | 2018-09-19 09:21 | Section 4 | Material | Not on List | Not on List | 18 | Each | 51.28 | 923.04 | Concrete Accessories | 2018-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN21 - Bar Hill Junction East Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23516-001025 | 23516 | 2019-09-11 13:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 13.31 | 26.62 | Small Tools (Consumables) | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23509-001025 | 23509 | 2019-09-11 12:02 | Section 4 | Material | Not on List | Not on List | 1 | Each | 109.6 | 109.6 | Small Tools (Consumables) | 2019-09-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23495-001025 | 23495 | 2019-09-11 10:40 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | NULL | 6.29 | 905.76 | Small Tools (Consumables) | 2019-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23875-001025 | 23875 | 2019-09-18 17:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1310.28 | Each | 1 | 1310.28 | PPE | 2019-09-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23662-001025 | 23662 | 2019-09-13 13:25 | Section 4 | Material | NULL | NULL | 130 | Each | 80 | 10400 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23662-001025 | 23662 | 2019-09-13 13:25 | Section 4 | Material | NULL | NULL | 2 | Each | 1350 | 2700 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23662-001025 | 23662 | 2019-09-13 13:25 | Section 4 | Material | NULL | NULL | 2 | Each | 95 | 190 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23699-001025 | 23699 | 2019-09-16 06:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Pack 10 | 1.92 | 19.2 | Small Tools (Consumables) | 2019-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23838-001025 | 23838 | 2019-09-18 10:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1181.99 | 1181.99 | Small Tools (Consumables) | 2019-09-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23912-001025 | 23912 | 2019-09-19 12:42 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23917-001025 | 23917 | 2019-09-19 13:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 150 | NULL | NULL | 0 | Surveying Consumables | 2019-09-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1805 - Cantilever Structures | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23886-001025 | 23886 | 2019-09-19 07:51 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 20 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-09-20 | RVP 426 - Robins Lane A14 Eastbound (1339622) | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23904-001025 | 23904 | 2019-09-19 09:33 | Section 4 | Material | Not on List | Not on List | 16 | Each | 25 | 400 | Miscellaneous | 2019-09-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23919-001025 | 23919 | 2019-09-19 13:57 | Core | Material | Not on List | Not on List | 1 | NULL | 2988.46 | 2988 | Miscellaneous | 2019-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23922-001025 | 23922 | 2019-09-19 14:21 | Section 5 | Material | Bagged | Not on List | 48 | NULL | NULL | 0 | Builders Merchants (General) | 2019-09-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23552-001025 | 23552 | 2019-09-12 08:24 | Section 3 | Material | Not on List | Not on List | 5 | ea | 199.96 | 999.8 | Miscellaneous | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | SC3A - Roadworks | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23955-001025 | 23955 | 2019-09-19 18:22 | Section 5 | Material | Twinwall | Not on List | 8 | NULL | NULL | 0 | Plastic Drainage | 2019-09-23 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23955-001025 | 23955 | 2019-09-19 18:22 | Section 5 | Material | Twinwall | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2019-09-23 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 11 | Each | 81.96 | 901.56 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 4 | Each | 81.96 | 327.84 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 10 | Each | 53.01 | 530.1 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 8 | Each | 36.62 | 292.96 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 16 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 1 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 2100 x 1000 D/S (890448) | 3 | Each | 283.24 | 849.72 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | CPM Chamber Ring 2100 x 1000 D/S (890448) | 3 | Each | 283.24 | 849.72 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 2 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 3 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Concrete Drainage | Not on List | 52 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23805-001025 | 23805 | 2019-09-17 16:18 | Section 6 | Material | Saint Gobain Castings | Not on List | 24 | Each | NULL | 0 | Concrete Drainage | 2019-09-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23846-001025 | 23846 | 2019-09-18 12:43 | Section 6 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Surveying Consumables | 2019-09-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 60 | No | 5.9 | 354 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 64 | No | 4.42 | 282.88 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 64 | No | 7.96 | 509.44 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 2 | No | 25.52 | 51.04 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 2 | No | 25.52 | 51.04 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 4 | No | 12.39 | 49.56 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23915-001025 | 23915 | 2019-09-19 12:48 | Section 3 | Material | Not on List | Not on List | 4 | No | 12.39 | 49.56 | Builders Merchants (General) | 2019-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23840-001025 | 23840 | 2019-09-18 10:51 | Section 5 | Material | NULL | NULL | 1 | EAch | 341.88 | 341.88 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23988-001025 | 23988 | 2019-09-20 09:54 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 145 | 145 | Waste (Recycling) | 2019-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23908-001025 | 23908 | 2019-09-19 10:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 11.63 | 116.3 | Small Tools (Consumables) | 2019-09-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23908-001025 | 23908 | 2019-09-19 10:32 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | 11.63 | 58.15 | Small Tools (Consumables) | 2019-09-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5057-0022 | 5057 | 2018-08-14 12:26 | Section 4 | Material | Not on List | Not on List | 2 | number | 11.9 | 0 | Miscellaneous | 2018-08-19 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23698-001025 | 23698 | 2019-09-16 06:40 | Section 4 | Material | Not on List | Not on List | 144 | NULL | 6.29 | 905.76 | Small Tools (Consumables) | 2019-09-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23969-001025 | 23969 | 2019-09-20 06:19 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-09-23 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23969-001025 | 23969 | 2019-09-20 06:19 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-09-23 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-21324-001025 | 21324 | 2019-07-25 11:03 | Section 5 | Material | NULL | NULL | 1 | Each | 160 | 160 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-21506-001025 | 21506 | 2019-07-29 14:00 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | No - Reject | Req - S5 Buyers
MREQ-23945-001025 | 23945 | 2019-09-19 16:55 | Section 4 | Material | Not on List | Not on List | 20 | EA | 21.96 | 439.2 | Concrete Accessories | 2019-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23945-001025 | 23945 | 2019-09-19 16:55 | Section 4 | Material | NULL | Not on List | 1 | EA | 35 | 35 | Concrete Accessories | 2019-09-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 1134 | Each | 19.95 | 22623.3 | Plastic Drainage | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 1 | Each | 4386.96 | 4386.96 | Geotextiles | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 1 | Each | 1111.54 | 1111.54 | Geotextiles | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6766-00751 | 6766 | 2018-09-20 11:24 | Section 4 | Material | Plastic Drainage | Not on List | 20 | Each | 69.21 | 1384.2 | Plastic Drainage | 2018-09-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1301 - Road Lighting Columns and Brackets | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 17 | Each | 66.48 | 1130.16 | Fixings and Fasteners | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 6 | Each | 106.96 | 641.76 | Plastic Drainage | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23862-001025 | 23862 | 2019-09-18 14:16 | Section 6 | Material | Not on List | Not on List | 6 | Each | NULL | 0 | Plastic Drainage | 2019-09-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-23938-001025 | 23938 | 2019-09-19 12:24 | Section 4 | Material | Not on List | Not on List | 48 | Each | 17 | 816 | Rebar and Mesh | 2019-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23866-001025 | 23866 | 2019-09-18 15:27 | Section 4 | Material | Not on List | Not on List | 22 | Each | 126.49 | 2782.78 | Plastic Drainage | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6780-00751 | 6780 | 2018-09-20 13:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 104587.34 | 104587.34 | Geotextiles | 2018-10-08 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23866-001025 | 23866 | 2019-09-18 15:27 | Section 4 | Material | NULL | Not on List | 22 | Each | 16.59 | 364.98 | Plastic Drainage | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23866-001025 | 23866 | 2019-09-18 15:27 | Section 4 | Material | NULL | Not on List | 44 | Each | 9.2 | 404.8 | Plastic Drainage | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24073-001025 | 24073 | 2019-09-23 09:56 | Core | Material | Not on List | Not on List | 1 | ea | 159456 | 159456 | Office Supplies | 2019-09-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24074-001025 | 24074 | 2019-09-23 10:08 | Core | Material | Not on List | Not on List | 1 | ea | 17100 | 17100 | Office Supplies | 2019-09-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24075-001025 | 24075 | 2019-09-23 10:12 | Core | Material | Not on List | Not on List | 1 | ea | 360 | 360 | Office Supplies | 2019-09-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24078-001025 | 24078 | 2019-09-23 10:40 | Core | Material | Not on List | Not on List | 1 | ea` | 500 | 500 | Office Supplies | 2019-09-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24079-001025 | 24079 | 2019-09-23 10:44 | Core | Material | Not on List | Not on List | 1 | ea | 279.18 | 279 | Office Supplies | 2019-09-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24079-001025 | 24079 | 2019-09-23 10:44 | Core | Material | Not on List | Not on List | 1 | ea | 279.18 | 279 | Office Supplies | 2019-09-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23990-001025 | 23990 | 2019-09-20 09:24 | Section 4 | Material | NULL | NULL | 52 | Each | 16.18 | 841.36 | Miscellaneous | 2019-09-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6783-00751 | 6783 | 2018-09-20 13:37 | Section 4 | Material | Plastic Drainage | NULL | 20 | Each | 47.87 | 957.4 | Plastic Drainage | 2018-09-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24021-001025 | 24021 | 2019-09-20 15:53 | Section 2 | Material | Not on List | Not on List | 50 | NULL | 19.51 | 975.5 | Concrete Accessories | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24021-001025 | 24021 | 2019-09-20 15:53 | Section 2 | Material | Not on List | Not on List | 25 | NULL | 19.51 | 487.75 | Concrete Accessories | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24021-001025 | 24021 | 2019-09-20 15:53 | Section 2 | Material | Not on List | Not on List | 100 | NULL | 19.51 | 1951 | Concrete Accessories | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24089-001025 | 24089 | 2019-09-23 12:10 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-10-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24022-001025 | 24022 | 2019-09-20 16:12 | Section 2 | Material | Not on List | Not on List | 5 | NULL | 64.3 | 321.5 | Concrete Accessories | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 0 | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6783-00751 | 6783 | 2018-09-20 13:37 | Section 4 | Material | Plastic Drainage | P/Pipe 225Mm Ridgidrain Dbl Skt Coupler | 70 | Each | 5.74 | 401.8 | Plastic Drainage | 2018-09-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24097-001025 | 24097 | 2019-09-22 07:35 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24108-001025 | 24108 | 2019-09-23 16:20 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 556.8 | 557 | Miscellaneous | 2019-09-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24023-001025 | 24023 | 2019-09-20 16:15 | Section 2 | Material | Not on List | Not on List | 1 | NULL | 9860 | 9860 | Fixings and Fasteners | 2019-09-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24070-001025 | 24070 | 2019-09-23 09:42 | Section 5 | Material | Not on List | Not on List | 10 | EA | 6.45 | 64.5 | Miscellaneous | NULL | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6783-00751 | 6783 | 2018-09-20 13:37 | Section 4 | Material | Not on List | Not on List | 20 | Each | 31.98 | 639.6 | Plastic Drainage | 2018-09-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24127-001025 | 24127 | 2019-09-24 07:54 | Section 3 | Material | Not on List | Not on List | 40 | No | NULL | 0 | Builders Merchants (General) | 2019-09-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 10 | Each | 81.73 | 817.3 | Miscellaneous | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | 430x370x100 D400 Watershed GG&F (376797) | 2 | Each | 37.4 | 74.8 | Miscellaneous | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | Not on List | 6 | Each | NULL | 0 | Miscellaneous | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 432 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 10 | Each | 35.52 | 355 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9461-001025 | 9461 | 2018-11-22 08:38 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-11-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 941 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 432 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9426-001025 | 9426 | 2018-11-21 14:30 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 196.91 | 196.91 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 940.8 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509.2 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5287-00223 | 5287 | 2018-08-17 12:25 | Section 4 | Material | Plastic Drainage | Not on List | 10 | no | 12.18 | 0 | Plastic Drainage | 2018-08-20 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9463-001025 | 9463 | 2018-11-22 08:44 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2018-11-20 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9408-001025 | 9408 | 2018-11-21 10:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 107.6 | 107.6 | PPE | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9423-001025 | 9423 | 2018-11-21 14:12 | Section 3 | Material | Not on List | Not on List | 1 | ea | 447.5 | 447.5 | Damage Charges | 2018-11-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9454-001025 | 9454 | 2018-11-22 07:32 | Section 3 | Material | NULL | Not on List | 40 | Bags | 15.54 | 621.6 | Builders Merchants (General) | 2018-11-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9458-001025 | 9458 | 2018-11-22 08:11 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1363.79 | 1363.79 | Damage Charges | 2018-11-23 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9479-001025 | 9479 | 2018-11-22 12:34 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 196.1 | 196 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9425-001025 | 9425 | 2018-11-21 14:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 525 | Each | 1 | 525 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9485-001025 | 9485 | 2018-11-22 14:15 | Section 4 | Material | Not on List | Not on List | 3 | U | 650 | 1950 | Miscellaneous | 2018-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5341-00236 | 5341 | 2018-08-20 10:47 | Section 4 | Material | Misc | Not on List | 4 | Rolls | NULL | 0 | Geotextiles | 2018-08-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9488-001025 | 9488 | 2018-11-22 14:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9366-001025 | 9366 | 2018-11-20 13:06 | Section 4 | Material | Aggregate | Not on List | 5 | no | 32.74 | 163.7 | Builders Merchants (General) | 2018-11-22 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9366-001025 | 9366 | 2018-11-20 13:06 | Section 4 | Material | NULL | Not on List | 4 | no | 11.94 | 47.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-22 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9366-001025 | 9366 | 2018-11-20 13:06 | Section 4 | Material | Not on List | Not on List | 168 | no | 8.4 | 1411.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-22 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9492-001025 | 9492 | 2018-11-22 15:17 | Section 3 | Material | Not on List | Not on List | 40 | Ton | 69.9 | 2796 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 30 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 36 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 30 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 15 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5245-00156 | 5245 | 2018-08-16 15:58 | Section 4 | Material | Not on List | Not on List | 336 | Metres | 5.9 | 1982.4 | Timber Products | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | Kerbs | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-11-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9465-001025 | 9465 | 2018-11-22 09:12 | Section 4 | Material | Not on List | Not on List | 120 | Each | 3.46 | 415.2 | Builders Merchants (General) | 2018-11-23 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9495-001025 | 9495 | 2018-11-22 16:23 | Section 3 | Material | Not on List | Not on List | 16 | No | NULL | 0 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9495-001025 | 9495 | 2018-11-22 16:23 | Section 3 | Material | Not on List | Not on List | 50 | rolls | NULL | 0 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9464-001025 | 9464 | 2018-11-22 08:49 | Section 4 | Material | Not on List | Not on List | 15 | Weeks | 300 | 4500 | Miscellaneous | 2018-11-22 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 0.533 | tonnes | NULL | 0 | Reinforcement | 2018-11-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 13.261 | tonnes | NULL | 0 | Reinforcement | 2019-01-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 22.285 | tonnes | NULL | 0 | Reinforcement | 2019-01-21 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9516-001025 | 9516 | 2018-11-23 08:35 | Section 3 | Material | Not on List | Not on List | 10 | No | NULL | 0 | Builders Merchants (General) | 2018-11-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 12 | packs | NULL | 0 | Not Sure | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5245-00156 | 5245 | 2018-08-16 15:58 | Section 4 | Material | Not on List | Not on List | 240 | NULL | NULL | 0 | NULL | NULL | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 8 | packs | NULL | 0 | Not Sure | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 10 | packs | NULL | 0 | Not Sure | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | Not on List | 20 | No. | 209.35 | 4187 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 940.8 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 10 | Each | 67.9 | 679 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 10 | Each | 50.92 | 509.2 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9460-001025 | 9460 | 2018-11-22 08:34 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 10 | Each | 35.52 | 355.2 | Concrete Drainage | 2018-11-27 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5346-00239 | 5346 | 2018-08-20 11:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Roll | NULL | 0 | Miscellaneous | 2018-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9516-001025 | 9516 | 2018-11-23 08:35 | Section 3 | Material | Misc | NULL | 10 | Each | 32.74 | 327.4 | Builders Merchants (General) | 2018-11-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9479-001025 | 9479 | 2018-11-22 12:34 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | 196.1 | 784.4 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9531-001025 | 9531 | 2018-11-23 10:21 | Section 3 | Material | Not on List | Not on List | 2 | each | 1200 | 2400 | Miscellaneous | 2018-11-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9534-001025 | 9534 | 2018-11-23 11:13 | Section 4 | Material | Concrete Drainage | Not on List | 5 | NULL | NULL | 0 | Concrete Drainage | 2018-12-05 | RVP 419 - 1340880 - A14 Westbound (West of Junction 28) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9451-001025 | 9451 | 2018-11-21 19:31 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 39.22 | 235.32 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9451-001025 | 9451 | 2018-11-21 19:31 | Section 4 | Material | Not on List | Not on List | 50 | Set | 27 | 1350 | Fixings and Fasteners | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 50.4 | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9540-001025 | 9540 | 2018-11-23 12:20 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 179.5 | 180 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9540-001025 | 9540 | 2018-11-23 12:20 | Section 4 | Material | Not on List | Not on List | 22 | NULL | NULL | 0 | Plastic Drainage | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9484-001025 | 9484 | 2018-11-22 13:20 | Section 4 | Material | Not on List | Not on List | 500 | Each | 0.03 | 15 | Concrete Accessories | 2018-11-26 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9484-001025 | 9484 | 2018-11-22 13:20 | Section 4 | Material | Not on List | Not on List | 1500 | Each | 0.05 | 75 | Concrete Accessories | 2018-11-26 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9549-001025 | 9549 | 2018-11-23 13:39 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Visit | 1179.33 | 1179 | Professional Services | 2018-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9488-001025 | 9488 | 2018-11-22 14:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 266.52 | 266.52 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 30.24 | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9411-001025 | 9411 | 2018-11-21 10:15 | Section 4 | Material | Not on List | Not on List | 1703 | Each | 1 | 1703 | Professional Services | 2018-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9492-001025 | 9492 | 2018-11-22 15:17 | Section 3 | Material | Not on List | Not on List | 40 | Ton | 69.9 | 2796 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9580-001025 | 9580 | 2018-11-23 16:22 | Section 3 | Material | Bagged | Not on List | 1 | palette | NULL | 0 | Builders Merchants (General) | 2018-11-30 | Gate F - 1339645 - BN11 Near Mere Way | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9587-001025 | 9587 | 2018-11-23 17:49 | Section 3 | Material | Not on List | Not on List | 100 | Each | 42.5 | 4250 | Miscellaneous | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9603-001025 | 9603 | 2018-11-26 09:50 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Office Supplies | 2018-12-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9603-001025 | 9603 | 2018-11-26 09:50 | Section 3 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Office Supplies | 2018-12-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9604-001025 | 9604 | 2018-11-26 10:03 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Electrical | 2018-11-27 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9495-001025 | 9495 | 2018-11-22 16:23 | Section 3 | Material | Not on List | Not on List | 16 | No | 35 | 560 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9495-001025 | 9495 | 2018-11-22 16:23 | Section 3 | Material | Not on List | Not on List | 50 | rolls | 6.4 | 320 | Builders Merchants (General) | 2018-12-14 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5278-00177 | 5278 | 2018-08-17 09:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | 1.31 | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 0.533 | tonnes | 538 | 286.75 | Rebar and Mesh | 2018-11-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 13.261 | tonnes | 538 | 7134.42 | Rebar and Mesh | 2019-01-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | Not on List | Not on List | 22.285 | tonnes | 538 | 11989.33 | Rebar and Mesh | 2019-01-21 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9499-001025 | 9499 | 2018-11-22 17:27 | Section 4 | Material | NULL | Not on List | 3 | Each | 125 | 375 | Rebar and Mesh | 2018-11-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9328-001025 | 9328 | 2018-11-19 12:35 | Section 3 | Material | Not on List | Not on List | 4 | number | NULL | 0 | Miscellaneous | 2018-11-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN06 - ECML Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 12 | packs | 168.35 | 2020.2 | Fixings and Fasteners | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 8 | packs | 11 | 88 | Fixings and Fasteners | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | Not on List | Not on List | 10 | Hun | 1.88 | 18.8 | Fixings and Fasteners | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9522-001025 | 9522 | 2018-11-23 09:12 | Section 4 | Material | NULL | Not on List | 10 | Hun | 1.55 | 15.5 | Fixings and Fasteners | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9580-001025 | 9580 | 2018-11-23 16:22 | Section 3 | Material | NULL | Not on List | 60 | palette ( 60 bags ) | 3.45 | 207 | Builders Merchants (General) | 2018-11-30 | Gate F - 1339645 - BN11 Near Mere Way | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5347-00243 | 5347 | 2018-08-20 11:52 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Not Sure | 2018-08-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9417-001025 | 9417 | 2018-11-21 12:04 | Section 3 | Material | Not on List | Not on List | 7 | No | 45 | 315 | Miscellaneous | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9628-001025 | 9628 | 2018-11-26 15:35 | Section 4 | Material | Not on List | Not on List | 0 | NULL | NULL | 0 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9603-001025 | 9603 | 2018-11-26 09:50 | Section 3 | Material | Not on List | Not on List | 1 | ea | 29.17 | 29.17 | Office Supplies | 2018-12-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9603-001025 | 9603 | 2018-11-26 09:50 | Section 3 | Material | Not on List | Not on List | 6 | e | 30.83 | 184.98 | Office Supplies | 2018-12-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9534-001025 | 9534 | 2018-11-23 11:13 | Section 4 | Material | Concrete Drainage | Not on List | 5 | Each | 361.34 | 1806.7 | Concrete Drainage | 2018-12-05 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9534-001025 | 9534 | 2018-11-23 11:13 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2018-12-05 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9274-001025 | 9274 | 2018-11-16 12:04 | Section 4 | Material | Not on List | Not on List | 45.495 | M2 | 71.23 | 3240.61 | Concrete Accessories | 2018-12-10 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9274-001025 | 9274 | 2018-11-16 12:04 | Section 4 | Material | NULL | Not on List | 1 | Each | 650 | 650 | Concrete Accessories | 2018-12-10 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5291-00225 | 5291 | 2018-08-17 13:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2018-08-17 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8073-001023 | 8073 | 2018-10-22 11:17 | Section 4 | Material | Not on List | Not on List | 10 | Each | NULL | 0 | Not Sure | 2018-10-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9677-001025 | 9677 | 2018-11-27 12:35 | Section 4 | Material | Aggregate | Bedding Sand | 20 | Tonnes | 11.5 | 230 | Aggregate | 2018-11-28 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9677-001025 | 9677 | 2018-11-27 12:35 | Section 4 | Material | Aggregate | Not on List | 200 | NULL | NULL | 0 | Aggregate | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5332-00234 | 5332 | 2018-08-20 09:18 | Section 3 | Material | Aggregate | Not on List | 2000 | m3 | 43.08 | 86160 | Aggregate | 2018-08-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9537-001025 | 9537 | 2018-11-23 11:59 | Section 4 | Material | Signage | Hazard Safety Signs - 335 X 500 | 50 | Each | 6.7 | 335 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9537-001025 | 9537 | 2018-11-23 11:59 | Section 4 | Material | Signage | Hazard Safety Signs - 335 X 500 | 50 | Each | 6.7 | 335 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9537-001025 | 9537 | 2018-11-23 11:59 | Section 4 | Material | Signage | Hazard Safety Signs - 335 X 500 | 50 | Each | 6.7 | 335 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9537-001025 | 9537 | 2018-11-23 11:59 | Section 4 | Material | Signage | Hazard Safety Signs - 335 X 500 | 50 | Each | 6.7 | 335 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9537-001025 | 9537 | 2018-11-23 11:59 | Section 4 | Material | Signage | Hazard Safety Signs - 335 X 500 | 50 | Each | 6.7 | 335 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9691-001025 | 9691 | 2018-11-27 15:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2018-12-19 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | Not on List | Not on List | 8 | no | NULL | 0 | Plastic Drainage | 2018-12-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 20 | Each | 10.5 | 210 | Plastic Drainage | 2018-12-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 50 | Each | 0.85 | 43 | Plastic Drainage | 2018-12-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 50 | Each | 1.84 | 92 | Plastic Drainage | 2018-12-03 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9549-001025 | 9549 | 2018-11-23 13:39 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Visit | 1179.33 | 1179.33 | Professional Services | 2018-11-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9687-001025 | 9687 | 2018-11-27 14:06 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 16 | Each | 110.27 | 1764.32 | Builders Merchants (General) | 2018-11-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9595-001025 | 9595 | 2018-11-26 07:56 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 16 | Each | 110.27 | 1764.32 | Geotextiles | 2018-11-28 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 30 | Each | 5.79 | 173.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 36 | Each | 5.79 | 208.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 30 | Each | 5.25 | 157.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 15 | Each | 5.25 | 78.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 2 | Each | 5.25 | 10.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 2 | Each | 5.25 | 10.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9493-001025 | 9493 | 2018-11-22 15:30 | Section 4 | Material | NULL | Not on List | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | Not on List | Not on List | 2 | Rolls | 9.6 | 19.2 | Concrete Accessories | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | Not on List | Not on List | 150 | ea | 0.55 | 82.5 | Concrete Accessories | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 110.27 | 1102.7 | Builders Merchants (General) | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11288-001025 | 11288 | 2019-01-22 09:06 | Section 3 | Material | NULL | NULL | 150 | ea | 0.64 | 96 | Concrete Accessories | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 20 | no. | 47.47 | 949.4 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 5 | no. | 46.5 | 232.5 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11251-001025 | 11251 | 2019-01-21 13:16 | Section 3 | Material | Not on List | Not on List | 200 | no | 0.07 | 14 | Miscellaneous | 2019-01-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11407-001025 | 11407 | 2019-01-24 11:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1179.2 | Each | 1 | 1179 | Janitorial | 2019-01-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11397-001025 | 11397 | 2019-01-24 08:05 | Section 3 | Material | Not on List | Not on List | 12580 | Ton | 4 | 50320 | Aggregate | 2019-01-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10975-001025 | 10975 | 2019-01-14 15:03 | Section 4 | Material | Not on List | Not on List | 0.827 | tonnes | 538 | 444.93 | NULL | 2019-02-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11298-001025 | 11298 | 2019-01-22 10:28 | Section 3 | Material | Not on List | Not on List | 12 | No | 63.32 | 759.84 | Builders Merchants (General) | 2019-01-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11412-001025 | 11412 | 2019-01-24 13:19 | Section 3 | Material | Not on List | Not on List | 40 | EA | 69 | 2760 | Miscellaneous | 2019-01-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11416-001025 | 11416 | 2019-01-24 14:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | NULL | 0 | PPE | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 289.33 | 289.33 | Small Tools (Consumables) | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 160.1 | 160.1 | Janitorial | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11378-001025 | 11378 | 2019-01-23 16:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1076.92 | 1076.92 | PPE | 2019-01-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11448-001025 | 11448 | 2019-01-25 07:57 | Section 3 | Material | Not on List | Not on List | 2 | Mo | NULL | 0 | Builders Merchants (General) | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11448-001025 | 11448 | 2019-01-25 07:57 | Section 3 | Material | Twinwall | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 10 | Each | 39.7 | 397 | Builders Merchants (General) | 2019-01-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 690 | 437895 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 555 | 437895 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 1 | Number | 420 | 437895 | Electrical | 2019-01-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 60 | Number | 5.45 | 437895 | Concrete Accessories | 2019-01-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10762-001025 | 10762 | 2019-01-09 12:53 | Section 3 | Material | Not on List | Not on List | 200 | Number | NULL | 437895 | Concrete Accessories | 2019-01-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 4 | rolls | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 2 | packs | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 5 | rolls | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 50 | bags | NULL | 0 | Not Sure | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5378-00250 | 5378 | 2018-08-20 16:43 | Section 3 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-08-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN31 - Culvert - 199 | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11513-001025 | 11513 | 2019-01-28 08:11 | Section 4 | Material | Not on List | Not on List | 1 | Sample analysis | 286 | 286 | Miscellaneous | 2019-01-30 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11552-001025 | 11552 | 2019-01-28 15:05 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11560-001025 | 11560 | 2019-01-28 15:57 | Section 3 | Material | Not on List | Not on List | 18 | Sheets | NULL | 0 | Not Sure | 2019-01-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11560-001025 | 11560 | 2019-01-28 15:57 | Section 3 | Material | Not on List | Not on List | 6 | Rolls | NULL | 0 | Not Sure | 2019-01-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11593-001025 | 11593 | 2019-01-29 08:14 | Section 4 | Material | Not on List | Not on List | 13 | ea | 1 | 13 | Concrete Drainage | 2019-02-04 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11597-001025 | 11597 | 2019-01-29 08:40 | Section 4 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Not Sure | 2019-01-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11598-001025 | 11598 | 2019-01-29 08:52 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Not Sure | 2019-01-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11171-001025 | 11171 | 2019-01-18 09:16 | Section 4 | Material | Not on List | Not on List | 4 | Each | 650 | 2600 | Miscellaneous | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11607-001025 | 11607 | 2019-01-29 09:58 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 400 | Each | 4.97 | 1988 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5378-00250 | 5378 | 2018-08-20 16:43 | Section 3 | Material | Not on List | Not on List | 6 | boxes | 9 | 0 | Fixings and Fasteners | 2018-08-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 3 | Each | 11.9 | 35.7 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 800 | Metre | 0.26 | 208 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.23 | 46 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 5 | Roll | 82.57 | 412.85 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 50 | Bags | 7.98 | 399 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | Not on List | Not on List | 100 | Metre | 0.78 | 78 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | NULL | Not on List | 5 | Each | 20.25 | 101.25 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11486-001025 | 11486 | 2019-01-25 13:30 | Section 4 | Material | NULL | Not on List | 3 | Each | 1.6 | 4.8 | Concrete Accessories | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11611-001025 | 11611 | 2019-01-29 11:05 | Section 3 | Material | Concrete Drainage | Not on List | 2 | no. | NULL | 0 | Concrete Drainage | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11616-001025 | 11616 | 2019-01-29 11:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 60 | Each | 3.42 | 205 | Small Tools (Consumables) | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5341 | 5341 | 2018-08-20 10:47 | Section 4 | Material | Misc | Not on List | 4 | Rolls | NULL | 0 | Geotextiles | 2018-08-28 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11616-001025 | 11616 | 2019-01-29 11:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 25 | Each | 30.56 | 764 | Small Tools (Consumables) | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11616-001025 | 11616 | 2019-01-29 11:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Roll | 36.98 | 1109 | Builders Merchants (General) | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11242-001025 | 11242 | 2019-01-21 11:04 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Not Sure | 2019-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1701 - Insitu Concrete | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-8282 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Finance Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8282 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Finance Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11624-001025 | 11624 | 2019-01-29 13:38 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 500 | 1000 | Surveying Consumables | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-11626-001025 | 11626 | 2019-01-29 13:52 | Section 3 | Material | Not on List | Not on List | 14 | no. | NULL | 0 | Concrete Accessories | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1801 - Structural Steelwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | Twinwall | Not on List | 2 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | Twinwall | Not on List | 1 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | Twinwall | Not on List | 2 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | Twinwall | Not on List | 6 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | Kerbs | Not on List | 1 | No | 600 | 600 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8282 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | Each | 21.43 | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Finance Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-8282-001023 | 8282 | 2018-10-26 09:28 | Section 3 | Material | Not on List | Not on List | 9 | NULL | NULL | 0 | Surveying Consumables | 2018-10-26 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 106 - Testing equipment and materials testing | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11638-001025 | 11638 | 2019-01-29 16:28 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Reinforcement | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11412-001025 | 11412 | 2019-01-24 13:19 | Section 3 | Material | Not on List | Not on List | 40 | tonne | 69.9 | 2796 | Miscellaneous | 2019-01-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11513-001025 | 11513 | 2019-01-28 08:11 | Section 4 | Material | Not on List | Not on List | 1 | Sample analysis | 286 | 286 | Miscellaneous | 2019-01-30 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11648-001025 | 11648 | 2019-01-30 06:33 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-01-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11560-001025 | 11560 | 2019-01-28 15:57 | Section 3 | Material | Not on List | Not on List | 18 | Sheets | 4.8 | 86.4 | Not Sure | 2019-01-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11560-001025 | 11560 | 2019-01-28 15:57 | Section 3 | Material | Not on List | Not on List | 6 | Rolls | 15.19 | 91.14 | Not Sure | 2019-01-31 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN13 - West Brook Underbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11648-001025 | 11648 | 2019-01-30 06:33 | Section 3 | Material | Not on List | Not on List | 1 | ea | 1396.85 | 1396.85 | Miscellaneous | 2019-01-31 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11667-001025 | 11667 | 2019-01-30 14:41 | Section 4 | Material | Not on List | Not on List | 400 | EA | NULL | 0 | Concrete Accessories | 2019-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 2 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Timber | Not on List | 1 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 2 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 14 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 3 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 6 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 28 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 4 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 2 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | Twinwall | Not on List | 4 | No | 0 | 0 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11681-001025 | 11681 | 2019-01-30 16:29 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 600 | 600 | Miscellaneous | 2019-02-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11696-001025 | 11696 | 2019-01-31 08:09 | Section 3 | Material | Twinwall | Not on List | 48 | No | 0 | 0 | Ductile Drainage | 2019-02-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11696-001025 | 11696 | 2019-01-31 08:09 | Section 3 | Material | Twinwall | Not on List | 36 | No | 0 | 0 | Ductile Drainage | 2019-02-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11702-001025 | 11702 | 2019-01-31 09:42 | Section 3 | Material | Not on List | Not on List | 40 | no | NULL | 0 | Builders Merchants (General) | 2019-02-05 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11702-001025 | 11702 | 2019-01-31 09:42 | Section 3 | Material | Not on List | Not on List | 1 | no | 8987.62 | 8987.62 | Builders Merchants (General) | 2019-02-05 | Gate C - 1339702 - BN06 (Silver St) Via logistics Yard Access | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11710-001025 | 11710 | 2019-01-31 11:43 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Concrete Drainage | 2019-02-05 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11626-001025 | 11626 | 2019-01-29 13:52 | Section 3 | Material | Not on List | Not on List | 14 | no. | 530.95 | 7433.3 | Concrete Accessories | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11624-001025 | 11624 | 2019-01-29 13:38 | Section 4 | Material | Not on List | Not on List | 2 | Each | 500 | 1000 | Surveying Consumables | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-11715-001025 | 11715 | 2019-01-31 12:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1742.38 | Each | 1 | 1742 | PPE | 2019-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11724-001025 | 11724 | 2019-01-31 13:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | Twinwall | Not on List | 3 | 0 | 0 | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | Twinwall | Not on List | 1 | 0 | 0 | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | Twinwall | Not on List | 20 | 0 | 0 | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | Twinwall | Not on List | 10 | 0 | 0 | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | Twinwall | Not on List | 10 | 0 | 0 | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 27 | No. | 39.22 | 1059 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 688 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 50 | No. | 48.86 | 2443 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11735-001025 | 11735 | 2019-01-31 13:58 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 115 | 115 | Surveying Consumables | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | NULL | Not on List | 2 | No | 121.59 | 243.18 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | NULL | Not on List | 1 | No | 113.25 | 113.25 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | NULL | Not on List | 2 | No | 164.37 | 328.74 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | NULL | Not on List | 6 | No | 84.41 | 506.46 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11629-001025 | 11629 | 2019-01-29 13:40 | Section 3 | Material | NULL | Not on List | 1 | No | 600 | 600 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11448-001025 | 11448 | 2019-01-25 07:57 | Section 3 | Material | Not on List | Not on List | 2 | Mo | NULL | 0 | Builders Merchants (General) | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11448-001025 | 11448 | 2019-01-25 07:57 | Section 3 | Material | NULL | Polypipe 225mm x 150mm Ridgidrain 90deg Junction (878037) | 10 | Each | 39.7 | 397 | Builders Merchants (General) | 2019-01-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11744-001025 | 11744 | 2019-01-31 15:54 | Section 3 | Material | Twinwall | Not on List | 2 | No | NULL | 0 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11743-001 | 11743 | 2019-01-31 15:53 | Section 3 | Material | Aggregate | A10 Pipe Bed | 300 | Tonnes | 16.5 | 4950 | Aggregate | 2019-02-01 | RVP 419 - 1340880 - A14 Westbound (West of Junction 28) | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11745-001025 | 11745 | 2019-01-31 15:36 | Section 4 | Material | Combined Drainage | Not on List | 8 | EA | 77.85 | 623 | Concrete Drainage | 2019-02-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11696-001025 | 11696 | 2019-01-31 08:09 | Section 3 | Material | NULL | Not on List | 48 | No | 15.71 | 754.08 | Ductile Drainage | 2019-02-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11696-001025 | 11696 | 2019-01-31 08:09 | Section 3 | Material | NULL | Not on List | 36 | No | 10.66 | 383.76 | Ductile Drainage | 2019-02-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | NULL | Not on List | 3 | EA | 84.41 | 253.23 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | NULL | Not on List | 1 | Ea | 44.41 | 44.41 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | NULL | Not on List | 20 | Ea | 7.64 | 152.8 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | NULL | Not on List | 10 | EA | 7.64 | 76.4 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11726-001025 | 11726 | 2019-01-31 12:42 | Section 3 | Material | NULL | Not on List | 10 | EA | 7.64 | 76.4 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11756-001025 | 11756 | 2019-01-31 16:46 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2019-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-11756-001025 | 11756 | 2019-01-31 16:46 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Accessories | 2019-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 30 | No. | 4.5 | 135 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 95 | No. | 5.72 | 543.4 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18044-001025 | 18044 | 2019-05-24 10:58 | Section 3 | Material | Not on List | Not on List | 145 | No. | 21.33 | 3092.85 | Fixings and Fasteners | 2019-05-29 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18202-001025 | 18202 | 2019-05-29 14:11 | Section 5 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Builders Merchants (General) | 2019-05-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18202-001025 | 18202 | 2019-05-29 14:11 | Section 5 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 14 | Each | 535 | 7490 | Builders Merchants (General) | 2019-05-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18202-001025 | 18202 | 2019-05-29 14:11 | Section 5 | Material | Not on List | Not on List | 750 | litres | NULL | 0 | Builders Merchants (General) | 2019-05-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18184-001025 | 18184 | 2019-05-29 09:24 | Section 4 | Material | Not on List | Not on List | 25 | EA | 12.81 | 320.25 | Concrete Accessories | 2019-06-12 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18182-001025 | 18182 | 2019-05-29 09:11 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18156-001025 | 18156 | 2019-05-29 07:22 | Section 4 | Material | Not on List | Not on List | 200 | Each | 7.48 | 1496 | Builders Merchants (General) | 2019-05-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18158-001025 | 18158 | 2019-05-29 07:29 | Section 4 | Material | Not on List | Not on List | 100 | Each | 3.04 | 304 | Builders Merchants (General) | 2019-05-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18219-001025 | 18219 | 2019-05-29 17:30 | Section 1 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196 | Aggregate | 2019-06-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18219-001025 | 18219 | 2019-05-29 17:30 | Section 1 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 80 | Each | 3.56 | 285 | Aggregate | 2019-06-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18219-001025 | 18219 | 2019-05-29 17:30 | Section 1 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Aggregate | 2019-06-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18219-001025 | 18219 | 2019-05-29 17:30 | Section 1 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Aggregate | 2019-06-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18219-001025 | 18219 | 2019-05-29 17:30 | Section 1 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Aggregate | 2019-06-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18222-001025 | 18222 | 2019-05-29 17:49 | Section 3 | Material | Twinwall | Not on List | 5 | NULL | NULL | 0 | Plastic Drainage | 2019-05-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-18237-001025 | 18237 | 2019-05-30 07:36 | Section 5 | Material | Not on List | Not on List | 1 | NULL | 1949 | 1949 | Surveying Consumables | 2019-05-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18248-001025 | 18248 | 2019-05-30 08:01 | Section 2 | Material | Not on List | Not on List | 1 | NULL | 281.7 | 282 | Miscellaneous | 2019-06-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18248-001025 | 18248 | 2019-05-30 08:01 | Section 2 | Material | Not on List | Not on List | 1 | NULL | 385.7 | 386 | Miscellaneous | 2019-06-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2A - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18183-001025 | 18183 | 2019-05-29 09:16 | Section 3 | Material | Not on List | Not on List | 1.5 | tonne | 538 | 807 | NULL | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18183-001025 | 18183 | 2019-05-29 09:16 | Section 3 | Material | Not on List | Not on List | 1.5 | tonne | 538 | 807 | NULL | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17958-001025 | 17958 | 2019-05-23 10:26 | Section 3 | Material | Not on List | Not on List | 25 | tins | 20.25 | 506.25 | Miscellaneous | 2019-05-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17958-001025 | 17958 | 2019-05-23 10:26 | Section 3 | Material | Not on List | Not on List | 10 | tins | 57.92 | 579.2 | Miscellaneous | 2019-05-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18229-001025 | 18229 | 2019-05-29 18:26 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18188-001025 | 18188 | 2019-05-29 08:08 | Section 4 | Material | Not on List | Not on List | 25 | coils | 46.5 | 1162.5 | NULL | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18188-001025 | 18188 | 2019-05-29 08:08 | Section 4 | Material | Not on List | Not on List | 9 | Pack | 40.6 | 365.4 | NULL | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18188-001025 | 18188 | 2019-05-29 08:08 | Section 4 | Material | Not on List | Not on List | 2 | Pack | 21 | 42 | NULL | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18188-001025 | 18188 | 2019-05-29 08:08 | Section 4 | Material | Not on List | Not on List | 30 | number | 4.94 | 148.2 | NULL | 2019-05-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4C - Structures (Culverts) 4C | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18264-001025 | 18264 | 2019-05-30 11:45 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-05-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-6624-00750 | 6624 | 2018-09-18 08:04 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 128.91 | 128.91 | Builders Merchants (General) | 2018-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2702 - Works by the Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6624-00750 | 6624 | 2018-09-18 08:04 | Section 3 | Material | Not on List | Not on List | 10 | NULL | 53.3 | 533 | Builders Merchants (General) | 2018-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2702 - Works by the Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18241-001025 | 18241 | 2019-05-30 08:08 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Bend 11.25deg (878082) | 2 | Each | 81.47 | 162.94 | Plastic Drainage | 2019-05-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18189-001025 | 18189 | 2019-05-29 10:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1441.64 | 1441.64 | PPE | 2019-06-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18257-001025 | 18257 | 2019-05-30 10:12 | Section 3 | Material | Not on List | Not on List | 4 | No | 104.99 | 419.96 | Plastic Drainage | 2019-06-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18257-001025 | 18257 | 2019-05-30 10:12 | Section 3 | Material | Not on List | Not on List | 4 | No | 125.94 | 503.76 | Plastic Drainage | 2019-06-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18257-001025 | 18257 | 2019-05-30 10:12 | Section 3 | Material | Not on List | Not on List | 4 | No | 18.87 | 75.48 | Plastic Drainage | 2019-06-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18257-001025 | 18257 | 2019-05-30 10:12 | Section 3 | Material | Not on List | Not on List | 16 | No | 10.84 | 173.44 | Plastic Drainage | 2019-06-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18181-001025 | 18181 | 2019-05-29 09:13 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Pack 24 | 6.29 | 905.76 | Small Tools (Consumables) | 2019-06-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-4993-006 | 4993 | 2018-08-13 14:56 | Section 4 | Material | Not on List | NULL | 63 | Each | 3.17 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6624-00750 | 6624 | 2018-09-18 08:04 | Section 3 | Material | Not on List | Not on List | 4 | NULL | 6.33 | 25.32 | Builders Merchants (General) | 2018-09-20 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2702 - Works by the Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18291-001025 | 18291 | 2019-05-30 15:34 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Builders Merchants (General) | 2019-05-31 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18080-001025 | 18080 | 2019-05-24 16:22 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18252-001025 | 18252 | 2019-05-30 10:09 | Section 4 | Material | Not on List | Not on List | 10 | bags | 1 | 10 | Builders Merchants (General) | 2019-06-03 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18190-001025 | 18190 | 2019-05-29 10:17 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2249.4 | 2249.4 | Small Tools (Consumables) | 2019-06-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18318-001025 | 18318 | 2019-05-31 07:34 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 5 | Each | 241.48 | 1207.4 | Concrete Drainage | 2019-06-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18318-001025 | 18318 | 2019-05-31 07:34 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Socket (249372) | 1 | Each | 289.78 | 289.78 | Concrete Drainage | 2019-06-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18318-001025 | 18318 | 2019-05-31 07:34 | Section 3 | Material | Concrete Drainage | CPM 900mm Concrete Spigot (249371) | 1 | Each | 278.64 | 278.64 | Concrete Drainage | 2019-06-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18318-001025 | 18318 | 2019-05-31 07:34 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 4 | Each | 48.92 | 195.68 | Concrete Drainage | 2019-06-04 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18318-001025 | 18318 | 2019-05-31 07:34 | Section 3 | Material | NULL | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 8 | Each | 179.74 | 1437.92 | Plastic Drainage | 2019-06-04 | Gate C - 1339699 - BN08 via Logistics Yard Access | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18247-001025 | 18247 | 2019-05-30 08:52 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 166.85 | 166.85 | Small Tools (Consumables) | 2019-06-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18210-001025 | 18210 | 2019-05-29 16:30 | Section 4 | Material | Concrete Drainage | Not on List | 1 | Each | 225.3 | 225.3 | Concrete Drainage | 2019-06-05 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18330-001025 | 18330 | 2019-05-31 10:28 | Section 5 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-06-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6626-00750 | 6626 | 2018-09-18 08:14 | Section 3 | Material | Not on List | Not on List | 1 | x200 Tubes | 692 | 692 | Concrete Accessories | 2018-09-21 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN10 - A1198 Ermine Street Overbridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18330-001025 | 18330 | 2019-05-31 10:28 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18330-001025 | 18330 | 2019-05-31 10:28 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-10 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18191-001025 | 18191 | 2019-05-29 10:25 | Section 3 | Material | Not on List | Not on List | 175 | roll | 196 | 34300 | Builders Merchants (General) | 2019-06-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18191-001025 | 18191 | 2019-05-29 10:25 | Section 3 | Material | Not on List | Not on List | 450 | No | 2.55 | 1147.5 | Builders Merchants (General) | 2019-06-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18195-001025 | 18195 | 2019-05-29 12:04 | Section 3 | Material | NULL | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 20 | Each | 130.26 | 2605.2 | Plastic Drainage | 2019-06-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18195-001025 | 18195 | 2019-05-29 12:04 | Section 3 | Material | NULL | Polypipe 400mm Seal (346394) | 40 | Each | 9.76 | 390.4 | Plastic Drainage | 2019-06-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18195-001025 | 18195 | 2019-05-29 12:04 | Section 3 | Material | Not on List | Not on List | 5 | ea | 164.37 | 821.85 | Plastic Drainage | 2019-06-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18195-001025 | 18195 | 2019-05-29 12:04 | Section 3 | Material | NULL | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 12 | Each | 125.94 | 1511.28 | Plastic Drainage | 2019-06-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18195-001025 | 18195 | 2019-05-29 12:04 | Section 3 | Material | NULL | Polypipe 450mm Ridgidrain Seal (346396) | 24 | Each | 10.8 | 259.2 | Plastic Drainage | 2019-06-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18378-001025 | 18378 | 2019-05-31 15:50 | Core | Material | Not on List | Not on List | 1 | ea | 1150 | 1150 | Training | 2019-05-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | NULL | Yes - Approve | REQ - Buyers
MREQ-18280-001025 | 18280 | 2019-05-30 14:55 | Section 4 | Material | Not on List | Not on List | 1 | EA | 72 | 72 | Concrete Accessories | 2019-06-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18280-001025 | 18280 | 2019-05-30 14:55 | Section 4 | Material | NULL | Not on List | 1 | Ea | 650 | 650 | Concrete Accessories | 2019-06-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18394-001025 | 18394 | 2019-06-02 15:59 | Section 3 | Material | Not on List | Not on List | 2000 | NULL | NULL | 0 | Miscellaneous | 2019-07-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18346-001025 | 18346 | 2019-05-31 13:32 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-06-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18346-001025 | 18346 | 2019-05-31 13:32 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-06-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18172-001025 | 18172 | 2019-05-29 08:24 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 370 | 370 | Laboratory Equipment / Certification | 2019-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15615-001025 | 15615 | 2019-04-10 14:10 | Core | Material | Not on List | Not on List | 1 | Sum | 1710 | 1710 | Miscellaneous | 2019-04-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15856-001025 | 15856 | 2019-04-15 12:42 | Core | Material | PPE, Small Tools and Consumables | Not on List | 6 | NULL | NULL | 0 | Office Supplies | 2019-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | NULL | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17367-001025 | 17367 | 2019-05-14 11:46 | Core | Material | Not on List | Not on List | 1 | NULL | 29.15 | 29 | Office Supplies | 2019-05-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17333-001025 | 17333 | 2019-05-14 07:34 | Core | Material | Not on List | Not on List | 12 | ea | 6000 | 72000 | Office Supplies | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18313-001025 | 18313 | 2019-05-30 16:44 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-4993-006 | 4993 | 2018-08-13 14:56 | Section 4 | Material | Not on List | NULL | 600 | Each | 0.55 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18285-001025 | 18285 | 2019-05-30 14:54 | Section 3 | Material | Not on List | Not on List | 1 | roll | 78.95 | 78.95 | Fixings and Fasteners | 2019-06-04 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18342-001025 | 18342 | 2019-05-31 13:00 | Section 4 | Material | Not on List | Not on List | 1 | EA | 100 | 100 | Concrete Accessories | 2019-06-07 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 64 | Each | 24.99 | 1599.36 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 100 | Each | 3.65 | 365 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 200 | Each | 2 | 400 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 55 | Each | 37.6 | 2068 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 70 | Each | 7.06 | 494.2 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 140 | Each | 2.97 | 415.8 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 82 | Each | 130.26 | 10681.32 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 100 | Each | 18.84 | 1884 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 200 | Each | 9.76 | 1952 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 80 | Each | 125.94 | 10075.2 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 100 | Each | 18.87 | 1887 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 200 | Each | 10.84 | 2168 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 16 | Each | 179.74 | 2875.84 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 48 | Each | 38.36 | 1841.28 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18335-001025 | 18335 | 2019-05-31 11:10 | Section 4 | Material | Not on List | Not on List | 100 | Each | 22.37 | 2237 | Plastic Drainage | 2019-06-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17239-001025 | 17239 | 2019-05-13 08:45 | Section 3 | Material | Not on List | Not on List | 1 | ea | 662.73 | 662.73 | Miscellaneous | 2019-05-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-17262-001025 | 17262 | 2019-05-13 12:06 | Section 3 | Material | Not on List | Not on List | 1 | EA | 7734.38 | 7734.38 | Miscellaneous | 2019-05-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18390-001025 | 18390 | 2019-06-01 13:36 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-18336-001025 | 18336 | 2019-05-31 11:38 | Section 6 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 25 | Each | 0.91 | 22.75 | Plastic Drainage | 2019-06-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18336-001025 | 18336 | 2019-05-31 11:38 | Section 6 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 50 | Each | 2 | 100 | Plastic Drainage | 2019-06-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18336-001025 | 18336 | 2019-05-31 11:38 | Section 6 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 25 | Each | 2.97 | 74.25 | Plastic Drainage | 2019-06-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6668-00750 | 6668 | 2018-09-18 12:53 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18414-001025 | 18414 | 2019-06-03 09:24 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18464-001025 | 18464 | 2019-06-03 16:02 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 48 | Each | 28.8 | 1382.4 | PPE | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18415-001025 | 18415 | 2019-06-03 09:36 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18393-001025 | 18393 | 2019-06-01 16:00 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18507-001025 | 18507 | 2019-06-04 10:41 | Section 3 | Material | Not on List | Not on List | 1 | each | 1580 | 1580 | Miscellaneous | 2019-06-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 3 Buyers
MREQ-16650-001025 | 16650 | 2019-04-30 11:55 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-04-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18456-001025 | 18456 | 2019-06-03 15:24 | Section 4 | Material | Not on List | Not on List | 15 | EA | 32.15 | 482.25 | Builders Merchants (General) | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18513-001025 | 18513 | 2019-06-04 11:25 | Core | Material | PPE, Small Tools and Consumables | Stake Marking Out Wooden 1200mm Nominal C.r.code Swcoc004463 (740904) | 100 | Each | 1.07 | 107 | Surveying Consumables | 2019-06-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18513-001025 | 18513 | 2019-06-04 11:25 | Core | Material | PPE, Small Tools and Consumables | Profile Board Wooden - 900mm Nominal C.r.code Swcoc004463 (740910) | 100 | Each | 0.67 | 67 | Surveying Consumables | 2019-06-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18155-001025 | 18155 | 2019-05-29 06:48 | Core | Material | Not on List | Not on List | 1 | GBP | 2820 | 2820 | Miscellaneous | 2019-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 209 | EA | 52.5 | 10972.5 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6668 | 6668 | 2018-09-18 12:53 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2018-09-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 2 | EA | 60 | 120 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 1 | EA | 75 | 75 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 2 | EA | 1200 | 2400 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 20 | EA | 12 | 240 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 20 | EA | 35 | 700 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 2 | Each | 189.47 | 378.94 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 1 | Each | 49.32 | 49.32 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 2 | Each | 158 | 316 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18267-001025 | 18267 | 2019-05-30 12:15 | Section 4 | Material | NULL | Not on List | 1 | Each | 11.68 | 11.68 | Ductile Drainage | 2019-06-20 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18562-001025 | 18562 | 2019-06-04 17:53 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18488-001025 | 18488 | 2019-06-04 07:45 | Section 4 | Material | NULL | NULL | 1 | Ea | NULL | 0 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18488-001025 | 18488 | 2019-06-04 07:45 | Section 4 | Material | NULL | NULL | 0 | Ea | NULL | 0 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18570-001025 | 18570 | 2019-06-05 07:42 | Core | Material | Not on List | Not on List | 150 | no | NULL | 0 | Surveying Consumables | 2019-06-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27945-001025 | 27945 | 2020-01-08 16:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Box | NULL | 0 | Small Tools (Consumables) | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 3020 - Seeding, Turfing and Planting | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27945-001025 | 27945 | 2020-01-08 16:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Box | NULL | 0 | Small Tools (Consumables) | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 3020 - Seeding, Turfing and Planting | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27952-001025 | 27952 | 2020-01-08 16:36 | Section 4 | Material | Kerbs | Not on List | 25 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | NULL | NULL | REQ - Section 4 Buyers
MREQ-27952-001025 | 27952 | 2020-01-08 16:36 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | NULL | NULL | REQ - Section 4 Buyers
MREQ-27963-001025 | 27963 | 2020-01-09 09:14 | Section 5 | Material | Timber | Not on List | 3 | packs | NULL | 0 | Timber Products | 2020-01-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27972-001025 | 27972 | 2020-01-09 11:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 80.82 | 162 | Small Tools (Consumables) | 2020-01-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27972-001025 | 27972 | 2020-01-09 11:39 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 21.6 | 22 | Small Tools (Consumables) | 2020-01-13 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-27973-001025 | 27973 | 2020-01-09 11:43 | Section 4 | Material | Not on List | Not on List | 150 | NULL | NULL | 0 | Timber Products | 2020-01-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27974-001025 | 27974 | 2020-01-09 11:56 | Core | Material | Not on List | Not on List | 6 | ea | 6000 | 36000 | Office Supplies | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27975-001025 | 27975 | 2020-01-09 12:24 | Core | Material | Not on List | Not on List | 1000 | ea | 2.75 | 2750 | Office Supplies | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27975-001025 | 27975 | 2020-01-09 12:24 | Core | Material | Not on List | Not on List | 4 | ea | 4.75 | 19 | Office Supplies | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27976-001025 | 27976 | 2020-01-09 12:42 | Core | Material | Not on List | Not on List | 6 | ea | 522 | 3132 | Office Supplies | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Buyers
MREQ-7366-001022 | 7366 | 2018-10-03 17:42 | Section 4 | Material | Not on List | Not on List | 10 | Number | 9906.83 | 99068.3 | Not Sure | 2018-10-18 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27977-001025 | 27977 | 2020-01-09 12:52 | Core | Material | Not on List | Not on List | 6 | ea | 2160 | 12960 | Office Supplies | 2020-01-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-7352-001022 | 7352 | 2018-10-03 12:25 | Section 4 | Material | NULL | Terram 1000 4.5m x 100m 16 rolls and above (820795) | 16 | Each | 110.27 | 1764.32 | Geotextiles | 2018-10-08 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 30 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 50 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 20 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27991-001025 | 27991 | 2020-01-09 14:48 | Section 4 | Material | Kerbs | Not on List | 20 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-27997-001025 | 27997 | 2020-01-09 15:48 | Section 4 | Material | Not on List | Not on List | 2 | Number | 65 | 130 | Surveying Consumables | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27992-001025 | 27992 | 2020-01-09 15:37 | Section 4 | Material | Not on List | Not on List | 30 | No | 23.25 | 697.5 | Builders Merchants (General) | 2020-01-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28022-001025 | 28022 | 2020-01-10 09:58 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27784-001025 | 27784 | 2019-12-18 10:04 | Section 3 | Material | Not on List | Not on List | 15 | no. | 44 | 660 | Miscellaneous | 2020-01-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN14 - Hilton Road Overbridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28037-001025 | 28037 | 2020-01-10 12:29 | Section 4 | Material | Not on List | Not on List | 140000 | ea | 1 | 140000 | Gas Oil | 2020-01-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28053-001025 | 28053 | 2020-01-10 15:05 | Section 4 | Material | Not on List | Not on List | 36 | NULL | NULL | 0 | Plastic Drainage | 2020-01-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27754-001025 | 27754 | 2019-12-18 09:51 | Section 3 | Material | Aggregate | 6G | 60 | Tonnes | 32.9 | 1974 | Aggregate | 2020-01-06 | Gate J - BN12 & BN13, B1040 St Ives Rd, Off A14 Jcn 26 Westbound | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 8 | meters | 4.6 | 36.8 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 4 | Meters | 4.6 | 18.4 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 3 | Meters | 4.6 | 13.8 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 6 | Number | 4.6 | 27.6 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 2 | Number | 4.6 | 9.2 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 2 | Number | 4.6 | 9.2 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 8 | Meters | 14.67 | 117.36 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 3 | Meters | 14.67 | 44.01 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 3 | Meters | 14.67 | 44.01 | Plastic Drainage | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 8 | Number | 19.9 | 159.2 | Fixings and Fasteners | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 3 | Number | 19.9 | 59.7 | Fixings and Fasteners | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27882-001025 | 27882 | 2020-01-06 16:09 | Section 2 | Material | Not on List | Not on List | 3 | Number | 19.9 | 59.7 | Fixings and Fasteners | 2020-01-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN26 - A14/A1 Link Underbridge | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-27988-001025 | 27988 | 2020-01-09 14:47 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28076-001025 | 28076 | 2020-01-13 08:20 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | PPE | 2020-01-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28076-001025 | 28076 | 2020-01-13 08:20 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | PPE | 2020-01-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28077-001025 | 28077 | 2020-01-13 08:32 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Ductile Drainage | 2020-01-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28083-001025 | 28083 | 2020-01-13 10:11 | Core | Material | Signage | Directional Signage - 460 x 190 | 1 | number | 694.09 | 694 | Miscellaneous | 2020-01-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28009-001025 | 28009 | 2020-01-09 16:20 | Section 5 | Material | Concrete Drainage | CPM 2100 Cover Slab 600x600 Opening (890472) | 1 | Each | 4360.79 | 4360.79 | Concrete Drainage | 2020-01-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1502 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 20 | ea | NULL | 0 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28088-001025 | 28088 | 2020-01-13 12:36 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-01-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28093-001025 | 28093 | 2020-01-13 14:54 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-01-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28094-001025 | 28094 | 2020-01-13 15:24 | Section 2 | Material | Not on List | Not on List | 1 | ea | 89.4 | 89 | Professional Services | 2019-12-29 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28103-001025 | 28103 | 2020-01-13 16:07 | Section 5 | Material | Not on List | Not on List | 1 | ea | 1437.48 | 1437 | Professional Services | 2019-12-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28123-001025 | 28123 | 2020-01-14 08:49 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 100 | Each | 5.9 | 590 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 66.97 | 67 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 30 | Each | 167.88 | 5036.4 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 30 | Each | 16.41 | 492.3 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 30 | Each | 11.34 | 340.2 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 30 | Each | 1.98 | 59.4 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 60 | Each | 0.91 | 54.6 | Ductile Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 30 | Each | 26.4 | 792 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 60 | Each | 16.41 | 984.6 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | Not on List | Not on List | 45 | Each | 74.3 | 3343.5 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 80 | Each | 189 | 15120 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 50 | Each | 16.96 | 848 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7114-001022 | 7114 | 2018-09-27 17:49 | Section 3 | Material | Not on List | Not on List | 1 | ea | 66.97 | 67 | Miscellaneous | 2018-10-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 10 | Each | 125.94 | 1259.4 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 10 | Each | 18.87 | 188.7 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 36 | Each | 11.51 | 414.36 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 36 | Each | 1.98 | 71.28 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ27965-001025 | 27965 | 2020-01-08 17:53 | Section 4 | Material | NULL | Not on List | 36 | Each | 0.91 | 32.76 | Plastic Drainage | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28138-001025 | 28138 | 2020-01-14 12:35 | Section 4 | Material | Not on List | Not on List | 1 | Number | 336 | 336 | Surveying Consumables | 2020-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 100 | number | 34.33 | 3433 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 60 | number | 43.4 | 2604 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 2 | number | 53.14 | 106.28 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 300 | number | 28.09 | 8427 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 60 | number | 27.9 | 1674 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 8 | number | 61.16 | 489.28 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 60 | number | 63.68 | 3820.8 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28011-001025 | 28011 | 2020-01-09 20:30 | Section 2 | Material | Combined Drainage | Not on List | 42 | number | 13.08 | 549.36 | Concrete Drainage | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28145-001025 | 28145 | 2020-01-14 14:13 | Section 5 | Material | Not on List | Not on List | 4 | bags | NULL | 0 | Concrete Accessories | 2020-01-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28156-001025 | 28156 | 2020-01-14 15:31 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 25 | 50 | Surveying Consumables | 2020-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1801 - Structural Steelwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28091-001025 | 28091 | 2020-01-13 14:17 | Section 4 | Material | NULL | NULL | 384 | Each | 5.9 | 2265.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28170-001025 | 28170 | 2020-01-15 10:53 | Core | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Office Supplies | 2020-01-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28171-001025 | 28171 | 2020-01-15 10:56 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 50 | number | NULL | 0 | Surveying Consumables | 2020-01-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28171-001025 | 28171 | 2020-01-15 10:56 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 50 | number | NULL | 0 | Surveying Consumables | 2020-01-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28099-001025 | 28099 | 2020-01-13 15:46 | Section 2 | Material | Not on List | Not on List | 1 | ea | 1353.57 | 1353.57 | Fixings and Fasteners | 2020-01-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28192-001025 | 28192 | 2020-01-15 16:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 664.46 | 664 | PPE | 2020-01-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28192-001025 | 28192 | 2020-01-15 16:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 286.48 | 286 | Janitorial | 2020-01-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28192-001025 | 28192 | 2020-01-15 16:27 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 69.48 | 69 | Small Tools (Consumables) | 2020-01-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28199-001025 | 28199 | 2020-01-15 17:28 | Section 6 | Material | Signage | Not on List | 16 | each | 7.65 | 122 | Professional Services | 2020-01-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28199-001025 | 28199 | 2020-01-15 17:28 | Section 6 | Material | Signage | Not on List | 10 | each | 7.65 | 77 | Professional Services | 2020-01-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 65 | Each | 65 | 4225 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 2 | Each | 2 | 4 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 30 | Each | 30 | 900 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 30 | Each | 30 | 900 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 27 | Each | 27 | 729 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 36 | Each | 36 | 1296 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 48 | Each | 48 | 2304 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28144-001025 | 28144 | 2020-01-14 13:04 | Section 4 | Material | Not on List | Not on List | 70 | Each | 70 | 4900 | Plastic Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28206-001025 | 28206 | 2020-01-16 08:29 | Core | Material | Not on List | Not on List | 1 | No | 373 | 373 | Office Supplies | 2020-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 118 - Catering Costs (buffets etc) | IMO - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-28196-001025 | 28196 | 2020-01-15 16:42 | Section 4 | Material | Not on List | Not on List | 1 | ea | 254.83 | 255 | Professional Services | 2019-12-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28214-001025 | 28214 | 2020-01-16 09:03 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 96.16 | 96 | Small Tools (Consumables) | 2020-01-20 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28221-001025 | 28221 | 2020-01-16 13:22 | Section 4 | Material | Not on List | Not on List | 1 | no | 5000 | 5000 | Electrical | 2020-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28228-001025 | 28228 | 2020-01-16 14:37 | Section 6 | Material | Not on List | Not on List | 1 | No | 434.16 | 434 | Professional Services | 2019-11-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28233-001025 | 28233 | 2020-01-16 14:50 | Section 5 | Material | Not on List | Not on List | 1 | No | 125 | 125 | Professional Services | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28233-001025 | 28233 | 2020-01-16 14:50 | Section 5 | Material | Not on List | Not on List | 1 | No | 165 | 165 | Professional Services | 2020-01-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28239-001025 | 28239 | 2020-01-16 15:34 | Core | Material | Not on List | Not on List | 1 | NULL | 7246.01 | 7246 | Miscellaneous | 2020-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28241-001025 | 28241 | 2020-01-16 16:01 | Core | Material | Not on List | Not on List | 1 | NULL | 207 | 207 | Miscellaneous | 2020-01-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28242-001025 | 28242 | 2020-01-16 15:40 | Section 3 | Material | Not on List | Not on List | 1 | No | 1440 | 1440 | Professional Services | 2019-12-19 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-7437-001022 | 7437 | 2018-10-05 10:39 | Section 4 | Material | Not on List | Not on List | 6 | boxes of 5 | 11.23 | 67 | Not Sure | 2018-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28242-001025 | 28242 | 2020-01-16 15:40 | Section 3 | Material | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2019-11-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28244-001025 | 28244 | 2020-01-16 16:52 | Section 4 | Material | Not on List | Not on List | 1 | No | 1478.32 | 1478 | Professional Services | 2020-01-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28244-001025 | 28244 | 2020-01-16 16:52 | Section 4 | Material | Not on List | Not on List | 1 | No | 270 | 270 | Professional Services | 2020-01-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 62 | Each | 70.62 | 4378.44 | Ductile Drainage | 2020-01-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 34 | Each | 52.97 | 1800.98 | Ductile Drainage | 2020-01-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 30 | Each | 44.89 | 1346.7 | Ductile Drainage | 2020-01-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 60 | Each | 48.92 | 2935.2 | Concrete Drainage | 2020-01-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19441-001025 | 19441 | 2019-06-20 14:59 | Section 4 | Material | Waste Management | Metal - Skip 12 cubic yard | 1 | Each | 75 | 75 | Laboratory Equipment / Certification | 2019-06-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17361-001025 | 17361 | 2019-05-14 09:49 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 80 | Each | 1.31 | 104.8 | Small Tools (Consumables) | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19854-001025 | 19854 | 2019-06-27 14:43 | Section 2 | Material | Twinwall | Polypipe 100mm Linflex 100m (877398) | 10 | Each | 175 | 1750 | Plastic Drainage | 2019-07-02 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19854-001025 | 19854 | 2019-06-27 14:43 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 3 | Each | 67.9 | 203.7 | Concrete Drainage | 2019-07-02 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19854-001025 | 19854 | 2019-06-27 14:43 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 3 | Each | 47.04 | 141.12 | Concrete Drainage | 2019-07-02 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19854-001025 | 19854 | 2019-06-27 14:43 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2019-07-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19854-001025 | 19854 | 2019-06-27 14:43 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2019-07-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19991-001025 | 19991 | 2019-07-01 10:56 | Section 2 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1157.8 | Geotextiles | 2019-07-03 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19992-001025 | 19992 | 2019-06-26 15:30 | Section 4 | Material | Not on List | Not on List | 200 | bags | 14.43 | 2886 | Builders Merchants (General) | 2019-07-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19992-001025 | 19992 | 2019-06-26 15:30 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 1200 | 1200 | Laboratory Equipment / Certification | 2019-07-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19766-001025 | 19766 | 2019-06-26 12:53 | Section 3 | Material | Not on List | Not on List | 2 | EACH | 16.1 | 32.2 | Miscellaneous | 2019-07-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20010-001025 | 20010 | 2019-07-01 13:56 | Section 5 | Material | Not on List | Not on List | 16 | EA | 134.7 | 2155.2 | Miscellaneous | 2019-07-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19872-001025 | 19872 | 2019-06-27 18:07 | Section 3 | Material | Not on List | Not on List | 200 | Bags | 14.43 | 2886 | Concrete Accessories | 2019-07-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19946-001025 | 19946 | 2019-06-28 15:15 | Section 2 | Material | Geotextile | Not on List | 20 | rolls | 266.67 | 5333.4 | Geotextiles | 2019-07-09 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19946-001025 | 19946 | 2019-06-28 15:15 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1000 | pins | 1.86 | 1860 | Miscellaneous | 2019-07-09 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19588-001025 | 19588 | 2019-06-24 09:07 | Core | Material | NULL | NULL | 1 | Each | 687.44 | 687.44 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19487-001025 | 19487 | 2019-06-21 09:48 | Core | Material | NULL | NULL | 1 | Each | 262 | 262 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19969-001025 | 19969 | 2019-06-30 21:04 | Section 5 | Material | Twinwall | NULL | 1 | SM | 3577.11 | 3577.11 | Plastic Drainage | 2019-07-03 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20051-001025 | 20051 | 2019-07-02 09:51 | Section 2 | Material | Aggregate | Type 1 | 750 | Tonnes | 21.65 | 16237.5 | Aggregate | 2019-07-02 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19950-001025 | 19950 | 2019-06-28 15:46 | Section 2 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 2 | Each | 535 | 1070 | Geotextiles | 2019-07-03 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19950-001025 | 19950 | 2019-06-28 15:46 | Section 2 | Material | Geotextile | Not on List | 5 | each | NULL | 0 | Geotextiles | 2019-07-03 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19482-001025 | 19482 | 2019-06-21 09:29 | Core | Material | NULL | NULL | 1 | Each | 650 | 650 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19978-001025 | 19978 | 2019-07-01 08:24 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Miscellaneous | 2019-07-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19790-001025 | 19790 | 2019-06-26 15:52 | Section 2 | Material | Not on List | Not on List | 129 | NULL | NULL | 0 | Ductile Drainage | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19790-001025 | 19790 | 2019-06-26 15:52 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Ductile Drainage | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19790-001025 | 19790 | 2019-06-26 15:52 | Section 2 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Ductile Drainage | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-19790-001025 | 19790 | 2019-06-26 15:52 | Section 2 | Material | Not on List | Not on List | 65 | NULL | NULL | 0 | Ductile Drainage | 2019-07-01 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20098-001025 | 20098 | 2019-07-02 14:30 | Core | Material | Not on List | Not on List | 1 | NULL | 312 | 312 | Miscellaneous | 2019-07-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19657-001025 | 19657 | 2019-06-25 08:48 | Core | Material | NULL | NULL | 1 | Each | 280 | 280 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19785-001025 | 19785 | 2019-06-26 15:52 | Section 4 | Material | Not on List | Not on List | 1 | ea | 241.48 | 241.48 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19785-001025 | 19785 | 2019-06-26 15:52 | Section 4 | Material | Not on List | Not on List | 2 | ea | 289.78 | 579.56 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19785-001025 | 19785 | 2019-06-26 15:52 | Section 4 | Material | NULL | Not on List | 1 | ea | 200 | 200 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19785-001025 | 19785 | 2019-06-26 15:52 | Section 4 | Material | NULL | Not on List | 1 | ea | 240 | 240 | Concrete Drainage | 2019-07-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20118-001025 | 20118 | 2019-07-02 19:48 | Section 5 | Material | Not on List | Not on List | 6 | number | 75 | 450 | Surveying Consumables | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | NULL | Req - S5 Buyers
MREQ-19661-001025 | 19661 | 2019-06-25 09:06 | Core | Material | NULL | NULL | 5 | Set 2 20ltr Buckets C/W Lids | 18.9 | 94.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18592-001025 | 18592 | 2019-06-05 12:20 | Section 4 | Material | Not on List | Not on List | 1 | £ | 9.99 | 10 | Office Supplies | 2019-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5142-0070 | 5142 | 2018-08-15 11:34 | Section 3 | Material | Concrete Drainage | Cpm 1050 Slab 600X600 Access | 16 | Each | 47.04 | 752.64 | Concrete Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20137-001025 | 20137 | 2019-07-03 08:42 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1720 | 1720 | Miscellaneous | 2019-07-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Ear Muff Helmet Mounted Jsp Inter Ex Black/Red Snr28 (254222) | 5 | Each | 13.44 | 67 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Water Natural Mineral Ideal Still 500ml Bottle Case Of 24 (744570) | 1 | Pallet | 6.29 | 6 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6465-00710 | 6465 | 2018-09-13 10:14 | Section 3 | Material | Not on List | Not on List | 1 | SUM | 2838.5 | 2838.5 | Damage Charges | 2018-09-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Tank Dust Suppression Duro 13 Litre Ref Dp-dst-13l (766568) | 4 | Each | 33.95 | 136 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 12 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Level Spirit Heavy Duty Aluminium Spartan Pro 1200mm/4 (740561) | 3 | Each | 14.99 | 45 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Tissue Toilet Roll Pristine 2ply White 36 X 320sheets 517347 (539289) | 20 | Each | 7.32 | 146 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Rake Asphalt/Tarmac Flat Tooth Metal Handle Spartan Pro (762583) | 10 | Each | 17.28 | 173 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Strap Lashing 8m Ratchet Hvy Duty 2 Tonne Load 5 Tonne Break (746483) | 10 | Each | 21.34 | 213 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Scraper First Task 75mm Stripping Knife Ref 14003020 (746838) | 5 | Each | 5.55 | 28 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Scourer Grooved Sponge Yellow 150 X 70mm Pack Of 10 (546416) | 5 | Each | 6.26 | 31 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Bucket Flexi Tub 40 Litre Black (506338) | 10 | Each | 9 | 90 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20154-001025 | 20154 | 2019-07-02 15:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19947-001025 | 19947 | 2019-06-28 15:45 | Section 3 | Material | Not on List | Not on List | 1 | Roll 700M | 78.95 | 78.95 | Aggregate | 2019-06-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20005-001025 | 20005 | 2019-07-01 12:49 | Section 4 | Material | NULL | NULL | 126 | Each | 29.76 | 3749.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-08 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20005-001025 | 20005 | 2019-07-01 12:49 | Section 4 | Material | NULL | NULL | 1 | Each | 204.75 | 204.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-08 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20005-001025 | 20005 | 2019-07-01 12:49 | Section 4 | Material | NULL | NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-08 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20009-001025 | 20009 | 2019-07-01 15:03 | Section 3 | Material | Not on List | Not on List | 5 | Boxes | 99.4 | 497 | Miscellaneous | 2019-07-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20139-001025 | 20139 | 2019-07-03 08:52 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5558-00360 | 5558 | 2018-08-23 09:26 | Section 4 | Material | Not on List | Not on List | 137055 | Each | 1 | 137055 | Geotextiles | 2018-09-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20170-001025 | 20170 | 2019-07-03 13:52 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20170-001025 | 20170 | 2019-07-03 13:52 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20170-001025 | 20170 | 2019-07-03 13:52 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-19838-001025 | 19838 | 2019-06-27 10:35 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1188.8 | Each | 1 | 1188.8 | Small Tools (Consumables) | 2019-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19838-001025 | 19838 | 2019-06-27 10:35 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | 2.5kg Tub | 33.03 | 660.6 | Miscellaneous | 2019-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19698-001025 | 19698 | 2019-06-25 11:38 | Section 4 | Material | NULL | NULL | 1 | Each | 1930.86 | 1930.86 | Miscellaneous | 2019-07-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19900-001025 | 19900 | 2019-06-28 08:51 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1800 x 500 D/S (528455) | 1 | Each | 108.94 | 108.94 | Concrete Drainage | 2019-07-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20109-001025 | 20109 | 2019-07-02 15:57 | Section 6 | Material | Twinwall | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2019-07-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20109-001025 | 20109 | 2019-07-02 15:57 | Section 6 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Plastic Drainage | 2019-07-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20109-001025 | 20109 | 2019-07-02 15:57 | Section 6 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Electrical | 2019-07-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5001-0014 | 5001 | 2018-08-13 16:25 | Section 4 | Material | Plastic Drainage | Not on List | 4 | each | 57.28 | 0 | Plastic Drainage | 2018-08-14 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20179-001025 | 20179 | 2019-07-03 16:30 | Section 6 | Material | Concrete Drainage | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2019-07-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20191-001025 | 20191 | 2019-07-04 01:59 | Section 5 | Material | Not on List | Not on List | 185 | no. | NULL | 0 | Reinforcement | 2019-07-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE28 - Milton Bridge Modifications | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20148-001025 | 20148 | 2019-07-03 11:13 | Section 3 | Material | Not on List | Not on List | 6 | No. Cans | 24.35 | 146.1 | Builders Merchants (General) | 2019-07-08 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20202-001025 | 20202 | 2019-07-04 10:01 | Core | Material | Not on List | Not on List | 50 | NULL | 42 | 2100 | Training | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5179-00112 | 5179 | 2018-08-15 16:25 | Section 4 | Material | Not on List | NULL | 21 | Sqmtr | 27.88 | 585.48 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20152-001025 | 20152 | 2019-07-03 11:49 | Section 3 | Material | Not on List | Not on List | 6 | Plates | 15 | 90 | Ductile Drainage | 2019-07-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20057-001025 | 20057 | 2019-07-02 10:29 | Core | Material | NULL | NULL | 1 | Each | 1397 | 1397 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20056-001025 | 20056 | 2019-07-02 10:18 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 17 | ea | 90 | 1530 | Miscellaneous | 2019-07-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20047-001025 | 20047 | 2019-07-02 09:18 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | 38.09 | 1142.7 | Miscellaneous | 2019-07-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19779-001025 | 19779 | 2019-06-26 14:30 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20208-001025 | 20208 | 2019-07-04 11:01 | Section 4 | Material | Twinwall | Polyipipe 150mm Ridgidrain Bend 90deg (878001) | 5 | Each | 17.06 | 85.3 | Plastic Drainage | 2019-07-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5179-00112 | 5179 | 2018-08-15 16:25 | Section 4 | Material | NULL | NULL | 4 | Each | 10 | 40 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20208-001025 | 20208 | 2019-07-04 11:01 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Bend 15deg (877998) | 30 | Each | 17.03 | 510.9 | Plastic Drainage | 2019-07-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20208-001025 | 20208 | 2019-07-04 11:01 | Section 4 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 60 | Each | 1.55 | 93 | Plastic Drainage | 2019-07-04 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20034-001025 | 20034 | 2019-07-02 07:45 | Section 4 | Material | Not on List | Not on List | 100 | Each | 142.82 | 14282 | Concrete Drainage | 2019-07-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20034-001025 | 20034 | 2019-07-02 07:45 | Section 4 | Material | NULL | Not on List | 1 | Each | 190 | 190 | Concrete Drainage | 2019-07-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20259-001025 | 20259 | 2019-07-05 07:10 | Section 3 | Material | Not on List | Not on List | 10 | No. | NULL | 0 | Builders Merchants (General) | 2019-07-09 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20052-001025 | 20052 | 2019-07-02 10:07 | Core | Material | NULL | NULL | 1 | Each | 1227.5 | 1227.5 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5179-00112 | 5179 | 2018-08-15 16:25 | Section 4 | Material | NULL | NULL | 4 | Each | 34.5 | 138 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-09-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20281-001025 | 20281 | 2019-07-05 08:59 | Section 5 | Material | Not on List | Not on List | 1 | pack | NULL | 0 | Builders Merchants (General) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20281-001025 | 20281 | 2019-07-05 08:59 | Section 5 | Material | Not on List | Not on List | 1 | list | NULL | 0 | Builders Merchants (General) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20281-001025 | 20281 | 2019-07-05 08:59 | Section 5 | Material | Not on List | Not on List | 20 | m | NULL | 0 | Builders Merchants (General) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5249-00162 | 5249 | 2018-08-16 16:33 | Section 4 | Material | Plastic Drainage | NULL | 200 | Each | 15.77 | 3154 | Plastic Drainage | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20281-001025 | 20281 | 2019-07-05 08:59 | Section 5 | Material | Not on List | Not on List | 25 | m | NULL | 0 | Builders Merchants (General) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20281-001025 | 20281 | 2019-07-05 08:59 | Section 5 | Material | Not on List | Not on List | 35 | number | NULL | 0 | Builders Merchants (General) | 2019-07-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20285-001025 | 20285 | 2019-07-05 10:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | 199 | 199 | Miscellaneous | 2019-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20232-001025 | 20232 | 2019-07-04 15:02 | Section 4 | Material | NULL | NULL | 2 | Each | 273.24 | 546.48 | Miscellaneous | 2019-07-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20301-001025 | 20301 | 2019-07-05 13:42 | Core | Material | Not on List | Not on List | 1 | NULL | 37.5 | 38 | Training | 2019-07-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20212-001025 | 20212 | 2019-07-04 11:21 | Core | Material | PPE, Small Tools and Consumables | Not on List | 443.76 | each | 1 | 443.76 | Janitorial | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5249-00162 | 5249 | 2018-08-16 16:33 | Section 4 | Material | Plastic Drainage | NULL | 100 | Each | 15.77 | 1577 | Plastic Drainage | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20210-001025 | 20210 | 2019-07-04 11:10 | Core | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20130-001025 | 20130 | 2019-07-03 08:02 | Section 4 | Material | NULL | NULL | 400 | Each | 7.5 | 3000 | Surveying Consumables | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20140-001025 | 20140 | 2019-07-03 10:39 | Core | Material | NULL | NULL | 215.26 | Each | 1 | 215.26 | NULL | 2019-07-10 | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20141-001025 | 20141 | 2019-07-03 10:49 | Core | Material | NULL | NULL | 419 | Each | 1 | 419 | NULL | 2019-07-10 | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20143-001025 | 20143 | 2019-07-03 10:55 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 127.1 | Each | 1 | 127.1 | Miscellaneous | 2019-07-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20209-001025 | 20209 | 2019-07-04 11:01 | Core | Material | PPE, Small Tools and Consumables | Not on List | 48 | Each | 28.8 | 1382.4 | PPE | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20209-001025 | 20209 | 2019-07-04 11:01 | Core | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 13.44 | 134.4 | PPE | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20211-001025 | 20211 | 2019-07-04 11:15 | Core | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | 3.42 | 136.8 | Small Tools (Consumables) | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5142-0070 | 5142 | 2018-08-15 11:34 | Section 3 | Material | Concrete Drainage | Not on List | 16 | Each | 209.35 | 3349.6 | Concrete Drainage | 2018-08-28 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5249-00162 | 5249 | 2018-08-16 16:33 | Section 4 | Material | Plastic Drainage | NULL | 100 | Each | 15.77 | 1577 | Plastic Drainage | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20382-001025 | 20382 | 2019-07-08 10:52 | Section 5 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 1 | Load | 24.32 | 24 | Timber Products | 2019-07-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20386-001025 | 20386 | 2019-07-08 11:02 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5249-00162 | 5249 | 2018-08-16 16:33 | Section 4 | Material | Plastic Drainage | NULL | 20 | Each | 26.5 | 530 | Plastic Drainage | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24142-001025 | 24142 | 2019-09-23 14:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | NULL | NULL | 0 | PPE | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S5 Buyers
MREQ-24142-001025 | 24142 | 2019-09-23 14:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | PPE | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S5 Buyers
MREQ-24142-001025 | 24142 | 2019-09-23 14:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-09-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | NULL | Req - S5 Buyers
MREQ-24119-001025 | 24119 | 2019-09-23 17:47 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 90deg (878086) | 50 | Each | 52.76 | 2638 | Plastic Drainage | 2019-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24119-001025 | 24119 | 2019-09-23 17:47 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Bend 45deg (878085) | 20 | Each | 52.76 | 1055.2 | Plastic Drainage | 2019-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24119-001025 | 24119 | 2019-09-23 17:47 | Section 4 | Material | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 140 | Each | 2.97 | 415.8 | Plastic Drainage | 2019-09-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6783-00751 | 6783 | 2018-09-20 13:37 | Section 4 | Material | Not on List | Not on List | 10 | Each | 59.5 | 595 | Plastic Drainage | 2018-09-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24184-001025 | 24184 | 2019-09-25 07:58 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 11.19 | 22 | Miscellaneous | 2019-09-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24184-001025 | 24184 | 2019-09-25 07:58 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 16.23 | 32 | Miscellaneous | 2019-09-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24194-001025 | 24194 | 2019-09-25 08:30 | Section 2 | Material | Waste Management | Not on List | 1 | each | 600 | 600 | Waste (General) | 2019-09-25 | Gate 5 - 1340889 - BN28 via Gate 5, A14 Eastbound Only Brampton | PLM2 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24203-001025 | 24203 | 2019-09-25 09:56 | Section 3 | Material | Not on List | Not on List | 500 | No | NULL | 0 | Builders Merchants (General) | 2019-09-27 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24163-001025 | 24163 | 2019-09-24 14:14 | Section 5 | Material | Aggregate | Type 1 | 1000 | Tonnes | 21.65 | 21650 | Aggregate | 2019-09-25 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23775-001025 | 23775 | 2019-09-17 10:32 | Section 4 | Material | Not on List | Not on List | 1 | Number | 2097.66 | 2097.66 | Surveying Consumables | 2019-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23973-001025 | 23973 | 2019-09-20 07:31 | Section 2 | Material | Not on List | Not on List | 3500 | m2 | NULL | 0 | Concrete Accessories | 2019-09-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23885-001025 | 23885 | 2019-09-19 07:46 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Concrete Accessories | 2019-09-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6833-00751 | 6833 | 2018-09-21 08:48 | Section 4 | Material | Not on List | Not on List | 10 | Each | 4.18 | 41.8 | Concrete Accessories | 2018-09-25 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23885-001025 | 23885 | 2019-09-19 07:46 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Accessories | 2019-09-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23850-001025 | 23850 | 2019-09-18 12:22 | Section 3 | Material | Combined Drainage | Kerb Drain 405 Drop Kerb 480 (947299) | 2 | Each | 34.93 | 69.86 | Concrete Drainage | 2019-09-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-23850-001025 | 23850 | 2019-09-18 12:22 | Section 3 | Material | Combined Drainage | Kerb Drain Splayed Gully Access (947299) | 1 | Each | 40.5 | 40.5 | Blocks and Bricks | 2019-09-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24130-001025 | 24130 | 2019-09-24 08:17 | Section 2 | Material | Not on List | Not on List | 1 | each | 3331.91 | 3331.91 | Professional Services | 2019-09-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6847-00751 | 6847 | 2018-09-21 09:48 | Section 4 | Material | Iron Wear | Not on List | 25 | Each | 58.04 | 1451 | Ductile Drainage | 2018-10-05 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24204-001025 | 24204 | 2019-09-25 10:38 | Section 3 | Material | Kerbs | Not on List | 6 | No | 7.96 | 47.76 | Builders Merchants (General) | 2019-09-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24214-001025 | 24214 | 2019-09-25 12:20 | Section 2 | Material | Geotextile | Not on List | 10 | rolls | 2047.57 | 20475.7 | Geotextiles | 2019-09-30 | Gate S/B5 - 1340891 - Access to BN03 East, A1 Southbound | SC2B - Roadworks - A14 | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24214-001025 | 24214 | 2019-09-25 12:20 | Section 2 | Material | Geotextile | Not on List | 5500 | pins | 1.3 | 7150 | Geotextiles | 2019-09-30 | Gate S/B5 - 1340891 - Access to BN03 East, A1 Southbound | SC2B - Roadworks - A14 | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24206-001025 | 24206 | 2019-09-25 11:22 | Section 4 | Material | Not on List | Not on List | 1 | Each | 485 | 485 | Fixings and Fasteners | 2019-09-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-24206-001025 | 24206 | 2019-09-25 11:22 | Section 4 | Material | NULL | Not on List | 1 | Each | 175 | 175 | Fixings and Fasteners | 2019-09-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-24176-001025 | 24176 | 2019-09-24 17:45 | Section 2 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2019-09-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24207-001025 | 24207 | 2019-09-25 11:08 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 4 | each | 70.99 | 283.96 | Concrete Drainage | 2019-09-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24207-001025 | 24207 | 2019-09-25 11:08 | Section 3 | Material | Not on List | Not on List | 4 | each | 74.3 | 297.2 | Miscellaneous | 2019-09-26 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6847-00751 | 6847 | 2018-09-21 09:48 | Section 4 | Material | Iron Wear | Not on List | 175 | Each | 58.04 | 10157 | Ductile Drainage | 2018-10-05 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24240-001025 | 24240 | 2019-09-26 08:16 | Section 3 | Material | Not on List | Not on List | 6 | EA | NULL | 0 | Fixings and Fasteners | 2019-09-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1201 - Traffic Signs | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-24240-001025 | 24240 | 2019-09-26 08:16 | Section 3 | Material | Not on List | Not on List | 6 | EA | NULL | 0 | Fixings and Fasteners | 2019-09-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1201 - Traffic Signs | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-5188-00115 | 5188 | 2018-08-15 18:58 | Section 4 | Material | Not on List | Not on List | 1000 | each | NULL | 0 | Timber Products | 2018-08-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6847-00751 | 6847 | 2018-09-21 09:48 | Section 4 | Material | Iron Wear | Not on List | 175 | Each | 86.24 | 15092 | Ductile Drainage | 2018-10-05 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24244-001025 | 24244 | 2019-09-26 09:18 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-09-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-23902-001025 | 23902 | 2019-09-19 09:29 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24266-001025 | 24266 | 2019-09-26 14:05 | Section 5 | Material | Not on List | Not on List | 2 | EA | 88.22 | 176.44 | Not Sure | 2019-09-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24274-001025 | 24274 | 2019-09-26 15:05 | Section 6 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2019-10-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6848-00751 | 6848 | 2018-09-21 09:56 | Section 4 | Material | Not on List | Not on List | 3 | Each | 336.95 | 1010.85 | Plastic Drainage | 2018-10-01 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24274-001025 | 24274 | 2019-09-26 15:05 | Section 6 | Material | Not on List | Not on List | 1 | ea | NULL | 0 | Miscellaneous | 2019-10-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24293-001025 | 24293 | 2019-09-27 07:45 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24303-001025 | 24303 | 2019-09-27 10:05 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Surveying Consumables | 2019-10-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24304-001025 | 24304 | 2019-09-27 10:52 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-09-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 2 | Each | 1460 | 2920 | Flow Control | 2019-10-04 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 1 | Each | 265 | 265 | Flow Control | 2019-10-04 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 1 | Each | 265 | 265 | Flow Control | 2019-10-04 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6848-00751 | 6848 | 2018-09-21 09:56 | Section 4 | Material | Not on List | Not on List | 18 | Each | 2.92 | 52.56 | Plastic Drainage | 2018-10-01 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 2 | Each | 95 | 190 | Flow Control | 2019-10-04 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 5 | Boxes | NULL | 0 | Concrete Drainage | 2019-10-04 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24238-001025 | 24238 | 2019-09-26 07:20 | Section 6 | Material | Not on List | Not on List | 2 | Boxes | NULL | 0 | Concrete Drainage | 2019-10-04 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24310-001025 | 24310 | 2019-09-27 12:17 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24318-001025 | 24318 | 2019-09-27 13:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1201 - Traffic Signs | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-24318-001025 | 24318 | 2019-09-27 13:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1201 - Traffic Signs | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-6848-00751 | 6848 | 2018-09-21 09:56 | Section 4 | Material | Not on List | Not on List | 8 | Each | 26.94 | 215.52 | Plastic Drainage | 2018-10-01 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6853-00751 | 6853 | 2018-09-21 07:56 | Section 4 | Material | Not on List | Not on List | 0.29 | Tonne | 538 | 156.02 | Rebar and Mesh | 2018-10-09 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6853-00751 | 6853 | 2018-09-21 07:56 | Section 4 | Material | Not on List | Not on List | 0.29 | Tonne | 538 | 156.02 | Rebar and Mesh | 2018-10-09 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6853-00751 | 6853 | 2018-09-21 07:56 | Section 4 | Material | Not on List | Not on List | 20 | Each | 93.93 | 1878.6 | Rebar and Mesh | 2018-10-04 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24302-001025 | 24302 | 2019-09-27 09:12 | Core | Material | Not on List | Not on List | 1 | SM | 623.54 | 623.54 | Not Sure | 2019-09-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24258-001025 | 24258 | 2019-09-26 11:54 | Section 5 | Material | Not on List | Not on List | 1 | NULL | 2699.4 | 2699.4 | Damage Charges | 2019-09-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24378-001025 | 24378 | 2019-09-30 11:00 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24369-001025 | 24369 | 2019-09-30 08:19 | Section 4 | Material | NULL | NULL | 1 | Each | 19.2 | 19.2 | Plastic Drainage | 2019-10-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6853-00751 | 6853 | 2018-09-21 07:56 | Section 4 | Material | Not on List | Not on List | 20 | Each | 51.87 | 1037.4 | Rebar and Mesh | 2018-10-04 | RVP 408 - 1339625 - Hazelwell Court - Bar Hill J29 A14 Eastbound | BN23 - Structure BN23 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24381-001025 | 24381 | 2019-09-30 12:20 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24375-001025 | 24375 | 2019-09-30 09:22 | Section 5 | Material | Twinwall | Not on List | 2 | No | 81.47 | 162.94 | Plastic Drainage | 2019-09-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24330-001025 | 24330 | 2019-09-27 15:11 | Section 4 | Material | Not on List | Not on List | 15 | Each | 51.5 | 772.5 | Rebar and Mesh | 2019-10-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24330-001025 | 24330 | 2019-09-27 15:11 | Section 4 | Material | Not on List | Not on List | 15 | Each | 38.77 | 581.55 | Builders Merchants (General) | 2019-10-02 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24394-001025 | 24394 | 2019-09-30 15:13 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24416-001025 | 24416 | 2019-10-01 06:23 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-10-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 153 - Temporary Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24434-001025 | 24434 | 2019-10-01 08:38 | Section 3 | Material | Not on List | Not on List | 1000 | 7717344434 | NULL | 0 | Miscellaneous | 2019-10-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24435-001025 | 24435 | 2019-10-01 08:45 | Section 2 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Miscellaneous | 2019-10-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 100 | Each | 25.5 | 2550 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24440-001025 | 24440 | 2019-10-01 09:58 | Section 4 | Material | Not on List | Not on List | 30 | NULL | 26.25 | 788 | Miscellaneous | 2019-10-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | REQ - Section 4 Buyers
MREQ-24449-001025 | 24449 | 2019-10-01 13:17 | Section 5 | Material | Not on List | Not on List | 5 | Number | NULL | 0 | Miscellaneous | 2019-10-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-23649-001025 | 23649 | 2019-09-13 11:35 | Section 4 | Material | Not on List | Not on List | 5 | Each | 51.48 | 257.4 | Concrete Accessories | 2019-09-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23649-001025 | 23649 | 2019-09-13 11:35 | Section 4 | Material | Not on List | Not on List | 225 | Kg | 3.1 | 697.5 | Concrete Accessories | 2019-09-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23649-001025 | 23649 | 2019-09-13 11:35 | Section 4 | Material | Not on List | Not on List | 2 | coils | 261.07 | 522.14 | Concrete Accessories | 2019-09-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23649-001025 | 23649 | 2019-09-13 11:35 | Section 4 | Material | NULL | Not on List | 3 | Each | 36.34 | 109.02 | Concrete Accessories | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23649-001025 | 23649 | 2019-09-13 11:35 | Section 4 | Material | NULL | Not on List | 1 | Each | 35 | 35 | Concrete Accessories | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 100 | Each | 2.65 | 265 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24165-001025 | 24165 | 2019-09-24 15:03 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 282.81 | 282.81 | Small Tools (Consumables) | 2019-09-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24472-001025 | 24472 | 2019-10-01 15:59 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 602 - Excavation (excl topsoil) | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-24472-001025 | 24472 | 2019-10-01 15:59 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-10-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 2703 - Works on behalf of Statutory Undertakers | Commercial - Rejected | Yes - Approve | No - Reject | Req - S2 Buyers
MREQ-24159-001025 | 24159 | 2019-09-24 13:13 | Section 4 | Material | NULL | NULL | 104 | Each | 16.18 | 1682.72 | Miscellaneous | 2019-10-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24242-001025 | 24242 | 2019-09-26 08:49 | Section 4 | Material | Not on List | Not on List | 8 | Each | 35 | 280 | Electrical | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24242-001025 | 24242 | 2019-09-26 08:49 | Section 4 | Material | Not on List | Not on List | 10 | Each | 10 | 100 | Electrical | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24242-001025 | 24242 | 2019-09-26 08:49 | Section 4 | Material | Not on List | Not on List | 2 | Each | 50 | 100 | Electrical | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24242-001025 | 24242 | 2019-09-26 08:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 50 | 50 | Electrical | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24483-001025 | 24483 | 2019-10-02 07:24 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5189-00116 | 5189 | 2018-08-16 07:01 | Section 4 | Material | Not on List | Not on List | 400 | each | NULL | 0 | Miscellaneous | 2018-08-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 100 | Each | 9.51 | 951 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24372-001025 | 24372 | 2019-09-30 07:59 | Section 6 | Material | Not on List | Not on List | 23 | Each | 36.14 | 831.22 | Miscellaneous | 2019-10-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24372-001025 | 24372 | 2019-09-30 07:59 | Section 6 | Material | Not on List | Not on List | 1 | Each | 20.92 | 20.92 | Miscellaneous | 2019-10-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24372-001025 | 24372 | 2019-09-30 07:59 | Section 6 | Material | Not on List | Not on List | 7 | Each | 25.34 | 177.38 | Miscellaneous | 2019-10-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24372-001025 | 24372 | 2019-09-30 07:59 | Section 6 | Material | Not on List | Not on List | 2 | Each | 39.34 | 78.68 | Miscellaneous | 2019-10-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24372-001025 | 24372 | 2019-09-30 07:59 | Section 6 | Material | Not on List | Not on List | 75 | Metres | NULL | 0 | Miscellaneous | 2019-10-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 100 | Each | 15.77 | 1577 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 100 | Each | 15.77 | 1577 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24512-001025 | 24512 | 2019-10-02 10:45 | Section 5 | Material | Not on List | Not on List | 1 | each | 750 | 750 | Miscellaneous | 2019-10-01 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24506-001025 | 24506 | 2019-10-02 09:58 | Section 2 | Material | Kerbs | Not on List | 45 | number | 5.75 | 258.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24463-001025 | 24463 | 2019-10-01 14:49 | Core | Material | NULL | NULL | 1 | Each | 1556 | 1556 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 400 | Each | 1.44 | 576 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24484-001025 | 24484 | 2019-10-02 07:17 | Section 4 | Material | Not on List | Not on List | 9 | packs | 168.5 | 1516.5 | Fixings and Fasteners | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24484-001025 | 24484 | 2019-10-02 07:17 | Section 4 | Material | Not on List | Not on List | 9 | packs | 11 | 99 | Fixings and Fasteners | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24484-001025 | 24484 | 2019-10-02 07:17 | Section 4 | Material | Not on List | Not on List | 6 | packs | 2.12 | 12.72 | Fixings and Fasteners | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24484-001025 | 24484 | 2019-10-02 07:17 | Section 4 | Material | Not on List | Not on List | 6 | packs | 1.55 | 9.3 | Fixings and Fasteners | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24484-001025 | 24484 | 2019-10-02 07:17 | Section 4 | Material | NULL | Not on List | 1 | Each | 38.5 | 38.5 | Fixings and Fasteners | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 5 | Each | 28.5 | 142.5 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23267-001025 | 23267 | 2019-09-05 13:11 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24460-001025 | 24460 | 2019-10-01 14:34 | Core | Material | NULL | NULL | 1 | Each | 950 | 950 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24501-001025 | 24501 | 2019-10-02 09:00 | Section 4 | Material | Not on List | Not on List | 20 | Each | 38.77 | 775.4 | Builders Merchants (General) | 2019-10-04 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24522-001025 | 24522 | 2019-10-02 12:34 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24528-001025 | 24528 | 2019-10-02 13:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 313.11 | 313 | Small Tools (Consumables) | 2019-10-07 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 20 | Each | 5.74 | 114.8 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24528-001025 | 24528 | 2019-10-02 13:12 | Core | Material | Not on List | Not on List | 1 | NULL | 474.28 | 474 | Janitorial | 2019-10-07 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24528-001025 | 24528 | 2019-10-02 13:12 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 1553.1 | 1553 | PPE | 2019-10-07 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6859-00751 | 6859 | 2018-09-21 11:44 | Section 4 | Material | Not on List | Not on List | 40 | Each | 3.17 | 126.8 | Plastic Drainage | 2018-09-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24327-001025 | 24327 | 2019-09-27 14:45 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24560-001025 | 24560 | 2019-10-03 08:37 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6863-00751 | 6863 | 2018-09-21 12:23 | Section 4 | Material | Concrete Drainage | CPM 1200mm Concrete Pipe 2.5m (249379) | 21 | Each | 483.27 | 10148.67 | Concrete Drainage | 2018-10-08 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24562-001025 | 24562 | 2019-10-03 09:05 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24565-001025 | 24565 | 2019-10-03 09:10 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-23707-001025 | 23707 | 2019-09-16 08:46 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24241-001025 | 24241 | 2019-09-26 08:46 | Core | Material | NULL | NULL | 1 | No. | 160.45 | 160 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24347-001025 | 24347 | 2019-09-28 15:10 | Section 5 | Material | Combined Drainage | NULL | 1 | SM | 17490.28 | 17490.28 | NULL | 2019-10-03 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14015-001025 | 14015 | 2019-03-14 09:26 | Section 2 | Material | Timber | Not on List | 35 | m | NULL | 0 | Timber Products | 2019-03-20 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14015-001025 | 14015 | 2019-03-14 09:26 | Section 2 | Material | Not on List | Not on List | 25 | NULL | NULL | 0 | Miscellaneous | 2019-03-20 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 44 | No. | 34.82 | 1532.08 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 16 | No. | 6.54 | 104.64 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 76 | No. | 2.75 | 209 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 36 | No. | 10.66 | 383.76 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 36 | No. | 1.84 | 66.24 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13959-001025 | 13959 | 2019-03-13 15:27 | Section 3 | Material | Not on List | Not on List | 72 | No. | 0.85 | 61.2 | Plastic Drainage | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14025-001025 | 14025 | 2019-03-14 10:59 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-03-15 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S1 Buyers
MREQ-13555-001025 | 13555 | 2019-03-06 12:50 | Section 2 | Material | Not on List | Not on List | 44 | No. | 14.46 | 636.24 | Fixings and Fasteners | 2019-03-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14032-001025 | 14032 | 2019-03-14 11:53 | Section 5 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Miscellaneous | 2019-03-18 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-13456-001025 | 13456 | 2019-03-04 09:54 | Core | Material | Not on List | Not on List | 1 | NULL | 513 | 513 | Office Supplies | 2019-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14019-001025 | 14019 | 2019-03-14 09:35 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 100 | each | 28.8 | 2880 | PPE | 2019-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14009-001025 | 14009 | 2019-03-14 09:13 | Section 4 | Material | Not on List | Not on List | 2 | Number | 44.25 | 88.5 | Miscellaneous | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13771-001025 | 13771 | 2019-03-11 12:01 | Core | Material | Not on List | Not on List | 1 | Number | 319.37 | 319 | Miscellaneous | 2019-03-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | 110 - Welfare Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 145 | Each | 28 | 4060 | Plastic Drainage | 2019-03-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 28 | 28 | Plastic Drainage | 2019-02-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 28 | 56 | Plastic Drainage | 2019-02-28 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 45 | 90 | Plastic Drainage | 2019-04-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 3000 | 3000 | Miscellaneous | 2019-02-25 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 20 | Each | 38 | 760 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 121 | Each | 28 | 3388 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 28 | 56 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 45 | 90 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 15 | Each | 38 | 570 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-4948-002 | 4948 | 2018-08-10 14:44 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 3987.4 | 0 | Miscellaneous | NULL | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5059-0024 | 5059 | 2018-08-14 12:47 | Section 4 | Material | Plastic Drainage | P/Pipe 100Mm X 100Mtr Linflex 100 | 20 | Each | 175 | 3500 | Plastic Drainage | 2018-08-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 145 | Each | 28 | 4060 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 28 | 28 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 28 | 56 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 45 | 90 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 20 | Each | 38 | 760 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 117 | Each | 28 | 3276 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 4 | Each | 28 | 112 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 28 | 28 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 2 | Each | 45 | 90 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 15 | Each | 38 | 570 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13044-001025 | 13044 | 2019-02-25 14:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 125 | 125 | Plastic Drainage | NULL | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13970-001025 | 13970 | 2019-03-13 15:47 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 3 | each | 304 | 912 | Fuel | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13970-001025 | 13970 | 2019-03-13 15:47 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | each | 68 | 408 | Fuel | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13970-001025 | 13970 | 2019-03-13 15:47 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 10 | each | 86 | 860 | Fuel | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13970-001025 | 13970 | 2019-03-13 15:47 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 6 | each | 170 | 1020 | Fuel | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13970-001025 | 13970 | 2019-03-13 15:47 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 100 | each | 11.99 | 1199 | Fuel | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14072-001025 | 14072 | 2019-03-14 17:21 | Section 2 | Material | Hazardous Waste | Not on List | 3 | each | 655 | 1965 | Waste (General) | 2019-03-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14023-001025 | 14023 | 2019-03-14 10:31 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | 18.32 | 54.96 | Small Tools (Consumables) | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14023-001025 | 14023 | 2019-03-14 10:31 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 39.38 | 236.28 | Small Tools (Consumables) | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14024-001025 | 14024 | 2019-03-14 10:31 | Section 2 | Material | Not on List | Not on List | 80 | number | NULL | 0 | Miscellaneous | 2019-03-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14024-001025 | 14024 | 2019-03-14 10:31 | Section 2 | Material | Not on List | Not on List | 50 | number | NULL | 0 | Miscellaneous | 2019-03-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14024-001025 | 14024 | 2019-03-14 10:31 | Section 2 | Material | Not on List | Not on List | 100 | number | NULL | 0 | Miscellaneous | 2019-03-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13915-001025 | 13915 | 2019-03-13 08:47 | Section 3 | Material | Not on List | Not on List | 30 | EA | 48.86 | 1465.8 | Builders Merchants (General) | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13915-001025 | 13915 | 2019-03-13 08:47 | Section 3 | Material | Not on List | Not on List | 30 | ea | 13.75 | 412.5 | Builders Merchants (General) | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13915-001025 | 13915 | 2019-03-13 08:47 | Section 3 | Material | Not on List | Not on List | 15 | EA | 34.82 | 522.3 | Builders Merchants (General) | 2019-03-14 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13571-001025 | 13571 | 2019-03-06 15:21 | Section 4 | Material | Not on List | Not on List | 30 | Each | NULL | 0 | Concrete Accessories | 2019-03-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13571-001025 | 13571 | 2019-03-06 15:21 | Section 4 | Material | Not on List | Not on List | 30 | Each | 0.13 | 3.9 | Concrete Accessories | 2019-03-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13571-001025 | 13571 | 2019-03-06 15:21 | Section 4 | Material | Not on List | Not on List | 10 | Each | 24.18 | 241.8 | Concrete Accessories | 2019-03-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13571-001025 | 13571 | 2019-03-06 15:21 | Section 4 | Material | Not on List | Not on List | 1 | Each | 101 | 101 | Concrete Accessories | 2019-03-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13571-001025 | 13571 | 2019-03-06 15:21 | Section 4 | Material | Not on List | Not on List | 3 | Each | 12.81 | 38.43 | Concrete Accessories | 2019-03-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14093-001025 | 14093 | 2019-03-15 09:58 | Section 2 | Material | Bagged | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14093-001025 | 14093 | 2019-03-15 09:58 | Section 2 | Material | Twinwall | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14093-001025 | 14093 | 2019-03-15 09:58 | Section 2 | Material | Twinwall | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14093-001025 | 14093 | 2019-03-15 09:58 | Section 2 | Material | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 30 | Each | 81.73 | 2452 | Plastic Drainage | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14103-001025 | 14103 | 2019-03-15 10:46 | Section 3 | Material | Twinwall | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-14061-001025 | 14061 | 2019-03-14 16:19 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3012.6 | Each | 1 | 3012.6 | Miscellaneous | 2019-03-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14111-001025 | 14111 | 2019-03-15 12:23 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14089-001025 | 14089 | 2019-03-15 09:09 | Section 4 | Material | Aggregate | Not on List | 10000 | Loads | 75 | 750000 | Aggregate | 2019-03-25 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14003-001025 | 14003 | 2019-03-14 08:57 | Section 4 | Material | Waste Management | Not on List | 38500 | Each | 1 | 38500 | Waste (General) | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14006-001025 | 14006 | 2019-03-14 09:03 | Section 4 | Material | Waste Management | Not on List | 47500 | Each | 1 | 47500 | Waste (General) | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13849-001025 | 13849 | 2019-03-12 11:26 | Section 4 | Material | Not on List | Not on List | 1 | Each | 336.28 | 336.28 | Miscellaneous | 2019-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14121-001025 | 14121 | 2019-03-15 13:44 | Section 2 | Material | Not on List | Not on List | 900 | sq meters | NULL | 0 | Concrete Accessories | 2019-03-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14121-001025 | 14121 | 2019-03-15 13:44 | Section 2 | Material | Not on List | Not on List | 180 | Lengths | NULL | 0 | Concrete Accessories | 2019-03-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14121-001025 | 14121 | 2019-03-15 13:44 | Section 2 | Material | Not on List | Not on List | 180 | Lengths | NULL | 0 | Concrete Accessories | 2019-03-20 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13539-001025 | 13539 | 2019-03-06 11:13 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2923.25 | 2923.25 | Miscellaneous | 2019-03-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14125-001025 | 14125 | 2019-03-15 10:04 | Section 4 | Material | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2019-03-18 | RVP 420 - A14 Eastbound - Opposite Crematorium | SC4C - Roadworks - Dry Drayton to Girton | 2703 - Works on behalf of Statutory Undertakers | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-14051-001025 | 14051 | 2019-03-14 15:38 | Section 3 | Material | Not on List | Not on List | 2 | ea | 3083.08 | 6166.16 | Damage Charges | 2019-03-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13838-001025 | 13838 | 2019-03-12 09:59 | Section 4 | Material | Not on List | Not on List | 1 | Each | 159.25 | 159.25 | Miscellaneous | 2019-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13936-001025 | 13936 | 2019-03-13 12:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 176.16 | 176.16 | Miscellaneous | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5672-00429 | 5672 | 2018-08-28 09:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2843.69 | 2843.69 | Small Tools (Consumables) | 2018-08-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Not on List | 20 | Units | NULL | 0 | Concrete Drainage | 2019-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 22 | Each | 67.9 | 1493.8 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 750 D/S (913030) | 4 | Each | 50.92 | 203.68 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 500 D/S (913004) | 10 | Each | 43.16 | 431.6 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 10 | Each | 35.52 | 355.2 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1500x1000 D/S (991900) | 4 | Each | 121.25 | 485 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM Chamber Ring 1500x750 D/S (991899) | 2 | Each | 90.94 | 181.88 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM 1500 Cover Slab 600x600 Opening (989592) | 6 | Each | 102.82 | 616.92 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5812-00493 | 5812 | 2018-08-30 13:00 | Section 3 | Material | Misc | Not on List | 3 | Hours | 40 | 120 | Professional Services | 2018-08-02 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 20 | Each | 47.04 | 940.8 | Concrete Drainage | 2019-03-18 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 50 | Each | 34.82 | 1741 | Plastic Drainage | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 40 | Each | 120.62 | 4824.8 | Plastic Drainage | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14062-001025 | 14062 | 2019-03-14 15:30 | Section 2 | Material | NULL | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2019-03-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14095-001025 | 14095 | 2019-03-15 10:07 | Core | Material | Not on List | Not on List | 1 | ea | 63002 | 63002 | Office Supplies | 2019-03-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14083-001025 | 14083 | 2019-03-15 08:07 | Core | Material | Not on List | Not on List | 1 | ea | 1440 | 1440 | Training | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14028-001025 | 14028 | 2019-03-14 11:17 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 144 | 144 | Laboratory Equipment / Certification | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13293-001025 | 13293 | 2019-02-28 16:57 | Core | Material | Not on List | Not on List | 1 | NULL | 345.01 | 345.01 | Miscellaneous | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5811-00489 | 5811 | 2018-08-30 12:54 | Section 3 | Material | Not on List | Not on List | 2 | Packs | 138.24 | 276.48 | Builders Merchants (General) | 2018-09-03 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11919-001025 | 11919 | 2019-02-05 09:28 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12009-001025 | 12009 | 2019-02-06 14:48 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-14163-001025 | 14163 | 2019-03-18 09:59 | Section 5 | Material | Signage | Miscellaneous Signs - 75 | 1 | Each | 0.22466 | 0 | Miscellaneous | 2019-03-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14163-001025 | 14163 | 2019-03-18 09:59 | Section 5 | Material | Signage | Miscellaneous Signs - 75 | 1 | Each | 0.22466 | 0 | Miscellaneous | 2019-03-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Padlock Brass Spartan 50mm Open Shackle (744428) | 30 | Each | 3.66 | 110 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Level Spirit Heavy Duty Boat Shaped Spartan Pro 225mm/9 (740523) | 5 | Each | 4.48 | 22 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Mallet Rubber C/W Wooden Handle 0.7kg/2 (790014) | 5 | Each | 4.78 | 24 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Mallet Rubber C/W Wooden Handle 0.7kg/2 (790014) | 5 | Each | 4.78 | 24 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Jerrican Metal 20 Litre Capacity Spartan Pro (708622) | 5 | Each | 13.19 | 66 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5811-00489 | 5811 | 2018-08-30 12:54 | Section 3 | Material | Not on List | Not on List | 2 | Packs | 138.24 | 276.48 | Builders Merchants (General) | 2018-09-03 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Can Fuel 5ltr Heavy Duty Green Plastic Long Spout Unleaded (706686) | 5 | Each | 5.82 | 29 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5811-00489 | 5811 | 2018-08-30 12:54 | Section 3 | Material | Not on List | Not on List | 2 | Packs | 138.24 | 276.48 | Builders Merchants (General) | 2018-09-03 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14167-001025 | 14167 | 2019-03-18 08:20 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-03-21 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14171-001025 | 14171 | 2019-03-18 11:25 | Section 2 | Material | Not on List | Not on List | 11 | ea | NULL | 0 | Miscellaneous | 2019-03-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 401 - Safety Barriers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14021-001025 | 14021 | 2019-03-14 09:39 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.8 | 80 | Surveying Consumables | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14021-001025 | 14021 | 2019-03-14 09:39 | Section 4 | Material | NULL | Not on List | 10 | Each | 25 | 250 | Surveying Consumables | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14132-001025 | 14132 | 2019-03-15 14:42 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327.4 | Aggregate | 2019-03-19 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 180 | Each | 2 | 360 | Plastic Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | Not on List | 30 | Each | NULL | 0 | Plastic Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | NULL | Polypipe 100mm Linflex 100m (877398) | 9 | Rolls | 175 | 1575 | Plastic Drainage | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15776-001025 | 15776 | 2019-04-12 11:32 | Section 3 | Material | Not on List | Not on List | 3 | Boxes | NULL | 0 | Miscellaneous | 2019-04-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15635-001025 | 15635 | 2019-04-10 16:43 | Core | Material | Not on List | Not on List | 1 | Number | 295 | 295 | Miscellaneous | 2019-04-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16166-001025 | 16166 | 2019-04-18 12:11 | Core | Material | Not on List | Not on List | 200 | Number | NULL | 0 | Surveying Consumables | 2019-04-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 900 | M | 1 | 900 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 22 | M | 1 | 22 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 18 | M | 1 | 18 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 30 | ea | 1 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 250 | M | 1 | 250 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 2 | M | 1 | 2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16167-001025 | 16167 | 2019-04-18 13:36 | Section 4 | Material | Not on List | Not on List | 2 | M | 1 | 2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-09 | RVP 406 - 1339624 - Bar Hill Left Site (J29 A14 Eastbound) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16127-001025 | 16127 | 2019-04-18 09:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 55.46 | 554.6 | Small Tools (Consumables) | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16127-001025 | 16127 | 2019-04-18 09:29 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | 113.57 | 1135.7 | Small Tools (Consumables) | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15876-001025 | 15876 | 2019-04-15 15:46 | Section 2 | Material | Not on List | Not on List | 23.123 | t | NULL | 0 | NULL | 2019-04-22 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | GN2B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16173-001025 | 16173 | 2019-04-18 14:23 | Core | Material | Not on List | Not on List | 1 | number | 2000 | 2000 | Miscellaneous | 2019-04-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6185-00631 | 6185 | 2018-09-07 10:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Packs | 9 | 90 | Small Tools (Consumables) | 2018-09-10 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6179-00630 | 6179 | 2018-09-07 09:57 | Section 4 | Material | Not on List | Not on List | 15 | number | 7.98 | 119.7 | Small Tools (Consumables) | 2018-09-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16177-001025 | 16177 | 2019-04-18 14:13 | Core | Material | Not on List | Not on List | 1 | NULL | 5827.5 | 5828 | Miscellaneous | 2019-04-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5489-00305 | 5489 | 2018-08-22 09:10 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 19.59 | 39.18 | Miscellaneous | 2018-08-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16180-001025 | 16180 | 2019-04-18 14:45 | Core | Material | Not on List | Not on List | 1 | number | 5827.5 | 5828 | Miscellaneous | 2019-04-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16192-001025 | 16192 | 2019-04-23 07:09 | Section 2 | Material | Not on List | Not on List | 20 | Rolls | NULL | 0 | Concrete Accessories | 2019-04-26 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16206-001025 | 16206 | 2019-04-23 08:49 | Section 4 | Material | Not on List | Not on List | 1000 | m | 1 | 1000 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-04-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16214-001025 | 16214 | 2019-04-23 10:15 | Section 2 | Material | Bagged | Not on List | 285 | No. | NULL | 0 | Miscellaneous | 2019-06-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16214-001025 | 16214 | 2019-04-23 10:15 | Section 2 | Material | Not on List | Not on List | 1 | No. | NULL | 0 | Miscellaneous | 2019-06-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16227-001025 | 16227 | 2019-04-23 11:54 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196 | Aggregate | 2019-04-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16227-001025 | 16227 | 2019-04-23 11:54 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142 | Aggregate | 2019-04-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5489-00305 | 5489 | 2018-08-22 09:10 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 100.11 | 200.22 | Miscellaneous | 2018-08-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16227-001025 | 16227 | 2019-04-23 11:54 | Section 2 | Material | Bagged | Not on List | 10 | NULL | NULL | 0 | Builders Merchants (General) | 2019-04-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16065-001025 | 16065 | 2019-04-17 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 350 | 350 | Surveying Consumables | 2019-04-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16073-001025 | 16073 | 2019-04-17 16:17 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2019-04-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16073-001025 | 16073 | 2019-04-17 16:17 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-04-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16061-001025 | 16061 | 2019-04-17 12:42 | Section 3 | Material | Not on List | Not on List | 500 | No | 0.26 | 130 | Builders Merchants (General) | 2019-04-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16061-001025 | 16061 | 2019-04-17 12:42 | Section 3 | Material | Not on List | Not on List | 600 | No | 0.37 | 222 | Builders Merchants (General) | 2019-04-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16039-001025 | 16039 | 2019-04-17 10:37 | Section 4 | Material | Not on List | Not on List | 3 | Each | 75 | 225 | Surveying Consumables | 2019-04-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15485-001025 | 15485 | 2019-04-08 17:29 | Section 4 | Material | Not on List | Not on List | 5 | Each | 18 | 90 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15485-001025 | 15485 | 2019-04-08 17:29 | Section 4 | Material | Not on List | Not on List | 2 | Each | 95 | 190 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6267-00653 | 6267 | 2018-09-10 13:49 | Section 4 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Surveying Consumables | 2018-09-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16184-001025 | 16184 | 2019-04-18 16:40 | Section 3 | Material | Not on List | Not on List | 2 | No. | 80 | 160 | Builders Merchants (General) | 2019-04-23 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 609 - Ground water lowering | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 100 | Each | 11.34 | 1134 | Plastic Drainage | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 300 | Each | 1.98 | 594 | Plastic Drainage | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 600 | Each | 0.91 | 546 | Plastic Drainage | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 50 | Each | 24.99 | 1249.5 | Plastic Drainage | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Coupler (878066) | 150 | Each | 3.65 | 547.5 | Plastic Drainage | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 225mm Ridgidrain Seal (346386) | 300 | Each | 2 | 600 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 100 | Each | 37.6 | 3760 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Coupler (878109) | 150 | Each | 7.06 | 1059 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | NULL | Polypipe 300mm Ridgidrain Seal (346388) | 300 | Each | 2.97 | 891 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 10 | Each | 130.26 | 1302.6 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 30 | Each | 18.84 | 565.2 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 60 | Each | 9.76 | 585.6 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 20 | Each | 125.94 | 2518.8 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 60 | Each | 18.87 | 1132.2 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16086-001025 | 16086 | 2019-04-17 16:26 | Section 4 | Material | Not on List | Not on List | 120 | Each | 10.84 | 1300.8 | Plastic Drainage | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16266-001025 | 16266 | 2019-04-23 17:27 | Section 5 | Material | Twinwall | Not on List | 2 | No | NULL | 0 | Plastic Drainage | 2019-04-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16266-001025 | 16266 | 2019-04-23 17:27 | Section 5 | Material | Twinwall | Not on List | 2 | No | NULL | 0 | Plastic Drainage | 2019-04-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15643-001025 | 15643 | 2019-04-10 16:23 | Section 4 | Material | Not on List | Not on List | 28 | Each | 150 | 4200 | Miscellaneous | 2019-04-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2702 - Works by the Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14719-001025 | 14719 | 2019-03-27 07:18 | Section 4 | Material | Signage | Directional Signage - 2300 x 750 | 1 | Each | 93.16 | 93.16 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14719-001025 | 14719 | 2019-03-27 07:18 | Section 4 | Material | Signage | Directional Signage - 460 x 190 | 1 | Each | 7.9 | 7.9 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14719-001025 | 14719 | 2019-03-27 07:18 | Section 4 | Material | Signage | Directional Signage - 460 x 190 | 1 | Each | 5.61 | 5.61 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16142-001025 | 16142 | 2019-04-18 11:46 | Section 4 | Material | Not on List | Not on List | 250 | Each | 0.34 | 85 | Concrete Accessories | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16142-001025 | 16142 | 2019-04-18 11:46 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.32 | 132 | Concrete Accessories | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16142-001025 | 16142 | 2019-04-18 11:46 | Section 4 | Material | Not on List | Not on List | 5 | Each | 46.5 | 232.5 | Concrete Accessories | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16142-001025 | 16142 | 2019-04-18 11:46 | Section 4 | Material | Not on List | Not on List | 100 | Each | 1.03 | 103 | Concrete Accessories | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16142-001025 | 16142 | 2019-04-18 11:46 | Section 4 | Material | Not on List | Not on List | 100 | Each | 0.88 | 88 | Concrete Accessories | 2019-04-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16293-001025 | 16293 | 2019-04-24 10:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 921.6 | 922 | PPE | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-6307-00657 | 6307 | 2018-09-11 09:04 | Section 4 | Material | Not on List | Not on List | 48 | NULL | NULL | 0 | Fixings and Fasteners | 2018-09-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16175-001025 | 16175 | 2019-04-18 14:33 | Core | Material | Not on List | Not on List | 5 | number | 800 | 4000 | Office Supplies | 2019-04-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16235-001025 | 16235 | 2019-04-23 13:05 | Section 2 | Material | NULL | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 40 | Each | 120.62 | 4824.8 | Plastic Drainage | 2019-04-29 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16308-001025 | 16308 | 2019-04-24 12:30 | Section 3 | Material | Not on List | Not on List | 300 | lm | NULL | 0 | Miscellaneous | 2019-04-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | BN06 - ECML Bridge | 2010 - Waterproofing for concrete structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16139-001025 | 16139 | 2019-04-18 11:15 | Core | Material | Not on List | Not on List | 1 | Each | 1737.5 | 1737.5 | Training | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16264-001025 | 16264 | 2019-04-23 17:36 | Section 2 | Material | NULL | Not on List | 16 | Number | NULL | 0 | Concrete Drainage | 2019-04-26 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16323-001025 | 16323 | 2019-04-24 14:37 | Core | Material | Not on List | Not on List | 1 | each | 945 | 945 | Laboratory Equipment / Certification | 2019-04-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16037-001025 | 16037 | 2019-04-17 10:26 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2002.65 | 2002.65 | Surveying Consumables | 2019-04-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 150 | Each | 23.14 | 3471 | Plastic Drainage | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 85 | Each | 34.82 | 2960 | Plastic Drainage | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Twinwall | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 50 | Each | 120.62 | 6031 | Plastic Drainage | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 1 | Price Per Thousand | 345 | 345 | Blocks and Bricks | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Bagged | Sharp Sand Bulk Bag (938208) | 1 | Each | 32.74 | 33 | Builders Merchants (General) | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Bagged | OP Cement; 25kg bag (767201) | 50 | Each | 2.9 | 145 | Builders Merchants (General) | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Laboratory Equipment / Certification | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Laboratory Equipment / Certification | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Laboratory Equipment / Certification | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Laboratory Equipment / Certification | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Laboratory Equipment / Certification | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16332-001025 | 16332 | 2019-04-24 08:01 | Section 6 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 40 | Each | 10.5 | 420 | Plastic Drainage | 2019-04-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-15665-001025 | 15665 | 2019-04-11 09:52 | Section 4 | Material | Not on List | Not on List | 6 | NULL | 17.87 | 107.22 | Miscellaneous | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16334-001025 | 16334 | 2019-04-24 15:42 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16338-001025 | 16338 | 2019-04-24 16:32 | Section 3 | Material | Aggregate | A10 Pipe Bed | 400 | Tonnes | 16.5 | 6600 | Aggregate | 2019-04-30 | Gate F - 1339644 - BN11 Access off A1198 | SC3A - Roadworks | 606 - Import | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16207-001025 | 16207 | 2019-04-23 09:10 | Section 4 | Material | Not on List | Not on List | 150 | ea | 7.5 | 1125 | Miscellaneous | 2019-04-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16354-001025 | 16354 | 2019-04-24 17:32 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-26 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-16295-001025 | 16295 | 2019-04-24 10:37 | Section 4 | Material | Waste Management | Dry Mixed Recycling - Skip 8 cubic yard | 2 | Each | 75 | 150 | Waste (General) | 2019-04-25 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 1783 | ea | 17.12 | 30525 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 25 | ea | 150.47 | 3762 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 13 | ea | 29.09 | 378 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 239 | ea | 22.61 | 5404 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 2 | ea | 35.11 | 70 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 1 | ea | 16712 | 16712 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 1319 | ea | 29.46 | 38858 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 10 | ea | 57.68 | 577 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 3 | ea | 32.03 | 96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 3329 | ea | 23.84 | 79363 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 49 | ea | 355.81 | 17435 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 37 | ea | 279.41 | 10338 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 24 | ea | 1260432.03 | 30250369 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 1 | ea | 5945 | 5945 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 37 | ea | 13.08 | 484 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16366-001025 | 16366 | 2019-04-25 07:07 | Section 4 | Material | Not on List | Not on List | 37 | ea | 13.08 | 484 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-16317-001025 | 16317 | 2019-04-24 13:48 | Section 2 | Material | NULL | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2019-04-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-16050-001025 | 16050 | 2019-04-17 13:18 | Section 3 | Material | Not on List | Not on List | 1 | person | 650 | 650 | Miscellaneous | 2019-04-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 5 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 2 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 14 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 46 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 58 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 5 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 62 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 124 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 8 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 38 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 44 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-9685-001025 | 9685 | 2018-11-27 13:52 | Section 4 | Material | Not on List | Not on List | 230 | Each | 1.04 | 239.2 | Concrete Accessories | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9685-001025 | 9685 | 2018-11-27 13:52 | Section 4 | Material | Not on List | Not on List | 400 | Each | 0.12 | 48 | Concrete Accessories | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9685-001025 | 9685 | 2018-11-27 13:52 | Section 4 | Material | Not on List | Not on List | 15 | Coil | 46.5 | 697.5 | Concrete Accessories | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9524-001025 | 9524 | 2018-11-23 08:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 13.19 | 105.52 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9524-001025 | 9524 | 2018-11-23 08:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | 25.13 | 376.95 | Miscellaneous | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9524-001025 | 9524 | 2018-11-23 08:37 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 25.58 | 204.64 | Small Tools (Consumables) | 2018-11-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9675-001025 | 9675 | 2018-11-27 12:05 | Section 4 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 3.56 | 199.36 | Builders Merchants (General) | 2018-11-29 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9682-001025 | 9682 | 2018-11-27 13:17 | Section 4 | Material | Not on List | Not on List | 1 | Each | 229 | 229 | Damage Charges | 2018-11-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1601 - Piling and attendances | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9718-001025 | 9718 | 2018-11-28 12:04 | Section 4 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Not Sure | 2018-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9720-001025 | 9720 | 2018-11-28 12:06 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Blocks and Bricks | 2018-12-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9723-001025 | 9723 | 2018-11-28 13:28 | Section 4 | Material | Not on List | Not on List | 3 | number | NULL | 0 | Not Sure | 2018-12-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9657-001025 | 9657 | 2018-11-27 07:19 | Section 4 | Material | Not on List | Not on List | 1 | Each | 326.03 | 326.03 | Not Sure | 2018-11-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | Combined Drainage | Not on List | 50 | M | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9485-001025 | 9485 | 2018-11-22 14:15 | Section 4 | Material | Not on List | Not on List | 3 | Each | 650 | 1950 | Miscellaneous | 2018-11-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9628-001025 | 9628 | 2018-11-26 15:35 | Section 4 | Material | Not on List | Not on List | 1 | Each | 3457.31 | 3457.31 | Miscellaneous | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5034-0020 | 5034 | 2018-08-14 09:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 920 | Each | 1.07 | 0 | Surveying Consumables | 2018-08-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5378-00250 | 5378 | 2018-08-20 16:43 | Section 3 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-08-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN31 - Culvert - 199 | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9726-001025 | 9726 | 2018-11-28 15:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 2353.08 | 2353.08 | Small Tools (Consumables) | 2018-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 1 | U | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 2 | U | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 1 | U | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 9 | M | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 33 | M | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5378-00250 | 5378 | 2018-08-20 16:43 | Section 3 | Material | Not on List | Not on List | 6 | boxes | NULL | 0 | Fixings and Fasteners | 2018-08-23 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN06 - ECML Bridge | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9776-001025 | 9776 | 2018-11-29 14:19 | Section 4 | Material | Kerbs | Not on List | 17 | M | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9428-001025 | 9428 | 2018-11-21 15:03 | Section 4 | Material | Not on List | Not on List | 1 | Each | 415.92 | 415.92 | Damage Charges | 2018-11-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9736-001025 | 9736 | 2018-11-28 16:24 | Section 4 | Material | Not on List | Not on List | 1 | Each | 506 | 506 | Electrical | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 300 | No | 29.28 | 8784 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 10 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 10 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 50 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 2 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 7 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Not on List | Not on List | 70 | No | NULL | 0 | Not Sure | 2018-12-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5380-00252 | 5380 | 2018-08-20 16:43 | Section 4 | Material | Not on List | Not on List | 0.103 | Tonnes | 538 | 55.41 | Rebar and Mesh | 2018-08-23 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | CL4B - Structures (Culverts) 4B | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Kerbs | Not on List | 6 | No | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | Combined Drainage | Not on List | 1 | U | 40.95 | 41 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | Combined Drainage | Not on List | 1 | U | 633.75 | 634 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | Combined Drainage | Not on List | 1 | U | 56.55 | 57 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | Combined Drainage | Not on List | 1 | U | 53.62 | 54 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | BN24 - Girton Interchange Bridge C | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9750-001025 | 9750 | 2018-11-29 07:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 199 | 199 | Damage Charges | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9737-001025 | 9737 | 2018-11-28 16:41 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4500 | 4500 | Damage Charges | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9807-001025 | 9807 | 2018-11-30 08:29 | Section 4 | Material | Concrete Drainage | Not on List | 10 | Packs | NULL | 0 | Concrete Drainage | 2018-12-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-9531 | 9531 | 2018-11-23 10:21 | Section 3 | Material | Not on List | Not on List | 2 | each | 1200 | 2400 | Miscellaneous | 2018-11-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9758-001025 | 9758 | 2018-11-29 08:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 10.76 | 64.56 | Small Tools (Consumables) | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 20 | no | 22.62 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9758-001025 | 9758 | 2018-11-29 08:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 37.08 | 222.48 | Small Tools (Consumables) | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9758-001025 | 9758 | 2018-11-29 08:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 10.76 | 64.56 | Small Tools (Consumables) | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 370mm X 7.6mm Pack Of 100 Spartan (230065) | 25 | Each | 3.88 | 97 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Microwave Oven Manual 700watt (230937) | 2 | Each | 38.22 | 76 | Miscellaneous | 2018-12-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Kettle Jug Electric Cordless White C/W Gauge 1.7ltrs 2.2kw (230998) | 4 | Each | 10.48 | 42 | Miscellaneous | 2018-12-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Torch Head Varta Indestructible 1watt Led 3aaa (764082) | 2 | Each | 15 | 30 | Miscellaneous | 2018-11-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9765-001025 | 9765 | 2018-11-29 08:48 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1342.96 | 1342.96 | Janitorial | 2018-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | 24.84 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9587-001025 | 9587 | 2018-11-23 17:49 | Section 3 | Material | Not on List | Not on List | 60 | Each | 42.5 | 2550 | Miscellaneous | 2018-11-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9718-001025 | 9718 | 2018-11-28 12:04 | Section 4 | Material | Not on List | Not on List | 200 | Each | 10 | 2000 | Fixings and Fasteners | 2018-12-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9723-001025 | 9723 | 2018-11-28 13:28 | Section 4 | Material | Not on List | Not on List | 3 | Each | 336.95 | 1010.85 | Plastic Drainage | 2018-12-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9833-001025 | 9833 | 2018-11-30 14:00 | Section 3 | Material | Signage | Not on List | 80 | number | NULL | 0 | Miscellaneous | 2018-12-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9833-001025 | 9833 | 2018-11-30 14:00 | Section 3 | Material | Signage | Not on List | 80 | number | NULL | 0 | Miscellaneous | 2018-12-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Cable Tie Plastic Black 370mm X 7.6mm Pack Of 100 Spartan (230065) | 25 | Each | 3.88 | 97 | Miscellaneous | 2018-12-03 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Microwave Oven Manual 700watt (230937) | 2 | Each | 38.22 | 76.44 | Miscellaneous | 2018-12-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Kettle Jug Electric Cordless White C/W Gauge 1.7ltrs 2.2kw (230998) | 4 | Each | 10.48 | 41.92 | Miscellaneous | 2018-12-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9811-001025 | 9811 | 2018-11-30 09:57 | Section 3 | Material | PPE, Small Tools and Consumables | Torch Head Varta Indestructible 1watt Led 3aaa (764082) | 2 | Each | 15 | 30 | Miscellaneous | 2018-11-04 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | 21.33 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 110 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 300 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 60 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | 6.1 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 120 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 45 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 45 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 32 | no | 6.26 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9756-001025 | 9756 | 2018-11-29 07:24 | Section 4 | Material | Not on List | Not on List | 150 | no | 20.5 | 3075 | Miscellaneous | 2018-12-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9756-001025 | 9756 | 2018-11-29 07:24 | Section 4 | Material | Not on List | Not on List | 110 | no | 9.58 | 1053.8 | Miscellaneous | 2018-12-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9819-001025 | 9819 | 2018-11-30 11:14 | Section 4 | Material | Aggregate | Not on List | 4 | Each | 52.5 | 210 | Builders Merchants (General) | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9819-001025 | 9819 | 2018-11-30 11:14 | Section 4 | Material | Aggregate | Not on List | 6 | Each | 32.74 | 196.44 | Builders Merchants (General) | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9819-001025 | 9819 | 2018-11-30 11:14 | Section 4 | Material | Aggregate | Not on List | 56 | Bag | 2.9 | 162.4 | Builders Merchants (General) | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9720-001025 | 9720 | 2018-11-28 12:06 | Section 4 | Material | Not on List | Not on List | 60 | Ea | 12 | 720 | Blocks and Bricks | 2018-12-04 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | NULL | Not on List | 1 | Each | 40.95 | 40.95 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | NULL | Not on List | 1 | Each | 633.75 | 633.75 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | NULL | Not on List | 1 | Each | 56.55 | 56.55 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | 3.35 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | NULL | Not on List | 1 | Each | 53.62 | 53.62 | Concrete Drainage | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9779-001025 | 9779 | 2018-11-29 15:13 | Section 4 | Material | NULL | Not on List | 100 | Each | 35 | 3500 | NULL | NULL | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 100 | Each | 35 | 3500 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 1 | Each | 45 | 45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 1 | Each | 58 | 58 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 1 | Each | 61 | 61 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 8 | Each | 7.5 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 14 | Each | 14.95 | 209.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9743-001025 | 9743 | 2018-11-28 16:54 | Section 4 | Material | NULL | Not on List | 1 | Each | 38 | 38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-05 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ9885 | 9885 | 2018-12-03 14:19 | Section 4 | Material | Not on List | Not on List | 86 | t | NULL | 0 | Reinforcement | 2019-01-08 | RVP 404 - 1339622 - Robin's Lane A14 Eastbound | BN19 - Robins Lane Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | 2.77 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9691-001025 | 9691 | 2018-11-27 15:36 | Section 4 | Material | Not on List | Not on List | 1 | Each | 4449.2 | 4449.2 | Plastic Drainage | 2019-01-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9691-001025 | 9691 | 2018-11-27 15:36 | Section 4 | Material | NULL | Not on List | 1 | Each | 140 | 140 | NULL | 2019-01-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9677-001025 | 9677 | 2018-11-27 12:35 | Section 4 | Material | Aggregate | Not on List | 200 | NULL | NULL | 0 | Aggregate | 2018-11-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9672-001025 | 9672 | 2018-11-27 11:27 | Section 4 | Material | Not on List | Not on List | 5 | Each | 11.5 | 57.5 | Surveying Consumables | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9672-001025 | 9672 | 2018-11-27 11:27 | Section 4 | Material | Not on List | Not on List | 3 | Each | 20 | 60 | Surveying Consumables | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9672-001025 | 9672 | 2018-11-27 11:27 | Section 4 | Material | Not on List | Not on List | 2 | Each | 28 | 56 | Surveying Consumables | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9672-001025 | 9672 | 2018-11-27 11:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 49 | 49 | Surveying Consumables | 2018-11-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 300 | No | 29.28 | 8784 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 10 | No | 29.01 | 290.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 10 | No | 29.01 | 290.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | 5.6 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 50 | No | 34.1 | 1705 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 2 | No | 46.35 | 92.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 7 | No | 243.87 | 1707.09 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | Not on List | Not on List | 70 | No | 7.5 | 525 | Not Sure | 2018-12-10 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9778-001025 | 9778 | 2018-11-29 13:43 | Section 3 | Material | NULL | Not on List | 6 | No | 4.67 | 28.02 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | NULL | 0 | Not Sure | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11760-001025 | 11760 | 2019-01-31 17:16 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1399.48 | Each | 1 | 1399 | Small Tools (Consumables) | 2019-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11745-001025 | 11745 | 2019-01-31 15:36 | Section 4 | Material | NULL | Not on List | 8 | EA | 77.85 | 622.8 | Concrete Drainage | 2019-02-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11745-001025 | 11745 | 2019-01-31 15:36 | Section 4 | Material | NULL | Not on List | 1 | Each | 200 | 200 | Concrete Drainage | 2019-02-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11745-001025 | 11745 | 2019-01-31 15:36 | Section 4 | Material | NULL | Not on List | 1 | Each | 240 | 240 | Concrete Drainage | 2019-02-06 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 2 | No | 121.59 | 243.18 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 1 | No | 113.25 | 113.25 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 2 | No | 164.37 | 328.74 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 14 | No | 83.41 | 1167.74 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 3 | No | 44.41 | 133.23 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 6 | No | 62.54 | 375.24 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 28 | No | 94.82 | 2654.96 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 4 | No | 103.11 | 412.44 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 2 | No | 111.58 | 223.16 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11678-001025 | 11678 | 2019-01-30 15:17 | Section 3 | Material | NULL | Not on List | 4 | No | 182.18 | 728.72 | Ductile Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11744-001025 | 11744 | 2019-01-31 15:54 | Section 3 | Material | NULL | Not on List | 2 | No | 39.7 | 79.4 | Ductile Drainage | 2019-02-06 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11842-001025 | 11842 | 2019-02-04 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-02-08 | Gate C - 1339702 - BN06 (East Coast Railway) Via Logistics Yard Access | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11743-001 | 11743 | 2019-01-31 15:53 | Section 3 | Material | Aggregate | A10 Pipe Bed | 300 | Tonnes | 21.1 | 6330 | Aggregate | 2019-02-01 | RVP 419 - 1340880 - A14 Westbound (West of Junction 28) | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 27 | No. | 34.82 | 940.14 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 50 | No. | 13.75 | 687.5 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11727-001025 | 11727 | 2019-01-31 13:26 | Section 3 | Material | Not on List | Not on List | 50 | No. | 48.86 | 2443 | Plastic Drainage | 2019-02-05 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11854-001025 | 11854 | 2019-02-04 11:49 | Section 4 | Material | Not on List | Not on List | 180 | ROLLS | NULL | 0 | Concrete Accessories | 2019-02-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11877-001025 | 11877 | 2019-02-04 16:24 | Section 4 | Material | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 3 | Price Per Thousand | 345 | 1035 | Blocks and Bricks | 2019-02-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - Buyers Group
MREQ-11877-001025 | 11877 | 2019-02-04 16:24 | Section 4 | Material | Not on List | Not on List | 500 | no | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - Buyers Group
MREQ-11877-001025 | 11877 | 2019-02-04 16:24 | Section 4 | Material | Kerbs | Not on List | 250 | no | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-18 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - Buyers Group
MREQ-11882-001025 | 11882 | 2019-02-04 16:38 | Section 2 | Material | Aggregate | 6G | 240 | Tonnes | 22 | 5280 | Aggregate | 2019-02-12 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Perf (346341) | 14 | Each | 24.82 | 347 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Perf (346341) | 14 | Each | 24.82 | 347 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 3 | Each | 34.82 | 104 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 400mm Ridgidrain 6m Unperf + Coupler (346364) | 2 | Each | 120.62 | 241 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 14 | Each | 116.62 | 1633 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 100 | no | NULL | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Not on List | 9 | NULL | NULL | 0 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Not on List | 2 | NULL | NULL | 0 | Plastic Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 10 | Each | 47.04 | 470 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 4 | Each | 59.17 | 237 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 1000 D/S (991897) | 8 | Each | 67.9 | 543 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1050 x 250 D/S (912958) | 2 | Each | 35.52 | 71 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 3 | Each | 81.96 | 246 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 1 | Each | 53.01 | 53 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 7 | Each | 3.38 | 24 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 2 | Each | 6.54 | 13 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Not on List | 5 | NULL | NULL | 0 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11889-001025 | 11889 | 2019-02-04 16:46 | Section 1 | Material | Twinwall | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-02-13 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | SEC1 - Roadworks | 501 - Drains | Commercial Approval | Yes - Approve | NULL | Req - Buyers Group
MREQ-11903-001025 | 11903 | 2019-02-05 07:29 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11905-001025 | 11905 | 2019-02-05 07:41 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11907-001025 | 11907 | 2019-02-05 07:50 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11908-001025 | 11908 | 2019-02-05 07:55 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11910-001025 | 11910 | 2019-02-05 07:59 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11916-001025 | 11916 | 2019-02-05 09:10 | Section 2 | Material | Not on List | Not on List | 1 | each | 3829.38 | 3829 | Not Sure | 2019-02-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11919-001025 | 11919 | 2019-02-05 09:28 | Section 5 | Material | Not on List | Not on List | 1 | each | 243.38 | 243 | Not Sure | 2019-02-05 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11920 | 11920 | 2019-04-11 11:35 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-02-07 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Request - Ops Pass Back | No - Pass Back | NULL | NULL
MREQ-11921-001025 | 11921 | 2019-02-05 09:38 | Section 4 | Material | Not on List | Not on List | 1 | each | 1767.13 | 1767 | Miscellaneous | 2019-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11922-001025 | 11922 | 2019-02-05 09:50 | Section 3 | Material | Not on List | Not on List | 1 | each | 3760.63 | 3761 | Miscellaneous | 2019-02-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11923-001025 | 11923 | 2019-02-05 10:18 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11812 | 11812 | 2019-02-01 13:29 | Section 4 | Material | Not on List | Not on List | 25 | rolls | 9.62 | 240.5 | Geotextiles | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-11812 | 11812 | 2019-02-01 13:29 | Section 4 | Material | Not on List | Not on List | 10 | rolls | 16.18 | 161.8 | Geotextiles | 2019-03-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-11812 | 11812 | 2019-02-01 13:29 | Section 4 | Material | NULL | Not on List | 1 | Each | 260 | 260 | Geotextiles | 2019-02-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | Ducting | Not on List | 2300 | metres | NULL | 0 | Electrical | 2019-02-08 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | Ducting | Polypipe 94mm Ridgiduct Coupler (877674) | 400 | Number | 2.6 | 1040 | Electrical | 2019-02-08 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | Ducting | Not on List | 800 | Number | NULL | 0 | Electrical | 2019-02-08 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | Ducting | Not on List | 400 | Number | NULL | 0 | Electrical | 2019-02-08 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | Ducting | Draw Cord 450m (537046) | 6 | Each | 25 | 150 | Electrical | 2019-02-08 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11926-001025 | 11926 | 2019-02-05 10:39 | Section 2 | Material | Not on List | Not on List | 1 | each | 56 | 56 | Laboratory Equipment / Certification | 2019-02-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11927-001025 | 11927 | 2019-02-05 10:49 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11927-001025 | 11927 | 2019-02-05 10:49 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Accessories | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11929-001025 | 11929 | 2019-02-05 11:01 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2019-02-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11930 | 11930 | NULL | NULL | NULL | Not on List | Not on List | 15 | ea | 330 | 4950 | Not Sure | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Buyer - Closed | NULL | NULL | NULL
MREQ-11930 | 11930 | NULL | NULL | NULL | Not on List | Not on List | 1 | ea | 330 | 330 | Not Sure | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 3030 - Special Ecological Measures | Buyer - Closed | NULL | NULL | NULL
MREQ-11933-001025 | 11933 | 2019-02-05 11:54 | Section 2 | Material | Timber | Not on List | 6 | packs of 25 normally | 0 | 0 | Timber Products | 2019-02-08 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11933-001025 | 11933 | 2019-02-05 11:54 | Section 2 | Material | Timber | Not on List | 4 | packs of 25 normally | 0 | 0 | Timber Products | 2019-02-08 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11944-001025 | 11944 | 2019-02-05 15:29 | Core | Material | Not on List | Not on List | 20000 | each | NULL | 0 | Office Supplies | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11947-001025 | 11947 | 2019-02-05 15:41 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Office Supplies | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11964-001025 | 11964 | 2019-02-05 17:05 | Section 2 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Fixings and Fasteners | 2019-02-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11968-001025 | 11968 | 2019-02-05 17:47 | Section 4 | Material | Not on List | Not on List | 500 | NULL | NULL | 0 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11982-001025 | 11982 | 2019-02-06 08:03 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Operations Rejected | No - Reject | NULL | NULL
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 100 | Meters | 4.59 | 459 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 40 | Meters | 6 | 240 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 1 | Each | 11.94 | 12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 200 | Meter | 3.52 | 704 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 20 | Meter | 5.43 | 109 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 3 | Each | 7.68 | 23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 3 | Each | 7.68 | 23 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 600 | Meter | 1.5 | 900 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | Kerbs | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11995-001025 | 11995 | 2019-02-06 11:20 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 28 | 28 | Miscellaneous | 2019-02-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11996 | 11996 | NULL | NULL | NULL | Not on List | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | NULL | NULL | NULL
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 220 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 200 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 30 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 4 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 4 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 4 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 4 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 1 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 1 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11999-001025 | 11999 | 2019-02-06 11:41 | Section 3 | Material | Kerbs | Not on List | 1 | No | 0 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-13 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12002-001025 | 12002 | 2019-02-06 12:37 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-08 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Commercial - Rejected | Yes - Approve | No - Reject | NULL
MREQ-12004 | 12004 | 2019-01-31 13:58 | Core | Material | Not on List | Not on List | 10 | Each | NULL | 0 | Electrical | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12006-001025 | 12006 | 2019-02-06 14:06 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Drainage | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12006-001025 | 12006 | 2019-02-06 14:06 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Drainage | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12007-001025 | 12007 | 2019-02-06 14:13 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2019-02-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12008-001025 | 12008 | 2019-02-06 14:18 | Section 4 | Material | Not on List | Not on List | 1 | Each | 440.75 | 441 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12009-001025 | 12009 | 2019-02-06 14:48 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-08 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11982-001025 | 11986 | 2019-02-06 09:02 | Section 2 | Material | Not on List | Not on List | 20 | Roll | 46.5 | 930 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | Bagged | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196 | Concrete Drainage | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142 | Concrete Drainage | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | Bagged | Not on List | 20 | Unit | NULL | 0 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | Bagged | Not on List | 40 | Tubs | NULL | 0 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12022-001025 | 12022 | 2019-02-06 17:10 | Section 2 | Material | Aggregate | Type 1 | 9400 | Tonnes | 16 | 150400 | Aggregate | 2019-02-06 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | NULL | Req - Buyers Group
MREQ-12031-001025 | 12031 | 2019-02-07 06:55 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12033-001025 | 12033 | 2019-02-07 07:25 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-02-08 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | NULL | Req - Buyers Group
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 12 | Each | 85.24 | 1022.88 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 8 | Each | 55.13 | 441.04 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 2 | Each | 126.11 | 252.22 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 10 | Each | 149.45 | 1494.5 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 2 | Each | 121.59 | 243.18 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 2 | Each | 109.94 | 219.88 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 12 | Each | 61.54 | 738.48 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 3 | Each | 106.93 | 320.79 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 3 | Each | 149.8 | 449.4 | Concrete Drainage | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 55 | Each | 31.37 | 1725.35 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 55 | Each | 31.37 | 1725.35 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28160-001025 | 28160 | 2020-01-14 15:14 | Section 4 | Material | Not on List | Not on List | 22 | Each | 86.24 | 1897.28 | Concrete Drainage | 2020-01-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28256-001025 | 28256 | 2020-01-17 07:23 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-01-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28259-001025 | 28259 | 2020-01-17 07:44 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-01-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 6 | Each | 24.45 | 146.7 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28038-001025 | 28038 | 2020-01-10 13:06 | Section 6 | Material | Not on List | Not on List | 1 | No | 115 | 115 | Builders Merchants (General) | 2020-01-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28266-001025 | 28266 | 2020-01-17 09:35 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 621.12 | 621 | Damage Charges | 2020-01-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 602 - Excavation (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28090-001025 | 28090 | 2020-01-13 13:37 | Section 6 | Material | Aggregate | A20 Pipe Bed | 300 | Tonnes | 4 | 1200 | Aggregate | 2020-01-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 32 | Each | 15.19 | 486.08 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27155-001025 | 27155 | 2019-11-29 14:22 | Section 3 | Material | Signage | IFE Signs - 540 | 6 | Each | 32 | 192 | Small Tools (Consumables) | 2019-12-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 1201 - Traffic Signs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28319-001025 | 28319 | 2020-01-20 09:45 | Section 4 | Material | Not on List | Not on List | 650 | NULL | NULL | 0 | Fixings and Fasteners | 2020-01-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27912-001025 | 27912 | 2020-01-07 15:33 | Section 3 | Material | Not on List | Not on List | 7 | no. | 418.81 | 2931.67 | Miscellaneous | 2020-01-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-26353-001025 | 26353 | 2019-11-08 13:28 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 18 | Each | 120.62 | 2171.16 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28338-001025 | 28338 | 2020-01-20 16:24 | Section 6 | Material | Not on List | Not on List | 130 | Number | NULL | 0 | Fixings and Fasteners | 2020-01-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16715-001025 | 16715 | 2019-05-01 10:35 | Core | Material | Not on List | Not on List | 1 | NULL | 1440 | 1440 | Miscellaneous | 2019-05-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28353-001025 | 28353 | 2020-01-21 07:44 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (General) | 2020-01-21 | RVP 417 - 1339631 - Girton Compound Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 201 - Site Clearance | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28274-001025 | 28274 | 2020-01-17 11:57 | Section 4 | Material | NULL | NULL | 300 | Each | 35.58 | 10674 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28274-001025 | 28274 | 2020-01-17 11:57 | Section 4 | Material | NULL | NULL | 10 | Each | 38.85 | 388.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28274-001025 | 28274 | 2020-01-17 11:57 | Section 4 | Material | NULL | NULL | 20 | Each | 41.1 | 822 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28274-001025 | 28274 | 2020-01-17 11:57 | Section 4 | Material | NULL | NULL | 7 | Each | 144.35 | 1010.45 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28274-001025 | 28274 | 2020-01-17 11:57 | Section 4 | Material | NULL | NULL | 200 | Each | 7.1 | 1420 | Builders Merchants (General) | 2020-01-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 22 | Each | 17.45 | 383.9 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-27930-001025 | 27930 | 2020-01-08 08:46 | Section 4 | Material | Hazardous Waste | Oil/water/diesel - 205L drum | 1 | Each | 4203.9 | 4203.9 | Fuel | 2020-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28332-001025 | 28332 | 2020-01-20 15:26 | Section 4 | Material | Not on List | Not on List | 4 | Each | 365 | 1460 | Ductile Drainage | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 44 | Each | 9.04 | 397.76 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 300 | Each | 4.59 | 1377 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 32 | Each | 5.44 | 174.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 32 | Each | 5.44 | 174.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 16 | Each | 5.44 | 87.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 16 | Each | 5.44 | 87.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 1 | Each | 22.5 | 22.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28296-001025 | 28296 | 2020-01-17 15:38 | Section 4 | Material | NULL | NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28381-001025 | 28381 | 2020-01-21 16:29 | Core | Material | Not on List | Not on List | 1 | NULL | 2750 | 2750 | Miscellaneous | 2020-01-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No | 222.75 | 223 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | No | 13.44 | 27 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 68 | Each | 34.82 | 2367.76 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | No | 15.55 | 31 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No | 145.89 | 146 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | Not on List | Not on List | 3 | No | 22 | 66 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | Not on List | Not on List | 1 | No | 30 | 30 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | Not on List | Not on List | 2 | Hr | 35 | 70 | Professional Services | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28373-001025 | 28373 | 2020-01-21 14:43 | Section 2 | Material | Not on List | Not on List | 1 | No | 53.98 | 54 | Small Tools (Consumables) | 2019-11-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28365-001025 | 28365 | 2020-01-21 13:26 | Section 4 | Material | NULL | NULL | 10 | Each | 5.24 | 52.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28365-001025 | 28365 | 2020-01-21 13:26 | Section 4 | Material | NULL | NULL | 6 | Each | 5.24 | 31.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 78 | Each | 6.54 | 510.12 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28404-001025 | 28404 | 2020-01-22 14:10 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-01-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 3020 - Seeding, Turfing and Planting | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28393-001025 | 28393 | 2020-01-22 09:16 | Section 4 | Material | NULL | NULL | 200 | Each | 4.97 | 994 | Builders Merchants (General) | 2020-01-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28409-001025 | 28409 | 2020-01-22 16:31 | Section 4 | Material | Kerbs | Not on List | 8 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28409-001025 | 28409 | 2020-01-22 16:31 | Section 4 | Material | Kerbs | Not on List | 8 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28409-001025 | 28409 | 2020-01-22 16:31 | Section 4 | Material | Kerbs | Not on List | 16 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28423-001025 | 28423 | 2020-01-23 08:15 | Section 4 | Material | Not on List | Not on List | 2 | Pallet | NULL | 0 | Miscellaneous | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28423-001025 | 28423 | 2020-01-23 08:15 | Section 4 | Material | Not on List | Not on List | 2 | Pallet | NULL | 0 | Miscellaneous | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28427-001025 | 28427 | 2020-01-23 08:36 | Section 4 | Material | Not on List | Not on List | 2000 | Number | NULL | 0 | Surveying Consumables | 2020-01-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28427-001025 | 28427 | 2020-01-23 08:36 | Section 4 | Material | Not on List | Not on List | 1000 | Number | NULL | 0 | Surveying Consumables | 2020-01-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 156 | Each | 2.75 | 429 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28427-001025 | 28427 | 2020-01-23 08:36 | Section 4 | Material | Not on List | Not on List | 1000 | Number | NULL | 0 | Surveying Consumables | 2020-01-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28428-001025 | 28428 | 2020-01-23 09:00 | Section 5 | Material | Not on List | Not on List | 1 | No | 3623 | 3623 | Miscellaneous | 2020-01-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-28431-001025 | 28431 | 2020-01-23 09:15 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 12 | Each | 179.84 | 2158.08 | Plastic Drainage | 2020-01-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28431-001025 | 28431 | 2020-01-23 09:15 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain Seal (346400) | 18 | Each | 22.36 | 402.48 | Plastic Drainage | 2020-01-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28431-001025 | 28431 | 2020-01-23 09:15 | Section 2 | Material | Twinwall | Not on List | 6 | ea | 231.57 | 1389.42 | Plastic Drainage | 2020-01-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28377-001025 | 28377 | 2020-01-21 15:07 | Section 4 | Material | NULL | NULL | 10 | Each | 40.16 | 401.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28377-001025 | 28377 | 2020-01-21 15:07 | Section 4 | Material | NULL | NULL | 10 | Each | 6 | 60 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 54 | Each | 23.14 | 1249.56 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28395-001025 | 28395 | 2020-01-22 11:41 | Section 5 | Material | NULL | NULL | 3 | Each | 92.7 | 278.1 | Plastic Drainage | 2020-01-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28453-001025 | 28453 | 2020-01-23 15:54 | Section 4 | Material | Not on List | Not on List | 1 | No | 490.47 | 490 | Professional Services | 2019-10-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28479-001025 | 28479 | 2020-01-24 08:30 | Section 4 | Material | Not on List | Not on List | 200 | no | NULL | 0 | Miscellaneous | 2020-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28445-001025 | 28445 | 2020-01-23 14:31 | Section 5 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28445-001025 | 28445 | 2020-01-23 14:31 | Section 5 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28445-001025 | 28445 | 2020-01-23 14:31 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 4 | Each | 32.74 | 131 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 65 | Each | 3.38 | 219.7 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28484-001025 | 28484 | 2020-01-24 10:04 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | 15.68 | 78 | Small Tools (Consumables) | 2020-01-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28486-001025 | 28486 | 2020-01-24 10:05 | Section 4 | Material | Not on List | Not on List | 1 | No | 555 | 555 | Miscellaneous | 2020-01-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 270 | No | 30.16 | 8143.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 5 | No | 311.01 | 1555.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 5 | No | 58.27 | 291.35 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 14 | bags | 59.26 | 829.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 1 | NULL | 215.85 | 215.85 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | Kerbs | Not on List | 1 | NULL | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 130 | Each | 1.86 | 241.8 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28363-001025 | 28363 | 2020-01-21 11:25 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-01-23 | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28405-001025 | 28405 | 2020-01-22 14:44 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 1210 | 1210 | Miscellaneous | 2020-01-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28234-001025 | 28234 | 2020-01-16 14:57 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28500-001025 | 28500 | 2020-01-24 13:46 | Section 4 | Material | Aggregate | 6G | 500 | Tonnes | 32.9 | 16450 | Aggregate | 2020-01-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28569-001025 | 28569 | 2020-01-28 07:59 | Section 6 | Material | Not on List | Not on List | 420 | Number | NULL | 0 | Fixings and Fasteners | 2020-01-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28569-001025 | 28569 | 2020-01-28 07:59 | Section 6 | Material | Not on List | Not on List | 50 | Number | NULL | 0 | Timber Products | 2020-01-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 12 | Each | 10.5 | 126 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28569-001025 | 28569 | 2020-01-28 07:59 | Section 6 | Material | Not on List | Not on List | 60 | m2 | NULL | 0 | Geotextiles | 2020-01-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28569-001025 | 28569 | 2020-01-28 07:59 | Section 6 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Fixings and Fasteners | 2020-01-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28569-001025 | 28569 | 2020-01-28 07:59 | Section 6 | Material | Not on List | Not on List | 3 | Number | NULL | 0 | Miscellaneous | 2020-01-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 20 | Each | 1.84 | 36.8 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28556-001025 | 28556 | 2020-01-27 16:09 | Section 4 | Material | Not on List | Not on List | 74 | Each | 130.26 | 9639.24 | Plastic Drainage | 2020-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28556-001025 | 28556 | 2020-01-27 16:09 | Section 4 | Material | Not on List | Not on List | 65 | Each | 9.46 | 614.9 | Plastic Drainage | 2020-01-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 1 | No. | 81 | 81 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 5 | No. | 115 | 575 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 20 | packs of 100 Flags | 10.5 | 210 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 15 | packs of 100 Flags | 10.5 | 158 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 20 | packs of 100 Flags | 10.5 | 210 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 40 | Each | 0.85 | 34 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 10 | packs of 100 Flags | 10.5 | 105 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28581-001025 | 28581 | 2020-01-28 10:32 | Core | Material | Not on List | Not on List | 10 | box | 10 | 100 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28293-001025 | 28293 | 2020-01-17 15:13 | Section 5 | Material | Not on List | Not on List | 23 | ea | 15.47 | 355.81 | Builders Merchants (General) | 2020-01-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28583-001025 | 28583 | 2020-01-28 11:33 | Section 4 | Material | Not on List | Not on List | 3 | Number | 32 | 96 | Surveying Consumables | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28583-001025 | 28583 | 2020-01-28 11:33 | Section 4 | Material | Not on List | Not on List | 1 | Number | 195 | 195 | Surveying Consumables | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28583-001025 | 28583 | 2020-01-28 11:33 | Section 4 | Material | Not on List | Not on List | 200 | Number | 0.2 | 40 | Surveying Consumables | 2020-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 124 | ea | 25.77 | 3195.48 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 62 | ea | 42.91 | 2660.42 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 56 | ea | 4.15 | 232.4 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 124 | ea | 15.8 | 1959.2 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 50 | Each | 14.93 | 746.5 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 2 | ea | 200.81 | 401.62 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 1 | ea | 111.15 | 111.15 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 1 | ea | 9.62 | 9.62 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28580-001025 | 28580 | 2020-01-28 10:04 | Section 6 | Material | Not on List | Not on List | 1 | ea | 9.62 | 9.62 | Fixings and Fasteners | 2020-01-31 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24354-001025 | 24354 | 2019-09-29 17:24 | Section 5 | Material | Not on List | Not on List | 1 | SM | 17490.28 | 17490.28 | Concrete Drainage | 2019-10-03 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24356-001025 | 24356 | 2019-09-29 18:07 | Section 5 | Material | Not on List | Not on List | 1 | SM | 17490.28 | 17490.28 | Not Sure | 2019-10-03 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24297-001025 | 24297 | 2019-09-27 08:20 | Section 5 | Material | Not on List | Not on List | 1 | SM | 15876.56 | 15876.56 | Miscellaneous | 2019-10-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6863-00751 | 6863 | 2018-09-21 12:23 | Section 4 | Material | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 4 | Each | 232.2 | 928.8 | Concrete Drainage | 2018-10-08 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24593-001025 | 24593 | 2019-10-03 13:33 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 339.6 | 340 | Miscellaneous | 2019-08-27 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24547-001025 | 24547 | 2019-10-02 17:42 | Core | Material | PPE, Small Tools and Consumables | Not on List | 144 | Pack 24 | 6.29 | 905.76 | Miscellaneous | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24389-001025 | 24389 | 2019-09-30 13:13 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | PACK | 55 | 110 | Janitorial | 2019-10-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24542-001025 | 24542 | 2019-10-02 15:51 | Section 2 | Material | Not on List | Not on List | 12 | Each | 36.14 | 433.68 | Builders Merchants (General) | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Concrete Drainage | CPM 825mm Concrete Pipe 2.5m (249364) | 17 | Each | 210.95 | 3586.15 | Concrete Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 2 | Each | 47.04 | 94.08 | Concrete Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6865-00751 | 6865 | 2018-09-21 12:34 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2166.3 | 2166.3 | Fixings and Fasteners | 2018-10-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 1 | Each | 59.17 | 59.17 | Concrete Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Twinwall | Polypipe Road Gully 450mm x 900mm (573005) | 14 | Each | 15.71 | 219.94 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Twinwall | Not on List | 10 | Each | NULL | 0 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 5 | Each | 116.62 | 583.1 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain 6m Unperf + Coupler (346382) | 18 | Each | 166.43 | 2995.74 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 72 | Each | 10.5 | 756 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Saint Gobain Castings | 454x454x100 D400 Watershed GG&F (257790) | 9 | Each | 63.84 | 574.56 | Builders Merchants (General) | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24505-001025 | 24505 | 2019-10-02 08:22 | Section 2 | Material | Saint Gobain Castings | Not on List | 1 | Each | NULL | 0 | Builders Merchants (General) | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5190-00117 | 5190 | 2018-08-16 07:50 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6865-00751 | 6865 | 2018-09-21 12:34 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1115.5 | 1115.5 | Fixings and Fasteners | 2018-10-08 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24510-001025 | 24510 | 2019-10-02 10:43 | Section 3 | Material | Not on List | Not on List | 1 | each | 1247.79 | 1247.79 | Miscellaneous | 2019-10-02 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24590-001025 | 24590 | 2019-10-03 09:58 | Section 4 | Material | Not on List | Not on List | 1 | SM | 1135.44 | 1135.44 | Miscellaneous | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24557-001025 | 24557 | 2019-10-03 07:46 | Section 2 | Material | Twinwall | Polypipe 600mm Ridgidrain Seal (346400) | 30 | Each | 28.18 | 845.4 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24557-001025 | 24557 | 2019-10-03 07:46 | Section 2 | Material | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 144 | Each | 1.55 | 223.2 | Plastic Drainage | 2019-10-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24606-001025 | 24606 | 2019-10-03 13:43 | Section 4 | Material | Not on List | Not on List | 10 | EA | 122.72 | 1227.2 | Builders Merchants (General) | 2019-10-04 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24509-001025 | 24509 | 2019-10-02 10:40 | Section 2 | Material | Not on List | Not on List | 1 | EACH | 3281.5 | 3281.5 | Miscellaneous | 2019-10-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6914-00751 | 6914 | 2018-09-24 10:28 | Section 4 | Material | Not on List | Not on List | 3.188 | Tonne | 538 | 1715.14 | Rebar and Mesh | 2018-10-01 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24601-001025 | 24601 | 2019-10-03 12:53 | Section 2 | Material | Bagged | Not on List | 3 | NULL | NULL | 0 | Concrete Accessories | 2019-10-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24601-001025 | 24601 | 2019-10-03 12:53 | Section 2 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Accessories | 2019-10-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24651-001025 | 24651 | 2019-10-04 12:13 | Section 2 | Material | Not on List | Not on List | 48 | NULL | NULL | 0 | Miscellaneous | 2019-10-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24594-001025 | 24594 | 2019-10-03 13:47 | Section 4 | Material | Not on List | Not on List | 7 | EA | 365 | 2555 | Plastic Drainage | 2019-10-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24594-001025 | 24594 | 2019-10-03 13:47 | Section 4 | Material | Not on List | Not on List | 20 | no | 4.6 | 92 | Plastic Drainage | 2019-10-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24323-001025 | 24323 | 2019-09-27 13:33 | Section 3 | Material | Not on List | Not on List | 2 | ea | 31.85 | 63.7 | Miscellaneous | 2019-10-03 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-6914-00751 | 6914 | 2018-09-24 10:28 | Section 4 | Material | Not on List | Not on List | 3.788 | Tonne | 538 | 2037.94 | Rebar and Mesh | 2018-10-01 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24659-001025 | 24659 | 2019-10-04 13:45 | Section 4 | Material | Not on List | Not on List | 8 | EA | 46.5 | 372 | Rebar and Mesh | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6915-00751 | 6915 | 2018-09-24 12:21 | Section 4 | Material | Not on List | Not on List | 16 | Each | 18.51 | 296.16 | Miscellaneous | 2018-10-01 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | BN24 - Girton Interchange Bridge C | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23522-001025 | 23522 | 2019-09-11 14:13 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 3387.91 | 3387.91 | Miscellaneous | 2019-09-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24708-001025 | 24708 | 2019-10-07 12:13 | Core | Material | Not on List | Not on List | 12823 | SUM | 1 | 12823 | Professional Services | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24682-001025 | 24682 | 2019-10-07 07:01 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 70 | no | 3.35 | 234.5 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24713-001025 | 24713 | 2019-10-07 13:39 | Section 2 | Material | Not on List | Not on List | 200 | m | NULL | 0 | Builders Merchants (General) | 2019-10-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24705-001025 | 24705 | 2019-10-07 11:41 | Core | Material | PPE, Small Tools and Consumables | Not on List | 20 | EA | 3.42 | 68.4 | Small Tools (Consumables) | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24730-001025 | 24730 | 2019-10-07 16:13 | Core | Material | Not on List | Not on List | 1 | ea | 26860.8 | 26861 | Training | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24733-001025 | 24733 | 2019-10-07 16:39 | Core | Material | Not on List | Not on List | 2 | number | 165 | 330 | Surveying Consumables | 2019-10-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24732-001025 | 24732 | 2019-10-07 16:33 | Section 2 | Material | Not on List | Not on List | 75 | no. | NULL | 0 | Concrete Accessories | 2019-10-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24744-001025 | 24744 | 2019-10-08 07:24 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23763-001025 | 23763 | 2019-09-17 07:37 | Section 2 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 50 | Each | 24.32 | 1216 | Timber Products | 2019-09-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23763-001025 | 23763 | 2019-09-17 07:37 | Section 2 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 50 | Each | 6.82 | 341 | Timber Products | 2019-09-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-23763-001025 | 23763 | 2019-09-17 07:37 | Section 2 | Material | Timber | 47x150x4800mm Sawn Timber (206904) | 50 | Each | 10.08 | 504 | Timber Products | 2019-09-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 70 | no | 2.77 | 193.9 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24518-001025 | 24518 | 2019-10-02 11:36 | Section 5 | Material | Kerbs | Not on List | 1 | SM | 358.84 | 358.84 | Not Sure | 2019-10-09 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24520-001025 | 24520 | 2019-10-02 11:17 | Section 6 | Material | Not on List | Not on List | 1 | Each | 1460 | 1460 | Flow Control | 2019-10-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24520-001025 | 24520 | 2019-10-02 11:17 | Section 6 | Material | Not on List | Not on List | 1 | Each | 1650 | 1650 | Flow Control | 2019-10-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24520-001025 | 24520 | 2019-10-02 11:17 | Section 6 | Material | Not on List | Not on List | 1 | Each | 265 | 265 | Flow Control | 2019-10-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24520-001025 | 24520 | 2019-10-02 11:17 | Section 6 | Material | Not on List | Not on List | 1 | Each | 265 | 265 | Flow Control | 2019-10-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24520-001025 | 24520 | 2019-10-02 11:17 | Section 6 | Material | Not on List | Not on List | 2 | Each | 95 | 190 | Flow Control | 2019-10-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24485-001025 | 24485 | 2019-10-02 07:38 | Core | Material | NULL | NULL | 1 | Each | 384.26 | 384.26 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 70 | no | 5.6 | 392 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24626-001025 | 24626 | 2019-10-04 06:57 | Section 4 | Material | Not on List | Not on List | 2000 | Each | 0.9 | 1800 | Timber Products | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24531-001025 | 24531 | 2019-10-02 13:47 | Core | Material | PPE, Small Tools and Consumables | Not on List | 32 | Each | 28.8 | 921.6 | PPE | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24534-001025 | 24534 | 2019-10-02 15:09 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1098.95 | Each | 1 | 1098.95 | Janitorial | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24773-001025 | 24773 | 2019-10-08 11:08 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | EACH | 76.5 | 153 | Small Tools (Consumables) | 2019-10-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24628-001025 | 24628 | 2019-10-04 07:26 | Section 4 | Material | Not on List | Not on List | 4 | Pack 100 | 10.5 | 42 | Surveying Consumables | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24756-001025 | 24756 | 2019-10-08 09:01 | Section 2 | Material | Not on List | Not on List | 100000 | Litres | 1 | 100000 | Fuel | 2019-10-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24689-001025 | 24689 | 2019-10-07 08:21 | Core | Material | NULL | NULL | 1 | Each | 440 | 440 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 70 | no | 3.91 | 273.7 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24625-001025 | 24625 | 2019-10-04 06:36 | Section 4 | Material | Not on List | Not on List | 10 | Each | 285 | 2850 | Miscellaneous | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24639-001025 | 24639 | 2019-10-04 10:55 | Core | Material | NULL | NULL | 1 | Each | 506 | 506 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24609-001025 | 24609 | 2019-10-03 16:37 | Core | Material | NULL | NULL | 1 | Each | 22 | 22 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24685-001025 | 24685 | 2019-10-07 07:22 | Section 3 | Material | Not on List | Not on List | 150 | EA | 0.95 | 142.5 | Surveying Consumables | 2019-10-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24685-001025 | 24685 | 2019-10-07 07:22 | Section 3 | Material | Not on List | Not on List | 4 | EA | 29.11 | 116.44 | Concrete Drainage | 2019-10-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24685-001025 | 24685 | 2019-10-07 07:22 | Section 3 | Material | Not on List | Not on List | 4 | EA | 29.11 | 116.44 | Concrete Drainage | 2019-10-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24575-001025 | 24575 | 2019-10-03 10:46 | Section 4 | Material | Not on List | Not on List | 112 | Each | 2.97 | 332.64 | Small Tools (Consumables) | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24702-001025 | 24702 | 2019-10-07 10:56 | Section 4 | Material | Not on List | Not on List | 1000 | Each | 0.37 | 370 | Miscellaneous | 2019-10-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24710-001025 | 24710 | 2019-10-07 12:29 | Section 4 | Material | Not on List | Not on List | 60 | Each | 10.7 | 642 | Small Tools (Consumables) | 2019-10-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 140 | no | 24.84 | 3477.6 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24516-001025 | 24516 | 2019-10-02 11:26 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 8 | Each | 3.66 | 29.28 | Small Tools (Consumables) | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24787-001025 | 24787 | 2019-10-08 14:21 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | 5.92 | 30 | Concrete Accessories | 2019-10-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24787-001025 | 24787 | 2019-10-08 14:21 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Concrete Accessories | 2019-10-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24787-001025 | 24787 | 2019-10-08 14:21 | Section 2 | Material | PPE, Small Tools and Consumables | Brush Wire 4 Row Heavy Duty C/W Scraper Spartan Pro (504004) | 10 | Each | 0.86 | 9 | Concrete Accessories | 2019-10-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24636-001025 | 24636 | 2019-10-04 09:34 | Section 4 | Material | Not on List | Not on List | 200 | NULL | 0.2 | 40 | Surveying Consumables | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24247-001025 | 24247 | 2019-09-26 09:41 | Section 4 | Material | Not on List | Not on List | 1 | Number | 100 | 100 | Surveying Consumables | 2019-09-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24259-001025 | 24259 | 2019-09-26 12:04 | Section 4 | Material | Not on List | Not on List | 1 | Number | 252.2 | 252.2 | Surveying Consumables | 2019-09-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24280-001025 | 24280 | 2019-09-26 16:09 | Section 4 | Material | Not on List | Not on List | 2 | Number | 18 | 36 | Surveying Consumables | 2019-09-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 140 | no | 21.33 | 2986.2 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24707-001025 | 24707 | 2019-10-07 12:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 30.24 | 302.4 | Small Tools (Consumables) | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24796-001025 | 24796 | 2019-10-08 16:11 | Core | Material | Not on List | Not on List | 1 | No. | 381.65 | 382 | Miscellaneous | 2019-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-24706-001025 | 24706 | 2019-10-07 11:47 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | 21.3 | 639 | Miscellaneous | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24766-001025 | 24766 | 2019-10-08 10:16 | Section 4 | Material | NULL | NULL | 450 | Each | 4.59 | 2065.5 | Builders Merchants (General) | 2019-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24766-001025 | 24766 | 2019-10-08 10:16 | Section 4 | Material | NULL | NULL | 12 | Each | 5.44 | 65.28 | Builders Merchants (General) | 2019-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24766-001025 | 24766 | 2019-10-08 10:16 | Section 4 | Material | NULL | NULL | 12 | Each | 5.44 | 65.28 | Builders Merchants (General) | 2019-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5192-00118 | 5192 | 2018-08-16 08:39 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 140 | no | 6.1 | 854 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 140 | no | 6.26 | 876.4 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24380-001025 | 24380 | 2019-09-30 12:13 | Section 4 | Material | Not on List | Not on List | 1 | Each | 264.25 | 264.25 | Miscellaneous | 2019-09-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24647-001025 | 24647 | 2019-10-04 11:40 | Core | Material | NULL | NULL | 1 | Each | 505.71 | 505.71 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24654-001025 | 24654 | 2019-10-04 10:11 | Section 4 | Material | Not on List | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2019-10-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24763-001025 | 24763 | 2019-10-08 09:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 7 | EAch | 53.6 | 375.2 | PPE | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24836-001025 | 24836 | 2019-10-09 11:33 | Section 2 | Material | Not on List | Not on List | 10 | ea | 35.15 | 351.5 | Damage Charges | 2019-10-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1705 - Repairs to Existing Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 250 | no | 22.62 | 5655 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23771-001025 | 23771 | 2019-09-17 08:59 | Core | Material | NULL | NULL | 1 | Each | 7944.71 | 7944.71 | Professional Services | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23771-001025 | 23771 | 2019-09-17 08:59 | Core | Material | NULL | NULL | 1 | Each | 6637.86 | 6637.86 | Professional Services | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-23771-001025 | 23771 | 2019-09-17 08:59 | Core | Material | NULL | NULL | 1 | Each | 4710.44 | 4710.44 | Professional Services | 2019-09-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24864-001025 | 24864 | 2019-10-09 15:28 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24866-001025 | 24866 | 2019-10-09 15:54 | Section 6 | Material | Aggregate | Class 1A | 10000 | Tonnes | 4 | 40000 | Aggregate | 2019-10-11 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 604 - Deposition (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24891-001025 | 24891 | 2019-10-10 07:47 | Section 5 | Material | Not on List | Not on List | 4 | NULL | 950 | 3800 | Miscellaneous | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6956-00752 | 6956 | 2018-09-25 10:07 | Section 4 | Material | Not on List | Not on List | 500 | no | 0.9 | 450 | Fixings and Fasteners | 2018-10-05 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24891-001025 | 24891 | 2019-10-10 07:47 | Section 5 | Material | Not on List | Not on List | 5 | NULL | 718 | 3590 | Miscellaneous | 2019-12-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | GN05 - Gantry structures | 1805 - Cantilever Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24251-001025 | 24251 | 2019-09-26 09:57 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24802-001025 | 24802 | 2019-10-08 16:25 | Section 6 | Material | Not on List | Not on List | 6 | Each | NULL | 0 | Miscellaneous | 2019-10-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24802-001025 | 24802 | 2019-10-08 16:25 | Section 6 | Material | Not on List | Not on List | 4 | Each | NULL | 0 | Miscellaneous | 2019-10-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24802-001025 | 24802 | 2019-10-08 16:25 | Section 6 | Material | Not on List | Not on List | 4 | Each | NULL | 0 | Miscellaneous | 2019-10-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24802-001025 | 24802 | 2019-10-08 16:25 | Section 6 | Material | Geotextile | Not on List | 1 | Roll (25m) | NULL | 0 | Geotextiles | 2019-10-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-24764-001025 | 24764 | 2019-10-08 09:53 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1098.95 | Each | 1 | 1098.95 | Janitorial | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | No - Reject | REQ - Buyers
MREQ-24910-001025 | 24910 | 2019-10-10 10:53 | Core | Material | PPE, Small Tools and Consumables | Jalas E-Sport S3 Mid-Cut Safety Boot (120102) | 5 | Each | 39.99 | 200 | PPE | 2019-10-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24910-001025 | 24910 | 2019-10-10 10:53 | Core | Material | Not on List | Not on List | 1 | Each | 91.36 | 91 | Janitorial | 2019-10-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24910-001025 | 24910 | 2019-10-10 10:53 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 1017.13 | 1017 | Small Tools (Consumables) | 2019-10-15 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24908-001025 | 24908 | 2019-10-10 10:40 | Section 5 | Material | Not on List | Not on List | 40 | EA | 6.5 | 260 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24821-001025 | 24821 | 2019-10-08 17:47 | Section 1 | Material | Not on List | Not on List | 1 | SM | 4349.78 | 4349.78 | Not Sure | 2019-10-14 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-24776-001025 | 24776 | 2019-10-08 12:27 | Core | Material | NULL | NULL | 1 | Each | 75 | 75 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24934-001025 | 24934 | 2019-10-10 16:39 | Section 4 | Material | Not on List | Not on List | 5 | Number | 60 | 300 | Surveying Consumables | 2019-10-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-24946-001025 | 24946 | 2019-10-10 18:08 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2176.86 | 2176.86 | Miscellaneous | 2019-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24980-001025 | 24980 | 2019-10-11 12:54 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 150 | EA | 7.5 | 1125 | Surveying Consumables | 2019-10-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18505-001025 | 18505 | 2019-06-04 10:34 | Section 2 | Material | Not on List | Not on List | 1 | each | 718 | 718 | Miscellaneous | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | NULL | Req - S2 Buyers
MREQ-18509-001025 | 18509 | 2019-06-04 10:37 | Section 3 | Material | Aggregate | 6C/6A1 | 60 | Tonnes | 22.2 | 1332 | Aggregate | 2019-06-06 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | CL3B - Structures (Culverts) 3B | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18580-001025 | 18580 | 2019-06-05 09:28 | Section 6 | Material | Not on List | Not on List | 1 | Set | NULL | 0 | Miscellaneous | 2019-06-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18580-001025 | 18580 | 2019-06-05 09:28 | Section 6 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2019-06-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-18581-001025 | 18581 | 2019-06-05 10:13 | Core | Material | Not on List | Not on List | 1 | each | 850 | 850 | Training | 2019-06-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Tape Gaffa Waterproof Cloth Grey 50mm X 50 Mtr Ref 3160 (964670) | 40 | Each | 1.91 | 76 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Paint Roller And Tray Set 9" Rskit1 (704256) | 20 | Each | 3.42 | 68 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Bucket Galvanised 2 1/2gall/11.42ltr 10"/30cm Dia Spartan (506016) | 20 | Each | 9 | 180 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Red (742163) | 20 | Each | 6.7 | 134 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Can Fuel 5ltr Heavy Duty Green Plastic Long Spout Unleaded (706686) | 5 | Each | 5.82 | 29 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-4993-006 | 4993 | 2018-08-13 14:56 | Section 4 | Material | Not on List | NULL | 1 | 25kg Box | 61.66 | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-08-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Can Fuel 5ltr Heavy Duty Black Plastic Long Spout For Diesel (706684) | 5 | Each | 5.85 | 29 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18583-001025 | 18583 | 2019-06-05 07:41 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-18587-001025 | 18587 | 2019-06-05 10:52 | Section 5 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18529-001025 | 18529 | 2019-06-04 14:05 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 4 | Each | 13 | 52 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Trouser Cargo Polycotton En471cl1 Saturn Short Ct01-y (302023) | 2 | Each | 13 | 26 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 20 | Each | 8.55 | 171 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 20 | Each | 8.55 | 171 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 25 | Each | 8.55 | 214 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 20 | Each | 8.55 | 171 | PPE | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml White (742159) | 45 | Each | 6.71 | 302 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Red (742163) | 25 | Each | 6.7 | 168 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Blue (742162) | 25 | Each | 6.66 | 167 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18601-001025 | 18601 | 2019-06-05 12:19 | Core | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Yellow (742161) | 25 | Each | 6.71 | 168 | Small Tools (Consumables) | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18575-001025 | 18575 | 2019-06-05 08:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-06-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18617-001025 | 18617 | 2019-06-05 16:33 | Section 5 | Material | Not on List | Not on List | 2 | NULL | 55.99 | 112 | Office Supplies | 2019-06-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18630-001025 | 18630 | 2019-06-06 06:58 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-06-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18631-001025 | 18631 | 2019-06-06 07:16 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18637-001025 | 18637 | 2019-06-06 08:23 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-07 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | NULL | Not on List | 1 | bag | NULL | 0 | Fixings and Fasteners | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | NULL | Not on List | 5 | sheets | NULL | 0 | Timber Products | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | NULL | Not on List | 20 | meters | NULL | 0 | Timber Products | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 8 | units | NULL | 0 | Miscellaneous | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 3 | units | NULL | 0 | Miscellaneous | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 9 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 9 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 9 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 22 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 9 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 8 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 8 | units | NULL | 0 | Fixings and Fasteners | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 60 | meters | NULL | 0 | Miscellaneous | 2019-06-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18469-001025 | 18469 | 2019-06-03 14:29 | Section 2 | Material | Not on List | Not on List | 3 | bags | NULL | 0 | Ready Mixed Concrete | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | GN2B - Gantry structures | 1705 - Repairs to Existing Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18639-001025 | 18639 | 2019-06-06 08:34 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18649-001025 | 18649 | 2019-06-06 09:40 | Core | Material | Not on List | Not on List | 60 | NULL | 2.5 | 150 | Surveying Consumables | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18654-001025 | 18654 | 2019-06-06 10:43 | Section 4 | Material | Not on List | Not on List | 1 | Number | 5450 | 5450 | Surveying Consumables | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-18654-001025 | 18654 | 2019-06-06 10:43 | Section 4 | Material | Not on List | Not on List | 1 | Number | 290 | 290 | Surveying Consumables | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-18602-001025 | 18602 | 2019-06-05 14:13 | Section 4 | Material | NULL | NULL | 10 | Each | 37.54 | 375.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-06-06 | RVP 410 - 1339627 - Slate Hall Farm J30 A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18544-001025 | 18544 | 2019-06-04 15:59 | Section 4 | Material | Not on List | Not on List | 100 | Hun | 838 | 83800 | Concrete Drainage | 2019-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18671-001025 | 18671 | 2019-06-06 11:43 | Section 5 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-06-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18512-001025 | 18512 | 2019-06-04 10:55 | Section 3 | Material | Aggregate | 6G | 150 | Tonnes | 32.9 | 4935 | Aggregate | 2019-06-10 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | CL3B - Structures (Culverts) 3B | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18220-001025 | 18220 | 2019-05-29 17:26 | Section 3 | Material | NULL | Not on List | 5 | ea | 164.37 | 821.85 | Plastic Drainage | 2019-05-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18220-001025 | 18220 | 2019-05-29 17:26 | Section 3 | Material | NULL | Polypipe 450mm Ridgidrain Seal (346396) | 6 | Each | 10.04 | 60.24 | Plastic Drainage | 2019-05-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18220-001025 | 18220 | 2019-05-29 17:26 | Section 3 | Material | NULL | Not on List | 6 | ea | 89.45 | 536.7 | Plastic Drainage | 2019-05-30 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18618-001025 | 18618 | 2019-06-05 16:34 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-06-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18688-001025 | 18688 | 2019-06-06 14:27 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18688-001025 | 18688 | 2019-06-06 14:27 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18688-001025 | 18688 | 2019-06-06 14:27 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18692-001025 | 18692 | 2019-06-06 15:26 | Core | Material | Not on List | Not on List | 1 | ea | 360 | 360 | Training | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18684-001025 | 18684 | 2019-06-06 14:14 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-18694-001025 | 18694 | 2019-06-06 16:03 | Core | Material | Not on List | Not on List | 1 | NULL | 110 | 110 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18695-001025 | 18695 | 2019-06-06 16:05 | Section 3 | Material | Not on List | Not on List | 400 | NULL | 2.06 | 824 | Office Supplies | 2019-06-13 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-18274-001025 | 18274 | 2019-05-30 14:03 | Core | Material | Not on List | Not on List | 60 | number | 50 | 3000 | Miscellaneous | 2019-05-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18702-001025 | 18702 | 2019-06-06 12:22 | Core | Material | Not on List | Not on List | 1 | NULL | 698.45 | 698 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18702-001025 | 18702 | 2019-06-06 12:22 | Core | Material | Not on List | Not on List | 1 | NULL | 19.21 | 19 | Miscellaneous | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18707-001025 | 18707 | 2019-06-06 17:39 | Section 4 | Material | Not on List | Not on List | 300 | Each | 7.5 | 2250 | Surveying Consumables | 2019-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18683-001025 | 18683 | 2019-06-06 14:09 | Section 4 | Material | Not on List | Not on List | 1 | Number | 5450 | 5450 | Surveying Consumables | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18683-001025 | 18683 | 2019-06-06 14:09 | Section 4 | Material | Not on List | Not on List | 1 | Number | 290 | 290 | Surveying Consumables | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17373-001025 | 17373 | 2019-05-14 13:03 | Core | Material | Not on List | Not on List | 150 | NULL | 0.14 | 21 | Office Supplies | 2019-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18576-001025 | 18576 | 2019-06-05 08:32 | Section 2 | Material | NULL | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 30 | Each | 81.73 | 2451.9 | Ductile Drainage | 2019-06-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18576-001025 | 18576 | 2019-06-05 08:32 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18576-001025 | 18576 | 2019-06-05 08:32 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18576-001025 | 18576 | 2019-06-05 08:32 | Section 2 | Material | Not on List | Not on List | 20 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-10 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18719-001025 | 18719 | 2019-06-07 09:03 | Core | Material | Not on List | Not on List | 1 | number | 6577.75 | 6578 | Professional Services | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18638-001025 | 18638 | 2019-06-06 07:49 | Section 3 | Material | Not on List | Not on List | 2370 | No | 3.12 | 7394.4 | Builders Merchants (General) | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18638-001025 | 18638 | 2019-06-06 07:49 | Section 3 | Material | Not on List | Not on List | 2370 | No | 3.12 | 7394.4 | Builders Merchants (General) | 2019-06-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18657-001025 | 18657 | 2019-06-06 10:54 | Section 4 | Material | Not on List | Not on List | 3 | Number | 1295 | 3885 | Surveying Consumables | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18698-001025 | 18698 | 2019-06-06 16:39 | Section 3 | Material | NULL | Not on List | 26 | No | 7.52 | 195.52 | Builders Merchants (General) | 2019-06-11 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18523-001025 | 18523 | 2019-06-04 13:17 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 247.97 | 247.97 | Small Tools (Consumables) | 2019-06-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18727-001025 | 18727 | 2019-06-07 09:40 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | Surveying Consumables | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Ops Pass Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-18727-001025 | 18727 | 2019-06-07 09:40 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | Surveying Consumables | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Ops Pass Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-18727-001025 | 18727 | 2019-06-07 09:40 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | Surveying Consumables | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Ops Pass Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-18727-001025 | 18727 | 2019-06-07 09:40 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | NULL | NULL | 0 | Surveying Consumables | 2019-06-05 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Request - Ops Pass Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-18524-001025 | 18524 | 2019-06-04 13:23 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 860.93 | 860.93 | Small Tools (Consumables) | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18689-001025 | 18689 | 2019-06-06 15:23 | Section 4 | Material | Not on List | Not on List | 16 | sheets | 54 | 864 | NULL | 2019-06-10 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18703-001025 | 18703 | 2019-06-06 17:09 | Section 4 | Material | Not on List | Not on List | 2 | packs | 217.7 | 435.4 | NULL | 2019-06-10 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18703-001025 | 18703 | 2019-06-06 17:09 | Section 4 | Material | Not on List | Not on List | 1 | packs | 149.8 | 149.8 | NULL | 2019-06-10 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18651-001025 | 18651 | 2019-06-06 10:07 | Section 3 | Material | Not on List | Not on List | 3 | ea | 36 | 108 | Small Tools (Consumables) | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18651-001025 | 18651 | 2019-06-06 10:07 | Section 3 | Material | Not on List | Not on List | 1 | ea | 126 | 126 | Small Tools (Consumables) | 2019-06-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18651-001025 | 18651 | 2019-06-06 10:07 | Section 3 | Material | NULL | Not on List | NULL | NULL | NULL | 0 | NULL | NULL | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-18738-001025 | 18738 | 2019-06-07 10:50 | Core | Material | Not on List | Not on List | 1 | number | 223.65 | 224 | Miscellaneous | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18635-001025 | 18635 | 2019-06-06 07:51 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 112 | Each | 2.97 | 332.64 | Builders Merchants (General) | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18697-001025 | 18697 | 2019-06-06 16:28 | Section 2 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Builders Merchants (General) | 2019-06-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2010 - Waterproofing for concrete structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-18696-001025 | 18696 | 2019-06-06 16:12 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 218.8 | 218.8 | Small Tools (Consumables) | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18525-001025 | 18525 | 2019-06-04 13:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 668.5 | 668.5 | PPE | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18757-001025 | 18757 | 2019-06-07 11:55 | Core | Material | Not on List | Not on List | 4 | Number | 5.99 | 24 | Miscellaneous | 2019-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-17594-001025 | 17594 | 2019-05-17 10:21 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-05-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-18101-001025 | 18101 | 2019-05-28 09:59 | Section 4 | Material | Not on List | Not on List | 1 | Number | 524.7 | 524.7 | Surveying Consumables | 2019-05-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-18659-001025 | 18659 | 2019-06-06 11:11 | Section 4 | Material | Not on List | Not on List | 1 | each | 388.7 | 388.7 | Miscellaneous | 2019-06-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14132-001025 | 14132 | 2019-03-15 14:42 | Section 3 | Material | Not on List | Not on List | 10 | Each | 16.5 | 165 | Aggregate | 2019-03-19 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5811-00489 | 5811 | 2018-08-30 12:54 | Section 3 | Material | Not on List | Not on List | 4 | Packs | 116 | 464 | Builders Merchants (General) | 2018-09-03 | Gate K - 1339704 - Access to BN14, BN15 & BN16 Connington off Connington Rd Eastbound | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11593-001025 | 11593 | 2019-01-29 08:14 | Section 4 | Material | Not on List | Not on List | 13 | Each | 314.15 | 4083.95 | Concrete Drainage | 2019-03-20 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13544-001025 | 13544 | 2019-03-06 11:30 | Core | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | 21.75 | 108.75 | Laboratory Equipment / Certification | 2019-03-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14201-001025 | 14201 | 2019-03-18 14:44 | Section 5 | Material | Not on List | Not on List | 100 | units | NULL | 0 | Builders Merchants (General) | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14201-001025 | 14201 | 2019-03-18 14:44 | Section 5 | Material | Not on List | Not on List | 1 | each | NULL | 0 | Builders Merchants (General) | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5723-00451 | 5723 | 2018-08-29 07:45 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 336.48 | 336.48 | Small Tools (Consumables) | 2018-08-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 4 | Each | 85.23 | 340.92 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 9 | Each | 63.93 | 575.37 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 2 | Each | 120.1 | 240.2 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 1 | Each | 106.93 | 106.93 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 2 | Each | 128.32 | 256.64 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 2 | Each | 294.58 | 589.16 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13969-001025 | 13969 | 2019-03-13 16:23 | Section 4 | Material | Not on List | Not on List | 1 | Each | 777.06 | 777.06 | Concrete Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13781-001025 | 13781 | 2019-03-11 14:07 | Core | Material | Not on List | Not on List | 4 | Each | 850 | 3400 | Training | 2019-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13783-001025 | 13783 | 2019-03-11 14:12 | Core | Material | Not on List | Not on List | 1 | Each | 1737.5 | 1737.5 | Training | 2019-04-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12865-001025 | 12865 | 2019-02-21 15:44 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 1597.71 | 1597.71 | Miscellaneous | 2019-02-22 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 107 - Insurance | Buyer - Closed | NULL | Yes - Approve | Req - S6 Buyers
MREQ-14082-001025 | 14082 | 2019-03-15 08:01 | Core | Material | Not on List | Not on List | 1 | ea | 1500 | 1500 | Training | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14169-001025 | 14169 | 2019-03-18 10:40 | Section 3 | Material | Not on List | Not on List | 1 | No | 175.45 | 175.45 | Professional Services | 2019-03-18 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14252-001025 | 14252 | 2019-03-19 09:05 | Section 3 | Material | Not on List | Not on List | 20 | Sheet | 12.81 | 256.2 | Concrete Accessories | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5721-00450 | 5721 | 2018-08-29 07:41 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 698.51 | 698.51 | Small Tools (Consumables) | 2018-08-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14252-001025 | 14252 | 2019-03-19 09:05 | Section 3 | Material | Not on List | Not on List | 20 | Sheet | 10.44 | 208.8 | Concrete Accessories | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14252-001025 | 14252 | 2019-03-19 09:05 | Section 3 | Material | Not on List | Not on List | 1 | Coil | 45.5 | 45.5 | Concrete Accessories | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14193-001025 | 14193 | 2019-03-18 13:47 | Section 3 | Material | Not on List | Not on List | 1 | ea | 400 | 400 | Miscellaneous | 2019-03-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14212-001025 | 14212 | 2019-03-18 16:03 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | EACH | 8.18 | 32.72 | Small Tools (Consumables) | 2019-03-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1401 - Trenches, Ducts and Chambers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14251-001025 | 14251 | 2019-03-19 09:12 | Section 3 | Material | Not on List | Not on List | 2000 | No | 0.49 | 980 | Builders Merchants (General) | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14251-001025 | 14251 | 2019-03-19 09:12 | Section 3 | Material | Not on List | Not on List | 500 | No | 0.25 | 125 | Builders Merchants (General) | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14205-001025 | 14205 | 2019-03-18 15:20 | Section 5 | Material | Not on List | Not on List | 1000 | EACH | 0.31 | 310 | Builders Merchants (General) | 2019-03-19 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14268-001025 | 14268 | 2019-03-19 11:22 | Section 3 | Material | Aggregate | Not on List | 250000 | Tonne | 4 | 1000000 | Aggregate | 2019-03-20 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14250-001025 | 14250 | 2019-03-19 09:05 | Section 3 | Material | Concrete Drainage | CPM 750mm Concrete Pipe 2.5m (911417) | 6 | Each | 165.1 | 990.6 | Concrete Drainage | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14250-001025 | 14250 | 2019-03-19 09:05 | Section 3 | Material | Concrete Drainage | CPM 750mm Concrete Socket (890395) | 2 | Each | 198.12 | 396.24 | Concrete Drainage | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5827-00516 | 5827 | 2018-08-30 16:49 | Section 3 | Material | Not on List | Not on List | 200 | NULL | NULL | 0 | Office Supplies | 2018-08-09 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14250-001025 | 14250 | 2019-03-19 09:05 | Section 3 | Material | Concrete Drainage | CPM 750mm Concrete Spigot (890374) | 2 | Each | 198.12 | 396.24 | Concrete Drainage | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14235-001025 | 14235 | 2019-03-18 19:19 | Section 3 | Material | Not on List | Not on List | 2.821 | tonne | 538 | 1517.7 | Rebar and Mesh | 2019-04-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14261-001025 | 14261 | 2019-03-19 11:05 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Pack 24 | 6.29 | 905.76 | Small Tools (Consumables) | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14330-001025 | 14330 | 2019-03-20 07:10 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 3 | number | NULL | 0 | PPE | 2019-03-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2302 - Sealing of gaps | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-14330-001025 | 14330 | 2019-03-20 07:10 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 3 | number | NULL | 0 | PPE | 2019-03-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2302 - Sealing of gaps | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-14334-001025 | 14334 | 2019-03-20 07:24 | Section 2 | Material | Bagged | OP Cement; 25kg bag (767201) | 40 | Each | 2.9 | 116 | Builders Merchants (General) | 2019-03-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2401 - Brickwork, Blockwork and Stonework | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14334-001025 | 14334 | 2019-03-20 07:24 | Section 2 | Material | Bagged | Not on List | 10 | each | NULL | 0 | Builders Merchants (General) | 2019-03-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2401 - Brickwork, Blockwork and Stonework | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14334-001025 | 14334 | 2019-03-20 07:24 | Section 2 | Material | Not on List | Not on List | 62 | each | NULL | 0 | Concrete Accessories | 2019-03-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2401 - Brickwork, Blockwork and Stonework | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14084-001025 | 14084 | 2019-03-15 08:28 | Core | Material | Not on List | Not on List | 1 | ea | 1023 | 1023 | Training | 2019-03-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13754-001025 | 13754 | 2019-03-11 10:07 | Core | Material | Not on List | Not on List | 2 | Number | 500 | 1000 | Surveying Consumables | 2019-04-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14360-001025 | 14360 | 2019-03-20 09:57 | Section 2 | Material | Not on List | Not on List | 30 | number | NULL | 0 | Reinforcement | 2019-03-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Municipal Waste - Wheelie Bin 1100 Litre | 150 | Each | 14.25 | 2137.5 | Waste (General) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Wood - Roll On Roll Off 20 cubic yard | 30 | Each | 250 | 7500 | Waste (Recycling) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Plastic - Roll On Roll Off 40 cubic yard | 30 | Each | 360 | 10800 | Waste (General) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 30 | Each | 95 | 2850 | Waste (General) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Construction Waste - Roll On Roll Off 20 cubic yard | 30 | Each | 370 | 11100 | Waste (General) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14200-001025 | 14200 | 2019-03-18 14:15 | Section 3 | Material | Waste Management | Dry Mixed Recycling - Wheelie Bin 1100 Litre | 125 | Each | 7 | 875 | Waste (General) | 2019-03-19 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14366-001025 | 14366 | 2019-03-20 11:03 | Section 2 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Surveying Consumables | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-14368-001025 | 14368 | 2019-03-20 11:33 | Section 5 | Material | Not on List | Not on List | 30 | LTRS | NULL | 0 | Miscellaneous | 2019-03-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14369-001025 | 14369 | 2019-03-20 11:39 | Section 5 | Material | Not on List | Not on List | 4 | each | NULL | 0 | Builders Merchants (General) | 2019-03-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-14372-001025 | 14372 | 2019-03-20 11:57 | Core | Material | Not on List | Not on List | 1 | NULL | 372.38 | 372 | Miscellaneous | 2019-03-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Operations Rejected | No - Reject | NULL | REQ - Buyers
MREQ-14367-001025 | 14367 | 2019-03-20 11:02 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 22550 | 22550 | Miscellaneous | 2019-03-29 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5128-0052 | 5128 | 2018-08-15 10:09 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Electrical | 2018-08-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-14308-001025 | 14308 | 2019-03-19 16:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | 1.99 | 79.6 | Small Tools (Consumables) | 2019-03-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14296-001025 | 14296 | 2019-03-19 15:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | 3.88 | 194 | Small Tools (Consumables) | 2019-03-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14296-001025 | 14296 | 2019-03-19 15:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | 3.13 | 313 | PPE | 2019-03-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14057-001025 | 14057 | 2019-03-14 16:15 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | 10.8 | 108 | Office Supplies | 2019-03-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13656-001025 | 13656 | 2019-03-08 11:36 | Core | Material | Not on List | Not on List | 5 | Boxes | 10 | 50 | Surveying Consumables | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13656-001025 | 13656 | 2019-03-08 11:36 | Core | Material | Not on List | Not on List | 1 | number | 81 | 81 | Surveying Consumables | 2019-03-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13996-001025 | 13996 | 2019-03-14 08:14 | Core | Material | Not on List | Not on List | 3 | No. | 500 | 1500 | Surveying Consumables | 2019-03-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13996-001025 | 13996 | 2019-03-14 08:14 | Core | Material | Not on List | Not on List | 1 | No. | 165 | 165 | Surveying Consumables | 2019-03-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13996-001025 | 13996 | 2019-03-14 08:14 | Core | Material | Not on List | Not on List | 3 | boxes | 40 | 120 | Surveying Consumables | 2019-03-18 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-13537-001025 | 13537 | 2019-03-06 11:05 | Section 1 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-14297-001025 | 14297 | 2019-03-19 15:43 | Section 4 | Material | Not on List | Not on List | 2 | Each | 13 | 26 | Concrete Drainage | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14297-001025 | 14297 | 2019-03-19 15:43 | Section 4 | Material | Not on List | Not on List | 2 | Each | 38.47 | 76.94 | Concrete Drainage | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14297-001025 | 14297 | 2019-03-19 15:43 | Section 4 | Material | Not on List | Not on List | 1 | Each | 242.19 | 242.19 | Concrete Drainage | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14297-001025 | 14297 | 2019-03-19 15:43 | Section 4 | Material | Not on List | Not on List | 1 | Each | 247.12 | 247.12 | Concrete Drainage | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14354-001025 | 14354 | 2019-03-20 09:36 | Section 3 | Material | Not on List | Not on List | 20 | tonne | 538 | 10760 | NULL | 2019-04-10 | RVP 419 (S3) - 1340880 - A14 Westbound (West of Junction 28) | BN16 - New Barns Lane Overbridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14364-001025 | 14364 | 2019-03-20 10:40 | Section 4 | Material | Not on List | Not on List | 500 | Each | 2.18 | 1090 | Miscellaneous | 2019-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14364-001025 | 14364 | 2019-03-20 10:40 | Section 4 | Material | Not on List | Not on List | 500 | Each | 3.38 | 1690 | Miscellaneous | 2019-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14348-001025 | 14348 | 2019-03-20 09:12 | Section 3 | Material | Not on List | Not on List | 126 | NULL | 2.5 | 315 | Miscellaneous | 2019-03-25 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14266-001025 | 14266 | 2019-03-19 11:17 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 320.54 | 320.54 | Small Tools (Consumables) | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14392-001025 | 14392 | 2019-03-20 15:59 | Section 3 | Material | NULL | Building Sand Bulk Bag (938155) | 10 | Each | 33.35 | 333.5 | Builders Merchants (General) | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 10 | Each | 179.94 | 1799.4 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 40 | Each | 38.36 | 1534.4 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 120 | Each | 22.36 | 2683.2 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 25 | Each | 26.8 | 670 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 100 | Each | 3.65 | 365 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 250 | Each | 2 | 500 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 10 | Each | 37.6 | 376 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 50 | Each | 7.06 | 353 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13957-001025 | 13957 | 2019-03-13 13:17 | Section 4 | Material | Not on List | Not on List | 120 | Each | 2.97 | 356.4 | Plastic Drainage | 2019-03-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14329-001025 | 14329 | 2019-03-20 07:15 | Section 4 | Material | Not on List | Not on List | 8 | Each | 15.52 | 124.16 | Rebar and Mesh | 2019-03-22 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14329-001025 | 14329 | 2019-03-20 07:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 30 | 30 | Rebar and Mesh | 2019-03-22 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14329-001025 | 14329 | 2019-03-20 07:15 | Section 4 | Material | NULL | Not on List | 20 | Each | 7.82 | 156.4 | Rebar and Mesh | 2019-03-22 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14387-001025 | 14387 | 2019-03-20 15:25 | Section 3 | Material | Not on List | Not on List | 1 | Unit | 30000 | 30000 | Concrete Accessories | 2019-03-22 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14414-001025 | 14414 | 2019-03-21 07:31 | Section 2 | Material | Not on List | Not on List | 40 | m2 | NULL | 0 | Concrete Accessories | 2019-03-24 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5831-00524 | 5831 | 2018-08-30 19:04 | Section 4 | Material | Not on List | Not on List | 14 | 500Litres | 16.55 | 232 | Builders Merchants (General) | 2018-08-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14439-001025 | 14439 | 2019-03-21 09:41 | Section 6 | Material | Timber | Not on List | 200 | number | NULL | 0 | Surveying Consumables | 2019-03-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-14424-001025 | 14424 | 2019-03-21 08:28 | Section 3 | Material | PPE, Small Tools and Consumables | Sandbag New Hessian Unproofed 31" X 13" 7.5oz (746642) | 2000 | Each | 0.31 | 620 | Builders Merchants (General) | 2019-03-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5831-00524 | 5831 | 2018-08-30 19:04 | Section 4 | Material | Not on List | Not on List | 4 | Number | NULL | 0 | Builders Merchants (General) | 2018-08-31 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14109-001025 | 14109 | 2019-03-15 12:00 | Section 4 | Material | Not on List | Not on List | 56 | Each | 10.85 | 607.6 | Builders Merchants (General) | 2019-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14109-001025 | 14109 | 2019-03-15 12:00 | Section 4 | Material | Not on List | Not on List | 112 | Each | 10.85 | 1215.2 | Builders Merchants (General) | 2019-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14109-001025 | 14109 | 2019-03-15 12:00 | Section 4 | Material | Not on List | Not on List | 4 | Each | 0.65 | 2.6 | Builders Merchants (General) | 2019-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14109-001025 | 14109 | 2019-03-15 12:00 | Section 4 | Material | Not on List | Not on List | 3 | Each | 11.9 | 35.7 | Builders Merchants (General) | 2019-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4C - Structures (Culverts) 4C | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14359-001025 | 14359 | 2019-03-20 10:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 100 | NULL | 28.8 | 2880 | PPE | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14359-001025 | 14359 | 2019-03-20 10:14 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 16 | NULL | 28.8 | 460.8 | PPE | 2019-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14380-001025 | 14380 | 2019-03-20 14:35 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 15 | 90 | Miscellaneous | 2019-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13964-001025 | 13964 | 2019-03-13 16:07 | Section 4 | Material | Not on List | Not on List | 1 | number | NULL | 0 | Miscellaneous | 2019-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13773-001025 | 13773 | 2019-03-11 12:17 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 6215 | 6215 | Miscellaneous | 2019-03-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-13233-001025 | 13233 | 2019-02-28 11:07 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 27 | 27 | Small Tools (Consumables) | 2019-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 105 - Site Security | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-13233-001025 | 13233 | 2019-02-28 11:07 | Section 4 | Material | NULL | Not on List | 2 | Each | 28.9 | 57.8 | Small Tools (Consumables) | 2019-03-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 105 - Site Security | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-14455-001025 | 14455 | 2019-03-21 13:53 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Surveying Consumables | 2019-03-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-13243-001025 | 13243 | 2019-02-28 12:00 | Core | Material | Not on List | Not on List | 1 | NULL | 93.47 | 90 | Miscellaneous | 2019-03-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14440-001025 | 14440 | 2019-03-21 09:14 | Section 3 | Material | Not on List | Not on List | 4 | Packs | 27.73 | 110.92 | Rebar and Mesh | 2019-04-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14440-001025 | 14440 | 2019-03-21 09:14 | Section 3 | Material | Not on List | Not on List | 150 | each | 0.55 | 82.5 | Concrete Accessories | 2019-04-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14440-001025 | 14440 | 2019-03-21 09:14 | Section 3 | Material | NULL | Not on List | 1 | Bag | 7.6 | 7.6 | Concrete Accessories | 2019-03-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14440-001025 | 14440 | 2019-03-21 09:14 | Section 3 | Material | Not on List | Not on List | 1 | (10 Sheets) | 109.4 | 109.4 | Miscellaneous | 2019-04-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14480-001025 | 14480 | 2019-03-21 16:00 | Section 2 | Material | NULL | Not on List | 20 | number | 188 | 3760 | Geotextiles | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14480-001025 | 14480 | 2019-03-21 16:00 | Section 2 | Material | NULL | Not on List | 6 | number | 181 | 1086 | Geotextiles | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14480-001025 | 14480 | 2019-03-21 16:00 | Section 2 | Material | NULL | Not on List | 19 | number | 177 | 3363 | Geotextiles | 2019-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14480-001025 | 14480 | 2019-03-21 16:00 | Section 2 | Material | NULL | Not on List | 1 | no | 650 | 650 | NULL | NULL | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-14510-001025 | 14510 | 2019-03-22 09:46 | Section 3 | Material | Not on List | Not on List | 24 | NULL | NULL | 0 | Concrete Accessories | 2019-03-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN16 - New Barns Lane Overbridge | 1701 - Insitu Concrete | Commercial - Rejected | Yes - Approve | No - Reject | REQ - Section 3 Buyers
MREQ-14500-001025 | 14500 | 2019-03-21 18:24 | Section 3 | Material | Not on List | Not on List | 36 | Tubes | 11.08 | 398.88 | Concrete Accessories | 2019-03-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14500-001025 | 14500 | 2019-03-21 18:24 | Section 3 | Material | Not on List | Not on List | 200 | 600ml Foil packs | 4.97 | 994 | Concrete Accessories | 2019-03-27 | Gate D - 1339643 - BN10 Via Main Compound Entrance | BN16 - New Barns Lane Overbridge | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-14209-001025 | 14209 | 2019-03-18 15:51 | Core | Material | Not on List | Not on List | 1 | number | 4212.44 | 4212.44 | Miscellaneous | 2019-03-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14381-001025 | 14381 | 2019-03-20 14:40 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 638.69 | 638.69 | Laboratory Equipment / Certification | 2019-03-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14204-001025 | 14204 | 2019-03-18 15:14 | Core | Material | Not on List | Not on List | 1 | ea | 250 | 250 | Miscellaneous | 2019-01-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14376-001025 | 14376 | 2019-03-20 13:11 | Core | Material | Not on List | Not on List | 1 | ea | 13289.52 | 13289.52 | Office Supplies | 2019-03-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14362-001025 | 14362 | 2019-03-20 10:44 | Core | Material | Not on List | Not on List | 500 | NULL | 0.67 | 335 | Office Supplies | 2019-03-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14351-001025 | 14351 | 2019-03-20 09:32 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 205.2 | 205.2 | Laboratory Equipment / Certification | 2019-03-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-14531-001025 | 14531 | 2019-03-22 13:27 | Section 5 | Material | Not on List | Not on List | 300 | number | NULL | 0 | Builders Merchants (General) | 2019-03-25 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20392-001025 | 20392 | 2019-07-08 08:58 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20395-001025 | 20395 | 2019-07-08 12:07 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20407-001025 | 20407 | 2019-07-08 14:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20407-001025 | 20407 | 2019-07-08 14:00 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 50 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5249-00162 | 5249 | 2018-08-16 16:33 | Section 4 | Material | Plastic Drainage | NULL | 100 | Each | 5.95 | 595 | Plastic Drainage | 2018-08-22 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20006-001025 | 20006 | 2019-07-01 13:06 | Section 4 | Material | NULL | NULL | 4 | Each | 93.97 | 375.88 | Plastic Drainage | 2019-07-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20006-001025 | 20006 | 2019-07-01 13:06 | Section 4 | Material | NULL | NULL | 1 | Each | 115 | 115 | Plastic Drainage | 2019-07-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20413-001025 | 20413 | 2019-07-08 16:01 | Core | Material | Not on List | Not on List | 7 | NULL | 5.25 | 37 | Office Supplies | 2019-07-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20413-001025 | 20413 | 2019-07-08 16:01 | Core | Material | Not on List | Not on List | 2 | NULL | 5.75 | 12 | Office Supplies | 2019-07-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20413-001025 | 20413 | 2019-07-08 16:01 | Core | Material | Not on List | Not on List | 1 | NULL | 4.95 | 5 | Miscellaneous | 2019-07-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5250-00168 | 5250 | 2018-08-16 17:00 | Section 4 | Material | Concrete Drainage | Cpm 1500X1000 C/W Steps | 5 | Each | 121.25 | 606.25 | Concrete Drainage | 2018-08-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20295-001025 | 20295 | 2019-07-05 13:05 | Section 5 | Material | Timber | NULL | 35 | No | 27.94 | 977.9 | NULL | 2019-07-09 | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5250-00168 | 5250 | 2018-08-16 17:00 | Section 4 | Material | Concrete Drainage | 1500Mm Dia Chamber Ring (R) Opc | 5 | m | 90.94 | 454.7 | Concrete Drainage | 2018-08-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20460-001025 | 20460 | 2019-07-09 10:05 | Core | Material | Not on List | Not on List | 1 | ea | 360 | 360 | Office Supplies | 2019-07-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20462-001025 | 20462 | 2019-07-09 10:10 | Core | Material | Not on List | Not on List | 6 | ea | 180 | 1080 | Office Supplies | 2019-07-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-5250-00168 | 5250 | 2018-08-16 17:00 | Section 4 | Material | Concrete Drainage | 1500Mm Dia Chamber Ring (R) Opc | 5 | m | 80.51 | 402.55 | Concrete Drainage | 2018-08-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20390-001025 | 20390 | 2019-07-08 11:26 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 695 | 695 | Miscellaneous | 2019-07-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20084-001025 | 20084 | 2019-07-02 11:13 | Section 3 | Material | Kerbs | NULL | 45 | Each | 3.52 | 158.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20084-001025 | 20084 | 2019-07-02 11:13 | Section 3 | Material | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 32 | Each | 6 | 192 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20084-001025 | 20084 | 2019-07-02 11:13 | Section 3 | Material | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 48 | Each | 5.43 | 260.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20084-001025 | 20084 | 2019-07-02 11:13 | Section 3 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | NULL | Each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-08-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20084-001025 | 20084 | 2019-07-02 11:13 | Section 3 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 10 | Each | 125.94 | 1259.4 | Plastic Drainage | 2019-07-04 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-19758-001025 | 19758 | 2019-06-26 12:08 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 152.9 | 152.9 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5250-00168 | 5250 | 2018-08-16 17:00 | Section 4 | Material | Concrete Drainage | 1500Mm Dia Cover Slab Opc | 5 | Each | 142.82 | 714.1 | Concrete Drainage | 2018-08-21 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20502-001025 | 20502 | 2019-07-09 16:10 | Core | Material | Not on List | Not on List | 4 | Packs | 18 | 72 | Miscellaneous | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20502-001025 | 20502 | 2019-07-09 16:10 | Core | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Miscellaneous | 2019-07-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20473-001025 | 20473 | 2019-07-09 11:41 | Core | Material | NULL | NULL | 2 | Each | 18 | 36 | NULL | NULL | NULL | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20443-001025 | 20443 | 2019-07-09 08:38 | Section 4 | Material | NULL | NULL | 1 | Each | 301.79 | 301.79 | NULL | NULL | NULL | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5276-00175 | 5276 | 2018-08-17 09:10 | Section 4 | Material | Plastic Drainage | P/Pipe 600Mm Ridgidrain Seal | 12 | Each | 26.1 | 313.2 | Plastic Drainage | 2018-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-17457-001025 | 17457 | 2019-05-15 12:57 | Section 3 | Material | Not on List | Not on List | 1 | ea | 105.15 | 105.15 | Miscellaneous | 2019-05-24 | Gate D - 1339643 - BN10 Via Main Compound Entrance | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20476-001025 | 20476 | 2019-07-09 12:27 | Section 4 | Material | NULL | NULL | 1 | Each | 966.87 | 966.87 | NULL | NULL | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20303-001025 | 20303 | 2019-07-05 13:46 | Section 4 | Material | Not on List | Not on List | 16 | EA | 47.89 | 766.24 | Miscellaneous | 2019-07-11 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5276-00175 | 5276 | 2018-08-17 09:10 | Section 4 | Material | Not on List | NULL | 12 | Each | 292.07 | 3504.84 | Plastic Drainage | 2018-08-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20304-001025 | 20304 | 2019-07-05 13:52 | Section 4 | Material | Not on List | Not on List | 10 | EA | 54 | 540 | Rebar and Mesh | 2019-07-11 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20525-001025 | 20525 | 2019-07-10 08:02 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-07-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5294-00226 | 5294 | 2018-08-17 13:26 | Section 4 | Material | Misc | Not on List | 3 | Tonne | 538 | 1614 | Rebar and Mesh | 2018-08-30 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19641-001025 | 19641 | 2019-06-24 23:35 | Section 4 | Material | Not on List | Not on List | 1 | Number | 3892 | 3892 | Surveying Consumables | 2019-06-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19754-001025 | 19754 | 2019-06-26 11:50 | Section 4 | Material | Not on List | Not on List | 1 | Each | 2314.83 | 2314.83 | Miscellaneous | 2019-06-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19581-001025 | 19581 | 2019-06-24 08:25 | Section 1 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2019-07-10 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-19740-001025 | 19740 | 2019-06-26 09:39 | Section 1 | Material | Twinwall | Not on List | 3 | NULL | NULL | 0 | Concrete Accessories | 2019-07-01 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-20519-001025 | 20519 | 2019-07-09 19:25 | Section 2 | Material | Not on List | Not on List | 1 | Quotation | 26106.97 | 26106.97 | Miscellaneous | 2019-07-22 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20520-001025 | 20520 | 2019-07-09 19:32 | Section 2 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 10 | Each | 6.82 | 68.2 | Timber Products | 2019-07-12 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20520-001025 | 20520 | 2019-07-09 19:32 | Section 2 | Material | Not on List | Not on List | 3 | roll | NULL | 0 | Timber Products | 2019-07-12 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20520-001025 | 20520 | 2019-07-09 19:32 | Section 2 | Material | Not on List | Not on List | 2 | roll | NULL | 0 | Timber Products | 2019-07-12 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5142-0070 | 5142 | 2018-08-15 11:34 | Section 3 | Material | Concrete Drainage | Not on List | 3 | Each | 43.16 | 129.48 | Concrete Drainage | 2018-08-28 | Gate C - 1339698 - BN07 (Offord Rd) via Logistics Yard Access | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5321-00227 | 5321 | 2018-08-20 08:16 | Section 4 | Material | Not on List | NULL | 2 | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20520-001025 | 20520 | 2019-07-09 19:32 | Section 2 | Material | Not on List | Not on List | 200 | number | NULL | 0 | Timber Products | 2019-07-12 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20341-001025 | 20341 | 2019-07-06 15:32 | Section 6 | Material | Ducting | Not on List | 60 | M [= 10x6m lengths] | 0 | 0 | Miscellaneous | 2019-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20533-001025 | 20533 | 2019-07-10 09:12 | Section 3 | Material | Twinwall | Polypipe 450mm Ridgidrain 6m Unperf + Coupler (346368) | 12 | Each | 125.94 | 1511.28 | Plastic Drainage | 2019-07-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20484-001025 | 20484 | 2019-07-09 13:50 | Section 3 | Material | Aggregate | 6G | 160 | Tonnes | 32.9 | 5264 | Aggregate | 2019-07-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20227-001025 | 20227 | 2019-07-04 12:56 | Section 4 | Material | Not on List | Not on List | 50 | Each | 43.39 | 2169.5 | Miscellaneous | 2019-07-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20227-001025 | 20227 | 2019-07-04 12:56 | Section 4 | Material | NULL | Not on List | 1 | Each | 550 | 550 | Miscellaneous | 2019-07-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20475-001025 | 20475 | 2019-07-09 12:04 | Section 3 | Material | Not on List | Not on List | 30 | Roll | 26.25 | 787.5 | Geotextiles | 2019-07-12 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20441-001025 | 20441 | 2019-07-09 08:07 | Section 4 | Material | NULL | NULL | 400 | Each | 3.52 | 1408 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5323 | 5323 | 2018-08-20 08:32 | Section 4 | Material | Not on List | NULL | 2 | NULL | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20441-001025 | 20441 | 2019-07-09 08:07 | Section 4 | Material | NULL | NULL | 1 | Each | 41.8 | 41.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20441-001025 | 20441 | 2019-07-09 08:07 | Section 4 | Material | NULL | NULL | 1 | Each | 30 | 30 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-07-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20529-001025 | 20529 | 2019-07-10 08:08 | Section 3 | Material | Twinwall | Not on List | 1 | ea | 167.88 | 167.88 | Plastic Drainage | 2019-07-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20529-001025 | 20529 | 2019-07-10 08:08 | Section 3 | Material | Twinwall | Not on List | 1 | ea | 199.68 | 199.68 | Plastic Drainage | 2019-07-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20556-001025 | 20556 | 2019-07-10 14:07 | Section 6 | Material | Not on List | Not on List | 1 | EACH | 166.25 | 166 | Miscellaneous | 2019-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20558-001025 | 20558 | 2019-07-10 14:08 | Section 3 | Material | Not on List | Not on List | 1 | EACH | 2401.75 | 2402 | Miscellaneous | 2019-07-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 104 - Site Transport | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20559-001025 | 20559 | 2019-07-10 14:12 | Section 1 | Material | Not on List | Not on List | 1 | each | 398.75 | 399 | Miscellaneous | 2019-07-10 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-20560-001025 | 20560 | 2019-07-10 14:14 | Section 5 | Material | Not on List | Not on List | 1 | each | 162.5 | 163 | Miscellaneous | 2019-07-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-5324 | 5324 | 2018-08-20 08:36 | Section 4 | Material | Not on List | NULL | NULL | NULL | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20562-001025 | 20562 | 2019-07-10 14:18 | Section 2 | Material | Not on List | Not on List | 1 | each | 3310.75 | 3311 | Miscellaneous | 2019-07-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20563-001025 | 20563 | 2019-07-10 14:06 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20563-001025 | 20563 | 2019-07-10 14:06 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20563-001025 | 20563 | 2019-07-10 14:06 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20563-001025 | 20563 | 2019-07-10 14:06 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-07-12 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-20453-001025 | 20453 | 2019-07-09 09:12 | Section 4 | Material | Not on List | Not on List | 2 | Number | 350 | 700 | Surveying Consumables | 2019-07-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20545-001025 | 20545 | 2019-07-10 11:24 | Section 6 | Material | Aggregate | Class 1A | 2000 | Tonnes | 12.5 | 25000 | Aggregate | 2019-07-11 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | NULL | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-5377-00248 | 5377 | 2018-08-20 16:25 | Section 4 | Material | Not on List | Not on List | 150 | Each | NULL | 0 | Miscellaneous | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20576-001025 | 20576 | 2019-07-10 16:23 | Section 4 | Material | Not on List | Not on List | 1 | Test | NULL | 0 | Miscellaneous | 2019-07-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20457-001025 | 20457 | 2019-07-09 09:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 139.16 | 139.16 | Miscellaneous | 2019-07-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20457-001025 | 20457 | 2019-07-09 09:45 | Section 4 | Material | Not on List | Not on List | 1 | EA | 162.63 | 162.63 | Miscellaneous | 2019-07-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20577-001025 | 20577 | 2019-07-10 16:37 | Section 4 | Material | Combined Drainage | 835 Quicklock Grating (163148) | 1 | Each | 6.94 | 7 | Aggregate | 2019-07-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-5377-00248 | 5377 | 2018-08-20 16:25 | Section 4 | Material | Not on List | Not on List | 26 | Each | NULL | 0 | Miscellaneous | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20599-001025 | 20599 | 2019-07-11 08:28 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-07-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20602-001025 | 20602 | 2019-07-11 09:06 | Core | Material | Not on List | Not on List | 1 | number | 120 | 120 | Office Supplies | 2019-07-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19976-001025 | 19976 | 2019-07-01 08:15 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20603-001025 | 20603 | 2019-07-11 08:57 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-07-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 103 - Staff | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 150 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20222-001025 | 20222 | 2019-07-04 12:25 | Section 6 | Material | Not on List | Not on List | 1 | NULL | 257.49 | 257 | Miscellaneous | 2019-07-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | NULL | 112 - CCTV / Security (NOT TM CCTV) | IMO Queue | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 150 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5377-00248 | 5377 | 2018-08-20 16:25 | Section 4 | Material | NULL | NULL | 2 | Each | NULL | 0 | Miscellaneous | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 150 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 8635 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 8635 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 8635 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 45 | m | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 2590 | m | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 6035 | m2 | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 20 | m2 | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 527 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20604-001025 | 20604 | 2019-07-11 09:18 | Section 2 | Material | Not on List | Not on List | 527 | no | NULL | 0 | Concrete Accessories | 2019-07-17 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5377-00248 | 5377 | 2018-08-20 16:25 | Section 4 | Material | NULL | NULL | 2 | Each | NULL | 0 | Miscellaneous | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-19597-001025 | 19597 | 2019-06-24 10:22 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-20606-001025 | 20606 | 2019-07-11 10:24 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-07-12 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20572-001025 | 20572 | 2019-07-10 15:31 | Section 4 | Material | Aggregate | Class 6F | 270 | load | 95 | 25650 | Aggregate | 2019-07-15 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Not on List | Not on List | 450 | Load | 75 | 33750 | Miscellaneous | 2019-07-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Not on List | Not on List | 450 | Load | 75 | 33750 | Miscellaneous | 2019-07-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Not on List | Not on List | 450 | Load | 100 | 45000 | Miscellaneous | 2019-07-15 | RVP 414 - 1346360 - Off A14 Eastbound past Jcn with M11 Motorway | SC4C - Roadworks - Dry Drayton to Girton | 608 - Topsoil (place) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Not on List | Not on List | 1000 | Load | 95 | 95000 | Miscellaneous | 2019-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 602 - Excavation (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Not on List | Not on List | 500 | Load | 85 | 42500 | Miscellaneous | 2019-07-08 | RVP 403 - 1339621 - Borrow Pit 5 A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | NULL | Not on List | 500 | Load | 85 | 42500 | Miscellaneous | 2019-07-01 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 605 - Disposal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20268-001025 | 20268 | 2019-07-05 08:28 | Section 4 | Material | Aggregate | Class 6F | 270 | Tonnes | 95 | 25650 | Miscellaneous | 2019-07-15 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | SC4A - Roadworks - Swavesey to Robins Lane | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5377-00248 | 5377 | 2018-08-20 16:25 | Section 4 | Material | NULL | NULL | 2 | Each | NULL | 0 | Miscellaneous | 2018-08-29 | RVP 421 - 1340881 - A14 Westbound (West of Junction 28) | BN17 - Swavesey Junction | 2302 - Sealing of gaps | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20609-001025 | 20609 | 2019-07-11 11:15 | Section 4 | Material | Not on List | Not on List | 2 | each | NULL | 0 | Small Tools (Consumables) | 2019-07-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1502 - Trenches, Ducts and Chambers | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20283-001025 | 20283 | 2019-07-05 08:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 542 | 542 | Miscellaneous | 2019-07-09 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-19428-001025 | 19428 | 2019-06-20 10:34 | Section 3 | Material | Not on List | Not on List | 56 | bags | 6.5 | 364 | Builders Merchants (General) | 2019-06-25 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3B - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 688 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 688 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 688 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 1691 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 1691 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-20615-001025 | 20615 | 2019-07-11 12:32 | Section 2 | Material | Not on List | Not on List | 1691 | no | NULL | 0 | Concrete Accessories | 2019-07-15 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | 4 | Tonne | 538 | 2152 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20622-001025 | 20622 | 2019-07-11 14:01 | Section 4 | Material | Not on List | Not on List | 1 | EACH | NULL | 0 | Surveying Consumables | 2019-07-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 82 | EA | 29.95 | 2455.9 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5264-00210 | 5264 | 2018-08-16 20:27 | Section 4 | Material | Not on List | Not on List | NULL | Tonne | NULL | 0 | Rebar and Mesh | 2018-09-03 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-20499-001025 | 20499 | 2019-07-09 16:18 | Section 4 | Material | Combined Drainage | Not on List | 1 | EA | 29.5 | 29.5 | Plastic Drainage | 2019-07-15 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | NULL | 0 | Not Sure | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | NULL | 0 | Not Sure | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | NULL | 0 | Not Sure | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 16 | number | NULL | 0 | Not Sure | 2018-12-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 16 | no | 3.91 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9933-001025 | 9933 | 2018-12-04 08:30 | Section 4 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 15 | Each | 47.04 | 706 | Concrete Drainage | 2018-12-07 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9933-001025 | 9933 | 2018-12-04 08:30 | Section 4 | Material | Concrete Drainage | Not on List | 15 | NULL | NULL | 0 | Concrete Drainage | 2018-12-07 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9945-001025 | 9945 | 2018-12-04 10:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-12-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9868-001025 | 9868 | 2018-12-03 08:52 | Section 4 | Material | Not on List | Not on List | 10 | 50m Length | 145 | 1450 | Not Sure | 2018-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9868-001025 | 9868 | 2018-12-03 08:52 | Section 4 | Material | Not on List | Not on List | 20 | Each | 1.24 | 24.8 | Not Sure | 2018-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9868-001025 | 9868 | 2018-12-03 08:52 | Section 4 | Material | NULL | Not on List | 20 | Each | 1.09 | 21.8 | Not Sure | 2018-12-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9957-001025 | 9957 | 2018-12-04 15:05 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-12-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-5080-0028 | 5080 | 2018-08-14 15:00 | Section 4 | Material | Misc | Not on List | 2 | Box of 50 | 45.05 | 0 | Concrete Accessories | 2018-08-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9963-001025 | 9963 | 2018-12-04 16:07 | Section 3 | Material | Not on List | Not on List | 350 | 25kg Bags | NULL | 0 | Builders Merchants (General) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9966-001025 | 9966 | 2018-12-04 16:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-12-06 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 70 | Each | 26.09 | 1826.3 | Plastic Drainage | 2018-12-06 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Seal (346385) | 100 | Each | 1.44 | 144 | Plastic Drainage | 2018-12-06 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | NULL | Polypipe 150mm Ridgidrain Coupler (878019) | 100 | Each | 2.92 | 292 | Plastic Drainage | 2018-12-06 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9692-001025 | 9692 | 2018-11-27 15:31 | Section 4 | Material | NULL | NULL | 2 | Each | 376.56 | 753.12 | Plastic Drainage | 2018-12-06 | RVP 413 - 1339629 - The Avenue Site A14 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9951-001025 | 9951 | 2018-12-04 11:34 | Section 4 | Material | Not on List | Not on List | 1 | each | 232.83 | 232.83 | Miscellaneous | 2018-12-06 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5397-00263 | 5397 | 2018-08-21 08:08 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | Small Tools (Consumables) | 2018-08-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9945-001025 | 9945 | 2018-12-04 10:22 | Section 3 | Material | Not on List | Not on List | 1 | ea | 1877.34 | 1877.34 | Damage Charges | 2018-12-05 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 507.3 | 507.3 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 1043.68 | 1043.68 | Small Tools (Consumables) | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9971-001025 | 9971 | 2018-12-04 17:30 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 156.32 | 156.32 | Janitorial | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9980-001025 | 9980 | 2018-12-05 10:14 | Section 4 | Material | Aggregate | 6F5 | 500 | Tonnes | 14.65 | 7325 | Aggregate | 2018-12-14 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9980-001025 | 9980 | 2018-12-05 10:14 | Section 4 | Material | Aggregate | 6F5 | 500 | Tonnes | 14.65 | 7325 | Aggregate | 2018-12-17 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9990-001025 | 9990 | 2018-12-05 12:27 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2018-12-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-9991-001025 | 9991 | 2018-12-05 12:28 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Timber Products | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9994-001025 | 9994 | 2018-12-05 13:06 | Section 4 | Material | Not on List | Not on List | 1 | Comission | 600 | 600 | Not Sure | 2018-12-07 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 122 | NULL | 60 | 7320 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 65 | 130 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 4 | NULL | 700 | 2800 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 36 | Tubes | NULL | 0 | Ductile Drainage | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3B - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Channle 1000mm (758898) | 100 | Each | 29.28 | 2928 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Channel 500mm (758908) | 20 | Each | 15.43 | 309 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Access Unit (947299) | 7 | Each | 30.32 | 212 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Dropper RH (758907) | 1 | Each | 27.56 | 28 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Dropper LH (758901) | 1 | Each | 27.56 | 28 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9996-001025 | 9996 | 2018-12-05 13:28 | Section 4 | Material | Combined Drainage | Kerb Drain 305 Inlet (947299) | 7 | Each | 7.59 | 53 | Concrete Drainage | 2018-12-10 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9997-001025 | 9997 | 2018-12-05 13:55 | Section 4 | Material | Not on List | Not on List | 1 | Annual Subsistence Charge | 1580 | 1580 | Not Sure | 2018-12-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | 6.05 | 121 | Not Sure | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | 13.92 | 278.4 | Not Sure | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | 5.9 | 118 | Not Sure | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 20 | number | 9.6 | 192 | Not Sure | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9908-001025 | 9908 | 2018-12-03 16:38 | Section 4 | Material | Not on List | Not on List | 16 | number | 23.15 | 370.4 | Not Sure | 2018-12-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN19 - Robins Lane Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10003-001025 | 10003 | 2018-12-05 14:25 | Section 3 | Material | Not on List | Not on List | 8 | EA | 25.48 | 204 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10003-001025 | 10003 | 2018-12-05 14:25 | Section 3 | Material | Not on List | Not on List | 12 | EA | 31.41 | 377 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10007-001025 | 10007 | 2018-12-05 13:50 | Section 3 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 6 | Each | 115.78 | 695 | Geotextiles | 2018-12-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10007-001025 | 10007 | 2018-12-05 13:50 | Section 3 | Material | Geotextile | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2018-12-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | BN16 - New Barns Lane Overbridge | 1601 - Piling and attendances | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 144 | NULL | NULL | 0 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 312 | NULL | NULL | 0 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 84 | NULL | NULL | 0 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10010-001025 | 10010 | 2018-12-05 16:26 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 144 | NULL | NULL | 0 | PPE | 2018-12-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10007-001025 | 10007 | 2018-12-05 13:50 | Section 3 | Material | NULL | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 6 | Each | 115.78 | 694.68 | Geotextiles | 2018-12-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10007-001025 | 10007 | 2018-12-05 13:50 | Section 3 | Material | NULL | Tensar TX160 4m x 75m (150563) | 10 | Each | 535 | 5350 | Geotextiles | 2018-12-17 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Buyer - Closed | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-10003-001025 | 10003 | 2018-12-05 14:25 | Section 3 | Material | Not on List | Not on List | 8 | EA | 25.48 | 203.84 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10003-001025 | 10003 | 2018-12-05 14:25 | Section 3 | Material | Not on List | Not on List | 12 | EA | 31.41 | 376.92 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 10 | no. | NULL | 0 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 100 | no. | NULL | 0 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10025-001025 | 10025 | 2018-12-06 08:36 | Section 3 | Material | Not on List | Not on List | 5 | bags | NULL | 0 | Miscellaneous | 2018-12-10 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | PLM3 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 122 | NULL | 60 | 7320 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 2 | NULL | 65 | 130 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 4 | NULL | 700 | 2800 | Ductile Drainage | 2019-01-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-9995-001025 | 9995 | 2018-12-05 11:53 | Section 3 | Material | Not on List | Not on List | 36 | Tubes | 4.55 | 163.8 | Ductile Drainage | 2019-01-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3B - Roadworks | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10032-001025 | 10032 | 2018-12-06 09:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2018-12-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 55 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 110 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 140 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 160 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 320 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 55 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 110 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 40 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 12 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 35 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10036-001025 | 10036 | 2018-12-06 10:50 | Section 4 | Material | Not on List | Not on List | 35 | NULL | NULL | 0 | Plastic Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-5072-0027 | 5072 | 2018-08-14 14:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 72 | Each | NULL | 0 | Miscellaneous | 2018-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 60 | Each | 10.5 | 630 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 110 | Each | 1.84 | 202.4 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 300 | Each | 0.85 | 255 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 23.14 | 462.8 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 30 | Each | 3.38 | 101.4 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 60 | Each | 1.86 | 111.6 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 34.82 | 696.4 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 6.54 | 130.8 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | Each | 2.75 | 110 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | Each | 26.94 | 1077.6 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 39.7 | 794 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 44.41 | 888.2 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 120 | Each | 7.64 | 916.8 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 100 | Each | 7.64 | 764 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 100 | Each | 7.64 | 764 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 45 | Each | 15.71 | 706.95 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 45 | Each | 4.9 | 220.5 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 10 | Each | 19.72 | 197.2 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 40 | Each | 10.66 | 426.4 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | Not on List | Not on List | 20 | Each | 7.64 | 152.8 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | NULL | Not on List | 840 | Each | 0.85 | 714 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | NULL | Not on List | 40 | Each | 1.86 | 74.4 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9851-001025 | 9851 | 2018-11-30 17:34 | Section 4 | Material | NULL | Not on List | 40 | Each | 2.75 | 110 | Plastic Drainage | 2018-12-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-9963-001025 | 9963 | 2018-12-04 16:07 | Section 3 | Material | Not on List | Not on List | 350 | 25kg Bags | 14.43 | 5050.5 | Builders Merchants (General) | 2019-01-07 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | GN3A - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-10047-001025 | 10047 | 2018-12-06 13:06 | Section 4 | Material | Kerbs | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-10047-001025 | 10047 | 2018-12-06 13:06 | Section 4 | Material | Kerbs | Not on List | 2 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2018-12-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Requestor - Buyers Pass Back | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 2 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 3 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 8 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-10038-001025 | 10038 | 2018-12-06 11:20 | Section 4 | Material | Not on List | Not on List | 6 | NULL | NULL | 0 | Concrete Drainage | 2018-12-13 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 126 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 3 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 3 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 6 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 28 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 72 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 22 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 50 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 20 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 20 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16033-001025 | 16033 | 2019-04-17 06:31 | Section 5 | Material | NULL | Not on List | 50 | No | NULL | 0 | Plastic Drainage | 2019-04-25 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15629-001025 | 15629 | 2019-04-10 14:53 | Section 3 | Material | Not on List | Not on List | 10 | ea | 150 | 1500 | Miscellaneous | 2019-04-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | SC3A - Roadworks | 1503 - Cables, Joints & Terminations | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15848-001025 | 15848 | 2019-04-15 11:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | number | 268.91 | 1075.64 | Miscellaneous | 2019-04-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15848-001025 | 15848 | 2019-04-15 11:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | number | 18.94 | 75.76 | Miscellaneous | 2019-04-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15848-001025 | 15848 | 2019-04-15 11:56 | Core | Material | PPE, Small Tools and Consumables | Not on List | 4 | number | 19.5 | 78 | Miscellaneous | 2019-04-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16420-001025 | 16420 | 2019-04-25 15:32 | Core | Material | Not on List | Not on List | 1 | £ | 2820 | 2820 | Miscellaneous | 2019-04-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16304-001025 | 16304 | 2019-04-24 11:59 | Section 4 | Material | NULL | Polypipe 110mm x 50m Ridgiduct Coil Orange S/L (877804) | 2 | Each | 113.44 | 226.88 | Builders Merchants (General) | 2019-04-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16304-001025 | 16304 | 2019-04-24 11:59 | Section 4 | Material | Not on List | Not on List | 10 | rolls | 11.51 | 115.1 | Builders Merchants (General) | 2019-04-26 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4C - Gantry structures | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16395-001025 | 16395 | 2019-04-25 10:20 | Section 4 | Material | Waste Management | Metal - Roll On Roll Off 40 cubic yard | 1 | Each | 95 | 95 | Waste (Recycling) | 2019-04-25 | RVP 420 - A14 Eastbound - Opposite Crematorium | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16433-001025 | 16433 | 2019-04-25 14:35 | Section 6 | Material | Signage | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16433-001025 | 16433 | 2019-04-25 14:35 | Section 6 | Material | Signage | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1201 - Traffic Signs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-16446-001025 | 16446 | 2019-04-25 15:24 | Section 3 | Material | PPE, Small Tools and Consumables | Cone Traffic Contractor Thermoplastic 750mm C/W Sleeve (204055) | 400 | Each | 3.04 | 1216 | Miscellaneous | 2019-04-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15938-001025 | 15938 | 2019-04-16 11:49 | Section 4 | Material | Not on List | Not on List | 3 | Each | 191.58 | 574.74 | Miscellaneous | 2019-04-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15938-001025 | 15938 | 2019-04-16 11:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 175.6 | 175.6 | Miscellaneous | 2019-04-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15938-001025 | 15938 | 2019-04-16 11:49 | Section 4 | Material | Not on List | Not on List | 1 | Each | 71.98 | 71.98 | Miscellaneous | 2019-04-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15938-001025 | 15938 | 2019-04-16 11:49 | Section 4 | Material | Not on List | Not on List | 2 | Each | 79.86 | 159.72 | Miscellaneous | 2019-04-30 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6337-00671 | 6337 | 2018-09-11 14:42 | Section 4 | Material | Not on List | Not on List | 10 | u | NULL | 0 | Rebar and Mesh | 2018-09-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16464-001025 | 16464 | 2019-04-26 08:53 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 24.65 | 123.25 | Miscellaneous | 2019-05-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16464-001025 | 16464 | 2019-04-26 08:53 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 5 | ea | 24.65 | 123.25 | Miscellaneous | 2019-05-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16419-001025 | 16419 | 2019-04-25 14:45 | Section 3 | Material | Not on List | Not on List | 100 | NULL | 5.3 | 530 | Miscellaneous | 2019-04-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16419-001025 | 16419 | 2019-04-25 14:45 | Section 3 | Material | Not on List | Not on List | 100 | NULL | 2.18 | 218 | Miscellaneous | 2019-04-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16419-001025 | 16419 | 2019-04-25 14:45 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 757.4 | 757.4 | Small Tools (Consumables) | 2019-04-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16476-001025 | 16476 | 2019-04-26 10:51 | Section 3 | Material | Not on List | Not on List | 100000 | Litres | 1 | 100000 | Gas Oil | 2019-04-29 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16342-001025 | 16342 | 2019-04-24 15:47 | Core | Material | Not on List | Not on List | 1 | NULL | 670 | 670 | Miscellaneous | 2019-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 25 | Each | 8.55 | 214 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 25 | Each | 8.55 | 214 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | ATG 44-3745 MaxiCut Ultra Lightweight Cut Level 5 Nitrile Palm Coated Glove (304192) | 25 | Each | 8.55 | 214 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 5 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 4 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Paint Roller And Tray Set 9" Rskit1 (704256) | 20 | Each | 3.42 | 68 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Roller Paint Final Task 9" Power Stripe Kit 16509020 (704250) | 5 | Each | 12.32 | 62 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 15 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Each | NULL | 0 | PPE | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-6255-00648 | 6255 | 2018-09-10 10:06 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 144 | Each | 6.29 | 905.76 | Miscellaneous | 2018-09-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 10 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Shovel No2 Taper Mouth Insulated Yd Handle - Spartan Xt (762641) | 5 | Each | 36.86 | 184 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Broom 11.5" Natural Fibre Bracketed 48" X 15/16" Handle (502213) | 15 | Each | 2.23 | 33 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Respirator Disposable 3m 8833 Ffp3 Valved Box Of 10 (292498) | 30 | Each | 33.81 | 1014 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Red (742163) | 20 | Each | 6.7 | 134 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Whipcheck End 1/2" To 1 1/4 (850028) | 7 | Each | 5.25 | 37 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Plant Nappy 1000mm X 685mm All Blue (600200) | 3 | Each | 101.96 | 306 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16487-001025 | 16487 | 2019-04-26 11:49 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 3 | Each | NULL | 0 | Small Tools (Consumables) | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16413-001025 | 16413 | 2019-04-23 16:19 | Section 4 | Material | Not on List | Not on List | 40 | Each | 47.89 | 1915.6 | Builders Merchants (General) | 2019-04-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16413-001025 | 16413 | 2019-04-23 16:19 | Section 4 | Material | Not on List | Not on List | 8 | Each | 47.89 | 383.12 | Builders Merchants (General) | 2019-04-30 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1502 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6355-00675 | 6355 | 2018-09-11 16:59 | Section 4 | Material | Not on List | Not on List | 3.74 | Tonnes | 287.7 | 1076 | Reinforcement | 2018-09-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15762-001025 | 15762 | 2019-04-12 11:58 | Core | Material | Not on List | Not on List | 30 | Each | 12.76 | 382.8 | Miscellaneous | 2019-04-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16330-001025 | 16330 | 2019-04-24 15:37 | Core | Material | Not on List | Not on List | 1 | Each | 70 | 70 | Miscellaneous | 2019-05-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16330-001025 | 16330 | 2019-04-24 15:37 | Core | Material | Not on List | NULL | 5 | Each | 5 | 25 | Miscellaneous | 2019-04-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16329-001025 | 16329 | 2019-04-24 15:31 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-05-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16534-001025 | 16534 | 2019-04-29 07:11 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-30 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16536-001025 | 16536 | 2019-04-29 07:19 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-6307 | 6307 | 2018-09-11 09:04 | Section 4 | Material | Not on List | Not on List | 48 | NULL | NULL | 0 | Fixings and Fasteners | 2018-09-12 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN21 - Bar Hill Junction East Bridge | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16538-001025 | 16538 | 2019-04-29 07:23 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-04-30 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-16557-001025 | 16557 | 2019-04-29 09:54 | Core | Material | Not on List | Not on List | 1 | number | 303.8 | 304 | Office Supplies | 2019-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16557-001025 | 16557 | 2019-04-29 09:54 | Core | Material | Not on List | Not on List | 1 | number | NULL | 0 | Office Supplies | 2019-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16558-001025 | 16558 | 2019-04-29 10:03 | Section 5 | Material | Not on List | Not on List | 1 | number | 10556.5 | 10557 | Miscellaneous | 2019-04-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-16558-001025 | 16558 | 2019-04-29 10:03 | Section 5 | Material | Not on List | Not on List | 1 | number | 7916.71 | 7917 | Miscellaneous | 2019-04-29 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 2337.11 | 2337.11 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 7016.34 | 7016.34 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-6355 | 6355 | 2018-09-11 16:59 | Section 4 | Material | Not on List | Not on List | 3.74 | Tonnes | 287.7 | 1076 | Reinforcement | 2018-09-24 | RVP 415 - 1339630 - Girton Underpass Huntingdon Rd A1307 | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 1379.56 | 1379.56 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 1286.5 | 1286.5 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 7016.34 | 7016.34 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 1026.67 | 1026.67 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 831.27 | 831.27 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 3207.03 | 3207.03 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-15674-001025 | 15674 | 2019-04-11 10:50 | Core | Material | Not on List | Not on List | 1 | ea | 8534.53 | 8534.53 | Training | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 3376 | ea | 22 | 74272 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 35 | ea | 35 | 1225 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 19 | ea | 17 | 323 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6254-00647 | 6254 | 2018-09-10 09:58 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | EAch | 1844.62 | 1844.62 | Small Tools (Consumables) | 2018-09-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 531 | ea | 29 | 15399 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 1 | ea | 58 | 58 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 1 | ea | 32 | 32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 3892 | EA | 23 | 89516 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 51 | ea | 355 | 18105 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 37 | ea | 279 | 10323 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 30 | ea | 125 | 3750 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 1 | ea | 100 | 100 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 3 | ea | 100 | 300 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | Not on List | Not on List | 37 | ea | 100 | 3700 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16359-001025 | 16359 | 2019-04-24 17:40 | Section 4 | Material | NULL | Not on List | 28 | ea | 30 | 840 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-05-13 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 9 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 4 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 9 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 2 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 1 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 10 | Cartons | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 40 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 25 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-16563-001025 | 16563 | 2019-04-29 08:43 | Section 5 | Material | Concrete Drainage | Not on List | 20 | No | NULL | 0 | Concrete Drainage | 2019-05-06 | EB5/12 Stockyard Access - 1356566 - A14 Eastbound, On Left between Jcn 32 - 33 | SEC5 - Roadworks | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-15447-001025 | 15447 | 2019-04-08 12:23 | Section 4 | Material | Not on List | Not on List | 500 | Shims | NULL | 0 | Fixings and Fasteners | 2019-04-11 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-15447-001025 | 15447 | 2019-04-08 12:23 | Section 4 | Material | Not on List | Not on List | 500 | Shims | NULL | 0 | Fixings and Fasteners | 2019-04-11 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-16474-001025 | 16474 | 2019-04-26 10:32 | Section 3 | Material | Not on List | Not on List | 500 | Number | 80 | 40000 | Aggregate | 2019-04-29 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-15709-001025 | 15709 | 2019-04-11 16:16 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | each | 503 | 503 | Laboratory Equipment / Certification | 2019-04-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-16565-001025 | 16565 | 2019-04-29 12:51 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2869.68 | 2870 | PPE | 2019-05-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-12041-001025 | 12041 | 2019-02-07 09:06 | Section 2 | Material | Not on List | Not on List | 6 | Units | NULL | 0 | Plastic Drainage | 2019-02-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12042-001025 | 12042 | 2019-02-07 09:19 | Section 2 | Material | Saint Gobain Castings | 454x454x100 D400 Watershed GG&F (257790) | 25 | Each | 63.84 | 1596 | Builders Merchants (General) | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12044-001025 | 12044 | 2019-02-07 10:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11905-001025 | 11905 | 2019-02-05 07:41 | Section 2 | Material | Misc | NULL | 1 | NULL | 487.54 | 487.54 | Miscellaneous | 2019-02-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | PPE | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Janitorial | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12055-001025 | 12055 | 2019-02-07 12:32 | Section 2 | Material | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1158 | Geotextiles | 2019-02-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 606 - Import | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11923-001025 | 11923 | 2019-02-05 10:18 | Section 2 | Material | Not on List | Not on List | 1 | EA | 400 | 400 | Miscellaneous | 2019-02-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs Splayed 45deg 125x255 (898227) | 100 | Meters | 4.59 | 459 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 40 | Meters | 6 | 240 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 1 | Each | 11.94 | 11.94 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 200 | Meter | 3.52 | 704 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs 125x255 HB External Radius (947297) | 20 | Meter | 5.43 | 108.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 3 | Each | 7.68 | 23.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 3 | Each | 7.68 | 23.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Concrete Flat Top Edging 50x150x915 (805282) | 600 | Meter | 1.5 | 900 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11989-001025 | 11989 | 2019-02-06 07:15 | Section 2 | Material | NULL | Transition Kerbs 125x255 (947297) | 1 | Each | 10.08 | 10.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-02-11 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | NULL | Building Sand Bulk Bag (938155) | 6 | Each | 32.74 | 196.44 | Concrete Drainage | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | NULL | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.56 | 142.4 | Concrete Drainage | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | NULL | Not on List | 20 | Unit | 13.95 | 279 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12018-001025 | 12018 | 2019-02-06 16:02 | Section 2 | Material | NULL | Not on List | 40 | Tubs | 14.48 | 579.2 | Concrete Accessories | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11927-001025 | 11927 | 2019-02-05 10:49 | Section 4 | Material | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11927-001025 | 11927 | 2019-02-05 10:49 | Section 4 | Material | Not on List | Not on List | 10 | NULL | NULL | 0 | Concrete Accessories | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11929-001025 | 11929 | 2019-02-05 11:01 | Section 4 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Plastic Drainage | 2019-02-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12064-001025 | 12064 | 2019-02-07 14:43 | Section 2 | Material | Not on List | Not on List | 1050 | meters | NULL | 0 | Rebar and Mesh | 2019-02-18 | Gate 2 - 1339617 - BN02 East & BN27, via Gate 2, A1 Layby Southbound Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12064-001025 | 12064 | 2019-02-07 14:43 | Section 2 | Material | Not on List | Not on List | 1050 | meters | NULL | 0 | Rebar and Mesh | 2019-02-18 | Gate 2 - 1339617 - BN02 East & BN27, via Gate 2, A1 Layby Southbound Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12064-001025 | 12064 | 2019-02-07 14:43 | Section 2 | Material | Not on List | Not on List | 420 | meters | NULL | 0 | Rebar and Mesh | 2019-02-18 | Gate 2 - 1339617 - BN02 East & BN27, via Gate 2, A1 Layby Southbound Brampton | BN27 - A14/A1 Link Overbridge | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12022-001025 | 12022 | 2019-02-06 17:10 | Section 2 | Material | Aggregate | Type 1 | 9400 | Tonnes | 16 | 150400 | Aggregate | 2019-02-06 | Gate 1 - 1339610 - Precast Yard via Gate 1, A1 Services Slip Northbound Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | NULL | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 65 | tonnes | NULL | 0 | Reinforcement | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 150 | tonnes | NULL | 0 | Reinforcement | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | CL4A - Structures (Culverts) 4A | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 35 | tonnes | NULL | 0 | Reinforcement | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN22 - Structure BN22 | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12066-001025 | 12066 | 2019-02-07 15:03 | Section 4 | Material | Not on List | Not on List | 50 | tonnes | NULL | 0 | Reinforcement | 2019-03-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN18 - Swavesey NMU Bridge | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 58.93 | 117.86 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 2 | Each | 81.84 | 163.68 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 20.65 | 20.65 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 27.81 | 27.81 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 327.87 | 327.87 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 237.86 | 237.86 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11946-001025 | 11946 | 2019-02-05 15:05 | Section 4 | Material | Not on List | Not on List | 1 | Each | 79.27 | 79.27 | Not Sure | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12078-001025 | 12078 | 2019-02-07 15:38 | Section 2 | Material | Bricks/Blocks | Not on List | 395 | m2 | NULL | 0 | Blocks and Bricks | 2019-02-11 | Gate 6 - 1350301 - Processing Plant, Buckden Road, PE19 5UH | SC2A - Roadworks - A1 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11783-001025 | 11783 | 2019-02-01 08:54 | Section 4 | Material | Not on List | Not on List | 1 | Each | 27.49 | 27.49 | Electrical | 2019-02-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12008-001025 | 12008 | 2019-02-06 14:18 | Section 4 | Material | Not on List | Not on List | 1 | Each | 440.75 | 440.75 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12081-001025 | 12081 | 2019-02-07 16:08 | Core | Material | Not on List | Not on List | 1 | number | 180 | 180 | Office Supplies | 2019-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | IMO - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11924-001025 | 11924 | 2019-02-05 10:07 | Section 2 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12006-001025 | 12006 | 2019-02-06 14:06 | Section 4 | Material | Not on List | Not on List | 50 | Each | 38.09 | 1904.5 | Concrete Drainage | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12006-001025 | 12006 | 2019-02-06 14:06 | Section 4 | Material | Not on List | Not on List | 10 | Each | 36 | 360 | Concrete Drainage | 2019-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12101-001025 | 12101 | 2019-02-07 17:37 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 643.99 | 644 | PPE | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12109-001025 | 12109 | 2019-02-08 07:20 | Section 2 | Material | Not on List | Not on List | 0.255 | Tonnes | 538 | 137 | Rebar and Mesh | 2019-02-14 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1704 - Reinforcement for Structures | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11995-001025 | 11995 | 2019-02-06 11:20 | Section 3 | Material | Not on List | Not on List | 1 | Ea | 28 | 28 | Miscellaneous | 2019-02-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Timber | 2440x1220x18mm Shuttering Ply (683573) | 14 | Each | 24.32 | 340 | Timber Products | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Not on List | Not on List | 1 | Drum | NULL | 0 | Concrete Accessories | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Not on List | Not on List | 1 | Drum | NULL | 0 | Concrete Accessories | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Not on List | Not on List | 20 | m | NULL | 0 | Concrete Accessories | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Timber | 47x100x4800mm Sawn Timber (206910) | 6 | Each | 5.82 | 35 | Timber Products | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12115-001025 | 12115 | 2019-02-08 07:37 | Section 2 | Material | Not on List | Not on List | 20 | Each | NULL | 0 | Concrete Accessories | 2019-02-15 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 540.59 | 540.59 | PPE | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 462.25 | 462.25 | Small Tools (Consumables) | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12053-001025 | 12053 | 2019-02-07 12:22 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 201.96 | 201.96 | Janitorial | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12120-001025 | 12120 | 2019-02-08 08:13 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Concrete Accessories | 2019-02-11 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12127-001025 | 12127 | 2019-02-08 08:48 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.5 | 150 | Surveying Consumables | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12042-001025 | 12042 | 2019-02-07 09:19 | Section 2 | Material | NULL | 454x454x100 D400 Watershed GG&F (257790) | 25 | Each | 63.84 | 1596 | Builders Merchants (General) | 2019-02-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12128-001025 | 12128 | 2019-02-08 09:43 | Core | Material | Not on List | Not on List | 1 | ea | 664 | 664 | Training | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12129-001025 | 12129 | 2019-02-08 10:01 | Section 4 | Material | Aggregate | Not on List | 9159.63 | ea | 5 | 45798 | Aggregate | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11933-001025 | 11933 | 2019-02-05 11:54 | Section 2 | Material | NULL | Not on List | 6 | pack | 21.25 | 127.5 | Timber Products | 2019-02-08 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11933-001025 | 11933 | 2019-02-05 11:54 | Section 2 | Material | NULL | Not on List | 4 | pack | 12.5 | 50 | Timber Products | 2019-02-08 | Gate 4 - 1339616 - Drainage Compound via GATE 4, A14 Westbound Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12131-001025 | 12131 | 2019-02-08 10:35 | Core | Material | Not on List | Not on List | 1 | ea | 970 | 970 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-12132-001025 | 12132 | 2019-02-08 10:54 | Section 4 | Material | Not on List | Not on List | 1 | number | 4950 | 4950 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 101 - Mob/Demob of Compounds | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11926-001025 | 11926 | 2019-02-05 10:39 | Section 2 | Material | Not on List | Not on List | 1 | each | 56 | 56 | Laboratory Equipment / Certification | 2019-02-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 603 - Processing | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12140-001025 | 12140 | 2019-02-08 10:51 | Section 4 | Material | Not on List | Not on List | 120 | tubes | 12 | 1440 | Blocks and Bricks | 2019-02-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12140-001025 | 12140 | 2019-02-08 10:51 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 60 | 60 | Blocks and Bricks | 2019-02-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11964-001025 | 11964 | 2019-02-05 17:05 | Section 2 | Material | Not on List | Not on List | 2 | No. | NULL | 0 | Fixings and Fasteners | 2019-02-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11842-001025 | 11842 | 2019-02-04 08:10 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 324.01 | 324.01 | Concrete Accessories | 2019-02-08 | Gate C - 1339702 - BN06 (East Coast Railway) Via Logistics Yard Access | BN16 - New Barns Lane Overbridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12045-001025 | 12045 | 2019-02-07 10:45 | Core | Material | Not on List | Not on List | 1 | ea | 1265.37 | 1265 | Training | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12007-001025 | 12007 | 2019-02-06 14:13 | Section 4 | Material | Not on List | Not on List | 100 | Each | 8.38 | 838 | Plastic Drainage | 2019-02-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12112-001025 | 12112 | 2019-02-08 07:43 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 653.1 | Each | 1 | 653.1 | Miscellaneous | 2019-02-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12155-001025 | 12155 | 2019-02-08 12:51 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 12 | each | 102 | 1224 | Tanks and Interceptors | 2019-02-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12156-001025 | 12156 | 2019-02-08 13:01 | Core | Material | Not on List | Not on List | 3 | number packs | 21.45 | 64 | Office Supplies | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | NULL
MREQ-12128-001025 | 12128 | 2019-02-08 09:43 | Core | Material | Not on List | Not on List | 1 | ea | 664 | 664 | Training | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12131-001025 | 12131 | 2019-02-08 10:35 | Core | Material | Not on List | Not on List | 1 | ea | 970 | 970 | Miscellaneous | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL
MREQ-11854-001025 | 11854 | 2019-02-04 11:49 | Section 4 | Material | Not on List | Not on List | 180 | ROLLS | 49.5 | 8910 | Concrete Accessories | 2019-02-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11854-001025 | 11854 | 2019-02-04 11:49 | Section 4 | Material | NULL | Not on List | 1 | Each | 650 | 650 | Concrete Accessories | 2019-02-13 | RVP 427 - 1350307 - Girton - Accessed through A14 W/B towards A428 (on slip road) | BN25 - Girton Interchange Bridge A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12133-001025 | 12133 | 2019-02-08 11:30 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1000 | Each | 1.07 | 1070 | Surveying Consumables | 2019-02-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12129-001025 | 12129 | 2019-02-08 10:01 | Section 4 | Material | Aggregate | Not on List | 9159.63 | ea | 5 | 45798.15 | Aggregate | 2019-02-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12140-001025 | 12140 | 2019-02-08 10:51 | Section 4 | Material | Not on List | Not on List | 120 | tubes | 12 | 1440 | Blocks and Bricks | 2019-02-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12140-001025 | 12140 | 2019-02-08 10:51 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 60 | 60 | Blocks and Bricks | 2019-02-07 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | BN23 - Structure BN23 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12127-001025 | 12127 | 2019-02-08 08:48 | Section 3 | Material | Not on List | Not on List | 60 | NULL | 2.5 | 150 | Surveying Consumables | 2019-02-12 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12217-001025 | 12217 | 2019-02-11 09:36 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | NULL
MREQ-12217-001025 | 12217 | 2019-02-11 09:36 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | NULL
MREQ-12219-001025 | 12219 | 2019-02-11 10:00 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 7548.8 | 7549 | Laboratory Equipment / Certification | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Commercial Approval | Yes - Approve | NULL | NULL
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 5 | no | 439 | 2195 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 2 | no | 95 | 190 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 1 | no | 95 | 95 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12035-001025 | 12035 | 2019-02-07 07:49 | Section 4 | Material | NULL | Not on List | 112 | Each | 4.95 | 554.4 | Builders Merchants (General) | 2019-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12078-001025 | 12078 | 2019-02-07 15:38 | Section 2 | Material | NULL | Not on List | 395 | m2 | NULL | 0 | Blocks and Bricks | 2019-02-11 | Gate 6 - 1350301 - Processing Plant, Buckden Road, PE19 5UH | SC2A - Roadworks - A1 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12078-001025 | 12078 | 2019-02-07 15:38 | Section 2 | Material | NULL | Not on List | 60 | number | 10 | 600 | NULL | NULL | Gate 6 - 1350301 - Processing Plant, Buckden Road, PE19 5UH | SC2A - Roadworks - A1 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12247-001025 | 12247 | 2019-02-11 15:21 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2019-02-14 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 502 - Chambers & Gullies | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12253-001025 | 12253 | 2019-02-11 16:05 | Section 3 | Material | Not on List | Not on List | 1 | EA | 2000 | 2000 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12254-001025 | 12254 | 2019-02-11 16:10 | Section 4 | Material | Not on List | Not on List | 1040 | hour | 21 | 21840 | Professional Services | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12257-001025 | 12257 | 2019-02-11 16:25 | Section 2 | Material | Not on List | Not on List | 15 | Bags | NULL | 0 | Concrete Accessories | 2019-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN27 - A14/A1 Link Overbridge | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12268-001025 | 12268 | 2019-02-11 18:34 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 160.57 | 161 | Damage Charges | 2019-02-13 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11751-001025 | 11751 | 2019-01-31 16:38 | Section 4 | Material | Not on List | Not on List | 5 | Each | 20 | 100 | Surveying Consumables | 2019-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-11903-001025 | 11903 | 2019-02-05 07:29 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 738.72 | 738.72 | Miscellaneous | 2019-02-07 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-11724-001025 | 11724 | 2019-01-31 13:00 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 675.34 | 675.34 | Miscellaneous | 2019-02-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12031-001025 | 12031 | 2019-02-07 06:55 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 320 | 320 | Miscellaneous | 2019-02-08 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - Buyers Group
MREQ-12278-001025 | 12278 | 2019-02-12 07:56 | Section 4 | Material | Not on List | Not on List | 13 | ea | NULL | 0 | Concrete Drainage | 2019-02-18 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | CL4B - Structures (Culverts) 4B | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12283-001025 | 12283 | 2019-02-12 08:21 | Section 2 | Material | Not on List | Not on List | 12 | Number | NULL | 0 | Fixings and Fasteners | 2019-02-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN03 - A1 Brampton Interchange Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-5346-00239 | 5346 | 2018-08-20 11:44 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 40 | Roll | 36.98 | 0 | Miscellaneous | 2018-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12287-001025 | 12287 | 2019-02-12 08:43 | Section 2 | Material | Not on List | Not on List | 8 | no | NULL | 0 | Concrete Accessories | 2019-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12287-001025 | 12287 | 2019-02-12 08:43 | Section 2 | Material | Not on List | Not on List | 4 | no | NULL | 0 | Concrete Accessories | 2019-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12289-001025 | 12289 | 2019-02-12 09:03 | Core | Material | Not on List | Not on List | 2 | each | 228 | 456 | Office Supplies | 2019-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-12293-001025 | 12293 | 2019-02-12 09:36 | Section 3 | Material | Not on List | Not on List | 250 | NULL | NULL | 0 | Timber Products | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 401 - Safety Barriers | Operations Rejected | No - Reject | NULL | REQ - Section 3 Buyers
MREQ-12268-001025 | 12268 | 2019-02-11 18:34 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 160.57 | 160.57 | Damage Charges | 2019-02-13 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12294-001025 | 12294 | 2019-02-12 09:49 | Section 3 | Material | Not on List | Not on List | 2000 | NULL | NULL | 0 | Miscellaneous | 2019-02-15 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3A - Roadworks | 401 - Safety Barriers | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12296-001025 | 12296 | 2019-02-12 10:04 | Core | Material | Not on List | Not on List | 1 | ea | 41504 | 41504 | Office Supplies | 2019-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-11611-001025 | 11611 | 2019-01-29 11:05 | Section 3 | Material | Concrete Drainage | Not on List | 2 | No. | 5698.22 | 11396.44 | Concrete Drainage | 2019-02-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3A - Structures (Culverts) 3A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-11713 | 11713 | 2019-01-31 11:57 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Set | NULL | 0 | Miscellaneous | 2019-01-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12300-001025 | 12300 | 2019-02-12 11:12 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 88.88 | 89 | Small Tools (Consumables) | 2019-02-14 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12254-001025 | 12254 | 2019-02-11 16:10 | Section 4 | Material | Not on List | Not on List | 1040 | hour | 21 | 21840 | Professional Services | 2019-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-12253-001025 | 12253 | 2019-02-11 16:05 | Section 3 | Material | Not on List | Not on List | 1 | EA | 2000 | 2000 | Miscellaneous | 2019-02-11 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12304-001025 | 12304 | 2019-02-12 12:01 | Section 2 | Material | Not on List | Not on List | 1 | Number | 253.66 | 254 | Surveying Consumables | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12304-001025 | 12304 | 2019-02-12 12:01 | Section 2 | Material | Not on List | Not on List | 1 | Number | 15.84 | 16 | Surveying Consumables | 2019-02-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 5 | no | 439 | 2195 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-12221-001025 | 12221 | 2019-02-11 10:06 | Section 3 | Material | Not on List | Not on List | 2 | no | 95 | 190 | Miscellaneous | 2019-02-15 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | GN3B - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28592-001025 | 28592 | 2020-01-28 14:44 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 691.37 | 691 | PPE | 2020-01-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28592-001025 | 28592 | 2020-01-28 14:44 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 272.7 | 273 | Janitorial | 2020-01-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28592-001025 | 28592 | 2020-01-28 14:44 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 203.43 | 203 | Small Tools (Consumables) | 2020-01-31 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-26797-001025 | 26797 | 2019-11-20 09:51 | Core | Material | Not on List | Not on List | 1 | NULL | 140 | 140 | Miscellaneous | 2019-11-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 107 - Fee based costs including insurance | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28597-001025 | 28597 | 2020-01-28 15:19 | Core | Material | Not on List | Not on List | 1 | NULL | 35000 | 35000 | Miscellaneous | 2020-01-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 153 - Temporary Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7397-001022 | 7397 | 2018-10-04 12:18 | Section 4 | Material | Not on List | Not on List | 2 | Each | 43.49 | 86.98 | Plastic Drainage | 2018-10-10 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28606-001025 | 28606 | 2020-01-28 19:39 | Section 4 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2020-01-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1502 - Trenches, Ducts and Chambers | Stores - Closed | NULL | Yes - Approve | REQ - Section 4 Buyers
MREQ-28558-001025 | 28558 | 2020-01-27 16:43 | Section 2 | Material | Not on List | Not on List | 5 | each | 78.5 | 392.5 | Builders Merchants (General) | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28614-001025 | 28614 | 2020-01-29 09:26 | Core | Material | Not on List | Not on List | 1 | Licence | 1950 | 1950 | Surveying Consumables | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7154-001020 | 7154 | 2018-09-28 13:07 | Section 4 | Material | Not on List | Not on List | 1 | Each | 494.73 | 494.73 | Professional Services | 2018-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2701 - Accommodation works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28633-001025 | 28633 | 2020-01-29 14:25 | Section 5 | Material | Timber | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28633-001025 | 28633 | 2020-01-29 14:25 | Section 5 | Material | Timber | Not on List | 50 | NULL | NULL | 0 | Timber Products | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7389-001022 | 7389 | 2018-10-04 11:28 | Section 4 | Material | NULL | Not on List | 2156 | M2 | 11.85 | 25548.6 | Blocks and Bricks | 2018-10-15 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28620-001025 | 28620 | 2020-01-29 10:08 | Section 4 | Material | Aggregate | Not on List | 60000 | ton | 5 | 300000 | Aggregate | 2020-01-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Bags | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 10 | Bags | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 10 | Bags | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 1 | Container | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 10 | Bags | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 6 | Packs | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7389-001022 | 7389 | 2018-10-04 11:28 | Section 4 | Material | NULL | NULL | 15 | Each | 30 | 450 | Blocks and Bricks | 2018-10-15 | RVP 411 - 1339640 - Dry Drayton Oakington Rd A14 J30 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28644-001025 | 28644 | 2020-01-29 14:38 | Section 5 | Material | Not on List | Not on List | 4 | Packs | NULL | 0 | Builders Merchants (General) | 2020-02-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE26 - King Hedges Bridge Modifications | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28603-001025 | 28603 | 2020-01-28 14:29 | Section 4 | Material | NULL | NULL | 1 | Each | 4681.16 | 4681.16 | Miscellaneous | 2020-01-31 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28649-001025 | 28649 | 2020-01-29 16:04 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 4 | NULL | NULL | 0 | Miscellaneous | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 1101 - Kerbs, Channels and Edgings | Operations Rejected | No - Reject | NULL | Req - S2 Buyers
MREQ-7415-001022 | 7415 | 2018-10-04 16:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 577.15 | 577.15 | Concrete Drainage | 2018-10-12 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28487-001025 | 28487 | 2020-01-24 10:15 | Section 4 | Material | Not on List | Not on List | 50 | Each | 50.69 | 2534.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28487-001025 | 28487 | 2020-01-24 10:15 | Section 4 | Material | Not on List | Not on List | 15 | Each | 158.78 | 2381.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28487-001025 | 28487 | 2020-01-24 10:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 75.46 | 75.46 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28487-001025 | 28487 | 2020-01-24 10:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 75.46 | 75.46 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28487-001025 | 28487 | 2020-01-24 10:15 | Section 4 | Material | Not on List | Not on List | 1 | Each | 115 | 115 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28579-001025 | 28579 | 2020-01-28 09:41 | Section 2 | Material | Concrete Drainage | Not on List | 60 | each | 0 | 0 | Builders Merchants (General) | 2020-01-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28270-001025 | 28270 | 2020-01-17 10:29 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28186-001025 | 28186 | 2020-01-15 15:05 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7415-001022 | 7415 | 2018-10-04 16:27 | Section 4 | Material | Not on List | Not on List | 8 | Each | 361.34 | 2890.72 | Concrete Drainage | 2018-10-12 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28657-001025 | 28657 | 2020-01-30 08:00 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 4 | ea | 30.24 | 120.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28657-001025 | 28657 | 2020-01-30 08:00 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 16 | ea | 1.62 | 25.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28657-001025 | 28657 | 2020-01-30 08:00 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | ea | 10.08 | 10.08 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28651-001025 | 28651 | 2020-01-30 07:31 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 4 | No | 30.24 | 120.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28651-001025 | 28651 | 2020-01-30 07:31 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 16 | No | 1.62 | 25.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28651-001025 | 28651 | 2020-01-30 07:31 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 2 | No | 10.08 | 20.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28650-001025 | 28650 | 2020-01-30 07:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 4 | No | 30.24 | 120.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28650-001025 | 28650 | 2020-01-30 07:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 18 | No | 1.62 | 29.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28650-001025 | 28650 | 2020-01-30 07:15 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 2 | No | 10.08 | 20.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28754-001025 | 28754 | 2020-02-01 09:52 | Section 5 | Material | Not on List | Not on List | 5 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-04 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7415-001022 | 7415 | 2018-10-04 16:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 1238.1 | 1238.1 | Concrete Drainage | 2018-10-12 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28778-001025 | 28778 | 2020-02-03 09:34 | Section 1 | Material | Not on List | Not on List | 20 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-02-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-28778-001025 | 28778 | 2020-02-03 09:34 | Section 1 | Material | Not on List | Not on List | 20 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-02-03 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-28778-001025 | 28778 | 2020-02-03 09:34 | Section 1 | Material | Not on List | Not on List | 25 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-02-03 | Gate 3 - 1339606 - Tophams Access Track A1 Northbound Alconbury | GN01 - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-7415-001022 | 7415 | 2018-10-04 16:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 534.53 | 534.53 | Concrete Drainage | 2018-10-12 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28786-001025 | 28786 | 2020-02-03 11:01 | Section 5 | Material | Not on List | Not on List | 20 | NULL | 12.43 | 249 | Miscellaneous | 2020-02-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28800-001025 | 28800 | 2020-02-03 14:38 | Section 5 | Material | Combined Drainage | Not on List | 400 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-06 | 1358004 - WB5/1- 1356557 - A14 Westbound, Works Access Junction 33 | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28801-001025 | 28801 | 2020-02-03 15:03 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28802-001025 | 28802 | 2020-02-03 14:53 | Section 5 | Material | Not on List | Not on List | 10 | bags | NULL | 0 | Builders Merchants (General) | 2020-02-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28802-001025 | 28802 | 2020-02-03 14:53 | Section 5 | Material | Not on List | Not on List | 40 | packs (600ml) | NULL | 0 | Builders Merchants (General) | 2020-02-06 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7415-001022 | 7415 | 2018-10-04 16:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 527.33 | 527.33 | Concrete Drainage | 2018-10-12 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28034-001025 | 28034 | 2020-01-10 11:45 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Each | 2467.72 | 2467.72 | Waste (General) | 2020-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28034-001025 | 28034 | 2020-01-10 11:45 | Section 4 | Material | Hazardous Waste | Not on List | 1 | Each | 805.14 | 805.14 | Waste (General) | 2020-01-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28781-001025 | 28781 | 2020-02-03 09:27 | Section 4 | Material | Not on List | Not on List | 55 | Each | 34 | 1870 | Ductile Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28781-001025 | 28781 | 2020-02-03 09:27 | Section 4 | Material | Not on List | Not on List | 10 | Each | 44.73 | 447.3 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28781-001025 | 28781 | 2020-02-03 09:27 | Section 4 | Material | Not on List | Not on List | 10 | Each | 24.33 | 243.3 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28781-001025 | 28781 | 2020-02-03 09:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 79.96 | 79.96 | Small Tools (Consumables) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28781-001025 | 28781 | 2020-02-03 09:27 | Section 4 | Material | Not on List | Not on List | 1 | Each | 15 | 15 | Plastic Drainage | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28812-001025 | 28812 | 2020-02-03 15:34 | Section 4 | Material | Not on List | Not on List | 20 | Number | NULL | 0 | Builders Merchants (General) | 2020-02-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 105 - Site Security | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28821-001025 | 28821 | 2020-02-04 08:36 | Core | Material | Not on List | Not on List | 1 | ea | 525 | 525 | Training | 2020-02-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | NULL | REQ - Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 8 | Each | 81.96 | 655.68 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28836-001025 | 28836 | 2020-02-04 11:40 | Core | Material | Not on List | Not on List | 4 | Number | 42.49 | 170 | Surveying Consumables | 2020-02-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-28847-001025 | 28847 | 2020-02-04 13:35 | Core | Material | Not on List | Not on List | 1 | number | 73.47 | 73 | Office Supplies | 2020-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Finance Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-28849-001025 | 28849 | 2020-02-04 14:13 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 8 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-02-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28616-001025 | 28616 | 2020-01-29 09:03 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28611-001025 | 28611 | 2020-01-29 08:16 | Section 4 | Material | Not on List | Not on List | 4182 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-01-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28635-001025 | 28635 | 2020-01-29 14:32 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28776-001025 | 28776 | 2020-02-03 09:16 | Section 6 | Material | Not on List | Not on List | 336 | m3 | 88.2 | 29635.2 | Ready Mixed Concrete | 2020-02-03 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28776-001025 | 28776 | 2020-02-03 09:16 | Section 6 | Material | Not on List | Not on List | 590 | m3 | 115.12 | 67920.8 | Ready Mixed Concrete | 2020-02-03 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | NULL | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-28776-001025 | 28776 | 2020-02-03 09:16 | Section 6 | Material | Not on List | Not on List | 1000 | m3 | 107.76 | 107760 | Ready Mixed Concrete | 2020-02-03 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 4 | Each | 61.48 | 245.92 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28779-001025 | 28779 | 2020-02-03 09:42 | Section 2 | Material | Not on List | Not on List | 20 | m3 | 76.5 | 1530 | Ready Mixed Concrete | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28779-001025 | 28779 | 2020-02-03 09:42 | Section 2 | Material | Not on List | Not on List | 30 | m3 | 87.25 | 2617.5 | Ready Mixed Concrete | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28779-001025 | 28779 | 2020-02-03 09:42 | Section 2 | Material | Not on List | Not on List | 30 | m3 | 107.76 | 3232.8 | Ready Mixed Concrete | 2020-02-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25001-001025 | 25001 | 2019-10-11 17:13 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 721.9 | 722 | Small Tools (Consumables) | 2019-10-16 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24886-001025 | 24886 | 2019-10-10 07:11 | Section 4 | Material | Not on List | Not on List | 15 | Each | 950 | 14250 | Miscellaneous | 2019-12-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24886-001025 | 24886 | 2019-10-10 07:11 | Section 4 | Material | Not on List | Not on List | 12 | Each | 718 | 8616 | Miscellaneous | 2019-12-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24886-001025 | 24886 | 2019-10-10 07:11 | Section 4 | Material | NULL | Not on List | 15 | Each | 120 | 1800 | Miscellaneous | 2019-12-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24886-001025 | 24886 | 2019-10-10 07:11 | Section 4 | Material | NULL | Not on List | 12 | Each | 110 | 1320 | Miscellaneous | 2019-12-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25010-001025 | 25010 | 2019-10-14 08:07 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7038-001008 | 7038 | 2018-09-26 15:49 | Section 4 | Material | Not on List | Not on List | 200 | Each | 0.18 | 36 | Fixings and Fasteners | 2018-10-01 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | GN4A - Gantry structures | 1805 - Cantilever Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25019-001025 | 25019 | 2019-10-14 09:02 | Core | Material | Not on List | Not on List | 1 | ea | 850 | 850 | Training | 2019-10-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25033-001025 | 25033 | 2019-10-14 10:04 | Section 5 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 96 | Each | 4.02 | 385.92 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 160 | Each | 3.03 | 484.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 390 | Each | 4.59 | 1790.1 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 384 | Each | 3.52 | 1351.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 432 | Each | 3.52 | 1520.64 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 32 | Each | 5.43 | 173.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 34 | Each | 5.43 | 184.62 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 4 | Each | 30 | 120 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24981-001025 | 24981 | 2019-10-11 11:53 | Section 4 | Material | NULL | NULL | 1 | Each | 55 | 55 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25036-001025 | 25036 | 2019-10-14 11:25 | Section 4 | Material | Not on List | Not on List | 1 | each | 126751.85 | 126751.85 | Gas Oil | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 602 - Excavation (excl topsoil) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6984-00752 | 6984 | 2018-09-25 16:57 | Section 3 | Material | Not on List | Not on List | 80 | 25m | 13.95 | 1116 | Miscellaneous | 2018-09-28 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25057-001025 | 25057 | 2019-10-14 14:48 | Section 5 | Material | Not on List | Not on List | 2 | Bundles (100l/m each) | 95 | 190 | Timber Products | 2019-10-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-25042-001025 | 25042 | 2019-10-14 13:15 | Section 4 | Material | NULL | NULL | 16 | Each | 7.96 | 127.36 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25042-001025 | 25042 | 2019-10-14 13:15 | Section 4 | Material | NULL | NULL | 16 | Each | 7.96 | 127.36 | Concrete Hard Landscaping (Kerbs, Slabs) | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25073-001025 | 25073 | 2019-10-14 16:28 | Core | Material | Not on List | Not on List | 1 | ea | 8750 | 8750 | Training | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25073-001025 | 25073 | 2019-10-14 16:28 | Core | Material | Not on List | Not on List | 1 | ea | 473.4 | 473 | Training | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25080-001025 | 25080 | 2019-10-14 17:12 | Section 5 | Material | Bagged | Building Sand Bulk Bag (938155) | 10 | Each | 32.74 | 327 | Builders Merchants (General) | 2019-10-16 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-25085-001025 | 25085 | 2019-10-14 17:47 | Section 4 | Material | Not on List | Not on List | 30 | NULL | NULL | 0 | Plastic Drainage | 2019-10-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25090-001025 | 25090 | 2019-10-15 07:17 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 1 | No | NULL | 0 | Small Tools (Consumables) | 2019-10-17 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25092-001025 | 25092 | 2019-10-15 07:46 | Core | Material | PPE, Small Tools and Consumables | Stake Marking Out Wooden 1200mm Nominal C.r.code Swcoc004463 (740904) | 50 | each | 1.07 | 54 | Surveying Consumables | 2019-10-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7012-00752 | 7012 | 2018-09-26 08:51 | Section 3 | Material | PPE, Small Tools and Consumables | Jalas Jupiter S3 Safety Boots (120104) | 3 | Each | 39.99 | 119.97 | PPE | 2018-10-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25088-001025 | 25088 | 2019-10-15 06:31 | Core | Material | PPE, Small Tools and Consumables | Not on List | 144 | each | 6.29 | 905.76 | Miscellaneous | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25106-001025 | 25106 | 2019-10-15 11:20 | Section 6 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25038-001025 | 25038 | 2019-10-14 11:40 | Section 4 | Material | Bricks/Blocks | Not on List | 2 | box | 468 | 936 | Blocks and Bricks | 2019-10-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25038-001025 | 25038 | 2019-10-14 11:40 | Section 4 | Material | Bricks/Blocks | Not on List | 1 | delivery | 275 | 275 | Blocks and Bricks | 2019-10-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN20 - Bar Hill Junction West Bridge | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25111-001025 | 25111 | 2019-10-15 12:47 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 283.9 | 284 | PPE | 2019-10-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25111-001025 | 25111 | 2019-10-15 12:47 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | Each | 597.9 | 598 | Small Tools (Consumables) | 2019-10-22 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25027-001025 | 25027 | 2019-10-14 09:33 | Section 3 | Material | Not on List | Not on List | 3 | ea | 88 | 264 | Miscellaneous | 2019-10-16 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24841-001025 | 24841 | 2019-10-09 12:40 | Core | Material | PPE, Small Tools and Consumables | NULL | 1 | EA | 205 | 205 | Laboratory Equipment / Certification | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7012-00752 | 7012 | 2018-09-26 08:51 | Section 3 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 164.43 | 164.43 | Small Tools (Consumables) | 2018-10-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24847-001025 | 24847 | 2019-10-09 13:09 | Core | Material | Not on List | NULL | 1 | SM | 606 | 606 | Miscellaneous | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24863-001025 | 24863 | 2019-10-09 15:23 | Core | Material | Not on List | NULL | 1 | SM | 200 | 200 | Laboratory Equipment / Certification | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24909-001025 | 24909 | 2019-10-10 10:46 | Core | Material | PPE, Small Tools and Consumables | NULL | 1 | EA | 506 | 506 | Laboratory Equipment / Certification | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24911-001025 | 24911 | 2019-10-10 11:14 | Core | Material | PPE, Small Tools and Consumables | NULL | 1 | SM | 356 | 356 | Laboratory Equipment / Certification | 2019-10-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25104-001025 | 25104 | 2019-10-15 10:38 | Core | Material | Not on List | Not on List | 9016.63 | NULL | 1 | 9016.63 | Professional Services | 2019-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 153 - Temporary Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-24992-001025 | 24992 | 2019-10-11 14:54 | Section 5 | Material | Aggregate | NULL | 6200 | MT | 21.65 | 134230 | Aggregate | 2019-10-15 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25045-001025 | 25045 | 2019-10-14 13:24 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1480.6 | Each | 1 | 1480.6 | PPE | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7012-00752 | 7012 | 2018-09-26 08:51 | Section 3 | Material | Not on List | Not on List | 1 | NULL | 158.66 | 158.66 | Janitorial | 2018-10-01 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24827-001025 | 24827 | 2019-10-09 09:11 | Core | Material | PPE, Small Tools and Consumables | Not on List | 566.52 | Each | 1 | 566.52 | Small Tools (Consumables) | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-7027-00753 | 7027 | 2018-09-26 14:01 | Section 3 | Material | Not on List | Not on List | 30 | Sheets | 9.44 | 283.2 | Concrete Drainage | 2018-10-01 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | CL3B - Structures (Culverts) 3B | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24819-001025 | 24819 | 2019-10-09 07:18 | Core | Material | Not on List | Not on List | 1 | Each | 984.64 | 984.64 | Miscellaneous | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-25149-001025 | 25149 | 2019-10-16 07:44 | Section 2 | Material | Kerbs | Not on List | 1 | ea | 1200 | 1200 | Ductile Drainage | 2019-10-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25149-001025 | 25149 | 2019-10-16 07:44 | Section 2 | Material | Kerbs | Not on List | 2 | ea | 2150 | 4300 | Ductile Drainage | 2019-10-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25149-001025 | 25149 | 2019-10-16 07:44 | Section 2 | Material | Kerbs | Not on List | 2 | ea | 2250 | 4500 | Ductile Drainage | 2019-10-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25149-001025 | 25149 | 2019-10-16 07:44 | Section 2 | Material | Kerbs | Not on List | 2 | ea | 2350 | 4700 | Ductile Drainage | 2019-10-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25196-001025 | 25196 | 2019-10-16 10:59 | Section 4 | Material | Not on List | Not on List | 1 | each | NULL | 0 | Miscellaneous | 2019-10-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Request - Ops Pass Back | No - Pass Back | NULL | REQ - Section 4 Buyers
MREQ-25220-001025 | 25220 | 2019-10-16 12:06 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25096-001025 | 25096 | 2019-10-15 08:37 | Section 4 | Material | Not on List | Not on List | 1 | Each | 159 | 159 | Miscellaneous | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25129-001025 | 25129 | 2019-10-15 15:52 | Section 4 | Material | Not on List | Not on List | 12 | bags | 32.1 | 385.2 | Builders Merchants (General) | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25129-001025 | 25129 | 2019-10-15 15:52 | Section 4 | Material | Not on List | Not on List | 1 | ea | 55 | 55 | Builders Merchants (General) | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2101 - Bearings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24890-001025 | 24890 | 2019-10-10 07:51 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 4000 | Each | 0.37 | 1480 | Miscellaneous | 2019-10-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25224-001025 | 25224 | 2019-10-16 12:30 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | CPM 1050 Cover Slab 600x600 Opening (989583) | 40 | Each | 47.04 | 1881.6 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24987-001025 | 24987 | 2019-10-11 14:00 | Section 4 | Material | Not on List | Not on List | 100 | Each | 5.8 | 580 | Miscellaneous | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25145-001025 | 25145 | 2019-10-16 07:01 | Section 2 | Material | Not on List | Not on List | 14 | no. | 18.49 | 258.86 | Concrete Accessories | 2019-10-18 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-24973-001025 | 24973 | 2019-10-11 10:02 | Section 4 | Material | Not on List | Not on List | 500 | Each | 2.18 | 1090 | Miscellaneous | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24973-001025 | 24973 | 2019-10-11 10:02 | Section 4 | Material | Not on List | Not on List | 500 | Each | 3.38 | 1690 | Miscellaneous | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24973-001025 | 24973 | 2019-10-11 10:02 | Section 4 | Material | Not on List | Not on List | 160 | Each | 5.3 | 848 | Miscellaneous | 2019-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24912-001025 | 24912 | 2019-10-10 11:20 | Section 4 | Material | Not on List | Not on List | 200 | NULL | 0.8 | 160 | Surveying Consumables | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25020-001025 | 25020 | 2019-10-14 09:02 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 20 | NULL | 34.19 | 683.8 | PPE | 2019-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25117-001025 | 25117 | 2019-10-15 14:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 25 | NULL | 2.07 | 51.75 | Small Tools (Consumables) | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 12 | Each | 59.17 | 710.04 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25117-001025 | 25117 | 2019-10-15 14:11 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 12 | NULL | 3.17 | 38.04 | Small Tools (Consumables) | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24508-001025 | 24508 | 2019-10-02 10:37 | Section 4 | Material | Not on List | Not on List | 1 | EACH | 2835.5 | 2835.5 | Miscellaneous | 2019-10-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24862-001025 | 24862 | 2019-10-09 15:03 | Section 4 | Material | Not on List | Not on List | 1 | NULL | 246.88 | 246.88 | Miscellaneous | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24916-001025 | 24916 | 2019-10-10 12:57 | Section 4 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25267-001025 | 25267 | 2019-10-16 15:54 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2019-10-17 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-24790-001025 | 24790 | 2019-10-08 15:09 | Section 4 | Material | Not on List | Not on List | 50 | NULL | 0.98 | 49 | Small Tools (Consumables) | 2019-10-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25309-001025 | 25309 | 2019-10-17 09:07 | Section 2 | Material | Not on List | Not on List | 1000 | Flags | NULL | 0 | Surveying Consumables | 2019-10-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Request - Commercial Pass Back | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 750 D/S (913226) | 8 | Each | 61.48 | 491.84 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25128-001025 | 25128 | 2019-10-15 15:19 | Section 5 | Material | Not on List | NULL | 1 | SM | 988.98 | 988.98 | Miscellaneous | 2019-10-08 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25198-001025 | 25198 | 2019-10-16 10:59 | Section 5 | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25110-001025 | 25110 | 2019-10-15 11:04 | Section 4 | Material | Not on List | Not on List | 10 | Number | 81.27 | 812.7 | Surveying Consumables | 2019-10-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25098-001025 | 25098 | 2019-10-15 09:38 | Section 4 | Material | Concrete Drainage | Not on List | 20 | Each | 48.92 | 978.4 | Concrete Drainage | 2019-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25098-001025 | 25098 | 2019-10-15 09:38 | Section 4 | Material | Concrete Drainage | Not on List | 30 | EACH | 70.91 | 2127.3 | Concrete Drainage | 2019-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25098-001025 | 25098 | 2019-10-15 09:38 | Section 4 | Material | Concrete Drainage | Not on List | 20 | EACH | 52.95 | 1059 | Concrete Drainage | 2019-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25098-001025 | 25098 | 2019-10-15 09:38 | Section 4 | Material | Concrete Drainage | Not on List | 20 | EACH | 44.88 | 897.6 | Concrete Drainage | 2019-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25325-001025 | 25325 | 2019-10-17 12:24 | Section 4 | Material | Combined Drainage | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2019-10-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Operations Rejected | No - Reject | NULL | REQ - Section 4 Buyers
MREQ-4997-0011 | 4997 | 2018-08-13 15:45 | Section 4 | Material | Not on List | Not on List | 9 | 1 | 1 | 9 | Not Sure | 2018-08-15 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 8 | Each | 53.01 | 424.08 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25241-001025 | 25241 | 2019-10-16 13:48 | Section 4 | Material | Not on List | Not on List | 20 | tonnes | 18.5 | 370 | Aggregate | 2019-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25228-001025 | 25228 | 2019-10-16 12:38 | Section 4 | Material | Bagged | NULL | 10 | EA | 33.55 | 335.5 | Builders Merchants (General) | 2019-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-25341-001025 | 25341 | 2019-10-17 12:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 6 | Each | 36 | 216 | Small Tools (Consumables) | 2019-10-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25341-001025 | 25341 | 2019-10-17 12:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 20 | Each | 0.6 | 12 | Small Tools (Consumables) | 2019-10-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25341-001025 | 25341 | 2019-10-17 12:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 30 | Each | 1.26 | 38 | Small Tools (Consumables) | 2019-10-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25341-001025 | 25341 | 2019-10-17 12:28 | Section 5 | Material | PPE, Small Tools and Consumables | Not on List | 100 | Each | 1.75 | 175 | PPE | 2019-10-22 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25343-001025 | 25343 | 2019-10-17 14:48 | Section 3 | Material | Aggregate | Type 1 | 30 | Tonnes | 21.65 | 650 | Aggregate | 2019-10-18 | Gate D - 1339643 - BN10 Via Main Compound Entrance | SC3B - Roadworks | 501 - Drains | Operational Approval | NULL | NULL | REQ - Section 3 Buyers
MREQ-25384-001025 | 25384 | 2019-10-18 10:57 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 3 | No | NULL | 0 | PPE | 2019-10-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 12 | Each | 81.96 | 983.52 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25384-001025 | 25384 | 2019-10-18 10:57 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 3 | No | NULL | 0 | PPE | 2019-10-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25384-001025 | 25384 | 2019-10-18 10:57 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 3 | No | NULL | 0 | PPE | 2019-10-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25384-001025 | 25384 | 2019-10-18 10:57 | Section 6 | Material | PPE, Small Tools and Consumables | Not on List | 3 | No | NULL | 0 | PPE | 2019-10-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25084-001025 | 25084 | 2019-10-14 15:38 | Section 4 | Material | Not on List | Not on List | 26 | ea | 30.81 | 801.06 | Builders Merchants (General) | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1704 - Reinforcement for Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25084-001025 | 25084 | 2019-10-14 15:38 | Section 4 | Material | Not on List | Not on List | 14 | ladder | 351.55 | 4921.7 | Fixings and Fasteners | 2019-10-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | GN4A - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25084-001025 | 25084 | 2019-10-14 15:38 | Section 4 | Material | Not on List | Not on List | 125 | number | 4.86 | 607.5 | Fixings and Fasteners | 2019-10-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25356-001025 | 25356 | 2019-10-17 16:41 | Section 2 | Material | Not on List | Not on List | 1 | as per attached quote | NULL | 0 | Concrete Drainage | 2019-11-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 601 - Topsoil Strip, Store, Dispose | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25333-001025 | 25333 | 2019-10-17 13:25 | Section 4 | Material | Concrete Drainage | Not on List | 1 | ea | 668.83 | 668.83 | Concrete Drainage | 2019-10-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7016-00752 | 7016 | 2018-09-26 10:37 | Section 3 | Material | Concrete Drainage | Not on List | 12 | NULL | 232.01 | 2784.12 | Concrete Drainage | 2018-10-03 | Gate C - 1339697 - Access to BN06-07-08-09 Via Logistics Yard | SC3A - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-25396-001025 | 25396 | 2019-10-18 12:51 | Section 5 | Material | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 28 | Each | 48.99 | 1371.72 | Plastic Drainage | 2019-10-21 | 1358006 - EB5/1, Works Access, A14 Eastbound, Just before Jcn 32 off Slip, Left Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-25414-001025 | 25414 | 2019-10-18 15:47 | Section 2 | Material | Not on List | Not on List | 5 | Litres | NULL | 0 | Miscellaneous | 2019-10-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | BN05 - Great River Ouse Viaduct | 2101 - Bearings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7075-001009 | 7075 | 2018-09-27 08:35 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 3336.28 | each | 1 | 3336.28 | Miscellaneous | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7078-001009 | 7078 | 2018-09-27 08:41 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 1000 | each | 1.07 | 1070 | Surveying Consumables | 2018-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25315-001025 | 25315 | 2019-10-17 10:13 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 156.6 | 313.2 | Plastic Drainage | 2019-10-22 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25431-001025 | 25431 | 2019-10-18 17:11 | Section 4 | Material | NULL | NULL | 1 | Each | 16229.02 | 16229.02 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-23723-001025 | 23723 | 2019-09-16 11:23 | Section 1 | Material | Not on List | Not on List | 6 | EA | 177.12 | 1062.72 | Ductile Drainage | 2019-09-27 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-25480-001025 | 25480 | 2019-10-21 13:56 | Section 6 | Material | Not on List | Not on List | 1 | ea | 69.99 | 70 | Miscellaneous | 2019-10-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-25426-001025 | 25426 | 2019-10-18 16:43 | Section 4 | Material | NULL | NULL | 1 | Each | 5786.46 | 5786.46 | NULL | NULL | NULL | NULL | NULL | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-25262-001025 | 25262 | 2019-10-16 15:30 | Section 4 | Material | Not on List | Not on List | 2 | NULL | 56.05 | 112.1 | Concrete Drainage | 2019-10-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-6989-00752 | 6989 | 2018-09-25 17:28 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2854.97 | Each | 1 | 2854.97 | Small Tools (Consumables) | 2018-09-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24487-001025 | 24487 | 2019-10-02 07:45 | Section 4 | Material | Not on List | Not on List | 1 | Each | 99.24 | 99.24 | Miscellaneous | 2019-10-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-24794-001025 | 24794 | 2019-10-08 15:43 | Section 2 | Material | Geotextile | Not on List | 3 | Rolls | 2047.57 | 6142.71 | Geotextiles | 2019-10-10 | Gate S/B7 - 1339617 - Access to BN03 East - BN26 - BN27 & Batching Plant, A1 Southbound | SC2B - Roadworks - A14 | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25531-001025 | 25531 | 2019-10-22 08:44 | Section 2 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-10-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-25532-001025 | 25532 | 2019-10-22 08:59 | Section 3 | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Fuel | 2019-10-24 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | REQ - Section 3 Buyers
MREQ-25517-001025 | 25517 | 2019-10-21 17:36 | Section 5 | Material | Not on List | Not on List | 30 | EA | 24.18 | 725.4 | Miscellaneous | 2019-10-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1703 - Formwork | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-7034-00965 | 7034 | 2018-09-26 15:25 | Section 4 | Material | PPE, Small Tools and Consumables | Not on List | 2 | Each | 15.67 | 31.34 | Small Tools (Consumables) | 2018-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28851-001025 | 28851 | 2020-02-04 15:33 | Core | Material | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-01-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-28823-001025 | 28823 | 2020-02-04 08:43 | Section 4 | Material | Not on List | Not on List | 10 | rolls | 111.59 | 1115.9 | Miscellaneous | 2020-02-06 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28857-001025 | 28857 | 2020-02-04 17:41 | Section 4 | Material | Not on List | Not on List | 1 | Number | NULL | 0 | Fixings and Fasteners | 2020-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Requestor - Buyers Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28866-001025 | 28866 | 2020-02-05 07:50 | Section 2 | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-02-10 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 4 | Each | 53.01 | 212.04 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28868-001025 | 28868 | 2020-02-05 08:27 | Section 5 | Material | Not on List | Not on List | 100 | NULL | NULL | 0 | Surveying Consumables | 2020-02-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 110 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 70 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 10 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 8 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 4 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 18 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 6 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 400 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 400 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 4 | Each | 36.62 | 146.48 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 2 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 7 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 12 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 1 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 2 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 2 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 270 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 170 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 1 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-28874-001025 | 28874 | 2020-02-05 08:25 | Section 5 | Material | Combined Drainage | Not on List | 1 | number | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 4 | Each | 59.17 | 236.68 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28875-001025 | 28875 | 2020-02-05 10:18 | Core | Material | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-02-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-28852-001025 | 28852 | 2020-02-04 15:59 | Section 3 | Material | Not on List | Not on List | 120 | m3 | 88.2 | 10584 | Ready Mixed Concrete | 2020-02-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28852-001025 | 28852 | 2020-02-04 15:59 | Section 3 | Material | Not on List | Not on List | 600 | m3 | 106.99 | 64194 | Ready Mixed Concrete | 2020-02-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28852-001025 | 28852 | 2020-02-04 15:59 | Section 3 | Material | Not on List | Not on List | 170 | m3 | 107.76 | 18319.2 | Ready Mixed Concrete | 2020-02-04 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | SC3B - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 25 | Each | 221.73 | 5543.25 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 25 | Each | 275.7 | 6892.5 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 25 | Each | 287.25 | 7181.25 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 25 | Each | 190.83 | 4770.75 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 10 | Each | 44.17 | 441.7 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 4 | Each | 43.12 | 172.48 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-7406-001022 | 7406 | 2018-10-04 15:53 | Section 4 | Material | Not on List | Not on List | 22 | Each | 67.9 | 1493.8 | Concrete Drainage | 2018-10-11 | RVP 418 - 1347987 - East of Jcn 29, A14 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 4 | Each | 43.12 | 172.48 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 40 | Each | 50.69 | 2027.6 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | Not on List | Not on List | 11 | Each | 75.46 | 830.06 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28631-001025 | 28631 | 2020-01-29 13:07 | Section 4 | Material | NULL | NULL | 5 | Each | 158.78 | 793.9 | Builders Merchants (General) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28195-001025 | 28195 | 2020-01-15 16:34 | Section 2 | Material | Not on List | Not on List | 1 | ea | 515.2 | 515 | Professional Services | 2019-11-29 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-28291-001025 | 28291 | 2020-01-17 14:50 | Core | Material | NULL | NULL | NULL | NULL | NULL | 0 | NULL | NULL | NULL | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-28884-001025 | 28884 | 2020-02-05 15:53 | Section 4 | Material | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 8300 | Each | 1.5 | 12450 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-28896-001025 | 28896 | 2020-02-05 08:51 | Section 4 | Material | Not on List | Not on List | 1 | Each | NULL | 0 | Miscellaneous | 2020-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Buyers - Stores Pass Back | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-28982 | 28982 | 2020-02-07 12:26 | Test Section | Material Requisition | Aggregate | A10 Pipe Bed | 54645 | Tonnes | 16.5 | 901642.5 | Blocks and Bricks | 2020-02-28 | Test Location | Test Section | Test Section | Buyer - Closed | Yes - Approve | Yes - Approve | Chris Henry
MREQ-28991 | 28991 | 2020-02-07 13:12 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 80 | 80 | Miscellaneous | 2020-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-29005 | 29005 | 2020-02-07 15:29 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 8 | No | 41 | 328 | Laboratory Equipment / Certification | 2020-02-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29027 | 29027 | 2020-02-10 11:09 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 133.35 | 133.35 | Professional Services | 2020-02-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29030 | 29030 | 2020-02-10 12:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 67.23 | 67.23 | Professional Services | 2020-02-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29035 | 29035 | 2020-02-10 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 137.5 | 137.5 | Professional Services | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29035 | 29035 | 2020-02-10 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 61.53 | 61.53 | Small Tools (Consumables) | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29035 | 29035 | 2020-02-10 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 4 | No | 13.8 | 55.2 | Small Tools (Consumables) | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29035 | 29035 | 2020-02-10 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 6 | No | 44.46 | 266.76 | Small Tools (Consumables) | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 15 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 2 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29036 | 29036 | 2020-02-10 12:13 | Section 4 | Material Requisition | Misc | Not on List | 5 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29039 | 29039 | 2020-02-10 16:26 | Section 5 | Material Requisition | Aggregate | A40 Pipe Bed | 100 | Tonnes | 20.95 | 2095 | Aggregate | 2020-02-12 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
1 | each | NULL | 0 | Flow Control | 2020-02-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29041 | REQ - Finance Team | NULL | NULL
MREQ-29043 | 29043 | 2020-02-10 16:45 | Section 2 | Material Requisition | Not on List | Not on List | 5 | Each | 78.5 | 392.5 | Builders Merchants (General) | 2020-02-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 301 - Fencing, Gates & Stiles | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-29064 | 29064 | 2020-02-11 08:36 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 159 | 159 | Surveying Consumables | 2020-02-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-29064 | 29064 | 2020-02-11 08:36 | Core | Material Requisition | Not on List | Not on List | 2 | No. | 150 | 300 | Surveying Consumables | 2020-02-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-29064 | 29064 | 2020-02-11 08:36 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 159 | 159 | Surveying Consumables | 2020-02-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-29065 | 29065 | 2020-02-11 09:00 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 7500 | 7500 | Miscellaneous | 2020-02-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
2 | ea | 6.75 | 13.5 | Builders Merchants (General) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 136290 | NULL | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29080 | REQ - Finance Team | NULL | NULL
MREQ-29080 | 29080 | 2020-02-11 14:06 | Section 6 | Material Requisition | Not on List | Not on List | 25 | ea | 2.07 | 51.75 | Builders Merchants (General) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29081 | 29081 | 2020-02-11 14:08 | Section 4 | Material Requisition | Geotextile | Not on List | 80 | Linear M | 26.5 | 2120 | Geotextiles | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29081 | 29081 | 2020-02-11 14:08 | Section 4 | Material Requisition | Geotextile | Not on List | 240 | Each | 0.3 | 72 | Geotextiles | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29081 | 29081 | 2020-02-11 14:08 | Section 4 | Material Requisition | Geotextile | Not on List | 1 | Each | 215 | 215 | Geotextiles | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29084 | 29084 | 2020-02-11 14:32 | Section 6 | Material Requisition | Misc | Not on List | 2 | 0 | 0 | 0 | Small Tools (Consumables) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29084 | 29084 | 2020-02-11 14:32 | Section 6 | Material Requisition | Misc | Not on List | 25 | 0 | 0 | 0 | Small Tools (Consumables) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29086 | 29086 | 2020-02-11 14:45 | Section 6 | Material Requisition | Misc | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | IMO Queue | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29086 | 29086 | 2020-02-11 14:45 | Section 6 | Material Requisition | Misc | Not on List | 25 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-02-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | IMO Queue | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29092 | 29092 | 2020-02-11 16:14 | Section 4 | Material Requisition | Geotextile | Not on List | 80 | Linear M | 26.5 | 2120 | Geotextiles | 2020-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29092 | 29092 | 2020-02-11 16:14 | Section 4 | Material Requisition | Geotextile | Not on List | 240 | Each | 0.3 | 72 | Geotextiles | 2020-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29092 | 29092 | 2020-02-11 16:14 | Section 4 | Material Requisition | Geotextile | Not on List | 1 | Each | 215 | 215 | Geotextiles | 2020-02-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29097 | 29097 | 2020-02-11 16:40 | Section 2 | Material Requisition | Hazardous Waste | Not on List | 1 | Quantity | 1740.84 | 1740.84 | Waste (General) | 2020-02-28 | Gate 6 - 1340890 - Batching Plant, Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Passed Back | Yes - Approve | No - Pass Back | Req - S2 Buyers
MREQ-29100 | 29100 | 2020-02-11 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 5 | Each | 75.46 | 377.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29100 | 29100 | 2020-02-11 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 5 | Each | 75.46 | 377.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29100 | 29100 | 2020-02-11 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29100 | 29100 | 2020-02-11 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 3 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29100 | 29100 | 2020-02-11 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 3 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29121 | 29121 | 2020-02-12 09:21 | Section 5 | Material Requisition | Linear Drainage | Not on List | 34 | Each | 9.45 | 321.3 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-18 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29121 | 29121 | 2020-02-12 09:21 | Section 5 | Material Requisition | Linear Drainage | Not on List | 17 | Each | 23.48 | 399.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-18 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 1222.09 | 1222.09 | Concrete Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 8 | Each | 26.79 | 214.32 | Plastic Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 10 | Each | 37.13 | 371.3 | Plastic Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 10 | Each | 62.47 | 624.7 | Plastic Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 6 | Each | 83.09 | 498.54 | Plastic Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29128 | 29128 | 2020-02-12 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 4 | Each | 89.6 | 358.4 | Plastic Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29138 | 29138 | 2020-02-12 13:39 | Section 4 | Material Requisition | Kerbs | Not on List | 100 | Each | 22.84 | 2284 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29138 | 29138 | 2020-02-12 13:39 | Section 4 | Material Requisition | Kerbs | Not on List | 100 | Each | 24.09 | 2409 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29142 | 29142 | 2020-02-12 14:18 | Section 3 | Material Requisition | Hazardous Waste | Not on List | 1 | batch | 3591 | 3591 | Miscellaneous | 2020-02-28 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-29143 | 29143 | 2020-02-12 14:32 | Section 2 | Material Requisition | Hazardous Waste | Not on List | 1 | Batch | 2850 | 2850 | Waste (General) | 2020-02-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29143 | 29143 | 2020-02-12 14:32 | Section 2 | Material Requisition | Hazardous Waste | Not on List | 1 | Batch | 2550 | 2550 | Waste (General) | 2020-02-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29143 | 29143 | 2020-02-12 14:32 | Section 2 | Material Requisition | Hazardous Waste | Not on List | 1 | Batch | 6650 | 6650 | Waste (General) | 2020-02-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29168 | 29168 | 2020-02-13 09:15 | Section 2 | Material Requisition | Not on List | Not on List | 5 | each | 78.5 | 392.5 | Builders Merchants (General) | 2020-02-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC1 - Roadworks | 301 - Fencing, Gates & Stiles | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
1 | Each | NULL | 0 | Concrete Drainage | 2020-02-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13642 | Keyline Builders Merchants Ltd (1100980) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29169 | REQ - Finance Team | NULL | NULL
MREQ-29171 | 29171 | 2020-02-13 09:01 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | consignment | 904.78 | 904.78 | Waste (General) | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29171 | 29171 | 2020-02-13 09:01 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | consignment | 776.78 | 776.78 | Waste (General) | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29172 | 29172 | 2020-02-13 09:39 | Section 3 | Material Requisition | Hazardous Waste | Not on List | 1 | Consignment | 4909.16 | 4909.16 | Waste (General) | 2020-02-28 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 587.88 | 587.88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 130 | 130 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 289.12 | 289.12 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 50 | 50 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 1927.14 | 1927.14 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 50 | 50 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 50 | 50 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 308.2 | 308.2 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29179 | 29179 | 2020-02-13 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 290 | 290 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29186 | 29186 | 2020-02-13 14:23 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 1000 | 1000 | Professional Services | 2020-02-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29187 | 29187 | 2020-02-13 14:34 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 230 | 230 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-29187 | 29187 | 2020-02-13 14:34 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 135 | 135 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-29188 | 29188 | 2020-02-13 14:46 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 47.16 | 47.16 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29188 | 29188 | 2020-02-13 14:46 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 60 | 60 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
2 | Each | 70.18 | 140.36 | Ductile Drainage | 2020-02-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | Caulfield | 13652 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29206 | REQ - Finance Team | NULL | NULL
MREQ-29206 | 29206 | 2020-02-13 18:03 | Section 4 | Material Requisition | Not on List | Not on List | 46 | Lengths | 14.98 | 689.08 | Fixings and Fasteners | 2020-02-18 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29216 | 29216 | 2020-02-14 08:04 | Section 4 | Material Requisition | Not on List | Not on List | 120 | Each | 42.96 | 5155.2 | Miscellaneous | 2020-02-19 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29216 | 29216 | 2020-02-14 08:04 | Section 4 | Material Requisition | Not on List | Not on List | 480 | Each | 1.41 | 676.8 | Miscellaneous | 2020-02-19 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29217 | 29217 | 2020-02-14 08:48 | Section 5 | Material Requisition | Aggregate | Not on List | 20376.77 | Tonne | 5.5 | 112072.24 | Aggregate | 2020-02-14 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29221 | 29221 | 2020-02-14 10:10 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 87.99 | 87.99 | Professional Services | 2020-02-28 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Approval | Yes - Approve | NULL | Req - S1 Buyers
MREQ-29223 | 29223 | 2020-02-14 10:20 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 167.82 | 167.82 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29223 | 29223 | 2020-02-14 10:20 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 660.2 | 660.2 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29223 | 29223 | 2020-02-14 10:20 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 175.33 | 175.33 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29223 | 29223 | 2020-02-14 10:20 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 167.88 | 167.88 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29226 | 29226 | 2020-02-14 11:34 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 81.41 | 81.41 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29227 | 29227 | 2020-02-14 11:35 | Core | Material Requisition | Not on List | Not on List | 1 | no. | 159 | 159 | Surveying Consumables | 2020-02-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29227 | 29227 | 2020-02-14 11:35 | Core | Material Requisition | Not on List | Not on List | 1 | no. | 159 | 159 | Surveying Consumables | 2020-02-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29227 | 29227 | 2020-02-14 11:35 | Core | Material Requisition | Not on List | Not on List | 2 | no. | 150 | 300 | Surveying Consumables | 2020-02-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29260 | 29260 | 2020-02-17 09:32 | Section 4 | Material Requisition | Not on List | Not on List | 300 | NULL | NULL | 0 | Miscellaneous | 2020-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29285 | 29285 | 2020-02-17 18:22 | Section 2 | Material Requisition | Hazardous Waste | Packaging waste containing residues** - 820L w/bin | 1 | Each | 2392 | 2392 | Waste (General) | 2020-02-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29286 | 29286 | 2020-02-17 19:41 | Section 4 | Material Requisition | Not on List | Not on List | 12 | Each | 10.85 | 130.2 | Fixings and Fasteners | 2020-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29286 | 29286 | 2020-02-17 19:41 | Section 4 | Material Requisition | Not on List | Not on List | 12 | Each | 3.35 | 40.2 | Fixings and Fasteners | 2020-02-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 402 - Parapets & Guardrails | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29294 | 29294 | 2020-02-18 09:44 | Section 4 | Material Requisition | Kerbs | Not on List | 350 | NULL | 24.09 | 8431.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29295 | 29295 | 2020-02-18 09:41 | Core | Material Requisition | Not on List | Not on List | 1 | Number | 3000 | 3000 | Surveying Consumables | 2020-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29296 | 29296 | 2020-02-18 09:57 | Section 2 | Material Requisition | Not on List | Not on List | 50 | NULL | NULL | 0 | Concrete Accessories | 2020-02-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29297 | 29297 | 2020-02-18 09:59 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Number | 40 | 120 | Surveying Consumables | 2020-02-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29301 | 29301 | 2020-02-18 10:43 | Core | Material Requisition | Not on List | Not on List | 3 | ea | 552.68 | 1658.04 | Office Supplies | 2020-02-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 56 | Each | 130.26 | 7294.56 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 75 | Each | 9.76 | 732 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Each | 18.84 | 376.8 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 47 | Each | 125.94 | 5919.18 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 65 | Each | 10.04 | 652.6 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29303 | 29303 | 2020-02-18 11:15 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Each | 18.87 | 377.4 | Plastic Drainage | 2020-02-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29314 | 29314 | 2020-02-18 12:46 | Section 6 | Material Requisition | Not on List | Not on List | 1 | NULL | 500 | 500 | Miscellaneous | 2020-03-02 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29322 | 29322 | 2020-02-18 14:28 | Section 4 | Material Requisition | Linear Drainage | Not on List | 2 | Each | 543.04 | 1086.08 | Concrete Drainage | 2020-03-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29326 | 29326 | 2020-02-18 15:27 | Core | Material Requisition | Not on List | Not on List | 1 | number | 1320 | 1320 | Miscellaneous | 2020-02-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29352 | 29352 | 2020-02-19 09:40 | Section 6 | Material Requisition | Concrete Drainage | CPM 600mm Concrete Pipe 2.5m (249353) | 13 | Each | 148.8 | 1934.4 | Concrete Drainage | 2020-02-24 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29352 | 29352 | 2020-02-19 09:40 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 10 | Boxes | 50.54 | 505.4 | Concrete Drainage | 2020-02-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29353 | 29353 | 2020-02-19 10:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 167.82 | 167.82 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29353 | 29353 | 2020-02-19 10:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 660.2 | 660.2 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29353 | 29353 | 2020-02-19 10:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 175.33 | 175.33 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29353 | 29353 | 2020-02-19 10:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 167.88 | 167.88 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29356 | 29356 | 2020-02-19 12:36 | Section 4 | Material Requisition | Kerbs | Not on List | 550 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-24 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
160 | tonnes | 19.5 | 3120 | Aggregate | 2020-02-25 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | A14 IDT | 13682 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29364 | REQ - Finance Team | NULL | NULL
MREQ-29368 | 29368 | 2020-02-19 15:58 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-02-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29369 | 29369 | 2020-02-19 16:00 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 143.91 | 143.91 | Professional Services | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29371 | 29371 | 2020-02-19 16:34 | Section 4 | Material Requisition | Misc | Not on List | 1 | No | 518.45 | 518.45 | Small Tools (Consumables) | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29371 | 29371 | 2020-02-19 16:34 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 84 | 84 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29376 | 29376 | 2020-02-19 17:42 | Section 4 | Material Requisition | Misc | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29383 | 29383 | 2020-02-20 08:04 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 38 | each | 10.98 | 417.24 | Builders Merchants (General) | 2020-02-21 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29389 | 29389 | 2020-02-20 09:03 | Section 2 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 30 | Each | 4.59 | 137.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-21 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29402 | 29402 | 2020-02-20 12:21 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | NULL | 384.4 | 3844 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29403 | 29403 | 2020-02-20 12:45 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 391.5 | 391.5 | Concrete Drainage | 2020-03-06 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29403 | 29403 | 2020-02-20 12:45 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 442.2 | 442.2 | Concrete Drainage | 2020-03-06 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29403 | 29403 | 2020-02-20 12:45 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 442.2 | 442.2 | Concrete Drainage | 2020-03-06 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29403 | 29403 | 2020-02-20 12:45 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 510.3 | 510.3 | Concrete Drainage | 2020-03-06 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29403 | 29403 | 2020-02-20 12:45 | Section 1 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 529.1 | 529.1 | Concrete Drainage | 2020-03-06 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29404 | 29404 | 2020-02-20 12:49 | Section 2 | Material Requisition | Concrete Drainage | Not on List | 1 | each | 442.2 | 442.2 | Concrete Drainage | 2020-03-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29408 | 29408 | 2020-02-20 12:51 | Section 6 | Material Requisition | Not on List | Not on List | 57 | Meters | 362 | 20634 | Concrete Drainage | 2020-03-06 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29408 | 29408 | 2020-02-20 12:51 | Section 6 | Material Requisition | Not on List | Not on List | 4 | no | 40.76 | 163.04 | Concrete Drainage | 2020-03-06 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29408 | 29408 | 2020-02-20 12:51 | Section 6 | Material Requisition | Not on List | Not on List | 4 | no | 407.64 | 1630.56 | Concrete Drainage | 2020-03-06 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29408 | 29408 | 2020-02-20 12:51 | Section 6 | Material Requisition | Not on List | Not on List | 4 | no | 996.45 | 3985.8 | Concrete Drainage | 2020-03-06 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29434 | 29434 | 2020-02-21 07:12 | Section 6 | Material Requisition | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 10 | Each | 115.78 | 1157.8 | Geotextiles | 2020-02-28 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 604 - Deposition (excl topsoil) | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29441 | 29441 | 2020-02-21 07:34 | Section 5 | Material Requisition | Bricks/Blocks | Class B Red Perforated Engineering Bricks (400 per pack) (870923) | 4 | Price Per Thousand | 345 | 1380 | Blocks and Bricks | 2020-02-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29441 | 29441 | 2020-02-21 07:34 | Section 5 | Material Requisition | Bagged | Building Sand 25kg Bag (996239) | 8 | Each | 1.8 | 14.4 | Aggregate | 2020-02-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29441 | 29441 | 2020-02-21 07:34 | Section 5 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 1 | Pallet | 3.56 | 3.56 | Aggregate | 2020-02-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29441 | 29441 | 2020-02-21 07:34 | Section 5 | Material Requisition | Bagged | Post Mix 25kg (348099) | 1 | Pallet | 3.45 | 3.45 | Aggregate | 2020-02-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
1 | NULL | NULL | 0 | Miscellaneous | 2020-02-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13676 | Ashtead Plant Hire Company Ltd (1109463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ29448/Request/Quote_3605776.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29448 | REQ - Finance Team | NULL | NULL
1 | NULL | NULL | 0 | Miscellaneous | 2020-02-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13675 | Ashtead Plant Hire Company Ltd (1109463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ29450/Request/Quote_3605776.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29450 | REQ - Finance Team | NULL | NULL
MREQ-29461 | 29461 | 2020-02-21 11:30 | Section 4 | Material Requisition | Not on List | Not on List | 50 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29461 | 29461 | 2020-02-21 11:30 | Section 4 | Material Requisition | Not on List | Not on List | 50 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29461 | 29461 | 2020-02-21 11:30 | Section 4 | Material Requisition | Not on List | Not on List | 50 | NULL | NULL | 0 | Builders Merchants (General) | 2020-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29463 | 29463 | 2020-02-21 12:13 | Section 4 | Material Requisition | Not on List | Not on List | 134 | Each | 14.43 | 1933.62 | Builders Merchants (General) | 2020-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29463 | 29463 | 2020-02-21 12:13 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 1200 | 1200 | Builders Merchants (General) | 2020-02-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29469 | 29469 | 2020-02-21 13:04 | Section 4 | Material Requisition | Kerbs | Not on List | 300 | Each | 5.17 | 1551 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29469 | 29469 | 2020-02-21 13:04 | Section 4 | Material Requisition | Bagged | Not on List | 5 | Each | 33.55 | 167.75 | Builders Merchants (General) | 2020-02-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29491 | 29491 | 2020-02-24 11:07 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No. | 1028 | 1028 | Miscellaneous | 2020-02-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29502 | 29502 | 2020-02-24 16:43 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 151.5 | 151.5 | Miscellaneous | 2020-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 2301 - Bridge Deck Expansion Joints | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29507 | 29507 | 2020-02-24 17:44 | Section 4 | Material Requisition | Aggregate | 6F5 | 50 | Load | 310 | 15500 | Aggregate | 2020-02-26 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 184 | Each | 30.16 | 5549.44 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 93 | Each | 22.84 | 2124.12 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 2 | Each | 16.88 | 33.76 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 8 | Each | 282.24 | 2257.92 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 2 | Each | 311.1 | 622.2 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 1 | Each | 35.47 | 35.47 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29525 | 29525 | 2020-02-25 10:11 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | Each | 59.26 | 592.6 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29532 | 29532 | 2020-02-25 14:02 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Number | 40 | 120 | Surveying Consumables | 2020-02-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29533 | 29533 | 2020-02-25 14:08 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 4580.4 | 4580.4 | Professional Services | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29534 | 29534 | 2020-02-25 14:42 | Section 4 | Material Requisition | Not on List | Not on List | 30 | boxes | NULL | 0 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1202 - Road Markings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29536 | 29536 | 2020-02-25 14:39 | Section 4 | Material Requisition | Not on List | Not on List | 5 | Each | 111.59 | 557.95 | Miscellaneous | 2020-02-28 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29563 | 29563 | 2020-02-26 09:17 | Section 4 | Material Requisition | Kerbs | Not on List | 3 | Each | 75.46 | 226.38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29563 | 29563 | 2020-02-26 09:17 | Section 4 | Material Requisition | Kerbs | Not on List | 3 | Each | 75.46 | 226.38 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29571 | 29571 | 2020-02-26 12:01 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 224.25 | 224.25 | Professional Services | 2020-02-28 | Gate N/B1 - 1339610 - Access to Processing Plant & Precast Yard, A1 Northbound | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29571 | 29571 | 2020-02-26 12:01 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 358 | 358 | Professional Services | 2020-02-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29571 | 29571 | 2020-02-26 12:01 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 448.5 | 448.5 | Professional Services | 2020-02-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29571 | 29571 | 2020-02-26 12:01 | Section 2 | Material Requisition | Not on List | Not on List | 1 | N0 | 89.7 | 89.7 | Professional Services | 2020-02-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29572 | 29572 | 2020-02-26 13:15 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 241.5 | 241.5 | Professional Services | 2020-02-28 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29572 | 29572 | 2020-02-26 13:15 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-02-28 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29572 | 29572 | 2020-02-26 13:15 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 106.95 | 106.95 | Professional Services | 2020-02-28 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-29574 | 29574 | 2020-02-26 13:48 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-02-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29579 | 29579 | 2020-02-26 15:07 | Section 4 | Material Requisition | Kerbs | Not on List | 30 | Each | 26.38 | 791.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29582 | 29582 | 2020-02-26 16:22 | Section 4 | Material Requisition | Kerbs | Not on List | 64 | Each | 4.75 | 304 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-02-28 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
2 | NULL | NULL | 0 | Plastic Drainage | 2020-03-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | Skyland Contractors Ltd | OP 13724 | Keyline Builders Merchants Ltd (1100980) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29588 | REQ - Finance Team | NULL | NULL
2 | NULL | NULL | 0 | Plastic Drainage | 2020-03-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | Skyland Contractors Ltd | OP 13724 | Keyline Builders Merchants Ltd (1100980) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29588 | REQ - Finance Team | NULL | NULL
MREQ-29588 | 29588 | 2020-02-26 17:30 | Section 2 | Material Requisition | Plastic Drainage | Not on List | 4 | NULL | NULL | 0 | Plastic Drainage | 2020-03-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 45 | No | 11.93 | 536.85 | Plastic Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 25 | No | 2.08 | 52 | Plastic Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 45 | No | 0.95 | 42.75 | Plastic Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 22 | No | 176.27 | 3877.94 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 40 | No | 17.23 | 689.2 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 35 | No | 7.43 | 260.05 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 36 | No | 84.83 | 3053.88 | Ductile Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 112.58 | 337.74 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 26 | No | 51.49 | 1338.74 | Concrete Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 60 | No | 18.08 | 1084.8 | Concrete Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 12 | No | 156.53 | 1878.36 | Concrete Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 34 | No | 17.85 | 606.9 | Plastic Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 55 | No | 4.9 | 269.5 | Plastic Drainage | 2020-03-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 12 | No | 156.63 | 1879.56 | Concrete Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 187.49 | 187.49 | Concrete Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29594 | 29594 | 2020-02-26 17:50 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 187.49 | 187.49 | Concrete Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29598 | 29598 | 2020-02-27 09:11 | Section 5 | Material Requisition | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 20 | Each | 74.3 | 1486 | Ductile Drainage | 2020-02-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29603 | 29603 | 2020-02-27 10:48 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 21.25 | 42.5 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29603 | 29603 | 2020-02-27 10:48 | Section 4 | Material Requisition | Not on List | Not on List | 4 | Each | 9.09 | 36.36 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29604 | 29604 | 2020-02-27 11:00 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 10.06 | 20.12 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29604 | 29604 | 2020-02-27 11:00 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 6.91 | 13.82 | Miscellaneous | 2020-02-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29624 | 29624 | 2020-02-27 13:06 | Section 5 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 21.25 | 4250 | Aggregate | 2020-02-27 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 606 - Import | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29633 | 29633 | 2020-02-27 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 12 | no | NULL | 0 | Flow Control | 2020-03-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29633 | 29633 | 2020-02-27 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 16 | no | 0.11 | 1.76 | Flow Control | 2020-03-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29633 | 29633 | 2020-02-27 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 1 | no | 1939.13 | 1939.13 | Flow Control | 2020-03-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29644 | 29644 | 2020-02-27 12:10 | Section 4 | Material Requisition | Not on List | Not on List | 18 | Each | NULL | 0 | Plastic Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29644 | 29644 | 2020-02-27 12:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29644 | 29644 | 2020-02-27 12:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29644 | 29644 | 2020-02-27 12:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29644 | 29644 | 2020-02-27 12:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Plastic Drainage | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | NULL | NULL | 0 | Miscellaneous | 2020-03-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13728 | Gap Group Ltd (1108091) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29677 | REQ - Finance Team | NULL | NULL
1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-03-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13729 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29678 | REQ - Finance Team | NULL | NULL
MREQ-29680 | 29680 | 2020-02-28 10:21 | Section 3 | Material Requisition | PPE, Small Tools and Consumables | Rope Blue Polypropylene 6mm X 500m (approx)on Drum (746415) | 10 | Each | 25.13 | 251.3 | Plastic Drainage | 2020-03-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 1103 - Linear Drainage Channel Systems | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
2 | Each | 875 | 1750 | Ductile Drainage | 2020-03-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 13740 | Fowler & Holden Ltd (1204843) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29686 | REQ - Finance Team | NULL | NULL
MREQ-29702 | 29702 | 2020-02-28 15:54 | Section 5 | Material Requisition | Aggregate | Not on List | 220 | tonnes | NULL | 0 | Aggregate | 2020-03-03 | 1358013 - EB5/5, A14 Eastbound, Works Access EB5/4, Access Gate | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
MREQ-29735 | 29735 | 2020-03-02 14:43 | Section 4 | Material Requisition | Not on List | Not on List | 160 | rolls | NULL | 0 | Miscellaneous | 2020-03-06 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1500 | each | NULL | 0 | Surveying Consumables | 2020-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | op 13741 | SCCS Survey Equipment Ltd t/a (1101886) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29735 | REQ - Finance Team | NULL | NULL
MREQ-29736 | 29736 | 2020-03-02 15:00 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 13125 | 13125 | Training | 2020-03-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29736 | 29736 | 2020-03-02 15:00 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 790 | 790 | Training | 2020-03-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29770 | 29770 | 2020-03-03 15:50 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Each | 28.8 | 576 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29770 | 29770 | 2020-03-03 15:50 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Each | 43.14 | 862.8 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29770 | 29770 | 2020-03-03 15:50 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Each | 64.35 | 1287 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29770 | 29770 | 2020-03-03 15:50 | Section 4 | Material Requisition | Not on List | Not on List | 30 | Each | 82.29 | 2468.7 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29770 | 29770 | 2020-03-03 15:50 | Section 4 | Material Requisition | Not on List | Not on List | 25 | Each | 87.96 | 2199 | Plastic Drainage | 2020-03-05 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Ea | 715 | 715 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Ea | 352 | 352 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Ea | 594 | 594 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Ea | 1386 | 1386 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29771 | 29771 | 2020-03-03 15:29 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Ea | 880 | 880 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | Ea | 189.75 | 189.75 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13751 | Speedy Asset Services Ltd (1241805) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29771 | REQ - Finance Team | NULL | NULL
1 | Ea | 4580.4 | 4580.4 | Miscellaneous | 2020-03-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13751 | Speedy Asset Services Ltd (1241805) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29771 | REQ - Finance Team | NULL | NULL
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 32 | Each | 132.56 | 4241.92 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 11 | Each | 47.7 | 524.7 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 5 | Each | 117.93 | 589.65 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 14 | Each | 39.57 | 553.98 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 9 | Each | 180.45 | 1624.05 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 15 | Each | 8.68 | 130.2 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 18 | Each | 8.68 | 156.24 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 28 | Each | 8.68 | 243.04 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29782 | 29782 | 2020-03-03 18:43 | Section 4 | Material Requisition | Not on List | Not on List | 4 | Each | 189.2 | 756.8 | Plastic Drainage | 2020-03-11 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29791 | 29791 | 2020-03-04 09:23 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 1085 | 1085 | Fixings and Fasteners | 2020-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1504 - Technology Equipment | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29792 | 29792 | 2020-03-04 10:39 | Section 4 | Material Requisition | Kerbs | Not on List | 1200 | Each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-10 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29795 | 29795 | 2020-03-04 11:38 | Section 4 | Material Requisition | Not on List | Not on List | 60 | Each | 42.96 | 2577.6 | Miscellaneous | 2020-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29795 | 29795 | 2020-03-04 11:38 | Section 4 | Material Requisition | Not on List | Not on List | 50 | Each | 1.41 | 70.5 | Miscellaneous | 2020-03-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29796 | 29796 | 2020-03-04 12:29 | Section 4 | Material Requisition | Kerbs | Not on List | 400 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyers Passed Back to Requestor | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29796 | 29796 | 2020-03-04 12:29 | Section 4 | Material Requisition | Kerbs | Not on List | 400 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1102 - Combined Drainage and Kerb Units | Buyers Passed Back to Requestor | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29797 | 29797 | 2020-03-04 13:08 | Section 6 | Material Requisition | Timber | Not on List | 240 | meters | 6.3 | 1512 | Timber Products | 2020-03-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29797 | 29797 | 2020-03-04 13:08 | Section 6 | Material Requisition | Not on List | Not on List | 2 | rolls | 103.17 | 206.34 | Miscellaneous | 2020-03-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29798 | 29798 | 2020-03-04 10:26 | Section 4 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2020-03-05 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 701 - Sub-base | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29798 | 29798 | 2020-03-04 10:26 | Section 4 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2020-03-06 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 701 - Sub-base | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29798 | 29798 | 2020-03-04 10:26 | Section 4 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2020-03-09 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 701 - Sub-base | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29798 | 29798 | 2020-03-04 10:26 | Section 4 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 21.65 | 10825 | Aggregate | 2020-03-10 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 701 - Sub-base | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 12 | Each | 147.21 | 1766.52 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 32.7 | 65.4 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 146.95 | 146.95 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 40.4 | 40.4 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 20.2 | 20.2 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29803 | 29803 | 2020-03-04 14:44 | Section 4 | Material Requisition | Not on List | Not on List | 30 | Each | 115 | 3450 | Plastic Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 50 | 50 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 188 | 188 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 257.28 | 257.28 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NO | 88 | 88 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29804 | 29804 | 2020-03-04 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 195 | 195 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29822 | 29822 | 2020-03-04 23:43 | Section 5 | Material Requisition | Kerbs | Not on List | 2 | number | 650 | 1300 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29832 | 29832 | 2020-03-05 08:51 | Section 4 | Material Requisition | Kerbs | Not on List | 200 | NULL | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyers Passed Back to Requestor | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29855 | 29855 | 2020-03-05 14:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29855 | 29855 | 2020-03-05 14:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 233.5 | 233.5 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29874 | 29874 | 2020-03-06 08:01 | Section 5 | Material Requisition | Bagged | Post Mix 25kg (348099) | 1 | Pallet | 3.45 | 3.45 | Builders Merchants (General) | 2020-03-10 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29877 | 29877 | 2020-03-06 08:01 | Section 6 | Material Requisition | Twinwall | Not on List | 10 | no | NULL | 0 | Ductile Drainage | 2020-03-16 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29877 | 29877 | 2020-03-06 08:01 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 200 | meters | NULL | 0 | Ductile Drainage | 2020-03-16 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 37.5 | 37.5 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 38.87 | 38.87 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 66.7 | 66.7 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 37.5 | 37.5 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 84.08 | 84.08 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 712.72 | 712.72 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | N0 | 36.21 | 36.21 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 145.26 | 145.26 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 367.49 | 367.49 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 332.27 | 332.27 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 937.5 | 937.5 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 38.87 | 38.87 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-29885 | 29885 | 2020-03-06 09:02 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 357.81 | 357.81 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
8 | Each | 70.18 | 561.44 | Ductile Drainage | 2020-03-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | Caulfield | 13753 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29886 | REQ - Finance Team | NULL | NULL
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 66.7 | 66.7 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 43.45 | 43.45 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 112.1 | 112.1 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 242 | 242 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 141.9 | 141.9 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | NO | 172.41 | 172.41 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29890 | 29890 | 2020-03-06 12:20 | Section 5 | Material Requisition | Not on List | Not on List | 1 | NO | 84.06 | 84.06 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-29894 | 29894 | 2020-03-06 14:00 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Each | 150.24 | 450.72 | Builders Merchants (General) | 2020-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29894 | 29894 | 2020-03-06 14:00 | Section 4 | Material Requisition | Not on List | Not on List | 4 | Each | 25.97 | 103.88 | Builders Merchants (General) | 2020-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29894 | 29894 | 2020-03-06 14:00 | Section 4 | Material Requisition | Not on List | Not on List | 6 | Each | 14.4 | 86.4 | Builders Merchants (General) | 2020-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29894 | 29894 | 2020-03-06 14:00 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Each | 30.62 | 91.86 | Builders Merchants (General) | 2020-03-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29923 | 29923 | 2020-03-09 10:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29923 | 29923 | 2020-03-09 10:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29923 | 29923 | 2020-03-09 10:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29923 | 29923 | 2020-03-09 10:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29923 | 29923 | 2020-03-09 10:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29924 | 29924 | 2020-03-09 10:58 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 603.4 | 603.4 | Professional Services | 2020-03-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-29926 | 29926 | 2020-03-09 11:10 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 555 | 555 | Professional Services | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-29929 | 29929 | 2020-03-09 12:15 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 400 | Tonnes | 21.75 | 8700 | Aggregate | 2020-03-11 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29929 | 29929 | 2020-03-09 12:15 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 400 | Tonnes | 21.75 | 8700 | Aggregate | 2020-03-12 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29929 | 29929 | 2020-03-09 12:15 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 400 | Tonnes | 21.75 | 8700 | Aggregate | 2020-03-13 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29931 | 29931 | 2020-03-09 14:00 | Core | Material Requisition | Not on List | Not on List | 6 | NULL | 39 | 234 | Office Supplies | 2020-03-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-29931 | 29931 | 2020-03-09 14:00 | Core | Material Requisition | Not on List | Not on List | 13 | NULL | 13.5 | 175.5 | Office Supplies | 2020-03-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
37 | NULL | NULL | 0 | Builders Merchants (General) | 2020-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13768 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ29932/Request/abus_41_series.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=29932 | REQ - Finance Team | NULL | NULL
MREQ-29932 | 29932 | 2020-03-09 14:20 | Section 4 | Material Requisition | Not on List | Not on List | 30 | bags | NULL | 0 | Builders Merchants (General) | 2020-03-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN18 - Swavesey NMU Bridge | 1701 - Insitu Concrete | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29959 | 29959 | 2020-03-10 08:07 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Builders Merchants (General) | 2020-03-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29959 | 29959 | 2020-03-10 08:07 | Section 4 | Material Requisition | Not on List | Not on List | 10 | NULL | NULL | 0 | Builders Merchants (General) | 2020-03-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4C - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-29970 | 29970 | 2020-03-10 11:58 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 23.16 | 23.16 | Miscellaneous | 2020-03-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-29971 | 29971 | 2020-03-10 12:04 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | No | 44.17 | 441.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30005 | 30005 | 2020-03-11 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Nr | 9000 | 9000 | Miscellaneous | 2020-03-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 101 - Mob/Demob of Compounds | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30005 | 30005 | 2020-03-11 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Nr | 4400 | 4400 | Miscellaneous | 2020-03-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30005 | 30005 | 2020-03-11 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Nr | 8075 | 8075 | Miscellaneous | 2020-03-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30005 | 30005 | 2020-03-11 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Nr | 6800 | 6800 | Miscellaneous | 2020-03-11 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 704 | Each | 4.59 | 3231.36 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Transition Kerbs 125x255 (947297) | 1 | Each | 10.83 | 10.83 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Transition Kerbs 125x255 (947297) | 2 | Each | 10.08 | 20.16 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 1 | Each | 11.94 | 11.94 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 637 | Each | 3.52 | 2242.24 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 10 | Each | 7.68 | 76.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 11 | Each | 7.68 | 84.48 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 202 | Each | 1.61 | 325.22 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 53 | Each | 3.03 | 160.59 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 25 | Each | 5.43 | 135.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 17 | Each | 5.43 | 92.31 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Kerbs | Not on List | 12 | Each | 16.17 | 194.04 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 16 | m2 | 477.36 | 7637.76 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 35 | m2 | 1113.84 | 38984.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30008 | 30008 | 2020-03-11 07:59 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 75 | m2 | 2817.56 | 211317 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30018 | 30018 | 2020-03-11 13:06 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 5 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-03-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30018 | 30018 | 2020-03-11 13:06 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 2 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-03-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
6 | NULL | NULL | 0 | PPE | 2020-03-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 13769 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30018 | REQ - Finance Team | NULL | NULL
MREQ-30019 | 30019 | 2020-03-11 15:24 | Section 5 | Material Requisition | Aggregate | 6G | 178.54 | Tonnes | 32.9 | 5873.97 | Aggregate | 2020-03-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30023 | 30023 | 2020-03-11 15:07 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 2040.09 | 2040.09 | Tanks and Interceptors | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
8 | Hrs | 35 | 280 | Tanks and Interceptors | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | A14 IDT | OP 13781 | Selwood Ltd (1105450) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30023/Request/BRW12R2SRV001_BRW_Office_WHL06494_1760_001.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30023 | REQ - Finance Team | NULL | NULL
MREQ-30023 | 30023 | 2020-03-11 15:07 | Section 3 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 200 | 200 | Tanks and Interceptors | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30023 | 30023 | 2020-03-11 15:07 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 41.95 | 41.95 | Tanks and Interceptors | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30023 | 30023 | 2020-03-11 15:07 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 750 | 750 | Tanks and Interceptors | 2020-03-27 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30044 | 30044 | 2020-03-12 10:53 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 400 | Tonnes | 24.5 | 9800 | Aggregate | 2020-03-16 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30044 | 30044 | 2020-03-12 10:53 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 450 | Tonnes | 24.5 | 11025 | Aggregate | 2020-03-18 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30058 | 30058 | 2020-03-12 12:56 | Section 6 | Material Requisition | Aggregate | A20 Pipe Bed | 100 | Tonnes | 24.5 | 2450 | Aggregate | 2020-03-13 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30113 | 30113 | 2020-03-13 10:20 | Core | Material Requisition | Not on List | Not on List | 300 | NULL | NULL | 0 | Janitorial | 2020-03-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-30125 | 30125 | 2020-03-13 14:44 | Section 3 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 200 | Each | 2.84 | 568 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-18 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 2 | Each | 145 | 290 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 145 | 145 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 145 | 145 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 145 | 145 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 2 | Each | 235 | 470 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 235 | 235 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 235 | 235 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 235 | 235 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 235 | 235 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 415 | 415 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 1340 | 1340 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30170 | 30170 | 2020-03-16 10:45 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 1340 | 1340 | Miscellaneous | 2020-03-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30174 | 30174 | 2020-03-16 12:16 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 950 | 950 | Miscellaneous | 2020-03-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
1 | NULL | 109.43 | 109.43 | Office Supplies | 2020-03-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30175 | REQ - Finance Team | NULL | NULL
MREQ-30176 | 30176 | 2020-03-16 13:12 | Section 4 | Material Requisition | Not on List | Not on List | 100 | NULL | NULL | 0 | Builders Merchants (General) | 2020-03-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30179 | 30179 | 2020-03-16 14:36 | Section 5 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 1 | Each | 12.27 | 12.27 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-24 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30179 | 30179 | 2020-03-16 14:36 | Section 5 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 1 | Each | 12.27 | 12.27 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-24 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30179 | 30179 | 2020-03-16 14:36 | Section 5 | Material Requisition | Kerbs | Not on List | 6 | Number | 24.48 | 146.88 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-24 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30180 | 30180 | 2020-03-16 15:46 | Section 6 | Material Requisition | Misc | Not on List | 1 | each | 245 | 245 | Miscellaneous | 2020-03-18 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1507 - Testing & Commissioning | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-30181 | 30181 | 2020-03-16 15:52 | Section 6 | Material Requisition | Misc | Not on List | 1 | each | 105 | 105 | Miscellaneous | 2020-03-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1507 - Testing & Commissioning | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-30203 | 30203 | 2020-03-17 08:33 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 147.21 | 294.42 | Plastic Drainage | 2020-03-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30203 | 30203 | 2020-03-17 08:33 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 32.71 | 32.71 | Plastic Drainage | 2020-03-25 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1102 - Combined Drainage and Kerb Units | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30203 | 30203 | 2020-03-17 08:33 | Section 4 | Material Requisition | Not on List | Not on List | 40 | Each | 20.64 | 825.6 | Plastic Drainage | 2020-03-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30208 | 30208 | 2020-03-17 09:20 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 100 | 200 | Electrical | 2020-03-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30211 | 30211 | 2020-03-17 11:28 | Section 6 | Material Requisition | Not on List | Not on List | 100 | no. | 8 | 800 | Miscellaneous | 2020-03-27 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30225 | 30225 | 2020-03-17 16:51 | Section 6 | Material Requisition | Concrete Drainage | CPM 900mm Concrete Pipe 2.5m (249369) | 6 | Each | 264.13 | 1584.78 | Concrete Drainage | 2020-03-18 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30247 | 30247 | 2020-03-18 09:11 | Section 5 | Material Requisition | Not on List | Not on List | 14 | No | 48.19 | 674.66 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30247 | 30247 | 2020-03-18 09:11 | Section 5 | Material Requisition | Not on List | Not on List | 37 | No | 48.19 | 1783.03 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30248 | 30248 | 2020-03-18 09:44 | Section 5 | Material Requisition | Not on List | Not on List | 5 | No | 32.4 | 162 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30248 | 30248 | 2020-03-18 09:44 | Section 5 | Material Requisition | Not on List | Not on List | 3 | No | 40.5 | 121.5 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 32 | Each | 78.67 | 2517.44 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm Ridgidrain 6m P/E Unperf (346339) | 3 | Each | 51.56 | 154.68 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 12 | Each | 3.31 | 39.72 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 24 | Each | 1.63 | 39.12 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm Ridgidrain Coupler (878066) | 30 | Each | 6.51 | 195.3 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm Ridgidrain Seal (346386) | 60 | Each | 3.36 | 201.6 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm Ridgidrain Bend 45deg (878031) | 3 | Each | 89.17 | 267.51 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm x 150mm Ridgidrain 45deg Junction (878038) | 3 | Each | 47.92 | 143.76 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 225mm x 225mm Ridgdrain 45deg Junction (878042) | 3 | Each | 109.52 | 328.56 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Polypipe 300mm Ridgidrain Bend 45deg (878085) | 2 | Each | 85.75 | 171.5 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Not on List | 1 | Each | 224.31 | 224.31 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Not on List | 5 | Each | 52.45 | 262.25 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Twinwall | Not on List | 3 | Each | 80.79 | 242.37 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30249 | 30249 | 2020-03-18 09:37 | Section 5 | Material Requisition | Not on List | Not on List | 7 | Each | 156.72 | 1097.04 | Ductile Drainage | 2020-03-26 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30256 | 30256 | 2020-03-18 12:06 | Section 4 | Material Requisition | Not on List | Not on List | 28 | NULL | NULL | 0 | Plastic Drainage | 2020-03-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyers Passed Back to Requestor | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30256 | 30256 | 2020-03-18 12:06 | Section 4 | Material Requisition | Not on List | Not on List | 32 | NULL | NULL | 0 | Plastic Drainage | 2020-03-20 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyers Passed Back to Requestor | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30260 | 30260 | 2020-03-18 12:45 | Section 5 | Material Requisition | Bagged | Building Sand Bulk Bag (938155) | 8 | Each | 32.74 | 261.92 | Builders Merchants (General) | 2020-03-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30260 | 30260 | 2020-03-18 12:45 | Section 5 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 1 | Each | 3.56 | 3.56 | Builders Merchants (General) | 2020-03-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30260 | 30260 | 2020-03-18 12:45 | Section 5 | Material Requisition | Not on List | Building Sand Bulk Bag (938155) | 40 | Pallets | 32.74 | 1309.6 | Builders Merchants (General) | 2020-03-19 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
1 | No | 801.72 | 801.72 | Miscellaneous | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13833 | K Guard International Ltd (1340982) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30262 | REQ - Finance Team | NULL | NULL
MREQ-30271 | 30271 | 2020-03-18 15:10 | Section 4 | Material Requisition | Not on List | Not on List | 350 | Ea | 0.68 | 238 | Office Supplies | 2020-03-23 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30299 | 30299 | 2020-03-19 12:00 | Section 4 | Material Requisition | Not on List | Not on List | 26 | Each | 137.11 | 3564.86 | Plastic Drainage | 2020-03-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30299 | 30299 | 2020-03-19 12:00 | Section 4 | Material Requisition | Not on List | Not on List | 42 | Each | 132.56 | 5567.52 | Plastic Drainage | 2020-03-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30299 | 30299 | 2020-03-19 12:00 | Section 4 | Material Requisition | Not on List | Not on List | 10 | Each | 198.95 | 1989.5 | Plastic Drainage | 2020-03-23 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
10 | Each | 87.9 | 879 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | Skyland Contractors Ltd | 13836 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30341 | REQ - Finance Team | NULL | NULL
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 10 | Each | 58.03 | 580.3 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 1 | Each | 40.8 | 40.8 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 10 | Each | 64.76 | 647.6 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 26 | Each | 18.08 | 470.08 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Combined Drainage | Not on List | 10 | Each | 118.92 | 1189.2 | Concrete Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 39 | No | 33.98 | 1325.22 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 12 | No | 53.24 | 638.88 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 10 | No | 15.91 | 159.1 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 7 | Each | 45.12 | 315.84 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 4 | Each | 50.48 | 201.92 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 1 | Each | 44.98 | 44.98 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 1 | Each | 50.31 | 50.31 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30341 | 30341 | 2020-03-20 13:33 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 2 | ea | 12.29 | 24.58 | Plastic Drainage | 2020-03-27 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30348 | 30348 | 2020-03-20 16:57 | Core | Material Requisition | Misc | Not on List | 200 | No | 2.75 | 550 | Office Supplies | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-30373 | 30373 | 2020-03-23 14:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-03-26 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-03-25 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 13818 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30387 | REQ - Finance Team | NULL | NULL
MREQ-30397 | 30397 | 2020-03-24 12:03 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 2142.8 | 2142.8 | Miscellaneous | 2020-03-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30418 | 30418 | 2020-03-24 17:57 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Each | 57291.51 | 57291.51 | Miscellaneous | 2020-03-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | BE25 - Impington Guided Busway Bridge Modifications | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30422 | 30422 | 2020-03-25 08:14 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 540.51 | 540.51 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30424 | 30424 | 2020-03-25 08:22 | Section 4 | Material Requisition | Aggregate | Type 1 | 10000 | Tonnes | 23.5 | 235000 | Aggregate | 2020-03-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30434 | 30434 | 2020-03-25 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 135 | 135 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30434 | 30434 | 2020-03-25 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30434 | 30434 | 2020-03-25 10:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 207 | 207 | Professional Services | 2020-03-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30450 | 30450 | 2020-03-26 08:18 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 9000 | 9000 | Ductile Drainage | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30450 | 30450 | 2020-03-26 08:18 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 9000 | 9000 | Ductile Drainage | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 504 - Drainage and Service Ducts in Structures | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30457 | 30457 | 2020-03-26 09:36 | Section 2 | Material Requisition | Misc | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-03-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-30461 | 30461 | 2020-03-26 10:56 | Section 4 | Material Requisition | Not on List | Not on List | 38 | Each | 84.83 | 3223.54 | Ductile Drainage | 2020-04-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30461 | 30461 | 2020-03-26 10:56 | Section 4 | Material Requisition | Not on List | Not on List | 80 | Each | 42.5 | 3400 | Concrete Drainage | 2020-04-02 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30466 | 30466 | 2020-03-26 13:16 | Section 3 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 450 | Each | 2.48 | 1116 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-03-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30476 | 30476 | 2020-03-26 14:30 | Section 4 | Material Requisition | Not on List | Not on List | 74 | Each | 13.29 | 983.46 | Builders Merchants (General) | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4B - Gantry structures | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30487 | 30487 | 2020-03-27 07:20 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 50 | number | NULL | 0 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30487 | 30487 | 2020-03-27 07:20 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 32 | number | NULL | 0 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30487 | 30487 | 2020-03-27 07:20 | Section 4 | Material Requisition | Saint Gobain Castings | Not on List | 38 | number | NULL | 0 | Ductile Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30487 | 30487 | 2020-03-27 07:20 | Section 4 | Material Requisition | Saint Gobain Castings | Not on List | 12 | number | NULL | 0 | Ductile Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30487 | 30487 | 2020-03-27 07:20 | Section 4 | Material Requisition | Aggregate | Not on List | 20 | ton | 25 | 500 | Ductile Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30497 | 30497 | 2020-03-27 10:27 | Section 4 | Material Requisition | Not on List | Not on List | 50 | Each | 35.17 | 1758.5 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30497 | 30497 | 2020-03-27 10:27 | Section 4 | Material Requisition | Not on List | Not on List | 32 | Each | 21.76 | 696.32 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30497 | 30497 | 2020-03-27 10:27 | Section 4 | Material Requisition | Not on List | Not on List | 38 | Each | 34.86 | 1324.68 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30497 | 30497 | 2020-03-27 10:27 | Section 4 | Material Requisition | Not on List | Not on List | 12 | Each | 70.18 | 842.16 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30497 | 30497 | 2020-03-27 10:27 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Tonnes | NULL | 0 | Plastic Drainage | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30498 | 30498 | 2020-03-27 10:26 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 733.42 | 733.42 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30498 | 30498 | 2020-03-27 10:26 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30501 | 30501 | 2020-03-27 11:55 | Section 5 | Material Requisition | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 27 | Each | 42.5 | 1147.5 | Concrete Drainage | 2020-04-02 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30501 | 30501 | 2020-03-27 11:55 | Section 5 | Material Requisition | Linear Drainage | Not on List | 1 | Each | 332.63 | 332.63 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-02 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 1103 - Linear Drainage Channel Systems | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30506 | 30506 | 2020-03-27 14:20 | Section 4 | Material Requisition | Not on List | Not on List | 150 | NULL | NULL | 0 | PPE | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30506 | 30506 | 2020-03-27 14:20 | Section 4 | Material Requisition | Not on List | Not on List | 150 | NULL | NULL | 0 | PPE | 2020-03-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 85 | 85 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 114 | 114 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 72 | 72 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 103.5 | 103.5 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 97.95 | 97.95 | Professional Services | 2020-03-27 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30507 | 30507 | 2020-03-27 13:56 | Section 5 | Material Requisition | Not on List | Not on List | 0 | NULL | NULL | 0 | Professional Services | NaN-NaN-NaN NaN:NaN:NaN | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Rejected | No - Reject | NULL | Req - S5 Buyers
MREQ-30511 | 30511 | 2020-03-27 15:35 | Section 5 | Material Requisition | Aggregate | A20 Pipe Bed | 100 | Tonnes | 21.25 | 2125 | Aggregate | 2020-03-31 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30514 | 30514 | 2020-03-27 16:33 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 2142.8 | 2142.8 | Miscellaneous | 2020-03-30 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | No | 233.52 | 233.52 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13861 | P Flannery Plant Hire (Oval) L (1107945) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30559/Request/SKM_C284e20032009380 (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30559 | REQ - Finance Team | NULL | NULL
MREQ-30574 | 30574 | 2020-03-31 09:00 | Section 6 | Material Requisition | Not on List | Not on List | 30 | linier m | NULL | 0 | Concrete Accessories | 2020-04-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30574 | 30574 | 2020-03-31 09:00 | Section 6 | Material Requisition | Not on List | Not on List | 100 | ea | NULL | 0 | Concrete Accessories | 2020-04-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30574 | 30574 | 2020-03-31 09:00 | Section 6 | Material Requisition | Not on List | Not on List | 100 | ea | NULL | 0 | Concrete Accessories | 2020-04-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30574 | 30574 | 2020-03-31 09:00 | Section 6 | Material Requisition | Not on List | Not on List | 100 | ea | NULL | 0 | Concrete Accessories | 2020-04-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30574 | 30574 | 2020-03-31 09:00 | Section 6 | Material Requisition | Not on List | Not on List | 15 | ea | NULL | 0 | Concrete Accessories | 2020-04-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30579 | 30579 | 2020-03-31 15:41 | Section 4 | Material Requisition | Misc | Not on List | 1 | Box | NULL | 0 | Miscellaneous | 2020-04-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | No | 132.25 | 132.25 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13855 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30581/Request/Mobile Job.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30581 | REQ - Finance Team | NULL | NULL
1 | No | 494.5 | 494.5 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13855 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30581 | REQ - Finance Team | NULL | NULL
1 | No | 109.25 | 109.25 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13855 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30581 | REQ - Finance Team | NULL | NULL
1 | No | 57.5 | 57.5 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13855 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30581 | REQ - Finance Team | NULL | NULL
1 | No | 83.37 | 83.37 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13855 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30581 | REQ - Finance Team | NULL | NULL
MREQ-30581 | 30581 | 2020-03-31 12:11 | Section 4 | Material Requisition | Not on List | Not on List | 81 | Ltrs | 0.8 | 64.8 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30595 | 30595 | 2020-04-01 09:20 | Section 5 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 1 | Pallet | 3.56 | 3.56 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
60 | boxes | 32.4 | 1944 | Builders Merchants (General) | 2020-04-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13853 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | Killgerm | /sites/BPM/FlowForma/FormDocuments/MREQ30602/Request/IM June 2018 BF contact.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30602 | REQ - Finance Team | NULL | NULL
12 | tube | 4.74 | 56.88 | Builders Merchants (General) | 2020-04-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13853 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | Killgerm | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30602 | REQ - Finance Team | NULL | NULL
MREQ-30603 | 30603 | 2020-04-01 10:19 | Core | Material Requisition | Not on List | Not on List | 1512 | No | 4.8 | 7257.6 | Miscellaneous | 2020-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-30608 | 30608 | 2020-04-01 13:52 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Roll | 243.25 | 729.75 | Geotextiles | 2020-04-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
5450 | No | 1 | 5450 | Miscellaneous | 2020-04-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13992 | Savills (UK) Ltd - Cambridge (1128665) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30609/Request/FW A14 - Trespass at Catch Hall Farm Buildings - Claim.msg | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30609 | REQ - Finance Team | NULL | NULL
1 | No | 97.95 | 97.95 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30622/Request/DOC110320-11032020093949.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
1 | No | 879.75 | 879.75 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
1 | No | 288.65 | 288.65 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
1 | No | 161.7 | 161.7 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
1 | No | 97.75 | 97.75 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
1 | No | 109.25 | 109.25 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
1 | No | 69 | 69 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
1 | N0 | 247.25 | 247.25 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
1 | No | 69 | 69 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
1 | No | 319 | 319 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13903 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30622 | REQ - Finance Team | NULL | NULL
200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-04-03 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | Skyland Contractors Ltd | 13854 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30623 | REQ - Finance Team | NULL | NULL
MREQ-30630 | 30630 | 2020-04-02 07:13 | Section 5 | Material Requisition | PPE, Small Tools and Consumables | Screws Self Tapping 305 Pcs Assorted Box 61275 (662414) | 10 | Boxes | 9.42 | 94.2 | Fixings and Fasteners | 2020-04-03 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30634 | 30634 | 2020-04-02 08:38 | Section 4 | Material Requisition | Misc | Not on List | 1 | box | NULL | 0 | Miscellaneous | 2020-04-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30634 | 30634 | 2020-04-02 08:38 | Section 4 | Material Requisition | Misc | Not on List | 1 | box | NULL | 0 | Miscellaneous | 2020-04-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
4000 | M2 | 4.85 | 19400 | Builders Merchants (General) | 2020-04-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 13871 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30638 | REQ - Finance Team | NULL | NULL
5 | 25KG | 7.95 | 39.75 | Builders Merchants (General) | 2020-04-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 13871 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30638 | REQ - Finance Team | NULL | NULL
MREQ-30640 | 30640 | 2020-04-02 11:55 | Section 5 | Material Requisition | Kerbs | Not on List | 80 | Each | 4.93 | 394.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30640 | 30640 | 2020-04-02 11:55 | Section 5 | Material Requisition | Kerbs | Not on List | 3 | Each | 5.84 | 17.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30640 | 30640 | 2020-04-02 11:55 | Section 5 | Material Requisition | Kerbs | Not on List | 3 | Each | 5.84 | 17.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-07 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
1000 | Tonnes | 21.25 | 21250 | Aggregate | 2020-04-06 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | Caulfield | 13859 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30641 | REQ - Finance Team | NULL | NULL
500 | Tonnes | 21.95 | 10975 | Aggregate | 2020-04-06 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | Caulfield | 13858 | Mick George Ltd (1220483) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30641 | REQ - Finance Team | NULL | NULL
MREQ-30647 | 30647 | 2020-04-02 12:30 | Section 4 | Material Requisition | Not on List | Not on List | 16 | Each | 142.02 | 2272.32 | Plastic Drainage | 2020-04-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30647 | 30647 | 2020-04-02 12:30 | Section 4 | Material Requisition | Not on List | Not on List | 6 | Each | 128.26 | 769.56 | Plastic Drainage | 2020-04-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30647 | 30647 | 2020-04-02 12:30 | Section 4 | Material Requisition | Not on List | Not on List | 6 | Each | 154.93 | 929.58 | Plastic Drainage | 2020-04-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30647 | 30647 | 2020-04-02 12:30 | Section 4 | Material Requisition | Not on List | Not on List | 10 | Each | 107.9 | 1079 | Plastic Drainage | 2020-04-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30647 | 30647 | 2020-04-02 12:30 | Section 4 | Material Requisition | Not on List | Not on List | 42 | Each | 11.93 | 501.06 | Plastic Drainage | 2020-04-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
18 | Ea | 5.39 | 97.02 | Miscellaneous | 2020-04-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13866 | Gap Group Ltd (1108091) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30666 | REQ - Finance Team | NULL | NULL
MREQ-30671 | 30671 | 2020-04-03 12:28 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | Each | 8.55 | 85.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30671 | 30671 | 2020-04-03 12:28 | Section 4 | Material Requisition | Kerbs | Not on List | 10 | Each | 8.55 | 85.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | ea | 468.38 | 468.38 | Damage Charges | 2020-04-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 113868 | Gap Group Ltd (1108091) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30687/Buyers/IMG_20191219_0003 (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30687 | REQ - Finance Team | NULL | NULL
MREQ-30712 | 30712 | 2020-04-06 08:27 | Section 4 | Material Requisition | Not on List | Not on List | 8 | number | 8.99 | 71.92 | Miscellaneous | 2020-04-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | IMO Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30720 | 30720 | 2020-04-06 10:23 | Test Section | Material Requisition | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 2 | Each | 59.17 | 118.34 | Concrete Drainage | 2020-05-07 | Test Location | Test Section | Test Section | IMO Queue | Yes - Approve | Yes - Approve | Chris Henry
MREQ-30729 | 30729 | 2020-04-06 13:32 | Test Section | Material Requisition | Geotextile | Tensar TX160 4m x 75m (150563) | 134 | Each | 535 | 71690 | Aggregate | 2020-05-01 | Test Location | Test Section | Test Section | IMO Queue | Yes - Approve | Yes - Approve | Chris Henry
MREQ-30751 | 30751 | 2020-04-07 09:04 | Section 3 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 360 | Each | 2.48 | 892.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-30755 | 30755 | 2020-04-07 09:11 | Section 4 | Material Requisition | Not on List | Not on List | 200 | NULL | NULL | 0 | Builders Merchants (General) | 2020-04-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30758 | 30758 | 2020-04-07 10:34 | Section 6 | Material Requisition | Not on List | Not on List | 36 | No | 5.4 | 194.4 | Miscellaneous | 2020-04-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30763 | 30763 | 2020-04-07 13:44 | Core | Material Requisition | Not on List | Not on List | 1 | number | 823.9 | 823.9 | Miscellaneous | 2020-04-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-30763 | 30763 | 2020-04-07 13:44 | Core | Material Requisition | Not on List | Not on List | 1 | number | 1282 | 1282 | Miscellaneous | 2020-04-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 115 - Medical / 1st Aid | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-30764 | 30764 | 2020-04-07 13:49 | Section 4 | Material Requisition | Not on List | Not on List | 1 | roll | NULL | 0 | Miscellaneous | 2020-04-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1502 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | Each | 152.5 | 152.5 | Miscellaneous | 2020-04-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13877 | Morelock Signs Ltd (1255521) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30766/Request/2m Apart.zip | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30766 | REQ - Finance Team | NULL | NULL
MREQ-30767 | 30767 | 2020-04-07 15:56 | Section 5 | Material Requisition | Not on List | Not on List | 225 | m3 | 81.3 | 18292.5 | Ready Mixed Concrete | 2020-04-09 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
24 | each | 18.75 | 450 | Miscellaneous | 2020-04-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13883 | Lattenbury Services Ltd (1289505) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30777 | REQ - Finance Team | NULL | NULL
MREQ-30779 | 30779 | 2020-04-08 10:53 | Section 5 | Material Requisition | Aggregate | Type 1 | 3000 | Tonnes | 23.5 | 70500 | Aggregate | 2020-04-10 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30780 | 30780 | 2020-04-08 11:04 | Section 2 | Material Requisition | Bricks/Blocks | Not on List | 132.5 | m2. | 34.59 | 4583.18 | Blocks and Bricks | 2020-04-14 | NULL | SEC1 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-30781 | 30781 | 2020-04-08 11:50 | Section 4 | Material Requisition | Kerbs | Not on List | 148 | Each | 31.83 | 4710.84 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30781 | 30781 | 2020-04-08 11:50 | Section 4 | Material Requisition | Kerbs | Not on List | 2 | Each | 134.8 | 269.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30782 | 30782 | 2020-04-08 12:27 | Section 6 | Material Requisition | Not on List | Not on List | 1 | total | 1513.14 | 1513.14 | Miscellaneous | 2020-04-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-30782 | 30782 | 2020-04-08 12:27 | Section 6 | Material Requisition | Not on List | Not on List | 1 | total | 91.73 | 91.73 | Miscellaneous | 2020-04-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No. | 850 | 850 | Small Tools (Consumables) | 2020-04-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13887 | Lattenbury Services Ltd (1289505) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30787 | REQ - Finance Team | NULL | NULL
1 | No | 85 | 85 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
1 | No | 114 | 114 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
1 | No | 72 | 72 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
1 | No | 103.5 | 103.5 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
1 | No | 97.95 | 97.95 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
1 | No | 97.95 | 97.95 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | OP 13884 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30792 | REQ - Finance Team | NULL | NULL
MREQ-30814 | 30814 | 2020-04-09 07:13 | Section 2 | Material Requisition | Misc | Not on List | 6 | NULL | NULL | 0 | Miscellaneous | 2020-04-14 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 702 - Pavement | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-30826 | 30826 | 2020-04-09 09:48 | Section 4 | Material Requisition | Not on List | Not on List | 30 | Bag | 44.6 | 1338 | Builders Merchants (General) | 2020-04-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30826 | 30826 | 2020-04-09 09:48 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 6.81 | 6.81 | Builders Merchants (General) | 2020-04-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-30826 | 30826 | 2020-04-09 09:48 | Section 4 | Material Requisition | Not on List | Not on List | 5 | Each | 3.97 | 19.85 | Builders Merchants (General) | 2020-04-14 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1701 - Insitu Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | No | 207 | 207 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | OP 13901 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30830/Request/DOC110320-11032020100911.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30830 | REQ - Finance Team | NULL | NULL
1 | No | 5.75 | 5.75 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | OP 13901 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30830 | REQ - Finance Team | NULL | NULL
1 | No | 284.12 | 284.12 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | OP 13901 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30830 | REQ - Finance Team | NULL | NULL
1 | No | 306.21 | 306.21 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | OP 13901 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30830 | REQ - Finance Team | NULL | NULL
1 | No | 84 | 84 | Professional Services | 2020-04-24 | Gate 1 - 1339601 - Main Compound Alconbury | A14 IDT | OP 13893 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30835/Request/DOC100320-10032020115410.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30835 | REQ - Finance Team | NULL | NULL
1 | No | 251.25 | 251.25 | Professional Services | 2020-04-24 | Gate 1 - 1339601 - Main Compound Alconbury | A14 IDT | OP 13893 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30835 | REQ - Finance Team | NULL | NULL
1 | No | 251.25 | 251.25 | Professional Services | 2020-04-24 | Gate 1 - 1339601 - Main Compound Alconbury | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30835 | REQ - Finance Team | NULL | NULL
1 | No | 800 | 800 | Surveying Consumables | 2020-04-20 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | A14 IDT | OP 13892 | Topcon (Great Britain) Ltd (1114363) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30952 | REQ - Finance Team | NULL | NULL
MREQ-30957 | 30957 | 2020-04-14 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 115.2 | 115.2 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30957 | 30957 | 2020-04-14 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 470.35 | 470.35 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30957 | 30957 | 2020-04-14 08:19 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 394.9 | 394.9 | Professional Services | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-30969 | 30969 | 2020-04-14 10:14 | Section 4 | Material Requisition | Not on List | Not on List | 20 | Rolls | NULL | 0 | Rebar and Mesh | 2020-04-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | set of 4 members | NULL | 0 | Miscellaneous | 2020-04-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | OP 13904 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30975 | REQ - Finance Team | NULL | NULL
MREQ-30977 | 30977 | 2020-04-14 12:29 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Tubs | NULL | 0 | Miscellaneous | 2020-04-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | No | 178.5 | 178.5 | Professional Services | 2020-04-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | A14 IDT | OP 13896 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30981 | REQ - Finance Team | NULL | NULL
1 | No | 57.5 | 57.5 | Professional Services | 2020-04-24 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | A14 IDT | OP 13896 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30981 | REQ - Finance Team | NULL | NULL
1 | No | 63.25 | 63.25 | Professional Services | 2020-04-24 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | A14 IDT | OP 13897 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ30988/Request/DOC100320-10032020115410 (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30988 | REQ - Finance Team | NULL | NULL
1 | No | 69 | 69 | Professional Services | 2020-04-24 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | A14 IDT | OP 13897 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=30988 | REQ - Finance Team | NULL | NULL
MREQ-31002 | 31002 | 2020-04-15 08:27 | Section 2 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 50 | Each | 3.56 | 178 | Aggregate | 2020-04-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31008 | 31008 | 2020-04-15 09:33 | Section 6 | Material Requisition | Concrete Drainage | CPM 900mm Concrete Socket (249372) | 1 | Each | 305.03 | 305.03 | Concrete Drainage | 2020-04-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31008 | 31008 | 2020-04-15 09:33 | Section 6 | Material Requisition | Concrete Drainage | CPM 900mm Concrete Spigot (249371) | 1 | Each | 305.03 | 305.03 | Concrete Drainage | 2020-04-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31008 | 31008 | 2020-04-15 09:33 | Section 6 | Material Requisition | Concrete Drainage | CPM 600mm Concrete Socket (249351) | 1 | Each | 106.73 | 106.73 | Concrete Drainage | 2020-04-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31008 | 31008 | 2020-04-15 09:33 | Section 6 | Material Requisition | Concrete Drainage | CPM 600mm Concrete Spigot (249354) | 1 | Each | 106.73 | 106.73 | Concrete Drainage | 2020-04-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31009 | 31009 | 2020-04-15 10:30 | Section 5 | Material Requisition | Bagged | Building Sand Bulk Bag (938155) | 5 | Each | 32.74 | 163.7 | Builders Merchants (General) | 2020-04-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
15 | Each | 20.47 | 307.05 | Builders Merchants (General) | 2020-04-17 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | JP Flynn Construction Ltd | 13899 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31011 | REQ - Finance Team | NULL | NULL
MREQ-31034 | 31034 | 2020-04-16 10:58 | Section 6 | Material Requisition | Not on List | Not on List | 1 | Ea | 17092.96 | 17092.96 | Miscellaneous | 2020-04-17 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | FEE6 - Fee Based Costs inc. insurance | 107 - Insurance | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31036 | 31036 | 2020-04-16 12:08 | Section 3 | Material Requisition | Not on List | Not on List | 3 | No | 51.5 | 154.5 | Miscellaneous | 2020-04-24 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31036 | 31036 | 2020-04-16 12:08 | Section 3 | Material Requisition | Not on List | Not on List | 3 | No | 45 | 135 | Miscellaneous | 2020-04-24 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31036 | 31036 | 2020-04-16 12:08 | Section 3 | Material Requisition | Not on List | Not on List | 3 | No | 45 | 135 | Miscellaneous | 2020-04-24 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31045 | 31045 | 2020-04-16 14:20 | Section 4 | Material Requisition | Not on List | Not on List | 10 | NULL | NULL | 0 | Ductile Drainage | 2020-04-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31059 | 31059 | 2020-04-17 07:48 | Section 4 | Material Requisition | Not on List | Not on List | 37 | NULL | NULL | 0 | Builders Merchants (General) | 2020-04-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | GN4A - Gantry structures | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31064 | 31064 | 2020-04-17 09:28 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | contract | 19606.06 | 19606.06 | Professional Services | 2020-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31068 | 31068 | 2020-04-17 10:22 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | Miscellaneous | 2020-04-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31068 | 31068 | 2020-04-17 10:22 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 50 | NULL | NULL | 0 | Miscellaneous | 2020-04-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31072 | 31072 | 2020-04-17 13:12 | Section 4 | Material Requisition | Aggregate | Bedding Sand | 20 | Tonnes | 18.5 | 370 | Aggregate | 2020-04-21 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31075 | 31075 | 2020-04-17 13:41 | Section 4 | Material Requisition | Not on List | Not on List | 1 | day | 225 | 225 | Electrical | 2020-04-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
500 | pallets | 2.92 | 1460 | Builders Merchants (General) | 2020-04-21 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 13914 | Keyline Builders Merchants Ltd (1100980) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31114 | REQ - Finance Team | NULL | NULL
1040 | Hrs | 21.61 | 22474.4 | Miscellaneous | 2020-04-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13915 | Robert Half Ltd (1263314) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31115 | REQ - Finance Team | NULL | NULL
1 | No | 120.5 | 120.5 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | OP 13916 | L Lynch (Plant Hire & Haulage) (1112290) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31145/Request/Advice Note N06-667824.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31145 | REQ - Finance Team | NULL | NULL
MREQ-31145 | 31145 | 2020-04-21 08:45 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31145 | 31145 | 2020-04-21 08:45 | Section 6 | Material Requisition | Misc | Not on List | 52 | Ltrs | 0.8 | 41.6 | Gas Oil | 2020-04-24 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No | 652.31 | 652.31 | Miscellaneous | 2020-04-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13921 | Change Capability Ltd t/a EQ P (1320940) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31147/Request/EQ Partnering Invoice0259.doc | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31147 | REQ - Finance Team | NULL | NULL
MREQ-31149 | 31149 | 2020-04-21 12:39 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 221.63 | 221.63 | Flow Control | 2020-04-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31149 | 31149 | 2020-04-21 12:39 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Each | 529.05 | 1587.15 | Concrete Drainage | 2020-04-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31149 | 31149 | 2020-04-21 12:39 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Each | 384.8 | 769.6 | Concrete Drainage | 2020-04-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31153 | 31153 | 2020-04-21 14:08 | Section 4 | Material Requisition | Not on List | Not on List | 7 | NULL | NULL | 0 | Plastic Drainage | 2020-04-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31154 | 31154 | 2020-04-21 14:30 | Section 4 | Material Requisition | Misc | Not on List | 15 | No | 51.5 | 772.5 | Tanks and Interceptors | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31154 | 31154 | 2020-04-21 14:30 | Section 4 | Material Requisition | Misc | Not on List | 2 | No | 12 | 24 | Tanks and Interceptors | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31154 | 31154 | 2020-04-21 14:30 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 456.83 | 456.83 | Tanks and Interceptors | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31157 | 31157 | 2020-04-21 16:06 | Section 6 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 21.25 | 4250 | Aggregate | 2020-04-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No | 613.33 | 613.33 | Miscellaneous | 2020-04-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | 13941 | Change Capability Ltd t/a EQ P (1320940) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31159/Request/EQ Partnering Invoice0259.doc | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31159 | REQ - Finance Team | NULL | NULL
MREQ-31168 | 31168 | 2020-04-22 08:03 | Section 2 | Material Requisition | Aggregate | Type B | 260 | Tonnes | 22.1 | 5746 | Aggregate | 2020-04-26 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31172 | 31172 | 2020-04-22 09:34 | Test Section | Material Requisition | Geotextile | Terram 1000 4.5m x 100m 1-15 rolls (820795) | 4 | Each | 115.78 | 463.12 | Concrete Drainage | 2020-04-28 | Test Location | Test Section | Test Section | Operational Approval | NULL | NULL | Chris Henry
MREQ-31173 | 31173 | 2020-04-22 10:00 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | No | 8132.02 | 8132.02 | Laboratory Equipment / Certification | 2020-04-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31193 | 31193 | 2020-04-23 03:12 | Section 4 | Material Requisition | Not on List | Not on List | 50 | ea | 5.7 | 285 | Fixings and Fasteners | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31193 | 31193 | 2020-04-23 03:12 | Section 4 | Material Requisition | Not on List | Not on List | 50 | ea | 2.84 | 142 | Fixings and Fasteners | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31193 | 31193 | 2020-04-23 03:12 | Section 4 | Material Requisition | Bagged | Building Sand Bulk Bag (938155) | 10 | Each | 34.94 | 349.4 | Builders Merchants (General) | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31193 | 31193 | 2020-04-23 03:12 | Section 4 | Material Requisition | Bagged | OP Cement; 25kg bag (767201) | 112 | Bags | 3.09 | 346.08 | Builders Merchants (General) | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | No | 3623 | 3623 | Miscellaneous | 2020-04-24 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31202/Request/Invoice 8308058.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31202 | REQ - Finance Team | NULL | NULL
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 66.7 | 66.7 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 38.87 | 38.87 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 37.5 | 37.5 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 37.5 | 37.5 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 36.21 | 36.21 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 38.87 | 38.87 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31203 | 31203 | 2020-04-23 11:59 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 145.26 | 145.26 | Professional Services | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31204 | 31204 | 2020-04-23 13:11 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 157.5 | 157.5 | Miscellaneous | 2020-04-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 121 - Phones / Radios / Comms | IMO - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Ducting | Not on List | 720 | M | 3.2 | 2304 | Plastic Drainage | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Ducting | Not on List | 680 | M | 7.42 | 5045.6 | Plastic Drainage | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Misc | Not on List | 720 | M | 0.05 | 36 | Miscellaneous | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Misc | Not on List | 1440 | M | 0.05 | 72 | Miscellaneous | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Misc | Not on List | 400 | M | 0.05 | 20 | Miscellaneous | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Misc | Not on List | 420 | M | 0.05 | 21 | Miscellaneous | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31206 | 31206 | 2020-04-23 14:26 | Section 6 | Material Requisition | Misc | Not on List | 540 | M | 0.05 | 27 | Miscellaneous | 2020-05-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 2703 - Works on behalf of Statutory Undertakers | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31212 | 31212 | 2020-04-23 17:47 | Section 4 | Material Requisition | Not on List | Not on List | 18 | Each | 20.64 | 371.52 | Plastic Drainage | 2020-04-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31212 | 31212 | 2020-04-23 17:47 | Section 4 | Material Requisition | Not on List | Not on List | 10 | Each | 84.83 | 848.3 | Ductile Drainage | 2020-04-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31230 | 31230 | 2020-04-24 10:51 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 943.48 | 943.48 | Miscellaneous | NaN-NaN-NaN NaN:NaN:NaN | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31233 | 31233 | 2020-04-24 13:13 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 3260 | 3260 | Miscellaneous | 2020-04-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31250 | 31250 | 2020-04-24 16:09 | Core | Material Requisition | Not on List | Not on List | 1 | no | 370 | 370 | Miscellaneous | 2020-04-24 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 500 | Each | 1.61 | 805 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 80 | Each | 3.25 | 260 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 2 | Each | 5.84 | 11.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 2 | Each | 5.84 | 11.68 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 10 | Each | 3.25 | 32.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Drop Kerb HB x BN LH (897468) | 3 | Each | 5.84 | 17.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31270 | 31270 | 2020-04-27 12:20 | Section 3 | Material Requisition | Kerbs | Drop Kerb HB x BN RH (897464) | 3 | Each | 5.84 | 17.52 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31271 | 31271 | 2020-04-27 12:01 | Section 6 | Material Requisition | Not on List | Not on List | 1 | number | 880 | 880 | Miscellaneous | 2020-05-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31288 | 31288 | 2020-04-28 12:20 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Each | 1848.3 | 1848.3 | Miscellaneous | 2020-05-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 154 - Traffic Management & Safety | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
34 | number | 3.21 | 109.14 | Timber Products | 2020-04-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13737 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31289/Request/Fwd Keyline credit.msg | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31289 | REQ - Finance Team | NULL | NULL
6 | Number | 45 | 270 | Surveying Consumables | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31291 | REQ - Finance Team | NULL | NULL
MREQ-31295 | 31295 | 2020-04-28 15:57 | Section 6 | Material Requisition | Misc | Not on List | NULL | NULL | NULL | 0 | Miscellaneous | 2020-05-04 | NULL | NULL | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31297 | 31297 | 2020-04-28 16:07 | Section 2 | Material Requisition | Misc | Not on List | 2 | Each | 5.11 | 10.22 | Miscellaneous | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31303 | 31303 | 2020-04-29 08:31 | Section 2 | Material Requisition | Not on List | Not on List | 1 | each | 1861 | 1861 | Professional Services | 2020-04-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31307 | 31307 | 2020-04-29 09:51 | Section 4 | Material Requisition | Not on List | Not on List | 20 | No | NULL | 0 | NULL | 2020-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31315 | 31315 | 2020-04-29 12:29 | Section 2 | Material Requisition | Twinwall | Polypipe 100mm Linflex 100m (877398) | 3 | Each | 198.95 | 596.85 | Plastic Drainage | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31316 | 31316 | 2020-04-29 13:35 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 HB Straight (898181) | 35 | Each | 3.03 | 106.05 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-04-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31320 | 31320 | 2020-04-29 16:48 | Section 4 | Material Requisition | Bagged | Not on List | 60 | Each | 7.95 | 477 | Builders Merchants (General) | 2020-04-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31325 | 31325 | 2020-04-30 07:23 | Section 5 | Material Requisition | Not on List | Not on List | 30 | Pallet | 2.92 | 87.6 | Builders Merchants (General) | 2020-04-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | SEC5 - Roadworks | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 24 | No | 6.66 | 159.84 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 20 | Prs | 10.97 | 219.4 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 6 | NULL | 3.96 | 23.76 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 6 | NULL | 9.95 | 59.7 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 12 | NULL | 1.5 | 18 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 16.21 | 32.42 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31330 | 31330 | 2020-04-30 08:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 2 | NULL | 14.79 | 29.58 | Small Tools (Consumables) | 2020-05-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31346 | 31346 | 2020-05-01 08:08 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31346 | 31346 | 2020-05-01 08:08 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 69 | 69 | Professional Services | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31346 | 31346 | 2020-05-01 08:08 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | lot | 414.49 | 414.49 | Damage Charges | 2020-05-01 | Gate 4 - 1339605 - Woolley Road Weybridge Farm A1 North Bound Alconbury | A14 IDT | 13966 | Ashtead Plant Hire Company Ltd (1109463) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31347/Buyers/20200512071201917.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31347 | REQ - Finance Team | NULL | NULL
MREQ-31353 | 31353 | 2020-05-01 11:23 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 60 | 60 | Professional Services | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31391 | 31391 | 2020-05-04 12:43 | Section 5 | Material Requisition | Aggregate | 6G | 20 | Tonnes | 22 | 440 | Aggregate | 2020-05-05 | 1358008 - EB5/3, Works Access, A14 Eastbound, Jcn 31 off Slip, Fisheries Access Gate | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31396 | 31396 | 2020-05-04 16:56 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | NULL | 1580 | 1580 | Waste (General) | 2020-05-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-31406 | 31406 | 2020-05-05 08:29 | Section 4 | Material Requisition | Not on List | Not on List | 45 | No | 25.17 | 1132.65 | Concrete Drainage | 2020-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31406 | 31406 | 2020-05-05 08:29 | Section 4 | Material Requisition | Not on List | Not on List | 8 | No | 241.46 | 1931.68 | Plastic Drainage | 2020-05-08 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31409 | 31409 | 2020-05-05 10:17 | Section 6 | Material Requisition | Iron Wear | Not on List | 2 | no | 310.24 | 620.48 | Miscellaneous | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31410 | 31410 | 2020-05-05 10:36 | Section 6 | Material Requisition | Not on List | Not on List | 4 | NULL | 318.9 | 1275.6 | Small Tools (Consumables) | 2020-05-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31410 | 31410 | 2020-05-05 10:36 | Section 6 | Material Requisition | Not on List | Not on List | 5 | No | 4.85 | 24.25 | Small Tools (Consumables) | 2020-05-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31410 | 31410 | 2020-05-05 10:36 | Section 6 | Material Requisition | Not on List | Not on List | 8 | No | 49.16 | 393.28 | Small Tools (Consumables) | 2020-05-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | Ea | 1200 | 1200 | Laboratory Equipment / Certification | 2020-05-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | 10325 | Acoustics Noise & Vibration Lt (1109268) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31414/Request/RE ANV POInvoices.msg | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31414 | REQ - Finance Team | NULL | NULL
MREQ-31419 | 31419 | 2020-05-05 14:13 | Section 6 | Material Requisition | Not on List | Not on List | 1 | Pr | 255.5 | 255.5 | Small Tools (Consumables) | 2020-05-11 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31422 | 31422 | 2020-05-05 16:05 | Section 5 | Material Requisition | Aggregate | Type 1 | 300 | Tonnes | 23.75 | 7125 | Aggregate | 2020-05-07 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31429 | 31429 | 2020-05-06 13:21 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Lot | 1995.84 | 1995.84 | Miscellaneous | 2020-05-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31433 | 31433 | 2020-05-06 13:49 | Section 4 | Material Requisition | Aggregate | Type 1 | 6000 | Tonnes | 23.5 | 141000 | Aggregate | 2020-05-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31446 | 31446 | 2020-05-06 16:04 | Core | Material Requisition | Not on List | Not on List | 1 | no. | 400 | 400 | Surveying Consumables | 2020-05-11 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-31450 | 31450 | 2020-05-07 08:10 | Section 1 | Material Requisition | Misc | Not on List | 2 | No | 19.5 | 39 | Damage Charges | 2020-05-07 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-31450 | 31450 | 2020-05-07 08:10 | Section 1 | Material Requisition | Misc | Not on List | 1 | No | 12.25 | 12.25 | Damage Charges | 2020-05-07 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 702 - Pavement | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-31454 | 31454 | 2020-05-07 07:58 | Section 6 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 40 | Each | 1.61 | 64.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31454 | 31454 | 2020-05-07 07:58 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 650 | Each | 4.93 | 3204.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31454 | 31454 | 2020-05-07 07:58 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 32 | Each | 3.78 | 120.96 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31454 | 31454 | 2020-05-07 07:58 | Section 6 | Material Requisition | Kerbs | Not on List | 6 | Each | 16.17 | 97.02 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31454 | 31454 | 2020-05-07 07:58 | Section 6 | Material Requisition | Kerbs | Not on List | 6 | Each | 15.65 | 93.9 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
150 | Each | 7.1 | 1065 | Miscellaneous | 2020-05-18 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 13964 | SCCS Survey Equipment Ltd t/a (1101886) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31470 | REQ - Finance Team | NULL | NULL
MREQ-31471 | 31471 | 2020-05-07 14:50 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 7532.6 | 7532.6 | Miscellaneous | 2020-05-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31509 | 31509 | 2020-05-11 16:09 | Section 4 | Material Requisition | Not on List | Not on List | 61000 | Litres | 0.35 | 21350 | Gas Oil | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31510 | 31510 | 2020-05-11 16:17 | Section 4 | Material Requisition | Not on List | Not on List | 430000 | Litres | 0.35 | 150500 | Gas Oil | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31518 | 31518 | 2020-05-12 11:12 | Section 5 | Material Requisition | Not on List | Not on List | 1 | NUMBER | 139.2 | 139.2 | Miscellaneous | 2020-05-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31522 | 31522 | 2020-05-12 15:16 | Section 4 | Material Requisition | Not on List | Not on List | 16 | Kg | 1.3 | 20.8 | Miscellaneous | 2020-05-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 90 | 90 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31535 | 31535 | 2020-05-13 08:25 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 235 | 235 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31536 | 31536 | 2020-05-13 10:40 | Section 5 | Material Requisition | Not on List | Not on List | 1 | £ | 1890 | 1890 | Professional Services | 2020-05-13 | 1358005 - WB5/7 Works Access - 1356563 - A14 Westbound, On Left between Jcn 32 - 31 | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Approval | Yes - Approve | NULL | Req - S5 Buyers
1 | No | 102 | 102 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13973 | L Lynch (Plant Hire & Haulage) (1112290) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31538/Request/Advice Note N06-667828.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31538 | REQ - Finance Team | NULL | NULL
MREQ-31538 | 31538 | 2020-05-13 11:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 115 | 115 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | No | 69 | 69 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13973 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31538/Request/DOC200420-20042020185334 (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31538 | REQ - Finance Team | NULL | NULL
MREQ-31538 | 31538 | 2020-05-13 11:35 | Section 4 | Material Requisition | Not on List | Not on List | 58 | LT | 0.8 | 46.4 | Gas Oil | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
180 | LT | 0.8 | 144 | Gas Oil | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13973 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31538 | REQ - Finance Team | NULL | NULL
1 | No | 82.8 | 82.8 | Professional Services | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 13973 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31538 | REQ - Finance Team | NULL | NULL
MREQ-31538 | 31538 | 2020-05-13 11:35 | Section 4 | Material Requisition | Not on List | Not on List | 55 | LT | 0.8 | 44 | Gas Oil | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31540 | 31540 | 2020-05-13 12:32 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 90 | Each | 5.55 | 499.5 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31540 | 31540 | 2020-05-13 12:32 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 15 | Each | 4.75 | 71.25 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31540 | 31540 | 2020-05-13 12:32 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 5 | Each | 13.32 | 66.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31540 | 31540 | 2020-05-13 12:32 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 5 | Each | 13.32 | 66.6 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31545 | 31545 | 2020-05-13 14:23 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 258.75 | 258.75 | Professional Services | 2020-05-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Passed Back | Yes - Approve | No - Pass Back | Req - S2 Buyers
1 | No | 86.25 | 86.25 | Professional Services | 2020-05-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Commercial Passed Back | Yes - Approve | No - Pass Back | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31545/Request/Scan_20200424_151518.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31545 | REQ - Finance Team | NULL | NULL
115 | LT | 1.8 | 207 | Gas Oil | 2020-05-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Commercial Passed Back | Yes - Approve | No - Pass Back | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31545 | REQ - Finance Team | NULL | NULL
MREQ-31546 | 31546 | 2020-05-13 15:09 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 95 | 95 | Professional Services | 2020-05-29 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-31547 | 31547 | 2020-05-13 15:26 | Section 6 | Material Requisition | Not on List | Not on List | 118 | LT | 0.8 | 94.4 | Gas Oil | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Commercial Rejected | Yes - Approve | No - Reject | Req - S6 Buyers
MREQ-31556 | 31556 | 2020-05-14 10:13 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Number | 3623 | 3623 | Miscellaneous | 2020-05-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31557 | 31557 | 2020-05-14 10:39 | Section 4 | Material Requisition | Bagged | Kiln Dried Sand 25kg (518674) | 25 | Each | 2.4 | 60 | Builders Merchants (General) | 2020-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 40 | Each | 20.64 | 825.6 | Plastic Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 35 | Each | 3.31 | 115.85 | Plastic Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain Seal (346385) | 70 | Each | 1.63 | 114.1 | Plastic Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm x 150mm 45deg Junction (878010) | 12 | Each | 30.02 | 360.24 | Plastic Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Not on List | Not on List | 15 | No | 70.18 | 1052.7 | Ductile Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31559 | 31559 | 2020-05-14 12:55 | Section 4 | Material Requisition | Not on List | Not on List | 12 | No | 31.05 | 372.6 | Plastic Drainage | 2020-05-19 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31561 | 31561 | 2020-05-14 16:08 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 700 | Each | 3.25 | 2275 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31561 | 31561 | 2020-05-14 16:08 | Section 4 | Material Requisition | Kerbs | Drop Kerb HB x BN LH (897468) | 10 | Each | 5.84 | 58.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31561 | 31561 | 2020-05-14 16:08 | Section 4 | Material Requisition | Kerbs | Drop Kerb HB x BN RH (897464) | 10 | Each | 5.84 | 58.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31570 | 31570 | 2020-05-14 17:33 | Section 6 | Material Requisition | Not on List | Not on List | 1 | Area | NULL | 0 | Miscellaneous | 2020-05-20 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 106 - Testing equipment and materials testing | Commercial Rejected | Yes - Approve | No - Reject | Req - S6 Buyers
MREQ-31582 | 31582 | 2020-05-15 10:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | £ | 1713.6 | 1713.6 | Professional Services | 2020-05-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 106 - Testing equipment and materials testing | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 885 | Each | 4.93 | 4363.05 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Transition Kerbs 125x255 (947297) | 4 | Each | 5.84 | 23.36 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Transition Kerbs 125x255 (947297) | 3 | Each | 5.84 | 17.52 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 460 | Each | 3.78 | 1738.8 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 4 | Each | 10.83 | 43.32 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 4 | Each | 10.83 | 43.32 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 480 | Each | 1.61 | 772.8 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 32 | Each | 3.25 | 104 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 305 Channel 500mm (758908) | 242 | Each | 17.85 | 4319.7 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 305 Access Unit (947299) | 3 | Each | 30.32 | 90.96 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Not on List | 1 | Each | 221.75 | 221.75 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Not on List | 1 | Each | 221.75 | 221.75 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 305 Dropper LH (758901) | 1 | Each | 31.81 | 31.81 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 305 Dropper RH (758907) | 1 | Each | 31.81 | 31.81 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 305 Center Stone (758899) | 6 | Each | 27.56 | 165.36 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Not on List | 1 | Each | 221.75 | 221.75 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Combined Drainage | Kerb Drain 405 Channel 1000mm (947299) | 15 | Each | 39.14 | 587.1 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 19 | Each | 5.84 | 110.96 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Not on List | 13 | Each | 16.17 | 210.21 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Kerbs | Not on List | 4 | NULL | 15.65 | 62.6 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 288 | No | 4.42 | 1272.96 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 336 | No | 4.42 | 1485.12 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 252 | No | 6.29 | 1585.08 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31588 | 31588 | 2020-05-15 09:41 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 35 | No | 6.29 | 220.15 | Blocks and Bricks | 2020-06-01 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31621 | 31621 | 2020-05-18 11:05 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 72 | meters | 32.19 | 2317.68 | Plastic Drainage | 2020-05-21 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 3030 - Special Ecological Measures | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31623 | 31623 | 2020-05-18 12:59 | Core | Material Requisition | Not on List | Not on List | 1 | No | 9016.63 | 9016.63 | Miscellaneous | 2020-05-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31623 | 31623 | 2020-05-18 12:59 | Core | Material Requisition | Not on List | Not on List | 1 | No | 3364.58 | 3364.58 | Miscellaneous | 2020-05-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31623 | 31623 | 2020-05-18 12:59 | Core | Material Requisition | Not on List | Not on List | 1 | No | 6038.34 | 6038.34 | Miscellaneous | 2020-05-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31631 | 31631 | 2020-05-18 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | NULL | 22613.41 | 22613.41 | Damage Charges | 2020-05-21 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | BES4 - Existing Structures | 1802 - Miscellaneous Metalwork | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31632 | 31632 | 2020-05-18 16:36 | Section 4 | Material Requisition | Concrete Drainage | CPM 1200mm Concrete Pipe 2.5m (249379) | 21 | Each | 529.05 | 11110.05 | Concrete Drainage | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31632 | 31632 | 2020-05-18 16:36 | Section 4 | Material Requisition | Concrete Drainage | CPM 1200mm Concrete Rocker (249380) | 2 | Each | 634.85 | 1269.7 | Concrete Drainage | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31632 | 31632 | 2020-05-18 16:36 | Section 4 | Material Requisition | Concrete Drainage | CPM 1200mm Concrete Spigot (249382) | 2 | Each | 634.85 | 1269.7 | Concrete Drainage | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31634 | 31634 | 2020-05-18 17:06 | Section 4 | Material Requisition | Not on List | Not on List | 1 | £ | 7225 | 7225 | Professional Services | 2020-05-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-31647 | 31647 | 2020-05-19 09:46 | Section 4 | Material Requisition | Not on List | Not on List | 5 | rolls | 3674 | 18370 | Builders Merchants (General) | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31647 | 31647 | 2020-05-19 09:46 | Section 4 | Material Requisition | Not on List | Not on List | 600 | numbers | 2.55 | 1530 | Builders Merchants (General) | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31647 | 31647 | 2020-05-19 09:46 | Section 4 | Material Requisition | Not on List | Not on List | 3 | Box | 40.31 | 120.93 | Builders Merchants (General) | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31652 | 31652 | 2020-05-19 13:54 | Section 6 | Material Requisition | Bagged | Sharp Sand Bulk Bag (938208) | 4 | Each | 34.94 | 139.76 | Builders Merchants (General) | 2020-05-21 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | Pallet | 3.79 | 3.79 | Miscellaneous | 2020-05-21 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 13987 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31652 | REQ - Finance Team | NULL | NULL
MREQ-31652 | 31652 | 2020-05-19 13:54 | Section 6 | Material Requisition | Twinwall | Polypipe 150mm x 25m Ridgiflex (877588) | 6 | meters | 164.84 | 989.04 | Ductile Drainage | 2020-05-21 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31652 | 31652 | 2020-05-19 13:54 | Section 6 | Material Requisition | Twinwall | Not on List | 1 | bag | 248.4 | 248.4 | Ductile Drainage | 2020-05-21 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31652 | 31652 | 2020-05-19 13:54 | Section 6 | Material Requisition | Not on List | Not on List | 1 | pallet | 4.31 | 4.31 | Concrete Drainage | 2020-05-21 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31656 | 31656 | 2020-05-19 15:05 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 28921.05 | 28921.05 | Miscellaneous | 2020-05-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31660 | 31660 | 2020-05-19 17:30 | Section 5 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 23.5 | 11750 | Aggregate | 2020-05-21 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | SEC5 - Roadworks | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31667 | 31667 | 2020-05-20 11:12 | Section 4 | Material Requisition | Not on List | Not on List | 12 | No | 84.83 | 1017.96 | Ductile Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31678 | 31678 | 2020-05-20 16:33 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 25 | 75 | Professional Services | 2020-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31678 | 31678 | 2020-05-20 16:33 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Np | 50 | 50 | Professional Services | 2020-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31683 | 31683 | 2020-05-20 17:27 | Section 4 | Material Requisition | Not on List | Not on List | 12 | No | 27.96 | 335.52 | Plastic Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31683 | 31683 | 2020-05-20 17:27 | Section 4 | Material Requisition | Not on List | Not on List | 16 | No | 39.87 | 637.92 | Plastic Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31683 | 31683 | 2020-05-20 17:27 | Section 4 | Material Requisition | Not on List | Not on List | 16 | No | 70.58 | 1129.28 | Plastic Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31683 | 31683 | 2020-05-20 17:27 | Section 4 | Material Requisition | Not on List | Not on List | 10 | No | 93.88 | 938.8 | Plastic Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31683 | 31683 | 2020-05-20 17:27 | Section 4 | Material Requisition | Not on List | Not on List | 10 | No | 101.24 | 1012.4 | Plastic Drainage | 2020-05-27 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31686 | 31686 | 2020-05-20 18:15 | Section 4 | Material Requisition | Aggregate | Type 1 | 5000 | Tonnes | 21.65 | 108250 | Aggregate | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 701 - Sub-base | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31688 | 31688 | 2020-05-20 19:24 | Core | Material Requisition | Not on List | Not on List | 1 | Ea | 10611.02 | 10611.02 | Miscellaneous | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31688 | 31688 | 2020-05-20 19:24 | Core | Material Requisition | Not on List | Not on List | 1 | Ea | 4378 | 4378 | Miscellaneous | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31688 | 31688 | 2020-05-20 19:24 | Core | Material Requisition | Not on List | Not on List | 1 | Ea | 14304 | 14304 | Miscellaneous | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31688 | 31688 | 2020-05-20 19:24 | Core | Material Requisition | Not on List | Not on List | 1 | Ea | 1054.7 | 1054.7 | Miscellaneous | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31688 | 31688 | 2020-05-20 19:24 | Core | Material Requisition | Not on List | Not on List | 1 | Ea | 4187 | 4187 | Miscellaneous | 2020-05-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31695 | 31695 | 2020-05-21 12:40 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 99.96 | 99.96 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31695 | 31695 | 2020-05-21 12:40 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 456 | 456 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31696 | 31696 | 2020-05-21 13:13 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 146.72 | 146.72 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31697 | 31697 | 2020-05-21 13:32 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 113 | 113 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31697 | 31697 | 2020-05-21 13:32 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 676.95 | 676.95 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31698 | 31698 | 2020-05-21 13:38 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 150 | 150 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31698 | 31698 | 2020-05-21 13:38 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 150 | 150 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
1 | NULL | 297 | 297 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31699/Request/Invoice ALARM Ltd.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31699 | REQ - Finance Team | NULL | NULL
MREQ-31701 | 31701 | 2020-05-21 13:56 | Section 4 | Material Requisition | Not on List | Not on List | 1 | number | 88.11 | 88.11 | Surveying Consumables | 2020-05-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31702 | 31702 | 2020-05-21 13:51 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 65 | 65 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31703 | 31703 | 2020-05-21 14:11 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1908 | 1908 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31704 | 31704 | 2020-05-21 14:21 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1440 | 1440 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31707 | 31707 | 2020-05-21 15:02 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 53.72 | 53.72 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31708 | 31708 | 2020-05-21 15:05 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 345 | 345 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31709 | 31709 | 2020-05-21 15:10 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 90 | 90 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31710 | 31710 | 2020-05-21 15:15 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 4000 | 4000 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31711 | 31711 | 2020-05-21 15:24 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 3219.1 | 3219.1 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31712 | 31712 | 2020-05-21 15:27 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 395 | 395 | Miscellaneous | 2020-05-21 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31735 | 31735 | 2020-05-22 13:51 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Batch | 3789 | 3789 | Flow Control | 2020-05-29 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31741 | 31741 | 2020-05-22 16:18 | Section 6 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 21.25 | 4250 | Aggregate | 2020-05-26 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31763 | 31763 | 2020-05-26 10:05 | Section 4 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain 6m P/E Unperf (877593) | 25 | Each | 20.64 | 516 | Plastic Drainage | 2020-05-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31765 | 31765 | 2020-05-26 11:09 | Section 4 | Material Requisition | Not on List | Not on List | 2 | Number | 404.13 | 808.26 | Plastic Drainage | 2020-05-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31769 | 31769 | 2020-05-26 09:33 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 446.6 | 446.6 | Miscellaneous | 2020-05-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31780 | 31780 | 2020-05-27 08:13 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 2467.43 | 2467.43 | Small Tools (Consumables) | 2020-05-29 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31785 | 31785 | 2020-05-27 09:52 | Section 4 | Material Requisition | Not on List | Not on List | 30 | No. | 13.62 | 408.6 | Janitorial | 2020-05-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31789 | 31789 | 2020-05-27 14:58 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 40 | Each | 6.6 | 264 | Blocks and Bricks | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31789 | 31789 | 2020-05-27 14:58 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 HB External Radius (947297) | 30 | Each | 5.83 | 174.9 | Blocks and Bricks | 2020-05-29 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 10 | Each | 25.17 | 251.7 | Concrete Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Twinwall | Polypipe 300mm Ridgidrain 6m P/E Unperf (179562) | 6 | Each | 78.67 | 472.02 | Plastic Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Twinwall | Polypipe 300mm Ridgidrain Coupler (878109) | 12 | Each | 12.37 | 148.44 | Plastic Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Twinwall | Polypipe 300mm Ridgidrain Seal (346388) | 24 | Each | 5.41 | 129.84 | Plastic Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Saint Gobain Castings | 600x600x150 D400 Inter Ax Manhole Cover (766618) | 5 | Each | 98.48 | 492.4 | Plastic Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Saint Gobain Castings | 454x454x100 D400 Watershed GG&F (257790) | 12 | Each | 62.04 | 744.48 | Plastic Drainage | 2020-06-01 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
1 | number | 1650 | 1650 | Flow Control | 2020-06-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | Skyland Contractors Ltd | 14006 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | Althon Ltd 1140767 | /sites/BPM/FlowForma/FormDocuments/MREQ31790/Request/Weir-Orifice Plate and Rolled Steel Angle.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31790 | REQ - Finance Team | NULL | NULL
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Misc | Not on List | 18 | number | NULL | 0 | Flow Control | 2020-06-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Operations Passed Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-31790 | 31790 | 2020-05-27 14:37 | Section 5 | Material Requisition | Misc | Not on List | 1 | number | NULL | 0 | Flow Control | 2020-06-12 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SEC5 - Roadworks | 503 - Headwalls and Outfall Works | Operations Passed Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-31804 | 31804 | 2020-05-28 12:36 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 240 | Each | 3.78 | 907.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31804 | 31804 | 2020-05-28 12:36 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 90 | Each | 4.93 | 443.7 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-05-29 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31819 | 31819 | 2020-05-29 10:27 | Section 4 | Material Requisition | Misc | Not on List | 10 | number | 52.66 | 526.6 | Builders Merchants (General) | 2020-06-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31826 | 31826 | 2020-05-29 15:17 | Section 6 | Material Requisition | Not on List | Not on List | 2 | TINS | 63.89 | 127.78 | Builders Merchants (General) | 2020-06-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | S6SF - Station Forecourt | 2703 - Works on behalf of Statutory Undertakers | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
11 | number | 47.57 | 523.27 | Builders Merchants (General) | 2020-06-04 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | Skyland Contractors Ltd | 14025 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ31828/Request/H259ps1i1.zip | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31828 | REQ - Finance Team | NULL | NULL
MREQ-31828 | 31828 | 2020-05-29 15:18 | Section 2 | Material Requisition | Aggregate | 6G | 60 | Tonnes | 32.9 | 1974 | Aggregate | 2020-06-04 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31854 | 31854 | 2020-06-01 09:56 | Core | Material Requisition | Not on List | Not on List | 1 | No | 50484.8 | 50484.8 | Miscellaneous | 2020-06-04 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | NULL | 153 - Temporary Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31855 | 31855 | 2020-06-01 12:03 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 103.75 | 103.75 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31855 | 31855 | 2020-06-01 12:03 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 96.8 | 96.8 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31855 | 31855 | 2020-06-01 12:03 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 86.9 | 86.9 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31855 | 31855 | 2020-06-01 12:03 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 52.5 | 52.5 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
50 | each | 62.04 | 3102 | Ductile Drainage | 2020-06-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 14015 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31868 | REQ - Finance Team | NULL | NULL
35 | each | 62.04 | 2171.4 | Ductile Drainage | 2020-06-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 14015 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31868 | REQ - Finance Team | NULL | NULL
4 | each | 62.04 | 248.16 | Ductile Drainage | 2020-06-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 14015 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31868 | REQ - Finance Team | NULL | NULL
1 | each | 62.04 | 62.04 | Ductile Drainage | 2020-06-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | Skyland Contractors Ltd | 14015 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31868 | REQ - Finance Team | NULL | NULL
MREQ-31877 | 31877 | 2020-06-03 14:04 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 19853 | 19853 | Miscellaneous | 2020-06-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 119 - Cleaning Sub.Con | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31880 | 31880 | 2020-06-03 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31880 | 31880 | 2020-06-03 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31880 | 31880 | 2020-06-03 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 70 | 70 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31880 | 31880 | 2020-06-03 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 160 | 160 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31880 | 31880 | 2020-06-03 14:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 200 | 200 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31882 | 31882 | 2020-06-04 16:33 | Section 6 | Material Requisition | Not on List | Not on List | 600 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-06-05 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31882 | 31882 | 2020-06-04 16:33 | Section 6 | Material Requisition | Not on List | Not on List | 120 | m3 | NULL | 0 | Ready Mixed Concrete | 2020-06-05 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31883 | 31883 | 2020-06-04 16:41 | Section 6 | Material Requisition | Aggregate | Not on List | 98.4 | ton | 32.9 | 3237.36 | Aggregate | 2020-06-05 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-31907 | 31907 | 2020-06-05 11:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | ea | 6713.96 | 6713.96 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31907 | 31907 | 2020-06-05 11:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | ea | 250 | 250 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31907 | 31907 | 2020-06-05 11:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | ea | 550 | 550 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31952 | 31952 | 2020-06-08 19:39 | Core | Material Requisition | Not on List | Not on List | 1 | No | 1625 | 1625 | Laboratory Equipment / Certification | 2020-06-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-31954 | 31954 | 2020-06-09 07:16 | Section 4 | Material Requisition | Not on List | Not on List | 250 | NULL | 7.1 | 1775 | Miscellaneous | 2020-06-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31962 | 31962 | 2020-06-09 10:50 | Section 4 | Material Requisition | Misc | Not on List | 2 | box | 10.5 | 21 | Miscellaneous | 2020-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 142.5 | 142.5 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 181.96 | 181.96 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 155.76 | 155.76 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 128.48 | 128.48 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 108.39 | 108.39 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 133.38 | 133.38 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 167.32 | 167.32 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 114.85 | 114.85 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 89.32 | 89.32 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 623.96 | 623.96 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 194.4 | 194.4 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31963 | 31963 | 2020-06-09 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 680.09 | 680.09 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31966 | 31966 | 2020-06-09 11:39 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 491.92 | 491.92 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31966 | 31966 | 2020-06-09 11:39 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 379.32 | 379.32 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-31966 | 31966 | 2020-06-09 11:39 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 3814.25 | 3814.25 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
1 | No | 103.53 | 103.53 | Concrete Accessories | 2020-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14037 | Ashtead Plant Hire Company Ltd (1109463) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | Sunbelt rentals | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31967 | REQ - Finance Team | NULL | NULL
MREQ-31968 | 31968 | 2020-06-09 12:42 | Section 6 | Material Requisition | Not on List | Not on List | 1 | NULL | 1559.94 | 1559.94 | Office Supplies | 2020-06-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-31968 | 31968 | 2020-06-09 12:42 | Section 6 | Material Requisition | Not on List | Not on List | 6 | ea | 12.74 | 76.44 | Office Supplies | 2020-06-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Operational Approval | NULL | NULL | Req - S6 Buyers
1 | Number | NULL | 0 | PPE | 2020-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31969 | REQ - Finance Team | NULL | NULL
1 | Number | NULL | 0 | PPE | 2020-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31969 | REQ - Finance Team | NULL | NULL
1 | Number | NULL | 0 | PPE | 2020-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31969 | REQ - Finance Team | NULL | NULL
MREQ-31979 | 31979 | 2020-06-09 16:58 | Section 4 | Material Requisition | Saint Gobain Castings | Not on List | 7 | Number | 74.26 | 519.82 | Ductile Drainage | 2020-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31982 | 31982 | 2020-06-10 08:06 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 45 | 45 | Professional Services | 2020-06-26 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-31983 | 31983 | 2020-06-10 08:13 | Section 2 | Material Requisition | Not on List | Not on List | 4 | No | 45 | 180 | Miscellaneous | 2020-06-26 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-31987 | 31987 | 2020-06-10 10:58 | Section 4 | Material Requisition | Twinwall | Polypipe Road Gully 450mm x 900mm (573005) | 20 | Each | 31.05 | 621 | Plastic Drainage | 2020-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31987 | 31987 | 2020-06-10 10:58 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 20 | No | 6.95 | 139 | Plastic Drainage | 2020-06-11 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31987 | 31987 | 2020-06-10 10:58 | Section 4 | Material Requisition | Saint Gobain Castings | Not on List | 10 | number | 43.58 | 435.8 | Ductile Drainage | 2020-06-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-31987 | 31987 | 2020-06-10 10:58 | Section 4 | Material Requisition | Saint Gobain Castings | Not on List | 10 | number | 43.58 | 435.8 | Ductile Drainage | 2020-06-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
100 | box of 100 | 45.04 | 4504 | Miscellaneous | 2020-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | op 14046 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31991 | REQ - Finance Team | NULL | NULL
100 | box of 100 | 83.15 | 8315 | Miscellaneous | 2020-06-12 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | op 14046 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31991 | REQ - Finance Team | NULL | NULL
MREQ-31996 | 31996 | 2020-06-11 08:48 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 3 | NULL | NULL | 0 | PPE | 2020-06-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32000 | 32000 | 2020-06-11 09:21 | Section 4 | Material Requisition | Concrete Drainage | CPM 1200 Cover Slab 600x600 Opening (989585) | 3 | Each | 100.77 | 302.31 | Concrete Drainage | 2020-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32000 | 32000 | 2020-06-11 09:21 | Section 4 | Material Requisition | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 6 | Each | 84.83 | 508.98 | Ductile Drainage | 2020-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32000 | 32000 | 2020-06-11 09:21 | Section 4 | Material Requisition | Concrete Drainage | Not on List | 2 | Each | 1224.54 | 2449.08 | Concrete Drainage | 2020-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
3000 | m3 | NULL | 0 | Miscellaneous | 2020-06-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operations Rejected | No - Reject | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32002 | REQ - Finance Team | NULL | NULL
0 | 0 | 0 | 0 | Miscellaneous | 2020-06-15 | RVP 405/407 - 1339623 - Robin's Lane A14 J28A Westbound | A14 IDT | 14049 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32003/Commercial-Approval/Topsoil - G. Webb Quote.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32003 | REQ - Finance Team | NULL | NULL
MREQ-32013 | 32013 | 2020-06-12 13:01 | Section 4 | Material Requisition | Not on List | Not on List | 20 | number | 47.57 | 951.4 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32013 | 32013 | 2020-06-12 13:01 | Section 4 | Material Requisition | Not on List | Not on List | 5 | number | 40 | 200 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32013 | 32013 | 2020-06-12 13:01 | Section 4 | Material Requisition | Aggregate | 6G | 60 | Tonnes | 22 | 1320 | Aggregate | 2020-06-25 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32053 | 32053 | 2020-06-15 08:58 | Section 4 | Material Requisition | Aggregate | Type 1 | 400 | Tonnes | 23.5 | 9400 | Aggregate | 2020-06-16 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32053 | 32053 | 2020-06-15 08:58 | Section 4 | Material Requisition | Aggregate | Type 1 | 300 | Tonnes | 23.5 | 7050 | Aggregate | 2020-06-17 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32053 | 32053 | 2020-06-15 08:58 | Section 4 | Material Requisition | Aggregate | Type 1 | 300 | Tonnes | 23.5 | 7050 | Aggregate | 2020-06-18 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4C - Roadworks - Dry Drayton to Girton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32055 | 32055 | 2020-06-15 10:09 | Section 4 | Material Requisition | Misc | Not on List | 7 | tubs | NULL | 0 | Miscellaneous | 2020-06-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32059 | 32059 | 2020-06-15 11:38 | Section 4 | Material Requisition | Not on List | Not on List | 2 | 12 kg tubs | 49.38 | 98.76 | Builders Merchants (General) | 2020-06-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | Licence | 3500 | 3500 | Surveying Consumables | 2020-06-19 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | 14052 | Korec (1114049) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32062 | REQ - Finance Team | NULL | NULL
MREQ-32063 | 32063 | 2020-06-15 14:30 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-06-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32064 | 32064 | 2020-06-15 15:24 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-06-17 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32064 | 32064 | 2020-06-15 15:24 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-06-18 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32064 | 32064 | 2020-06-15 15:24 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-06-19 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32085 | 32085 | 2020-06-16 17:09 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 15 | Each | 8.08 | 121.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-06-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32086 | 32086 | 2020-06-17 11:02 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 973.42 | 973.42 | Professional Services | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32090 | 32090 | 2020-06-17 14:28 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 2231.82 | 2231.82 | Miscellaneous | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32090 | 32090 | 2020-06-17 14:28 | Section 5 | Material Requisition | Not on List | Not on List | 13 | no | 76.48 | 994.24 | Miscellaneous | 2020-06-26 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Paint Spartan Pro Line Marking 750ml Red (742163) | 12 | Each | 6.7 | 80.4 | Surveying Consumables | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Paint Spot Marking Contractor Red 750ml Ref 43083 (742167) | 12 | Each | 3.03 | 36.36 | Surveying Consumables | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Tape Gaffa Waterproof Cloth Black 50mm X 50mtr (764674) | 12 | Each | 4.1 | 49.2 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Cable Tie Plastic Black 300mm X 4.8mm Pack Of 100 Spartan (230061) | 10 | Each | 1.94 | 19.4 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Line Brick Masons 100m Pink Bl100hv Ref 27428 Spartan (767804) | 10 | Each | 7.72 | 77.2 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32097 | 32097 | 2020-06-18 07:54 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Broom Head Natural Coco Fibre Size 250mm/10" Flat Stock (502031) | 10 | Each | 1.79 | 17.9 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 120 - Small Tools (hand) | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
150 | NULL | 6.93 | 1039.5 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14064 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32097 | REQ - Finance Team | NULL | NULL
5 | NULL | 18.43 | 92.15 | Miscellaneous | 2020-06-22 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14064 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32097 | REQ - Finance Team | NULL | NULL
MREQ-32099 | 32099 | 2020-06-18 08:23 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 3300 | 3300 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32099 | 32099 | 2020-06-18 08:23 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 5930 | 5930 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 45 | 45 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 65 | 65 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 130 | 130 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 45 | 45 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 65 | 65 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32100 | 32100 | 2020-06-18 08:38 | Section 4 | Material Requisition | Not on List | Not on List | 8 | Hrs | 65 | 520 | Professional Services | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
3 | NULL | 32.48 | 97.44 | Small Tools (Consumables) | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14069 | Ashtead Plant Hire Company Ltd (1109463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32108 | REQ - Finance Team | NULL | NULL
10 | NULL | 0.72 | 7.2 | Small Tools (Consumables) | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14066 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32108 | REQ - Finance Team | NULL | NULL
10 | NULL | 0.82 | 8.2 | Small Tools (Consumables) | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14066 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32108 | REQ - Finance Team | NULL | NULL
6 | NULL | 0.71 | 4.26 | Small Tools (Consumables) | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14066 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32108 | REQ - Finance Team | NULL | NULL
6 | NULL | 0.47 | 2.82 | Small Tools (Consumables) | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14066 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32108 | REQ - Finance Team | NULL | NULL
MREQ-32123 | 32123 | 2020-06-19 13:05 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 10648.5 | 10648.5 | Miscellaneous | 2020-06-19 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32165 | 32165 | 2020-06-22 11:27 | Section 2 | Material Requisition | Misc | Not on List | 1 | No | NULL | 0 | Damage Charges | 2020-06-22 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32192 | 32192 | 2020-06-24 07:55 | Section 4 | Material Requisition | Not on List | Not on List | 36 | number | 7.4 | 266.4 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-06-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32196 | 32196 | 2020-06-24 08:35 | Section 1 | Material Requisition | Not on List | Not on List | 1 | lot | 3324.91 | 3324.91 | Rebar and Mesh | 2020-06-29 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32199 | 32199 | 2020-06-24 11:26 | Section 6 | Material Requisition | Misc | Not on List | 1 | no | 2097 | 2097 | Ductile Drainage | 2020-06-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32202 | 32202 | 2020-06-24 14:19 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 3 | Each | 180 | 540 | Small Tools (Consumables) | 2020-06-25 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32215 | 32215 | 2020-06-25 10:31 | Section 4 | Material Requisition | Aggregate | Type 1 | 500 | Tonnes | 23.5 | 11750 | Aggregate | 2020-06-26 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32217 | 32217 | 2020-06-25 11:38 | Section 6 | Material Requisition | Not on List | Not on List | 1 | Number | 390 | 390 | Miscellaneous | 2020-06-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 202 - Demolition | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32230 | 32230 | 2020-06-25 15:14 | Section 3 | Material Requisition | Misc | Not on List | 3 | No | 45 | 135 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32230 | 32230 | 2020-06-25 15:14 | Section 3 | Material Requisition | Misc | Not on List | 1 | No | 14 | 14 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32230 | 32230 | 2020-06-25 15:14 | Section 3 | Material Requisition | Misc | Not on List | 1 | No | 18 | 18 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32230 | 32230 | 2020-06-25 15:14 | Section 3 | Material Requisition | Misc | Not on List | 1 | No | 14 | 14 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32230 | 32230 | 2020-06-25 15:14 | Section 3 | Material Requisition | Misc | Not on List | 1 | No | 18 | 18 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32237 | 32237 | 2020-06-26 08:59 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 43262 | 43262 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32237 | 32237 | 2020-06-26 08:59 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 66560 | 66560 | Miscellaneous | 2020-06-26 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32237 | 32237 | 2020-06-26 08:59 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 44800 | 44800 | Miscellaneous | 2020-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32237 | 32237 | 2020-06-26 08:59 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 48384 | 48384 | Miscellaneous | 2020-06-26 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | PRLM - Preliminaries | 102 - Compound running costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32238 | 32238 | 2020-06-26 11:14 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32239 | 32239 | 2020-06-26 11:55 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No. | 43262 | 43262 | Miscellaneous | 2020-06-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32240 | 32240 | 2020-06-26 11:58 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 66560 | 66560 | Miscellaneous | 2020-06-26 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32241 | 32241 | 2020-06-26 12:00 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No. | 44800 | 44800 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32242 | 32242 | 2020-06-26 12:04 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No. | 48384 | 48384 | Miscellaneous | 2020-06-26 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 102 - Compound running costs | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32245 | 32245 | 2020-06-26 15:02 | Section 3 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 200 | Each | 2.48 | 496 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-06-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32245 | 32245 | 2020-06-26 15:02 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 36 | Each | 5.55 | 199.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-06-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32245 | 32245 | 2020-06-26 15:02 | Section 3 | Material Requisition | Not on List | Not on List | 16 | ea | 21.1 | 337.6 | Builders Merchants (General) | 2020-06-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32245 | 32245 | 2020-06-26 15:02 | Section 3 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 18 | Each | 6.34 | 114.12 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-06-29 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32272 | 32272 | 2020-06-29 12:33 | Section 6 | Material Requisition | Not on List | Not on List | 5 | NULL | 7.95 | 39.75 | Surveying Consumables | 2020-06-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 113 - Survey Equipment Costs | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 300 | Each | 6 | 1800 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop L/H (898584) | 2 | Each | 11.94 | 23.88 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 150x125 Sply - BN Drop R/H (899183) | 2 | Each | 11.94 | 23.88 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255x914 HB2 Straight (753046) | 300 | Each | 3.52 | 1056 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 2 | Each | 7.68 | 15.36 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 2 | Each | 7.68 | 15.36 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs 125x150x914 BN Straight (753034) | 30 | Each | 3.03 | 90.9 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 30 | Each | 6 | 180 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 75 | Each | 6 | 450 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 80 | Each | 6 | 480 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32274 | 32274 | 2020-06-29 11:40 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 70 | Each | 6 | 420 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
80.08 | m2 | 69.5 | 5565.56 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | JP Flynn Construction Ltd | 14105 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32274 | REQ - Finance Team | NULL | NULL
55.44 | m2 | 69.54 | 3855.3 | Blocks and Bricks | 2020-07-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | JP Flynn Construction Ltd | 14105 | NULL | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32274 | REQ - Finance Team | NULL | NULL
MREQ-32277 | 32277 | 2020-06-29 16:36 | Section 4 | Material Requisition | Saint Gobain Castings | 600x600x100 D400 Inter Ax Manhole Cover (766602) | 10 | Each | 84.83 | 848.3 | Ductile Drainage | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32277 | 32277 | 2020-06-29 16:36 | Section 4 | Material Requisition | Not on List | Not on List | 8 | Each | 65.73 | 525.84 | Rebar and Mesh | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 503 - Headwalls and Outfall Works | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
35 | Each | 27.21 | 952.35 | Flow Control | 2020-07-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14089 | Keyline Builders Merchants Ltd (1100980) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32283 | REQ - Finance Team | NULL | NULL
MREQ-32287 | 32287 | 2020-06-30 10:56 | Section 4 | Material Requisition | Concrete Drainage | CPM Chamber Ring 2400 x 1000 D/S (890451) | 2 | Each | 415.34 | 830.68 | Concrete Accessories | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32287 | 32287 | 2020-06-30 10:56 | Section 4 | Material Requisition | Concrete Drainage | CPM Chamber Ring 2400 x 500 D/S (890449) | 1 | Each | 285.72 | 285.72 | Concrete Accessories | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32287 | 32287 | 2020-06-30 10:56 | Section 4 | Material Requisition | Concrete Drainage | Not on List | 1 | NULL | 1224.54 | 1224.54 | Concrete Accessories | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32289 | 32289 | 2020-06-30 11:21 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 291.03 | 291.03 | Professional Services | 2020-06-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32290 | 32290 | 2020-06-30 11:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 114.87 | 114.87 | Professional Services | 2020-06-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32291 | 32291 | 2020-06-30 11:41 | Section 3 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 3.09 | 173.04 | Builders Merchants (General) | 2020-07-03 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32296 | 32296 | 2020-06-30 13:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 383.54 | 383.54 | Miscellaneous | 2020-06-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 164.96 | 164.96 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 187.5 | 187.5 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 390.96 | 390.96 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 112.5 | 112.5 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 21.56 | 21.56 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32309 | 32309 | 2020-07-01 08:19 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 195.62 | 195.62 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32311 | 32311 | 2020-07-01 11:38 | Section 2 | Material Requisition | Not on List | Not on List | 1 | £ | 1344 | 1344 | Professional Services | 2020-07-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 3010 - Ground Preparation, Cultivation and Mulching | IMO - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32312 | 32312 | 2020-07-01 12:13 | Section 5 | Material Requisition | Not on List | Not on List | 16 | No | 56.7 | 907.2 | Miscellaneous | 2020-07-01 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32314 | 32314 | 2020-07-01 13:54 | Section 2 | Material Requisition | Aggregate | A20 Pipe Bed | 60 | Tonnes | 21.75 | 1305 | Aggregate | 2020-07-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 501 - Drains | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32323 | 32323 | 2020-07-02 07:54 | Section 4 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 400 | Each | 2.48 | 992 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32336 | 32336 | 2020-07-02 13:57 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 342 | 342 | Miscellaneous | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32337 | 32337 | 2020-07-03 13:26 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 342 | 342 | Miscellaneous | 2020-07-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32339 | 32339 | 2020-07-03 13:53 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 1825 | 1825 | Miscellaneous | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32340 | 32340 | 2020-07-03 14:12 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 1825 | 1825 | Miscellaneous | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32341 | 32341 | 2020-07-03 14:23 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2020-07-03 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32347 | 32347 | 2020-07-03 15:19 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 89.5 | 89.5 | Small Tools (Consumables) | 2020-07-06 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32348 | 32348 | 2020-07-03 15:26 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-07-03 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32371 | 32371 | 2020-07-06 11:05 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 18270 | 18270 | Office Supplies | 2020-07-10 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-32373 | 32373 | 2020-07-06 11:37 | Section 6 | Material Requisition | Not on List | Not on List | 1 | ea | 25832.98 | 25832.98 | Office Supplies | 2020-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32374 | 32374 | 2020-07-06 12:00 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Professional Services | 2020-07-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-32375 | 32375 | 2020-07-06 12:02 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 480 | 480 | Miscellaneous | 2020-07-06 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Commercial Approval | Yes - Approve | NULL | REQ - Buyers
MREQ-32390 | 32390 | 2020-07-07 10:12 | Section 4 | Material Requisition | Not on List | Not on List | 30 | No. | 2.85 | 85.5 | Miscellaneous | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32391 | 32391 | 2020-07-07 11:05 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2020-07-09 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32392 | 32392 | 2020-07-07 11:43 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 478.2 | 478.2 | Miscellaneous | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32393 | 32393 | 2020-07-07 13:56 | Test Section | Material Requisition | Ducting | Polypipe 110mm x 50m Ridgiduct Coil Blue (877802) | 33 | Each | 105.04 | 3466.32 | Blocks and Bricks | 2020-07-29 | Test Location | Test Section | Test Section | Operational Approval | NULL | NULL | Chris Henry
MREQ-32394 | 32394 | 2020-07-07 14:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | 1 | 365 | 365 | Ductile Drainage | 2020-07-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 504 - Drainage and Service Ducts in Structures | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32395 | 32395 | 2020-07-07 15:45 | Section 6 | Material Requisition | Iron Wear | Not on List | 48 | each | NULL | 0 | Ductile Drainage | 2020-07-17 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32395 | 32395 | 2020-07-07 15:45 | Section 6 | Material Requisition | Iron Wear | Not on List | 17 | each | NULL | 0 | Ductile Drainage | 2020-07-17 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32398 | 32398 | 2020-07-07 16:41 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | £ | 349 | 349 | Small Tools (Consumables) | 2020-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32398 | 32398 | 2020-07-07 16:41 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 153b - Temporary Works Viaduct- Miscelaneous | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32405 | 32405 | 2020-07-08 12:02 | Section 4 | Material Requisition | Not on List | Not on List | 3 | 12 kg tubs | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-07-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32405 | 32405 | 2020-07-08 12:02 | Section 4 | Material Requisition | Concrete Drainage | CPM Seating Ring 600x600 Opening (528483) | 30 | Each | 16.49 | 494.7 | Concrete Drainage | 2020-07-10 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 502 - Chambers & Gullies | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32409 | 32409 | 2020-07-08 12:43 | Section 4 | Material Requisition | Not on List | Not on List | 1 | number | NULL | 0 | Ductile Drainage | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 503 - Headwalls and Outfall Works | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
2 | Pounds | 61.57 | 123.14 | Small Tools (Consumables) | 2020-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32411 | REQ - Finance Team | NULL | NULL
2 | Pounds | 29.9 | 59.8 | Small Tools (Consumables) | 2020-07-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32411 | REQ - Finance Team | NULL | NULL
1 | 908.6 | 908.6 | 908.6 | Office Supplies | 2020-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32412 | REQ - Finance Team | NULL | NULL
12 | 360 | 4320 | 51840 | Office Supplies | 2020-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32412 | REQ - Finance Team | NULL | NULL
1 | 1440 | 1440 | 1440 | Office Supplies | 2020-07-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32412 | REQ - Finance Team | NULL | NULL
MREQ-32413 | 32413 | 2020-07-08 15:23 | Section 2 | Material Requisition | Misc | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2020-07-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-32413 | 32413 | 2020-07-08 15:23 | Section 2 | Material Requisition | Misc | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2020-07-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S2 Buyers
2 | NULL | NULL | 0 | Miscellaneous | 2020-07-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32415 | REQ - Finance Team | NULL | NULL
MREQ-32421 | 32421 | 2020-07-09 09:33 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No, | 4024.75 | 4024.75 | Laboratory Equipment / Certification | 2020-07-09 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32423 | 32423 | 2020-07-09 12:11 | Section 6 | Material Requisition | Not on List | Not on List | 1 | 1 | 150 | 150 | PPE | 2020-07-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 104 - Site Transport | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32424 | 32424 | 2020-07-09 12:27 | Section 2 | Material Requisition | Not on List | Not on List | 5 | ea | 66 | 330 | Ductile Drainage | 2020-07-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2A - Roadworks - A1 | 504 - Drainage and Service Ducts in Structures | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-32429 | 32429 | 2020-07-09 15:57 | Section 6 | Material Requisition | PPE, Small Tools and Consumables | Boot Composite Toe/Mid Magnum Roadmaster Black S3 Hro Src (100054) | 1 | Each | 55.3 | 55.3 | PPE | 2020-07-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 151 - Prelims attendant Labour and Equipment | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32433 | 32433 | 2020-07-10 07:29 | Section 4 | Material Requisition | Not on List | Not on List | 65 | Cubic meter | NULL | 0 | Concrete Accessories | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32433 | 32433 | 2020-07-10 07:29 | Section 4 | Material Requisition | Not on List | Not on List | 160 | Cubic meter | NULL | 0 | Concrete Accessories | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32433 | 32433 | 2020-07-10 07:29 | Section 4 | Material Requisition | Not on List | Not on List | 300 | Cubic meter | NULL | 0 | Concrete Accessories | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32433 | 32433 | 2020-07-10 07:29 | Section 4 | Material Requisition | Not on List | Not on List | 60 | Cubic meter | NULL | 0 | Concrete Accessories | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1104 - Footways and Paved Areas | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
5000 | Tonnes | 23.5 | 117500 | Aggregate | 2020-07-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32433 | REQ - Finance Team | NULL | NULL
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 180.83 | 180.83 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 90 | 90 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 325 | 325 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | N0 | 59.8 | 59.8 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 375 | Ltrs | 0.8 | 300 | Gas Oil | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32443 | 32443 | 2020-07-10 08:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 85 | 85 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32454 | 32454 | 2020-07-10 14:44 | Section 6 | Material Requisition | Not on List | Not on List | 1 | 1 | 216.38 | 216.38 | Small Tools (Consumables) | 2020-07-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32454 | 32454 | 2020-07-10 14:44 | Section 6 | Material Requisition | Not on List | Not on List | 1 | 1 | 392.86 | 392.86 | Small Tools (Consumables) | 2020-07-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32465 | 32465 | 2020-07-13 12:04 | Section 6 | Material Requisition | Aggregate | Bedding Sand | 6 | Tonnes | 11.5 | 69 | Aggregate | 2020-07-14 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32480 | 32480 | 2020-07-14 10:33 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-07-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32480 | 32480 | 2020-07-14 10:33 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-07-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
1 | No | 1718.08 | 1718.08 | Miscellaneous | 2020-07-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32482 | REQ - Finance Team | NULL | NULL
1 | No | 228.64 | 228.64 | Miscellaneous | 2020-07-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32482/Request/20200713100503935.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32482 | REQ - Finance Team | NULL | NULL
1 | No | 331.03 | 331.03 | Miscellaneous | 2020-07-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32482/Request/20200713094531833.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32482 | REQ - Finance Team | NULL | NULL
1 | No | 245.34 | 245.34 | Miscellaneous | 2020-07-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32482 | REQ - Finance Team | NULL | NULL
1 | No | 556.36 | 556.36 | Miscellaneous | 2020-07-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32482 | REQ - Finance Team | NULL | NULL
MREQ-32484 | 32484 | 2020-07-14 15:57 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Small Tools (Consumables) | 2020-07-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32486 | 32486 | 2020-07-15 08:02 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 60 | 60 | Small Tools (Consumables) | 2020-07-15 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-32487 | 32487 | 2020-07-15 08:36 | Section 4 | Material Requisition | Not on List | Not on List | 1 | £ | 621 | 621 | Professional Services | 2020-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 106 - Testing equipment and materials testing | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
153f - Tempoary Works - Miscellaneous temporary works | A14 IDT | OP 11456 | Anglian Water Services Ltd (1106439) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32491 | 32491 | 2020-07-06 15:34 | Core | Material Requisition | Not on List | Not on List | 1 | Each | 478.2 | 478.2 | Miscellaneous | 2020-07-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32492 | 32492 | 2020-07-15 15:48 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 897.53 | 897.53 | Miscellaneous | 2020-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Operational Approval | NULL | NULL | REQ - Buyers
150 | Number | NULL | 0 | Fixings and Fasteners | 2020-07-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32493 | REQ - Finance Team | NULL | NULL
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 27 | each | NULL | 0 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Plastic Drainage | Not on List | 31 | each | NULL | 0 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 1 | Pallet | 3.56 | 3.56 | Miscellaneous | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Twinwall | Not on List | 80 | meters | NULL | 0 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Twinwall | Not on List | 30 | meters | NULL | 0 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Twinwall | Not on List | 1 | bag | NULL | 0 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
6 | Each | 81.96 | 491.76 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | Skyland Contractors Ltd | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32494 | REQ - Finance Team | NULL | NULL
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 250 D/S (913115) | 1 | Each | 36.62 | 36.62 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 500 D/S (913180) | 2 | Each | 53.01 | 106.02 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 750 D/S (913226) | 1 | Each | 61.48 | 61.48 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 2 | each | NULL | 0 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 16 | each | NULL | 0 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 6 | each | NULL | 0 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | Not on List | 1 | each | NULL | 0 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Not on List | Not on List | 1 | pallet | NULL | 0 | Miscellaneous | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Concrete Drainage | CPM Chamber Ring 1200 x 1000 D/S (991913) | 1 | Each | 81.96 | 81.96 | Concrete Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32494 | 32494 | 2020-07-15 16:44 | Section 6 | Material Requisition | Twinwall | Polypipe 150mm Ridgidrain Coupler (878019) | 100 | Each | 1.98 | 198 | Plastic Drainage | 2020-07-15 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32496 | 32496 | 2020-07-16 06:23 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 1367.93 | 1367.93 | Office Supplies | 2020-07-20 | Main Compound Gate D - 1339642 - Main Compound Entrance A1198 (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Operational Approval | NULL | NULL | REQ - Buyers
130 | number | NULL | 0 | Fixings and Fasteners | 2020-06-12 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=31959 | REQ - Finance Team | NULL | NULL
MREQ-32498 | 32498 | 2020-07-16 10:13 | Core | Material Requisition | Not on List | Not on List | 1 | Each | 90 | 90 | Professional Services | 2020-07-16 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32498 | 32498 | 2020-07-16 10:13 | Core | Material Requisition | Misc | Not on List | 1 | Each | 1825 | 1825 | Miscellaneous | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32498 | 32498 | 2020-07-16 10:13 | Core | Material Requisition | Misc | Not on List | 1 | Each | 1825 | 1825 | Miscellaneous | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32498 | 32498 | 2020-07-16 10:13 | Core | Material Requisition | Misc | Not on List | 1 | Each | 342 | 342 | Miscellaneous | 2020-07-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32498 | 32498 | 2020-07-16 10:13 | Core | Material Requisition | Misc | Not on List | 1 | Each | 342 | 342 | Miscellaneous | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 103 - Staff | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32500 | 32500 | 2020-07-16 12:10 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | Each | 0 | 0 | Laboratory Equipment / Certification | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32500 | 32500 | 2020-07-16 12:10 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | Each | 0 | 0 | Laboratory Equipment / Certification | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32500 | 32500 | 2020-07-16 12:10 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | Each | 0 | 0 | Laboratory Equipment / Certification | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32501 | 32501 | 2020-07-16 12:17 | Core | Material Requisition | Not on List | Not on List | 1 | Each | 10648.5 | 10648.5 | Miscellaneous | 2020-07-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32502 | 32502 | 2020-07-16 12:21 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | Each | NULL | 0 | PPE | 2020-07-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
1 | Number | NULL | 0 | PPE | 2020-07-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32503 | REQ - Finance Team | NULL | NULL
1 | Number | NULL | 0 | PPE | 2020-07-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32503 | REQ - Finance Team | NULL | NULL
1 | Number | NULL | 0 | PPE | 2020-07-16 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32503 | REQ - Finance Team | NULL | NULL
MREQ-32506 | 32506 | 2020-07-16 14:53 | Section 2 | Material Requisition | Not on List | Not on List | 1 | £ | 4778.1 | 4778.1 | Professional Services | 2020-07-16 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-32507 | 32507 | 2020-07-16 15:20 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 2596.52 | 2596.52 | Miscellaneous | 2020-07-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Operational Approval | NULL | NULL | REQ - Buyers
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | Yes | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 267 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
Yes - Approve | Yes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
2 | NULL | NULL | 0 | Miscellaneous | 2020-07-24 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32526 | REQ - Finance Team | NULL | NULL
NULL | NULL | NULL | Buyer - Closed | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 110 | 110 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 165 | 165 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 190 | 190 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32533 | 32533 | 2020-07-20 10:16 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 585 | 585 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32535 | 32535 | 2020-07-20 14:19 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32535 | 32535 | 2020-07-20 14:19 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32535 | 32535 | 2020-07-20 14:19 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 12 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-32536 | 32536 | 2020-07-20 13:58 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 185 | 185 | Professional Services | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-32536 | 32536 | 2020-07-20 13:58 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 117.5 | 117.5 | Professional Services | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-32536 | 32536 | 2020-07-20 13:58 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 227.5 | 227.5 | Professional Services | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
MREQ-32536 | 32536 | 2020-07-20 13:58 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 153.35 | 153.35 | Professional Services | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | NULL | Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | NULL | Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | NULL | Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | NULL | Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | NULL | Buyer - Closed | Yes - ApproveYes - Approve | Yes - ApproveYes - Approve | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32540 | 32540 | 2020-07-20 17:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 102 | 102 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32540 | 32540 | 2020-07-20 17:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32540 | 32540 | 2020-07-20 17:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 95 | 95 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S6 Buyers
MREQ-32540 | 32540 | 2020-07-20 17:02 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 95 | 95 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S6 Buyers
2000 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | OP 14154 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32546 | REQ - Finance Team | NULL | NULL
1 | No. | 573.54 | 573.54 | Surveying Consumables | 2020-07-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | A14 IDT | 14161 | Korec (1114049) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32547/Request/est52231.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32547 | REQ - Finance Team | NULL | NULL
MREQ-32553 | 32553 | 2020-07-21 16:28 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 40 | NULL | NULL | 0 | Fixings and Fasteners | 2020-07-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 106 - Testing equipment and materials testing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32556 | 32556 | 2020-07-22 07:49 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32556 | 32556 | 2020-07-22 07:49 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 3 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32556 | 32556 | 2020-07-22 07:49 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 3 | NULL | NULL | 0 | PPE | 2020-07-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
NULL | 32558 | 2020-07-22 10:39 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 643.68 | 643.68 | Miscellaneous | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32558 | 2020-07-22 10:39 | Section 5 | Material Requisition | Misc | Not on List | 1 | No | 9975 | 9975 | Miscellaneous | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32558 | 2020-07-22 10:39 | Section 5 | Material Requisition | Misc | Not on List | 1 | No | 85 | 85 | Miscellaneous | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32558 | 2020-07-22 10:39 | Section 5 | Material Requisition | Misc | Not on List | 1 | No | 212.45 | 212.45 | Miscellaneous | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32559 | 2020-07-22 12:12 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 165 | 165 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32559 | 2020-07-22 12:12 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 290 | 290 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32559 | 2020-07-22 12:12 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 1182.22 | 1182.22 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32559 | 2020-07-22 12:12 | Section 4 | Material Requisition | Not on List | Not on List | 1 | N0 | 85 | 85 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32570 | 2020-07-23 10:56 | Section 4 | Material Requisition | Not on List | Not on List | 30 | NULL | NULL | 0 | Miscellaneous | 2020-07-27 | RVP 404 - 1339622 - A14 Jnc 28, Swavesey North Roundabout | PLM4 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32575 | 2020-07-23 14:11 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Laboratory Equipment / Certification | 2020-07-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 120 - Small Tools (hand) | Operational Approval | NULL | NULL | REQ - Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 7 | No | 45 | 315 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 45 | 45 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 5 | No | 45 | 225 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 39 | 39 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 9 | No | 39 | 351 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 7 | No | 51.5 | 360.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 10 | No | 39 | 390 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 4 | No | 45 | 180 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 4 | No | 45 | 180 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 21 | 63 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 21 | 63 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 2 | No | 35.5 | 71 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 11.5 | 11.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 2 | No | 45 | 90 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 21 | 63 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 3 | No | 45 | 135 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32576 | 2020-07-23 14:10 | Section 4 | Material Requisition | Not on List | Not on List | 5 | No | 45 | 225 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32577 | 32577 | 2020-07-23 17:40 | Section 4 | Material Requisition | Plastic Drainage | Not on List | 66 | NULL | NULL | 0 | Plastic Drainage | 2020-07-27 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 2401 - Brickwork, Blockwork and Stonework | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32578 | 32578 | 2020-07-23 18:03 | Section 5 | Material Requisition | Not on List | Not on List | 40 | each | NULL | 0 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-07-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SEC5 - Roadworks | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32581 | 32581 | 2020-07-24 07:52 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.75 | 97.75 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32581 | 32581 | 2020-07-24 07:52 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 102 | 102 | Professional Services | 2020-07-31 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
NULL | 32582 | 2020-07-24 08:28 | Section 5 | Material Requisition | Not on List | Not on List | 4 | No | 47.37 | 189.48 | Professional Services | 2020-07-31 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
NULL | 32582 | 2020-07-24 08:28 | Section 5 | Material Requisition | Not on List | Not on List | 0 | NULL | NULL | 0 | Professional Services | NaN-NaN-NaN NaN:NaN:NaN | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S5 Buyers
1 | No | 95 | 95 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32583/Request/DOC220620-22062020122019.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32583 | REQ - Finance Team | NULL | NULL
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 43 | 43 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 220 | 220 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 126.5 | 126.5 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 92 | ltrs | 0.8 | 73.6 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 74.22 | 74.22 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 32583 | 2020-07-24 08:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 95 | 95 | Professional Services | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-32584 | 32584 | 2020-07-24 10:16 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 86.25 | 86.25 | Professional Services | 2020-07-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32584 | 32584 | 2020-07-24 10:16 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 95 | 95 | Professional Services | 2020-07-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32584 | 32584 | 2020-07-24 10:16 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 106.88 | 106.88 | Professional Services | 2020-07-31 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyer - Closed | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32593 | 32593 | 2020-07-26 08:41 | Section 4 | Material Requisition | Concrete Drainage | Not on List | 1 | NULL | NULL | 0 | Concrete Drainage | 2020-07-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN17 - Swavesey Junction | 1702 - Precast Concrete | Buyer - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
50 | Tonnes | 16.5 | 825 | Miscellaneous | 2020-07-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | Skyland Contractors Ltd | 14167 | G Webb Haulage Ltd (1300938) | Buyer - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32594 | REQ - Finance Team | NULL | NULL
7 | No | 45 | 315 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32571/Request/3876 Damage letter.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
1 | No | 45 | 45 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
1 | No | 45 | 45 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32571/Request/3619 damage letter.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
1 | No | 39 | 39 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32571/Request/3619 damage letter 2.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
1 | No | 19.5 | 19.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
9 | No | 39 | 351 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
7 | No | 51.5 | 360.5 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | NULL | NULL | Operational Approval | NULL | NULL | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32571 | REQ - Finance Team | NULL | NULL
NULL | 32571 | 2020-07-23 10:25 | Section 4 | Material Requisition | Not on List | Not on List | 0 | NULL | NULL | 0 | Miscellaneous | 2020-07-31 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
NULL | 17590 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 19694 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17467 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17547 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 26341 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 19697 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17576 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 18890 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 23507 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 27062 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 29524 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 24592 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 22457 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17439 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17539 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17559 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 27060 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 29768 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 18891 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 26571 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17597 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17580 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 31775 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 10753 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17506 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 30258 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 20552 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 19945 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17197 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17592 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17366 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 29523 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17329 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 18082 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17435 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 26987 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 17438 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
NULL | 27571 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL
MREQ-32610 | 32610 | 2020-07-28 08:36 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 2550.9 | 2550.9 | Miscellaneous | 2020-07-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32615 | 32615 | 2020-07-29 10:55 | Core | Material Requisition | Signage | Not on List | 2 | NULL | 69 | 138 | Miscellaneous | 2020-08-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32617 | 32617 | 2020-07-29 13:50 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 1500 | 1500 | Professional Services | 2020-07-30 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32622 | 32622 | 2020-07-30 07:56 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | £ | 92423.92 | 92423.92 | Professional Services | 2020-07-31 | RVP 402 - 1339620 - Swavesey Junction North A14 J28 Eastbound (Trinity Pub) | SC4A - Roadworks - Swavesey to Robins Lane | 605 - Disposal | Commercial Rejected | Yes - Approve | No - Reject | REQ - Section 4 Buyers
MREQ-32623 | 32623 | 2020-07-30 09:38 | Section 6 | Material Requisition | Bagged | Building Sand Bulk Bag (938155) | 5 | Each | 34.94 | 174.7 | Aggregate | 2020-08-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32623 | 32623 | 2020-07-30 09:38 | Section 6 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 40 | Each | 3.79 | 151.6 | Aggregate | 2020-08-03 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
20 | m3 | 107.76 | 2155.2 | Ready Mixed Concrete | 2020-08-03 | Gate 1 - 1339601 - Main Compound Alconbury | Sian Formwork Ltd | 13593 | Mick George Ltd (1220483) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32624 | REQ - Finance Team | NULL | NULL
MREQ-32626 | 32626 | 2020-07-30 10:13 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Wrap Pallet C/W Extended Core 400mm X 300m X 17mu (766058) | 12 | Each | 11.97 | 143.64 | Miscellaneous | 2020-07-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32626 | 32626 | 2020-07-30 10:13 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Bucket Industrial Black Plastic 3 Gallon (506200) | 6 | Each | 1.43 | 8.58 | Miscellaneous | 2020-07-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32626 | 32626 | 2020-07-30 10:13 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Padlock Cast Iron Spartan 48mm Open Shackle (744411) | 10 | Each | 5.75 | 57.5 | Miscellaneous | 2020-07-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32626 | 32626 | 2020-07-30 10:13 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Bucket Flexi Tub 40 Litre Black (506338) | 3 | Each | 4.95 | 14.85 | Miscellaneous | 2020-07-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32626 | 32626 | 2020-07-30 10:13 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Sack Cleanworks Black Regran 20kg 18x29x38 Cs/200 Gro009 (746625) | 6 | Each | 26.55 | 159.3 | Miscellaneous | 2020-07-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32629 | 32629 | 2020-07-30 12:34 | Section 4 | Material Requisition | Timber | Not on List | 50 | each | 26.97 | 1348.5 | Timber Products | 2020-08-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32629 | 32629 | 2020-07-30 12:34 | Section 4 | Material Requisition | Timber | Not on List | 4 | each | 24 | 96 | Timber Products | 2020-08-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32629 | 32629 | 2020-07-30 12:34 | Section 4 | Material Requisition | Not on List | Not on List | 28 | each | 14.3 | 400.4 | Miscellaneous | 2020-08-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32629 | 32629 | 2020-07-30 12:34 | Section 4 | Material Requisition | Not on List | Not on List | 28 | each | 10 | 280 | Miscellaneous | 2020-08-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32629 | 32629 | 2020-07-30 12:34 | Section 4 | Material Requisition | Bagged | Post Mix 25kg (348099) | 2 | pallets | 5.25 | 10.5 | Builders Merchants (General) | 2020-08-03 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
8 | No. | 74.22 | 593.76 | Electrical | 2020-08-03 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | Telent Technology Services Ltd | Euros Charge | NULL | IMO - Closed | Yes - Approve | Yes - Approve | Yes | Reichelt Elektronik | /sites/BPM/FlowForma/FormDocuments/MREQ32645/IMO-P-Card-Purchase/MREQ 32645 Receipt_Invoice.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32645 | REQ - Finance Team | NULL | NULL
MREQ-32647 | 32647 | 2020-07-31 14:35 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 205 | 205 | Miscellaneous | 2020-07-31 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32654 | 32654 | 2020-08-03 07:55 | Section 6 | Material Requisition | Not on List | Not on List | 2 | ea | 264.79 | 529.58 | Office Supplies | 2020-08-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Commercial Rejected | Yes - Approve | No - Reject | Req - S6 Buyers
MREQ-32654 | 32654 | 2020-08-03 07:55 | Section 6 | Material Requisition | Not on List | Not on List | 2 | ea | 14.81 | 29.62 | Office Supplies | 2020-08-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Commercial Rejected | Yes - Approve | No - Reject | Req - S6 Buyers
MREQ-32654 | 32654 | 2020-08-03 07:55 | Section 6 | Material Requisition | Not on List | Not on List | 1 | ea | 0 | 0 | Office Supplies | 2020-08-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Commercial Rejected | Yes - Approve | No - Reject | Req - S6 Buyers
MREQ-32658 | 32658 | 2020-08-03 14:39 | Section 6 | Material Requisition | Bagged | Not on List | 6 | Tubs | 10.4 | 62.4 | Builders Merchants (General) | 2020-08-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
2 | ea | 264.29 | 528.58 | Office Supplies | 2020-08-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14199 | Comperte Ltd (1323061) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32668 | REQ - Finance Team | NULL | NULL
2 | ea | 17.77 | 35.54 | Office Supplies | 2020-08-07 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14199 | Comperte Ltd (1323061) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32668 | REQ - Finance Team | NULL | NULL
2 | ea | 48.96 | 87.98 | Office Supplies | 2020-08-16 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | Amazon | IMO - Closed | Yes - Approve | Yes - Approve | Yes | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32673/Request/Amazon Cat 5 Cable.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32673 | REQ - Finance Team | NULL | NULL
MREQ-32678 | 32678 | 2020-08-05 08:43 | Core | Material Requisition | Not on List | Not on List | 1 | No. | 65 | 65 | Surveying Consumables | 2020-08-05 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
20 | ton | 0 | 0 | Aggregate | 2020-08-07 | Gate 4 - 1340888 - Access to AI batching Plant & Drainage Yard, A14 Westbound Brampton | A14 IDT | 14198 | G Webb Haulage Ltd (1300938) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32679 | REQ - Finance Team | NULL | NULL
MREQ-32682 | 32682 | 2020-08-05 10:25 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 11097.96 | 11097.96 | Office Supplies | 2020-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32682 | 32682 | 2020-08-05 10:25 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 13338.08 | 13338.08 | Office Supplies | 2020-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32683 | 32683 | 2020-08-05 10:35 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 968.06 | 968.06 | Office Supplies | 2020-08-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 748.11 | 748.11 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 972.97 | 972.97 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 563.98 | 563.98 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 635.57 | 635.57 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 1331.14 | 1331.14 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32685 | 32685 | 2020-08-05 09:37 | Section 4 | Material Requisition | Hazardous Waste | Not on List | 1 | No | 444.93 | 444.93 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32686 | 32686 | 2020-08-05 13:12 | Core | Material Requisition | Not on List | Not on List | 1 | no. | 27000 | 27000 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 30 | Number | 8.54 | 256.2 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 8 | Number | 5.76 | 46.08 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 100 | Number | 0.04 | 4 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 30 | Number | 0.11 | 3.3 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 100 | Number | 0.14 | 14 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 11.83 | 11.83 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 45.46 | 45.46 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 6 | NULL | 6.58 | 39.48 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32690 | 32690 | 2020-08-05 14:14 | Section 1 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 8.19 | 8.19 | Small Tools (Consumables) | 2020-08-06 | Gate 1 - 1339601 - Main Compound Alconbury | GN01 - Gantry structures | 1804 - Portal Gantries | Stores - Closed | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32691 | 32691 | 2020-08-05 16:30 | Core | Material Requisition | Not on List | Not on List | 1 | No | 16214.4 | 16214.4 | Professional Services | 2020-08-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
1 | No | 160316.47 | 160316.47 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | 14206 | JLT Speciality Ltd (1135940) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32693/Request/Additional Premuim for Sections 1,2,3,4 &5.pdf_V1.0.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32693 | REQ - Finance Team | NULL | NULL
MREQ-32694 | 32694 | 2020-08-05 17:23 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 27962.32 | 27962.32 | Professional Services | 2020-08-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEE6 - Fee Based Costs inc. insurance | 107 - Insurance | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32709 | 32709 | 2020-08-06 07:30 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 270 | Tonnes | 24.5 | 6615 | Aggregate | 2020-08-10 | RVP 428 - 1352015&nbsp; On Slip, A14 Eastbound between Jcn 30 – 31 | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32710 | 32710 | 2020-08-06 13:01 | Section 6 | Material Requisition | Not on List | Not on List | 2 | NULL | NULL | 0 | Office Supplies | 2020-08-06 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 117 - Computer & Acc Charges | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 641.46 | 641.46 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 631.13 | 631.13 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 435.33 | 435.33 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 313.65 | 313.65 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 1594.98 | 1594.98 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32729 | 32729 | 2020-08-10 14:33 | Section 5 | Material Requisition | Waste Management | Not on List | 1 | No | 306 | 306 | Professional Services | 2020-08-14 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32744 | 32744 | 2020-08-11 14:09 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 3137.73 | 3137.73 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 121 - Phones / Radios / Comms | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32745 | 32745 | 2020-08-11 14:16 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 720 | 720 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Operations Rejected | No - Reject | NULL | REQ - Buyers
1 | NULL | 27.14 | 27.14 | PPE | 2020-08-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | OP 14214 | Greenham Trading Ltd (1100463) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32748 | REQ - Finance Team | NULL | NULL
MREQ-32750 | 32750 | 2020-08-12 01:24 | Section 6 | Material Requisition | Bagged | Building Sand Bulk Bag (938155) | 3 | Each | 34.93 | 104.79 | Aggregate | 2020-08-12 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32757 | 32757 | 2020-08-13 10:08 | Section 2 | Material Requisition | Not on List | Not on List | 1 | £ | 1861 | 1861 | Professional Services | 2020-08-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32758 | 32758 | 2020-08-13 12:43 | Section 6 | Material Requisition | Not on List | Not on List | 1 | ea | 69.44 | 69.44 | PPE | 2020-08-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32758 | 32758 | 2020-08-13 12:43 | Section 6 | Material Requisition | Not on List | Not on List | 3 | ea | 69.44 | 208.32 | PPE | 2020-08-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32758 | 32758 | 2020-08-13 12:43 | Section 6 | Material Requisition | Not on List | Not on List | 4 | ea | 35.64 | 142.56 | PPE | 2020-08-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 109 - PPE Costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
10 | M3 | 88 | 880 | Ready Mixed Concrete | 2020-08-15 | Gate 1 - 1339601 - Main Compound Alconbury | A14 IDT | 13598 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | Cardinalis Dev ltd 1366537 | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32763 | REQ - Finance Team | NULL | NULL
1 | NULL | 621.5 | 621.5 | Small Tools (Consumables) | 2020-08-17 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | Telent Technology Services Ltd | op 14225 | Orbital Fasteners Ltd (1118568) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32764 | REQ - Finance Team | NULL | NULL
1 | NULL | 146 | 146 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32765/Request/Imperial Hotel Invoice for Andrew Hobson.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32765 | REQ - Finance Team | NULL | NULL
1 | NULL | 146 | 146 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32765/Request/Imperial Hotel Invoice for Nicole Preston.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32765 | REQ - Finance Team | NULL | NULL
1 | NULL | 146 | 146 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32765/Request/Imperial Hotel Invoice for Graham Cole.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32765 | REQ - Finance Team | NULL | NULL
1 | NULL | 146 | 146 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32765/Request/Imperial Hotel Invoice for Tom Reynolds.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32765 | REQ - Finance Team | NULL | NULL
1 | NULL | 15.6 | 15.6 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32766/Request/London Taxi Receipt 15.60.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32766 | REQ - Finance Team | NULL | NULL
1 | NULL | 18 | 18 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Grosvenver Receipt 3.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
1 | NULL | 20.45 | 20.45 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/London Taxi Receipt 7.11.19. 20.46.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
1 | NULL | 5 | 5 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Atrium Bar London Receipt 2.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
1 | NULL | 6.2 | 6.2 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Atrium Bar London Receipt 3.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
1 | NULL | 5.7 | 5.7 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Atrium Bar London Receipt 4.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
1 | NULL | 7.5 | 7.5 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Atrium Bar London Receipt.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
1 | NULL | 13.25 | 13.25 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32767/Request/Imperial Receipt 2.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32767 | REQ - Finance Team | NULL | NULL
MREQ-32769 | 32769 | 2020-08-14 14:13 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 319 | 319 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32770 | 32770 | 2020-08-14 15:09 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 29.5 | 29.5 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
2 | NULL | 97.5 | 195 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | A14 IDT | NULL | NULL | IMO Queue | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32775 | REQ - Finance Team | NULL | NULL
MREQ-32776 | 32776 | 2020-08-14 15:49 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 10.95 | 10.95 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32777 | 32777 | 2020-08-14 15:53 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 2.85 | 2.85 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32777 | 32777 | 2020-08-14 15:53 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 25.45 | 25.45 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32778 | 32778 | 2020-08-14 15:56 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1020 | 1020 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32778 | 32778 | 2020-08-14 15:56 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 510 | 510 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32779 | 32779 | 2020-08-14 16:02 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 861.86 | 861.86 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32780 | 32780 | 2020-08-14 16:21 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 2874 | 2874 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32781 | 32781 | 2020-08-14 16:24 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 3750 | 3750 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32782 | 32782 | 2020-08-14 16:28 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 720 | 720 | Miscellaneous | 2020-08-17 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 121 - Phones / Radios / Comms | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32784 | 32784 | 2020-08-14 16:29 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 35.22 | 35.22 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32794 | 32794 | 2020-08-14 23:17 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 39.99 | 39.99 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32795 | 32795 | 2020-08-14 23:35 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 2102.64 | 2102.64 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 114 - Office Furniture | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32796 | 32796 | 2020-08-14 23:49 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 28.99 | 28.99 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32797 | 32797 | 2020-08-14 23:52 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 208.99 | 208.99 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32798 | 32798 | 2020-08-14 23:57 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1248 | 1248 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32798 | 32798 | 2020-08-14 23:57 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1000 | 1000 | Miscellaneous | 2020-08-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 122 - Entertainment | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32799 | 32799 | 2020-08-15 00:14 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 765.49 | 765.49 | Miscellaneous | 2020-08-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 101 - Mob/Demob of Compounds | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32803 | 32803 | 2020-08-17 08:33 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 345 | 345 | Miscellaneous | 2020-08-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32804 | 32804 | 2020-08-17 09:10 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 430 | 430 | Office Supplies | 2020-08-17 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 110 - Welfare Costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32823 | 32823 | 2020-08-18 11:08 | Section 6 | Material Requisition | Not on List | Not on List | 5 | Box's | 132.96 | 664.8 | Builders Merchants (General) | 2020-08-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32829 | 32829 | 2020-08-18 16:46 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | 51.84 | 51.84 | Small Tools (Consumables) | 2020-08-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32829 | 32829 | 2020-08-18 16:46 | Core | Material Requisition | PPE, Small Tools and Consumables | Not on List | 5 | Boxes | 71.11 | 355.55 | Small Tools (Consumables) | 2020-08-20 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 110 - Welfare Costs | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32830 | 32830 | 2020-08-18 17:09 | Section 6 | Material Requisition | Aggregate | Type 1 | 60 | Tonnes | 23.5 | 1410 | Aggregate | 2020-08-20 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | S6SF - Station Forecourt | 2703 - Works on behalf of Statutory Undertakers | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No | 95 | 95 | Professional Services | 2020-08-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | 14232 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32839/Request/DOC140820-14082020094958.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32839 | REQ - Finance Team | NULL | NULL
1 | No | 85 | 85 | Professional Services | 2020-08-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | 14232 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32839 | REQ - Finance Team | NULL | NULL
1 | No | 95 | 95 | Professional Services | 2020-08-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | A14 IDT | 14232 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32839 | REQ - Finance Team | NULL | NULL
MREQ-32839 | 32839 | 2020-08-19 12:24 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.95 | 97.95 | Professional Services | 2020-08-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32839 | 32839 | 2020-08-19 12:24 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 97.95 | 97.95 | Professional Services | 2020-08-28 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No | 86.25 | 86.25 | Professional Services | 2020-08-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | A14 IDT | 14233 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32840/Request/DOC140820-14082020094958.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32840 | REQ - Finance Team | NULL | NULL
1 | No | 258.75 | 258.75 | Professional Services | 2020-08-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | A14 IDT | 14233 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32840 | REQ - Finance Team | NULL | NULL
1 | No | 95 | 95 | Professional Services | 2020-08-28 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | A14 IDT | 14233 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32840 | REQ - Finance Team | NULL | NULL
MREQ-32846 | 32846 | 2020-08-20 12:42 | Section 5 | Material Requisition | Not on List | Not on List | 34 | each | 0.63 | 21.42 | Miscellaneous | 2020-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SEC5 - Roadworks | 1504 - Technology Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32846 | 32846 | 2020-08-20 12:42 | Section 5 | Material Requisition | Not on List | Not on List | 34 | each | 0.63 | 21.42 | Miscellaneous | 2020-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SEC5 - Roadworks | 1504 - Technology Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32846 | 32846 | 2020-08-20 12:42 | Section 5 | Material Requisition | Not on List | Not on List | 34 | each | 0.25 | 8.5 | Miscellaneous | 2020-08-23 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SEC5 - Roadworks | 1504 - Technology Equipment | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32850 | 32850 | 2020-08-20 14:46 | Section 4 | Material Requisition | Not on List | Not on List | 40 | Bags | NULL | 0 | Builders Merchants (General) | 2020-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 2701 - Accommodation works | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-32851 | 32851 | 2020-08-20 15:08 | Section 4 | Material Requisition | Not on List | Not on List | 46 | NULL | NULL | 0 | Builders Merchants (General) | 2020-08-20 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32855 | 32855 | 2020-08-21 07:50 | Section 5 | Material Requisition | Not on List | Not on List | 1 | Lot | 70000 | 70000 | Miscellaneous | 2020-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153a - Temporary Works - Site Infrastructure | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
1 | No | 1606 | 1606 | Miscellaneous | 2020-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 14246 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32857/Request/RE Advice Note - N06-668733.msg | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32857 | REQ - Finance Team | NULL | NULL
1 | No | 507.5 | 507.5 | Miscellaneous | 2020-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | A14 IDT | 14246 | L Lynch (Plant Hire & Haulage) (1112290) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32857/Request/DOC140820-14082020094958.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32857 | REQ - Finance Team | NULL | NULL
MREQ-32857 | 32857 | 2020-08-21 08:06 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 82.6 | 82.6 | Miscellaneous | 2020-08-28 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
1 | No | 72 | 72 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32858/Request/DOC140820-14082020094958 (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
1 | No | 120 | 120 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
1 | No | 90 | 90 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
1 | No | 70 | 70 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
1 | No | 72 | 72 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
1 | No | 85 | 85 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
1 | No | 97.75 | 97.75 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
1 | No | 79.5 | 79.5 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
1 | No | 95 | 95 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
1 | No | 386 | 386 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
1 | No | 440.62 | 440.62 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14235 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32858 | REQ - Finance Team | NULL | NULL
MREQ-32858 | 32858 | 2020-08-21 10:21 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | NULL | 0 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32878 | 32878 | 2020-08-24 08:39 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 1715.2 | 1715.2 | Miscellaneous | 2020-08-24 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-32882 | 32882 | 2020-08-25 07:45 | Section 6 | Material Requisition | Not on List | Not on List | 700 | m | 69.85 | 48895 | Miscellaneous | 2020-09-04 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 301 - Fencing, Gates & Stiles | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32886 | 32886 | 2020-08-25 09:31 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No. | 341.4 | 341.4 | Miscellaneous | 2020-08-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 104 - Site Transport | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32887 | 32887 | 2020-08-25 11:23 | Section 6 | Material Requisition | Bagged | Sharp Sand Bulk Bag (938208) | 10 | Each | 34.94 | 349.4 | Aggregate | 2020-09-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32887 | 32887 | 2020-08-25 11:23 | Section 6 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 30 | Each | 3.79 | 113.7 | Aggregate | 2020-09-01 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32888 | 32888 | 2020-08-25 11:25 | Section 4 | Material Requisition | Aggregate | A20 Pipe Bed | 200 | Tonnes | 24.5 | 4900 | Aggregate | 2020-08-26 | RVP 409 - 1339625 - Bar Hill A14 Jcn 29 Westbound (B1050) | SC4B - Roadworks - Robins Lane to Dry Drayton | 501 - Drains | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-32888 | 32888 | 2020-08-25 11:25 | Section 4 | Material Requisition | Not on List | Not on List | 4 | tubs | NULL | 0 | Builders Merchants (General) | 2020-08-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Commercial Approval | Yes - Approve | NULL | REQ - Section 4 Buyers
MREQ-32892 | 32892 | 2020-08-25 14:31 | Core | Material Requisition | PPE, Small Tools and Consumables | Helmet Safety Evolite Slip Cr2 Black C/W A14 Logos (13663) | 5 | Each | 11.15 | 55.75 | PPE | 2020-08-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32892 | 32892 | 2020-08-25 14:31 | Core | Material Requisition | PPE, Small Tools and Consumables | Helmet Safety Evolite Slip Cr2 White C/W A14 Logos (13668) | 15 | Each | 11.15 | 167.25 | PPE | 2020-08-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Commercial Rejected | Yes - Approve | No - Reject | REQ - Buyers
MREQ-32893 | 32893 | 2020-08-25 15:57 | Section 6 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45 Radius 125x255 (947297) | 60 | Each | 6.45 | 387 | Blocks and Bricks | 2020-08-28 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 130 | 130 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 184.85 | 184.85 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | No | 1654.8 | 1654.8 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20041612180.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | No | 1365 | 1365 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20031910420.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
1 | No | 400.32 | 400.32 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20052716020.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
1 | No | 188.6 | 188.6 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20062914390.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | No | 905.28 | 905.28 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20070110150 (2).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
1 | No | 223.79 | 223.79 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14242 | NULL | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32894/Request/SKM_C284e20070710490.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32894 | REQ - Finance Team | NULL | NULL
MREQ-32894 | 32894 | 2020-08-25 13:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Professional Services | 2020-08-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
240 | Each | 2.48 | 595.2 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-08-27 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14245 | Keyline Builders Merchants Ltd (1100980) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32904 | REQ - Finance Team | NULL | NULL
MREQ-32906 | 32906 | 2020-08-26 13:23 | Section 4 | Material Requisition | Not on List | Not on List | 56 | No | 5.23 | 292.88 | Builders Merchants (General) | 2020-08-26 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32939 | 32939 | 2020-09-01 08:45 | Section 4 | Material Requisition | Not on List | Not on List | 8 | number | 177.53 | 1420.24 | Miscellaneous | 2020-09-02 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | BN22 - Structure BN22 | 1802 - Miscellaneous Metalwork | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32946 | 32946 | 2020-09-02 07:00 | Section 6 | Material Requisition | Not on List | Not on List | 150 | m3 | 81.3 | 12195 | Ready Mixed Concrete | 2020-09-02 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 501 - Drains | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 354.93 | 354.93 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 459.41 | 459.41 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 186.34 | 186.34 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 821.72 | 821.72 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 272.38 | 272.38 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 7219.39 | 7219.39 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 305.72 | 305.72 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 7223.39 | 7223.39 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 566.49 | 566.49 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 45.24 | 45.24 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 1276.12 | 1276.12 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 364.51 | 364.51 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 65.16 | 65.16 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 165.42 | 165.42 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 193.6 | 193.6 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 264 | 264 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32954 | 32954 | 2020-09-03 11:24 | Section 4 | Material Requisition | Not on List | Not on List | 4 | No | 2.36 | 9.44 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | NULL | 14330.34 | 14330.34 | Electrical | 2020-09-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14250 | UK Power Networks (Operations) (1284772) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ32960/Request/S6 - Electrical Wks. for Rd. Lighting-Extg.L.Column Disconnections.zip | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32960 | REQ - Finance Team | NULL | NULL
MREQ-32962 | 32962 | 2020-09-04 13:41 | Section 2 | Material Requisition | Not on List | Not on List | 9 | number | 262 | 2358 | Miscellaneous | 2020-09-13 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC2B - Roadworks - A14 | 503 - Headwalls and Outfall Works | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-32963 | 32963 | 2020-09-04 13:44 | Section 1 | Material Requisition | Not on List | Not on List | 3 | number | 262 | 786 | Miscellaneous | 2020-09-13 | Gate 1 - 1339601 - Main Compound Alconbury | SEC1 - Roadworks | 503 - Headwalls and Outfall Works | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-32964 | 32964 | 2020-09-04 13:46 | Section 3 | Material Requisition | Not on List | Not on List | 10 | number | 262 | 2620 | Miscellaneous | 2020-09-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3A - Roadworks | 503 - Headwalls and Outfall Works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-32967 | 32967 | 2020-09-04 14:14 | Section 4 | Material Requisition | Aggregate | Not on List | 500 | tonnes | 21.75 | 10875 | Builders Merchants (General) | 2020-09-04 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32979 | 32979 | 2020-09-07 08:33 | Section 4 | Material Requisition | Not on List | Not on List | 1 | number | 450 | 450 | Miscellaneous | 2020-09-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | PRLM - Preliminaries | 101 - Mob/Demob of Compounds | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
20 | Each | 3.79 | 75.8 | Builders Merchants (General) | 2020-09-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | Skyland Contractors Ltd | op 14254 | Keyline Builders Merchants Ltd (1100980) | Stores - Closed | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=32985 | REQ - Finance Team | NULL | NULL
MREQ-32985 | 32985 | 2020-09-07 08:36 | Section 6 | Material Requisition | Bagged | Sharp Sand Bulk Bag (938208) | 2 | Each | 34.94 | 69.88 | Builders Merchants (General) | 2020-09-08 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 501 - Drains | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 289.52 | 289.52 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 425.52 | 425.52 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 23.61 | 23.61 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 479.22 | 479.22 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 276.45 | 276.45 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 114.72 | 114.72 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32987 | 32987 | 2020-09-07 09:08 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 56.1 | 56.1 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-32992 | 32992 | 2020-09-07 11:51 | Section 6 | Material Requisition | Not on List | Not on List | 1 | 1 | NULL | 0 | Miscellaneous | 2020-09-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SEC6 - Huntingdon Viaduct works | 3030 - Special Ecological Measures | Operations Rejected | No - Reject | NULL | Req - S6 Buyers
MREQ-32996 | 32996 | 2020-09-07 13:39 | Section 4 | Material Requisition | Kerbs | Not on List | 5 | Units | 8.55 | 42.75 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-09-07 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-32998 | 32998 | 2020-09-07 15:21 | Section 4 | Material Requisition | Not on List | Not on List | 40 | loads | 140 | 5600 | Builders Merchants (General) | 2020-09-07 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 608 - Topsoil (place) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33000 | 33000 | 2020-09-07 16:10 | Core | Material Requisition | Waste Management | Not on List | 1 | no | 2500 | 2500 | Waste (Recycling) | 2020-09-07 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33001 | 33001 | 2020-09-07 16:00 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 224.89 | 224.89 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33005 | 33005 | 2020-09-07 20:03 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 1162.46 | 1162.46 | Office Supplies | 2020-09-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33006 | 33006 | 2020-09-07 20:08 | Core | Material Requisition | Misc | Not on List | 1 | NULL | 1199.14 | 1199.14 | Miscellaneous | 2020-09-08 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 121 - Phones / Radios / Comms | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
4 | Each | 4.67 | 18.68 | Concrete Drainage | 2020-09-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | JP Flynn Construction Ltd | 14258 | Keyline Builders Merchants Ltd (1100980) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33008 | REQ - Finance Team | NULL | NULL
MREQ-33012 | 33012 | 2020-09-08 08:43 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 4456 | 4456 | Damage Charges | 2020-09-08 | RVP 412 - 1339628 - Borrow Pit 6 J30 Eastbound | PLM4 - Site Preliminaries | 153b - Temporary Works - Waste Removal | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
25 | ltrs | 0.01 | 0.25 | Gas Oil | 2020-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 1088 | Watson Petroleum Ltd (Hall Fue (1262699) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33013 | REQ - Finance Team | NULL | NULL
25 | ltrs | 1 | 25 | Gas Oil | 2020-09-28 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 3689 | Watson Petroleum Ltd (Hall Fue (1262699) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33014 | REQ - Finance Team | NULL | NULL
MREQ-33015 | 33015 | 2020-09-08 15:10 | Core | Material Requisition | Not on List | Not on List | 3 | no. | 95 | 285 | Surveying Consumables | 2020-09-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33015 | 33015 | 2020-09-08 15:10 | Core | Material Requisition | Not on List | Not on List | 10 | no. | 2 | 20 | Surveying Consumables | 2020-09-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33015 | 33015 | 2020-09-08 15:10 | Core | Material Requisition | Not on List | Not on List | 3 | no. | 75 | 225 | Surveying Consumables | 2020-09-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33015 | 33015 | 2020-09-08 15:10 | Core | Material Requisition | Not on List | Not on List | 5 | No. | 18 | 90 | Surveying Consumables | 2020-09-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33015 | 33015 | 2020-09-08 15:10 | Core | Material Requisition | Not on List | Not on List | 3 | no. | 295 | 885 | Surveying Consumables | 2020-09-18 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 113 - Survey Equipment Costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33016 | 33016 | 2020-09-08 16:35 | Section 6 | Material Requisition | Misc | Not on List | 1 | NULL | 1000 | 1000 | Office Supplies | 2020-09-09 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 111 - Stationery / Postage | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33017 | 33017 | 2020-09-08 16:51 | Section 4 | Material Requisition | Not on List | Not on List | 56 | bags | 3.67 | 205.52 | Builders Merchants (General) | 2020-09-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153c - Temporary Works - Fencing | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33021 | 33021 | 2020-09-09 08:32 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 163.83 | 163.83 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33021 | 33021 | 2020-09-09 08:32 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 536.52 | 536.52 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33021 | 33021 | 2020-09-09 08:32 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 373.54 | 373.54 | Miscellaneous | 2020-09-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33021 | 33021 | 2020-09-09 08:32 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 65 | 65 | Miscellaneous | 2020-09-25 | 1355303 - EB5/7, A14 Eastbound, Just on Jcn 33 off Slip, Right Hand Side | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33021 | 33021 | 2020-09-09 08:32 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 4590.83 | 4590.83 | Miscellaneous | 2020-09-25 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Stores - Closed | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33025 | 33025 | 2020-09-09 09:00 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 442.7 | 442.7 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33025 | 33025 | 2020-09-09 09:00 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 445.12 | 445.12 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33025 | 33025 | 2020-09-09 09:00 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 850 | 850 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
NULL | 33025 | 2020-09-09 09:00 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 6187.5 | 6187.5 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Operational Approval | NULL | NULL | Req - S2 Buyers
MREQ-33027 | 33027 | 2020-09-09 09:59 | Section 4 | Material Requisition | Kerbs | Not on List | 40 | No. | 2.48 | 99.2 | Builders Merchants (General) | 2020-09-09 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33026 | 33026 | 2020-09-09 09:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 1142.97 | 1142.97 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33026 | 33026 | 2020-09-09 09:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 764.7 | 764.7 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33026 | 33026 | 2020-09-09 09:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 589.85 | 589.85 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33026 | 33026 | 2020-09-09 09:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 18257.14 | 18257.14 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33026 | 33026 | 2020-09-09 09:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 4945.14 | 4945.14 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33028 | 33028 | 2020-09-09 10:53 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 67.1 | 67.1 | Miscellaneous | 2020-09-25 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No | 4027.24 | 4027.24 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14268 | Gap Group Ltd (1108091) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33029/Request/Fwd claim _254843 2855PH33105040331 COSTAIN SKANSKA-F586337-120 ROLLER- 3194189.msg | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33029 | REQ - Finance Team | NULL | NULL
MREQ-33029 | 33029 | 2020-09-09 14:23 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 3357.6 | 3357.6 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33029 | 33029 | 2020-09-09 14:23 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 2016.43 | 2016.43 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
26 | each | 58.04 | 1509.04 | Miscellaneous | 2020-09-10 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | Skyland Contractors Ltd | 14281 | Keyline Builders Merchants Ltd (1100980) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33032 | REQ - Finance Team | NULL | NULL
MREQ-33037 | 33037 | 2020-09-10 09:33 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 770 | 770 | Miscellaneous | 2020-09-10 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33038 | 33038 | 2020-09-10 09:51 | Section 6 | Material Requisition | Not on List | Not on List | 1500 | NULL | 0.45 | 675 | Office Supplies | 2020-09-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | IMO - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33045 | 33045 | 2020-09-11 07:04 | Section 6 | Material Requisition | Bagged | OP Cement Multicem Plastic Bag 25kg (210768) | 56 | Each | 3.79 | 212.24 | Aggregate | 2020-09-14 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33045 | 33045 | 2020-09-11 07:04 | Section 6 | Material Requisition | Bagged | Kiln Dried Sand 25kg (518674) | 20 | Each | 2.31 | 46.2 | Aggregate | 2020-09-14 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
2 | No. | 120 | 240 | Miscellaneous | 2020-09-14 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | IMO - Closed | Yes - Approve | Yes - Approve | Yes | Thermometer Point | /sites/BPM/FlowForma/FormDocuments/MREQ33062/IMO-P-Card-Purchase/MREQ33062 -Invoice SI-131194_2020-09-17_17-30-29.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33062 | REQ - Finance Team | NULL | NULL
MREQ-33064 | 33064 | 2020-09-14 15:48 | Section 4 | Material Requisition | Kerbs | Not on List | 20 | No, | 4.42 | 88.4 | Builders Merchants (General) | 2020-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33065 | 33065 | 2020-09-14 15:56 | Section 4 | Material Requisition | Not on List | Not on List | 36 | Number | 8.25 | 297 | Blocks and Bricks | 2020-09-14 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-0033071 | 33071 | 2020-09-15 10:57 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | No - Pass Back | NULL | REQ - Buyers
MREQ-0033071 | 33071 | 2020-09-15 10:57 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 253 | 253 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Operational Approval | No - Pass Back | NULL | REQ - Buyers
MREQ-33072 | 33072 | 2020-09-15 11:22 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 3830 | 3830 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33072 | 33072 | 2020-09-15 11:22 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 5136.32 | 5136.32 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33072 | 33072 | 2020-09-15 11:22 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 2184.9 | 2184.9 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33072 | 33072 | 2020-09-15 11:22 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 19617.83 | 19617.83 | Miscellaneous | 2020-09-15 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33073 | 33073 | 2020-09-15 12:18 | Section 6 | Material Requisition | Combined Drainage | Not on List | 4 | No | 42.74 | 170.96 | Concrete Drainage | 2020-09-18 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No | 177.6 | 177.6 | Miscellaneous | 2020-09-16 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | A14 IDT | NULL | NULL | Operational Approval | No - Pass Back | NULL | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33080/Request/DOC120820-12082020081706.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33080 | REQ - Finance Team | NULL | NULL
MREQ-33081 | 33081 | 2020-09-15 15:44 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 212.45 | 212.45 | Miscellaneous | 2020-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Passed Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-33081 | 33081 | 2020-09-15 15:44 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 395 | 395 | Miscellaneous | 2020-09-18 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Operations Passed Back | No - Pass Back | NULL | Req - S5 Buyers
MREQ-33089 | 33089 | 2020-09-17 07:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 528 | 528 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33089 | 33089 | 2020-09-17 07:52 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 85 | 85 | Miscellaneous | 2020-09-25 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33090 | 33090 | 2020-09-17 08:18 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 72 | 72 | Miscellaneous | 2020-09-25 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33091 | 33091 | 2020-09-17 11:06 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 19237.98 | 19237.98 | Miscellaneous | 2020-09-18 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | FEEC - Preliminaries | 107 - Fee based costs including insurance | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33092 | 33092 | 2020-09-17 11:18 | Section 6 | Material Requisition | Not on List | Not on List | 1 | NULL | 31317.8 | 31317.8 | Miscellaneous | 2020-09-18 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | FEE6 - Fee Based Costs inc. insurance | 107 - Insurance | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | NULL | 52.36 | 52.36 | Small Tools (Consumables) | 2020-09-21 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | op 14290 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33106 | REQ - Finance Team | NULL | NULL
MREQ-33120 | 33120 | 2020-09-21 09:53 | Section 6 | Material Requisition | Kerbs | Concrete Flat Top Edging 50x150x915 (805282) | 520 | Each | 2.48 | 1289.6 | Blocks and Bricks | 2020-09-22 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33123 | 33123 | 2020-09-22 07:10 | Section 6 | Material Requisition | Bagged | Sharp Sand Bulk Bag (938208) | 8 | Each | 34.94 | 279.52 | Aggregate | 2020-09-23 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33124 | 33124 | 2020-09-22 08:28 | Section 4 | Material Requisition | Concrete Drainage | Not on List | 3 | No. | 25.17 | 75.51 | Concrete Drainage | 2020-09-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2701 - Accommodation works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33124 | 33124 | 2020-09-22 08:28 | Section 4 | Material Requisition | Concrete Drainage | Not on List | 5 | No. | 100.77 | 503.85 | Concrete Drainage | 2020-09-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 2701 - Accommodation works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33125 | 33125 | 2020-09-22 08:45 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs Splayed 45deg 125x255 (898227) | 16 | No. | 6.34 | 101.44 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-09-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33125 | 33125 | 2020-09-22 08:45 | Section 4 | Material Requisition | Misc | Not on List | 3 | No. | 30.26 | 90.78 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-09-22 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33161 | 33161 | 2020-09-28 07:59 | Core | Material Requisition | Misc | Not on List | 1 | No. | 1200 | 1200 | Professional Services | 2020-09-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 116 - Copying Charges | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33162 | 33162 | 2020-09-28 09:36 | Section 3 | Material Requisition | Aggregate | Not on List | 100 | TM | 34.25 | 3425 | Aggregate | 2020-10-08 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | SC3B - Roadworks | 503 - Headwalls and Outfall Works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
1 | NULL | NULL | 0 | Damage Charges | 2020-09-28 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | 14299 | T & M Plant Hire Ltd (1134413) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33163/Request/BRWA86BAD89A65C_021226.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33163 | REQ - Finance Team | NULL | NULL
1 | NULL | 795.06 | 795.06 | Surveying Consumables | 2020-09-28 | Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ (Core) | A14 IDT | 14306 | Korec (1114049) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33171/Request/hun052648 merged.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33171 | REQ - Finance Team | NULL | NULL
MREQ-33174 | 33174 | 2020-09-28 13:20 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 688 | no | 5.52 | 3797.76 | Blocks and Bricks | 2020-09-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33176 | 33176 | 2020-09-28 16:32 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop L/H (898584) | 10 | Each | 8.08 | 80.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-09-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33176 | 33176 | 2020-09-28 16:32 | Section 4 | Material Requisition | Kerbs | Concrete Kerbs 125x255 - 125x150 HB - BN Drop R/H (897467) | 10 | Each | 8.08 | 80.8 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-09-28 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33177 | 33177 | 2020-09-28 16:52 | Section 6 | Material Requisition | Bagged | Sharp Sand Bulk Bag (938208) | 12 | Each | 34.94 | 419.28 | Builders Merchants (General) | 2020-09-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33177 | 33177 | 2020-09-28 16:52 | Section 6 | Material Requisition | Bricks/Blocks | Not on List | 250 | m2 | 34.59 | 8647.5 | Builders Merchants (General) | 2020-09-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | SC6R - Roadworks Section 6 | 1104 - Footways and Paved Areas | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33178 | 33178 | 2020-09-28 17:05 | Section 6 | Material Requisition | Aggregate | Not on List | 300 | m3 | 77.33 | 23199 | Aggregate | 2020-09-30 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33184 | 33184 | 2020-09-29 08:25 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 6187.5 | 6187.5 | Miscellaneous | 2020-09-30 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
8 | ea | 58.87 | 470.96 | Flow Control | 2020-09-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | Skyland Contractors Ltd | 14311 | Keyline Builders Merchants Ltd (1100980) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33186 | REQ - Finance Team | NULL | NULL
MREQ-33198 | 33198 | 2020-09-30 12:37 | Core | Material Requisition | Not on List | Not on List | 1 | No | 345 | 345 | Miscellaneous | 2020-09-30 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 111 - Stationery /Postage | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33200 | 33200 | 2020-09-30 16:48 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 80 | 80 | Miscellaneous | 2020-09-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 115 - Medical / 1st Aid | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No | 310.31 | 310.31 | Miscellaneous | 2020-09-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14309 | UK Power Networks (Operations) (1284772) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33202 | REQ - Finance Team | NULL | NULL
MREQ-33212 | 33212 | 2020-10-01 15:13 | Section 4 | Material Requisition | Kerbs | Not on List | 3 | Tubs | 49 | 147 | Builders Merchants (General) | 2020-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33212 | 33212 | 2020-10-01 15:13 | Section 4 | Material Requisition | Not on List | Not on List | 40 | bags | 3.67 | 146.8 | Builders Merchants (General) | 2020-10-01 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | CL4A - Structures (Culverts) 4A | 1701 - Insitu Concrete | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33217 | 33217 | 2020-10-02 12:54 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 365 | 365 | Miscellaneous | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33217 | 33217 | 2020-10-02 12:54 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 135 | 135 | Miscellaneous | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33217 | 33217 | 2020-10-02 12:54 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 173.19 | 173.19 | Miscellaneous | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33217 | 33217 | 2020-10-02 12:54 | Section 5 | Material Requisition | Not on List | Not on List | 1 | No | 230 | 230 | Miscellaneous | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33220 | 33220 | 2020-10-02 15:44 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 19304 | 19304 | Builders Merchants (General) | 2020-10-02 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | PRLM - Preliminaries | 154 - Traffic Management & Safety | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33221 | 33221 | 2020-10-02 15:34 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33221 | 33221 | 2020-10-02 15:34 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 1365 | 1365 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33221 | 33221 | 2020-10-02 15:34 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 120 | 120 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33232 | 33232 | 2020-10-05 15:39 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1193.8 | 1193.8 | Miscellaneous | 2020-10-05 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | WAOC - Working Areas overhead Costs | 123 - Venue / Meeting Costs (Hotel Conf etc) | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33233 | 33233 | 2020-10-05 15:56 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 88 | 88 | Miscellaneous | 2020-10-30 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-33233 | 33233 | 2020-10-05 15:56 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 138 | 138 | Miscellaneous | 2020-10-30 | Gate D - 1350303 - Batching Plant, Ermine St. A1198 Rd, PE29 2NH | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-33234 | 33234 | 2020-10-05 16:12 | Section 2 | Material Requisition | Not on List | Not on List | 1 | No | 350 | 350 | Miscellaneous | 2020-10-30 | Gate 3 - 1339618 - BN05/06 Buckden Rd Brampton PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33244 | 33244 | 2020-10-07 09:35 | Section 5 | Material Requisition | Not on List | Not on List | 5 | No | 119.44 | 597.2 | Miscellaneous | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 153e - Temporary Works - Temporary piling & Cofferdams | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33245 | 33245 | 2020-10-07 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 43 | 43 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33245 | 33245 | 2020-10-07 09:42 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 288 | 288 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 30.429 | M3 | 10.52 | 320.11 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 1 | No | 6 | 6 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 13.609 | M3 | 10.52 | 143.17 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 1 | No | 6 | 6 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 4.157 | M3 | 10.52 | 43.73 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33248 | 33248 | 2020-10-07 14:22 | Section 4 | Material Requisition | Waste Management | Not on List | 1 | No | 6 | 6 | Waste (General) | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33249 | 33249 | 2020-10-07 15:42 | Section 5 | Material Requisition | Waste Management | Not on List | 5.372 | M3 | 10.52 | 56.51 | Waste (General) | 2020-10-30 | 1358003 - Main Compound, Gate 1 - 1344810 - Cambridge Rd, Milton, Cambridge, CB24 6AZ | PLM5 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S5 Buyers
MREQ-33250 | 33250 | 2020-10-07 16:05 | Section 2 | Material Requisition | Waste Management | Not on List | 1 | No | 950 | 950 | Waste (General) | 2020-10-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33250 | 33250 | 2020-10-07 16:05 | Section 2 | Material Requisition | Waste Management | Not on List | 1 | No | 950 | 950 | Waste (General) | 2020-10-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 102 - Compound running costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33255 | 33255 | 2020-10-08 11:12 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-10-08 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | IMO Queue | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33267 | 33267 | 2020-10-09 10:06 | Section 6 | Material Requisition | Aggregate | Not on List | 8 | M3 | 80.6 | 644.8 | Aggregate | 2020-10-09 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 1101 - Kerbs, Channels and Edgings | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No | 537.54 | 537.54 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157474(Previously Sent) (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
2 | No | 0 | 0 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157472(Previously Sent).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
1 | No | 50.15 | 50.15 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157458 (Previously Sent).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
1 | No | 15.17 | 15.17 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157458 (Previously Sent) (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
1 | No | 83.2 | 83.2 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157458 (Previously Sent) (2).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
1 | No | 15.17 | 15.17 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157458 (Previously Sent) (3).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
1 | No | 87.75 | 87.75 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157458 (Previously Sent) (4).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
1 | No | 42.8 | 42.8 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157470(Previously Sent).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
1 | No | 127.47 | 127.47 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14334 | Marwood Group Ltd (1101768) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33272/Request/LossDamage Advice Note 03157470(Previously Sent) (1).pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33272 | REQ - Finance Team | NULL | NULL
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List | 4 | No | 724.14 | 2896.56 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 525.1 | 525.1 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33272 | 33272 | 2020-10-09 14:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | N0 | 708.71 | 708.71 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153f - Tempoary Works - Miscellaneous temporary works | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33280 | 33280 | 2020-10-12 07:48 | Section 6 | Material Requisition | Aggregate | Type 1 | 220 | Tonnes | 21.65 | 4763 | Aggregate | 2020-10-13 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | SC6R - Roadworks Section 6 | 701 - Sub-base | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No | 38.87 | 38.87 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33282/Request/BRW12R2SRV001_BRW_Office_WHL06494_4230_001.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
1 | No | 332.27 | 332.27 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
1 | No | 357.81 | 357.81 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
1 | No | 367.49 | 367.49 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
1 | No | 712.72 | 712.72 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
1 | No | 113.3 | 113.3 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
1 | No | 82.8 | 82.8 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14338 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33282 | REQ - Finance Team | NULL | NULL
NULL | 33285 | 2020-10-12 16:03 | Core | Material Requisition | Not on List | Not on List | 1 | NULL | 1229.69 | 1229.69 | Miscellaneous | 2020-10-12 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 109 - PPE Costs | Operational Approval | NULL | NULL | REQ - Buyers
MREQ-33286 | 33286 | 2020-10-12 16:11 | Section 4 | Material Requisition | Not on List | Not on List | 1 | Lot | 72228.16 | 72228.16 | Electrical | 2020-10-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound (Core) | SC4B - Roadworks - Robins Lane to Dry Drayton | 1504 - Technology Equipment | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
NULL | 33288 | 2020-10-13 07:53 | Section 4 | Material Requisition | Not on List | Not on List | 56 | number | NULL | 0 | Builders Merchants (General) | 2020-10-13 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4B - Roadworks - Robins Lane to Dry Drayton | 1101 - Kerbs, Channels and Edgings | Operational Approval | NULL | NULL | REQ - Section 4 Buyers
MREQ-33289 | 33289 | 2020-10-13 08:46 | Core | Material Requisition | Not on List | Not on List | 1 | ea | 426.97 | 426.97 | Office Supplies | 2020-10-15 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton (Core) | WAOC - Working Areas overhead Costs | 117 - Computer & Acc Charges | IMO - Closed | Yes - Approve | Yes - Approve | REQ - Buyers
MREQ-33293 | 33293 | 2020-10-13 10:09 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 490 | 490 | Professional Services | 2020-10-13 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 115 - Medical / 1st Aid | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33294 | 33294 | 2020-10-13 10:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 184.17 | 184.17 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33294 | 33294 | 2020-10-13 10:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 187.2 | 187.2 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33294 | 33294 | 2020-10-13 10:47 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 750 | 750 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33295 | 33295 | 2020-10-13 12:01 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 456 | 456 | Miscellaneous | 2020-10-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33295 | 33295 | 2020-10-13 12:01 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 234 | 234 | Miscellaneous | 2020-10-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33295 | 33295 | 2020-10-13 12:01 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No | 137 | 137 | Miscellaneous | 2020-10-30 | S6MC – Mill Common - 1351842 - Mill Common Road Huntingdon PE29 3AR | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
1 | No | 66.7 | 66.7 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33306/Request/20201008135452445.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 38.26 | 38.26 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 58.44 | 58.44 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 34.45 | 34.45 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 5.68 | 5.68 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 98.02 | 98.02 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead PlantHire CoLtd t/a Ev (1315401) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 102.7 | 102.7 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 184.56 | 184.56 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 177.03 | 177.03 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 96.39 | 96.39 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 683.02 | 683.02 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
1 | No | 372.22 | 372.22 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | A14 IDT | 14345 | Ashtead Plant Hire Company Ltd (1109463) | Closed - Buyers | Yes - Approve | Yes - Approve | NULL | NULL | NULL | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33306 | REQ - Finance Team | NULL | NULL
MREQ-33311 | 33311 | 2020-10-14 19:17 | Section 6 | Material Requisition | Not on List | Not on List | 1 | as per attached quotation | 679.11 | 679.11 | Miscellaneous | 2020-10-18 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 154 - Traffic Management and Safety | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33312 | 33312 | 2020-10-14 20:15 | Section 6 | Material Requisition | Bagged | Not on List | 56 | bags | 6.75 | 378 | Builders Merchants (General) | 2020-10-16 | S6VL – Views Common - 1351843 - Link Hinchingbrooke Park Rd Huntingdon PE29 6NB | PLM6 - Site Preliminaries | 153c - Temporary Works - Roads | Stores - Closed | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33317 | 33317 | 2020-10-15 12:53 | Section 4 | Material Requisition | Not on List | Not on List | 994 | 1 | 1.33 | 1322.02 | Ductile Drainage | 2020-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4C - Roadworks - Dry Drayton to Girton | 1401 - Trenches, Ducts and Chambers | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33317 | 33317 | 2020-10-15 12:53 | Section 4 | Material Requisition | Kerbs | Not on List | 48 | 1 | 6.34 | 304.32 | Concrete Hard Landscaping (Kerbs, Slabs) | 2020-10-16 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | SC4A - Roadworks - Swavesey to Robins Lane | 1101 - Kerbs, Channels and Edgings | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33322 | 33322 | 2020-10-15 16:08 | Section 6 | Material Requisition | Not on List | Not on List | 1 | No. | 425 | 425 | Miscellaneous | 2020-10-15 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | WAO6 - Working Area Overhead | 110 - Welfare Costs | Closed - Buyers | Yes - Approve | Yes - Approve | Req - S6 Buyers
MREQ-33323 | 33323 | 2020-10-16 09:15 | Section 4 | Material Requisition | PPE, Small Tools and Consumables | Boot Magnum Sitemaster Comp Toe/Plate M801232 Black (195306) | 1 | Each | 62.53 | 62.53 | PPE | 2020-10-16 | RVP 401A - 1339583 -Swavesey South Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 103 - Staff | Stores - Closed | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33336 | 33336 | 2020-10-19 08:35 | Section 4 | Material Requisition | Not on List | Not on List | 1 | No | 182.67 | 182.67 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyers Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33336 | 33336 | 2020-10-19 08:35 | Section 4 | Material Requisition | Not on List | Not on List | 40 | No | 12.21 | 488.4 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyers Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33336 | 33336 | 2020-10-19 08:35 | Section 4 | Material Requisition | Not on List | Not on List | 40 | No | 28.81 | 1152.4 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyers Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
MREQ-33336 | 33336 | 2020-10-19 08:35 | Section 4 | Material Requisition | Not on List | Not on List | 38 | No | 143.87 | 5467.06 | Miscellaneous | 2020-10-30 | Main Compound RVP 401 - 1333676 - Swavesey Main Compound A14 J28 Westbound | PLM4 - Site Preliminaries | 153d - Temporary Works - Scaffolding & Falsework | Buyers Queue | Yes - Approve | Yes - Approve | REQ - Section 4 Buyers
1 | No | 132.83 | 132.83 | Miscellaneous | 2020-10-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | A14 IDT | NULL | NULL | Buyers Queue | Yes - Approve | Yes - Approve | NULL | NULL | /sites/BPM/FlowForma/FormDocuments/MREQ33338/Request/20201008135452445.pdf | https://costaingroup-b9a8a868df8007.sharepoint.com/sites/ff/FlowForma/Lists/Forms/DispForm.aspx?ID=33338 | REQ - Finance Team | NULL | NULL
MREQ-33339 | 33339 | 2020-10-19 11:42 | Section 3 | Material Requisition | Not on List | Not on List | 1 | No | 278.41 | 278.41 | Miscellaneous | 2020-10-30 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM3 - Site Preliminaries | 152 - Attendant / General Plant | Buyers Queue | Yes - Approve | Yes - Approve | REQ - Section 3 Buyers
MREQ-33340 | 33340 | 2020-10-19 12:04 | Section 1 | Material Requisition | Not on List | Not on List | 1 | No | 114 | 114 | Miscellaneous | 2020-10-30 | Gate 1 - 1339601 - Main Compound Alconbury | PLM1 - Site Preliminaries | 152 - Attendant / General Plant | Buyers Queue | Yes - Approve | Yes - Approve | Req - S1 Buyers
MREQ-33345 | 33345 | 2020-10-20 07:42 | Section 2 | Material Requisition | PPE, Small Tools and Consumables | Not on List | 1 | NULL | NULL | 0 | Damage Charges | 2020-10-23 | Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM2 - Site Preliminaries | 152 - Attendant / General Plant | Buyers Queue | Yes - Approve | Yes - Approve | Req - S2 Buyers
MREQ-33349 | 33349 | 2020-10-20 09:13 | Section 6 | Material Requisition | Not on List | Not on List | 1 | NULL | NULL | 0 | Miscellaneous | 2020-10-20 | Section 2 Main Compound - 1339608 - Buckden Rd PE19 5UH Brampton | PLM6 - Site Preliminaries | 152 - Attendant / General Plant | Buyers Queue | Yes - Approve | Yes - Approve | Req - S6 Buyers